## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PASCHIM MEDINIPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PASCHIM MEDINIPUR | SM/19051 | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | TSM/018890 | 40049053 | Augmentation | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 2324.71 | 152.02 | 2476.73 | Midnapore Division | Midnapore Mechanical Division | 15.4 | 0.67 | 0 | 0 | 16.07 | 15.4 | 0.67 | 0 | 0 | 16.07 | 0.65 | 5
2 | PASCHIM MEDINIPUR | SM/14485 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017389 | 40062013 | Augmentation | MVS | GO2223012340PH | 20/01/2023 | 0 | 54.66 | 54.66 |  | Midnapore Mechanical Division | 0 | 0.19 | 0 | 0 | 0.19 | 0 | 0.19 | 0 | 0 | 0.19 | 0.35 | 10
3 | PASCHIM MEDINIPUR | SM/17184 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT PIRAKATA AND OTHER 35 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017386 | 40060316 | Augmentation | MVS | GO2223016356PH | 15/03/2023 | 0 | 72.89 | 72.89 |  | Midnapore Mechanical Division | 0 | 30.32 | 0 | 0 | 30.32 | 0 | 30.32 | 0 | 0 | 30.32 | 41.6 | 30
4 | PASCHIM MEDINIPUR | SM/16296 | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | TSM/011588 | 40036864 | Augmentation | SVS | GO2223014877PH | 24/02/2023 | 246.76 | 26.57 | 273.33 | Midnapore Division | Midnapore Mechanical Division | 8.54 | 10.93 | 19.28 | 0 | 38.76 | 8.54 | 10.93 | 19.28 | 0 | 38.76 | 14.18 | 15
5 | PASCHIM MEDINIPUR | SM/19050 | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/018326 | 40046984 | Augmentation | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1133.21 | 83.98 | 1217.19 | Midnapore Division | Midnapore Mechanical Division | 232.35 | 35.22 | 0 | 0 | 267.58 | 232.35 | 24.96 | 0 | 0 | 257.31 | 21.14 | 7
6 | PASCHIM MEDINIPUR | SM/13709 | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015080 | 40060041 | Augmentation | MVS | GO2223009712PH | 14/11/2022 | 213.06 | 26.57 | 239.63 | Midnapore Division | Midnapore Mechanical Division | 42.98 | 10.42 | 4.96 | 0 | 58.36 | 42.98 | 10.42 | 4.96 | 0 | 58.36 | 24.35 | 17
7 | PASCHIM MEDINIPUR | SM/19037 | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | TSM/020218 | 40067334 | Augmentation | MVS | 3416/PHE-28011/253/2023-SCHM CELL-Dept. of PHE | 08/11/2023 | 1672.77 | 91.92 | 1764.69 | Midnapore Division | Midnapore Mechanical Division | 153.68 | 53.1 | 0 | 0 | 206.78 | 153.68 | 33.55 | 0 | 0 | 187.23 | 10.61 | 6
8 | PASCHIM MEDINIPUR | SM/17946 | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | TSM/016253 | 40049997 | Augmentation | MVS | GO2223016955PH | 17/03/2023 | 524.86 | 55.99 | 580.85 | Midnapore Division | Midnapore Mechanical Division | 5.83 | 10.57 | 1.37 | 0 | 17.77 | 5.83 | 10.57 | 1.37 | 0 | 17.77 | 3.06 | 11
9 | PASCHIM MEDINIPUR | SM/14478 | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014762 | 40060052 | Augmentation | MVS | GO2223012310PH | 20/01/2023 | 660.95 | 26.57 | 687.52 | Midnapore Division | Midnapore Mechanical Division | 340.95 | 16.19 | 3.33 | 0 | 360.47 | 340.95 | 16.19 | 3.33 | 0 | 360.47 | 52.43 | 87
10 | PASCHIM MEDINIPUR | SM/14479 | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014863 | 40050218 | Augmentation | MVS | GO2223012307PH | 20/01/2023 | 501.96 | 26.57 | 528.53 | Midnapore Division | Midnapore Mechanical Division | 291.04 | 10.29 | 0 | 0 | 301.33 | 291.04 | 10.29 | 0 | 0 | 301.33 | 57.01 | 13
11 | PASCHIM MEDINIPUR | SM/13123 | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014553 | 40050133 | Augmentation | MVS | GO2223008538PH | 10/10/2022 | 455.86 | 26.57 | 482.44 | Midnapore Division | Midnapore Mechanical Division | 144.65 | 14.74 | 27.96 | 0 | 187.35 | 144.65 | 14.74 | 27.96 | 0 | 187.35 | 38.83 | 23
12 | PASCHIM MEDINIPUR | SM/15092 | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | TSM/018413 | 40036927 | Augmentation | MVS | GO2223013188PH | 04/02/2023 | 403.83 | 55.99 | 459.82 | Midnapore Division | Midnapore Mechanical Division | 100.02 | 24.94 | 3.24 | 0 | 128.2 | 100.02 | 24.94 | 3.24 | 0 | 128.2 | 27.88 | 56
13 | PASCHIM MEDINIPUR | SM/14480 | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015518 | 40050541 | Augmentation | MVS | GO2223012304PH | 20/01/2023 | 184.53 | 26.57 | 211.1 | Midnapore Division | Midnapore Mechanical Division | 78.57 | 13.1 | 5.62 | 0 | 97.29 | 78.57 | 13.09 | 5.62 | 0 | 97.29 | 46.09 | 14
14 | PASCHIM MEDINIPUR | SM/14481 | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015211 | 40050225 | Augmentation | MVS | GO2223012305PH | 20/01/2023 | 457.95 | 26.57 | 484.52 | Midnapore Division | Midnapore Mechanical Division | 237.39 | 13.51 | 0 | 0 | 250.91 | 237.39 | 7.28 | 0 | 0 | 244.67 | 50.5 | 73
15 | PASCHIM MEDINIPUR | SM/17949 | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | TSM/015745 | 40035897 | Augmentation | MVS | GO2223016948PH | 17/03/2023 | 454.37 | 27.99 | 482.36 | Midnapore Division | Midnapore Mechanical Division | 97.75 | 13.49 | 0 | 0 | 111.24 | 97.75 | 13.49 | 0 | 0 | 111.24 | 23.06 | 76
16 | PASCHIM MEDINIPUR | SM/18191 | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/016116 | 40048821 | Augmentation | SVS | GO2223018090PH | 30/03/2023 | 232.29 | 55.99 | 288.28 | Midnapore Division | Midnapore Mechanical Division | 48.63 | 15.72 | 2.26 | 0 | 66.62 | 48.63 | 15.72 | 2.26 | 0 | 66.62 | 23.11 | 17
17 | PASCHIM MEDINIPUR | SM/09923 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | TSM/008491 | 40006991 | Augmentation | MVS | GO2122006611PH | 10/12/2021 | 961.18 | 84.47 | 1045.66 | Midnapore Division | Jhargram Mechanical Division | 374.56 | 0 | 63.43 | 0 | 437.99 | 374.56 | 0 | 63.43 | 0 | 437.99 | 41.89 | 32
18 | PASCHIM MEDINIPUR | SM/15570 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018343 | 40063829 | Augmentation | MVS | GO2223013904PH | 15/02/2023 | 299.77 | 84.47 | 384.24 | Midnapore Division | Midnapore Mechanical Division | 42.94 | 27.94 | 1.95 | 0 | 72.83 | 42.94 | 27.94 | 1.95 | 0 | 72.83 | 18.95 | 100
19 | PASCHIM MEDINIPUR | SM/15572 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018349 | 6372746 | Augmentation | MVS | GO2223013890PH | 15/02/2023 | 264.37 | 84.47 | 348.84 | Midnapore Division | Midnapore Mechanical Division | 4.2 | 21.34 | 1.72 | 0 | 27.26 | 4.2 | 21.34 | 1.72 | 0 | 27.26 | 7.81 | 100
20 | PASCHIM MEDINIPUR | SM/15574 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018342 | 40046946 | Augmentation | MVS | GO2223013892PH | 15/02/2023 | 391.54 | 42.24 | 433.78 | Midnapore Division | Midnapore Mechanical Division | 1.11 | 17.37 | 20.42 | 0 | 38.9 | 1.11 | 17.37 | 20.42 | 0 | 38.9 | 8.97 | 76
21 | PASCHIM MEDINIPUR | SM/11898 | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008557 | 40020403 | Augmentation | MVS | GO2223006587PH | 22/08/2022 | 1518.36 | 84.47 | 1602.83 | Midnapore Division | Midnapore Mechanical Division | 257.44 | 21.52 | 74.13 | 0 | 353.1 | 257.44 | 21.52 | 74.13 | 0 | 353.1 | 22.03 | 12
22 | PASCHIM MEDINIPUR | SM/13823 | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008549 | 40036745 | Augmentation | SVS | GO2223010041PH | 25/11/2022 | 167.91 | 42.24 | 210.14 | Midnapore Division | Midnapore Mechanical Division | 99.95 | 10.39 | 4.43 | 0 | 114.77 | 99.95 | 10.39 | 4.43 | 0 | 114.77 | 54.62 | 72
23 | PASCHIM MEDINIPUR | SM/13826 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008494 | 40036645 | Augmentation | SVS | GO2223010042PH | 25/11/2022 | 239.12 | 42.24 | 281.35 | Midnapore Division | Midnapore Mechanical Division | 140.64 | 13.76 | 0 | 0 | 154.4 | 140.64 | 13.76 | 0 | 0 | 154.4 | 54.88 | 20
24 | PASCHIM MEDINIPUR | SM/10091 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | TSM/008500 | 40007184 | Augmentation | MVS | GO2122009010PH | 01/02/2022 | 1645.45 | 126.71 | 1772.16 | Midnapore Division | Jhargram Mechanical Division | 562.7 | 15.55 | 104.44 | 0 | 682.7 | 561.97 | 15.55 | 104.44 | 0 | 681.96 | 38.48 | 51
25 | PASCHIM MEDINIPUR | SM/11880 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012022 | 40018795 | Augmentation | MVS | GO2223006437PH | 17/08/2022 | 345.75 | 42.24 | 387.99 | Midnapore Division | Midnapore Mechanical Division | 90.1 | 28.14 | 20.31 | 0 | 138.55 | 90.1 | 28.14 | 20.31 | 0 | 138.55 | 35.71 | 74
26 | PASCHIM MEDINIPUR | SM/10000 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008553 | 40003855 | Augmentation | MVS | GO2122007049PH | 20/12/2021 | 1671.1 | 168.95 | 1840.05 | Midnapore Division | Midnapore Mechanical Division | 745.49 | 16.74 | 206.44 | 0 | 968.67 | 745.49 | 16.74 | 206.44 | 0 | 968.67 | 52.64 | 10
27 | PASCHIM MEDINIPUR | SM/18506 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/009166 | 40050725 | Augmentation | MVS | 2040/PHE-28011/17/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1284.16 | 126.71 | 1410.87 | Midnapore Division | Midnapore Mechanical Division | 479.31 | 37.84 | 0 | 0 | 517.15 | 479.31 | 37.84 | 0 | 0 | 517.15 | 36.65 | 4
28 | PASCHIM MEDINIPUR | SM/09430 | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. | TSM/008554 | 40027210 | Augmentation | MVS | GO2122005501PH | 17/11/2021 | 997.1 | 0 | 997.1 | Midnapore Division | Midnapore Mechanical Division | 611.05 | 0 | 76.32 | 0 | 687.37 | 611.05 | 0 | 76.32 | 0 | 687.37 | 68.94 | 10
29 | PASCHIM MEDINIPUR | SM/17395 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018218 | 40059683 | Augmentation | MVS | GO2223016349PH | 15/03/2023 | 162.04 | 0 | 162.04 | Midnapore Division |  | 3.25 | 0 | 0.43 | 0 | 3.69 | 1.23 | 0 | 0.43 | 0 | 1.66 | 1.03 | 100
30 | PASCHIM MEDINIPUR | SM/15576 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018213 | 40047109 | Augmentation | MVS | GO2223013891PH | 15/02/2023 | 412.64 | 0 | 412.64 | Midnapore Division |  | 0 | 0 | 1.63 | 0 | 1.63 | 0 | 0 | 1.63 | 0 | 1.63 | 0.39 | 100
31 | PASCHIM MEDINIPUR | SM/09933 | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | TSM/008584 | 40006982 | Augmentation | MVS | GO2122006699PH | 13/12/2021 | 810.35 | 92.2 | 902.55 | Midnapore Division | Jhargram Mechanical Division | 386.74 | 35.3 | 110.73 | 0 | 532.77 | 386.74 | 35.3 | 110.73 | 0 | 532.77 | 59.03 | 24
32 | PASCHIM MEDINIPUR | SM/12825 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012018 | 40024553 | Augmentation | MVS | GO2223008117PH | 22/09/2022 | 329.84 | 84.47 | 414.31 | Midnapore Division | Midnapore Mechanical Division | 78.14 | 18.01 | 0 | 0 | 96.15 | 78.14 | 18.01 | 0 | 0 | 96.15 | 23.21 | 77
33 | PASCHIM MEDINIPUR | SM/13822 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | TSM/008555 | 40036736 | Augmentation | SVS | GO2223010040PH | 25/11/2022 | 354.83 | 84.74 | 439.58 | Midnapore Division | Midnapore Mechanical Division | 68.8 | 20.37 | 0 | 0 | 89.17 | 68.8 | 20.37 | 0 | 0 | 89.17 | 20.29 | 5
34 | PASCHIM MEDINIPUR | SM/17396 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018341 | 40059482 | Augmentation | SVS | GO2223016348PH | 15/03/2023 | 169.98 | 84.47 | 254.45 | Midnapore Division | Midnapore Mechanical Division | 0.81 | 13.95 | 0.2 | 0 | 14.96 | 0.81 | 13.95 | 0.2 | 0 | 14.96 | 5.88 | 15
35 | PASCHIM MEDINIPUR | SM/10124 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | TSM/008498 | 40010379 | Augmentation | MVS | GO2122009286PH | 08/02/2022 | 880.97 | 168.95 | 1049.92 | Midnapore Division | Midnapore Mechanical Division | 487.89 | 37.01 | 55.56 | 0 | 580.46 | 487.89 | 37.01 | 55.56 | 0 | 580.46 | 55.29 | 56
36 | PASCHIM MEDINIPUR | SM/09979 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | TSM/008559 | 40007023 | Augmentation | MVS | GO2122006878PH | 16/12/2021 | 853.12 | 168.95 | 1022.06 | Midnapore Division | Midnapore Mechanical Division | 637.02 | 26.65 | 23.69 | 0 | 687.37 | 637.02 | 26.65 | 23.69 | 0 | 687.37 | 67.25 | 68
37 | PASCHIM MEDINIPUR | SM/09431 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | TSM/008552 | 40018306 | Augmentation | MVS | GO2122005500PH | 17/11/2021 | 589.71 | 0 | 589.71 | Midnapore Division |  | 313.22 | 0 | 19.67 | 0 | 332.89 | 313.22 | 0 | 19.67 | 0 | 332.89 | 56.45 | 76
38 | PASCHIM MEDINIPUR | SM/09432 | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. | TSM/008485 | 40027245 | Augmentation | MVS | GO2122005500PH | 17/11/2021 | 323.02 | 0 | 323.02 | Midnapore Division | Midnapore Mechanical Division | 124.72 | 11.65 | 7.59 | 0 | 143.97 | 124.72 | 11.65 | 7.59 | 0 | 143.97 | 44.57 | 26
39 | PASCHIM MEDINIPUR | SM/15084 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018354 | 6848018 | Augmentation | MVS | GO2223013191PH | 04/02/2023 | 365.97 | 42.24 | 408.2 | Midnapore Division | Midnapore Mechanical Division | 38.12 | 15.53 | 3.22 | 0 | 56.86 | 38.12 | 11.75 | 3.22 | 0 | 53.08 | 13 | 6
40 | PASCHIM MEDINIPUR | SM/10839 | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009942 | 40014619 | Augmentation | MVS | GO2223003643PH | 30/05/2022 | 854.03 | 42.24 | 896.27 | Midnapore Division | Midnapore Mechanical Division | 724.88 | 10.96 | 25.82 | 0 | 761.65 | 724.88 | 10.96 | 25.82 | 0 | 761.65 | 84.98 | 23
41 | PASCHIM MEDINIPUR | SM/15578 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018368 | 6348257 | Augmentation | MVS | GO2223013898PH | 15/02/2023 | 221.26 | 42.24 | 263.49 | Midnapore Division | Midnapore Mechanical Division | 7.52 | 3.14 | 2.11 | 0 | 12.77 | 7.52 | 3.14 | 2.11 | 0 | 12.77 | 4.85 | 86
42 | PASCHIM MEDINIPUR | SM/09999 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | TSM/008832 | 40003885 | Augmentation | MVS | GO2122007048PH | 20/12/2021 | 923.51 | 84.47 | 1007.98 | Midnapore Division | Midnapore Mechanical Division | 694.92 | 20.93 | 21.67 | 0 | 737.52 | 694.92 | 20.93 | 21.67 | 0 | 737.52 | 73.17 | 52
43 | PASCHIM MEDINIPUR | SM/15072 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018372 | 40047956 | Augmentation | MVS | GO2223013184PH | 04/02/2023 | 267.74 | 42.24 | 309.98 | Midnapore Division | Midnapore Mechanical Division | 8.75 | 8.23 | 3.09 | 0 | 20.07 | 8.75 | 0 | 3.09 | 0 | 11.85 | 3.82 | 79
44 | PASCHIM MEDINIPUR | SM/09585 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | TSM/008556 | 40000106 | Augmentation | MVS | GO2122005673PH | 22/11/2021 | 693.96 | 84.47 | 778.43 | Midnapore Division | Midnapore Mechanical Division | 249.26 | 20.91 | 55.31 | 0 | 325.48 | 249.26 | 20.91 | 55.31 | 0 | 325.48 | 41.81 | 63
45 | PASCHIM MEDINIPUR | SM/09455 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008496 | 40000104 | Augmentation | MVS | GO2122005600PH | 19/11/2021 | 195.44 | 42.24 | 237.68 | Midnapore Division | Midnapore Mechanical Division | 110.53 | 14.81 | 15.76 | 0 | 141.1 | 110.53 | 14.81 | 15.76 | 0 | 141.1 | 59.37 | 58
46 | PASCHIM MEDINIPUR | SM/12826 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012024 | 40024574 | Augmentation | MVS | GO2223008119PH | 22/09/2022 | 296 | 84.47 | 380.48 | Midnapore Division | Midnapore Mechanical Division | 26.4 | 11.15 | 0 | 0 | 37.56 | 26.4 | 11.15 | 0 | 0 | 37.56 | 9.87 | 22
47 | PASCHIM MEDINIPUR | SM/12827 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012025 | 40024128 | Augmentation | MVS | GO2223008120PH | 22/09/2022 | 426.33 | 42.24 | 468.57 | Midnapore Division | Midnapore Mechanical Division | 28.56 | 0 | 0 | 0 | 28.56 | 28.56 | 0 | 0 | 0 | 28.56 | 6.09 | 5
48 | PASCHIM MEDINIPUR | SM/16999 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018179 | 40059581 | Augmentation | SVS | GO2223016503PH | 16/03/2023 | 170.91 | 84.47 | 255.39 | Midnapore Division | Midnapore Mechanical Division | 0 | 18.83 | 0 | 0 | 18.83 | 0 | 0 | 0 | 0 | 0 | 0 | 83
49 | PASCHIM MEDINIPUR | SM/09980 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | TSM/008495 | 40007004 | Augmentation | MVS | GO2122006877PH | 16/12/2021 | 1095.63 | 126.71 | 1222.34 | Midnapore Division | Midnapore Mechanical Division | 606.02 | 44.23 | 159.2 | 0 | 809.44 | 606.02 | 44.23 | 159.2 | 0 | 809.44 | 66.22 | 15
50 | PASCHIM MEDINIPUR | SM/15905 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018382 | 6348345 | Augmentation | MVS | GO2223013894PH | 15/02/2023 | 316.19 | 84.47 | 400.66 | Midnapore Division | Midnapore Mechanical Division | 44 | 20.27 | 6.15 | 0 | 70.42 | 44 | 20.27 | 6.15 | 0 | 70.42 | 17.58 | 3
51 | PASCHIM MEDINIPUR | SM/15567 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | TSM/018377 | 40046811 | Augmentation | MVS | GO2223013901PH | 15/02/2023 | 286.45 | 84.47 | 370.93 | Midnapore Division | Midnapore Mechanical Division | 43.34 | 13.67 | 2 | 0 | 59.01 | 43.34 | 13.67 | 2 | 0 | 59.01 | 15.91 | 88
52 | PASCHIM MEDINIPUR | SM/15569 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/018394 | 40046859 | Augmentation | MVS | GO2223013900PH | 15/02/2023 | 426.81 | 42.24 | 469.04 | Midnapore Division | Jhargram Mechanical Division | 76.51 | 25.08 | 18.28 | 0 | 119.87 | 76.51 | 25.08 | 18.28 | 0 | 119.87 | 25.56 | 55
53 | PASCHIM MEDINIPUR | SM/17000 | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. | TSM/020423 | 40059720 | Augmentation | MVS | GO2223016498PH | 16/03/2023 | 877.42 | 54.2 | 931.61 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
54 | PASCHIM MEDINIPUR | SM/17812 | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019360 | 40061674 | Augmentation | SVS | GO2223016671PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
55 | PASCHIM MEDINIPUR | SM/17818 | Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019365 | 40061642 | Augmentation | MVS | GO2223016683PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Midnapore Mechanical Division | 0 | 0.19 | 0 | 0 | 0.19 | 0 | 0.19 | 0 | 0 | 0.19 | 0.78 | 40
56 | PASCHIM MEDINIPUR | SM/17758 | Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019370 | 40061040 | Augmentation | SVS | GO2223016694PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 5.29 | 0 | 0 | 5.29 | 0 | 5.29 | 0 | 0 | 5.29 | 42.69 | 60
57 | PASCHIM MEDINIPUR | SM/17779 | Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019366 | 40061492 | Augmentation | MVS | GO2223016685PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 11.28 | 0 | 0 | 11.28 | 0 | 11.28 | 0 | 0 | 11.28 | 90.97 | 60
58 | PASCHIM MEDINIPUR | SM/17796 | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019374 | 40061886 | Augmentation | SVS | GO2223016702PH | 17/03/2023 | 0 | 5.55 | 5.55 |  | Jhargram Mechanical Division | 0 | 5.07 | 0 | 0 | 5.07 | 0 | 5.07 | 0 | 0 | 5.07 | 91.37 | 60
59 | PASCHIM MEDINIPUR | SM/17754 | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019363 | 40060888 | Augmentation | MVS | GO2223016678PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 8.64 | 0 | 0 | 8.64 | 0 | 8.64 | 0 | 0 | 8.64 | 69.69 | 100
60 | PASCHIM MEDINIPUR | SM/17728 | Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019361 | 40060490 | Augmentation | MVS | GO2223016673PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 10.32 | 0 | 0 | 10.32 | 0 | 10.32 | 0 | 0 | 10.32 | 83.29 | 30
61 | PASCHIM MEDINIPUR | SM/17822 | Rejuvenation of Electro-Mechanical components of Gobardhanpur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019372 | 40061275 | Augmentation | MVS | GO2223016697PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.96 | 0 | 0 | 0.96 | 0 | 0.96 | 0 | 0 | 0.96 | 7.72 | 20
62 | PASCHIM MEDINIPUR | SM/17750 | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019373 | 40060747 | Augmentation | SVS | GO2223016700PH | 17/03/2023 | 0 | 5.55 | 5.55 |  | Jhargram Mechanical Division | 0 | 5.07 | 0 | 0 | 5.07 | 0 | 5.07 | 0 | 0 | 5.07 | 91.37 | 60
63 | PASCHIM MEDINIPUR | SM/17776 | Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019362 | 40061287 | Augmentation | MVS | GO2223016675PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.41 | 0 | 0 | 0.41 | 0 | 0.41 | 0 | 0 | 0.41 | 3.27 | 20
64 | PASCHIM MEDINIPUR | SM/17792 | Rejuvenation of Electro-Mechanical components of Lutunia PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019391 | 40061841 | Augmentation | MVS | GO2223016681PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 5.98 | 0 | 0 | 5.98 | 0 | 5.98 | 0 | 0 | 5.98 | 48.23 | 60
65 | PASCHIM MEDINIPUR | SM/17785 | Rejuvenation of Electro-Mechanical components of Satkui PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019359 | 40061512 | Augmentation | MVS | GO2223016669PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 4.95 | 0 | 0 | 4.95 | 0 | 4.95 | 0 | 0 | 4.95 | 39.95 | 30
66 | PASCHIM MEDINIPUR | SM/17820 | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019369 | 40062747 | Augmentation | SVS | GO2223016692PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Jhargram Mechanical Division | 0 | 8.24 | 0 | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 8.24 | 33.24 | 2
67 | PASCHIM MEDINIPUR | SM/17755 | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019368 | 40062693 | Augmentation | SVS | GO2223016689PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Jhargram Mechanical Division | 0 | 8.46 | 0 | 0 | 8.46 | 0 | 8.46 | 0 | 0 | 8.46 | 34.14 | 2
68 | PASCHIM MEDINIPUR | SM/13046 | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | TSM/011552 | 6372771 | Augmentation | MVS | GO2223008462PH | 29/09/2022 | 291.75 | 4.22 | 295.97 | Midnapore Division |  | 241.75 | 16.49 | 0 | 0 | 258.25 | 241.75 | 15.84 | 0 | 0 | 257.6 | 87.03 | 15
69 | PASCHIM MEDINIPUR | SM/15217 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009612 | 40063834 | Augmentation | MVS | GO2223013462PH | 07/02/2023 | 67.56 | 7.53 | 75.1 | Midnapore Division | Midnapore Mechanical Division | 65.6 | 7.25 | 0 | 0 | 72.85 | 65.6 | 7.25 | 0 | 0 | 72.85 | 97 | 17
70 | PASCHIM MEDINIPUR | SM/10842 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009954 | 40015135 | Augmentation | MVS | GO2223003647PH | 30/05/2022 | 60.23 | 27.66 | 87.89 | Midnapore Division | Midnapore Mechanical Division | 58.47 | 26.85 | 0 | 0 | 85.32 | 58.47 | 20.9 | 0 | 0 | 79.37 | 90.31 | 60
71 | PASCHIM MEDINIPUR | SM/15218 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009948 | 40063745 | Augmentation | MVS | GO2223013465PH | 07/02/2023 | 76.97 | 55.33 | 132.3 | Midnapore Division | Midnapore Mechanical Division | 65.5 | 26.69 | 0 | 0 | 92.19 | 65.5 | 26.69 | 0 | 0 | 92.19 | 69.68 | 27
72 | PASCHIM MEDINIPUR | SM/15219 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009955 | 40037019 | Augmentation | MVS | GO2223013464PH | 07/02/2023 | 117.66 | 27.66 | 145.33 | Midnapore Division | Midnapore Mechanical Division | 74.45 | 12.5 | 0 | 0 | 86.94 | 74.45 | 12.5 | 0 | 0 | 86.94 | 59.83 | 51
73 | PASCHIM MEDINIPUR | SM/10686 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009947 | 40014395 | Augmentation | MVS | GO2223000917PH | 06/05/2022 | 60.21 | 27.66 | 87.88 | Midnapore Division | Midnapore Mechanical Division | 50.02 | 17.82 | 0 | 0 | 67.84 | 50.02 | 17.23 | 0 | 0 | 67.25 | 76.53 | 65
74 | PASCHIM MEDINIPUR | SM/10840 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009615 | 40015136 | Augmentation | SVS | GO2223003648PH | 30/05/2022 | 57.35 | 7.53 | 64.89 | Midnapore Division | Midnapore Mechanical Division | 42.8 | 6.63 | 0 | 0 | 49.42 | 42.8 | 6.01 | 0 | 0 | 48.81 | 75.23 | 100
75 | PASCHIM MEDINIPUR | SM/10821 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009956 | 40014829 | Augmentation | MVS | GO2223003603PH | 27/05/2022 | 141.22 | 55.33 | 196.55 | Midnapore Division | Midnapore Mechanical Division | 128.17 | 28.21 | 0 | 8.94 | 165.32 | 128.17 | 27.62 | 0 | 8.94 | 164.73 | 83.81 | 58
76 | PASCHIM MEDINIPUR | SM/11811 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009949 | 40018782 | Augmentation | MVS | GO2223006318PH | 16/08/2022 | 56.65 | 27.66 | 84.32 | Midnapore Division | Midnapore Mechanical Division | 44.42 | 20.71 | 0 | 0 | 65.13 | 44.42 | 20.71 | 0 | 0 | 65.13 | 77.25 | 78
77 | PASCHIM MEDINIPUR | SM/11895 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009944 | 40018866 | Augmentation | MVS | GO2223006513PH | 18/08/2022 | 28.97 | 27.66 | 56.64 | Midnapore Division | Midnapore Mechanical Division | 26.83 | 26.86 | 0 | 0 | 53.69 | 26.83 | 26.86 | 0 | 0 | 53.69 | 94.79 | 70
78 | PASCHIM MEDINIPUR | SM/10778 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009952 | 40014750 | Augmentation | MVS | GO2223003518PH | 25/05/2022 | 112.92 | 27.66 | 140.59 | Midnapore Division | Midnapore Mechanical Division | 71.16 | 27.08 | 0 | 0 | 98.24 | 71.16 | 27.08 | 0 | 0 | 98.24 | 69.88 | 64
79 | PASCHIM MEDINIPUR | SM/10731 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009614 | 5265789 | Augmentation | MVS | GO2223002161PH | 19/05/2022 | 112.63 | 7.53 | 120.16 | Midnapore Division | Midnapore Mechanical Division | 63.09 | 5.87 | 0 | 0 | 68.96 | 63.09 | 5.87 | 0 | 0 | 68.96 | 57.39 | 13
80 | PASCHIM MEDINIPUR | SM/14720 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009951 | 40063744 | Augmentation | MVS | GO2223012743PH | 31/01/2023 | 62.64 | 27.66 | 90.31 | Midnapore Division | Midnapore Mechanical Division | 57.09 | 11.38 | 0 | 0 | 68.47 | 57.09 | 11.38 | 0 | 0 | 68.47 | 75.82 | 25
81 | PASCHIM MEDINIPUR | SM/10779 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009950 | 40014827 | Augmentation | MVS | GO2223003519PH | 25/05/2022 | 51.83 | 27.66 | 79.49 | Midnapore Division | Midnapore Mechanical Division | 12.29 | 14.62 | 0 | 9.35 | 36.26 | 12.29 | 14.62 | 0 | 9.35 | 36.26 | 45.62 | 18
82 | PASCHIM MEDINIPUR | SM/10841 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009945 | 40015132 | Augmentation | MVS | GO2223003646PH | 30/05/2022 | 66.01 | 27.66 | 93.67 | Midnapore Division | Midnapore Mechanical Division | 12.59 | 13.98 | 0 | 0 | 26.57 | 12.59 | 13.98 | 0 | 0 | 26.57 | 28.37 | 10
83 | PASCHIM MEDINIPUR | SM/10685 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009946 | 40014396 | Augmentation | MVS | GO2223000916PH | 06/05/2022 | 95.88 | 27.66 | 123.54 | Midnapore Division | Midnapore Mechanical Division | 74.22 | 16.01 | 0 | 0 | 90.22 | 74.22 | 15.46 | 0 | 0 | 89.68 | 72.59 | 79
Total | [9 empty] | 33017.57 | 4044.95 | 37062.52 |  |  | 11055.15 | 1228.49 | 1173.72 | 18.29 | 13475.65 | 11052.38 | 1152.67 | 1173.72 | 18.29 | 13397.07 | 36.15