## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PASCHIM MEDINIPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PASCHIM MEDINIPUR | SM/14689 | ABHAYA AND ADJOINING MOUJAS PWSS | TSM/016168 | 40035537 | New | MVS | GO2223012728PH | 31/01/2023 | 154.09 | 3.95 | 158.04 | Midnapore Division | Jhargram Mechanical Division | 28.31 | 0 | 1.51 | 11.82 | 41.64 | 28.31 | 0 | 1.51 | 11.82 | 41.64 | 26.35 | 30
2 | PASCHIM MEDINIPUR | SM/13052 | AGRA & ADJOINING MOUJAS PWSS | TSM/013395 | 40028713 | New | MVS | GO2223008502PH | 29/09/2022 | 306.78 | 36.38 | 343.16 | Midnapore Division | Jhargram Mechanical Division | 130.18 | 8.6 | 20.47 | 12.28 | 171.52 | 101.86 | 8.6 | 20.47 | 12.28 | 143.21 | 41.73 | 35
3 | PASCHIM MEDINIPUR | SM/13176 | AKANDA AND ADJOINING MOUJAS PWSS | TSM/014328 | 40034264 | New | MVS | GO2223008656PH | 12/10/2022 | 510.73 | 38.73 | 549.46 | Midnapore Division | Midnapore Mechanical Division | 0 | 3.15 | 25.34 | 0 | 28.49 | 0 | 3.15 | 25.34 | 0 | 28.49 | 5.19 | 20
4 | PASCHIM MEDINIPUR | SM/17003 | AKRA MARKANDAPUR PWSS | TSM/017988 | 40054168 | New | SVS | GO2223016500PH | 16/03/2023 | 35.97 | 9.17 | 45.14 | Midnapore Division | Midnapore Mechanical Division | 14.17 | 4.16 | 0 | 0 | 18.34 | 14.17 | 4.16 | 0 | 0 | 18.34 | 40.62 | 80
5 | PASCHIM MEDINIPUR | SM/13177 | AMDA AND ADJOINING MOUJAS PWSS | TSM/014572 | 40034930 | New | MVS | GO2223008660PH | 12/10/2022 | 464.76 | 37.66 | 502.42 | Midnapore Division | Midnapore Mechanical Division | 96.52 | 4.88 | 17.29 | 6.52 | 125.21 | 96.52 | 4.88 | 17.29 | 6.52 | 125.21 | 24.92 | 50
6 | PASCHIM MEDINIPUR | SM/13707 | AMJOR AND ADJOINING MOUJAS PWSS | TSM/015062 | 40059417 | New | MVS | GO2223009724PH | 14/11/2022 | 314.6 | 35.59 | 350.18 | Midnapore Division | Midnapore Mechanical Division | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 72
7 | PASCHIM MEDINIPUR | SM/10318 | Amjor Piped Water Supply Scheme. | TSM/004490 | 40059417 | New | MVS | GO2122010475PH | 04/03/2022 | 474.37 | 36.29 | 510.66 | Midnapore Division | Jhargram Mechanical Division | 166.47 | 23.4 | 26.07 | 0 | 215.94 | 162.78 | 23.4 | 26.07 | 0 | 212.24 | 41.56 | 72
8 | PASCHIM MEDINIPUR | SM/18584 | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | TSM/017358 | 40034546 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1178.57 | 41.23 | 1219.81 | Midnapore Division | Midnapore Mechanical Division | 651.73 | 26.85 | 0 | 0 | 678.58 | 651.73 | 24.92 | 0 | 0 | 676.65 | 55.47 | 60
9 | PASCHIM MEDINIPUR | SM/14989 | AMLASULI AND ADJOINING MOUJAS PWSS | TSM/015791 | 40035448 | New | MVS | GO2223013050PH | 04/02/2023 | 513.11 | 49.87 | 562.97 | Midnapore Division | Jhargram Mechanical Division | 129.43 | 8.09 | 9.97 | 6.56 | 154.04 | 129.43 | 8.09 | 9.97 | 6.56 | 154.04 | 27.36 | 30
10 | PASCHIM MEDINIPUR | SM/13178 | AMRA TARYA AND ADJOINING MOUJAS PWSS | TSM/014571 | 40034915 | New | MVS | GO2223008659PH | 12/10/2022 | 428.59 | 37.64 | 466.23 | Midnapore Division | Midnapore Mechanical Division | 90 | 6.74 | 7.34 | 8.71 | 112.8 | 90 | 6.74 | 7.34 | 8.71 | 112.8 | 24.19 | 23
11 | PASCHIM MEDINIPUR | SM/13179 | AMSOL AND ADJOINING MOUJAS PWSS | TSM/014456 | 40033114 | New | MVS | GO2223008658PH | 12/10/2022 | 368.87 | 36.58 | 405.45 | Midnapore Division | Jhargram Mechanical Division | 70.6 | 10.25 | 6.48 | 6.52 | 93.84 | 70.6 | 10.25 | 6.48 | 6.52 | 93.84 | 23.14 | 34
12 | PASCHIM MEDINIPUR | SM/13180 | ANAR AND ADJOINING MOUJAS PWSS | TSM/014649 | 40034969 | New | MVS | GO2223008657PH | 12/10/2022 | 575.5 | 39.45 | 614.95 | Midnapore Division | Midnapore Mechanical Division | 103.99 | 28.4 | 14.72 | 24.54 | 171.66 | 103.99 | 28.4 | 14.72 | 24.54 | 171.66 | 27.91 | 35
13 | PASCHIM MEDINIPUR | SM/13635 | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | TSM/014629 | 40030361 | New | MVS | GO2223009606PH | 11/11/2022 | 601.22 | 57.66 | 658.87 | Midnapore Division | Jhargram Mechanical Division | 21.39 | 13.18 | 52 | 12.65 | 99.21 | 21.39 | 13.18 | 52 | 12.65 | 99.21 | 15.06 | 25
14 | PASCHIM MEDINIPUR | SM/12989 | ANGUA AND ADJOINING MOUJAS PWSS | TSM/014240 | 40025991 | New | MVS | GO2223008344PH | 28/09/2022 | 367.43 | 36.45 | 403.88 | Midnapore Division | Midnapore Mechanical Division | 45.41 | 10.59 | 7.7 | 0 | 63.71 | 34.6 | 10.59 | 7.7 | 0 | 52.9 | 13.1 | 45
15 | PASCHIM MEDINIPUR | SM/09991 | Antla Piped Water Supply Scheme. | TSM/008037 | 40008563 | New | MVS | GO2122006951PH | 16/12/2021 | 669.25 | 0 | 669.25 | Midnapore Division | Midnapore Mechanical Division | 382.38 | 0 | 68.09 | 0 | 450.47 | 382.18 | 0 | 68.09 | 0 | 450.27 | 67.28 | 95
16 | PASCHIM MEDINIPUR | SM/13636 | ANTRI AND ADJOINING MOUJAS PWSS | TSM/014683 | 40030188 | New | MVS | GO2223009607PH | 11/11/2022 | 840.52 | 39.49 | 880.01 | Midnapore Division | Midnapore Mechanical Division | 339.58 | 30.5 | 1.89 | 0 | 371.97 | 326.06 | 30.5 | 1.89 | 0 | 358.44 | 40.73 | 65
17 | PASCHIM MEDINIPUR | SM/12198 | ASHARI AND IT'S ADJOINING MOUJAS PWSS | TSM/013126 | 40021620 | New | MVS | GO2223007234PH | 07/09/2022 | 369.7 | 37.89 | 407.59 | Midnapore Division | Midnapore Mechanical Division | 153.69 | 8.25 | 7.1 | 0 | 169.03 | 138.74 | 8.25 | 7.1 | 0 | 154.09 | 37.8 | 20
18 | PASCHIM MEDINIPUR | SM/13655 | ASTI AND ADJOINING MOUJAS PWSS | TSM/014385 | 40034135 | New | MVS | GO2223009605PH | 11/11/2022 | 740.59 | 40.11 | 780.7 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 7.23 | 22.04 | 0 | 34.05 | 4.78 | 7.23 | 22.04 | 0 | 34.05 | 4.36 | 61
19 | PASCHIM MEDINIPUR | SM/13753 | BABAIBASA AND ADJOINING MOUJAS PWSS | TSM/014992 | 40033948 | New | MVS | GO2223009800PH | 17/11/2022 | 349.48 | 38.33 | 387.81 | Midnapore Division | Jhargram Mechanical Division | 118.47 | 6.05 | 5.99 | 18.12 | 148.63 | 118.47 | 6.05 | 5.99 | 18.12 | 148.63 | 38.32 | 45
20 | PASCHIM MEDINIPUR | SM/13754 | BABALPUR AND ADJOINING MOUJAS PWSS | TSM/014504 | 40034187 | New | MVS | GO2223009798PH | 17/11/2022 | 423.48 | 38.53 | 462.01 | Midnapore Division | Midnapore Mechanical Division | 52.75 | 6.48 | 2.02 | 13.12 | 74.37 | 52.75 | 6.48 | 2.02 | 13.12 | 74.37 | 16.1 | 15
21 | PASCHIM MEDINIPUR | SM/13805 | BAGBASA AND ADJOINING MOUJAS PWSS | TSM/014986 | 40034070 | New | MVS | GO2223009964PH | 22/11/2022 | 495.18 | 37.78 | 532.96 | Midnapore Division | Jhargram Mechanical Division | 161.18 | 9.63 | 51.03 | 10.09 | 231.93 | 147.13 | 9.63 | 51.03 | 10.09 | 217.88 | 40.88 | 30
22 | PASCHIM MEDINIPUR | SM/14690 | BAGDOBA AND ADJOINING MOUJAS PWSS | TSM/016495 | 40033440 | New | MVS | GO2223012732PH | 31/01/2023 | 353.24 | 54.59 | 407.83 | Midnapore Division | Jhargram Mechanical Division | 86.1 | 4.53 | 4.92 | 6.52 | 102.07 | 86.1 | 4.53 | 4.92 | 6.52 | 102.07 | 25.03 | 30
23 | PASCHIM MEDINIPUR | SM/19052 | BAGRUI AND ITS ADJOINING MOUZAS PWSS | TSM/017511 | 40044556 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1194.95 | 42.8 | 1237.75 | Midnapore Division | Midnapore Mechanical Division | 175.6 | 20.95 | 19.21 | 0 | 215.76 | 114.81 | 20.95 | 19.21 | 0 | 154.97 | 12.52 | 30
24 | PASCHIM MEDINIPUR | SM/17623 | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS | TSM/011859 | 40033382 | New | MVS | GO2223017415PH | 21/03/2023 | 476.96 | 38.28 | 515.24 | Midnapore Division | Midnapore Mechanical Division | 160.34 | 3.38 | 27.44 | 0 | 191.16 | 160.34 | 3.38 | 27.44 | 0 | 191.16 | 37.1 | 24
25 | PASCHIM MEDINIPUR | SM/13755 | BAHURUPA AND ADJOINING MOUJAS PWSS | TSM/014436 | 40034012 | New | MVS | GO2223009797PH | 17/11/2022 | 552.23 | 38.53 | 590.76 | Midnapore Division | Midnapore Mechanical Division | 29.74 | 9.39 | 1.71 | 12.65 | 53.49 | 29.74 | 9.39 | 1.71 | 12.65 | 53.49 | 9.05 | 15
26 | PASCHIM MEDINIPUR | SM/18658 | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | TSM/017510 | 40036357 | New | MVS | 2231/PHE-28011/21/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1175.02 | 41.23 | 1216.26 | Midnapore Division | Midnapore Mechanical Division | 7.5 | 21.38 | 14.31 | 0 | 43.19 | 7.5 | 21.38 | 14.31 | 0 | 43.19 | 3.55 | 12
27 | PASCHIM MEDINIPUR | SM/12199 | BAKALSABAKARAM PWSS | TSM/011656 | 40021327 | New | MVS | GO2223007212PH | 07/09/2022 | 565.6 | 38.2 | 603.79 | Midnapore Division | Midnapore Mechanical Division | 96.46 | 30.69 | 34.34 | 0 | 161.49 | 96.46 | 30.69 | 34.34 | 0 | 161.49 | 26.75 | 24
28 | PASCHIM MEDINIPUR | SM/12990 | BALADAGHATA AND ADJOINING MOUJAS PWSS | TSM/014125 | 40025985 | New | MVS | GO2223008343PH | 28/09/2022 | 633.23 | 40.02 | 673.25 | Midnapore Division | Jhargram Mechanical Division | 178.79 | 10.08 | 33.86 | 15 | 237.73 | 168.4 | 10.08 | 33.86 | 15 | 227.34 | 33.77 | 31
29 | PASCHIM MEDINIPUR | SM/13063 | BALARAMPUR AND ADJOINING MOUJAS PWSS | TSM/014493 | 40029976 | New | MVS | GO2223008478PH | 29/09/2022 | 352.11 | 36.58 | 388.69 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 5.64 | 9.56 | 15.2 | 0 | 0 | 5.64 | 9.56 | 15.2 | 3.91 | 17
30 | PASCHIM MEDINIPUR | SM/14990 | BALIBANDH AND ADJOINING MOUJAS PWSS | TSM/015799 | 40035559 | New | MVS | GO2223013091PH | 04/02/2023 | 505.34 | 40.17 | 545.5 | Midnapore Division | Jhargram Mechanical Division | 56.73 | 0 | 7.46 | 0 | 64.19 | 56.73 | 0 | 7.46 | 0 | 64.19 | 11.77 | 20
31 | PASCHIM MEDINIPUR | SM/12991 | BAMANBIRUA AND ADJOINING MOUJAS PWSS | TSM/014261 | 40026005 | New | MVS | GO2223008337PH | 28/09/2022 | 515.74 | 38.61 | 554.34 | Midnapore Division | Midnapore Mechanical Division | 313.89 | 25.74 | 0 | 0 | 339.63 | 309.23 | 25.74 | 0 | 0 | 334.97 | 60.43 | 80
32 | PASCHIM MEDINIPUR | SM/12993 | BAMANDA AND ADJOINING MOUJAS PWSS | TSM/014223 | 40026018 | New | MVS | GO2223008345PH | 28/09/2022 | 525.97 | 38.85 | 564.82 | Midnapore Division | Midnapore Mechanical Division | 310.21 | 17.47 | 2.4 | 0 | 330.08 | 272.77 | 17.47 | 2.4 | 0 | 292.64 | 51.81 | 75
33 | PASCHIM MEDINIPUR | SM/13047 | BAMANSAI AND IT'S ADJOINING MOUJAS PWSS | TSM/013156 | 40031751 | New | MVS | GO2223008497PH | 29/09/2022 | 338.78 | 37.83 | 376.6 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 7.72 | 0 | 7.72 | 0 | 0 | 7.72 | 0 | 7.72 | 2.05 | 9
34 | PASCHIM MEDINIPUR | SM/13064 | BANAMALIPUR AND ADJOINING MOUJAS PWSS | TSM/015010 | 40029901 | New | MVS | GO2223008475PH | 29/09/2022 | 445.72 | 25.57 | 471.29 | Midnapore Division | Jhargram Mechanical Division | 111.48 | 3.91 | 6.93 | 11.18 | 133.49 | 67.87 | 3.91 | 6.93 | 11.18 | 89.89 | 19.07 | 25
35 | PASCHIM MEDINIPUR | SM/13065 | BANKIBANDH AND ADJOINING MOUJAS PWSS | TSM/014956 | 40031740 | New | MVS | GO2223008496PH | 29/09/2022 | 380.35 | 28.91 | 409.26 | Midnapore Division | Jhargram Mechanical Division | 39.8 | 0 | 7.21 | 21.89 | 68.89 | 39.8 | 0 | 7.21 | 21.89 | 68.89 | 16.83 | 18
36 | PASCHIM MEDINIPUR | SM/12200 | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS | TSM/013141 | 40021345 | New | MVS | GO2223007233PH | 07/09/2022 | 238.3 | 37.8 | 276.09 | Midnapore Division | Midnapore Mechanical Division | 124.65 | 29.43 | 7.65 | 0 | 161.73 | 110.67 | 29.43 | 7.65 | 0 | 147.75 | 53.51 | 65
37 | PASCHIM MEDINIPUR | SM/14941 | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | TSM/014437 | 40034011 | New | MVS | GO2223012938PH | 03/02/2023 | 430.97 | 38.61 | 469.58 | Midnapore Division | Midnapore Mechanical Division | 93.19 | 9.28 | 9.55 | 15 | 127.03 | 93.19 | 9.28 | 9.55 | 15 | 127.03 | 27.05 | 50
38 | PASCHIM MEDINIPUR | SM/13066 | BARABOLABANDI AND ADJOINING MOUJAS PWSS | TSM/014850 | 40030023 | New | MVS | GO2223008485PH | 29/09/2022 | 327.32 | 37.66 | 364.98 | Midnapore Division | Jhargram Mechanical Division | 113.77 | 9.67 | 5.93 | 15.81 | 145.17 | 104.49 | 9.67 | 5.93 | 15.81 | 135.9 | 37.23 | 34
39 | PASCHIM MEDINIPUR | SM/12201 | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | TSM/011732 | 40021312 | New | MVS | GO2223007204PH | 07/09/2022 | 414.76 | 37.89 | 452.65 | Midnapore Division | Midnapore Mechanical Division | 150.4 | 26.08 | 23.12 | 0 | 199.61 | 147.41 | 26.08 | 23.12 | 0 | 196.61 | 43.44 | 19
40 | PASCHIM MEDINIPUR | SM/14991 | BARAKADRA AND ADJOINING MOUJAS PWSS | TSM/015848 | 40035386 | New | MVS | GO2223013052PH | 04/02/2023 | 443.76 | 39.18 | 482.93 | Midnapore Division | Jhargram Mechanical Division | 167.09 | 15.27 | 11.54 | 13.03 | 206.93 | 167.09 | 15.27 | 11.54 | 13.03 | 206.93 | 42.85 | 52
41 | PASCHIM MEDINIPUR | SM/13067 | BARAKALANKI AND ADJOINING MOUJAS PWSS | TSM/014283 | 40031763 | New | MVS | GO2223008498PH | 29/09/2022 | 541.45 | 38.61 | 580.05 | Midnapore Division | Midnapore Mechanical Division | 215.02 | 11.04 | 0 | 13.12 | 239.18 | 215.02 | 11.04 | 0 | 13.12 | 239.18 | 41.23 | 50
42 | PASCHIM MEDINIPUR | SM/13002 | BARAKEUNDI AND ADJOINING MOUJAS PWSS | TSM/015011 | 40026203 | New | MVS | GO2223008405PH | 29/09/2022 | 482.75 | 37.9 | 520.65 | Midnapore Division | Jhargram Mechanical Division | 194.16 | 6.96 | 8.78 | 12.77 | 222.67 | 186.42 | 6.96 | 8.78 | 12.77 | 214.94 | 41.28 | 26
43 | PASCHIM MEDINIPUR | SM/13068 | BARAKURYA AND ADJOINING MOUJAS PWSS | TSM/014496 | 40029978 | New | MVS | GO2223008481PH | 29/09/2022 | 267.97 | 60.49 | 328.47 | Midnapore Division | Jhargram Mechanical Division | 22.71 | 12.13 | 3.6 | 13.03 | 51.47 | 22.71 | 12.13 | 3.6 | 13.03 | 51.47 | 15.67 | 16
44 | PASCHIM MEDINIPUR | SM/12994 | BARAMURA AND ADJOINING MOUJAS PWSS | TSM/014126 | 40025978 | New | MVS | GO2223008342PH | 28/09/2022 | 429.48 | 35.61 | 465.08 | Midnapore Division | Jhargram Mechanical Division | 142.34 | 0 | 10.66 | 19.15 | 172.16 | 131.62 | 0 | 10.66 | 19.15 | 161.43 | 34.71 | 35
45 | PASCHIM MEDINIPUR | SM/13003 | BARANAGARA AND ADJOINING MOUJAS PWSS | TSM/014740 | 40026236 | New | MVS | GO2223008413PH | 29/09/2022 | 378.61 | 37.78 | 416.39 | Midnapore Division | Jhargram Mechanical Division | 139.25 | 16.89 | 4.31 | 12.57 | 173.02 | 125.96 | 16.89 | 4.31 | 12.57 | 159.73 | 38.36 | 40
46 | PASCHIM MEDINIPUR | SM/12996 | BARANGI AND ADJOINING MOUJAS PWSS | TSM/014222 | 40025954 | New | MVS | GO2223008336PH | 28/09/2022 | 652.34 | 40.04 | 692.38 | Midnapore Division | Midnapore Mechanical Division | 168.9 | 7.72 | 16.34 | 0 | 192.96 | 168.9 | 7.72 | 16.34 | 0 | 192.96 | 27.87 | 50
47 | PASCHIM MEDINIPUR | SM/18507 | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016340 | 40035807 | New | MVS | 2041/PHE-28011/43/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1112.5 | 44.17 | 1156.66 | Midnapore Division | Midnapore Mechanical Division | 637.14 | 26.22 | 96.1 | 0 | 759.46 | 559.76 | 26.22 | 96.1 | 0 | 682.08 | 58.97 | 35
48 | PASCHIM MEDINIPUR | SM/12841 | BARBHUNA BASAN STAND ALONE PWSS | TSM/014548 | 40024290 | New | SVS | GO2223008080PH | 22/09/2022 | 46.81 | 8.69 | 55.5 | Midnapore Division | Midnapore Mechanical Division | 0 | 4.35 | 0 | 0 | 4.35 | 0 | 4.35 | 0 | 0 | 4.35 | 7.83 | 50
49 | PASCHIM MEDINIPUR | SM/14692 | BARDIHA AND ADJOINING MOUJAS PWSS | TSM/014467 | 40036359 | New | MVS | GO2223012725PH | 31/01/2023 | 200.06 | 31.77 | 231.83 | Midnapore Division | Jhargram Mechanical Division | 32.66 | 12.65 | 2.55 | 11.92 | 59.79 | 32.66 | 12.65 | 2.55 | 11.92 | 59.79 | 25.79 | 40
50 | PASCHIM MEDINIPUR | SM/13004 | BARGOPAL AND ADJOINING MOUJAS PWSS | TSM/014779 | 40026199 | New | MVS | GO2223008401PH | 29/09/2022 | 742.95 | 39.29 | 782.23 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 9.94 | 0 | 15 | 29.72 | 4.78 | 9.94 | 0 | 15 | 29.72 | 3.8 | 20
51 | PASCHIM MEDINIPUR | SM/13048 | BELDA AND IT'S ADJOINING MOUJAS | TSM/013155 | 40031461 | New | MVS | GO2223008494PH | 29/09/2022 | 487.9 | 38.28 | 526.18 | Midnapore Division | Midnapore Mechanical Division | 18.76 | 6.26 | 11.38 | 0 | 36.4 | 4.78 | 6.26 | 11.38 | 0 | 22.42 | 4.26 | 10
52 | PASCHIM MEDINIPUR | SM/14992 | BENACHAPRA AND ADJOINING MOUJAS PWSS | TSM/015807 | 40035704 | New | MVS | GO2223013090PH | 04/02/2023 | 362.63 | 38.84 | 401.48 | Midnapore Division | Jhargram Mechanical Division | 82.18 | 9.09 | 6.74 | 12.11 | 110.12 | 82.18 | 9.09 | 6.74 | 12.11 | 110.12 | 27.43 | 40
53 | PASCHIM MEDINIPUR | SM/14993 | BENADIHA AND ADJOINING MOUJAS PWSS | TSM/016082 | 40034137 | New | MVS | GO2223013089PH | 04/02/2023 | 819.34 | 39.18 | 858.52 | Midnapore Division | Midnapore Mechanical Division | 410.46 | 7.72 | 0 | 20.05 | 438.23 | 410.46 | 7.72 | 0 | 20.05 | 438.23 | 51.05 | 70
54 | PASCHIM MEDINIPUR | SM/13069 | BENUCHA AND ADJOINING MOUJAS PWSS | TSM/014953 | 40029977 | New | MVS | GO2223008480PH | 29/09/2022 | 419.65 | 39.06 | 458.71 | Midnapore Division | Jhargram Mechanical Division | 54.49 | 11.64 | 8.9 | 12.75 | 87.78 | 42.95 | 11.64 | 8.9 | 12.75 | 76.25 | 16.62 | 20
55 | PASCHIM MEDINIPUR | SM/14721 | BENYA AND IT'S ADJOINING MOUJAS PWSS. | TSM/013182 | 40033298 | New | MVS | GO2223012696PH | 31/01/2023 | 581.22 | 38.28 | 619.5 | Midnapore Division | Midnapore Mechanical Division | 284.68 | 25.68 | 11.09 | 0 | 321.45 | 284.68 | 24.29 | 11.09 | 0 | 320.06 | 51.66 | 2
56 | PASCHIM MEDINIPUR | SM/12202 | BHAGABANPUR PIPED WATER SUPPLY SCHEME | TSM/011569 | 40021629 | New | MVS | GO2223007260PH | 07/09/2022 | 416.75 | 38.05 | 454.8 | Midnapore Division | Midnapore Mechanical Division | 95.94 | 16.05 | 8.75 | 0 | 120.74 | 85.39 | 16.05 | 8.75 | 0 | 110.19 | 24.23 | 15
57 | PASCHIM MEDINIPUR | SM/13005 | BHANSRA AND ADJOINING MOUJAS PWSS | TSM/014653 | 40026202 | New | MVS | GO2223008403PH | 29/09/2022 | 492.45 | 39.33 | 531.78 | Midnapore Division | Midnapore Mechanical Division | 114.16 | 17.86 | 13.91 | 11.12 | 157.04 | 97.93 | 17.86 | 13.91 | 11.12 | 140.81 | 26.48 | 38
58 | PASCHIM MEDINIPUR | SM/14644 | BHATMARA AND ADJOINING MOUJAS PWSS | TSM/016781 | 40033437 | New | MVS | GO2223012736PH | 31/01/2023 | 174.96 | 13.72 | 188.68 | Midnapore Division | Jhargram Mechanical Division | 32.58 | 0 | 13.48 | 9.95 | 56.01 | 32.58 | 0 | 13.48 | 9.95 | 56.01 | 29.69 | 20
59 | PASCHIM MEDINIPUR | SM/15509 | BHATUIGERYA PIPED WATER SUPPLY SCHEME | TSM/012537 | 40036355 | New | MVS | GO2223014032PH | 16/02/2023 | 1028.03 | 36.83 | 1064.86 | Midnapore Division | Midnapore Mechanical Division | 250.37 | 8.09 | 27.43 | 0 | 285.89 | 167.46 | 8.09 | 27.43 | 0 | 202.98 | 19.06 | 32
60 | PASCHIM MEDINIPUR | SM/14825 | BHATURBANDI AND ADJOINING MOUJAS PWSS | TSM/014562 | 40036361 | New | MVS | GO2223012931PH | 03/02/2023 | 266.57 | 35.56 | 302.13 | Midnapore Division | Jhargram Mechanical Division | 81.58 | 4.02 | 3.02 | 6.52 | 95.14 | 81.58 | 4.02 | 3.02 | 6.52 | 95.14 | 31.49 | 38
61 | PASCHIM MEDINIPUR | SM/13070 | BHAUDI AND ADJOINING MOUJAS PWSS | TSM/015008 | 40029899 | New | MVS | GO2223008473PH | 29/09/2022 | 374.86 | 35.08 | 409.94 | Midnapore Division | Jhargram Mechanical Division | 83.56 | 5.13 | 7.28 | 22.59 | 118.57 | 83.23 | 5.13 | 7.28 | 22.59 | 118.24 | 28.84 | 25
62 | PASCHIM MEDINIPUR | SM/12998 | BHETIAMLA AND ADJOINING MOUJAS PWSS | TSM/014219 | 40026007 | New | MVS | GO2223008340PH | 28/09/2022 | 501.13 | 38.73 | 539.86 | Midnapore Division | Midnapore Mechanical Division | 88.77 | 27.93 | 11.99 | 0 | 128.69 | 88.77 | 27.93 | 11.99 | 0 | 128.69 | 23.84 | 60
63 | PASCHIM MEDINIPUR | SM/13071 | BHIKUBAR AND ADJOINING MOUJAS PWSS | TSM/014774 | 40029979 | New | MVS | GO2223008482PH | 29/09/2022 | 366.83 | 37.66 | 404.49 | Midnapore Division | Midnapore Mechanical Division | 84.54 | 24.18 | 25.28 | 0 | 134 | 84.54 | 24.18 | 25.28 | 0 | 134 | 33.13 | 60
64 | PASCHIM MEDINIPUR | SM/12203 | BIKRAMPUR PWSS | TSM/011638 | 40021624 | New | MVS | GO2223007259PH | 07/09/2022 | 423.71 | 38.05 | 461.76 | Midnapore Division | Midnapore Mechanical Division | 235.64 | 30.75 | 0 | 0 | 266.38 | 197.76 | 25.4 | 0 | 0 | 223.16 | 48.33 | 52
65 | PASCHIM MEDINIPUR | SM/14994 | BIRSINGPUR AND ADJOINING MOUJAS PWSS | TSM/015842 | 40033239 | New | MVS | GO2223013088PH | 04/02/2023 | 573.09 | 40.6 | 613.69 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 0 | 10.31 | 0 | 15.08 | 4.78 | 0 | 10.31 | 0 | 15.08 | 2.46 | 5
66 | PASCHIM MEDINIPUR | SM/13006 | BISHNUPUR AND ADJOINING MOUJAS PWSS | TSM/015042 | 40026204 | New | MVS | GO2223008407PH | 29/09/2022 | 288.29 | 36.08 | 324.37 | Midnapore Division | Jhargram Mechanical Division | 86.79 | 8.45 | 4.21 | 0 | 99.45 | 85.22 | 8.45 | 4.21 | 0 | 97.88 | 30.18 | 29
67 | PASCHIM MEDINIPUR | SM/17398 | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017562 | 40053739 | New | MVS | GO2223016350PH | 15/03/2023 | 883.57 | 79.89 | 963.46 | Midnapore Division | Midnapore Mechanical Division | 0.57 | 0 | 37.96 | 0 | 38.53 | 0.57 | 0 | 37.96 | 0 | 38.53 | 4 | 20
68 | PASCHIM MEDINIPUR | SM/13051 | BRAHMAN KHALISA & ADJOINING MOUZAS | TSM/013158 | 40031783 | New | MVS | GO2223008499PH | 29/09/2022 | 397.22 | 38.28 | 435.5 | Midnapore Division | Midnapore Mechanical Division | 16.15 | 7.35 | 10.59 | 12.32 | 46.41 | 0 | 7.35 | 10.59 | 12.32 | 30.26 | 6.95 | 8
69 | PASCHIM MEDINIPUR | SM/12384 | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | TSM/013157 | 40024222 | New | MVS | GO2223007524PH | 13/09/2022 | 484.4 | 37.89 | 522.3 | Midnapore Division | Midnapore Mechanical Division | 254.4 | 11.76 | 27.33 | 0 | 293.49 | 251.01 | 3.55 | 27.33 | 0 | 281.89 | 53.97 | 1
70 | PASCHIM MEDINIPUR | SM/14031 | BULANPUR AND ADJOINING MOUJAS PWSS | TSM/015902 | 40035534 | New | MVS | GO2223010520PH | 05/12/2022 | 413.21 | 48.03 | 461.25 | Midnapore Division | Jhargram Mechanical Division | 82.41 | 16.89 | 6.79 | 17.43 | 123.52 | 74.09 | 16.89 | 6.79 | 17.43 | 115.2 | 24.98 | 25
71 | PASCHIM MEDINIPUR | SM/12410 | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS | TSM/013046 | 40024218 | New | MVS | GO2223007523PH | 13/09/2022 | 330.34 | 37.8 | 368.13 | Midnapore Division | Midnapore Mechanical Division | 211.68 | 22.27 | 30.43 | 0 | 264.38 | 163.58 | 22.27 | 30.43 | 0 | 216.27 | 58.75 | 70
72 | PASCHIM MEDINIPUR | SM/12411 | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS | TSM/013204 | 40024206 | New | MVS | GO2223007522PH | 13/09/2022 | 301.14 | 37.66 | 338.8 | Midnapore Division | Midnapore Mechanical Division | 56.02 | 10.08 | 25.03 | 0 | 91.12 | 56.02 | 10.08 | 25.03 | 0 | 91.12 | 26.89 | 15
73 | PASCHIM MEDINIPUR | SM/17615 | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS | TSM/011854 | 40033288 | New | MVS | GO2223017408PH | 21/03/2023 | 377.84 | 38.05 | 415.89 | Midnapore Division | Midnapore Mechanical Division | 40.67 | 23.02 | 8.48 | 0 | 72.17 | 40.67 | 23.02 | 8.48 | 0 | 72.17 | 17.35 | 3
74 | PASCHIM MEDINIPUR | SM/12412 | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | TSM/013111 | 40024200 | New | MVS | GO2223007521PH | 13/09/2022 | 405.61 | 37.83 | 443.43 | Midnapore Division | Midnapore Mechanical Division | 127.01 | 22.73 | 15.26 | 0 | 165 | 91.5 | 22.73 | 15.26 | 0 | 129.49 | 29.2 | 34
75 | PASCHIM MEDINIPUR | SM/14995 | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | TSM/016157 | 40035772 | New | MVS | GO2223013051PH | 04/02/2023 | 605.88 | 37.5 | 643.38 | Midnapore Division | Midnapore Mechanical Division | 250.08 | 28.04 | 0 | 0 | 278.12 | 250.08 | 28.04 | 0 | 0 | 278.12 | 43.23 | 70
76 | PASCHIM MEDINIPUR | SM/16259 | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | TSM/016102 | 40035763 | New | MVS | GO2223014869PH | 24/02/2023 | 573.02 | 41.42 | 614.44 | Midnapore Division | Midnapore Mechanical Division | 169.63 | 6.88 | 24.86 | 0 | 201.37 | 169.63 | 6.88 | 24.86 | 0 | 201.37 | 32.77 | 35
77 | PASCHIM MEDINIPUR | SM/14996 | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | TSM/016125 | 40035764 | New | MVS | GO2223013048PH | 04/02/2023 | 359.56 | 18.97 | 378.53 | Midnapore Division | Midnapore Mechanical Division | 26.78 | 5.77 | 6.31 | 0 | 38.85 | 26.78 | 5.77 | 6.31 | 0 | 38.85 | 10.26 | 35
78 | PASCHIM MEDINIPUR | SM/14997 | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015716 | 40034745 | New | MVS | GO2223013177PH | 04/02/2023 | 571.34 | 77.41 | 648.75 | Midnapore Division | Midnapore Mechanical Division | 17.26 | 29.08 | 0 | 0 | 46.34 | 17.26 | 29.08 | 0 | 0 | 46.34 | 7.14 | 27
79 | PASCHIM MEDINIPUR | SM/13054 | CHANDABILA & ADJOINING MOUJAS PWSS | TSM/013387 | 40031792 | New | MVS | GO2223008500PH | 29/09/2022 | 362.88 | 36.34 | 399.22 | Midnapore Division | Jhargram Mechanical Division | 204.26 | 10.44 | 6.45 | 15.23 | 236.38 | 179.52 | 10.44 | 6.45 | 15.23 | 211.65 | 53.01 | 53
80 | PASCHIM MEDINIPUR | SM/13074 | CHANDANA AND ADJOINING MOUJAS PWSS | TSM/014627 | 40029840 | New | MVS | GO2223008469PH | 29/09/2022 | 310.43 | 36.8 | 347.23 | Midnapore Division | Midnapore Mechanical Division | 69.49 | 13.92 | 6.74 | 20.34 | 110.48 | 69.49 | 11.02 | 6.74 | 20.34 | 107.59 | 30.98 | 45
81 | PASCHIM MEDINIPUR | SM/14998 | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017443 | 40034656 | New | MVS | GO2223013152PH | 04/02/2023 | 198.36 | 37.91 | 236.26 | Midnapore Division | Midnapore Mechanical Division | 7.37 | 0 | 0 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 7.37 | 3.12 | 15
82 | PASCHIM MEDINIPUR | SM/13007 | CHHATNI AND ADJOINING MOUJAS PWSS | TSM/015014 | 40026227 | New | MVS | GO2223008412PH | 29/09/2022 | 249.44 | 35.6 | 285.05 | Midnapore Division | Jhargram Mechanical Division | 44.34 | 0 | 3.59 | 0 | 47.93 | 44.34 | 0 | 3.59 | 0 | 47.93 | 16.82 | 20
83 | PASCHIM MEDINIPUR | SM/13078 | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | TSM/014681 | 40026286 | New | MVS | GO2223008457PH | 29/09/2022 | 515.29 | 39.33 | 554.62 | Midnapore Division | Jhargram Mechanical Division | 180.62 | 8.83 | 10.08 | 14.53 | 214.07 | 180.62 | 8.83 | 10.08 | 14.53 | 214.07 | 38.6 | 30
84 | PASCHIM MEDINIPUR | SM/18619 | CHOTA TARA AND ADJOINING MOUJAS PWSS | TSM/014555 | 40033370 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 948.37 | 74.76 | 1023.13 | Midnapore Division | Jhargram Mechanical Division | 72.23 | 15.71 | 75.56 | 4.65 | 168.15 | 72.23 | 15.71 | 75.56 | 4.65 | 168.15 | 16.44 | 25
85 | PASCHIM MEDINIPUR | SM/16202 | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | TSM/016000 | 40065396 | New | MVS | GO2223014804PH | 23/02/2023 | 502.93 | 0 | 502.93 | Midnapore Division | Midnapore Mechanical Division | 255.46 | 0 | 0 | 0 | 255.46 | 245.65 | 0 | 0 | 0 | 245.65 | 48.84 | 60
86 | PASCHIM MEDINIPUR | SM/12999 | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | TSM/014246 | 40026006 | New | MVS | GO2223008338PH | 28/09/2022 | 355.53 | 36.34 | 391.87 | Midnapore Division | Midnapore Mechanical Division | 9.86 | 29.81 | 12.39 | 0 | 52.06 | 9.86 | 29.81 | 12.39 | 0 | 52.06 | 13.28 | 50
87 | PASCHIM MEDINIPUR | SM/17004 | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | TSM/017512 | 40053744 | New | MVS | GO2223016499PH | 16/03/2023 | 788.53 | 38.79 | 827.32 | Midnapore Division | Midnapore Mechanical Division | 398.27 | 16.37 | 0 | 0 | 414.64 | 360.15 | 6.4 | 0 | 0 | 366.56 | 44.31 | 65
88 | PASCHIM MEDINIPUR | SM/13079 | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | TSM/014628 | 40029898 | New | MVS | GO2223008472PH | 29/09/2022 | 444.44 | 37.78 | 482.22 | Midnapore Division | Midnapore Mechanical Division | 126.13 | 25.24 | 9.36 | 19 | 179.73 | 126.13 | 5.94 | 9.36 | 19 | 160.42 | 33.27 | 60
89 | PASCHIM MEDINIPUR | SM/13008 | DAMODARPUR AND ADJOINING MOUJAS PWSS | TSM/014491 | 40026246 | New | MVS | GO2223008416PH | 29/09/2022 | 615.66 | 60.49 | 676.15 | Midnapore Division | Jhargram Mechanical Division | 133.12 | 0 | 24.18 | 0 | 157.3 | 133.12 | 0 | 24.18 | 0 | 157.3 | 23.26 | 20
90 | PASCHIM MEDINIPUR | SM/18524 | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | TSM/017371 | 40034448 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1071.57 | 42.81 | 1114.38 | Midnapore Division | Midnapore Mechanical Division | 209 | 15.1 | 0 | 0 | 224.1 | 209 | 15.1 | 0 | 0 | 224.1 | 20.11 | 31
91 | PASCHIM MEDINIPUR | SM/13000 | DHENGADAHA AND ADJOINING MOUJAS PWSS | TSM/014168 | 40025969 | New | MVS | GO2223008341PH | 28/09/2022 | 443.79 | 38.53 | 482.32 | Midnapore Division | Jhargram Mechanical Division | 183.28 | 12.3 | 24.21 | 13.07 | 232.87 | 183.28 | 12.3 | 24.21 | 13.07 | 232.87 | 48.28 | 34
92 | PASCHIM MEDINIPUR | SM/16374 | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | TSM/017287 | 40035788 | New | MVS | GO2223014980PH | 28/02/2023 | 745.2 | 41.07 | 786.27 | Midnapore Division | Midnapore Mechanical Division | 249.15 | 19.02 | 0 | 0 | 268.17 | 246.67 | 19.02 | 0 | 0 | 265.69 | 33.79 | 65
93 | PASCHIM MEDINIPUR | SM/13140 | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | TSM/014165 | 40033887 | New | MVS | GO2223008651PH | 12/10/2022 | 655.04 | 40.25 | 695.29 | Midnapore Division | Jhargram Mechanical Division | 125.4 | 7.78 | 55.83 | 13.12 | 202.13 | 125.4 | 7.78 | 55.83 | 13.12 | 202.13 | 29.07 | 31
94 | PASCHIM MEDINIPUR | SM/17005 | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | TSM/018441 | 40053727 | New | MVS | GO2223016504PH | 16/03/2023 | 694.35 | 79.57 | 773.92 | Midnapore Division | Midnapore Mechanical Division | 221.57 | 8.75 | 9.27 | 0 | 239.59 | 221.57 | 8.18 | 9.27 | 0 | 239.01 | 30.88 | 75
95 | PASCHIM MEDINIPUR | SM/12828 | DINGAL AND ITS ADJOINING MOUJAS PWSS | TSM/011799 | 40024541 | New | MVS | GO2223008116PH | 22/09/2022 | 439.41 | 38.14 | 477.55 | Midnapore Division | Midnapore Mechanical Division | 246.84 | 23.1 | 36.57 | 0 | 306.51 | 246.84 | 23.1 | 36.57 | 0 | 306.51 | 64.18 | 48
96 | PASCHIM MEDINIPUR | SM/14646 | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017444 | 40034780 | New | MVS | GO2223012712PH | 31/01/2023 | 441.94 | 76.3 | 518.24 | Midnapore Division | Midnapore Mechanical Division | 2.66 | 0 | 0 | 0 | 2.66 | 2.66 | 0 | 0 | 0 | 2.66 | 0.51 | 3
97 | PASCHIM MEDINIPUR | SM/15589 | DOSATINA AND ITS ADJOINING MOUZAS PWSS | TSM/017367 | 40044668 | New | MVS | GO2223013897PH | 15/02/2023 | 936.82 | 42.81 | 979.63 | Midnapore Division | Midnapore Mechanical Division | 492.5 | 30.19 | 19.76 | 0 | 542.45 | 492.5 | 24.94 | 19.76 | 0 | 537.2 | 54.84 | 54
98 | PASCHIM MEDINIPUR | SM/17616 | DUAN-II AND ITS ADJOINING MOUJAS PWSS | TSM/011845 | 40033286 | New | MVS | GO2223017409PH | 21/03/2023 | 499.79 | 38.14 | 537.93 | Midnapore Division | Midnapore Mechanical Division | 315.4 | 24.69 | 26.14 | 0 | 366.24 | 315.4 | 24.69 | 26.14 | 0 | 366.24 | 68.08 | 65
99 | PASCHIM MEDINIPUR | SM/18533 | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | TSM/016524 | 40035880 | New | MVS | 2052/PHE-28011/223/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1034.17 | 52.78 | 1086.95 | Midnapore Division | Midnapore Mechanical Division | 514.73 | 26.71 | 19.57 | 0 | 561 | 514.73 | 26.71 | 19.57 | 0 | 561 | 51.61 | 40
100 | PASCHIM MEDINIPUR | SM/13080 | DUDHE BUDE AND ADJOINING MOUJAS PWSS | TSM/014626 | 40026295 | New | MVS | GO2223008459PH | 29/09/2022 | 661.31 | 37.98 | 699.28 | Midnapore Division | Midnapore Mechanical Division | 148.75 | 15.79 | 15.24 | 21.31 | 201.09 | 148.75 | 6.98 | 15.24 | 21.31 | 192.27 | 27.5 | 60
101 | PASCHIM MEDINIPUR | SM/14645 | DUKI AND ADJOINING MOUJAS PWSS | TSM/017109 | 40033275 | New | MVS | GO2223012737PH | 31/01/2023 | 562.22 | 57.41 | 619.63 | Midnapore Division | Jhargram Mechanical Division | 100.62 | 10.01 | 43.01 | 12.77 | 166.41 | 100.62 | 10.01 | 43.01 | 12.77 | 166.41 | 26.86 | 20
102 | PASCHIM MEDINIPUR | SM/14032 | DUMURIA AND ADJOINING MOUJAS PWSS | TSM/015808 | 40035413 | New | MVS | GO2223010499PH | 05/12/2022 | 678.36 | 66.16 | 744.52 | Midnapore Division | Jhargram Mechanical Division | 26.69 | 8.54 | 12.12 | 0 | 47.36 | 26.69 | 8.54 | 12.12 | 0 | 47.36 | 6.36 | 20
103 | PASCHIM MEDINIPUR | SM/13009 | DURIA AND ADJOINING MOUJAS PWSS | TSM/014268 | 40026208 | New | MVS | GO2223008411PH | 29/09/2022 | 698.67 | 40.25 | 738.92 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 7.3 | 0 | 0 | 12.08 | 4.78 | 7.3 | 0 | 0 | 12.08 | 1.64 | 30
104 | PASCHIM MEDINIPUR | SM/14999 | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015715 | 40034653 | New | MVS | GO2223013156PH | 04/02/2023 | 531.96 | 78.37 | 610.33 | Midnapore Division | Midnapore Mechanical Division | 252.95 | 25.17 | 14.75 | 0 | 292.87 | 211.16 | 25.17 | 14.75 | 0 | 251.08 | 41.14 | 79
105 | PASCHIM MEDINIPUR | SM/13081 | ELUNI PIPED WATER SUPPLY SCHEME | TSM/014921 | 40026280 | New | MVS | GO2223008449PH | 29/09/2022 | 588.63 | 37.58 | 626.21 | Midnapore Division | Midnapore Mechanical Division | 209.04 | 20.31 | 0 | 0 | 229.35 | 59.33 | 20.31 | 0 | 0 | 79.64 | 12.72 | 32
106 | PASCHIM MEDINIPUR | SM/13062 | FATEHSINGPUR AND ADJOINING MOUJAS PWSS | TSM/013503 | 40031723 | New | MVS | GO2223008495PH | 29/09/2022 | 338.63 | 36.34 | 374.97 | Midnapore Division | Jhargram Mechanical Division | 81.54 | 3.4 | 20.66 | 16.03 | 121.62 | 51.45 | 3.4 | 20.66 | 16.03 | 91.54 | 24.41 | 30
107 | PASCHIM MEDINIPUR | SM/13082 | GAGANESHWAR AND ADJOINING MOUJAS PWSS | TSM/014662 | 40029791 | New | MVS | GO2223008461PH | 29/09/2022 | 848 | 55.39 | 903.4 | Midnapore Division | Midnapore Mechanical Division | 267.89 | 21.14 | 15.68 | 21.25 | 325.96 | 267.89 | 21.14 | 15.68 | 21.25 | 325.96 | 36.08 | 45
108 | PASCHIM MEDINIPUR | SM/13010 | GAHIRA AND ADJOINING MOUJAS PWSS | TSM/014271 | 40026243 | New | MVS | GO2223008415PH | 29/09/2022 | 458.93 | 38.61 | 497.53 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 6.29 | 0 | 0 | 11.07 | 4.78 | 6.29 | 0 | 0 | 11.07 | 2.22 | 5
109 | PASCHIM MEDINIPUR | SM/13083 | GAMA AND ADJOINING MOUJAS PWSS | TSM/014270 | 40026300 | New | MVS | GO2223008460PH | 29/09/2022 | 545.23 | 36.72 | 581.95 | Midnapore Division | Midnapore Mechanical Division | 194.11 | 6.86 | 1.26 | 13.12 | 215.35 | 194.11 | 6.86 | 1.26 | 13.12 | 215.35 | 37 | 40
110 | PASCHIM MEDINIPUR | SM/13141 | GAMARIA PIPED WATER SUPPLY SCHEME | TSM/013580 | 40034356 | New | MVS | GO2223008648PH | 12/10/2022 | 766.27 | 38.18 | 804.45 | Midnapore Division | Midnapore Mechanical Division | 205.02 | 19.12 | 0 | 0 | 224.14 | 205.02 | 19.12 | 0 | 0 | 224.14 | 27.86 | 42
111 | PASCHIM MEDINIPUR | SM/19099 | GANGANI AND ADJOINING MOUJAS PWSS | TSM/015823 | 40033429 | New | MVS | 3714/PHE-28011/267/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1332.65 | 78.62 | 1411.27 | Midnapore Division | Jhargram Mechanical Division | 1.3 | 7.79 | 28.37 | 19.29 | 56.76 | 1.3 | 7.79 | 28.37 | 19.29 | 56.76 | 4.02 | 20
112 | PASCHIM MEDINIPUR | SM/15000 | GANUA AND ADJOINING MOUJAS PWSS | TSM/015980 | 40034061 | New | MVS | GO2223013049PH | 04/02/2023 | 831.9 | 39.84 | 871.74 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
113 | PASCHIM MEDINIPUR | SM/14090 | GARMAL AND ADJOINING MOUJAS PWSS | TSM/015815 | 40035625 | New | MVS | GO2223010860PH | 12/12/2022 | 419.88 | 62.37 | 482.26 | Midnapore Division | Jhargram Mechanical Division | 7.62 | 14.34 | 5.84 | 0 | 27.8 | 0 | 14.34 | 5.84 | 0 | 20.18 | 4.18 | 30
114 | PASCHIM MEDINIPUR | SM/13084 | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS | TSM/014325 | 40029837 | New | MVS | GO2223008463PH | 29/09/2022 | 602.36 | 40.04 | 642.4 | Midnapore Division | Midnapore Mechanical Division | 289.67 | 6.61 | 1.71 | 0 | 297.99 | 266.39 | 3.7 | 1.71 | 0 | 271.8 | 42.31 | 75
115 | PASCHIM MEDINIPUR | SM/14647 | GHAGRASOL AND ADJOINING MOUJAS PWSS | TSM/016783 | 40035614 | New | MVS | GO2223012729PH | 31/01/2023 | 61.42 | 1.71 | 63.13 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 11.17 | 11.17 | 0 | 0 | 0 | 11.17 | 11.17 | 17.7 | 16
116 | PASCHIM MEDINIPUR | SM/18535 | GHOSHPUR PIPED WATER SUPPLY SCHEME | TSM/013511 | 40034439 | New | MVS | 2054/PHE-28011/48/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1084.91 | 41.28 | 1126.19 | Midnapore Division | Midnapore Mechanical Division | 135.65 | 27.95 | 0 | 0 | 163.61 | 135.65 | 27.95 | 0 | 0 | 163.61 | 14.53 | 30
117 | PASCHIM MEDINIPUR | SM/14648 | GHRITAGRAM AND ADJOINING MOUJAS PWSS | TSM/016544 | 40034941 | New | MVS | GO2223012726PH | 31/01/2023 | 873.73 | 47.64 | 921.37 | Midnapore Division | Midnapore Mechanical Division | 180.07 | 21.58 | 1.71 | 20.3 | 223.66 | 180.07 | 21.58 | 1.71 | 20.3 | 223.66 | 24.27 | 55
118 | PASCHIM MEDINIPUR | SM/13142 | GILABANI AND ADJOINING MOUJAS PWSS | TSM/014180 | 40033758 | New | MVS | GO2223008650PH | 12/10/2022 | 647.9 | 40.25 | 688.15 | Midnapore Division | Jhargram Mechanical Division | 159.89 | 8.3 | 15.55 | 15.06 | 198.8 | 159.89 | 8.3 | 15.55 | 15.06 | 198.8 | 28.89 | 40
119 | PASCHIM MEDINIPUR | SM/10066 | Gobindanagar Piped Water Supply Scheme | TSM/005229 | 40006618 | New | MVS | GO2122008790PH | 27/01/2022 | 359.55 | 52.53 | 412.08 | Midnapore Division | Midnapore Mechanical Division | 317.52 | 30.38 | 8.38 | 6.19 | 362.47 | 317.52 | 27.79 | 8.38 | 6.19 | 359.88 | 87.33 | 78
120 | PASCHIM MEDINIPUR | SM/17620 | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013168 | 40033324 | New | MVS | GO2223017414PH | 21/03/2023 | 546.33 | 38.28 | 584.61 | Midnapore Division | Midnapore Mechanical Division | 302.14 | 27.69 | 8.83 | 0 | 338.66 | 282.84 | 27.69 | 8.83 | 0 | 319.36 | 54.63 | 70
121 | PASCHIM MEDINIPUR | SM/13077 | GODAPIASOL AND ADJOINING MOUJAS PWSS | TSM/014977 | 40029851 | New | MVS | GO2223008471PH | 29/09/2022 | 316.81 | 36.02 | 352.83 | Midnapore Division | Jhargram Mechanical Division | 58.75 | 6.76 | 5.15 | 11.92 | 82.58 | 58.75 | 6.76 | 5.15 | 11.92 | 82.58 | 23.41 | 42
122 | PASCHIM MEDINIPUR | SM/15004 | GOHALDANGA AND ADJOINING MOUJAS PWSS | TSM/016065 | 40035498 | New | MVS | GO2223013047PH | 04/02/2023 | 559.61 | 48.23 | 607.84 | Midnapore Division | Jhargram Mechanical Division | 202.63 | 24.1 | 9.47 | 13.12 | 249.32 | 202.63 | 24.1 | 9.47 | 13.12 | 249.32 | 41.02 | 60
123 | PASCHIM MEDINIPUR | SM/14649 | GOKULPUR AND ADJOINING MOUJAS PWSS | TSM/016187 | 40034049 | New | MVS | GO2223012711PH | 31/01/2023 | 590.98 | 55.45 | 646.43 | Midnapore Division | Midnapore Mechanical Division | 83.94 | 12.19 | 32.6 | 13.03 | 141.77 | 83.94 | 12.19 | 32.6 | 13.03 | 141.77 | 21.93 | 1
124 | PASCHIM MEDINIPUR | SM/17617 | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | TSM/011835 | 40033317 | New | MVS | GO2223017411PH | 21/03/2023 | 642 | 38.24 | 680.25 | Midnapore Division | Midnapore Mechanical Division | 221.42 | 16.02 | 26.36 | 0 | 263.8 | 221.42 | 16.02 | 26.36 | 0 | 263.8 | 38.78 | 25
125 | PASCHIM MEDINIPUR | SM/18508 | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | TSM/014933 | 40034354 | New | MVS | 2042/PHE-28011/139/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1269.48 | 127.81 | 1397.29 | Midnapore Division | Midnapore Mechanical Division | 284.65 | 28.03 | 0 | 0 | 312.67 | 284.65 | 28.03 | 0 | 0 | 312.67 | 22.38 | 40
126 | PASCHIM MEDINIPUR | SM/19044 | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015587 | 40034917 | New | MVS | 3546/PHE-28011/198/2023-SCHM CELL-Dept. of PHE | 24/11/2023 | 1135.06 | 77.24 | 1212.3 | Midnapore Division | Midnapore Mechanical Division | 606.9 | 10.58 | 102.6 | 0 | 720.08 | 606.9 | 10.58 | 102.6 | 0 | 720.08 | 59.4 | 45
127 | PASCHIM MEDINIPUR | SM/12986 | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011810 | 40025997 | New | MVS | GO2223008330PH | 28/09/2022 | 383.93 | 37.89 | 421.82 | Midnapore Division | Midnapore Mechanical Division | 171.64 | 8.09 | 0 | 0 | 179.73 | 171.64 | 8.09 | 0 | 0 | 179.73 | 42.61 | 15
128 | PASCHIM MEDINIPUR | SM/07964 | Gopinathpur Piped Water Supply Scheme. | TSM/005703 | 8290938 | New | MVS | GO2021004404PH | 11/01/2021 | 616.81 | 36.39 | 653.2 | Midnapore Division | Midnapore Mechanical Division | 246.3 | 22.13 | 15.13 | 0 | 283.56 | 246.3 | 22.13 | 15.13 | 0 | 283.56 | 43.41 | 85
129 | PASCHIM MEDINIPUR | SM/14651 | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017439 | 40034982 | New | SVS | GO2223012714PH | 31/01/2023 | 439.03 | 77.41 | 516.44 | Midnapore Division | Midnapore Mechanical Division | 68.46 | 22.6 | 8.33 | 0 | 99.39 | 68.46 | 22.6 | 8.33 | 0 | 99.39 | 19.24 | 25
130 | PASCHIM MEDINIPUR | SM/15010 | GOTSHINGLA AND ADJOINING MOUJAS PWSS | TSM/016085 | 40035429 | New | MVS | GO2223013053PH | 04/02/2023 | 294.27 | 36.76 | 331.03 | Midnapore Division | Jhargram Mechanical Division | 72.94 | 3.68 | 0 | 0 | 76.61 | 72.94 | 3.68 | 0 | 0 | 76.61 | 23.14 | 31
131 | PASCHIM MEDINIPUR | SM/13076 | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | TSM/014580 | 40030026 | New | MVS | GO2223008489PH | 29/09/2022 | 892.61 | 39.41 | 932.03 | Midnapore Division | Midnapore Mechanical Division | 178.57 | 8.23 | 24.8 | 14.06 | 225.66 | 178.57 | 8.23 | 24.8 | 14.06 | 225.66 | 24.21 | 18
132 | PASCHIM MEDINIPUR | SM/11858 | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009250 | 40018793 | New | SVS | GO2223006396PH | 17/08/2022 | 104.18 | 15.07 | 119.24 | Midnapore Division | Midnapore Mechanical Division | 81.79 | 11.7 | 0 | 0 | 93.49 | 81.79 | 11.7 | 0 | 0 | 93.49 | 78.4 | 100
133 | PASCHIM MEDINIPUR | SM/10648 | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009245 | 40033734 | New | SVS | GO2223000499PH | 22/04/2022 | 95.7 | 15.07 | 110.76 | Midnapore Division | Midnapore Mechanical Division | 73.75 | 11.16 | 0 | 0 | 84.9 | 73.75 | 11.16 | 0 | 0 | 84.9 | 76.65 | 100
134 | PASCHIM MEDINIPUR | SM/09681 | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008458 | 40002530 | New | SVS | GO2122005818PH | 24/11/2021 | 208.84 | 30.13 | 238.97 | Midnapore Division | Midnapore Mechanical Division | 187.66 | 26.45 | 5.54 | 0 | 219.65 | 187.66 | 26.45 | 5.54 | 0 | 219.65 | 91.92 | 100
135 | PASCHIM MEDINIPUR | SM/09441 | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | TSM/008114 | 40002283 | New | SVS | GO2122004669PH | 29/10/2021 | 32.59 | 7.53 | 40.12 | Midnapore Division | Midnapore Mechanical Division | 30.83 | 4.38 | 0 | 0 | 35.22 | 30.83 | 4.38 | 0 | 0 | 35.22 | 87.78 | 100
136 | PASCHIM MEDINIPUR | SM/10649 | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | TSM/010638 | 40014397 | New | MVS | GO2223000500PH | 22/04/2022 | 796.7 | 53.14 | 849.85 | Midnapore Division | Midnapore Mechanical Division | 342.24 | 27.43 | 49.61 | 17.71 | 436.99 | 342.24 | 27.43 | 49.61 | 17.71 | 436.99 | 51.42 | 70
137 | PASCHIM MEDINIPUR | SM/10658 | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | TSM/009246 | 40014735 | New | SVS | GO2223000514PH | 22/04/2022 | 88.51 | 15.07 | 103.58 | Midnapore Division | Midnapore Mechanical Division | 65.92 | 13.29 | 0 | 0 | 79.21 | 65.92 | 13.28 | 0 | 0 | 79.2 | 76.47 | 100
138 | PASCHIM MEDINIPUR | SM/17008 | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | TSM/017509 | 40054163 | New | SVS | GO2223016502PH | 16/03/2023 | 34.57 | 7.94 | 42.51 | Midnapore Division | Jhargram Mechanical Division | 27.57 | 0 | 0 | 0 | 27.57 | 27.57 | 0 | 0 | 0 | 27.57 | 64.86 | 100
139 | PASCHIM MEDINIPUR | SM/10003 | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | TSM/009189 | 40008706 | New | SVS | GO2122007167PH | 22/12/2021 | 180.95 | 30.13 | 211.08 | Midnapore Division | Midnapore Mechanical Division | 143.36 | 21.29 | 4.04 | 0 | 168.68 | 143.36 | 21.29 | 4.04 | 0 | 168.68 | 79.91 | 100
140 | PASCHIM MEDINIPUR | SM/09439 | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | TSM/008113 | 40004888 | New | SVS | GO2122004669PH | 29/10/2021 | 38.41 | 7.53 | 45.94 | Midnapore Division | Midnapore Mechanical Division | 36.16 | 4.13 | 0 | 0 | 40.29 | 36.16 | 4 | 0 | 0 | 40.16 | 87.42 | 100
141 | PASCHIM MEDINIPUR | SM/09682 | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | TSM/008457 | 40004872 | New | SVS | GO2122005818PH | 24/11/2021 | 27.42 | 7.53 | 34.95 | Midnapore Division | Midnapore Mechanical Division | 23.72 | 6.8 | 0.67 | 0 | 31.19 | 23.72 | 6.67 | 0.67 | 0 | 31.06 | 88.87 | 100
142 | PASCHIM MEDINIPUR | SM/15220 | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009243 | 40032889 | New | SVS | GO2223013466PH | 07/02/2023 | 97.27 | 15.07 | 112.33 | Midnapore Division | Midnapore Mechanical Division | 74.66 | 10.72 | 0 | 0 | 85.37 | 73.32 | 10.72 | 0 | 0 | 84.03 | 74.81 | 100
143 | PASCHIM MEDINIPUR | SM/09680 | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008463 | 40004710 | New | SVS | GO2122005818PH | 24/11/2021 | 41.27 | 7.53 | 48.8 | Midnapore Division | Midnapore Mechanical Division | 39.03 | 6.66 | 1.04 | 0 | 46.73 | 37.65 | 6.66 | 1.04 | 0 | 45.35 | 92.93 | 100
144 | PASCHIM MEDINIPUR | SM/10655 | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009249 | 40014743 | New | SVS | GO2223000510PH | 22/04/2022 | 95.03 | 15.07 | 110.1 | Midnapore Division | Midnapore Mechanical Division | 73.72 | 11.93 | 0 | 0 | 85.65 | 73.72 | 11.77 | 0 | 0 | 85.49 | 77.65 | 100
145 | PASCHIM MEDINIPUR | SM/09684 | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008448 | 40002463 | New | MVS | GO2122005818PH | 24/11/2021 | 49.75 | 7.53 | 57.28 | Midnapore Division | Midnapore Mechanical Division | 45.59 | 6.92 | 1.27 | 0 | 53.78 | 45.59 | 6.92 | 1.27 | 0 | 53.78 | 93.88 | 80
146 | PASCHIM MEDINIPUR | SM/10717 | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009248 | 40014749 | New | SVS | GO2223002123PH | 18/05/2022 | 48.56 | 7.53 | 56.09 | Midnapore Division | Midnapore Mechanical Division | 32.63 | 6.1 | 0 | 0 | 38.73 | 23.18 | 6.1 | 0 | 0 | 29.27 | 52.19 | 76
147 | PASCHIM MEDINIPUR | SM/09675 | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008487 | 40005314 | New | MVS | GO2122005818PH | 24/11/2021 | 56.64 | 15.07 | 71.71 | Midnapore Division | Midnapore Mechanical Division | 41.9 | 14.42 | 1.3 | 0 | 57.63 | 41.9 | 14.42 | 1.3 | 0 | 57.63 | 80.37 | 99
148 | PASCHIM MEDINIPUR | SM/09677 | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | TSM/008478 | 40005295 | New | SVS | GO2122005818PH | 24/11/2021 | 29.96 | 7.53 | 37.49 | Midnapore Division | Midnapore Mechanical Division | 21.88 | 6.52 | 0.58 | 0 | 28.98 | 21.88 | 6.52 | 0.58 | 0 | 28.98 | 77.3 | 100
149 | PASCHIM MEDINIPUR | SM/18785 | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur | TSM/009247 | 40048958 | New | SVS | PHE/IV/2608/W-641/23 | 29/08/2023 | 37.34 | 7.53 | 44.88 | Midnapore Division | Midnapore Mechanical Division | 19.83 | 0.1 | 0 | 0 | 19.93 | 17.7 | 0.1 | 0 | 0 | 17.8 | 39.67 | 85
150 | PASCHIM MEDINIPUR | SM/10002 | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | TSM/009187 | 40008696 | New | SVS | GO2122007167PH | 22/12/2021 | 85.48 | 15.07 | 100.55 | Midnapore Division | Midnapore Mechanical Division | 61.58 | 11.13 | 1.64 | 0 | 74.34 | 60.6 | 11.13 | 1.64 | 0 | 73.37 | 72.97 | 100
151 | PASCHIM MEDINIPUR | SM/09679 | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008475 | 40005301 | New | SVS | GO2122005818PH | 24/11/2021 | 23.47 | 7.53 | 31 | Midnapore Division | Midnapore Mechanical Division | 20.73 | 4.1 | 0.31 | 0 | 25.14 | 20.73 | 4.1 | 0.31 | 0 | 25.14 | 81.11 | 100
152 | PASCHIM MEDINIPUR | SM/09442 | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas | TSM/008115 | 40002331 | New | SVS | GO2122004669PH | 29/10/2021 | 36.2 | 7.53 | 43.73 | Midnapore Division | Midnapore Mechanical Division | 34.89 | 6.64 | 0 | 0 | 41.53 | 34.89 | 6.51 | 0 | 0 | 41.4 | 94.68 | 100
153 | PASCHIM MEDINIPUR | SM/09683 | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008454 | 40002349 | New | SVS | GO2122005818PH | 24/11/2021 | 101.39 | 15.07 | 116.45 | Midnapore Division | Midnapore Mechanical Division | 94.52 | 12.94 | 2.92 | 0 | 110.37 | 94.52 | 12.94 | 2.92 | 0 | 110.37 | 94.78 | 100
154 | PASCHIM MEDINIPUR | SM/09676 | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008479 | 40002347 | New | SVS | GO2122005818PH | 24/11/2021 | 43.95 | 7.53 | 51.48 | Midnapore Division | Midnapore Mechanical Division | 41.28 | 4 | 1.39 | 0 | 46.67 | 41.28 | 4 | 1.39 | 0 | 46.67 | 90.65 | 100
155 | PASCHIM MEDINIPUR | SM/10657 | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009244 | 40014394 | New | SVS | GO2223000516PH | 22/04/2022 | 142.86 | 22.6 | 165.46 | Midnapore Division | Midnapore Mechanical Division | 81.42 | 11.68 | 0 | 0 | 93.1 | 81.42 | 11.68 | 0 | 0 | 93.1 | 56.27 | 76
156 | PASCHIM MEDINIPUR | SM/09440 | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | TSM/008112 | 40004859 | New | SVS | GO2122004669PH | 29/10/2021 | 39.79 | 7.53 | 47.32 | Midnapore Division | Midnapore Mechanical Division | 29.45 | 6.67 | 0 | 0 | 36.13 | 29.45 | 7.82 | 0 | 0 | 37.27 | 78.76 | 100
157 | PASCHIM MEDINIPUR | SM/09678 | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008476 | 40002471 | New | SVS | GO2122005818PH | 24/11/2021 | 76.56 | 15.07 | 91.62 | Midnapore Division | Midnapore Mechanical Division | 70.75 | 13.17 | 1.93 | 0 | 85.85 | 70.75 | 12.92 | 1.93 | 0 | 85.6 | 93.42 | 100
158 | PASCHIM MEDINIPUR | SM/09795 | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008489 | 40003746 | New | SVS | GO2122006297PH | 01/12/2021 | 116.29 | 0 | 116.29 | Midnapore Division | Midnapore Mechanical Division | 96.35 | 0 | 2.28 | 0 | 98.63 | 96.35 | 0 | 2.28 | 0 | 98.63 | 84.82 | 100
159 | PASCHIM MEDINIPUR | SM/19049 | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017678 | 40043840 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1255.39 | 167.97 | 1423.36 | Midnapore Division | Midnapore Mechanical Division | 260.73 | 67.72 | 0 | 0 | 328.45 | 260.73 | 61 | 0 | 0 | 321.73 | 22.6 | 38
160 | PASCHIM MEDINIPUR | SM/15533 | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015517 | 40034848 | New | MVS | GO2223013987PH | 16/02/2023 | 1528.77 | 151.48 | 1680.25 | Midnapore Division | Midnapore Mechanical Division | 307.17 | 79.9 | 7.03 | 0 | 394.09 | 305.65 | 79.9 | 7.03 | 0 | 392.57 | 23.36 | 48
161 | PASCHIM MEDINIPUR | SM/18622 | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | TSM/012901 | 40034716 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1264.55 | 106.28 | 1370.84 | Midnapore Division | Midnapore Mechanical Division | 317.71 | 22.48 | 0 | 0 | 340.19 | 210.62 | 22.48 | 0 | 0 | 233.1 | 17 | 29
162 | PASCHIM MEDINIPUR | SM/19053 | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017559 | 40044206 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1376.89 | 127.85 | 1504.74 | Midnapore Division | Midnapore Mechanical Division | 111.73 | 63.43 | 21.29 | 0 | 196.45 | 111.73 | 56.64 | 21.29 | 0 | 189.66 | 12.6 | 70
163 | PASCHIM MEDINIPUR | SM/18539 | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020284 | 40053751 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1200.51 | 111.98 | 1312.49 | Midnapore Division | Midnapore Mechanical Division | 6.81 | 35.64 | 31.98 | 0 | 74.43 | 6.81 | 35.64 | 31.98 | 0 | 74.43 | 5.67 | 3
164 | PASCHIM MEDINIPUR | SM/12875 | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | TSM/011782 | 40024617 | New | MVS | GO2223008168PH | 23/09/2022 | 1343.8 | 106.28 | 1450.08 | Midnapore Division | Midnapore Mechanical Division | 336.07 | 64.19 | 0 | 0 | 400.25 | 336.07 | 64.19 | 0 | 0 | 400.25 | 27.6 | 41
165 | PASCHIM MEDINIPUR | SM/17558 | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020257 | 40054155 | New | MVS | GO2223017029PH | 18/03/2023 | 529.05 | 55.99 | 585.04 | Midnapore Division | Midnapore Mechanical Division | 0 | 19.97 | 9.07 | 0 | 29.04 | 0 | 19.97 | 9.07 | 0 | 29.04 | 4.96 | 14
166 | PASCHIM MEDINIPUR | SM/19102 | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | TSM/013481 | 40034767 | New | MVS | 3715/PHE-28011/265/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1335.41 | 113.82 | 1449.22 | Midnapore Division | Midnapore Mechanical Division | 132.61 | 31.55 | 0 | 0 | 164.16 | 132.61 | 26.85 | 0 | 0 | 159.46 | 11 | 42
167 | PASCHIM MEDINIPUR | SM/19048 | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017300 | 40044543 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1051.16 | 111.98 | 1163.14 | Midnapore Division | Midnapore Mechanical Division | 224.4 | 16.54 | 0 | 0 | 240.94 | 224.4 | 16.54 | 0 | 0 | 240.94 | 20.71 | 75
168 | PASCHIM MEDINIPUR | SM/18621 | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | TSM/012657 | 40034735 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1659.55 | 121.35 | 1780.9 | Midnapore Division | Midnapore Mechanical Division | 0 | 29.34 | 1.31 | 0 | 30.66 | 0 | 24.47 | 1.31 | 0 | 25.78 | 1.45 | 20
169 | PASCHIM MEDINIPUR | SM/14483 | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015079 | 40035690 | New | MVS | GO2223012272PH | 20/01/2023 | 991.62 | 121.35 | 1112.97 | Midnapore Division | Midnapore Mechanical Division | 340.82 | 43 | 21.96 | 0 | 405.78 | 336.2 | 43 | 21.96 | 0 | 401.17 | 36.04 | 50
170 | PASCHIM MEDINIPUR | SM/11622 | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | TSM/011566 | 40017903 | New | MVS | GO2223005555PH | 26/07/2022 | 848.95 | 53.14 | 902.09 | Midnapore Division | Midnapore Mechanical Division | 234.7 | 35.01 | 26.78 | 0 | 296.49 | 234.7 | 35.01 | 26.78 | 0 | 296.49 | 32.87 | 65
171 | PASCHIM MEDINIPUR | SM/14492 | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/016252 | 40035316 | New | MVS | GO2223012354PH | 20/01/2023 | 741.75 | 79.8 | 821.55 | Midnapore Division | Midnapore Mechanical Division | 402.25 | 43.48 | 2.7 | 0 | 448.43 | 402.25 | 43.48 | 2.7 | 0 | 448.43 | 54.58 | 75
172 | PASCHIM MEDINIPUR | SM/18758 | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | TSM/012658 | 40036188 | New | MVS | 2525/PHE/IV/W-638/23 | 23/08/2023 | 759.63 | 53.14 | 812.77 | Midnapore Division | Midnapore Mechanical Division | 0 | 13.36 | 22.44 | 0 | 35.8 | 0 | 13.36 | 22.44 | 0 | 35.8 | 4.4 | 10
173 | PASCHIM MEDINIPUR | SM/11879 | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | TSM/011673 | 40018787 | New | MVS | GO2223006377PH | 17/08/2022 | 589.43 | 53.14 | 642.57 | Midnapore Division | Midnapore Mechanical Division | 140.73 | 21.17 | 0 | 0 | 161.9 | 140.73 | 21.17 | 0 | 0 | 161.9 | 25.2 | 37
174 | PASCHIM MEDINIPUR | SM/18192 | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017301 | 40053813 | New | MVS | GO2223018115PH | 31/03/2023 | 494.2 | 71.86 | 566.06 | Midnapore Division | Midnapore Mechanical Division | 14.67 | 30.45 | 12.19 | 0 | 57.31 | 14.67 | 30.45 | 12.19 | 0 | 57.31 | 10.12 | 25
175 | PASCHIM MEDINIPUR | SM/15590 | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/018412 | 40043813 | New | MVS | GO2223013903PH | 15/02/2023 | 174.37 | 23.81 | 198.18 | Midnapore Division | Midnapore Mechanical Division | 59.38 | 8.6 | 0 | 0 | 67.98 | 59.38 | 8.6 | 0 | 0 | 67.98 | 34.3 | 55
176 | PASCHIM MEDINIPUR | SM/19101 | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | TSM/012817 | 40034740 | New | MVS | 3715/PHE-28011/265/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1001.18 | 53.14 | 1054.32 | Midnapore Division | Midnapore Mechanical Division | 183.36 | 2.81 | 0 | 0 | 186.17 | 155.63 | 2.81 | 0 | 0 | 158.44 | 15.03 | 28
177 | PASCHIM MEDINIPUR | SM/18620 | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | TSM/013268 | 40034577 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1465.1 | 106.28 | 1571.38 | Midnapore Division | Midnapore Mechanical Division | 132.84 | 50.29 | 31.33 | 0 | 214.46 | 96.98 | 50.29 | 31.33 | 0 | 178.6 | 11.37 | 2
178 | PASCHIM MEDINIPUR | SM/18538 | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020283 | 40053752 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1351.07 | 111.98 | 1463.05 | Midnapore Division | Midnapore Mechanical Division | 10.78 | 35.66 | 40.09 | 0 | 86.53 | 10.78 | 35.66 | 40.09 | 0 | 86.53 | 5.91 | 2
179 | PASCHIM MEDINIPUR | SM/15257 | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015744 | 40035307 | New | MVS | GO2223013432PH | 07/02/2023 | 703.47 | 55.99 | 759.46 | Midnapore Division | Midnapore Mechanical Division | 561.48 | 21.47 | 1.2 | 0 | 584.15 | 561.48 | 21.47 | 1.2 | 0 | 584.15 | 76.92 | 98
180 | PASCHIM MEDINIPUR | SM/11623 | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | TSM/011567 | 40017916 | New | MVS | GO2223005584PH | 26/07/2022 | 578.78 | 53.14 | 631.92 | Midnapore Division | Midnapore Mechanical Division | 279.46 | 35.36 | 16.84 | 0 | 331.66 | 279.46 | 35.36 | 16.84 | 0 | 331.66 | 52.48 | 93
181 | PASCHIM MEDINIPUR | SM/11624 | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | TSM/011561 | 40017910 | New | MVS | GO2223005582PH | 26/07/2022 | 848.82 | 53.14 | 901.96 | Midnapore Division | Midnapore Mechanical Division | 340.74 | 30.27 | 35.73 | 0 | 406.73 | 340.74 | 30.27 | 35.73 | 0 | 406.73 | 45.09 | 86
182 | PASCHIM MEDINIPUR | SM/15591 | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017561 | 40044112 | New | MVS | GO2223013896PH | 15/02/2023 | 790.54 | 55.99 | 846.53 | Midnapore Division | Midnapore Mechanical Division | 375.63 | 23.71 | 34.16 | 0 | 433.5 | 375.63 | 23.71 | 34.16 | 0 | 433.5 | 51.21 | 80
183 | PASCHIM MEDINIPUR | SM/16262 | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/016251 | 40035711 | New | MVS | GO2223014805PH | 23/02/2023 | 777.46 | 95.67 | 873.13 | Midnapore Division | Midnapore Mechanical Division | 134.87 | 16.03 | 12.53 | 0 | 163.43 | 126.68 | 16.03 | 12.53 | 0 | 155.24 | 17.78 | 25
184 | PASCHIM MEDINIPUR | SM/18696 | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015743 | 40035003 | New | MVS | 2249/PHE-28011/172/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 956.86 | 71.86 | 1028.72 | Midnapore Division | Midnapore Mechanical Division | 103.91 | 46.02 | 60.88 | 0 | 210.81 | 75.88 | 46.02 | 60.88 | 0 | 182.77 | 17.77 | 20
185 | PASCHIM MEDINIPUR | SM/12876 | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. | TSM/011871 | 40024584 | New | MVS | GO2223008167PH | 23/09/2022 | 1417.93 | 106.28 | 1524.21 | Midnapore Division | Midnapore Mechanical Division | 339.65 | 37.63 | 0 | 0 | 377.28 | 339.65 | 37.63 | 0 | 0 | 377.28 | 24.75 | 38
186 | PASCHIM MEDINIPUR | SM/18171 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013342 | 40066260 | New | MVS | GO2223017902PH | 29/03/2023 | 914.61 | 84.47 | 999.09 | Midnapore Division | Jhargram Mechanical Division | 291.01 | 30.73 | 36.54 | 0 | 358.27 | 291.01 | 30.73 | 36.54 | 0 | 358.27 | 35.86 | 82
187 | PASCHIM MEDINIPUR | SM/18172 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013349 | 40066261 | New | MVS | GO2223017899PH | 29/03/2023 | 864.31 | 84.47 | 948.79 | Midnapore Division | Jhargram Mechanical Division | 384.14 | 37.73 | 15 | 0 | 436.87 | 384.14 | 37.73 | 15 | 0 | 436.87 | 46.04 | 75
188 | PASCHIM MEDINIPUR | SM/18173 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013346 | 40066262 | New | MVS | GO2223017900PH | 29/03/2023 | 730.56 | 84.47 | 815.03 | Midnapore Division | Jhargram Mechanical Division | 361.09 | 32.04 | 12.43 | 0 | 405.56 | 361.09 | 32.04 | 12.43 | 0 | 405.56 | 49.76 | 85
189 | PASCHIM MEDINIPUR | SM/18615 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013347 | 40066263 | New | MVS | 2159/PHE-28011/232/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 964.27 | 84.47 | 1048.75 | Midnapore Division | Jhargram Mechanical Division | 318.77 | 29.66 | 42.09 | 0 | 390.52 | 318.77 | 29.66 | 42.09 | 0 | 390.52 | 37.24 | 80
190 | PASCHIM MEDINIPUR | SM/18184 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013443 | 40032934 | New | MVS | GO2223018114PH | 31/03/2023 | 773.1 | 84.47 | 857.57 | Midnapore Division | Jhargram Mechanical Division | 0 | 22.82 | 18.85 | 0 | 41.67 | 0 | 22.82 | 18.85 | 0 | 41.67 | 4.86 | 35
191 | PASCHIM MEDINIPUR | SM/13053 | HARI PURA AND ADJOINING MOUJAS PWSS | TSM/014660 | 40029983 | New | MVS | GO2223008483PH | 29/09/2022 | 418.14 | 37.78 | 455.91 | Midnapore Division | Midnapore Mechanical Division | 87.21 | 14.69 | 10.6 | 0 | 112.5 | 87.21 | 14.69 | 10.6 | 0 | 112.5 | 24.68 | 21
192 | PASCHIM MEDINIPUR | SM/13085 | HARINASULI & ADJOINING MOUJAS PWSS | TSM/013388 | 40026272 | New | MVS | GO2223008448PH | 29/09/2022 | 578.97 | 40.37 | 619.34 | Midnapore Division | Jhargram Mechanical Division | 299.84 | 7.23 | 31.32 | 17.43 | 355.81 | 196.26 | 7.23 | 31.32 | 17.43 | 252.23 | 40.73 | 40
193 | PASCHIM MEDINIPUR | SM/15592 | HATKATA AND ITS ADJOINING MOUZAS PWSS | TSM/017354 | 40044770 | New | MVS | GO2223013888PH | 15/02/2023 | 865.21 | 42.81 | 908.02 | Midnapore Division | Midnapore Mechanical Division | 272.44 | 39.97 | 17.75 | 0 | 330.16 | 272.44 | 39.97 | 17.75 | 0 | 330.16 | 36.36 | 42
194 | PASCHIM MEDINIPUR | SM/15011 | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017445 | 40034696 | New | MVS | GO2223013154PH | 04/02/2023 | 198.87 | 37.91 | 236.77 | Midnapore Division | Midnapore Mechanical Division | 62.83 | 14.08 | 2.91 | 0 | 79.81 | 62.83 | 14.08 | 2.91 | 0 | 79.81 | 33.71 | 35
195 | PASCHIM MEDINIPUR | SM/07386 | IRPALA Piped Water Supply Scheme. | TSM/004506 | 8290871 | New | MVS | GO2021002983PH | 03/12/2020 | 689.48 | 39.41 | 728.89 | Midnapore Division | Midnapore Mechanical Division | 319.64 | 21.08 | 47.68 | 0 | 388.4 | 319.64 | 21.08 | 47.68 | 0 | 388.4 | 53.29 | 87
196 | PASCHIM MEDINIPUR | SM/18782 | Islampur Piped Water Supply Scheme. | TSM/004474 | 40026000 | New | MVS | PHE/IV/2605/W-642/23 | 29/08/2023 | 763.99 | 37.49 | 801.48 | Midnapore Division | Midnapore Mechanical Division | 0 | 26.17 | 28.43 | 0 | 54.6 | 0 | 26.17 | 28.43 | 0 | 54.6 | 6.81 | 20
197 | PASCHIM MEDINIPUR | SM/13143 | JADABBATI AND ADJOINING MOUJAS PWSS | TSM/014184 | 40033466 | New | MVS | GO2223008643PH | 12/10/2022 | 530.64 | 40.04 | 570.68 | Midnapore Division | Jhargram Mechanical Division | 160.68 | 11.68 | 36.68 | 15.11 | 224.15 | 160.68 | 11.68 | 36.68 | 15.11 | 224.15 | 39.28 | 40
198 | PASCHIM MEDINIPUR | SM/18583 | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | TSM/016526 | 40036024 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1231.08 | 42.92 | 1274.01 | Midnapore Division | Midnapore Mechanical Division | 494.48 | 28.67 | 127.15 | 0 | 650.31 | 482.87 | 28.67 | 127.15 | 0 | 638.69 | 50.13 | 55
199 | PASCHIM MEDINIPUR | SM/13055 | JAGARDANGA AND ADJOINING MOUJAS PWSS | TSM/014773 | 40031436 | New | MVS | GO2223008493PH | 29/09/2022 | 494.96 | 55.1 | 550.06 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 0 | 3.3 | 0 | 8.08 | 4.78 | 0 | 3.3 | 0 | 8.08 | 1.47 | 16
200 | PASCHIM MEDINIPUR | SM/13086 | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013106 | 40026284 | New | MVS | GO2223008450PH | 29/09/2022 | 390.22 | 37.94 | 428.16 | Midnapore Division | Midnapore Mechanical Division | 43.62 | 0 | 9.25 | 12 | 64.87 | 27.11 | 0 | 9.25 | 12 | 48.36 | 11.3 | 10
201 | PASCHIM MEDINIPUR | SM/13087 | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013120 | 40026256 | New | MVS | GO2223008444PH | 29/09/2022 | 709.66 | 38.16 | 747.82 | Midnapore Division | Midnapore Mechanical Division | 354.68 | 28.77 | 14.71 | 0 | 398.16 | 354.68 | 28.77 | 14.71 | 0 | 398.16 | 53.24 | 27
202 | PASCHIM MEDINIPUR | SM/13056 | JAMUNA AND ADJOINING MOUJAS PWSS | TSM/014383 | 40029905 | New | MVS | GO2223008477PH | 29/09/2022 | 474.4 | 38.53 | 512.93 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 3.87 | 11.01 | 0 | 19.66 | 4.78 | 3.87 | 11.01 | 0 | 19.66 | 3.83 | 26
203 | PASCHIM MEDINIPUR | SM/18786 | Jankapur Piped Water Supply Scheme. | TSM/006520 | 40032925 | New | MVS | PHE/IV/2609/W-640/23 | 29/08/2023 | 767.9 | 38.8 | 806.7 | Midnapore Division | Midnapore Mechanical Division | 100.92 | 6.51 | 11.72 | 7.55 | 126.7 | 100.92 | 6.51 | 11.72 | 7.55 | 126.7 | 15.71 | 12
204 | PASCHIM MEDINIPUR | SM/17559 | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017568 | 40053733 | New | MVS | GO2223017050PH | 18/03/2023 | 564.75 | 76.24 | 641 | Midnapore Division | Midnapore Mechanical Division | 227 | 25.5 | 9.68 | 0 | 262.18 | 205.09 | 25.5 | 9.68 | 0 | 240.27 | 37.48 | 55
205 | PASCHIM MEDINIPUR | SM/17560 | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017569 | 40053732 | New | MVS | GO2223017031PH | 18/03/2023 | 649.05 | 74.87 | 723.92 | Midnapore Division | Midnapore Mechanical Division | 237.68 | 27.48 | 36.82 | 0 | 301.99 | 237.68 | 27.48 | 36.82 | 0 | 301.99 | 41.72 | 60
206 | PASCHIM MEDINIPUR | SM/14652 | JHARBHANGA AND ADJOINING MOUJAS PWSS | TSM/015951 | 40035495 | New | MVS | GO2223012720PH | 31/01/2023 | 638.75 | 57.35 | 696.1 | Midnapore Division | Jhargram Mechanical Division | 293.08 | 6.79 | 11.59 | 15.27 | 326.73 | 293.08 | 6.79 | 11.59 | 15.27 | 326.73 | 46.94 | 45
207 | PASCHIM MEDINIPUR | SM/13806 | JHETA JAMBONI PIPED WATER SUPPLY SCHEME | TSM/015054 | 40034527 | New | MVS | GO2223009969PH | 22/11/2022 | 871.52 | 41.52 | 913.04 | Midnapore Division | Midnapore Mechanical Division | 90.08 | 15.34 | 0 | 0 | 105.42 | 14.82 | 9.22 | 0 | 0 | 24.04 | 2.63 | 25
208 | PASCHIM MEDINIPUR | SM/18188 | KADABANI AND ADJOINING MOUJAS PWSS | TSM/013999 | 40047060 | New | MVS | GO2223018189PH | 31/03/2023 | 262.78 | 36.17 | 298.95 | Midnapore Division | Jhargram Mechanical Division | 85.82 | 30.59 | 4.87 | 0 | 121.28 | 85.82 | 30.59 | 4.87 | 0 | 121.28 | 40.57 | 50
209 | PASCHIM MEDINIPUR | SM/13058 | KADAM BANDHI AND ADJOINING MOUJAS PWSS | TSM/014559 | 40031875 | New | MVS | GO2223008506PH | 29/09/2022 | 376.54 | 35.93 | 412.47 | Midnapore Division | Jhargram Mechanical Division | 158.31 | 15.85 | 5.5 | 13.03 | 192.7 | 122.91 | 15.85 | 5.5 | 13.03 | 157.29 | 38.13 | 35
210 | PASCHIM MEDINIPUR | SM/15012 | KADAM DIHA AND ADJOINING MOUJAS PWSS | TSM/015816 | 40033241 | New | MVS | GO2223013054PH | 04/02/2023 | 265.57 | 36.65 | 302.22 | Midnapore Division | Jhargram Mechanical Division | 65.42 | 12.28 | 12.09 | 10.54 | 100.34 | 65.42 | 12.28 | 12.09 | 10.54 | 100.34 | 33.2 | 33
211 | PASCHIM MEDINIPUR | SM/16620 | KADAMDIHA AND IT'S ADJOINING MOUJAS PWSS | TSM/017360 | 40036360 | New | MVS | GO2223015893PH | 14/03/2023 | 801.03 | 82.68 | 883.71 | Midnapore Division | Jhargram Mechanical Division | 16.03 | 0 | 0 | 2.46 | 18.49 | 16.03 | 0 | 0 | 2.46 | 18.49 | 2.09 | 11
212 | PASCHIM MEDINIPUR | SM/13144 | KADRA AND ADJOINING MOUJAS PWSS | TSM/014124 | 40033423 | New | MVS | GO2223008653PH | 12/10/2022 | 362.26 | 36.3 | 398.56 | Midnapore Division | Jhargram Mechanical Division | 182.31 | 13.2 | 43.71 | 13.03 | 252.25 | 182.31 | 13.2 | 43.71 | 13.03 | 252.25 | 63.29 | 45
213 | PASCHIM MEDINIPUR | SM/15013 | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | TSM/017352 | 40034388 | New | MVS | GO2223013176PH | 04/02/2023 | 787.66 | 42.67 | 830.33 | Midnapore Division | Midnapore Mechanical Division | 328.33 | 28.56 | 0 | 0 | 356.89 | 328.33 | 25.07 | 0 | 0 | 353.4 | 42.56 | 53
214 | PASCHIM MEDINIPUR | SM/18502 | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015588 | 40028858 | New | MVS | 2037/PHE-28011/20/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1547.92 | 116.02 | 1663.94 | Midnapore Division | Midnapore Mechanical Division | 3.73 | 36.79 | 119.83 | 0 | 160.35 | 3.73 | 36.79 | 119.83 | 0 | 160.35 | 9.64 | 30
215 | PASCHIM MEDINIPUR | SM/12988 | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011809 | 40025936 | New | MVS | GO2223008331PH | 28/09/2022 | 483.44 | 38.2 | 521.64 | Midnapore Division | Midnapore Mechanical Division | 51.64 | 18.08 | 35.91 | 0 | 105.63 | 51.64 | 18.08 | 35.91 | 0 | 105.63 | 20.25 | 15
216 | PASCHIM MEDINIPUR | SM/13089 | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | TSM/013055 | 40065575 | New | MVS | GO2223008447PH | 29/09/2022 | 283.84 | 37.66 | 321.5 | Midnapore Division | Midnapore Mechanical Division | 180.82 | 18.36 | 6.54 | 0 | 205.71 | 180.82 | 18.36 | 6.54 | 0 | 205.71 | 63.99 | 55
217 | PASCHIM MEDINIPUR | SM/14033 | KANKRISOL AND ADJOINING MOUJAS PWSS | TSM/015827 | 40035384 | New | MVS | GO2223010498PH | 05/12/2022 | 265.76 | 36.65 | 302.42 | Midnapore Division | Jhargram Mechanical Division | 64.65 | 5.11 | 2.92 | 6.52 | 79.2 | 64.65 | 5.11 | 2.92 | 6.52 | 79.2 | 26.19 | 25
218 | PASCHIM MEDINIPUR | SM/13059 | KANPUR AND ADJOINING MOUJAS PWSS | TSM/014655 | 40031419 | New | MVS | GO2223008492PH | 29/09/2022 | 523.34 | 39.33 | 562.67 | Midnapore Division | Midnapore Mechanical Division | 112.34 | 12.1 | 11.35 | 21.37 | 157.16 | 112.34 | 6.94 | 11.35 | 21.37 | 152 | 27.01 | 35
219 | PASCHIM MEDINIPUR | SM/13060 | KANTAL AND ADJOINING MOUJAS PWSS | TSM/014650 | 40031814 | New | MVS | GO2223008504PH | 29/09/2022 | 458.93 | 38.4 | 497.33 | Midnapore Division | Jhargram Mechanical Division | 7.04 | 12.47 | 18.22 | 0 | 37.73 | 7.04 | 12.47 | 18.22 | 0 | 37.73 | 7.59 | 30
220 | PASCHIM MEDINIPUR | SM/13061 | KARANJIMURA AND ADJOINING MOUJAS PWSS | TSM/014756 | 40031799 | New | MVS | GO2223008501PH | 29/09/2022 | 392.81 | 37.76 | 430.57 | Midnapore Division | Midnapore Mechanical Division | 109.05 | 25.79 | 9.09 | 22.5 | 166.44 | 109.05 | 25.79 | 9.09 | 22.5 | 166.44 | 38.65 | 35
221 | PASCHIM MEDINIPUR | SM/13001 | KARNAGAR AND ADJOINING MAOUJAS PWSS | TSM/015012 | 40026205 | New | MVS | GO2223008409PH | 29/09/2022 | 522.52 | 39.33 | 561.85 | Midnapore Division | Jhargram Mechanical Division | 97.69 | 6.22 | 28.33 | 13.42 | 145.66 | 89.8 | 6.22 | 28.33 | 13.42 | 137.77 | 24.52 | 35
222 | PASCHIM MEDINIPUR | SM/13090 | KARSA AND ADJOINING MOUJAS PWSS | TSM/014471 | 40031911 | New | MVS | GO2223008533PH | 10/10/2022 | 361.95 | 60.49 | 422.45 | Midnapore Division | Jhargram Mechanical Division | 110.09 | 10.01 | 5.67 | 13.03 | 138.81 | 105.72 | 10.01 | 5.67 | 13.03 | 134.44 | 31.82 | 40
223 | PASCHIM MEDINIPUR | SM/19100 | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS | TSM/016189 | 40034225 | New | MVS | 3714/PHE-28011/267/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1065.92 | 49.81 | 1115.72 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 26.48 | 5.09 | 31.58 | 0 | 0 | 26.48 | 5.09 | 31.58 | 2.83 | 4
224 | PASCHIM MEDINIPUR | SM/14653 | KASHBA AND ITS ADJOINING MOUZAS PWSS | TSM/017291 | 40035835 | New | MVS | GO2223012731PH | 31/01/2023 | 271.44 | 19.75 | 291.2 | Midnapore Division | Midnapore Mechanical Division | 49.6 | 5.11 | 0.46 | 0 | 55.17 | 49.6 | 5.11 | 0.46 | 0 | 55.17 | 18.95 | 65
225 | PASCHIM MEDINIPUR | SM/12331 | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | TSM/014276 | 40023590 | New | MVS | GO2223007342PH | 09/09/2022 | 612.01 | 38.73 | 650.74 | Midnapore Division | Midnapore Mechanical Division | 0 | 3.7 | 26.69 | 0 | 30.39 | 0 | 3.7 | 26.69 | 0 | 30.39 | 4.67 | 20
226 | PASCHIM MEDINIPUR | SM/17561 | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017566 | 40053734 | New | MVS | GO2223017045PH | 18/03/2023 | 584.52 | 76.24 | 660.76 | Midnapore Division | Midnapore Mechanical Division | 205.21 | 25.59 | 25.42 | 0 | 256.21 | 205.21 | 25.59 | 25.42 | 0 | 256.21 | 38.78 | 10
227 | PASCHIM MEDINIPUR | SM/17562 | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017567 | 40053735 | New | MVS | GO2223017074PH | 18/03/2023 | 841.92 | 77.87 | 919.79 | Midnapore Division | Midnapore Mechanical Division | 322.43 | 15.66 | 13.6 | 0 | 351.69 | 322.43 | 8.79 | 13.6 | 0 | 344.83 | 37.49 | 60
228 | PASCHIM MEDINIPUR | SM/15014 | KASHIPUR AND ADJOINING MOUJAS PWSS | TSM/015979 | 40034081 | New | MVS | GO2223013055PH | 04/02/2023 | 858.33 | 41.57 | 899.9 | Midnapore Division | Midnapore Mechanical Division | 567.01 | 12.47 | 0 | 18.51 | 597.99 | 567.01 | 12.47 | 0 | 18.51 | 597.99 | 66.45 | 85
229 | PASCHIM MEDINIPUR | SM/13088 | KATAI AND IT'S ADJOINING MOUJAS PWSS | TSM/013121 | 40026264 | New | MVS | GO2223008446PH | 29/09/2022 | 421.54 | 37.83 | 459.37 | Midnapore Division | Midnapore Mechanical Division | 217.11 | 23.31 | 1.33 | 0 | 241.76 | 195.86 | 23.31 | 1.33 | 0 | 220.5 | 48 | 70
230 | PASCHIM MEDINIPUR | SM/17621 | KEDAR AND ITS ADJOINING MOUJAS PWSS | TSM/013136 | 40033089 | New | MVS | GO2223017413PH | 21/03/2023 | 321.75 | 37.89 | 359.64 | Midnapore Division | Midnapore Mechanical Division | 27.48 | 9.96 | 42.55 | 0 | 79.98 | 0 | 9.96 | 42.55 | 0 | 52.5 | 14.6 | 10
231 | PASCHIM MEDINIPUR | SM/13023 | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS | TSM/013163 | 40026032 | New | MVS | GO2223008353PH | 28/09/2022 | 697.07 | 38.51 | 735.57 | Midnapore Division | Midnapore Mechanical Division | 78.03 | 8.77 | 17.95 | 0 | 104.75 | 4.78 | 8.77 | 17.95 | 0 | 31.49 | 4.28 | 8
232 | PASCHIM MEDINIPUR | SM/13124 | KESHIA AND ADJOINING MOUJAS PWSS | TSM/014747 | 40031906 | New | MVS | GO2223008532PH | 10/10/2022 | 467.2 | 37.78 | 504.98 | Midnapore Division | Jhargram Mechanical Division | 217.36 | 11.14 | 9.57 | 13.03 | 251.11 | 217.36 | 11.14 | 9.57 | 13.03 | 251.11 | 49.73 | 54
233 | PASCHIM MEDINIPUR | SM/13026 | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | TSM/010246 | 40026106 | New | MVS | GO2223008361PH | 28/09/2022 | 477.89 | 38.2 | 516.09 | Midnapore Division | Midnapore Mechanical Division | 323.51 | 21.64 | 22.49 | 0 | 367.65 | 307.9 | 17.46 | 22.49 | 0 | 347.85 | 67.4 | 40
234 | PASCHIM MEDINIPUR | SM/13024 | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | TSM/013105 | 40026141 | New | MVS | GO2223008366PH | 28/09/2022 | 350.31 | 37.83 | 388.14 | Midnapore Division | Midnapore Mechanical Division | 214.38 | 26.74 | 0 | 0 | 241.12 | 206.15 | 26.74 | 0 | 0 | 232.88 | 60 | 72
235 | PASCHIM MEDINIPUR | SM/13025 | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. | TSM/013179 | 40026116 | New | MVS | GO2223008362PH | 28/09/2022 | 471.71 | 38.28 | 509.99 | Midnapore Division | Midnapore Mechanical Division | 1.27 | 11.81 | 12.01 | 0 | 25.08 | 0 | 11.81 | 12.01 | 0 | 23.82 | 4.67 | 10
236 | PASCHIM MEDINIPUR | SM/18532 | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | TSM/017513 | 40044943 | New | MVS | 2051/PHE-28011/177/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1011.28 | 42.82 | 1054.1 | Midnapore Division | Midnapore Mechanical Division | 299.18 | 8.88 | 17.2 | 0 | 325.25 | 299.18 | 8.88 | 17.2 | 0 | 325.25 | 30.86 | 34
237 | PASCHIM MEDINIPUR | SM/15015 | KHARIKA AND ITS ADJOINING MOUZAS PWSS | TSM/016020 | 40034390 | New | MVS | GO2223013087PH | 04/02/2023 | 942.1 | 39.86 | 981.96 | Midnapore Division | Midnapore Mechanical Division | 259.05 | 8 | 0 | 0 | 267.04 | 212.53 | 8 | 0 | 0 | 220.53 | 22.46 | 42
238 | PASCHIM MEDINIPUR | SM/13125 | KHARIPARA AND IT'S ADJOINING MOUJAS | TSM/014733 | 40031924 | New | MVS | GO2223008536PH | 10/10/2022 | 406.09 | 37.78 | 443.87 | Midnapore Division | Midnapore Mechanical Division | 69.78 | 22.32 | 9.38 | 20.95 | 122.43 | 69.78 | 22.32 | 9.38 | 20.95 | 122.43 | 27.58 | 30
239 | PASCHIM MEDINIPUR | SM/14506 | KHAS JANGAL PIPED WATER SUPPLY SCHEME | TSM/015765 | 40034445 | New | MVS | GO2223012311PH | 20/01/2023 | 883.33 | 37.53 | 920.87 | Midnapore Division | Midnapore Mechanical Division | 347.55 | 22.36 | 0 | 0 | 369.9 | 347.55 | 22.36 | 0 | 0 | 369.9 | 40.17 | 55
240 | PASCHIM MEDINIPUR | SM/17618 | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS | TSM/011838 | 40033914 | New | MVS | GO2223017410PH | 21/03/2023 | 578.14 | 38.2 | 616.34 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 26.53 | 0 | 26.53 | 0 | 0 | 26.53 | 0 | 26.53 | 4.3 | 2
241 | PASCHIM MEDINIPUR | SM/07393 | Khirinda Piped Water Supply Scheme. | TSM/004519 | 8290951 | New | MVS | GO2021003568PH | 21/12/2020 | 859.9 | 40.82 | 900.72 | Midnapore Division | Midnapore Mechanical Division | 4.52 | 5.32 | 0 | 27.2 | 37.03 | 4.52 | 5.32 | 0 | 27.2 | 37.03 | 4.11 | 5
242 | PASCHIM MEDINIPUR | SM/18525 | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | TSM/017514 | 40034349 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1138.94 | 40.76 | 1179.7 | Midnapore Division | Midnapore Mechanical Division | 208.3 | 26.11 | 0 | 0 | 234.41 | 208.3 | 26.11 | 0 | 0 | 234.41 | 19.87 | 36
243 | PASCHIM MEDINIPUR | SM/13126 | KHURSI AND ADJOINING MOUJAS PWSS | TSM/014267 | 40034078 | New | MVS | GO2223008570PH | 10/10/2022 | 603.88 | 38.48 | 642.36 | Midnapore Division | Midnapore Mechanical Division | 246.62 | 9.39 | 15.74 | 13.72 | 285.47 | 246.62 | 9.39 | 15.74 | 13.72 | 285.47 | 44.44 | 60
244 | PASCHIM MEDINIPUR | SM/13113 | KONTORE AND ADJOINING MOUJAS PWSS | TSM/014749 | 40031882 | New | MVS | GO2223008531PH | 10/10/2022 | 333.76 | 37.66 | 371.42 | Midnapore Division | Jhargram Mechanical Division | 111.88 | 12.7 | 6.34 | 13.03 | 143.96 | 111.88 | 12.7 | 6.34 | 13.03 | 143.96 | 38.76 | 47
245 | PASCHIM MEDINIPUR | SM/14034 | KOREDAN AND ADJOINING MOUJAS PWSS | TSM/015817 | 40035656 | New | MVS | GO2223010497PH | 05/12/2022 | 445.27 | 39.38 | 484.66 | Midnapore Division | Jhargram Mechanical Division | 86.51 | 0 | 8.21 | 0 | 94.71 | 86.51 | 0 | 8.21 | 0 | 94.71 | 19.54 | 20
246 | PASCHIM MEDINIPUR | SM/14484 | KUBIR CHAK PIPED WATER SUPPLY SCHEME | TSM/015084 | 40034440 | New | MVS | GO2223012312PH | 20/01/2023 | 773.09 | 37.62 | 810.71 | Midnapore Division | Midnapore Mechanical Division | 158.43 | 27.06 | 0 | 0 | 185.5 | 155.84 | 26.08 | 0 | 0 | 181.92 | 22.44 | 40
247 | PASCHIM MEDINIPUR | SM/12335 | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. | TSM/013977 | 40023633 | New | MVS | GO2223007344PH | 09/09/2022 | 686.38 | 40.37 | 726.75 | Midnapore Division | Jhargram Mechanical Division | 276.75 | 17.94 | 16.98 | 14.08 | 325.74 | 245.13 | 17.94 | 16.98 | 14.08 | 294.12 | 40.47 | 39
248 | PASCHIM MEDINIPUR | SM/14654 | KUKRADA AND ITS ADJOINING MOUZAS PWSS | TSM/017288 | 40035810 | New | MVS | GO2223012733PH | 31/01/2023 | 627.67 | 41.21 | 668.88 | Midnapore Division | Midnapore Mechanical Division | 123.28 | 5.47 | 1.71 | 0 | 130.47 | 123.28 | 5.47 | 1.71 | 0 | 130.47 | 19.51 | 65
249 | PASCHIM MEDINIPUR | SM/13121 | KULBANI AND ADJOINING MOUJAS PWSS | TSM/014763 | 40032102 | New | MVS | GO2223008559PH | 10/10/2022 | 673.26 | 57.61 | 730.87 | Midnapore Division | Midnapore Mechanical Division | 115.13 | 35.22 | 18.71 | 19.43 | 188.49 | 115.13 | 35.22 | 18.71 | 19.43 | 188.49 | 25.79 | 40
250 | PASCHIM MEDINIPUR | SM/14655 | KULDIHA AND ITS ADJOINING MOUZAS PWSS | TSM/017167 | 40035858 | New | MVS | GO2223012713PH | 31/01/2023 | 659.98 | 41.06 | 701.03 | Midnapore Division | Midnapore Mechanical Division | 2.7 | 6.33 | 13.78 | 0 | 22.81 | 0 | 6.33 | 13.78 | 0 | 20.11 | 2.87 | 35
251 | PASCHIM MEDINIPUR | SM/14939 | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/011807 | 40033801 | New | MVS | GO2223012937PH | 03/02/2023 | 338.67 | 38.05 | 376.72 | Midnapore Division | Midnapore Mechanical Division | 203.6 | 30.04 | 15.13 | 0 | 248.76 | 196.04 | 30.04 | 15.13 | 0 | 241.2 | 64.03 | 76
252 | PASCHIM MEDINIPUR | SM/13122 | KUNARPUR AND ADJOINING MOUJAS PWSS | TSM/014399 | 40032106 | New | MVS | GO2223008560PH | 10/10/2022 | 515.04 | 36.72 | 551.76 | Midnapore Division | Midnapore Mechanical Division | 94.98 | 8.65 | 29.26 | 5.4 | 138.29 | 94.98 | 8.65 | 29.26 | 5.4 | 138.29 | 25.06 | 30
253 | PASCHIM MEDINIPUR | SM/15017 | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017440 | 40034895 | New | MVS | GO2223013179PH | 04/02/2023 | 480.5 | 76.3 | 556.8 | Midnapore Division | Midnapore Mechanical Division | 256.71 | 16.54 | 14.79 | 0 | 288.04 | 256.57 | 16.54 | 14.79 | 0 | 287.9 | 51.71 | 55
254 | PASCHIM MEDINIPUR | SM/14656 | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017441 | 40034791 | New | MVS | GO2223012715PH | 31/01/2023 | 527.27 | 77.41 | 604.67 | Midnapore Division | Midnapore Mechanical Division | 92.68 | 15.19 | 3.93 | 0 | 111.8 | 92.68 | 8.94 | 3.93 | 0 | 105.55 | 17.46 | 37
255 | PASCHIM MEDINIPUR | SM/18531 | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | TSM/014870 | 40034431 | New | MVS | 2050/PHE-28011/24/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1204.79 | 49.05 | 1253.84 | Midnapore Division | Midnapore Mechanical Division | 366.85 | 18.36 | 0 | 0 | 385.21 | 176.17 | 8.68 | 0 | 0 | 184.86 | 14.74 | 45
256 | PASCHIM MEDINIPUR | SM/13093 | KUSUMPUR AND ADJOINING MOUJAS | TSM/014746 | 40034914 | New | MVS | GO2223008574PH | 10/10/2022 | 544.81 | 39.33 | 584.14 | Midnapore Division | Midnapore Mechanical Division | 127.14 | 5.5 | 12.05 | 22.27 | 166.95 | 127.14 | 5.5 | 12.05 | 22.27 | 166.95 | 28.58 | 35
257 | PASCHIM MEDINIPUR | SM/15016 | KUTKI AND ADJOINING MOUJAS PWSS | TSM/014438 | 40034063 | New | MVS | GO2223013150PH | 04/02/2023 | 564.93 | 51.42 | 616.35 | Midnapore Division | Midnapore Mechanical Division | 19.42 | 7.93 | 10.52 | 13.03 | 50.91 | 19.42 | 7.93 | 10.52 | 13.03 | 50.91 | 8.26 | 42
258 | PASCHIM MEDINIPUR | SM/09988 | Kutulpur Piped Water Supply Scheme. | TSM/004504 | 40006881 | New | MVS | GO2122006952PH | 16/12/2021 | 490.72 | 42.59 | 533.31 | Midnapore Division | Midnapore Mechanical Division | 112.75 | 11.31 | 0 | 0 | 124.06 | 112.75 | 6.82 | 0 | 0 | 119.57 | 22.42 | 41
259 | PASCHIM MEDINIPUR | SM/13094 | LENGA MARA AND IT'S ADJOINING MOUJAS | TSM/014731 | 40032142 | New | MVS | GO2223008564PH | 10/10/2022 | 664.32 | 55.35 | 719.67 | Midnapore Division | Midnapore Mechanical Division | 90.06 | 28.26 | 38.47 | 20.14 | 176.92 | 90.06 | 28.26 | 38.47 | 20.14 | 176.92 | 24.58 | 30
260 | PASCHIM MEDINIPUR | SM/12992 | LOYADA AND ITS ADJOINING MOUJAS PWSS | TSM/011794 | 40025941 | New | MVS | GO2223008332PH | 28/09/2022 | 316.22 | 37.83 | 354.05 | Midnapore Division | Midnapore Mechanical Division | 210.43 | 25.62 | 7.71 | 0 | 243.76 | 210.43 | 25.62 | 7.71 | 0 | 243.76 | 68.85 | 85
261 | PASCHIM MEDINIPUR | SM/17622 | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013137 | 40033285 | New | MVS | GO2223017405PH | 21/03/2023 | 349.21 | 37.83 | 387.04 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 30.4 | 0 | 30.4 | 0 | 0 | 30.4 | 0 | 30.4 | 7.86 | 22
262 | PASCHIM MEDINIPUR | SM/14035 | MADHUPUR AND ADJOINING MOUJAS PWSS | TSM/015831 | 40035518 | New | MVS | GO2223010488PH | 05/12/2022 | 476.77 | 40.32 | 517.09 | Midnapore Division | Jhargram Mechanical Division | 190.07 | 12.51 | 7.91 | 6.52 | 217.01 | 190.07 | 12.51 | 7.91 | 6.52 | 217.01 | 41.97 | 35
263 | PASCHIM MEDINIPUR | SM/15325 | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015712 | 40034649 | New | MVS | GO2223013664PH | 09/02/2023 | 812.03 | 80.51 | 892.54 | Midnapore Division | Midnapore Mechanical Division | 4.95 | 12.83 | 0 | 0 | 17.78 | 4.95 | 12.83 | 0 | 0 | 17.78 | 1.99 | 13
264 | PASCHIM MEDINIPUR | SM/14036 | MAHASOL AND ADJOINING MOUJAS PWSS | TSM/014959 | 40035554 | New | MVS | GO2223010500PH | 05/12/2022 | 522.4 | 56.8 | 579.21 | Midnapore Division | Jhargram Mechanical Division | 203.01 | 11.98 | 0 | 22.83 | 237.82 | 203.01 | 11.98 | 0 | 22.83 | 237.82 | 41.06 | 47
265 | PASCHIM MEDINIPUR | SM/13095 | MAHISAMURA PWSS | TSM/014787 | 40035030 | New | SVS | GO2223008567PH | 10/10/2022 | 417.82 | 37.82 | 455.65 | Midnapore Division | Midnapore Mechanical Division | 78.09 | 26.5 | 8.59 | 21.8 | 134.98 | 78.09 | 26.5 | 8.59 | 21.8 | 134.98 | 29.62 | 50
266 | PASCHIM MEDINIPUR | SM/18586 | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015925 | 40034970 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1002.76 | 77.78 | 1080.54 | Midnapore Division | Midnapore Mechanical Division | 266.77 | 9.39 | 55.73 | 0 | 331.88 | 179.59 | 9.39 | 55.73 | 0 | 244.71 | 22.65 | 29
267 | PASCHIM MEDINIPUR | SM/13096 | MAKLI AND ADJOINING MOUJAS PWSS | TSM/014874 | 40032111 | New | MVS | GO2223008562PH | 10/10/2022 | 342.72 | 35.62 | 378.34 | Midnapore Division | Jhargram Mechanical Division | 124.36 | 16.49 | 4.37 | 6.52 | 151.75 | 124.36 | 16.49 | 4.37 | 6.52 | 151.75 | 40.11 | 17
268 | PASCHIM MEDINIPUR | SM/13027 | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | TSM/011784 | 40026078 | New | MVS | GO2223008356PH | 28/09/2022 | 478.49 | 38.26 | 516.76 | Midnapore Division | Midnapore Mechanical Division | 137.79 | 4.99 | 10.86 | 0 | 153.64 | 137.79 | 4.99 | 10.86 | 0 | 153.64 | 29.73 | 15
269 | PASCHIM MEDINIPUR | SM/16615 | MALIHATI AND IT'S ADJOINING MOUJAS PWSS | TSM/011812 | 40033283 | New | MVS | GO2223015963PH | 14/03/2023 | 343.62 | 37.83 | 381.45 | Midnapore Division | Midnapore Mechanical Division | 151.2 | 23.03 | 24.6 | 0 | 198.82 | 113.6 | 5.64 | 24.6 | 0 | 143.84 | 37.71 | 23
270 | PASCHIM MEDINIPUR | SM/15020 | MANGAL BANDI AND ADJOINING MOUJAS PWSS | TSM/017105 | 40033256 | New | MVS | GO2223013174PH | 04/02/2023 | 557.44 | 39.15 | 596.58 | Midnapore Division | Jhargram Mechanical Division | 109.78 | 10.88 | 10.16 | 6.52 | 137.34 | 109.78 | 10.88 | 10.16 | 6.52 | 137.34 | 23.02 | 25
271 | PASCHIM MEDINIPUR | SM/14493 | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016286 | 40035774 | New | MVS | GO2223012314PH | 20/01/2023 | 542.1 | 40.85 | 582.95 | Midnapore Division | Midnapore Mechanical Division | 118.56 | 8.44 | 53.56 | 0 | 180.56 | 118.56 | 8.44 | 53.56 | 0 | 180.56 | 30.97 | 40
272 | PASCHIM MEDINIPUR | SM/13097 | MANIKDIPABARA AND AJOINING MOUJAS PWSS | TSM/014748 | 40032120 | New | MVS | GO2223008563PH | 10/10/2022 | 431.12 | 39.33 | 470.46 | Midnapore Division | Jhargram Mechanical Division | 122.26 | 6.95 | 0 | 13.35 | 142.56 | 122.26 | 6.95 | 0 | 13.35 | 142.56 | 30.3 | 30
273 | PASCHIM MEDINIPUR | SM/14002 | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS | TSM/015944 | 40033482 | New | MVS | GO2223010486PH | 05/12/2022 | 141.27 | 9.83 | 151.1 | Midnapore Division | Jhargram Mechanical Division | 44.2 | 0 | 1.9 | 0 | 46.1 | 44.2 | 0 | 1.9 | 0 | 46.1 | 30.51 | 34
274 | PASCHIM MEDINIPUR | SM/15593 | MARKHA AND ITS ADJOINING MOUZAS PWSS | TSM/017515 | 40044482 | New | MVS | GO2223013887PH | 15/02/2023 | 945.67 | 44.91 | 990.58 | Midnapore Division | Midnapore Mechanical Division | 196.33 | 10.08 | 100.82 | 0 | 307.23 | 151.65 | 10.08 | 100.82 | 0 | 262.55 | 26.5 | 45
275 | PASCHIM MEDINIPUR | SM/13098 | MARKUNDA AND ADJOINING MOUJAS PWSS | TSM/014435 | 40034261 | New | MVS | GO2223008573PH | 10/10/2022 | 414.11 | 36.34 | 450.45 | Midnapore Division | Midnapore Mechanical Division | 296 | 7.61 | 31.45 | 17.43 | 352.49 | 296 | 7.61 | 31.45 | 17.43 | 352.49 | 78.25 | 85
276 | PASCHIM MEDINIPUR | SM/18587 | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | TSM/016525 | 40035943 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1071.76 | 42.81 | 1114.57 | Midnapore Division | Midnapore Mechanical Division | 546.58 | 26.62 | 0 | 0 | 573.2 | 546.58 | 26.62 | 0 | 0 | 573.2 | 51.43 | 62
277 | PASCHIM MEDINIPUR | SM/14624 | METELDEBIGHATA AND ADJOINING MOUJAS PWSS | TSM/016797 | 40035603 | New | MVS | GO2223012703PH | 31/01/2023 | 79.73 | 1.26 | 81 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
278 | PASCHIM MEDINIPUR | SM/13099 | MIRGA AND ADJOINING MOUJAS PWSS | TSM/015059 | 40032217 | New | MVS | GO2223008569PH | 10/10/2022 | 474.93 | 38.04 | 512.97 | Midnapore Division | Jhargram Mechanical Division | 117.08 | 10.95 | 7.99 | 12.77 | 148.8 | 117.08 | 10.95 | 7.99 | 12.77 | 148.8 | 29.01 | 40
279 | PASCHIM MEDINIPUR | SM/13028 | MOHANPUR & ADJOINING MOUJAS PWSS | TSM/013390 | 40026098 | New | MVS | GO2223008358PH | 28/09/2022 | 515.92 | 40.16 | 556.08 | Midnapore Division | Jhargram Mechanical Division | 249.91 | 9.42 | 11.82 | 13.03 | 284.19 | 214.05 | 9.42 | 11.82 | 13.03 | 248.33 | 44.66 | 36
280 | PASCHIM MEDINIPUR | SM/10017 | Monoharpur Piped Water Supply Scheme. | TSM/004465 | 40027372 | New | MVS | GO2122007553PH | 30/12/2021 | 928.81 | 0 | 928.81 | Midnapore Division | Midnapore Mechanical Division | 185.44 | 25.68 | 44.01 | 0 | 255.13 | 185.44 | 25.68 | 44.01 | 0 | 255.13 | 27.47 | 50
281 | PASCHIM MEDINIPUR | SM/16542 | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | TSM/017130 | 40035058 | New | MVS | GO2223015487PH | 10/03/2023 | 636.31 | 48.41 | 684.72 | Midnapore Division | Midnapore Mechanical Division | 107.88 | 34.05 | 12.72 | 23.21 | 177.86 | 107.88 | 34.05 | 12.72 | 23.21 | 177.86 | 25.98 | 35
282 | PASCHIM MEDINIPUR | SM/13100 | MURAKATA AND ADJOINING MOUJAS PWSS | TSM/014445 | 40032184 | New | MVS | GO2223008565PH | 10/10/2022 | 604.59 | 38.61 | 643.19 | Midnapore Division | Midnapore Mechanical Division | 261.7 | 11.92 | 16.47 | 13.12 | 303.2 | 261.7 | 11.92 | 16.47 | 13.12 | 303.2 | 47.14 | 73
283 | PASCHIM MEDINIPUR | SM/14004 | MURAKATI AND ADJOINING MOUJAS PWSS | TSM/016132 | 40035405 | New | MVS | GO2223010487PH | 05/12/2022 | 429.87 | 38.84 | 468.71 | Midnapore Division | Jhargram Mechanical Division | 104.32 | 12.48 | 8.28 | 13.03 | 138.11 | 104.32 | 12.48 | 8.28 | 13.03 | 138.11 | 29.47 | 34
284 | PASCHIM MEDINIPUR | SM/15021 | MURARI AND ADJOINING MOUJAS PWSS | TSM/015110 | 40035591 | New | MVS | GO2223013147PH | 04/02/2023 | 586.63 | 57.29 | 643.92 | Midnapore Division | Jhargram Mechanical Division | 141.36 | 11.41 | 40.49 | 6.26 | 199.52 | 141.36 | 11.41 | 40.49 | 6.26 | 199.52 | 30.99 | 35
285 | PASCHIM MEDINIPUR | SM/13029 | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS | TSM/013117 | 40026126 | New | MVS | GO2223008365PH | 28/09/2022 | 420.2 | 38.05 | 458.25 | Midnapore Division | Midnapore Mechanical Division | 5.99 | 0 | 8.9 | 0 | 14.89 | 4.78 | 0 | 8.9 | 0 | 13.68 | 2.99 | 10
286 | PASCHIM MEDINIPUR | SM/15024 | NAHARPUR AND ADJOINING MOUJAS PWSS | TSM/015836 | 40034192 | New | MVS | GO2223013081PH | 04/02/2023 | 832.48 | 50.68 | 883.16 | Midnapore Division | Midnapore Mechanical Division | 64.56 | 2.96 | 26.32 | 6.56 | 100.4 | 64.56 | 2.96 | 26.32 | 6.56 | 100.4 | 11.37 | 39
287 | PASCHIM MEDINIPUR | SM/13101 | NALBONA AND ADJOINING MOUJAS PWSS | TSM/014450 | 40033372 | New | MVS | GO2223008571PH | 10/10/2022 | 458.22 | 38.61 | 496.83 | Midnapore Division | Jhargram Mechanical Division | 87.8 | 6.48 | 9.65 | 5.44 | 109.37 | 87.8 | 6.48 | 9.65 | 5.44 | 109.37 | 22.01 | 25
288 | PASCHIM MEDINIPUR | SM/14723 | NAMJABA AND ADJOINING MOUJAS PWSS | TSM/014172 | 40033472 | New | MVS | GO2223012710PH | 31/01/2023 | 759.99 | 58.49 | 818.48 | Midnapore Division | Jhargram Mechanical Division | 165.6 | 6.77 | 78.5 | 7.5 | 258.37 | 165.6 | 6.77 | 78.5 | 7.5 | 258.37 | 31.57 | 37
289 | PASCHIM MEDINIPUR | SM/13808 | NANASOL AND ADJOINING MOUJAS PWSS | TSM/015783 | 40035490 | New | MVS | GO2223009963PH | 22/11/2022 | 257.45 | 36.65 | 294.11 | Midnapore Division | Jhargram Mechanical Division | 16.22 | 7.91 | 3.26 | 12.77 | 40.16 | 16.22 | 7.91 | 3.26 | 12.77 | 40.16 | 13.65 | 16
290 | PASCHIM MEDINIPUR | SM/15025 | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | TSM/016101 | 40035730 | New | MVS | GO2223013137PH | 04/02/2023 | 518.95 | 37.42 | 556.37 | Midnapore Division | Midnapore Mechanical Division | 155.15 | 6.54 | 31.59 | 0 | 193.28 | 155.15 | 6.54 | 31.59 | 0 | 193.28 | 34.74 | 60
291 | PASCHIM MEDINIPUR | SM/18229 | NARMA AND ADJOINING MOUJAS PWSS | TSM/015801 | 40034051 | New | MVS | GO2324000612PH | 15/05/2023 | 1072.09 | 39.97 | 1112.06 | Midnapore Division | Midnapore Mechanical Division | 239.24 | 11.63 | 70.89 | 4.82 | 326.58 | 239.24 | 11.63 | 70.89 | 4.82 | 326.58 | 29.37 | 51
292 | PASCHIM MEDINIPUR | SM/14130 | NAYA BASAT AND ADJOINING MOUJAS PWSS | TSM/015824 | 40033143 | New | MVS | GO2223011524PH | 02/01/2023 | 861.6 | 59.99 | 921.59 | Midnapore Division | Jhargram Mechanical Division | 159.36 | 0 | 81.6 | 6.52 | 247.48 | 159.36 | 0 | 81.6 | 6.52 | 247.48 | 26.85 | 30
293 | PASCHIM MEDINIPUR | SM/13102 | NAYAPUKUR AND ADJOINING MOUJAS PWSS | TSM/014448 | 40034161 | New | MVS | GO2223008572PH | 10/10/2022 | 589.49 | 38.61 | 628.1 | Midnapore Division | Midnapore Mechanical Division | 118.79 | 4.06 | 38.88 | 6.56 | 168.29 | 118.79 | 4.06 | 38.88 | 6.56 | 168.29 | 26.79 | 23
294 | PASCHIM MEDINIPUR | SM/13103 | NERASOL AND ADJOINING MOUJAS PWSS | TSM/014269 | 40032207 | New | MVS | GO2223008568PH | 10/10/2022 | 860.24 | 65.15 | 925.39 | Midnapore Division | Jhargram Mechanical Division | 443.54 | 9.91 | 64.84 | 28.55 | 546.83 | 388.8 | 9.91 | 64.84 | 28.55 | 492.09 | 53.18 | 33
295 | PASCHIM MEDINIPUR | SM/17619 | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | TSM/011785 | 40033305 | New | MVS | GO2223017412PH | 21/03/2023 | 318.96 | 37.83 | 356.79 | Midnapore Division | Midnapore Mechanical Division | 119.29 | 31.25 | 7.37 | 0 | 157.9 | 119.29 | 31.25 | 7.37 | 0 | 157.9 | 44.26 | 23
296 | PASCHIM MEDINIPUR | SM/17565 | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION | TSM/018466 | 40053710 | New | MVS | GO2223017064PH | 18/03/2023 | 454.02 | 79.57 | 533.58 | Midnapore Division | Midnapore Mechanical Division | 7.66 | 22.34 | 5.94 | 0 | 35.95 | 7.66 | 22.34 | 5.94 | 0 | 35.95 | 6.74 | 40
297 | PASCHIM MEDINIPUR | SM/17566 | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018444 | 40053712 | New | MVS | GO2223017055PH | 18/03/2023 | 585.83 | 76.27 | 662.1 | Midnapore Division | Midnapore Mechanical Division | 69.06 | 31.3 | 6.35 | 0 | 106.7 | 69.06 | 31.3 | 6.35 | 0 | 106.7 | 16.12 | 20
298 | PASCHIM MEDINIPUR | SM/14732 | PACHADAHARA & ADJOINING MOUJAS PWSS | TSM/013391 | 40033524 | New | MVS | GO2223012648PH | 31/01/2023 | 476.9 | 38.41 | 515.32 | Midnapore Division | Jhargram Mechanical Division | 130.9 | 7.16 | 10.63 | 6.56 | 155.25 | 130.9 | 7.16 | 10.63 | 6.56 | 155.25 | 30.13 | 28
299 | PASCHIM MEDINIPUR | SM/13104 | PAKURSENI AND ADJOINING MOUJAS PWSS | TSM/014331 | 40032191 | New | MVS | GO2223008566PH | 10/10/2022 | 767.5 | 40.25 | 807.74 | Midnapore Division | Midnapore Mechanical Division | 219.59 | 7.81 | 32.07 | 13.72 | 273.19 | 219.59 | 7.81 | 32.07 | 13.72 | 273.19 | 33.82 | 65
300 | PASCHIM MEDINIPUR | SM/15026 | PALAIBANI AND ADJOINING MOUJAS PWSS | TSM/015949 | 40035351 | New | MVS | GO2223013065PH | 04/02/2023 | 305.26 | 36.67 | 341.93 | Midnapore Division | Jhargram Mechanical Division | 83.21 | 16 | 39.61 | 12.51 | 151.34 | 83.21 | 16 | 39.61 | 12.51 | 151.34 | 44.26 | 28
301 | PASCHIM MEDINIPUR | SM/13168 | PALASIA AND ADJOINING MOUJAS PWSS | TSM/014242 | 40036193 | New | MVS | GO2223008647PH | 12/10/2022 | 435.2 | 38.61 | 473.81 | Midnapore Division | Midnapore Mechanical Division | 204.7 | 24.13 | 1.26 | 0 | 230.09 | 188.05 | 24.13 | 1.26 | 0 | 213.44 | 45.05 | 80
302 | PASCHIM MEDINIPUR | SM/13216 | PANCHYAR AND ADJOINING MOUJAS PWSS | TSM/014654 | 40034894 | New | MVS | GO2223008642PH | 12/10/2022 | 464.57 | 37.78 | 502.34 | Midnapore Division | Midnapore Mechanical Division | 63.98 | 6.2 | 9.2 | 22.24 | 101.63 | 63.98 | 6.2 | 9.2 | 22.24 | 101.63 | 20.23 | 50
303 | PASCHIM MEDINIPUR | SM/10065 | Panna Piped Water Supply Scheme. | TSM/005101 | 40006626 | New | MVS | GO2122008790PH | 27/01/2022 | 407.47 | 0 | 407.47 | Midnapore Division | Midnapore Mechanical Division | 120.56 | 9.34 | 8.18 | 0 | 138.08 | 117.44 | 9.34 | 8.18 | 0 | 134.96 | 33.12 | 60
304 | PASCHIM MEDINIPUR | SM/13105 | PARBATIPUR AND ADJOINING MOUJAS PWSS | TSM/014190 | 40032088 | New | MVS | GO2223008545PH | 10/10/2022 | 885.01 | 73.6 | 958.61 | Midnapore Division | Jhargram Mechanical Division | 147.59 | 7.19 | 75.23 | 34.08 | 264.09 | 115.87 | 7.19 | 75.23 | 34.08 | 232.36 | 24.24 | 34
305 | PASCHIM MEDINIPUR | SM/15027 | PATAJHARIA AND ADJOINING MOUJAS PWSS | TSM/015109 | 40035571 | New | MVS | GO2223013042PH | 04/02/2023 | 279.4 | 36.65 | 316.05 | Midnapore Division | Jhargram Mechanical Division | 9.76 | 8.54 | 3.3 | 5.4 | 27 | 9.76 | 8.54 | 3.3 | 5.4 | 27 | 8.54 | 16
306 | PASCHIM MEDINIPUR | SM/13030 | PATHARISOL AND ADJOINING MOUJAS PWSS | TSM/013517 | 40026155 | New | MVS | GO2223008367PH | 28/09/2022 | 412.69 | 36.3 | 448.99 | Midnapore Division | Jhargram Mechanical Division | 110.39 | 11.73 | 40.93 | 13.07 | 176.12 | 94.13 | 11.73 | 40.93 | 13.07 | 159.86 | 35.6 | 40
307 | PASCHIM MEDINIPUR | SM/13106 | PATHARTERIA AND ADJOINING MOUJAS PWSS | TSM/014596 | 40032073 | New | MVS | GO2223008544PH | 10/10/2022 | 433.79 | 37.66 | 471.45 | Midnapore Division | Jhargram Mechanical Division | 181.38 | 4.64 | 21.63 | 6.52 | 214.16 | 162.22 | 4.64 | 21.63 | 6.52 | 195 | 41.36 | 45
308 | PASCHIM MEDINIPUR | SM/15535 | PATHRAJURI AND ADJOINING MOUJAS PWSS | TSM/016493 | 40035633 | New | MVS | GO2223013876PH | 15/02/2023 | 166.07 | 8.99 | 175.06 | Midnapore Division | Jhargram Mechanical Division | 20.99 | 0 | 2.13 | 10.09 | 33.21 | 20.99 | 0 | 2.13 | 10.09 | 33.21 | 18.97 | 25
309 | PASCHIM MEDINIPUR | SM/13807 | PATHRI AND AJOINING MOUJAS | TSM/015016 | 40033973 | New | MVS | GO2223009967PH | 22/11/2022 | 416.96 | 38.23 | 455.19 | Midnapore Division | Jhargram Mechanical Division | 108.03 | 11.82 | 6.86 | 13.03 | 139.74 | 108.03 | 11.82 | 6.86 | 13.03 | 139.74 | 30.7 | 37
310 | PASCHIM MEDINIPUR | SM/13031 | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | TSM/011739 | 40026171 | New | MVS | GO2223008369PH | 28/09/2022 | 483 | 38.14 | 521.14 | Midnapore Division | Midnapore Mechanical Division | 290.05 | 23.12 | 9.73 | 0 | 322.9 | 290.05 | 23.12 | 9.73 | 0 | 322.9 | 61.96 | 15
311 | PASCHIM MEDINIPUR | SM/16378 | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016334 | 40035782 | New | MVS | GO2223014979PH | 28/02/2023 | 717.42 | 40.66 | 758.08 | Midnapore Division | Midnapore Mechanical Division | 280.44 | 24.16 | 39.26 | 0 | 343.86 | 280.44 | 24.16 | 39.26 | 0 | 343.86 | 45.36 | 45
312 | PASCHIM MEDINIPUR | SM/13107 | PERUABAD AND ADJOINING MOUJAS PWSS | TSM/014804 | 40031954 | New | MVS | GO2223008540PH | 10/10/2022 | 377.56 | 39.06 | 416.62 | Midnapore Division | Jhargram Mechanical Division | 168.54 | 11.11 | 7.5 | 13.03 | 200.17 | 147.11 | 11.11 | 7.5 | 13.03 | 178.74 | 42.9 | 30
313 | PASCHIM MEDINIPUR | SM/14628 | PIASALA AND ADJOINING MOUJAS PWSS | TSM/016270 | 40036354 | New | MVS | GO2223012722PH | 31/01/2023 | 943.53 | 42.58 | 986.11 | Midnapore Division | Jhargram Mechanical Division | 221.19 | 14.99 | 16.64 | 18.66 | 271.49 | 221.19 | 14.99 | 16.64 | 18.66 | 271.49 | 27.53 | 36
314 | PASCHIM MEDINIPUR | SM/13032 | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | TSM/013446 | 40026181 | New | MVS | GO2223008370PH | 28/09/2022 | 924.17 | 41.32 | 965.49 | Midnapore Division | Midnapore Mechanical Division | 343.34 | 15.27 | 0 | 0 | 358.61 | 343.34 | 8.99 | 0 | 0 | 352.33 | 36.49 | 80
315 | PASCHIM MEDINIPUR | SM/15028 | PIRRAKULI AND ADJOINING MOUJAS PWSS | TSM/015097 | 40035575 | New | MVS | GO2223013043PH | 04/02/2023 | 519.69 | 38.96 | 558.66 | Midnapore Division | Jhargram Mechanical Division | 165.67 | 17.08 | 8.77 | 12 | 203.51 | 165.67 | 17.08 | 8.77 | 12 | 203.51 | 36.43 | 34
316 | PASCHIM MEDINIPUR | SM/15029 | PUKHARIA SOL AND ADJOINING MOUJAS PWSS | TSM/015809 | 40035497 | New | MVS | GO2223013080PH | 04/02/2023 | 426.37 | 38.84 | 465.21 | Midnapore Division | Jhargram Mechanical Division | 147.36 | 17.14 | 6.3 | 2.88 | 173.68 | 147.36 | 17.14 | 6.3 | 2.88 | 173.68 | 37.33 | 35
317 | PASCHIM MEDINIPUR | SM/13169 | PUNDRA AND ADJOINING MOUJAS PWSS | TSM/014255 | 40036086 | New | MVS | GO2223008644PH | 12/10/2022 | 461.42 | 38.61 | 500.02 | Midnapore Division | Midnapore Mechanical Division | 274.31 | 24.2 | 1.71 | 0 | 300.23 | 268.02 | 24.2 | 1.71 | 0 | 293.94 | 58.78 | 80
318 | PASCHIM MEDINIPUR | SM/13033 | PUNYA AND IT'S ADJOINING MOUJAS PWSS | TSM/013160 | 40026187 | New | MVS | GO2223008372PH | 28/09/2022 | 449.8 | 38.28 | 488.08 | Midnapore Division | Midnapore Mechanical Division | 1.22 | 8.8 | 10.65 | 0 | 20.67 | 0 | 8.8 | 10.65 | 0 | 19.45 | 3.98 | 10
319 | PASCHIM MEDINIPUR | SM/17567 | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015927 | 40053746 | New | MVS | GO2223017026PH | 18/03/2023 | 438.14 | 74.94 | 513.09 | Midnapore Division | Midnapore Mechanical Division | 4.37 | 0 | 5.32 | 0 | 9.68 | 4.37 | 0 | 5.32 | 0 | 9.68 | 1.89 | 10
320 | PASCHIM MEDINIPUR | SM/13034 | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | TSM/013191 | 40026101 | New | MVS | GO2223008360PH | 28/09/2022 | 349.55 | 37.66 | 387.21 | Midnapore Division | Midnapore Mechanical Division | 169.9 | 6.82 | 6.89 | 0 | 183.61 | 169.9 | 6.82 | 6.89 | 0 | 183.61 | 47.42 | 22
321 | PASCHIM MEDINIPUR | SM/12997 | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | TSM/012538 | 40026004 | New | MVS | GO2223008335PH | 28/09/2022 | 783.32 | 36.38 | 819.71 | Midnapore Division | Midnapore Mechanical Division | 387.52 | 26.74 | 0 | 0 | 414.26 | 387.52 | 26.74 | 0 | 0 | 414.26 | 50.54 | 80
322 | PASCHIM MEDINIPUR | SM/18526 | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | TSM/016507 | 40035798 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1221.36 | 42.96 | 1264.33 | Midnapore Division | Midnapore Mechanical Division | 277.39 | 11.9 | 115.64 | 0 | 404.94 | 277.39 | 11.9 | 115.64 | 0 | 404.94 | 32.03 | 45
323 | PASCHIM MEDINIPUR | SM/14940 | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | TSM/011853 | 40033927 | New | MVS | GO2223012879PH | 03/02/2023 | 356.77 | 37.89 | 394.66 | Midnapore Division | Midnapore Mechanical Division | 168.46 | 20.44 | 6.86 | 0 | 195.76 | 168.46 | 20.44 | 6.86 | 0 | 195.76 | 49.6 | 15
324 | PASCHIM MEDINIPUR | SM/14131 | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017438 | 40034847 | New | MVS | GO2223011528PH | 02/01/2023 | 865.82 | 80.51 | 946.33 | Midnapore Division | Midnapore Mechanical Division | 87.65 | 11.89 | 0 | 0 | 99.53 | 87.65 | 11.89 | 0 | 0 | 99.53 | 10.52 | 33
325 | PASCHIM MEDINIPUR | SM/13217 | RADHANAGAR AND ADJOINING MOUJAS PWSS | TSM/014337 | 40034140 | New | MVS | GO2223008641PH | 12/10/2022 | 630.4 | 38.61 | 669 | Midnapore Division | Midnapore Mechanical Division | 61.34 | 4.23 | 13.25 | 6.22 | 85.05 | 61.34 | 4.23 | 13.25 | 6.22 | 85.05 | 12.71 | 60
326 | PASCHIM MEDINIPUR | SM/13170 | RAIPUR AND ITS ADJOINING MOUJAS PWSS | TSM/014287 | 40034284 | New | MVS | GO2223008646PH | 12/10/2022 | 502.31 | 36.34 | 538.65 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 6.31 | 25.41 | 0 | 36.5 | 4.78 | 6.31 | 25.41 | 0 | 36.5 | 6.78 | 20
327 | PASCHIM MEDINIPUR | SM/13035 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | TSM/013128 | 40026087 | New | MVS | GO2223008357PH | 28/09/2022 | 544.84 | 38.28 | 583.12 | Midnapore Division | Midnapore Mechanical Division | 203.05 | 23.34 | 56.12 | 0 | 282.51 | 203.05 | 23.34 | 56.12 | 0 | 282.51 | 48.45 | 15
328 | PASCHIM MEDINIPUR | SM/16632 | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015585 | 40067336 | New | MVS | GO2223015892PH | 14/03/2023 | 476.01 | 74.96 | 550.96 | Midnapore Division | Midnapore Mechanical Division | 76.88 | 6.37 | 0 | 0 | 83.25 | 76.88 | 6.37 | 0 | 0 | 83.25 | 15.11 | 17
329 | PASCHIM MEDINIPUR | SM/15118 | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015714 | 40034676 | New | MVS | GO2223013224PH | 04/02/2023 | 678.25 | 78.37 | 756.61 | Midnapore Division | Midnapore Mechanical Division | 18.94 | 9.81 | 13.4 | 0 | 42.15 | 18.94 | 9.81 | 13.4 | 0 | 42.15 | 5.57 | 15
330 | PASCHIM MEDINIPUR | SM/13218 | RAUTARA AND ADJOINING MOUJAS PWSS | TSM/015013 | 40033974 | New | MVS | GO2223008639PH | 12/10/2022 | 413.98 | 39.06 | 453.04 | Midnapore Division | Jhargram Mechanical Division | 76.83 | 5.17 | 8.17 | 11.31 | 101.49 | 76.83 | 5.17 | 8.17 | 11.31 | 101.49 | 22.4 | 22
331 | PASCHIM MEDINIPUR | SM/18523 | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | TSM/017289 | 40035852 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1035.31 | 41.24 | 1076.55 | Midnapore Division | Midnapore Mechanical Division | 63.63 | 9.84 | 15.28 | 0 | 88.75 | 63.63 | 9.84 | 15.28 | 0 | 88.75 | 8.24 | 18
332 | PASCHIM MEDINIPUR | SM/13036 | RELA AND IT'S ADJOINING MOUJAS PWSS | TSM/013214 | 40026120 | New | MVS | GO2223008364PH | 28/09/2022 | 361.03 | 37.83 | 398.86 | Midnapore Division | Midnapore Mechanical Division | 31.02 | 9.01 | 7.26 | 12 | 59.28 | 4.78 | 9.01 | 7.26 | 12 | 33.05 | 8.29 | 10
333 | PASCHIM MEDINIPUR | SM/18530 | RERIPUR AND ADJ0INING MOUJAS PWSS | TSM/014535 | 40034188 | New | MVS | 2050/PHE-28011/24/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1128.05 | 57.85 | 1185.9 | Midnapore Division | Midnapore Mechanical Division | 321.53 | 6.42 | 41.46 | 15 | 384.42 | 321.53 | 6.42 | 41.46 | 15 | 384.42 | 32.42 | 60
334 | PASCHIM MEDINIPUR | SM/13108 | RUPARGHAGRA AND ADJOINING MOUJAS PWSS | TSM/014661 | 40031944 | New | MVS | GO2223008539PH | 10/10/2022 | 272.06 | 35.88 | 307.94 | Midnapore Division | Jhargram Mechanical Division | 98.63 | 15.72 | 3.12 | 13.03 | 130.51 | 98.32 | 15.72 | 3.12 | 13.03 | 130.19 | 42.28 | 42
335 | PASCHIM MEDINIPUR | SM/11460 | Sabra Piped Water Supply Scheme. | TSM/006521 | 40017888 | New | SVS | GO2223004996PH | 12/07/2022 | 953.45 | 58.5 | 1011.95 | Midnapore Division | Midnapore Mechanical Division | 542.96 | 51.02 | 107.15 | 0 | 701.12 | 542.96 | 51.02 | 107.15 | 0 | 701.12 | 69.28 | 95
336 | PASCHIM MEDINIPUR | SM/15119 | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015586 | 40036184 | New | MVS | GO2223013239PH | 04/02/2023 | 713.74 | 77.24 | 790.98 | Midnapore Division | Midnapore Mechanical Division | 31.57 | 20.78 | 10.49 | 0 | 62.84 | 16.22 | 20.78 | 10.49 | 0 | 47.49 | 6 | 28
337 | PASCHIM MEDINIPUR | SM/17996 | SAIYADPUR AND ADJOINING MOUJAS PWSS | TSM/015810 | 40035558 | New | MVS | GO2223016935PH | 17/03/2023 | 373.06 | 36.66 | 409.72 | Midnapore Division | Jhargram Mechanical Division | 111.96 | 15.68 | 5.05 | 10.81 | 143.5 | 111.96 | 15.68 | 5.05 | 10.81 | 143.5 | 35.02 | 35
338 | PASCHIM MEDINIPUR | SM/13171 | SALIKOTHA AND ADJOINING MOUJAS PWSS | TSM/014259 | 40036074 | New | MVS | GO2223008649PH | 12/10/2022 | 936.24 | 40.04 | 976.28 | Midnapore Division | Midnapore Mechanical Division | 491.79 | 30.95 | 6.21 | 0 | 528.94 | 448.05 | 30.95 | 6.21 | 0 | 485.2 | 49.7 | 75
339 | PASCHIM MEDINIPUR | SM/17568 | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018445 | 40053721 | New | MVS | GO2223017035PH | 18/03/2023 | 496.34 | 76.27 | 572.61 | Midnapore Division | Midnapore Mechanical Division | 7.8 | 21.08 | 7.1 | 0 | 35.98 | 7.8 | 21.08 | 7.1 | 0 | 35.98 | 6.28 | 50
340 | PASCHIM MEDINIPUR | SM/17569 | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018464 | 40053723 | New | MVS | GO2223017072PH | 18/03/2023 | 649.48 | 76.45 | 725.94 | Midnapore Division | Midnapore Mechanical Division | 0 | 14.12 | 8.42 | 0 | 22.54 | 0 | 14.12 | 8.42 | 0 | 22.54 | 3.1 | 2
341 | PASCHIM MEDINIPUR | SM/13219 | SANTRAPUR AND ADJOINING MOUJAS PWSS | TSM/014737 | 40035104 | New | MVS | GO2223008640PH | 12/10/2022 | 504.44 | 37.98 | 542.41 | Midnapore Division | Midnapore Mechanical Division | 78.81 | 20.89 | 0 | 21.85 | 121.55 | 78.81 | 18.09 | 0 | 21.85 | 118.74 | 21.89 | 45
342 | PASCHIM MEDINIPUR | SM/13172 | SAORAPIR AND ADJOINING MOUJAS PWSS | TSM/014253 | 40036163 | New | MVS | GO2223008654PH | 12/10/2022 | 309.68 | 36.31 | 345.99 | Midnapore Division | Midnapore Mechanical Division | 21.33 | 9.54 | 7.04 | 0 | 37.9 | 21.33 | 9.54 | 7.04 | 0 | 37.9 | 10.96 | 45
343 | PASCHIM MEDINIPUR | SM/13809 | SARANG AND ADJOINING MOUJAS PWSS | TSM/015093 | 40033142 | New | MVS | GO2223009968PH | 22/11/2022 | 672.14 | 39.23 | 711.37 | Midnapore Division | Midnapore Mechanical Division | 332.47 | 10.48 | 10.56 | 0 | 353.51 | 328.21 | 10.48 | 10.56 | 0 | 349.25 | 49.1 | 80
344 | PASCHIM MEDINIPUR | SM/18001 | SASHA BEDIA AND ADJOINING MOUJAS PWSS | TSM/015797 | 40036348 | New | MVS | GO2223016938PH | 17/03/2023 | 917.77 | 77.79 | 995.57 | Midnapore Division | Jhargram Mechanical Division | 376.33 | 17.92 | 15.98 | 23.99 | 434.22 | 376.33 | 17.92 | 15.98 | 23.99 | 434.22 | 43.62 | 28
345 | PASCHIM MEDINIPUR | SM/18009 | SATPATI AND ADJOINING MOUJAS PWSS | TSM/015805 | 40035356 | New | MVS | GO2223016945PH | 17/03/2023 | 536.9 | 39.18 | 576.07 | Midnapore Division | Jhargram Mechanical Division | 92.82 | 7.32 | 10.72 | 10.34 | 121.21 | 92.82 | 7.32 | 10.72 | 10.34 | 121.21 | 21.04 | 33
346 | PASCHIM MEDINIPUR | SM/13038 | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013118 | 40026057 | New | MVS | GO2223008354PH | 28/09/2022 | 512.89 | 38.28 | 551.17 | Midnapore Division | Midnapore Mechanical Division | 274.34 | 23.76 | 12.47 | 0 | 310.57 | 274.34 | 23.76 | 12.47 | 0 | 310.57 | 56.35 | 31
347 | PASCHIM MEDINIPUR | SM/17572 | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017563 | 40053736 | New | MVS | GO2223017059PH | 18/03/2023 | 665.28 | 75.01 | 740.3 | Midnapore Division | Midnapore Mechanical Division | 127.16 | 25.96 | 10.52 | 0 | 163.63 | 127.16 | 25.96 | 10.52 | 0 | 163.63 | 22.1 | 60
348 | PASCHIM MEDINIPUR | SM/17573 | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017564 | 40053737 | New | MVS | GO2223017034PH | 18/03/2023 | 508.78 | 75.01 | 583.8 | Midnapore Division | Midnapore Mechanical Division | 0 | 20.78 | 7.86 | 0 | 28.64 | 0 | 8.01 | 7.86 | 0 | 15.87 | 2.72 | 25
349 | PASCHIM MEDINIPUR | SM/13220 | SHAKHA BAI AND ADJOINING MOUJAS PWSS | TSM/014590 | 40033129 | New | MVS | GO2223008637PH | 12/10/2022 | 355.04 | 36.02 | 391.07 | Midnapore Division | Jhargram Mechanical Division | 106.36 | 14.49 | 6.7 | 13.03 | 140.58 | 106.36 | 14.49 | 6.7 | 13.03 | 140.58 | 35.95 | 35
350 | PASCHIM MEDINIPUR | SM/18013 | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | TSM/016553 | 40065561 | New | MVS | GO2223016957PH | 17/03/2023 | 323.91 | 29.87 | 353.79 | Midnapore Division | Jhargram Mechanical Division | 71.39 | 25.63 | 3.25 | 0 | 100.27 | 71.39 | 25.63 | 3.25 | 0 | 100.27 | 28.34 | 30
351 | PASCHIM MEDINIPUR | SM/18017 | SHASHINDA SVS PWSS | TSM/016249 | 40034157 | New | SVS | GO2223016959PH | 17/03/2023 | 402.55 | 55.45 | 458 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 8.04 | 0 | 8.04 | 0 | 0 | 8.04 | 0 | 8.04 | 1.76 | 10
352 | PASCHIM MEDINIPUR | SM/18585 | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015713 | 40034737 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 999.84 | 78.9 | 1078.74 | Midnapore Division | Midnapore Mechanical Division | 240.17 | 23.95 | 0 | 0 | 264.13 | 236.55 | 20.58 | 0 | 0 | 257.13 | 23.84 | 18
353 | PASCHIM MEDINIPUR | SM/15120 | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017442 | 40034703 | New | SVS | GO2223013229PH | 04/02/2023 | 194.95 | 38.15 | 233.1 | Midnapore Division | Midnapore Mechanical Division | 59.32 | 13.51 | 4.11 | 0 | 76.94 | 54.43 | 13.51 | 4.11 | 0 | 72.05 | 30.91 | 23
354 | PASCHIM MEDINIPUR | SM/13109 | SHUJA AND ADJOINING MOUJAS PWSS | TSM/014451 | 40031959 | New | MVS | GO2223008541PH | 10/10/2022 | 407.08 | 36.34 | 443.41 | Midnapore Division | Midnapore Mechanical Division | 64.26 | 6.88 | 12.54 | 13.03 | 96.72 | 64.26 | 6.88 | 12.54 | 13.03 | 96.72 | 21.81 | 15
355 | PASCHIM MEDINIPUR | SM/18020 | SHUKHNATOR AND ADJOINING MOUJAS PWSS | TSM/015814 | 40033206 | New | MVS | GO2223016940PH | 17/03/2023 | 760.95 | 59.63 | 820.59 | Midnapore Division | Jhargram Mechanical Division | 108.86 | 14.15 | 17.16 | 0 | 140.18 | 108.86 | 14.15 | 17.16 | 0 | 140.18 | 17.08 | 25
356 | PASCHIM MEDINIPUR | SM/13173 | SHYAMNAGAR AND ADJOINING MOUJAS PWSS | TSM/014133 | 40034038 | New | MVS | GO2223008652PH | 12/10/2022 | 766.22 | 38.85 | 805.07 | Midnapore Division | Jhargram Mechanical Division | 174.8 | 7.09 | 52.25 | 26.2 | 260.34 | 174.8 | 7.09 | 52.25 | 26.2 | 260.34 | 32.34 | 34
357 | PASCHIM MEDINIPUR | SM/17624 | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013197 | 40033799 | New | MVS | GO2223017406PH | 21/03/2023 | 304.79 | 37.8 | 342.58 | Midnapore Division | Midnapore Mechanical Division | 90.45 | 26.62 | 24.1 | 0 | 141.17 | 90.45 | 26.62 | 24.1 | 0 | 141.17 | 41.21 | 15
358 | PASCHIM MEDINIPUR | SM/13110 | SINGLA AND IT'S ADJOINING MOUJAS | TSM/014730 | 40031880 | New | MVS | GO2223008530PH | 10/10/2022 | 279.43 | 38.41 | 317.84 | Midnapore Division | Jhargram Mechanical Division | 125.06 | 6.62 | 4.46 | 13.03 | 149.18 | 114.71 | 6.62 | 4.46 | 13.03 | 138.83 | 43.68 | 45
359 | PASCHIM MEDINIPUR | SM/18527 | SINNIBAR PIPED WATER SUPPLY SCHEME | TSM/013550 | 40034484 | New | MVS | 2047/PHE-28011/62/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1102.53 | 41.24 | 1143.77 | Midnapore Division | Midnapore Mechanical Division | 0 | 27.44 | 0 | 0 | 27.44 | 0 | 27.44 | 0 | 0 | 27.44 | 2.4 | 32
360 | PASCHIM MEDINIPUR | SM/13057 | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013200 | 40031808 | New | MVS | GO2223008503PH | 29/09/2022 | 429.67 | 38.14 | 467.81 | Midnapore Division | Midnapore Mechanical Division | 56.57 | 6.52 | 27.49 | 15 | 105.59 | 4.78 | 6.52 | 27.49 | 15 | 53.8 | 11.5 | 45
361 | PASCHIM MEDINIPUR | SM/13139 | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS | TSM/013167 | 40033875 | New | MVS | GO2223008617PH | 12/10/2022 | 480.66 | 38.28 | 518.94 | Midnapore Division | Midnapore Mechanical Division | 27.42 | 7.56 | 11.46 | 0 | 46.45 | 4.78 | 7.56 | 11.46 | 0 | 23.8 | 4.59 | 10
362 | PASCHIM MEDINIPUR | SM/13174 | SOLPOTA AND ADJOINING MOUJAS PWSS | TSM/014241 | 40036186 | New | MVS | GO2223008655PH | 12/10/2022 | 424.17 | 38.39 | 462.56 | Midnapore Division | Midnapore Mechanical Division | 150.42 | 27.82 | 26.21 | 0 | 204.44 | 150.42 | 27.82 | 26.21 | 0 | 204.44 | 44.2 | 50
363 | PASCHIM MEDINIPUR | SM/13221 | SONIAKON AND ADJOINING MOUJAS PWSS | TSM/014868 | 40035404 | New | MVS | GO2223008635PH | 12/10/2022 | 413.64 | 39.33 | 452.97 | Midnapore Division | Jhargram Mechanical Division | 117.68 | 0 | 43.5 | 6.56 | 167.74 | 117.68 | 0 | 43.5 | 6.56 | 167.74 | 37.03 | 35
364 | PASCHIM MEDINIPUR | SM/19043 | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015926 | 40036221 | New | MVS | 3546/PHE-28011/198/2023-SCHM CELL-Dept. of PHE | 24/11/2023 | 961.39 | 77.24 | 1038.63 | Midnapore Division | Midnapore Mechanical Division | 259.55 | 16.03 | 189.2 | 0 | 464.78 | 228.22 | 16.03 | 189.2 | 0 | 433.45 | 41.73 | 44
365 | PASCHIM MEDINIPUR | SM/17614 | TALBANDI AND ITS ADJOINING MOUJAS PWSS | TSM/011840 | 40033188 | New | MVS | GO2223017407PH | 21/03/2023 | 262.12 | 37.76 | 299.88 | Midnapore Division | Midnapore Mechanical Division | 39.49 | 9.75 | 4.39 | 0 | 53.63 | 15.63 | 9.75 | 4.39 | 0 | 29.77 | 9.93 | 20
366 | PASCHIM MEDINIPUR | SM/09992 | Tanuya Piped Water Supply Scheme. | TSM/005513 | 40008567 | New | MVS | GO2122006950PH | 16/12/2021 | 883.09 | 0 | 883.09 | Midnapore Division | Midnapore Mechanical Division | 413.16 | 21.61 | 70.33 | 0 | 505.09 | 413.16 | 21.61 | 70.33 | 0 | 505.09 | 57.2 | 85
367 | PASCHIM MEDINIPUR | SM/13166 | TARUA AND ADJOINING MOUJAS PWSS | TSM/014582 | 40034311 | New | MVS | GO2223008636PH | 12/10/2022 | 808.83 | 39.41 | 848.24 | Midnapore Division | Midnapore Mechanical Division | 87.29 | 0 | 33.4 | 0 | 120.69 | 87.29 | 0 | 33.4 | 0 | 120.69 | 14.23 | 20
368 | PASCHIM MEDINIPUR | SM/18540 | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015924 | 40053812 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1455.41 | 116.34 | 1571.76 | Midnapore Division | Midnapore Mechanical Division | 173.24 | 15.19 | 155.16 | 0 | 343.6 | 27.36 | 15.19 | 155.16 | 0 | 197.71 | 12.58 | 27
369 | PASCHIM MEDINIPUR | SM/15594 | TEGHARI AND ITS ADJOINING MOUZAS PWSS | TSM/017363 | 40044756 | New | MVS | GO2223013899PH | 15/02/2023 | 866.33 | 41.28 | 907.61 | Midnapore Division | Midnapore Mechanical Division | 99.23 | 25.12 | 0 | 0 | 124.35 | 0 | 25.12 | 0 | 0 | 25.12 | 2.77 | 45
370 | PASCHIM MEDINIPUR | SM/13175 | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | TSM/014123 | 40033764 | New | MVS | GO2223008645PH | 12/10/2022 | 714.55 | 36.72 | 751.27 | Midnapore Division | Jhargram Mechanical Division | 299.05 | 7.22 | 14.59 | 13.12 | 333.97 | 299.05 | 7.22 | 14.59 | 13.12 | 333.97 | 44.45 | 45
371 | PASCHIM MEDINIPUR | SM/15906 | THAUR AND ITS ADJOINING MOUZAS PWSS | TSM/017350 | 40044850 | New | MVS | GO2223013895PH | 15/02/2023 | 801.39 | 42.81 | 844.2 | Midnapore Division | Midnapore Mechanical Division | 0 | 24.66 | 31.89 | 0 | 56.55 | 0 | 24.66 | 31.89 | 0 | 56.55 | 6.7 | 35
372 | PASCHIM MEDINIPUR | SM/18236 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017054 | 40036238 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 941.53 | 84.47 | 1026.01 | Midnapore Division | Jhargram Mechanical Division | 18.23 | 22.25 | 0 | 0 | 40.48 | 9.36 | 22.25 | 0 | 0 | 31.61 | 3.08 | 22
373 | PASCHIM MEDINIPUR | SM/18027 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017058 | 40036324 | New | MVS | GO2223016943PH | 17/03/2023 | 653.31 | 84.47 | 737.78 | Midnapore Division | Jhargram Mechanical Division | 210.03 | 43.88 | 66.28 | 0 | 320.19 | 210.03 | 43.88 | 66.28 | 0 | 320.19 | 43.4 | 54
374 | PASCHIM MEDINIPUR | SM/18028 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017061 | 40036216 | New | MVS | GO2223016956PH | 17/03/2023 | 766 | 84.47 | 850.47 | Midnapore Division | Jhargram Mechanical Division | 178.37 | 34.31 | 32.25 | 0 | 244.93 | 178.37 | 34.31 | 32.25 | 0 | 244.93 | 28.8 | 34
375 | PASCHIM MEDINIPUR | SM/17574 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/017316 | 40053756 | New | SVS | GO2223017020PH | 18/03/2023 | 60.38 | 6.47 | 66.85 | Midnapore Division | Jhargram Mechanical Division | 25.89 | 4.69 | 0 | 0 | 30.59 | 25.89 | 4.69 | 0 | 0 | 30.59 | 45.76 | 95
376 | PASCHIM MEDINIPUR | SM/13111 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013441 | 40036225 | New | MVS | GO2223008542PH | 10/10/2022 | 412.79 | 42.24 | 455.02 | Midnapore Division | Jhargram Mechanical Division | 0 | 16.96 | 0 | 0 | 16.96 | 0 | 16.96 | 0 | 0 | 16.96 | 3.73 | 35
377 | PASCHIM MEDINIPUR | SM/18249 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/016011 | 40032738 | New | MVS | 1560/PHE-28011/235/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1073.7 | 84.47 | 1158.17 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 1.97 | 0 | 1.97 | 0 | 0 | 1.97 | 0 | 1.97 | 0.17 | 3
378 | PASCHIM MEDINIPUR | SM/15121 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/017060 | 40036309 | New | MVS | GO2223013232PH | 04/02/2023 | 700.22 | 84.47 | 784.7 | Midnapore Division | Jhargram Mechanical Division | 364.45 | 36.67 | 44.91 | 0 | 446.02 | 364.45 | 36.67 | 44.91 | 0 | 446.02 | 56.84 | 88
379 | PASCHIM MEDINIPUR | SM/18234 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017049 | 40036239 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1317.39 | 126.71 | 1444.1 | Midnapore Division | Jhargram Mechanical Division | 337.9 | 43.66 | 56.31 | 0 | 437.87 | 337.9 | 43.66 | 56.31 | 0 | 437.87 | 30.32 | 73
380 | PASCHIM MEDINIPUR | SM/19046 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017585 | 40043995 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 955.56 | 84.47 | 1040.03 | Midnapore Division | Jhargram Mechanical Division | 130.64 | 36.78 | 15.84 | 0 | 183.25 | 130.64 | 36.78 | 15.84 | 0 | 183.25 | 17.62 | 30
381 | PASCHIM MEDINIPUR | SM/18541 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017582 | 40053730 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1212.83 | 126.71 | 1339.54 | Midnapore Division | Jhargram Mechanical Division | 0 | 29.56 | 17.96 | 0 | 47.51 | 0 | 29.56 | 17.96 | 0 | 47.51 | 3.55 | 3
382 | PASCHIM MEDINIPUR | SM/15595 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017583 | 40044064 | New | MVS | GO2223013889PH | 15/02/2023 | 893.82 | 84.47 | 978.29 | Midnapore Division | Jhargram Mechanical Division | 86.03 | 24.71 | 16.63 | 0 | 127.38 | 86.03 | 24.71 | 16.63 | 0 | 127.38 | 13.02 | 34
383 | PASCHIM MEDINIPUR | SM/13167 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013440 | 40032983 | New | MVS | GO2223008638PH | 12/10/2022 | 899.66 | 84.47 | 984.13 | Midnapore Division | Jhargram Mechanical Division | 446.66 | 31.65 | 2.62 | 0 | 480.93 | 446.66 | 31.65 | 2.62 | 0 | 480.93 | 48.87 | 31
384 | PASCHIM MEDINIPUR | SM/18233 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | TSM/016008 | 40036224 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1042.56 | 84.47 | 1127.03 | Midnapore Division | Jhargram Mechanical Division | 184.03 | 27.08 | 0 | 0 | 211.1 | 184.03 | 27.08 | 0 | 0 | 211.1 | 18.73 | 18
385 | PASCHIM MEDINIPUR | SM/19047 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017584 | 40044032 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 915.55 | 84.47 | 1000.02 | Midnapore Division | Jhargram Mechanical Division | 20.63 | 6.8 | 33.74 | 0 | 61.17 | 16.14 | 6.8 | 33.74 | 0 | 56.68 | 5.67 | 27
386 | PASCHIM MEDINIPUR | SM/18032 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/016027 | 40036214 | New | MVS | GO2223016933PH | 17/03/2023 | 782.81 | 84.47 | 867.28 | Midnapore Division | Jhargram Mechanical Division | 224.29 | 23.95 | 46.53 | 0 | 294.77 | 224.29 | 23.95 | 46.53 | 0 | 294.77 | 33.99 | 36
387 | PASCHIM MEDINIPUR | SM/18237 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017039 | 40034524 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1285.92 | 84.47 | 1370.39 | Midnapore Division | Jhargram Mechanical Division | 0 | 6.8 | 69.82 | 0 | 76.63 | 0 | 6.8 | 69.82 | 0 | 76.63 | 5.59 | 6
388 | PASCHIM MEDINIPUR | SM/15122 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017053 | 40034548 | New | MVS | GO2223013234PH | 04/02/2023 | 668.96 | 84.47 | 753.44 | Midnapore Division | Jhargram Mechanical Division | 0 | 9.56 | 45.41 | 0 | 54.98 | 0 | 9.56 | 45.41 | 0 | 54.98 | 7.3 | 25
389 | PASCHIM MEDINIPUR | SM/16252 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013442 | 40036206 | New | MVS | GO2223014868PH | 24/02/2023 | 914.69 | 84.47 | 999.16 | Midnapore Division | Jhargram Mechanical Division | 226.6 | 18.75 | 51.44 | 0 | 296.79 | 226.6 | 18.75 | 51.44 | 0 | 296.79 | 29.7 | 42
390 | PASCHIM MEDINIPUR | SM/18235 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/016022 | 40036292 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1000.08 | 84.47 | 1084.55 | Midnapore Division | Jhargram Mechanical Division | 308.48 | 23.06 | 0 | 0 | 331.55 | 308.48 | 23.06 | 0 | 0 | 331.55 | 30.57 | 44
391 | PASCHIM MEDINIPUR | SM/17575 | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015589 | 40053749 | New | MVS | GO2223017023PH | 18/03/2023 | 352.38 | 72.16 | 424.54 | Midnapore Division | Midnapore Mechanical Division | 44.63 | 12.43 | 2.41 | 0 | 59.48 | 44.63 | 12.43 | 2.41 | 0 | 59.48 | 14.01 | 37
392 | PASCHIM MEDINIPUR | SM/18494 | TORIA PIPED WATER SUPPLY SCHEME | TSM/013444 | 40034393 | New | MVS | 2033/PHE-28011/25/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1060.88 | 39.84 | 1100.72 | Midnapore Division | Midnapore Mechanical Division | 293.49 | 30.03 | 0 | 0 | 323.51 | 293.49 | 30.03 | 0 | 0 | 323.51 | 29.39 | 40
393 | PASCHIM MEDINIPUR | SM/13112 | TRIKALPUR AND ADJOINING MOUJAS PWSS | TSM/014449 | 40031965 | New | MVS | GO2223008543PH | 10/10/2022 | 474.01 | 38.53 | 512.54 | Midnapore Division | Midnapore Mechanical Division | 156.98 | 6.29 | 7.42 | 15.33 | 186.02 | 156.98 | 6.29 | 7.42 | 15.33 | 186.02 | 36.29 | 75
394 | PASCHIM MEDINIPUR | SM/13049 | TRILOCHANPUR PWSS | TSM/011604 | 40031822 | New | MVS | GO2223008505PH | 29/09/2022 | 569.36 | 38.28 | 607.64 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 15.96 | 29.82 | 0 | 50.56 | 4.78 | 15.96 | 29.82 | 0 | 50.56 | 8.32 | 5
395 | PASCHIM MEDINIPUR | SM/13050 | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | TSM/013129 | 40031878 | New | MVS | GO2223008507PH | 29/09/2022 | 426.58 | 38.28 | 464.86 | Midnapore Division | Midnapore Mechanical Division | 37.43 | 10.56 | 10.85 | 9.64 | 68.49 | 0 | 10.56 | 10.85 | 9.64 | 31.06 | 6.68 | 10
396 | PASCHIM MEDINIPUR | SM/13131 | TUTRANGA AND ADJOINING MOUJAS PWSS | TSM/014384 | 40031916 | New | MVS | GO2223008535PH | 10/10/2022 | 439.25 | 38.53 | 477.78 | Midnapore Division | Midnapore Mechanical Division | 78.32 | 6.38 | 9.16 | 13.12 | 106.97 | 78.32 | 6.38 | 9.16 | 13.12 | 106.97 | 22.39 | 60
397 | PASCHIM MEDINIPUR | SM/15123 | UMRAPATA AND ADJOINING MOUJAS PWSS | TSM/016216 | 40035422 | New | MVS | GO2223013221PH | 04/02/2023 | 133.55 | 8.85 | 142.4 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 1.79 | 1.25 | 16
398 | PASCHIM MEDINIPUR | SM/13130 | URIYASHAI AND ADJOINING MOUJAS PWSS | TSM/014646 | 40031913 | New | MVS | GO2223008534PH | 10/10/2022 | 475.49 | 39.33 | 514.82 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 8.81 | 0 | 8.81 | 0 | 0 | 8.81 | 0 | 8.81 | 1.71 | 2
399 | PASCHIM MEDINIPUR | SM/13129 | UTATR KARKARA AND ADJOINING MOUJAS PWSS | TSM/014277 | 40031936 | New | MVS | GO2223008537PH | 10/10/2022 | 495.4 | 38.53 | 533.93 | Midnapore Division | Midnapore Mechanical Division | 58.24 | 10.11 | 9.18 | 6.56 | 84.09 | 58.24 | 10.11 | 9.18 | 6.56 | 84.09 | 15.75 | 64
400 | PASCHIM MEDINIPUR | SM/13810 | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME | TSM/014972 | 40034510 | New | MVS | GO2223009965PH | 22/11/2022 | 781.28 | 38.26 | 819.54 | Midnapore Division | Midnapore Mechanical Division | 230.85 | 19.68 | 0 | 0 | 250.53 | 221.63 | 19.68 | 0 | 0 | 241.31 | 29.44 | 41
Total | [9 empty] | 234041.9 | 18777.77 | 252819.68 |  |  | 57956.58 | 6159.78 | 6729.83 | 1897.44 | 72743.63 | 55088.44 | 5978.03 | 6729.83 | 1897.44 | 69693.74 | 27.57