## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PURBA MEDINIPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PURBA MEDINIPUR | SM/15037 | TULIA AND ADJOINING MOUJAS PWSS | TSM/015986 | 40049060 | New | MVS | GO2223013260PH | 04/02/2023 | 533.72 | 39.21 | 572.93 | Tamluk Division | Midnapore Mechanical Division | 65.22 | 27.06 | 19.81 | 0 | 112.1 | 65.22 | 27.06 | 19.81 | 0 | 112.1 | 19.57 | 68
2 | PURBA MEDINIPUR | SM/16711 | Augmentation of Ground Water Based Bagmari Water Supply Scheme | TSM/009993 | 40032669 | Augmentation | MVS | GO2223015966PH | 14/03/2023 | 309.03 | 30.1 | 339.13 | Tamluk Division | Midnapore Mechanical Division | 170.11 | 0.64 | 5.72 | 0 | 176.47 | 170.11 | 0.64 | 5.72 | 0 | 176.47 | 52.04 | 70
3 | PURBA MEDINIPUR | SM/11206 | Augmentation of Ground water Based Betkundu Water Supply Scheme | TSM/009994 | 40016974 | Augmentation | MVS | GO2223003927PH | 08/06/2022 | 1232.96 | 84.47 | 1317.43 | Tamluk Division | Midnapore Mechanical Division | 889.18 | 4.84 | 44.03 | 0 | 938.06 | 889.18 | 4.84 | 44.03 | 0 | 938.06 | 71.2 | 60
4 | PURBA MEDINIPUR | SM/10393 | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | TSM/009767 | 40005503 | Augmentation | MVS | GO2122011525PH | 29/03/2022 | 702.56 | 84.47 | 787.03 | Tamluk Division | Midnapore Mechanical Division | 510.26 | 0 | 40.39 | 0 | 550.65 | 510.26 | 0 | 40.39 | 0 | 550.65 | 69.97 | 95
5 | PURBA MEDINIPUR | SM/11948 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) | TSM/010119 | 40019018 | Augmentation | MVS | GO2223006676PH | 24/08/2022 | 406.59 | 126.71 | 533.3 | Tamluk Division | Midnapore Mechanical Division | 392.18 | 32.64 | 3.11 | 0 | 427.94 | 387.55 | 32.64 | 3.11 | 0 | 423.3 | 79.37 | 60
6 | PURBA MEDINIPUR | SM/11896 | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/010576 | 40018868 | Augmentation | MVS | GO2223006512PH | 18/08/2022 | 35.91 | 26.58 | 62.49 | Tamluk Division | Midnapore Mechanical Division | 0 | 9.66 | 0 | 0 | 9.66 | 0 | 9.66 | 0 | 0 | 9.66 | 15.46 | 35
7 | PURBA MEDINIPUR | SM/15038 | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018664 | 40052208 | Augmentation | MVS | GO2223013254PH | 04/02/2023 | 57.63 | 28 | 85.63 | Tamluk Division | Midnapore Mechanical Division | 35.49 | 6.02 | 0 | 0 | 41.51 | 35.49 | 6.02 | 0 | 0 | 41.51 | 48.48 | 40
8 | PURBA MEDINIPUR | SM/14843 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/019290 | 40052052 | Augmentation | MVS | GO2223012984PH | 03/02/2023 | 35.12 | 28 | 63.12 | Tamluk Division | Midnapore Mechanical Division | 13.01 | 7.18 | 0 | 0 | 20.19 | 13.01 | 7.18 | 0 | 0 | 20.19 | 31.98 | 40
9 | PURBA MEDINIPUR | SM/18765 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/019291 | 40052048 | Augmentation | MVS | 2530/PHE/IV/W-633/23 | 23/08/2023 | 35.12 | 28 | 63.12 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
10 | PURBA MEDINIPUR | SM/14844 | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018668 | 40052074 | Augmentation | MVS | GO2223012981PH | 03/02/2023 | 34.77 | 28 | 62.78 | Tamluk Division | Midnapore Mechanical Division | 22.79 | 14.8 | 0 | 0 | 37.59 | 22.79 | 14.8 | 0 | 0 | 37.59 | 59.87 | 25
11 | PURBA MEDINIPUR | SM/11887 | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | TSM/010579 | 40018781 | Augmentation | MVS | GO2223006376PH | 17/08/2022 | 30.7 | 26.58 | 57.27 | Tamluk Division | Midnapore Mechanical Division | 10.88 | 12.26 | 0 | 14.04 | 37.18 | 10.88 | 12.26 | 0 | 14.04 | 37.18 | 64.92 | 35
12 | PURBA MEDINIPUR | SM/17193 | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020309 | 40057086 | Augmentation | MVS | GO2223016093PH | 15/03/2023 | 44.49 | 36.25 | 80.74 | Tamluk Division | Midnapore Mechanical Division | 16.48 | 16.33 | 0 | 0 | 32.81 | 16.48 | 16.33 | 0 | 0 | 32.81 | 40.64 | 50
13 | PURBA MEDINIPUR | SM/16206 | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016264 | 6904605 | Augmentation | SVS | GO2223014874PH | 24/02/2023 | 32.54 | 42.24 | 74.78 | Tamluk Division | Midnapore Mechanical Division | 28.98 | 18.36 | 0 | 0 | 47.33 | 28.98 | 18.36 | 0 | 0 | 47.33 | 63.3 | 95
14 | PURBA MEDINIPUR | SM/16279 | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020317 | 40056981 | Augmentation | MVS | GO2223014872PH | 24/02/2023 | 44.49 | 36.25 | 80.74 | Tamluk Division | Midnapore Mechanical Division | 17.82 | 12.04 | 4.88 | 0 | 34.73 | 17.82 | 12.04 | 4.88 | 0 | 34.73 | 43.02 | 10
15 | PURBA MEDINIPUR | SM/16205 | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016267 | 40052584 | Augmentation | MVS | GO2223014873PH | 24/02/2023 | 33.14 | 42.24 | 75.38 | Tamluk Division | Midnapore Mechanical Division | 31.08 | 17.73 | 0 | 0 | 48.81 | 31.08 | 17.73 | 0 | 0 | 48.81 | 64.75 | 40
16 | PURBA MEDINIPUR | SM/17221 | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020313 | 40053276 | Augmentation | SVS | GO2223016101PH | 15/03/2023 | 44.49 | 36.25 | 80.74 | Tamluk Division | Midnapore Mechanical Division | 16.12 | 20.88 | 4.88 | 0 | 41.88 | 16.12 | 20.88 | 4.88 | 0 | 41.88 | 51.87 | 35
17 | PURBA MEDINIPUR | SM/16938 | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020322 | 40057078 | Augmentation | MVS | GO2223016546PH | 16/03/2023 | 44.49 | 36.25 | 80.74 | Tamluk Division | Midnapore Mechanical Division | 30.8 | 11.69 | 4.88 | 0 | 47.36 | 30.8 | 11.69 | 4.88 | 0 | 47.36 | 58.66 | 15
18 | PURBA MEDINIPUR | SM/16939 | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/020298 | 40053469 | Augmentation | MVS | GO2223016548PH | 16/03/2023 | 34.87 | 28 | 62.87 | Tamluk Division | Midnapore Mechanical Division | 0.83 | 0 | 0 | 0 | 0.83 | 0.83 | 0 | 0 | 0 | 0.83 | 1.32 | 15
19 | PURBA MEDINIPUR | SM/16204 | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016269 | 40052659 | Augmentation | MVS | GO2223014875PH | 24/02/2023 | 33.84 | 42.24 | 76.08 | Tamluk Division | Midnapore Mechanical Division | 31.36 | 16.57 | 0 | 0 | 47.92 | 31.36 | 16.57 | 0 | 0 | 47.92 | 62.99 | 30
20 | PURBA MEDINIPUR | SM/16390 | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020319 | 40057085 | Augmentation | MVS | GO2223014978PH | 28/02/2023 | 89.19 | 72.5 | 161.69 | Tamluk Division | Midnapore Mechanical Division | 60.86 | 9.43 | 0 | 0 | 70.29 | 60.86 | 9.43 | 0 | 0 | 70.29 | 43.47 | 40
21 | PURBA MEDINIPUR | SM/17194 | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020324 | 40057084 | Augmentation | MVS | GO2223016104PH | 15/03/2023 | 89.19 | 72.5 | 161.69 | Tamluk Division | Midnapore Mechanical Division | 35.83 | 22.64 | 10 | 0 | 68.48 | 35.83 | 22.64 | 10 | 0 | 68.48 | 42.35 | 40
22 | PURBA MEDINIPUR | SM/15036 | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/015459 | 40052399 | Augmentation | MVS | GO2223013262PH | 04/02/2023 | 133.78 | 108.75 | 242.53 | Tamluk Division | Midnapore Mechanical Division | 36.98 | 63.63 | 0 | 14.72 | 115.33 | 36.98 | 63.63 | 0 | 14.72 | 115.33 | 47.55 | 50
23 | PURBA MEDINIPUR | SM/12162 | ABAS BERYA & ADJOINING MOUZAS | TSM/013303 | 40021625 | New | MVS | GO2223007203PH | 07/09/2022 | 581.76 | 38.85 | 620.61 | Tamluk Division | Midnapore Mechanical Division | 103.04 | 18 | 27.36 | 0 | 148.41 | 101.03 | 18 | 27.36 | 0 | 146.4 | 23.59 | 30
24 | PURBA MEDINIPUR | SM/12131 | AGAR & ADJOINING MOUJAS PWSS | TSM/011926 | 40022775 | New | MVS | GO2223007253PH | 07/09/2022 | 350.8 | 37.78 | 388.58 | Tamluk Division | Midnapore Mechanical Division | 76.89 | 6.52 | 18.07 | 43.9 | 145.39 | 76.89 | 6.52 | 18.07 | 43.9 | 145.39 | 37.41 | 60
25 | PURBA MEDINIPUR | SM/15514 | AILAN AND IT'S ADJOINING MOUJAS PWSS | TSM/014592 | 40027224 | New | MVS | GO2223014005PH | 16/02/2023 | 1087.85 | 39.79 | 1127.65 | Tamluk Division | Midnapore Mechanical Division | 114.59 | 22.21 | 22.46 | 0 | 159.26 | 114.59 | 3.8 | 22.46 | 0 | 140.85 | 12.49 | 35
26 | PURBA MEDINIPUR | SM/13852 | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | TSM/015760 | 40026867 | New | SVS | GO2223010044PH | 25/11/2022 | 147.86 | 18.74 | 166.59 | Tamluk Division | Midnapore Mechanical Division | 28.29 | 13.27 | 0 | 0 | 41.55 | 28.29 | 13.27 | 0 | 0 | 41.55 | 24.94 | 70
27 | PURBA MEDINIPUR | SM/12174 | AJAYA & ADJOINING MOUJAS PWSS | TSM/013505 | 40021587 | New | MVS | GO2223007182PH | 07/09/2022 | 778.28 | 38.85 | 817.13 | Tamluk Division | Midnapore Mechanical Division | 432.68 | 24.09 | 39.53 | 7.83 | 504.13 | 432.68 | 24.09 | 39.53 | 7.83 | 504.13 | 61.69 | 75
28 | PURBA MEDINIPUR | SM/12320 | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | TSM/014317 | 40027188 | New | SVS | GO2223007329PH | 09/09/2022 | 636.37 | 38.39 | 674.76 | Tamluk Division | Midnapore Mechanical Division | 180.76 | 19.91 | 4.3 | 0 | 204.97 | 180.76 | 19.91 | 4.3 | 0 | 204.97 | 30.38 | 60
29 | PURBA MEDINIPUR | SM/12132 | AMARPUR & ADJOINING MOUZAS | TSM/013130 | 40022755 | New | MVS | GO2223007256PH | 07/09/2022 | 499.48 | 37.89 | 537.37 | Tamluk Division | Midnapore Mechanical Division | 175.32 | 21.59 | 21.29 | 0 | 218.2 | 175.32 | 21.59 | 21.29 | 0 | 218.2 | 40.61
30 | PURBA MEDINIPUR | SM/12634 | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | TSM/014306 | 40027162 | New | SVS | GO2223007815PH | 19/09/2022 | 464.75 | 38.85 | 503.6 | Tamluk Division | Midnapore Mechanical Division | 50.9 | 10.47 | 15.13 | 0 | 76.5 | 50.9 | 10.47 | 15.13 | 0 | 76.5 | 15.19 | 60
31 | PURBA MEDINIPUR | SM/15511 | AMRITBERYA AND ADJOINING MOUJAS | TSM/014710 | 40027196 | New | MVS | GO2223014007PH | 16/02/2023 | 983.99 | 40.74 | 1024.73 | Tamluk Division | Midnapore Mechanical Division | 346.75 | 31.48 | 23.26 | 0 | 401.49 | 346.75 | 31.48 | 23.26 | 0 | 401.49 | 39.18 | 35
32 | PURBA MEDINIPUR | SM/15462 | Augmentation of Astichak (Zone-I) PWSS | TSM/017768 | 40052341 | Augmentation | MVS | GO2223013272PH | 04/02/2023 | 590.24 | 88.97 | 679.21 | Tamluk Division | Midnapore Mechanical Division | 4.94 | 11.45 | 19.41 | 0 | 35.8 | 4.94 | 11.45 | 19.41 | 0 | 35.8 | 5.27 | 40
33 | PURBA MEDINIPUR | SM/15035 | Augmentation of Astichak (Zone-II) PWSS | TSM/017769 | 40052336 | Augmentation | MVS | GO2223013257PH | 04/02/2023 | 695.66 | 72.5 | 768.16 | Tamluk Division | Midnapore Mechanical Division | 406.56 | 25.66 | 22.68 | 0 | 454.91 | 406.56 | 25.66 | 22.68 | 0 | 454.91 | 59.22 | 20
34 | PURBA MEDINIPUR | SM/15034 | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | TSM/017807 | 40052290 | Augmentation | MVS | GO2223013253PH | 04/02/2023 | 557.36 | 78.48 | 635.84 | Tamluk Division | Midnapore Mechanical Division | 3.2 | 0 | 18.99 | 0 | 22.19 | 3.2 | 0 | 18.99 | 0 | 22.19 | 3.49 | 15
35 | PURBA MEDINIPUR | SM/16464 | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | TSM/017823 | 40052287 | Augmentation | MVS | GO2223015236PH | 03/03/2023 | 587.34 | 78.48 | 665.82 | Tamluk Division | Midnapore Mechanical Division | 3.49 | 0 | 0 | 0 | 3.49 | 3.49 | 0 | 0 | 0 | 3.49 | 0.52 | 10
36 | PURBA MEDINIPUR | SM/16194 | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | TSM/017824 | 40056794 | Augmentation | MVS | GO2223014878PH | 24/02/2023 | 645.77 | 84.84 | 730.61 | Tamluk Division | Midnapore Mechanical Division | 90.84 | 0 | 119.43 | 0 | 210.27 | 90.84 | 0 | 119.43 | 0 | 210.27 | 28.78 | 20
37 | PURBA MEDINIPUR | SM/16946 | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) | TSM/020297 | 40056799 | Augmentation | MVS | GO2223016551PH | 16/03/2023 | 85.63 | 0 | 85.63 | Tamluk Division |  | 56.28 | 0 | 0 | 0 | 56.28 | 56.28 | 0 | 0 | 0 | 56.28 | 65.72 | 15
38 | PURBA MEDINIPUR | SM/14486 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017387 | 40062608 | Augmentation | MVS | GO2223012341PH | 20/01/2023 | 0 | 42.52 | 42.52 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
39 | PURBA MEDINIPUR | SM/11920 | Augmentation of Ground Water based Jalpai Water Supply Scheme. | TSM/011021 | 40018956 | Augmentation | MVS | GO2223006627PH | 22/08/2022 | 1898.55 | 110.9 | 2009.45 | Tamluk Division | Midnapore Mechanical Division | 1025.75 | 32.09 | 182.14 | 19.44 | 1259.41 | 1025.75 | 32.09 | 182.14 | 19.44 | 1259.41 | 62.67 | 60
40 | PURBA MEDINIPUR | SM/11474 | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010400 | 40016828 | Augmentation | MVS | GO2223005071PH | 14/07/2022 | 914.51 | 82.5 | 997.01 | Tamluk Division | Midnapore Mechanical Division | 367.76 | 25.86 | 129.36 | 16.09 | 539.08 | 367.76 | 25.86 | 129.36 | 16.09 | 539.08 | 54.07 | 70
41 | PURBA MEDINIPUR | SM/11549 | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011087 | 40016983 | Augmentation | MVS | GO2223005378PH | 22/07/2022 | 823.95 | 26.58 | 850.53 | Tamluk Division | Midnapore Mechanical Division | 472.72 | 25.8 | 87.56 | 16.11 | 602.2 | 472.72 | 25.8 | 87.56 | 16.11 | 602.2 | 70.8 | 56
42 | PURBA MEDINIPUR | SM/09337 | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008486 | 8390580 | Augmentation | MVS | GO2122005383PH | 12/11/2021 | 445.37 | 84.47 | 529.85 | Tamluk Division | Midnapore Mechanical Division | 311.16 | 21.18 | 21.85 | 52.33 | 406.52 | 310.97 | 21.18 | 21.85 | 52.33 | 406.33 | 76.69 | 69
43 | PURBA MEDINIPUR | SM/14113 | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | TSM/009748 | 40005488 | Augmentation | MVS | GO2223011502PH | 02/01/2023 | 1216.2 | 84.47 | 1300.67 | Tamluk Division | Midnapore Mechanical Division | 716.22 | 33.75 | 118.16 | 0 | 868.13 | 716.22 | 33.75 | 118.16 | 0 | 868.13 | 66.74 | 40
44 | PURBA MEDINIPUR | SM/09336 | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008492 | 8390594 | Augmentation | SVS | GO2122005404PH | 12/11/2021 | 471.86 | 84.47 | 556.34 | Tamluk Division | Midnapore Mechanical Division | 283.23 | 25.44 | 29.29 | 43.29 | 381.24 | 283.23 | 25.44 | 29.29 | 43.29 | 381.24 | 68.53 | 65
45 | PURBA MEDINIPUR | SM/09913 | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008359 | 40001096 | Augmentation | MVS | GO2122006633PH | 10/12/2021 | 1104.23 | 0 | 1104.23 | Tamluk Division | Midnapore Mechanical Division | 749.69 | 0 | 73.89 | 15.3 | 838.88 | 749.69 | 0 | 73.89 | 15.3 | 838.88 | 75.97 | 65
46 | PURBA MEDINIPUR | SM/10125 | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | TSM/009104 | 40007339 | Augmentation | MVS | GO2122009414PH | 08/02/2022 | 1866.71 | 211.18 | 2077.89 | Tamluk Division | Midnapore Mechanical Division | 1296.34 | 22.64 | 57.51 | 34.4 | 1410.88 | 1296.34 | 22.64 | 57.51 | 34.4 | 1410.88 | 67.9 | 95
47 | PURBA MEDINIPUR | SM/11553 | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010395 | 40016985 | Augmentation | MVS | GO2223005391PH | 22/07/2022 | 865.03 | 79.74 | 944.76 | Tamluk Division | Midnapore Mechanical Division | 364.21 | 50.15 | 31.69 | 0 | 446.04 | 364.21 | 50.15 | 31.69 | 0 | 446.04 | 47.21 | 55
48 | PURBA MEDINIPUR | SM/09444 | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008974 | 8390702 | Augmentation | MVS | GO2122005599PH | 19/11/2021 | 682.64 | 43.88 | 726.52 | Tamluk Division | Midnapore Mechanical Division | 438.42 | 9.38 | 17.79 | 0 | 465.58 | 436.59 | 9.38 | 17.79 | 0 | 463.76 | 63.83 | 78
49 | PURBA MEDINIPUR | SM/09402 | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008484 | 8390413 | Augmentation | SVS | GO2122005503PH | 17/11/2021 | 450.55 | 84.47 | 535.02 | Tamluk Division | Midnapore Mechanical Division | 225.34 | 19.27 | 26.09 | 15.33 | 286.03 | 225.34 | 19.27 | 26.09 | 15.33 | 286.03 | 53.46 | 70
50 | PURBA MEDINIPUR | SM/10684 | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | TSM/008363 | 40013982 | Augmentation | MVS | GO2223000914PH | 06/05/2022 | 1309.53 | 0 | 1309.53 | Tamluk Division | Midnapore Mechanical Division | 1041.22 | 0 | 121.48 | 0 | 1162.7 | 1041.22 | 0 | 121.48 | 0 | 1162.7 | 88.79 | 78
51 | PURBA MEDINIPUR | SM/11473 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010401 | 40016835 | Augmentation | MVS | GO2223005072PH | 14/07/2022 | 846.9 | 26.58 | 873.48 | Tamluk Division | Midnapore Mechanical Division | 119.47 | 24.61 | 83.51 | 19.89 | 247.48 | 119.47 | 24.61 | 83.51 | 19.89 | 247.48 | 28.33 | 50
52 | PURBA MEDINIPUR | SM/11472 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010402 | 40016836 | Augmentation | MVS | GO2223005073PH | 14/07/2022 | 719 | 115.19 | 834.19 | Tamluk Division | Midnapore Mechanical Division | 575.73 | 4.12 | 15.11 | 0 | 594.96 | 575.73 | 4.12 | 15.11 | 0 | 594.96 | 71.32 | 65
53 | PURBA MEDINIPUR | SM/11471 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010403 | 40016838 | Augmentation | MVS | GO2223005074PH | 14/07/2022 | 718.79 | 26.58 | 745.37 | Tamluk Division | Midnapore Mechanical Division | 266.58 | 17.72 | 0 | 19.11 | 303.41 | 266.58 | 17.72 | 0 | 19.11 | 303.41 | 40.71 | 35
54 | PURBA MEDINIPUR | SM/11470 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010432 | 40016839 | Augmentation | MVS | GO2223005076PH | 14/07/2022 | 750.85 | 119.08 | 869.93 | Tamluk Division | Midnapore Mechanical Division | 532.78 | 0 | 140.16 | 0 | 672.93 | 532.78 | 0 | 140.16 | 0 | 672.93 | 77.36 | 47
55 | PURBA MEDINIPUR | SM/09334 | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | TSM/008497 | 8390611 | Augmentation | MVS | GO2122005384PH | 12/11/2021 | 650.4 | 53.89 | 704.29 | Tamluk Division | Midnapore Mechanical Division | 392.36 | 20.4 | 52.29 | 0 | 465.05 | 392.36 | 20.4 | 52.29 | 0 | 465.05 | 66.03 | 98
56 | PURBA MEDINIPUR | SM/09335 | Augmentation of Ground Water Based Piped Supply Scheme for Majna | TSM/008493 | 8390601 | Augmentation | MVS | GO2122005402PH | 12/11/2021 | 502.96 | 53.89 | 556.85 | Tamluk Division | Midnapore Mechanical Division | 327.3 | 8.19 | 35.39 | 0 | 370.87 | 327.3 | 8.19 | 35.39 | 0 | 370.87 | 66.6 | 98
57 | PURBA MEDINIPUR | SM/12487 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | TSM/012804 | 40022589 | Augmentation | MVS | GO2223007655PH | 13/09/2022 | 945.6 | 43.71 | 989.31 | Tamluk Division | Midnapore Mechanical Division | 210.9 | 4.79 | 32.07 | 14.1 | 261.86 | 210.9 | 4.79 | 32.07 | 14.1 | 261.86 | 26.47 | 40
58 | PURBA MEDINIPUR | SM/12488 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | TSM/012805 | 40022590 | Augmentation | MVS | GO2223007656PH | 13/09/2022 | 666.43 | 74.49 | 740.92 | Tamluk Division | Midnapore Mechanical Division | 274.12 | 26.33 | 64.73 | 25.25 | 390.43 | 274.12 | 26.33 | 64.73 | 25.25 | 390.43 | 52.69 | 85
59 | PURBA MEDINIPUR | SM/15635 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. | TSM/009926 | 40052416 | Augmentation | MVS | GO2223014256PH | 20/02/2023 | 58.07 | 0 | 58.07 | Tamluk Division |  | 55.82 | 0 | 0 | 0 | 55.82 | 55.82 | 0 | 0 | 0 | 55.82 | 96.13 | 35
60 | PURBA MEDINIPUR | SM/10072 | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | TSM/009590 | 40003113 | Augmentation | MVS | GO2122008782PH | 27/01/2022 | 565.95 | 15.81 | 581.76 | Tamluk Division | Midnapore Mechanical Division | 284.72 | 0 | 21.44 | 0 | 306.15 | 284.72 | 0 | 21.44 | 0 | 306.15 | 52.63 | 50
61 | PURBA MEDINIPUR | SM/16712 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | TSM/009925 | 40049962 | Augmentation | MVS | GO2223015966PH | 14/03/2023 | 101.12 | 42.24 | 143.36 | Tamluk Division | Midnapore Mechanical Division | 54.68 | 14.83 | 0 | 0 | 69.52 | 54.68 | 14.83 | 0 | 0 | 69.52 | 48.49 | 35
62 | PURBA MEDINIPUR | SM/12489 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | TSM/012050 | 40022592 | Augmentation | MVS | GO2223007659PH | 13/09/2022 | 658.8 | 53.89 | 712.69 | Tamluk Division | Midnapore Mechanical Division | 282.37 | 19.41 | 100.9 | 0 | 402.68 | 282.37 | 19.41 | 100.9 | 0 | 402.68 | 56.5 | 42
63 | PURBA MEDINIPUR | SM/12490 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | TSM/012051 | 40022593 | Augmentation | MVS | GO2223007663PH | 13/09/2022 | 587.96 | 74.49 | 662.45 | Tamluk Division | Midnapore Mechanical Division | 292.53 | 30.6 | 51.2 | 0 | 374.34 | 292.53 | 30.6 | 51.2 | 0 | 374.34 | 56.51 | 80
64 | PURBA MEDINIPUR | SM/15510 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | TSM/012055 | 40032680 | Augmentation | MVS | GO2223014003PH | 16/02/2023 | 1280.73 | 125.46 | 1406.2 | Tamluk Division | Midnapore Mechanical Division | 312.38 | 28.42 | 224.8 | 0 | 565.6 | 312.38 | 28.42 | 224.8 | 0 | 565.6 | 40.22 | 15
65 | PURBA MEDINIPUR | SM/09034 | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | TSM/008361 | 8390160 | Augmentation | SVS | GO2122004725PH | 30/10/2021 | 829.85 | 0 | 829.85 | Tamluk Division | Midnapore Mechanical Division | 488.43 | 0 | 21.62 | 17.25 | 527.31 | 488.43 | 0 | 21.62 | 17.25 | 527.31 | 63.54 | 95
66 | PURBA MEDINIPUR | SM/09912 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | TSM/008360 | 40001097 | Augmentation | MVS | GO2122006633PH | 10/12/2021 | 975.56 | 53.89 | 1029.45 | Tamluk Division | Midnapore Mechanical Division | 652.62 | 14.5 | 35.35 | 15.7 | 718.16 | 652.62 | 14.5 | 35.35 | 15.7 | 718.16 | 69.76 | 100
67 | PURBA MEDINIPUR | SM/10126 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | TSM/009080 | 40007368 | Augmentation | MVS | GO2122009414PH | 08/02/2022 | 1091.29 | 53.89 | 1145.17 | Tamluk Division | Midnapore Mechanical Division | 602.91 | 10.24 | 42.12 | 0 | 655.27 | 602.91 | 10.24 | 42.12 | 0 | 655.27 | 57.22 | 81
68 | PURBA MEDINIPUR | SM/09288 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | TSM/008356 | 8390093 | Augmentation | MVS | GO2122004876PH | 03/11/2021 | 796.45 | 53.89 | 850.34 | Tamluk Division | Midnapore Mechanical Division | 485.58 | 14.63 | 29.45 | 30.1 | 559.76 | 485.58 | 14.63 | 29.45 | 30.1 | 559.76 | 65.83 | 90
69 | PURBA MEDINIPUR | SM/10323 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | TSM/009492 | 40003114 | Augmentation | MVS | GO2122010463PH | 07/03/2022 | 1109.82 | 56.98 | 1166.79 | Tamluk Division | Midnapore Mechanical Division | 475.25 | 12.06 | 212.6 | 18.12 | 718.04 | 472.29 | 12.06 | 212.6 | 18.12 | 715.07 | 61.29 | 86
70 | PURBA MEDINIPUR | SM/09447 | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | TSM/008927 | 8390666 | Augmentation | MVS | GO2122005596PH | 19/11/2021 | 609.16 | 53.89 | 663.05 | Tamluk Division | Midnapore Mechanical Division | 277.53 | 5.82 | 28.02 | 9.61 | 320.98 | 277.53 | 5.82 | 28.02 | 9.61 | 320.98 | 48.41 | 75
71 | PURBA MEDINIPUR | SM/10127 | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | TSM/009079 | 40007359 | Augmentation | MVS | GO2122009414PH | 08/02/2022 | 1373.49 | 45.15 | 1418.64 | Tamluk Division | Midnapore Mechanical Division | 753.45 | 17.4 | 50.48 | 0 | 821.33 | 751.96 | 17.4 | 50.48 | 0 | 819.84 | 57.79 | 85
72 | PURBA MEDINIPUR | SM/10344 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda | TSM/009494 | 40003128 | Augmentation | SVS | GO2122010922PH | 16/03/2022 | 898.12 | 53.89 | 952 | Tamluk Division |  | 455.51 | 13.86 | 23.01 | 0 | 492.39 | 455.51 | 13.86 | 23.01 | 0 | 492.39 | 51.72 | 70
73 | PURBA MEDINIPUR | SM/10128 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | TSM/009078 | 40007365 | Augmentation | MVS | GO2122009414PH | 08/02/2022 | 1574.89 | 59.71 | 1634.61 | Tamluk Division | Midnapore Mechanical Division | 563.08 | 14.82 | 29.48 | 14.91 | 622.3 | 563.08 | 14.82 | 29.48 | 14.91 | 622.3 | 38.07 | 53
74 | PURBA MEDINIPUR | SM/09446 | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | TSM/008948 | 8390680 | Augmentation | MVS | GO2122005597PH | 19/11/2021 | 657.09 | 53.89 | 710.98 | Tamluk Division | Midnapore Mechanical Division | 373.91 | 17.5 | 35.55 | 0 | 426.96 | 373.91 | 13.96 | 35.55 | 0 | 423.41 | 59.55 | 87
75 | PURBA MEDINIPUR | SM/12491 | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | TSM/011282 | 40037058 | Augmentation | MVS | GO2223007658PH | 13/09/2022 | 665.22 | 80.31 | 745.53 | Tamluk Division | Midnapore Mechanical Division | 212.52 | 30.21 | 60.42 | 30.16 | 333.32 | 212.52 | 30.21 | 60.42 | 30.16 | 333.32 | 44.71 | 35
76 | PURBA MEDINIPUR | SM/12118 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | TSM/010583 | 40021630 | Augmentation | MVS | GO2223007089PH | 06/09/2022 | 1026 | 53.89 | 1079.89 | Tamluk Division | Midnapore Mechanical Division | 474.08 | 32.91 | 157.8 | 0 | 664.79 | 474.08 | 32.91 | 157.8 | 0 | 664.79 | 61.56 | 44
77 | PURBA MEDINIPUR | SM/13716 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | TSM/010584 | 40031971 | Augmentation | MVS | GO2223009856PH | 17/11/2022 | 973.94 | 86.14 | 1060.08 | Tamluk Division | Midnapore Mechanical Division | 408.44 | 44.97 | 144.04 | 0 | 597.45 | 408.44 | 44.97 | 144.04 | 0 | 597.45 | 56.36 | 20
78 | PURBA MEDINIPUR | SM/16713 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | TSM/009924 | 40049978 | Augmentation | MVS | GO2223015966PH | 14/03/2023 | 98.13 | 42.24 | 140.37 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
79 | PURBA MEDINIPUR | SM/09287 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | TSM/008358 | 8390112 | Augmentation | MVS | GO2122004872PH | 03/11/2021 | 324.6 | 24.87 | 349.47 | Tamluk Division | Midnapore Mechanical Division | 258.09 | 11.28 | 5.77 | 0 | 275.14 | 258.01 | 11.28 | 5.77 | 0 | 275.06 | 78.71 | 98
80 | PURBA MEDINIPUR | SM/10342 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | TSM/009493 | 40005476 | Augmentation | MVS | GO2122010691PH | 14/03/2022 | 746.25 | 53.89 | 800.14 | Tamluk Division | Midnapore Mechanical Division | 389.61 | 16.69 | 0 | 0 | 406.29 | 389.61 | 16.69 | 0 | 0 | 406.29 | 50.78 | 89
81 | PURBA MEDINIPUR | SM/09445 | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | TSM/008950 | 8390690 | Augmentation | MVS | GO2122005598PH | 19/11/2021 | 768.33 | 53.89 | 822.22 | Tamluk Division | Midnapore Mechanical Division | 501.11 | 3.1 | 55.87 | 0 | 560.08 | 501.11 | 3.1 | 55.87 | 0 | 560.08 | 68.12 | 80
82 | PURBA MEDINIPUR | SM/11984 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011103 | 40019992 | Augmentation | MVS | GO2223006892PH | 01/09/2022 | 1327.47 | 126.71 | 1454.18 | Tamluk Division | Midnapore Mechanical Division | 904.75 | 38.34 | 263.71 | 0 | 1206.8 | 904.75 | 38.34 | 263.71 | 0 | 1206.8 | 82.99 | 90
83 | PURBA MEDINIPUR | SM/11469 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011102 | 40016827 | Augmentation | MVS | GO2223005077PH | 14/07/2022 | 485.8 | 84.47 | 570.27 | Tamluk Division | Midnapore Mechanical Division | 281.36 | 10.96 | 0.81 | 70.35 | 363.48 | 281.36 | 10.96 | 0.81 | 70.35 | 363.48 | 63.74 | 90
84 | PURBA MEDINIPUR | SM/11617 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | TSM/011146 | 40017031 | Augmentation | MVS | GO2223005566PH | 26/07/2022 | 682.87 | 160.21 | 843.08 | Tamluk Division | Midnapore Mechanical Division | 303.94 | 31.44 | 80.59 | 0 | 415.97 | 303.94 | 31.44 | 80.59 | 0 | 415.97 | 49.34 | 70
85 | PURBA MEDINIPUR | SM/11618 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | TSM/011144 | 40017032 | Augmentation | MVS | GO2223005564PH | 26/07/2022 | 806.74 | 0 | 806.74 | Tamluk Division |  | 598.73 | 0 | 189.75 | 0 | 788.49 | 598.73 | 0 | 189.75 | 0 | 788.49 | 97.74 | 85
86 | PURBA MEDINIPUR | SM/11616 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) | TSM/011148 | 40017033 | Augmentation | MVS | GO2223005567PH | 26/07/2022 | 838.08 | 0 | 838.08 | Tamluk Division |  | 711.24 | 0 | 0 | 0 | 711.24 | 711.24 | 0 | 0 | 0 | 711.24 | 84.87 | 82
87 | PURBA MEDINIPUR | SM/11554 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | TSM/011149 | 40016989 | Augmentation | MVS | GO2223005429PH | 22/07/2022 | 531.17 | 211.18 | 742.35 | Tamluk Division | Midnapore Mechanical Division | 225.36 | 45.89 | 219.11 | 0 | 490.36 | 225.36 | 45.89 | 219.11 | 0 | 490.36 | 66.05 | 65
88 | PURBA MEDINIPUR | SM/10681 | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008372 | 40013978 | Augmentation | MVS | GO2223000914PH | 06/05/2022 | 1073.49 | 0 | 1073.49 | Tamluk Division | Midnapore Mechanical Division | 500.97 | 0 | 57.24 | 15.24 | 573.44 | 500.97 | 0 | 57.24 | 15.24 | 573.44 | 53.42 | 55
89 | PURBA MEDINIPUR | SM/11552 | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | TSM/010673 | 40016980 | Augmentation | MVS | GO2223005401PH | 22/07/2022 | 591.01 | 26.58 | 617.59 | Tamluk Division | Midnapore Mechanical Division | 323.26 | 19.48 | 7 | 1.75 | 351.49 | 323.26 | 19.48 | 7 | 1.75 | 351.49 | 56.91 | 50
90 | PURBA MEDINIPUR | SM/10121 | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008977 | 40007389 | Augmentation | MVS | GO2122009407PH | 08/02/2022 | 2188.12 | 126.71 | 2314.83 | Tamluk Division | Midnapore Mechanical Division | 1391.26 | 47.28 | 148.36 | 49.78 | 1636.68 | 1391.26 | 47.25 | 148.36 | 49.78 | 1636.65 | 70.7 | 70
91 | PURBA MEDINIPUR | SM/09920 | Augmentation of Madhakhali piped water supply scheme. | TSM/005363 | 40001085 | Augmentation | MVS | GO2122006634PH | 10/12/2021 | 2079.8 | 253.42 | 2333.22 | Tamluk Division | Midnapore Mechanical Division | 1279 | 83.69 | 78.88 | 42.03 | 1483.62 | 1279 | 83.69 | 78.88 | 42.03 | 1483.62 | 63.59 | 74
92 | PURBA MEDINIPUR | SM/11614 | Augmentation of Moyna (Zone-I) PWSS | TSM/011492 | 40017034 | Augmentation | MVS | GO2223005570PH | 26/07/2022 | 913.93 | 84.47 | 998.4 | Tamluk Division | Midnapore Mechanical Division | 362.47 | 36.43 | 118.56 | 32.49 | 549.95 | 362.47 | 36.43 | 118.56 | 32.49 | 549.95 | 55.08 | 40
93 | PURBA MEDINIPUR | SM/11639 | Augmentation of Moyna (Zone-II) PWSS | TSM/011493 | 40017459 | Augmentation | MVS | GO2223005649PH | 27/07/2022 | 863.46 | 126.71 | 990.17 | Tamluk Division | Midnapore Mechanical Division | 522.49 | 52.41 | 97.08 | 47.42 | 719.39 | 522.49 | 52.41 | 97.08 | 47.42 | 719.39 | 72.65 | 45
94 | PURBA MEDINIPUR | SM/14845 | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/018665 | 40052086 | Augmentation | MVS | GO2223012986PH | 03/02/2023 | 40.16 | 26.58 | 66.74 | Tamluk Division | Midnapore Mechanical Division | 28.5 | 9.81 | 0 | 0 | 38.32 | 28.5 | 9.81 | 0 | 0 | 38.32 | 57.41 | 30
95 | PURBA MEDINIPUR | SM/12485 | Augmentation of Ramnagar (Zone-I) PWSS | TSM/012859 | 40022995 | Augmentation | MVS | GO2223007653PH | 13/09/2022 | 750.75 | 84.47 | 835.22 | Tamluk Division | Midnapore Mechanical Division | 177.08 | 2.66 | 74.69 | 0 | 254.43 | 177.08 | 2.66 | 74.69 | 0 | 254.43 | 30.46 | 30
96 | PURBA MEDINIPUR | SM/12486 | Augmentation of Ramnagar (Zone-II) PWSS | TSM/012861 | 40023004 | Augmentation | MVS | GO2223007654PH | 13/09/2022 | 805.11 | 84.47 | 889.59 | Tamluk Division | Midnapore Mechanical Division | 193.8 | 21.7 | 69.36 | 34.39 | 319.26 | 193.8 | 21.7 | 69.36 | 34.39 | 319.26 | 35.89 | 90
97 | PURBA MEDINIPUR | SM/09919 | Augmentation of Suadighi piped water supply scheme. | TSM/005364 | 40001087 | Augmentation | MVS | GO2122006634PH | 10/12/2021 | 1968.69 | 253.42 | 2222.11 | Tamluk Division | Midnapore Mechanical Division | 977.89 | 72.19 | 48.64 | 80.88 | 1179.6 | 977.89 | 72.19 | 48.64 | 80.88 | 1179.6 | 53.08 | 50
98 | PURBA MEDINIPUR | SM/13696 | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | TSM/015381 | 40026872 | New | MVS | GO2223009728PH | 14/11/2022 | 385.67 | 36.7 | 422.36 | Tamluk Division | Midnapore Mechanical Division | 3.2 | 29.83 | 12.72 | 0 | 45.75 | 3.2 | 29.83 | 12.72 | 0 | 45.75 | 10.83
99 | PURBA MEDINIPUR | SM/13887 | BADALPUR AND IT'S ADJOINING MOUJAS | TSM/015813 | 40027023 | New | MVS | GO2223010052PH | 25/11/2022 | 344.96 | 36.7 | 381.66 | Tamluk Division | Midnapore Mechanical Division | 240.46 | 27.79 | 6.05 | 0 | 274.31 | 240.46 | 27.79 | 6.05 | 0 | 274.31 | 71.87 | 90
100 | PURBA MEDINIPUR | SM/15852 | BADALPUR PIPED WATER SUPPLY SCHEME. | TSM/020433 | 40052296 | New | SVS | GO2223014237PH | 20/02/2023 | 63.71 | 10.68 | 74.39 | Tamluk Division | Midnapore Mechanical Division | 0.95 | 0.86 | 5.14 | 0 | 6.96 | 0.95 | 0.86 | 5.14 | 0 | 6.96 | 9.35 | 5
101 | PURBA MEDINIPUR | SM/12429 | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | TSM/014858 | 40025901 | New | MVS | GO2223007624PH | 13/09/2022 | 522.78 | 37.64 | 560.42 | Tamluk Division | Midnapore Mechanical Division | 267.08 | 30.07 | 40.86 | 0 | 338.01 | 267.08 | 30.07 | 40.86 | 0 | 338.01 | 60.31 | 75
102 | PURBA MEDINIPUR | SM/13854 | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | TSM/016073 | 40026971 | New | MVS | GO2223010104PH | 25/11/2022 | 710.44 | 38.88 | 749.32 | Tamluk Division | Midnapore Mechanical Division | 124.43 | 3.63 | 38.8 | 0 | 166.86 | 124.43 | 3.63 | 38.8 | 0 | 166.86 | 22.27 | 10
103 | PURBA MEDINIPUR | SM/12169 | BAHADURPUR AND ADJOINING MOUJAS PWSS | TSM/013492 | 40021599 | New | MVS | GO2223007190PH | 07/09/2022 | 876.57 | 38.85 | 915.42 | Tamluk Division | Midnapore Mechanical Division | 311.18 | 5.41 | 74.94 | 48.98 | 440.51 | 311.18 | 5.41 | 74.94 | 48.98 | 440.51 | 48.12 | 20
104 | PURBA MEDINIPUR | SM/08879 | Baharampur Piped Water Supply Scheme. | TSM/005079 | 8384579 | New | MVS | GO2122003549PH | 24/09/2021 | 631.47 | 57.17 | 688.64 | Tamluk Division | Midnapore Mechanical Division | 501.56 | 24.06 | 20.11 | 15.66 | 561.38 | 501.56 | 24.06 | 20.11 | 15.66 | 561.38 | 81.52 | 99
105 | PURBA MEDINIPUR | SM/14455 | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | TSM/017200 | 40026731 | New | MVS | GO2223012277PH | 20/01/2023 | 375.45 | 36.98 | 412.43 | Tamluk Division | Midnapore Mechanical Division | 136.69 | 19.07 | 29.96 | 0 | 185.73 | 136.69 | 19.07 | 29.96 | 0 | 185.73 | 45.03 | 25
106 | PURBA MEDINIPUR | SM/12290 | BAISPUR AND ADJOINING MOUJAS PWSS | TSM/014224 | 40023011 | New | MVS | GO2223007333PH | 09/09/2022 | 456.99 | 38.85 | 495.84 | Tamluk Division | Midnapore Mechanical Division | 164.98 | 15.44 | 17.53 | 0 | 197.95 | 164.98 | 15.44 | 17.53 | 0 | 197.95 | 39.92 | 50
107 | PURBA MEDINIPUR | SM/12146 | BAKCHA AND ADJOINING MOUJAS PWSS | TSM/013173 | 40022434 | New | MVS | GO2223007206PH | 07/09/2022 | 584.68 | 38.85 | 623.54 | Tamluk Division | Midnapore Mechanical Division | 269.47 | 31.2 | 43.81 | 0 | 344.49 | 269.47 | 31.2 | 43.81 | 0 | 344.49 | 55.25 | 80
108 | PURBA MEDINIPUR | SM/13851 | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | TSM/016024 | 40026864 | New | SVS | GO2223010094PH | 25/11/2022 | 158.07 | 9.87 | 167.94 | Tamluk Division | Midnapore Mechanical Division | 66.17 | 0 | 0 | 0 | 66.17 | 66.17 | 0 | 0 | 0 | 66.17 | 39.4 | 15
109 | PURBA MEDINIPUR | SM/09073 | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S | TSM/008440 | 7326702 | Retrofitting | SVS | GO2122004573PH | 28/10/2021 | 21.74 | 0 | 21.74 | Tamluk Division | Midnapore Mechanical Division | 20.5 | 0 | 0 | 0 | 20.5 | 18.98 | 0 | 0 | 0 | 18.98 | 87.3 | 95
110 | PURBA MEDINIPUR | SM/16469 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M | TSM/018277 | 40049143 | Retrofitting | MVS | GO2223015244PH | 03/03/2023 | 108.21 | 0 | 108.21 | Tamluk Division |  | 79.29 | 0 | 0 | 0 | 79.29 | 79.29 | 0 | 0 | 0 | 79.29 | 73.28 | 50
111 | PURBA MEDINIPUR | SM/09443 | Balance Work for Retrofitting to Accommodate FHTC (152 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of different nodal point of Dona Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk | TSM/009044 | 7326710 | Retrofitting | MVS | GO2122005587PH | 19/11/2021 | 48.34 | 0 | 48.34 | Tamluk Division |  | 47.35 | 0 | 0 | 0 | 47.35 | 45.8 | 0 | 0 | 0 | 45.8 | 94.75 | 99
112 | PURBA MEDINIPUR | SM/10434 | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, | TSM/009921 | 6328427 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 82 | 0 | 82 | Tamluk Division |  | 79.61 | 0 | 0 | 0 | 79.61 | 79.61 | 0 | 0 | 0 | 79.61 | 97.09 | 100
113 | PURBA MEDINIPUR | SM/16468 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) | TSM/018312 | 40049124 | Retrofitting | MVS | GO2223015242PH | 03/03/2023 | 34.18 | 0 | 34.18 | Tamluk Division |  | 30.37 | 0 | 0 | 0 | 30.37 | 30.37 | 0 | 0 | 0 | 30.37 | 88.84 | 95
114 | PURBA MEDINIPUR | SM/16452 | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me | TSM/013424 | 40048879 | Retrofitting | MVS | GO2223015246PH | 03/03/2023 | 110.15 | 0 | 110.15 | Tamluk Division |  | 79.22 | 0 | 0 | 0 | 79.22 | 79.22 | 0 | 0 | 0 | 79.22 | 71.92 | 79
115 | PURBA MEDINIPUR | SM/10095 | Balance Work for Retrofitting to Accommodate FHTC (750 Nos.) and Laying of left-out portion UPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-XI, Block-Kolaghat in this | TSM/009589 | 6328427 | Retrofitting | MVS | GO2122009023PH | 01/02/2022 | 95.4 | 0 | 95.4 | Tamluk Division |  | 93 | 0 | 0 | 0 | 93 | 92.89 | 0 | 0 | 0 | 92.89 | 97.36 | 100
116 | PURBA MEDINIPUR | SM/16470 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA | TSM/018280 | 40049137 | Retrofitting | MVS | GO2223015243PH | 03/03/2023 | 59.08 | 0 | 59.08 | Tamluk Division |  | 51.09 | 0 | 0 | 0 | 51.09 | 51.09 | 0 | 0 | 0 | 51.09 | 86.47 | 95
117 | PURBA MEDINIPUR | SM/10436 | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl | TSM/009911 | 6328427 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 99.32 | 0 | 99.32 | Tamluk Division |  | 96.36 | 0 | 0 | 0 | 96.36 | 96.36 | 0 | 0 | 0 | 96.36 | 97.03 | 100
118 | PURBA MEDINIPUR | SM/09058 | Balance work for Retrofitting to accommodate FHTC (907 Nos.) and laying of laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for | TSM/008314 | 6328427 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 130.31 | 0 | 130.31 | Tamluk Division |  | 115.86 | 0 | 0 | 0 | 115.86 | 115.86 | 0 | 0 | 0 | 115.86 | 88.91 | 100
119 | PURBA MEDINIPUR | SM/10096 | Balance work for Retrofitting to Accommodate FHTC (951 Nos.) and laying of Left-out portion UPVC pipeline due to uncovered area of this Zone and Damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme under Zone-III | TSM/009577 | 6328427 | Retrofitting | MVS | GO2122009023PH | 01/02/2022 | 89.89 | 0 | 89.89 | Tamluk Division |  | 77.04 | 0 | 0 | 0 | 77.04 | 77.04 | 0 | 0 | 0 | 77.04 | 85.71 | 100
120 | PURBA MEDINIPUR | SM/12143 | BALGOBINDAPUR & ADJOINING MOUZAS | TSM/013159 | 40022484 | New | MVS | GO2223007252PH | 07/09/2022 | 841.41 | 37.99 | 879.41 | Tamluk Division | Midnapore Mechanical Division | 0 | 19.97 | 41.02 | 0 | 60.99 | 0 | 19.97 | 41.02 | 0 | 60.99 | 6.94 | 40
121 | PURBA MEDINIPUR | SM/12493 | BAMANPUR AND ADJOINING MOUJAS PWSS | TSM/014648 | 40025952 | New | MVS | GO2223007651PH | 13/09/2022 | 569.8 | 36.24 | 606.04 | Tamluk Division | Midnapore Mechanical Division | 201.9 | 28.94 | 12.99 | 0 | 243.82 | 201.9 | 28.94 | 12.99 | 0 | 243.82 | 40.23 | 25
122 | PURBA MEDINIPUR | SM/16200 | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | TSM/019328 | 40052289 | New | MVS | GO2223014796PH | 23/02/2023 | 186.64 | 10.82 | 197.46 | Tamluk Division | Midnapore Mechanical Division | 86.24 | 0 | 13.92 | 40.02 | 140.18 | 86.24 | 0 | 13.92 | 35.64 | 135.8 | 68.77 | 20
123 | PURBA MEDINIPUR | SM/12704 | BARA BHAGIA AND ADJOINING MOUJAS PWSS | TSM/014512 | 40024521 | New | MVS | GO2223007974PH | 20/09/2022 | 460.17 | 37.93 | 498.09 | Tamluk Division | Midnapore Mechanical Division | 0 | 25.22 | 29 | 0 | 54.22 | 0 | 25.22 | 29 | 0 | 54.22 | 10.89
124 | PURBA MEDINIPUR | SM/13885 | BARAGECHA AND ADJOINING MOUJAS PWSS | TSM/015972 | 40027020 | New | MVS | GO2223010049PH | 25/11/2022 | 425.27 | 36.7 | 461.96 | Tamluk Division | Midnapore Mechanical Division | 17.94 | 13.46 | 51.58 | 0 | 82.98 | 17.94 | 10.04 | 51.58 | 0 | 79.56 | 17.22 | 20
125 | PURBA MEDINIPUR | SM/12399 | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014484 | 40026086 | New | MVS | GO2223007601PH | 13/09/2022 | 655.98 | 40.37 | 696.35 | Tamluk Division | Midnapore Mechanical Division | 151.65 | 6.2 | 0 | 0 | 157.84 | 151.65 | 6.2 | 0 | 0 | 157.84 | 22.67 | 15
126 | PURBA MEDINIPUR | SM/12816 | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS | TSM/014666 | 40024513 | New | MVS | GO2223007964PH | 20/09/2022 | 562.71 | 37.66 | 600.38 | Tamluk Division | Midnapore Mechanical Division | 293.79 | 35.49 | 16.33 | 0 | 345.61 | 293.79 | 35.49 | 16.33 | 0 | 345.61 | 57.57 | 35
127 | PURBA MEDINIPUR | SM/12306 | BARDA AND ADJOINING MOUJAS PWSS | TSM/014245 | 40023178 | New | MVS | GO2223007326PH | 09/09/2022 | 558.03 | 36.34 | 594.37 | Tamluk Division | Midnapore Mechanical Division | 114.66 | 13 | 23.8 | 0 | 151.46 | 114.66 | 13 | 23.8 | 0 | 151.46 | 25.48 | 45
128 | PURBA MEDINIPUR | SM/12878 | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013148 | 40027169 | New | MVS | GO2223008166PH | 23/09/2022 | 683.19 | 37.99 | 721.18 | Tamluk Division | Midnapore Mechanical Division | 0.95 | 26.25 | 9.41 | 0 | 36.61 | 0.95 | 26.25 | 9.41 | 0 | 36.61 | 5.08 | 62
129 | PURBA MEDINIPUR | SM/11884 | BARNAN AND ITS ADJOINING MOUJAS PWSS | TSM/011802 | 40018784 | New | MVS | GO2223006388PH | 17/08/2022 | 367.05 | 37.54 | 404.59 | Tamluk Division | Midnapore Mechanical Division | 46.01 | 29.05 | 19.41 | 0 | 94.47 | 46.01 | 29.05 | 19.41 | 0 | 94.47 | 23.35 | 20
130 | PURBA MEDINIPUR | SM/12501 | BARTTAN AND ADJOINING MOUJAS PWSS | TSM/014483 | 40026095 | New | MVS | GO2223007650PH | 13/09/2022 | 1008.09 | 40.57 | 1048.66 | Tamluk Division | Midnapore Mechanical Division | 344.73 | 24.9 | 35.2 | 0 | 404.82 | 344.73 | 24.9 | 35.2 | 0 | 404.82 | 38.6 | 45
131 | PURBA MEDINIPUR | SM/13697 | BARTTANA & IT'S ADJOINING MOUJAS PWSS | TSM/015437 | 40026777 | New | MVS | GO2223009734PH | 14/11/2022 | 658.15 | 37.78 | 695.93 | Tamluk Division | Midnapore Mechanical Division | 147.34 | 5.33 | 33.46 | 0 | 186.13 | 147.34 | 5.33 | 33.46 | 0 | 186.13 | 26.75 | 45
132 | PURBA MEDINIPUR | SM/12144 | BASANTA CHAK AND ADJOINING MOUJAS PWSS | TSM/013164 | 40022479 | New | MVS | GO2223007230PH | 07/09/2022 | 524.88 | 40.1 | 564.98 | Tamluk Division | Midnapore Mechanical Division | 276.66 | 30.09 | 33.31 | 0 | 340.06 | 276.66 | 30.09 | 33.31 | 0 | 340.06 | 60.19 | 15
133 | PURBA MEDINIPUR | SM/14451 | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | TSM/017153 | 40026675 | New | MVS | GO2223012280PH | 20/01/2023 | 486.05 | 39.05 | 525.09 | Tamluk Division | Midnapore Mechanical Division | 102.11 | 7.85 | 26.44 | 0 | 136.41 | 102.11 | 7.85 | 26.44 | 0 | 136.41 | 25.98 | 45
134 | PURBA MEDINIPUR | SM/12297 | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | TSM/013975 | 40023151 | New | MVS | GO2223007356PH | 09/09/2022 | 504.64 | 36.45 | 541.09 | Tamluk Division | Midnapore Mechanical Division | 139.54 | 7.2 | 34.72 | 21.38 | 202.85 | 139.54 | 7.2 | 34.72 | 21.38 | 202.85 | 37.49 | 75
135 | PURBA MEDINIPUR | SM/16257 | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | TSM/017160 | 40026706 | New | MVS | GO2223014876PH | 24/02/2023 | 484.27 | 36.63 | 520.9 | Tamluk Division | Midnapore Mechanical Division | 47.72 | 0 | 43.04 | 0 | 90.75 | 47.72 | 0 | 43.04 | 0 | 90.75 | 17.42 | 45
136 | PURBA MEDINIPUR | SM/12710 | BELDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013396 | 40024648 | New | MVS | GO2223007975PH | 20/09/2022 | 659.27 | 40.61 | 699.88 | Tamluk Division | Midnapore Mechanical Division | 195.97 | 7.4 | 2.39 | 0 | 205.76 | 195.97 | 7.4 | 2.39 | 0 | 205.76 | 29.4 | 65
137 | PURBA MEDINIPUR | SM/12134 | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | TSM/013135 | 40022687 | New | MVS | GO2223007262PH | 07/09/2022 | 665.95 | 40.49 | 706.44 | Tamluk Division | Midnapore Mechanical Division | 0.95 | 27.83 | 49.37 | 0 | 78.15 | 0.95 | 27.83 | 49.37 | 0 | 78.15 | 11.06 | 10
138 | PURBA MEDINIPUR | SM/16203 | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | TSM/019333 | 40052291 | New | MVS | GO2223014797PH | 23/02/2023 | 155.72 | 10.91 | 166.63 | Tamluk Division | Midnapore Mechanical Division | 48 | 0 | 5.35 | 42.25 | 95.6 | 48 | 0 | 5.35 | 37.87 | 91.22 | 54.75 | 10
139 | PURBA MEDINIPUR | SM/13742 | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/015383 | 40026866 | New | MVS | GO2223009810PH | 17/11/2022 | 656.82 | 37.78 | 694.6 | Tamluk Division | Midnapore Mechanical Division | 444.54 | 23.8 | 19.41 | 0 | 487.75 | 444.54 | 23.8 | 19.41 | 0 | 487.75 | 70.22 | 65
140 | PURBA MEDINIPUR | SM/12157 | BIJAYNAGAR & ADJOINING MOUJAS PWSS | TSM/013223 | 40021655 | New | MVS | GO2223007194PH | 07/09/2022 | 657.01 | 38.65 | 695.66 | Tamluk Division | Midnapore Mechanical Division | 265.45 | 28.66 | 25.89 | 0 | 320 | 265.45 | 28.66 | 25.89 | 0 | 320 | 46 | 20
141 | PURBA MEDINIPUR | SM/12497 | BIRAMPUT AND ADJOINING MOUJAS PWSS | TSM/014502 | 40026047 | New | MVS | GO2223007641PH | 13/09/2022 | 476.47 | 35.62 | 512.1 | Tamluk Division | Midnapore Mechanical Division | 177.34 | 17.42 | 35.74 | 0 | 230.5 | 177.34 | 17.42 | 35.74 | 0 | 230.5 | 45.01 | 20
142 | PURBA MEDINIPUR | SM/13850 | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | TSM/016060 | 40026859 | New | SVS | GO2223010090PH | 25/11/2022 | 169.56 | 9.92 | 179.48 | Tamluk Division | Midnapore Mechanical Division | 91.4 | 9.53 | 0 | 0 | 100.92 | 91.4 | 9.53 | 0 | 0 | 100.92 | 56.23 | 50
143 | PURBA MEDINIPUR | SM/12148 | BRINDABANPUR & ADJOINING MOUJAS PWSS | TSM/013186 | 40022426 | New | MVS | GO2223007255PH | 07/09/2022 | 391.39 | 37.75 | 429.14 | Tamluk Division | Midnapore Mechanical Division | 201.72 | 29.67 | 25.71 | 0 | 257.11 | 201.72 | 29.67 | 25.71 | 0 | 257.11 | 59.91 | 55
144 | PURBA MEDINIPUR | SM/15512 | CHAK BHABANI & ADJOINING MOUJAS PWSS | TSM/013330 | 40026649 | New | MVS | GO2223014008PH | 16/02/2023 | 1055.45 | 40.02 | 1095.47 | Tamluk Division | Midnapore Mechanical Division | 606.52 | 31.38 | 17.51 | 0 | 655.41 | 606.52 | 31.38 | 17.51 | 0 | 655.41 | 59.83 | 15
145 | PURBA MEDINIPUR | SM/12505 | CHALTI AND ADJOINING MOUJAS PWSS | TSM/014430 | 40026316 | New | MVS | GO2223007644PH | 13/09/2022 | 556.44 | 36.38 | 592.82 | Tamluk Division | Midnapore Mechanical Division | 48.22 | 21.46 | 29.22 | 0 | 98.9 | 48.22 | 21.46 | 29.22 | 0 | 98.9 | 16.68 | 15
146 | PURBA MEDINIPUR | SM/13693 | CHANDPUR AND ADJOINING MOUJAS PWSS | TSM/015438 | 40026772 | New | MVS | GO2223009733PH | 14/11/2022 | 575.69 | 37.78 | 613.46 | Tamluk Division | Midnapore Mechanical Division | 136.67 | 8.92 | 18.74 | 0 | 164.33 | 136.67 | 8.92 | 18.74 | 0 | 164.33 | 26.79 | 30
147 | PURBA MEDINIPUR | SM/12495 | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | TSM/014595 | 40026019 | New | MVS | GO2223007635PH | 13/09/2022 | 543.89 | 37.85 | 581.74 | Tamluk Division | Midnapore Mechanical Division | 90.66 | 25.47 | 16.41 | 0 | 132.54 | 90.66 | 17.58 | 16.41 | 0 | 124.65 | 21.43 | 10
148 | PURBA MEDINIPUR | SM/12129 | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | TSM/011904 | 40022791 | New | MVS | GO2223007218PH | 07/09/2022 | 544.68 | 37.75 | 582.43 | Tamluk Division | Midnapore Mechanical Division | 423.27 | 30.43 | 35.88 | 0 | 489.58 | 423.27 | 30.43 | 35.88 | 0 | 489.58 | 84.06 | 30
149 | PURBA MEDINIPUR | SM/12431 | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | TSM/014797 | 40025893 | New | MVS | GO2223007616PH | 13/09/2022 | 787.6 | 40.04 | 827.64 | Tamluk Division | Midnapore Mechanical Division | 293.31 | 6.87 | 28.39 | 40.21 | 368.78 | 293.31 | 6.87 | 28.39 | 40.21 | 368.78 | 44.56 | 60
150 | PURBA MEDINIPUR | SM/14672 | CHISTIPUR AND ADJOINING MOUJAS | TSM/016729 | 40026835 | New | MVS | GO2223012687PH | 31/01/2023 | 629.27 | 39.22 | 668.48 | Tamluk Division | Midnapore Mechanical Division | 0.95 | 11.01 | 0 | 0 | 11.96 | 0.95 | 11.01 | 0 | 0 | 11.96 | 1.79 | 50
151 | PURBA MEDINIPUR | SM/12318 | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | TSM/014236 | 40023237 | New | MVS | GO2223007368PH | 09/09/2022 | 688.96 | 38.85 | 727.81 | Tamluk Division | Midnapore Mechanical Division | 282.92 | 37.72 | 27.02 | 0 | 347.66 | 282.92 | 37.72 | 27.02 | 0 | 347.66 | 47.77 | 80
152 | PURBA MEDINIPUR | SM/15849 | DAHA DAYA PIPED WATER SUPPLY SCHEME. | TSM/019329 | 40052294 | New | SVS | GO2223014235PH | 20/02/2023 | 147.33 | 10.91 | 158.24 | Tamluk Division | Midnapore Mechanical Division | 0 | 8.93 | 5.35 | 0 | 14.28 | 0 | 8.93 | 5.35 | 0 | 14.28 | 9.03
153 | PURBA MEDINIPUR | SM/12405 | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | TSM/014390 | 40026469 | New | MVS | GO2223007628PH | 13/09/2022 | 429.93 | 36.38 | 466.31 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 23.03 | 0 | 23.03 | 0 | 0 | 23.03 | 0 | 23.03 | 4.94 | 15
154 | PURBA MEDINIPUR | SM/12406 | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | TSM/014320 | 40026476 | New | MVS | GO2223007630PH | 13/09/2022 | 1021.74 | 40.04 | 1061.78 | Tamluk Division | Midnapore Mechanical Division | 553.91 | 38.16 | 13.44 | 13.69 | 619.2 | 553.91 | 38.16 | 13.44 | 13.69 | 619.2 | 58.32 | 40
155 | PURBA MEDINIPUR | SM/14745 | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/017133 | 40026650 | New | MVS | GO2223012697PH | 31/01/2023 | 197.97 | 18.73 | 216.7 | Tamluk Division | Midnapore Mechanical Division | 76.57 | 7.55 | 9.37 | 0 | 93.48 | 76.57 | 7.55 | 9.37 | 0 | 93.48 | 43.14 | 10
156 | PURBA MEDINIPUR | SM/12407 | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | TSM/014290 | 40026480 | New | MVS | GO2223007629PH | 13/09/2022 | 508.74 | 36.34 | 545.08 | Tamluk Division | Midnapore Mechanical Division | 137.69 | 15.34 | 53.55 | 44.83 | 251.4 | 137.69 | 15.34 | 53.55 | 44.83 | 251.4 | 46.12 | 30
157 | PURBA MEDINIPUR | SM/12130 | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | TSM/011925 | 40022789 | New | MVS | GO2223007265PH | 07/09/2022 | 373.7 | 37.76 | 411.46 | Tamluk Division | Midnapore Mechanical Division | 73.45 | 8.22 | 22.44 | 0 | 104.11 | 73.45 | 8.22 | 22.44 | 0 | 104.11 | 25.3 | 20
158 | PURBA MEDINIPUR | SM/12293 | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | TSM/014119 | 40023054 | New | MVS | GO2223007327PH | 09/09/2022 | 627.06 | 38.39 | 665.46 | Tamluk Division | Midnapore Mechanical Division | 173.59 | 0 | 36.63 | 0 | 210.21 | 173.59 | 0 | 36.63 | 0 | 210.21 | 31.59 | 48
159 | PURBA MEDINIPUR | SM/12285 | DANGAR TULSI AND ADJOINING MOUJAS PWSS | TSM/014243 | 40022909 | New | MVS | GO2223007365PH | 09/09/2022 | 673.91 | 38.85 | 712.76 | Tamluk Division | Midnapore Mechanical Division | 211.9 | 17.65 | 0 | 0 | 229.55 | 211.9 | 17.65 | 0 | 0 | 229.55 | 32.21 | 65
160 | PURBA MEDINIPUR | SM/15515 | DEKHALI AND ADJOINING MOUJAS PWSS | TSM/014485 | 40027237 | New | MVS | GO2223014004PH | 16/02/2023 | 1199.6 | 39.79 | 1239.4 | Tamluk Division | Midnapore Mechanical Division | 827.12 | 31.89 | 19.47 | 0 | 878.48 | 827.12 | 31.89 | 19.47 | 0 | 878.48 | 70.88 | 50
161 | PURBA MEDINIPUR | SM/12287 | DEPAL AND ADJOINING MOUJAS PWSS | TSM/014228 | 40022988 | New | MVS | GO2223007336PH | 09/09/2022 | 601.3 | 38.85 | 640.15 | Tamluk Division | Midnapore Mechanical Division | 234.46 | 30.02 | 18.74 | 0 | 283.22 | 234.46 | 30.02 | 18.74 | 0 | 283.22 | 44.24 | 65
162 | PURBA MEDINIPUR | SM/15851 | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | TSM/020432 | 40052266 | New | SVS | GO2223014239PH | 20/02/2023 | 64.49 | 10.41 | 74.9 | Tamluk Division | Midnapore Mechanical Division | 41.51 | 0.13 | 19.61 | 0 | 61.25 | 41.51 | 0.13 | 19.61 | 0 | 61.25 | 81.78 | 25
163 | PURBA MEDINIPUR | SM/13744 | DEULI & IT'S ADJOINING MOUJAS PWSS | TSM/015434 | 40026844 | New | MVS | GO2223009808PH | 17/11/2022 | 687.6 | 37.98 | 725.58 | Tamluk Division | Midnapore Mechanical Division | 253.43 | 18.87 | 38.07 | 0 | 310.38 | 253.43 | 18.87 | 38.07 | 0 | 310.38 | 42.78 | 20
164 | PURBA MEDINIPUR | SM/12484 | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | TSM/014727 | 40025932 | New | MVS | GO2223007636PH | 13/09/2022 | 444.05 | 38.02 | 482.07 | Tamluk Division | Midnapore Mechanical Division | 153.74 | 17.8 | 22.49 | 0 | 194.02 | 153.74 | 17.8 | 22.49 | 0 | 194.02 | 40.25 | 2
165 | PURBA MEDINIPUR | SM/10120 | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | TSM/008980 | 40007379 | Augmentation | MVS | GO2122009407PH | 08/02/2022 | 1410.29 | 105.19 | 1515.48 | Tamluk Division | Midnapore Mechanical Division | 1023.06 | 31.55 | 58.21 | 0 | 1112.83 | 1023.06 | 31.55 | 58.21 | 0 | 1112.83 | 73.43 | 70
166 | PURBA MEDINIPUR | SM/09281 | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | TSM/008368 | 8390237 | Augmentation | MVS | GO2122004893PH | 03/11/2021 | 681.09 | 0 | 681.09 | Tamluk Division |  | 504.87 | 0 | 92.92 | 0 | 597.79 | 504.87 | 0 | 92.92 | 0 | 597.79 | 87.77 | 90
167 | PURBA MEDINIPUR | SM/10683 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | TSM/008367 | 40013983 | Augmentation | MVS | GO2223000914PH | 06/05/2022 | 1126.18 | 0 | 1126.18 | Tamluk Division | Midnapore Mechanical Division | 612.24 | 0 | 239.41 | 0 | 851.65 | 612.24 | 0 | 239.41 | 0 | 851.65 | 75.62 | 50
168 | PURBA MEDINIPUR | SM/10122 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | TSM/008952 | 40007374 | Augmentation | MVS | GO2122009407PH | 08/02/2022 | 1389.93 | 102.47 | 1492.39 | Tamluk Division | Midnapore Mechanical Division | 948.67 | 36.24 | 81.57 | 45.18 | 1111.65 | 948.67 | 36.24 | 81.57 | 45.18 | 1111.65 | 74.49 | 75
169 | PURBA MEDINIPUR | SM/09285 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | TSM/008434 | 8390311 | Augmentation | MVS | GO2122004888PH | 03/11/2021 | 932.77 | 0 | 932.77 | Tamluk Division | Midnapore Mechanical Division | 664.23 | 0 | 109.7 | 0 | 773.92 | 664.23 | 0 | 109.7 | 0 | 773.92 | 82.97 | 90
170 | PURBA MEDINIPUR | SM/09448 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | TSM/008913 | 8390641 | Augmentation | MVS | GO2122005595PH | 19/11/2021 | 741.02 | 61.34 | 802.36 | Tamluk Division | Midnapore Mechanical Division | 642.53 | 14.32 | 60.4 | 16.51 | 733.75 | 642.53 | 14.29 | 60.4 | 16.51 | 733.73 | 91.45 | 73
171 | PURBA MEDINIPUR | SM/09977 | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. | TSM/008362 | 40001111 | Augmentation | MVS | GO2122006969PH | 17/12/2021 | 1187.36 | 0 | 1187.36 | Tamluk Division | Midnapore Mechanical Division | 611.62 | 0 | 68.82 | 34.84 | 715.28 | 610.86 | 0 | 68.82 | 34.84 | 714.52 | 60.18 | 80
172 | PURBA MEDINIPUR | SM/11979 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | TSM/010437 | 40019747 | Augmentation | MVS | GO2223006825PH | 31/08/2022 | 1589.03 | 79.74 | 1668.76 | Tamluk Division | Midnapore Mechanical Division | 332.44 | 57.12 | 224.96 | 0 | 614.52 | 332.44 | 57.12 | 224.96 | 0 | 614.52 | 36.82 | 40
173 | PURBA MEDINIPUR | SM/10682 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | TSM/008369 | 40013980 | Augmentation | MVS | GO2223000914PH | 06/05/2022 | 1414.27 | 0 | 1414.27 | Tamluk Division | Midnapore Mechanical Division | 837.07 | 0 | 265.53 | 15.62 | 1118.22 | 837.07 | 0 | 265.53 | 15.62 | 1118.22 | 79.07 | 65
174 | PURBA MEDINIPUR | SM/09284 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | TSM/008371 | 8390265 | Augmentation | MVS | GO2122004879PH | 03/11/2021 | 696.07 | 43.4 | 739.47 | Tamluk Division | Midnapore Mechanical Division | 609.97 | 11.06 | 21.79 | 19.85 | 662.67 | 609.97 | 11.06 | 21.79 | 19.85 | 662.67 | 89.61 | 80
175 | PURBA MEDINIPUR | SM/14837 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | TSM/018351 | 40052263 | Augmentation | MVS | GO2223012985PH | 03/02/2023 | 584.82 | 119.36 | 704.17 | Tamluk Division | Midnapore Mechanical Division | 170.44 | 52.1 | 30.1 | 0 | 252.65 | 170.44 | 52.1 | 30.1 | 0 | 252.65 | 35.88 | 35
176 | PURBA MEDINIPUR | SM/14838 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | TSM/018345 | 40052270 | Augmentation | MVS | GO2223012980PH | 03/02/2023 | 800.66 | 97.26 | 897.92 | Tamluk Division | Midnapore Mechanical Division | 189.36 | 15.74 | 68.51 | 0 | 273.61 | 189.36 | 15.74 | 68.51 | 0 | 273.61 | 30.47 | 60
177 | PURBA MEDINIPUR | SM/16288 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | TSM/018348 | 40056954 | Augmentation | MVS | GO2223014798PH | 23/02/2023 | 424.95 | 97.26 | 522.2 | Tamluk Division | Midnapore Mechanical Division | 146.2 | 19.02 | 4.82 | 0 | 170.03 | 146.2 | 19.02 | 4.82 | 0 | 170.03 | 32.56 | 5
178 | PURBA MEDINIPUR | SM/10396 | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | TSM/009747 | 40005465 | Augmentation | MVS | GO2122011548PH | 29/03/2022 | 1463.44 | 84.47 | 1547.92 | Tamluk Division | Midnapore Mechanical Division | 905.6 | 27.58 | 138.12 | 0 | 1071.3 | 905.6 | 27.58 | 138.12 | 0 | 1071.3 | 69.21 | 85
179 | PURBA MEDINIPUR | SM/10030 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | TSM/008480 | 40005433 | Augmentation | MVS | GO2122008408PH | 19/01/2022 | 1237.13 | 84.47 | 1321.6 | Tamluk Division | Midnapore Mechanical Division | 933.06 | 27.01 | 90.89 | 0 | 1050.97 | 933.06 | 27.01 | 90.89 | 0 | 1050.96 | 79.52 | 66
180 | PURBA MEDINIPUR | SM/09278 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | TSM/008438 | 8390366 | Augmentation | MVS | GO2122004883PH | 03/11/2021 | 678.53 | 0 | 678.53 | Tamluk Division | Midnapore Mechanical Division | 422.2 | 0 | 34.51 | 29.66 | 486.36 | 422.2 | 0 | 34.51 | 29.66 | 486.36 | 71.68 | 70
181 | PURBA MEDINIPUR | SM/09276 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme | TSM/008370 | 8390252 | Augmentation | SVS | GO2122004880PH | 03/11/2021 | 298.18 | 42.24 | 340.42 | Tamluk Division | Midnapore Mechanical Division | 154.33 | 12.86 | 0 | 0 | 167.18 | 154.33 | 12.86 | 0 | 0 | 167.18 | 49.11 | 60
182 | PURBA MEDINIPUR | SM/09274 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | TSM/008439 | 8390392 | Augmentation | SVS | GO2122004874PH | 03/11/2021 | 359.88 | 0 | 359.88 | Tamluk Division | Midnapore Mechanical Division | 160.82 | 0 | 8.69 | 12.92 | 182.43 | 160.82 | 0 | 8.69 | 12.92 | 182.43 | 50.69 | 55
183 | PURBA MEDINIPUR | SM/10031 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | TSM/008466 | 40005442 | Augmentation | MVS | GO2122008408PH | 19/01/2022 | 998.92 | 42.24 | 1041.15 | Tamluk Division | Midnapore Mechanical Division | 712.24 | 24.39 | 53.8 | 0 | 790.43 | 712.24 | 24.39 | 53.8 | 0 | 790.43 | 75.92 | 70
184 | PURBA MEDINIPUR | SM/09338 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. | TSM/008474 | 8390407 | Augmentation | MVS | GO2122005382PH | 12/11/2021 | 685.69 | 0 | 685.69 | Tamluk Division | Midnapore Mechanical Division | 345.76 | 0 | 33.06 | 0 | 378.83 | 345.76 | 0 | 33.06 | 0 | 378.83 | 55.25 | 75
185 | PURBA MEDINIPUR | SM/09283 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | TSM/008435 | 8390325 | Augmentation | MVS | GO2122004892PH | 03/11/2021 | 686.91 | 0 | 686.91 | Tamluk Division |  | 418.96 | 0 | 23.45 | 35.66 | 478.06 | 418.96 | 0 | 23.45 | 35.66 | 478.06 | 69.6 | 50
186 | PURBA MEDINIPUR | SM/09282 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | TSM/008437 | 8390355 | Augmentation | MVS | GO2122004884PH | 03/11/2021 | 890.9 | 0 | 890.9 | Tamluk Division | Midnapore Mechanical Division | 658 | 0 | 33.4 | 0 | 691.4 | 658 | 0 | 33.4 | 0 | 691.4 | 77.61 | 70
187 | PURBA MEDINIPUR | SM/12515 | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | TSM/014728 | 40025931 | New | MVS | GO2223007620PH | 13/09/2022 | 619.74 | 37.97 | 657.71 | Tamluk Division | Midnapore Mechanical Division | 291.03 | 23.74 | 50.78 | 22.21 | 387.74 | 291.03 | 23.74 | 50.78 | 22.21 | 387.74 | 58.95 | 35
188 | PURBA MEDINIPUR | SM/15513 | DUBDA IT'S ADJOINING MOUJAS PWSS | TSM/014644 | 40027206 | New | MVS | GO2223014006PH | 16/02/2023 | 1235.37 | 55.17 | 1290.54 | Tamluk Division | Midnapore Mechanical Division | 236.48 | 23.45 | 43.53 | 0 | 303.45 | 236.48 | 23.45 | 43.53 | 0 | 303.45 | 23.51 | 25
189 | PURBA MEDINIPUR | SM/12820 | DURMUT AND ADJOINING MOUJAS PWSS | TSM/014591 | 40024517 | New | MVS | GO2223007969PH | 20/09/2022 | 652.58 | 37.85 | 690.44 | Tamluk Division | Midnapore Mechanical Division | 2.5 | 9.45 | 48.21 | 0 | 60.15 | 2.5 | 9.45 | 48.21 | 0 | 60.15 | 8.71 | 15
190 | PURBA MEDINIPUR | SM/12404 | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | TSM/014419 | 40026423 | New | MVS | GO2223007602PH | 13/09/2022 | 534.28 | 38.53 | 572.81 | Tamluk Division | Midnapore Mechanical Division | 0 | 7.77 | 13.98 | 0 | 21.75 | 0 | 0 | 13.98 | 0 | 13.98 | 2.44 | 10
191 | PURBA MEDINIPUR | SM/12139 | EREKHALI AND ADJOINING MOUJAS PWSS | TSM/013147 | 40022556 | New | MVS | GO2223007205PH | 07/09/2022 | 589.99 | 37.99 | 627.99 | Tamluk Division | Midnapore Mechanical Division | 219.73 | 27.64 | 28.49 | 29.24 | 305.1 | 219.73 | 27.64 | 28.49 | 29.24 | 305.1 | 48.58 | 60
192 | PURBA MEDINIPUR | SM/12298 | ERENDA AND ADJOINING MOUJAS PWSS | TSM/013974 | 40023156 | New | MVS | GO2223007360PH | 09/09/2022 | 658.75 | 38.73 | 697.48 | Tamluk Division | Midnapore Mechanical Division | 221.63 | 19.22 | 23.26 | 0 | 264.12 | 221.63 | 19.22 | 23.26 | 0 | 264.12 | 37.87 | 15
193 | PURBA MEDINIPUR | SM/13687 | FATEPUR AND ADJOINING MOUJAS PWSS | TSM/015723 | 40026712 | New | MVS | GO2223009730PH | 14/11/2022 | 211.32 | 19.68 | 231 | Tamluk Division | Midnapore Mechanical Division | 76.25 | 12.15 | 0 | 0 | 88.39 | 76.25 | 12.15 | 0 | 0 | 88.39 | 38.27 | 75
194 | PURBA MEDINIPUR | SM/12500 | FULESHWAR AND ADJOINING MOUJAS PWSS | TSM/014498 | 40026071 | New | MVS | GO2223007648PH | 13/09/2022 | 622.67 | 35.55 | 658.22 | Tamluk Division | Midnapore Mechanical Division | 171.38 | 25.92 | 7.8 | 0 | 205.1 | 171.38 | 25.92 | 7.8 | 0 | 205.1 | 31.16 | 5
195 | PURBA MEDINIPUR | SM/12774 | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/014776 | 40024496 | New | MVS | GO2223007958PH | 20/09/2022 | 638.73 | 37.85 | 676.58 | Tamluk Division | Midnapore Mechanical Division | 127.13 | 7.08 | 23.05 | 0 | 157.26 | 127.13 | 7.08 | 23.05 | 0 | 157.26 | 23.24 | 15
196 | PURBA MEDINIPUR | SM/12159 | GAR BHERA & ADJOINING MOUZAS | TSM/013250 | 40021650 | New | MVS | GO2223007186PH | 07/09/2022 | 557.8 | 38.65 | 596.45 | Tamluk Division | Midnapore Mechanical Division | 308.41 | 35.26 | 22.49 | 0 | 366.16 | 308.41 | 35.26 | 22.49 | 0 | 366.16 | 61.39 | 25
197 | PURBA MEDINIPUR | SM/15850 | GARABAR PIPED WATER SUPPLY SCHEME. | TSM/019287 | 40052280 | New | SVS | GO2223014221PH | 20/02/2023 | 155.96 | 10.21 | 166.18 | Tamluk Division | Midnapore Mechanical Division | 37.96 | 0 | 17.45 | 44 | 99.41 | 37.96 | 0 | 17.45 | 41 | 96.41 | 58.02 | 55
198 | PURBA MEDINIPUR | SM/12299 | GATHRA AND ADJOINING MOUJAS PWSS | TSM/013973 | 40023167 | New | MVS | GO2223007358PH | 09/09/2022 | 589.17 | 38.61 | 627.78 | Tamluk Division | Midnapore Mechanical Division | 278.72 | 15.4 | 13.37 | 0 | 307.49 | 278.72 | 15.4 | 13.37 | 0 | 307.49 | 48.98 | 65
199 | PURBA MEDINIPUR | SM/14456 | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | TSM/017188 | 40026725 | New | MVS | GO2223012279PH | 20/01/2023 | 315.15 | 36.7 | 351.84 | Tamluk Division | Midnapore Mechanical Division | 184.54 | 12.46 | 23.74 | 0 | 220.73 | 184.54 | 12.46 | 23.74 | 0 | 220.73 | 62.74 | 90
200 | PURBA MEDINIPUR | SM/12149 | GOBINDAPUR & ADJOINING MOUZAS | TSM/013193 | 40021795 | New | MVS | GO2223007264PH | 07/09/2022 | 348.21 | 37.76 | 385.96 | Tamluk Division | Midnapore Mechanical Division | 0 | 8.37 | 10.71 | 0 | 19.08 | 0 | 8.37 | 10.71 | 0 | 19.08 | 4.94 | 15
201 | PURBA MEDINIPUR | SM/12161 | GOBRADAN & ADJOINING MOUZAS | TSM/013255 | 40021628 | New | MVS | GO2223007213PH | 07/09/2022 | 531.08 | 38.65 | 569.73 | Tamluk Division | Midnapore Mechanical Division | 238.02 | 24.26 | 35.57 | 0 | 297.85 | 238.02 | 24.26 | 35.57 | 0 | 297.85 | 52.28 | 75
202 | PURBA MEDINIPUR | SM/12812 | GOJINA AND IT'S ADJOINING MOUJAS PWSS | TSM/014708 | 40024499 | New | MVS | GO2223007960PH | 20/09/2022 | 728.37 | 37.98 | 766.35 | Tamluk Division | Midnapore Mechanical Division | 356.82 | 14.08 | 54.21 | 0 | 425.11 | 356.82 | 14.08 | 54.21 | 0 | 425.11 | 55.47 | 75
203 | PURBA MEDINIPUR | SM/12165 | GOKULNAGAR AND ADJOINING MOUJAS | TSM/013479 | 40021615 | New | MVS | GO2223007200PH | 07/09/2022 | 782.33 | 38.85 | 821.18 | Tamluk Division | Midnapore Mechanical Division | 356.96 | 32.75 | 17.94 | 0 | 407.64 | 356.96 | 32.75 | 17.94 | 0 | 407.64 | 49.64 | 75
204 | PURBA MEDINIPUR | SM/12158 | GOPINATHPUR & ADJOINING MOUZAS | TSM/013247 | 40021649 | New | MVS | GO2223007193PH | 07/09/2022 | 688.57 | 38.85 | 727.42 | Tamluk Division | Midnapore Mechanical Division | 387.98 | 28.63 | 43.9 | 0 | 460.51 | 387.98 | 28.63 | 43.9 | 0 | 460.51 | 63.31 | 50
205 | PURBA MEDINIPUR | SM/13884 | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | TSM/015973 | 40027019 | New | MVS | GO2223010080PH | 25/11/2022 | 551.03 | 38.88 | 589.91 | Tamluk Division | Midnapore Mechanical Division | 150.25 | 32.47 | 29.98 | 0 | 212.7 | 150.25 | 32.47 | 29.98 | 0 | 212.7 | 36.06 | 70
206 | PURBA MEDINIPUR | SM/12155 | GOYALDA & ADJOINING MOUZAS PWSS | TSM/013213 | 40021661 | New | MVS | GO2223007232PH | 07/09/2022 | 541.78 | 38.14 | 579.91 | Tamluk Division | Midnapore Mechanical Division | 205.36 | 24.95 | 18.74 | 0 | 249.05 | 205.36 | 24.95 | 18.74 | 0 | 249.05 | 42.95 | 60
207 | PURBA MEDINIPUR | SM/10593 | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010114 | 40013348 | Augmentation | MVS | GO2223000377PH | 18/04/2022 | 953.74 | 42.24 | 995.98 | Tamluk Division | Midnapore Mechanical Division | 612.71 | 41.01 | 84.39 | 20.24 | 758.35 | 612.71 | 41.01 | 84.39 | 20.24 | 758.35 | 76.14 | 80
208 | PURBA MEDINIPUR | SM/12570 | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011901 | 40022490 | Augmentation | MVS | GO2223007701PH | 14/09/2022 | 1666.16 | 42.24 | 1708.39 | Tamluk Division | Midnapore Mechanical Division | 1146.57 | 9.58 | 45.22 | 0 | 1201.37 | 1146.57 | 9.58 | 45.22 | 0 | 1201.37 | 70.32 | 60
209 | PURBA MEDINIPUR | SM/12279 | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011906 | 40021638 | Augmentation | MVS | GO2223007389PH | 09/09/2022 | 1558.2 | 126.71 | 1684.91 | Tamluk Division | Midnapore Mechanical Division | 880.27 | 28.91 | 325.57 | 0 | 1234.76 | 880.27 | 28.91 | 325.57 | 0 | 1234.76 | 73.28 | 95
210 | PURBA MEDINIPUR | SM/12268 | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | TSM/011155 | 40021632 | Augmentation | MVS | GO2223007394PH | 09/09/2022 | 1367.53 | 42.24 | 1409.77 | Tamluk Division | Midnapore Mechanical Division | 292.89 | 0 | 318.86 | 0 | 611.75 | 292.89 | 0 | 318.86 | 0 | 611.75 | 43.39 | 25
211 | PURBA MEDINIPUR | SM/11615 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | TSM/011150 | 40017035 | Augmentation | MVS | GO2223005568PH | 26/07/2022 | 830.87 | 84.47 | 915.35 | Tamluk Division | Midnapore Mechanical Division | 25.92 | 15.25 | 159.2 | 0 | 200.37 | 25.92 | 15.25 | 159.2 | 0 | 200.37 | 21.89 | 35
212 | PURBA MEDINIPUR | SM/12364 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | TSM/011153 | 40021805 | Augmentation | MVS | GO2223007565PH | 13/09/2022 | 1026.43 | 42.24 | 1068.67 | Tamluk Division | Midnapore Mechanical Division | 237.08 | 4.72 | 247.78 | 0 | 489.58 | 237.08 | 4.72 | 247.78 | 0 | 489.58 | 45.81 | 35
213 | PURBA MEDINIPUR | SM/10647 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | TSM/010095 | 40013437 | Augmentation | MVS | GO2223000496PH | 22/04/2022 | 539.62 | 0 | 539.62 | Tamluk Division | Midnapore Mechanical Division | 360.6 | 0 | 166.59 | 0 | 527.18 | 360.6 | 0 | 166.59 | 0 | 527.18 | 97.7 | 98
214 | PURBA MEDINIPUR | SM/10592 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | TSM/010094 | 40013432 | Augmentation | MVS | GO2223000348PH | 18/04/2022 | 903.71 | 0 | 903.71 | Tamluk Division | Midnapore Mechanical Division | 508.76 | 0 | 0 | 0 | 508.76 | 508.76 | 0 | 0 | 0 | 508.76 | 56.3 | 45
215 | PURBA MEDINIPUR | SM/10664 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | TSM/010118 | 40013440 | Augmentation | MVS | GO2223000519PH | 22/04/2022 | 599.83 | 0 | 599.83 | Tamluk Division | Midnapore Mechanical Division | 79.68 | 0 | 14.15 | 0 | 93.83 | 79.68 | 0 | 14.15 | 0 | 93.83 | 15.64 | 50
216 | PURBA MEDINIPUR | SM/16941 | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018767 | 40052016 | New | MVS | GO2223016578PH | 16/03/2023 | 380.82 | 67.82 | 448.63 | Tamluk Division | Midnapore Mechanical Division | 9.16 | 0 | 10.62 | 0 | 19.78 | 9.16 | 0 | 10.62 | 0 | 19.78 | 4.41 | 35
217 | PURBA MEDINIPUR | SM/17173 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte | TSM/020403 | 40066067 | New | MVS | GO2223016579PH | 16/03/2023 | 448.63 | 0 | 448.63 | Tamluk Division | Midnapore Mechanical Division | 310.37 | 0 | 2.26 | 0 | 312.63 | 310.37 | 0 | 2.26 | 0 | 312.63 | 69.68 | 30
218 | PURBA MEDINIPUR | SM/10586 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. | TSM/010150 | 40014365 | New | MVS | GO2223000393PH | 18/04/2022 | 992 | 0 | 992 | Tamluk Division |  | 761.92 | 0 | 2.04 | 0 | 763.96 | 761.92 | 0 | 2.04 | 0 | 763.96 | 77.01 | 45
219 | PURBA MEDINIPUR | SM/10618 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. | TSM/010147 | 40016846 | New | MVS | GO2223000430PH | 20/04/2022 | 969 | 0 | 969 | Tamluk Division |  | 472.79 | 0 | 14.27 | 0 | 487.06 | 472.79 | 0 | 14.27 | 0 | 487.06 | 50.26 | 30
220 | PURBA MEDINIPUR | SM/10585 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. | TSM/010151 | 40016845 | New | MVS | GO2223000369PH | 18/04/2022 | 969 | 0 | 969 | Tamluk Division |  | 728.63 | 0 | 30.33 | 0 | 758.96 | 728.63 | 0 | 30.33 | 0 | 758.96 | 78.32 | 30
221 | PURBA MEDINIPUR | SM/10617 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. | TSM/010295 | 40016843 | New | MVS | GO2223000452PH | 20/04/2022 | 977.46 | 0 | 977.46 | Tamluk Division |  | 790.86 | 0 | 4.17 | 0 | 795.03 | 790.86 | 0 | 4.17 | 0 | 795.03 | 81.34 | 35
222 | PURBA MEDINIPUR | SM/16948 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/020289 | 40052297 | New | MVS | GO2223016549PH | 16/03/2023 | 59.13 | 12.14 | 71.27 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
223 | PURBA MEDINIPUR | SM/10620 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. | TSM/010128 | 40016850 | New | MVS | GO2223000431PH | 20/04/2022 | 992 | 0 | 992 | Tamluk Division |  | 621.46 | 0 | 22.78 | 0 | 644.24 | 621.46 | 0 | 22.78 | 0 | 644.24 | 64.94 | 30
224 | PURBA MEDINIPUR | SM/10621 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. | TSM/010127 | 40016851 | New | MVS | GO2223000454PH | 20/04/2022 | 989 | 0 | 989 | Tamluk Division |  | 726.81 | 0 | 34.68 | 0 | 761.49 | 726.81 | 0 | 34.68 | 0 | 761.49 | 77 | 30
225 | PURBA MEDINIPUR | SM/10689 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010132 | 40016847 | New | MVS | GO2223001394PH | 12/05/2022 | 963 | 0 | 963 | Tamluk Division |  | 846.13 | 0 | 24.83 | 0 | 870.96 | 846.13 | 0 | 24.83 | 0 | 870.96 | 90.44 | 50
226 | PURBA MEDINIPUR | SM/10619 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010131 | 40016848 | New | MVS | GO2223000453PH | 20/04/2022 | 974 | 0 | 974 | Tamluk Division |  | 456.41 | 0 | 27.79 | 0 | 484.2 | 456.41 | 0 | 27.79 | 0 | 484.2 | 49.71 | 30
227 | PURBA MEDINIPUR | SM/10666 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010130 | 40016849 | New | MVS | GO2223000602PH | 26/04/2022 | 980.83 | 0 | 980.83 | Tamluk Division |  | 551.93 | 0 | 30.86 | 0 | 582.79 | 551.93 | 0 | 30.86 | 0 | 582.79 | 59.42 | 55
228 | PURBA MEDINIPUR | SM/10590 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | TSM/010121 | 40013401 | Augmentation | MVS | GO2223000341PH | 18/04/2022 | 467.71 | 117.97 | 585.68 | Tamluk Division | Midnapore Mechanical Division | 308.78 | 29.2 | 0 | 0 | 337.98 | 308.78 | 29.2 | 0 | 0 | 337.98 | 57.71 | 42
229 | PURBA MEDINIPUR | SM/10591 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | TSM/010120 | 40013391 | Augmentation | MVS | GO2223000346PH | 18/04/2022 | 703.33 | 0 | 703.33 | Tamluk Division | Midnapore Mechanical Division | 140.16 | 0 | 107.05 | 0 | 247.2 | 140.16 | 0 | 107.05 | 0 | 247.2 | 35.15 | 40
230 | PURBA MEDINIPUR | SM/10588 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | TSM/010123 | 40013416 | Augmentation | MVS | GO2223000384PH | 18/04/2022 | 873.02 | 126.71 | 999.73 | Tamluk Division | Midnapore Mechanical Division | 671.35 | 35.01 | 0.33 | 0 | 706.69 | 671.35 | 35.01 | 0.33 | 0 | 706.69 | 70.69 | 60
231 | PURBA MEDINIPUR | SM/10589 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | TSM/010122 | 40013402 | Augmentation | MVS | GO2223000381PH | 18/04/2022 | 980.6 | 0 | 980.6 | Tamluk Division | Midnapore Mechanical Division | 430.63 | 0 | 92.64 | 0 | 523.27 | 430.63 | 0 | 92.64 | 0 | 523.27 | 53.36 | 35
232 | PURBA MEDINIPUR | SM/10725 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I | TSM/010096 | 40014258 | Augmentation | MVS | GO2223001661PH | 18/05/2022 | 952.2 | 53.89 | 1006.09 | Tamluk Division | Midnapore Mechanical Division | 175.94 | 0 | 158.45 | 0 | 334.39 | 175.94 | 0 | 158.45 | 0 | 334.39 | 33.24 | 35
233 | PURBA MEDINIPUR | SM/10594 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | TSM/010097 | 40013367 | Augmentation | MVS | GO2223000370PH | 18/04/2022 | 713.43 | 106.36 | 819.79 | Tamluk Division | Midnapore Mechanical Division | 162.26 | 34.19 | 84.73 | 0 | 281.18 | 162.26 | 34.19 | 84.73 | 0 | 281.18 | 34.3 | 22
234 | PURBA MEDINIPUR | SM/13888 | GULURI AND IT'S ADJOING MOUJAS | TSM/015793 | 40027025 | New | MVS | GO2223010050PH | 25/11/2022 | 496.79 | 36.7 | 533.49 | Tamluk Division | Midnapore Mechanical Division | 93.78 | 19.06 | 29.68 | 0 | 142.52 | 93.78 | 19.06 | 29.68 | 0 | 142.52 | 26.71 | 18
235 | PURBA MEDINIPUR | SM/18311 | GURGRAM & ADJOINING MOUZAS | TSM/013294 | 40026877 | New | MVS | 1653/PHE-28011/47/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 986.37 | 41.62 | 1027.99 | Tamluk Division | Midnapore Mechanical Division | 603.82 | 35.26 | 17.85 | 0 | 656.92 | 603.82 | 35.26 | 17.85 | 0 | 656.92 | 63.9 | 20
236 | PURBA MEDINIPUR | SM/12821 | HALUD BARI AND ADJOINING MOUJAS | TSM/014557 | 40024519 | New | MVS | GO2223007971PH | 20/09/2022 | 688.02 | 39.98 | 728 | Tamluk Division | Midnapore Mechanical Division | 483.76 | 25.5 | 16.33 | 0 | 525.6 | 483.76 | 25.5 | 16.33 | 0 | 525.6 | 72.2 | 40
237 | PURBA MEDINIPUR | SM/11881 | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | TSM/011827 | 40018786 | New | MVS | GO2223006378PH | 17/08/2022 | 557.33 | 38.04 | 595.37 | Tamluk Division | Midnapore Mechanical Division | 247.37 | 16.11 | 14.73 | 15.45 | 293.65 | 247.37 | 16.11 | 14.73 | 15.45 | 293.65 | 49.32 | 70
238 | PURBA MEDINIPUR | SM/11947 | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | TSM/011798 | 40019023 | New | MVS | GO2223006679PH | 24/08/2022 | 527.85 | 37.9 | 565.75 | Tamluk Division | Midnapore Mechanical Division | 207.83 | 29.85 | 17.54 | 0 | 255.22 | 207.83 | 29.85 | 17.54 | 0 | 255.22 | 45.11 | 25
239 | PURBA MEDINIPUR | SM/12142 | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | TSM/013154 | 40022485 | New | MVS | GO2223007258PH | 07/09/2022 | 684.2 | 37.99 | 722.2 | Tamluk Division | Midnapore Mechanical Division | 286.45 | 13.39 | 12.71 | 0 | 312.55 | 286.45 | 13.39 | 12.71 | 0 | 312.55 | 43.28 | 80
240 | PURBA MEDINIPUR | SM/12152 | HARINAN PWSS & ADJOINING MOUJAS | TSM/013202 | 40021788 | New | MVS | GO2223007224PH | 07/09/2022 | 670.66 | 37.86 | 708.52 | Tamluk Division | Midnapore Mechanical Division | 385.84 | 28.97 | 30.09 | 0 | 444.9 | 385.84 | 28.97 | 30.09 | 0 | 444.9 | 62.79 | 44
241 | PURBA MEDINIPUR | SM/12150 | HOGALBERYA AND ADJOINING MOUJAS PWSS | TSM/013195 | 40021789 | New | MVS | GO2223007183PH | 07/09/2022 | 724.32 | 38.12 | 762.45 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 9.27 | 0 | 9.27 | 0 | 0 | 9.27 | 0 | 9.27 | 1.22 | 10
242 | PURBA MEDINIPUR | SM/12294 | ILASHPUR AND ADJOINING MOUJAS PWSS | TSM/013993 | 40023058 | New | MVS | GO2223007361PH | 09/09/2022 | 808.79 | 38.85 | 847.64 | Tamluk Division | Midnapore Mechanical Division | 369.37 | 25.78 | 28.03 | 0 | 423.18 | 369.37 | 25.78 | 28.03 | 0 | 423.18 | 49.92 | 50
243 | PURBA MEDINIPUR | SM/13683 | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015729 | 40026674 | New | MVS | GO2223009738PH | 14/11/2022 | 671.25 | 39.18 | 710.43 | Tamluk Division | Midnapore Mechanical Division | 232.91 | 7.76 | 19.81 | 36.43 | 296.92 | 232.91 | 7.76 | 19.81 | 36.43 | 296.92 | 41.79 | 25
244 | PURBA MEDINIPUR | SM/14042 | ITA BARIA & ADJOINING MOUZAS | TSM/013169 | 40027178 | New | MVS | GO2223010852PH | 12/12/2022 | 896.68 | 38.04 | 934.72 | Tamluk Division | Midnapore Mechanical Division | 264.2 | 3.54 | 168.42 | 41.48 | 477.64 | 264.2 | 3.54 | 168.42 | 41.48 | 477.64 | 51.1 | 40
245 | PURBA MEDINIPUR | SM/12813 | JAHANABAD AND IT'S ADJOINING MOUJAS | TSM/014704 | 40024501 | New | MVS | GO2223007966PH | 20/09/2022 | 934.82 | 39.27 | 974.08 | Tamluk Division | Midnapore Mechanical Division | 327.94 | 12.81 | 25.14 | 13.39 | 379.28 | 327.94 | 12.81 | 25.14 | 13.39 | 379.28 | 38.94 | 25
246 | PURBA MEDINIPUR | SM/12137 | JAMITTA & ADJOINING MOUZAS | TSM/013145 | 40022629 | New | MVS | GO2223007220PH | 07/09/2022 | 335.92 | 37.76 | 373.67 | Tamluk Division | Midnapore Mechanical Division | 67.94 | 13.96 | 20.09 | 44 | 145.99 | 67.94 | 13.96 | 20.09 | 44 | 145.99 | 39.07 | 35
247 | PURBA MEDINIPUR | SM/14694 | JAMUASHANKARPUR PWSS | TSM/017103 | 40026824 | New | SVS | GO2223012682PH | 31/01/2023 | 325.97 | 18.25 | 344.23 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 16.9 | 0 | 16.9 | 0 | 0 | 16.9 | 0 | 16.9 | 4.91 | 6
248 | PURBA MEDINIPUR | SM/12502 | JAYNAGAR AND ADJOINING MOUJAS PWSS | TSM/014479 | 40026119 | New | MVS | GO2223007652PH | 13/09/2022 | 733.2 | 40.04 | 773.24 | Tamluk Division | Midnapore Mechanical Division | 178.28 | 12.5 | 37.92 | 0 | 228.7 | 178.28 | 12.5 | 37.92 | 0 | 228.7 | 29.58 | 38
249 | PURBA MEDINIPUR | SM/12308 | JERTHAN AND ADJOINING MOUJAS PWSS | TSM/014233 | 40023186 | New | MVS | GO2223007367PH | 09/09/2022 | 722.29 | 40.04 | 762.33 | Tamluk Division | Midnapore Mechanical Division | 341.48 | 30.99 | 30.27 | 0 | 402.74 | 341.48 | 30.99 | 30.27 | 0 | 402.74 | 52.83 | 40
250 | PURBA MEDINIPUR | SM/15842 | JHAUGERYA PIPED WATER SUPPLY SCHEME. | TSM/019331 | 40052283 | New | SVS | GO2223014243PH | 20/02/2023 | 168.44 | 10.82 | 179.26 | Tamluk Division | Midnapore Mechanical Division | 85.33 | 0 | 14.46 | 0 | 99.79 | 85.33 | 0 | 14.46 | 0 | 99.79 | 55.66 | 35
251 | PURBA MEDINIPUR | SM/12995 | JUMKI AND ADJOINING MOUJAS PWSS | TSM/014230 | 40027261 | New | MVS | GO2223008399PH | 28/09/2022 | 582.26 | 38.73 | 620.99 | Tamluk Division | Midnapore Mechanical Division | 241.06 | 25.47 | 18.49 | 0 | 285.02 | 241.06 | 25.47 | 18.49 | 0 | 285.02 | 45.9 | 65
252 | PURBA MEDINIPUR | SM/13689 | KADUA AND IT'S ADJOINING MOUJAS | TSM/015580 | 40026721 | New | MVS | GO2223009731PH | 14/11/2022 | 702.69 | 39.18 | 741.86 | Tamluk Division | Midnapore Mechanical Division | 157.48 | 5.73 | 29.77 | 59.25 | 252.23 | 157.48 | 5.73 | 29.77 | 59.25 | 252.23 | 34 | 60
253 | PURBA MEDINIPUR | SM/12514 | KAINARA & IT'S ADJOING MOUJAS | TSM/014729 | 40025930 | New | MVS | GO2223007625PH | 13/09/2022 | 745.19 | 39.41 | 784.6 | Tamluk Division | Midnapore Mechanical Division | 229.99 | 32.6 | 60.23 | 0 | 322.81 | 229.99 | 32.6 | 60.23 | 0 | 322.81 | 41.14 | 70
254 | PURBA MEDINIPUR | SM/12499 | KAJI BASAN AND ADJOINING MOUJAS PWSS | TSM/014499 | 40026058 | New | MVS | GO2223007639PH | 13/09/2022 | 540.54 | 35.55 | 576.08 | Tamluk Division | Midnapore Mechanical Division | 146.95 | 24.15 | 17.28 | 0 | 188.37 | 146.95 | 24.15 | 17.28 | 0 | 188.37 | 32.7
255 | PURBA MEDINIPUR | SM/12138 | KAKRA & ADJOINING MOUZAS | TSM/013146 | 40022573 | New | MVS | GO2223007211PH | 07/09/2022 | 744.21 | 39.98 | 784.19 | Tamluk Division | Midnapore Mechanical Division | 467.04 | 29.41 | 26.48 | 0 | 522.94 | 467.04 | 29.41 | 26.48 | 0 | 522.94 | 66.69 | 40
256 | PURBA MEDINIPUR | SM/12136 | KALABERIA & ADJOINING MOUZAS | TSM/013144 | 40022650 | New | MVS | GO2223007225PH | 07/09/2022 | 704.63 | 38.85 | 743.49 | Tamluk Division | Midnapore Mechanical Division | 43.7 | 6.87 | 17.54 | 0 | 68.11 | 43.7 | 0 | 17.54 | 0 | 61.24 | 8.24 | 10
257 | PURBA MEDINIPUR | SM/13694 | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | TSM/015575 | 40026737 | New | MVS | GO2223009732PH | 14/11/2022 | 586.27 | 38.96 | 625.23 | Tamluk Division | Midnapore Mechanical Division | 240.34 | 30.28 | 33.89 | 0 | 304.51 | 240.34 | 30.28 | 33.89 | 0 | 304.51 | 48.7 | 65
258 | PURBA MEDINIPUR | SM/12307 | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | TSM/014232 | 40023182 | New | MVS | GO2223007346PH | 09/09/2022 | 478.21 | 36.3 | 514.51 | Tamluk Division | Midnapore Mechanical Division | 23.24 | 7.1 | 21.3 | 0 | 51.65 | 23.24 | 7.1 | 21.3 | 0 | 51.65 | 10.04
259 | PURBA MEDINIPUR | SM/12403 | KANCHANPUR AND ADJOINING MOUJAS PWSS | TSM/014432 | 40026314 | New | MVS | GO2223007593PH | 13/09/2022 | 545.51 | 38.73 | 584.24 | Tamluk Division | Midnapore Mechanical Division | 158.42 | 20.04 | 25.38 | 12.66 | 216.5 | 158.42 | 20.04 | 25.38 | 12.66 | 216.5 | 37.06 | 35
260 | PURBA MEDINIPUR | SM/12289 | KANTHI BARI AND ADJOINING MOUJAS PWSS | TSM/014225 | 40022998 | New | MVS | GO2223007328PH | 09/09/2022 | 756.6 | 38.73 | 795.33 | Tamluk Division | Midnapore Mechanical Division | 359.89 | 15.76 | 36.02 | 26.25 | 437.91 | 359.89 | 15.76 | 36.02 | 26.25 | 437.91 | 55.06 | 15
261 | PURBA MEDINIPUR | SM/13692 | KAPASDA & IT'S ADJOINING MOUJAS PWSS | TSM/015579 | 40026728 | New | MVS | GO2223009736PH | 14/11/2022 | 739.89 | 38.84 | 778.74 | Tamluk Division | Midnapore Mechanical Division | 136.77 | 0 | 38.63 | 0 | 175.4 | 136.77 | 0 | 38.63 | 0 | 175.4 | 22.52 | 35
262 | PURBA MEDINIPUR | SM/12172 | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | TSM/013500 | 40021593 | New | MVS | GO2223007185PH | 07/09/2022 | 625.87 | 38.85 | 664.72 | Tamluk Division | Midnapore Mechanical Division | 14.47 | 4.59 | 35.27 | 0 | 54.33 | 14.47 | 0 | 35.27 | 0 | 49.75 | 7.48 | 10
263 | PURBA MEDINIPUR | SM/14673 | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | TSM/016550 | 40028669 | New | MVS | GO2223012685PH | 31/01/2023 | 605.27 | 36.79 | 642.05 | Tamluk Division | Midnapore Mechanical Division | 173.08 | 26.14 | 3.78 | 0 | 202.99 | 173.08 | 26.14 | 3.78 | 0 | 202.99 | 31.62 | 15
264 | PURBA MEDINIPUR | SM/12815 | KATARI AND ADJOINING MOUJAS PWSS | TSM/014682 | 40024510 | New | MVS | GO2223007963PH | 20/09/2022 | 380.9 | 35.62 | 416.52 | Tamluk Division | Midnapore Mechanical Division | 124.19 | 31.3 | 7.66 | 27.71 | 190.86 | 124.19 | 31.3 | 7.66 | 27.71 | 190.86 | 45.82 | 95
265 | PURBA MEDINIPUR | SM/14457 | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS | TSM/017178 | 40026718 | New | MVS | GO2223012276PH | 20/01/2023 | 298.99 | 18.68 | 317.67 | Tamluk Division | Midnapore Mechanical Division | 33.74 | 8.04 | 22.25 | 0 | 64.03 | 33.74 | 8.04 | 22.25 | 0 | 64.03 | 20.16 | 10
266 | PURBA MEDINIPUR | SM/12167 | KAYEMGERYA AND ADJOINING MOUJAS PWSS | TSM/013485 | 40021605 | New | MVS | GO2223007197PH | 07/09/2022 | 706.08 | 38.85 | 744.93 | Tamluk Division | Midnapore Mechanical Division | 248.81 | 18.27 | 43.59 | 22.74 | 333.41 | 248.81 | 18.27 | 43.59 | 22.74 | 333.41 | 44.76 | 40
267 | PURBA MEDINIPUR | SM/12168 | KEKAI & ADJOINING MOUJAS PWSS | TSM/013491 | 40021603 | New | MVS | GO2223007192PH | 07/09/2022 | 703.17 | 38.85 | 742.03 | Tamluk Division | Midnapore Mechanical Division | 142.39 | 12.94 | 26 | 0 | 181.34 | 142.39 | 12.94 | 26 | 0 | 181.34 | 24.44 | 10
268 | PURBA MEDINIPUR | SM/12504 | KHAGA AND IT'S ADJOINING MOUJAS PWSS | TSM/014443 | 40026305 | New | MVS | GO2223007618PH | 13/09/2022 | 725.58 | 38.73 | 764.31 | Tamluk Division | Midnapore Mechanical Division | 260.41 | 6.83 | 43.63 | 0 | 310.87 | 260.41 | 6.83 | 43.63 | 0 | 310.87 | 40.67 | 25
269 | PURBA MEDINIPUR | SM/12483 | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | TSM/014423 | 40026829 | New | SVS | GO2223007657PH | 13/09/2022 | 484.29 | 36.38 | 520.66 | Tamluk Division | Midnapore Mechanical Division | 97.49 | 21.76 | 61.01 | 0 | 180.26 | 97.49 | 21.76 | 61.01 | 0 | 180.26 | 34.62 | 25
270 | PURBA MEDINIPUR | SM/13743 | KHAR & IT'S ADJOINING MOUJAS PWSS | TSM/015435 | 40026837 | New | MVS | GO2223009806PH | 17/11/2022 | 947.76 | 39.49 | 987.25 | Tamluk Division | Midnapore Mechanical Division | 22.13 | 9.39 | 17.52 | 0 | 49.04 | 22.13 | 9.39 | 17.52 | 0 | 49.04 | 4.97 | 70
271 | PURBA MEDINIPUR | SM/12175 | KHARAT KATBAR & ADJOINING MOUJAS PWSS | TSM/013509 | 40021353 | New | MVS | GO2223007180PH | 07/09/2022 | 686.75 | 38.73 | 725.48 | Tamluk Division | Midnapore Mechanical Division | 70.73 | 25.15 | 39.22 | 0 | 135.09 | 70.73 | 25.15 | 39.22 | 0 | 135.09 | 18.62 | 10
272 | PURBA MEDINIPUR | SM/11945 | KHARUI AND ADJOINING MOUZAS PWSS | TSM/011813 | 40019033 | New | MVS | GO2223006675PH | 24/08/2022 | 598.86 | 38.28 | 637.14 | Tamluk Division | Midnapore Mechanical Division | 160.63 | 24.29 | 69.07 | 0 | 253.99 | 160.63 | 24.29 | 69.07 | 0 | 253.99 | 39.86 | 75
273 | PURBA MEDINIPUR | SM/12814 | KIA AND IT'S ADJOINING MOUJAS | TSM/014692 | 40024504 | New | MVS | GO2223007962PH | 20/09/2022 | 682.12 | 37.98 | 720.1 | Tamluk Division | Midnapore Mechanical Division | 156.56 | 15.85 | 31.07 | 0 | 203.48 | 156.56 | 15.85 | 31.07 | 0 | 203.48 | 28.26 | 60
274 | PURBA MEDINIPUR | SM/12628 | KIARANA AND ADJOINING MOUJAS PWSS | TSM/014257 | 40022799 | New | MVS | GO2223007814PH | 19/09/2022 | 672.02 | 38.85 | 710.87 | Tamluk Division | Midnapore Mechanical Division | 198 | 37.72 | 8.77 | 0 | 244.5 | 198 | 37.72 | 8.77 | 0 | 244.5 | 34.39 | 20
275 | PURBA MEDINIPUR | SM/12513 | KSHETRAPAL AND IT'S ADJOINING MOUJAS | TSM/014735 | 40025923 | New | MVS | GO2223007631PH | 13/09/2022 | 657.53 | 37.64 | 695.17 | Tamluk Division | Midnapore Mechanical Division | 256.52 | 8.96 | 28.3 | 0 | 293.78 | 256.52 | 8.96 | 28.3 | 0 | 293.78 | 42.26 | 10
276 | PURBA MEDINIPUR | SM/14671 | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | TSM/016738 | 40027033 | New | MVS | GO2223012691PH | 31/01/2023 | 434.25 | 36.83 | 471.07 | Tamluk Division | Midnapore Mechanical Division | 125.85 | 8.23 | 15.14 | 0 | 149.21 | 125.85 | 8.23 | 15.14 | 0 | 149.21 | 31.68 | 15
277 | PURBA MEDINIPUR | SM/11882 | KURPAI AND ADJOINING MOUJAS PWSS | TSM/011814 | 40018788 | New | MVS | GO2223006382PH | 17/08/2022 | 460.4 | 38.12 | 498.52 | Tamluk Division | Midnapore Mechanical Division | 57.75 | 8.64 | 18.74 | 0 | 85.13 | 57.75 | 8.64 | 18.74 | 0 | 85.13 | 17.08 | 45
278 | PURBA MEDINIPUR | SM/12498 | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | TSM/014501 | 40026050 | New | MVS | GO2223007643PH | 13/09/2022 | 728.6 | 38.73 | 767.33 | Tamluk Division | Midnapore Mechanical Division | 298.97 | 21.17 | 27.08 | 0 | 347.22 | 298.97 | 21.17 | 27.08 | 0 | 347.22 | 45.25 | 30
279 | PURBA MEDINIPUR | SM/12510 | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | TSM/014394 | 40026450 | New | MVS | GO2223007645PH | 13/09/2022 | 717.14 | 38.73 | 755.87 | Tamluk Division | Midnapore Mechanical Division | 184.91 | 6.36 | 20.39 | 0 | 211.66 | 184.91 | 6.36 | 20.39 | 0 | 211.66 | 28 | 45
280 | PURBA MEDINIPUR | SM/14749 | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | TSM/016745 | 40027028 | New | MVS | GO2223012684PH | 31/01/2023 | 322.6 | 19.68 | 342.28 | Tamluk Division | Midnapore Mechanical Division | 0 | 14.63 | 15.33 | 0 | 29.96 | 0 | 14.63 | 15.33 | 0 | 29.96 | 8.75 | 15
281 | PURBA MEDINIPUR | SM/12282 | MAKRAMPUR AND ADJOINING MOUJAS PWSS | TSM/014260 | 40022796 | New | MVS | GO2223007362PH | 09/09/2022 | 713.43 | 38.85 | 752.28 | Tamluk Division | Midnapore Mechanical Division | 75.02 | 8.5 | 0 | 0 | 83.52 | 75.02 | 8.5 | 0 | 0 | 83.52 | 11.1 | 50
282 | PURBA MEDINIPUR | SM/12141 | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013152 | 40022495 | New | MVS | GO2223007263PH | 07/09/2022 | 856.48 | 37.76 | 894.23 | Tamluk Division | Midnapore Mechanical Division | 212.88 | 3.66 | 55.5 | 0 | 272.04 | 212.88 | 3.66 | 55.5 | 0 | 272.04 | 30.42 | 40
283 | PURBA MEDINIPUR | SM/11885 | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011790 | 40018790 | New | MVS | GO2223006392PH | 17/08/2022 | 373.32 | 37.54 | 410.86 | Tamluk Division | Midnapore Mechanical Division | 83.66 | 7.41 | 19.55 | 0 | 110.61 | 83.66 | 7.41 | 19.55 | 0 | 110.61 | 26.92 | 20
284 | PURBA MEDINIPUR | SM/12171 | MANIKJOR AND ADJOINING MOUJAS PWSS | TSM/013499 | 40021595 | New | MVS | GO2223007173PH | 07/09/2022 | 888.69 | 38.73 | 927.42 | Tamluk Division | Midnapore Mechanical Division | 187.52 | 0 | 40.38 | 0 | 227.91 | 187.52 | 0 | 40.38 | 0 | 227.91 | 24.57 | 10
285 | PURBA MEDINIPUR | SM/13883 | MASHAGON AND ITS ADJOINING MOUJAS PWSS | TSM/015974 | 40027016 | New | MVS | GO2223010081PH | 25/11/2022 | 194.31 | 9.92 | 204.23 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 2.47 | 0 | 2.47 | 0 | 0 | 2.47 | 0 | 2.47 | 1.21 | 15
286 | PURBA MEDINIPUR | SM/13745 | MATHURA AND IT'S ADJOINING MOUJAS PWSS | TSM/014944 | 40026939 | New | MVS | GO2223009811PH | 17/11/2022 | 694.33 | 37.85 | 732.18 | Tamluk Division | Midnapore Mechanical Division | 163.28 | 12.07 | 13.35 | 0 | 188.7 | 163.28 | 7.31 | 13.35 | 0 | 183.94 | 25.12 | 10
287 | PURBA MEDINIPUR | SM/12281 | MAYACHAR AND ADJOINING MOUJAS PWSS | TSM/014303 | 40027126 | New | SVS | GO2223007348PH | 09/09/2022 | 536.64 | 38.85 | 575.5 | Tamluk Division | Midnapore Mechanical Division | 181.09 | 31.34 | 10.04 | 0 | 222.47 | 181.09 | 31.34 | 10.04 | 0 | 222.47 | 38.66 | 45
288 | PURBA MEDINIPUR | SM/11946 | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | TSM/011808 | 40019036 | New | MVS | GO2223006678PH | 24/08/2022 | 946.16 | 38.71 | 984.88 | Tamluk Division | Midnapore Mechanical Division | 0 | 31.31 | 33.47 | 0 | 64.78 | 0 | 31.31 | 33.47 | 0 | 64.78 | 6.58 | 10
289 | PURBA MEDINIPUR | SM/12153 | MIRJAPUR AND ADJOINING MOUJAS PWSS | TSM/013480 | 40021613 | New | MVS | GO2223007196PH | 07/09/2022 | 900.34 | 38.85 | 939.19 | Tamluk Division | Midnapore Mechanical Division | 478.77 | 28.05 | 16.68 | 0 | 523.49 | 478.77 | 28.05 | 16.68 | 0 | 523.49 | 55.74 | 50
290 | PURBA MEDINIPUR | SM/12516 | MIRJAPUR AND IT'S ADJOINING MOUJAS | TSM/014726 | 40025935 | New | MVS | GO2223007632PH | 13/09/2022 | 479.58 | 35.59 | 515.17 | Tamluk Division | Midnapore Mechanical Division | 0 | 8.12 | 32.5 | 27.72 | 68.34 | 0 | 8.12 | 32.5 | 27.72 | 68.34 | 13.27 | 30
291 | PURBA MEDINIPUR | SM/13695 | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/015485 | 40026771 | New | MVS | GO2223009729PH | 14/11/2022 | 682.05 | 37.85 | 719.9 | Tamluk Division | Midnapore Mechanical Division | 133.35 | 33.03 | 34.86 | 29 | 230.23 | 133.35 | 33.03 | 34.86 | 29 | 230.23 | 31.98 | 10
292 | PURBA MEDINIPUR | SM/13740 | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015572 | 40026752 | New | MVS | GO2223009832PH | 17/11/2022 | 632.92 | 36.66 | 669.57 | Tamluk Division | Midnapore Mechanical Division | 196.5 | 2.83 | 15.81 | 0 | 215.15 | 196.5 | 2.83 | 15.81 | 0 | 215.15 | 32.13 | 15
293 | PURBA MEDINIPUR | SM/14693 | MURARI KALUA PWSS | TSM/017101 | 40026789 | New | SVS | GO2223012680PH | 31/01/2023 | 217.96 | 18.57 | 236.53 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
294 | PURBA MEDINIPUR | SM/12398 | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | TSM/014495 | 40026076 | New | MVS | GO2223007599PH | 13/09/2022 | 607.65 | 37.85 | 645.5 | Tamluk Division | Midnapore Mechanical Division | 171.19 | 6.82 | 26.08 | 0 | 204.1 | 171.19 | 6.82 | 26.08 | 0 | 204.1 | 31.62 | 55
295 | PURBA MEDINIPUR | SM/12295 | NAICHHANPUR AND ADJOINING MOUJAS PWSS | TSM/013987 | 40023065 | New | MVS | GO2223007357PH | 09/09/2022 | 552.94 | 40.1 | 593.04 | Tamluk Division | Midnapore Mechanical Division | 331.01 | 7.29 | 22.01 | 42.35 | 402.66 | 331.01 | 7.29 | 22.01 | 42.35 | 402.66 | 67.9 | 50
296 | PURBA MEDINIPUR | SM/12135 | NAIPUR & ADJOINING MOUZAS | TSM/013138 | 40022678 | New | MVS | GO2223007189PH | 07/09/2022 | 513.07 | 37.89 | 550.96 | Tamluk Division | Midnapore Mechanical Division | 153.23 | 22.94 | 27.31 | 0 | 203.48 | 153.23 | 22.94 | 27.31 | 0 | 203.48 | 36.93 | 10
297 | PURBA MEDINIPUR | SM/12401 | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014472 | 40026123 | New | MVS | GO2223007600PH | 13/09/2022 | 666.25 | 40.17 | 706.42 | Tamluk Division | Midnapore Mechanical Division | 23.48 | 16.85 | 12.72 | 0 | 53.04 | 23.48 | 16.85 | 12.72 | 0 | 53.04 | 7.51
298 | PURBA MEDINIPUR | SM/09342 | Narikeldaha Piped Water Supply Scheme. | TSM/004396 | 8390194 | New | MVS | GO2122005381PH | 12/11/2021 | 848.91 | 0 | 848.91 | Tamluk Division | Midnapore Mechanical Division | 722.99 | 0 | 31.95 | 0 | 754.94 | 722.99 | 0 | 31.95 | 0 | 754.94 | 88.93 | 99
299 | PURBA MEDINIPUR | SM/12517 | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | TSM/014534 | 40026027 | New | MVS | GO2223007597PH | 13/09/2022 | 704.67 | 38.73 | 743.4 | Tamluk Division | Midnapore Mechanical Division | 230.6 | 26.11 | 12.34 | 0 | 269.06 | 230.6 | 26.11 | 12.34 | 0 | 269.06 | 36.19 | 68
300 | PURBA MEDINIPUR | SM/06651 | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | TSM/005473 | 7958962 | New | MVS | GO1920007103PH | 12/02/2020 | 28.92 | 0 | 28.92 | Tamluk Division |  | 28.06 | 0 | 0 | 0 | 28.06 | 28.06 | 0 | 0 | 0 | 28.06 | 97.02 | 100
301 | PURBA MEDINIPUR | SM/12286 | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | TSM/014238 | 40022918 | New | MVS | GO2223007338PH | 09/09/2022 | 737.15 | 38.85 | 776 | Tamluk Division | Midnapore Mechanical Division | 293.27 | 5.83 | 48.13 | 46.44 | 393.68 | 293.27 | 5.83 | 48.13 | 46.44 | 393.68 | 50.73 | 90
302 | PURBA MEDINIPUR | SM/13741 | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015436 | 40026782 | New | MVS | GO2223009805PH | 17/11/2022 | 338.25 | 18.92 | 357.16 | Tamluk Division | Midnapore Mechanical Division | 144.34 | 5.95 | 13.39 | 0 | 163.68 | 144.34 | 5.95 | 13.39 | 0 | 163.68 | 45.83 | 35
303 | PURBA MEDINIPUR | SM/12402 | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014433 | 40026308 | New | MVS | GO2223007594PH | 13/09/2022 | 611.73 | 38.53 | 650.26 | Tamluk Division | Midnapore Mechanical Division | 127.04 | 33.61 | 26.61 | 0 | 187.26 | 127.04 | 32.73 | 26.61 | 0 | 186.38 | 28.66 | 35
304 | PURBA MEDINIPUR | SM/11883 | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | TSM/011811 | 40018792 | New | MVS | GO2223006384PH | 17/08/2022 | 391.09 | 37.81 | 428.89 | Tamluk Division | Midnapore Mechanical Division | 73.51 | 10 | 15.13 | 23.65 | 122.29 | 73.51 | 10 | 15.13 | 23.65 | 122.29 | 28.51 | 35
305 | PURBA MEDINIPUR | SM/13857 | NONAKOURDA AND IT'S ADJOINING MOUJAS | TSM/015987 | 40027007 | New | MVS | GO2223010096PH | 25/11/2022 | 392.22 | 36.66 | 428.88 | Tamluk Division | Midnapore Mechanical Division | 63.18 | 8.06 | 6.27 | 0 | 77.5 | 63.18 | 8.06 | 6.27 | 0 | 77.5 | 18.07 | 15
306 | PURBA MEDINIPUR | SM/18303 | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | TSM/017173 | 40026713 | New | MVS | 1662/PHE-28011/22/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1398.79 | 59.76 | 1458.55 | Tamluk Division | Midnapore Mechanical Division | 327.7 | 16.6 | 72.77 | 65.46 | 482.52 | 327.7 | 16.6 | 72.77 | 62.35 | 479.41 | 32.87 | 25
307 | PURBA MEDINIPUR | SM/12292 | PACHAHRI & ADJOINING MOUJAS PWSS | TSM/014128 | 40023045 | New | MVS | GO2223007331PH | 09/09/2022 | 575.7 | 38.39 | 614.09 | Tamluk Division | Midnapore Mechanical Division | 217.17 | 7.25 | 39.88 | 50.24 | 314.54 | 217.17 | 7.25 | 39.88 | 50.24 | 314.54 | 51.22 | 70
308 | PURBA MEDINIPUR | SM/12430 | PADIMA AND ADJOINING MOUJAS PWSS | TSM/014852 | 40025888 | New | MVS | GO2223007633PH | 13/09/2022 | 422.61 | 37.64 | 460.25 | Tamluk Division | Midnapore Mechanical Division | 211.01 | 33.93 | 21.42 | 0 | 266.36 | 211.01 | 33.93 | 21.42 | 0 | 266.36 | 57.87 | 80
309 | PURBA MEDINIPUR | SM/12400 | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014480 | 40026112 | New | MVS | GO2223007595PH | 13/09/2022 | 428.68 | 36.46 | 465.14 | Tamluk Division | Midnapore Mechanical Division | 127.31 | 23.99 | 45.89 | 0 | 197.19 | 127.31 | 23.99 | 45.89 | 0 | 197.19 | 42.39 | 10
310 | PURBA MEDINIPUR | SM/12508 | PALPARA AND ADJOINING MOUJAS PWSS | TSM/014407 | 40026426 | New | MVS | GO2223007640PH | 13/09/2022 | 714.25 | 40.57 | 754.82 | Tamluk Division | Midnapore Mechanical Division | 126.69 | 25.92 | 14.08 | 0 | 166.7 | 126.69 | 25.92 | 14.08 | 0 | 166.7 | 22.08 | 10
311 | PURBA MEDINIPUR | SM/12173 | PANCH BAJARI & ADJOINING MOUJAS PWSS | TSM/013501 | 40021589 | New | MVS | GO2223007184PH | 07/09/2022 | 447.89 | 36.38 | 484.28 | Tamluk Division | Midnapore Mechanical Division | 94.95 | 11.85 | 6.24 | 47.53 | 160.57 | 94.95 | 11.85 | 6.24 | 47.53 | 160.57 | 33.16 | 70
312 | PURBA MEDINIPUR | SM/16201 | PANCHBERYA PIPED WATER SUPPLY SCHEME | TSM/019332 | 40052292 | New | SVS | GO2223014795PH | 23/02/2023 | 159.3 | 12.64 | 171.95 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 4.29 | 0 | 4.29 | 2.49
313 | PURBA MEDINIPUR | SM/12170 | PANCHET AND ADJOINING MOUJAS PWSS | TSM/013494 | 40021598 | New | MVS | GO2223007188PH | 07/09/2022 | 858.97 | 38.85 | 897.82 | Tamluk Division | Midnapore Mechanical Division | 211.54 | 10.97 | 11.8 | 0 | 234.32 | 211.54 | 10.97 | 11.8 | 0 | 234.32 | 26.1 | 59
314 | PURBA MEDINIPUR | SM/12506 | PANUSI AND ADJOINING MOUJAS PWSS | TSM/014429 | 40026319 | New | MVS | GO2223007649PH | 13/09/2022 | 749.43 | 38.73 | 788.16 | Tamluk Division | Midnapore Mechanical Division | 248.99 | 17.93 | 31.27 | 44.86 | 343.05 | 248.99 | 17.93 | 31.27 | 44.86 | 343.05 | 43.53 | 30
315 | PURBA MEDINIPUR | SM/13699 | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | TSM/015384 | 40026861 | New | MVS | GO2223009726PH | 14/11/2022 | 1057.73 | 39.49 | 1097.22 | Tamluk Division | Midnapore Mechanical Division | 617.04 | 29.49 | 35.69 | 0 | 682.23 | 617.04 | 29.49 | 35.69 | 0 | 682.23 | 62.18 | 45
316 | PURBA MEDINIPUR | SM/13853 | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | TSM/016081 | 40026952 | New | MVS | GO2223010103PH | 25/11/2022 | 470.85 | 36.63 | 507.49 | Tamluk Division | Midnapore Mechanical Division | 0 | 9.75 | 6.1 | 0 | 15.85 | 0 | 9.75 | 6.1 | 0 | 15.85 | 3.12 | 15
317 | PURBA MEDINIPUR | SM/12164 | PATNA & ADJOINING MOUZAS | TSM/013343 | 40021618 | New | MVS | GO2223007201PH | 07/09/2022 | 1024.59 | 40.49 | 1065.08 | Tamluk Division | Midnapore Mechanical Division | 437.25 | 30.94 | 18.02 | 0 | 486.22 | 437.25 | 26.96 | 18.02 | 0 | 482.23 | 45.28 | 15
318 | PURBA MEDINIPUR | SM/14839 | Piped Water Supply Scheme for Bathuari Zone-I | TSM/017717 | 40052348 | Augmentation | MVS | GO2223013002PH | 03/02/2023 | 181.49 | 0 | 181.49 | Tamluk Division | Midnapore Mechanical Division | 87.07 | 0 | 0 | 0 | 87.07 | 87.07 | 0 | 0 | 0 | 87.07 | 47.98 | 35
319 | PURBA MEDINIPUR | SM/15853 | Piped Water Supply Scheme for Bathuari Zone-II | TSM/017729 | 40053394 | Augmentation | MVS | GO2223014228PH | 20/02/2023 | 404.63 | 35.09 | 439.72 | Tamluk Division | Midnapore Mechanical Division | 105.36 | 13.98 | 12.05 | 0 | 131.38 | 105.36 | 13.98 | 12.05 | 0 | 131.38 | 29.88 | 25
320 | PURBA MEDINIPUR | SM/16300 | Piped Water Supply Scheme for Bathuari Zone-III | TSM/017733 | 40053444 | Augmentation | MVS | GO2223014803PH | 23/02/2023 | 361.71 | 35.09 | 396.8 | Tamluk Division | Midnapore Mechanical Division | 61.02 | 7.77 | 13.52 | 0 | 82.31 | 61.02 | 7.22 | 13.52 | 0 | 81.77 | 20.61 | 5
321 | PURBA MEDINIPUR | SM/15845 | Piped Water Supply Scheme for Bathuari Zone-IV | TSM/017749 | 40053448 | Augmentation | MVS | GO2223014225PH | 20/02/2023 | 388.08 | 39.93 | 428.01 | Tamluk Division | Midnapore Mechanical Division | 29.63 | 8.39 | 0 | 0 | 38.03 | 29.63 | 8.39 | 0 | 0 | 38.03 | 8.88 | 5
322 | PURBA MEDINIPUR | SM/16284 | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | TSM/017995 | 40056856 | Augmentation | MVS | GO2223014801PH | 23/02/2023 | 344.07 | 59.74 | 403.81 | Tamluk Division | Midnapore Mechanical Division | 121.58 | 13.67 | 0 | 0 | 135.26 | 121.58 | 13.67 | 0 | 0 | 135.26 | 33.5 | 5
323 | PURBA MEDINIPUR | SM/14840 | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | TSM/017929 | 40052385 | Augmentation | SVS | GO2223013000PH | 03/02/2023 | 154.51 | 0 | 154.51 | Tamluk Division | Midnapore Mechanical Division | 64.07 | 0 | 0 | 0 | 64.07 | 64.07 | 0 | 0 | 0 | 64.07 | 41.47 | 20
324 | PURBA MEDINIPUR | SM/14836 | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | TSM/018371 | 40052253 | Augmentation | MVS | GO2223012999PH | 03/02/2023 | 344.02 | 47.38 | 391.4 | Tamluk Division | Midnapore Mechanical Division | 81.91 | 8.66 | 0 | 0 | 90.57 | 81.91 | 8.66 | 0 | 0 | 90.57 | 23.14 | 65
325 | PURBA MEDINIPUR | SM/15844 | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | TSM/018383 | 40056866 | Augmentation | MVS | GO2223014232PH | 20/02/2023 | 396.63 | 47.38 | 444.01 | Tamluk Division | Midnapore Mechanical Division | 2.89 | 0 | 0 | 0 | 2.89 | 2.89 | 0 | 0 | 0 | 2.89 | 0.65 | 25
326 | PURBA MEDINIPUR | SM/14841 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | TSM/018396 | 40052398 | Augmentation | SVS | GO2223013001PH | 03/02/2023 | 207.52 | 0 | 207.52 | Tamluk Division | Midnapore Mechanical Division | 63.23 | 0 | 0 | 0 | 63.23 | 63.23 | 0 | 0 | 0 | 63.23 | 30.47 | 25
327 | PURBA MEDINIPUR | SM/15841 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | TSM/018410 | 40056894 | Augmentation | MVS | GO2223014247PH | 20/02/2023 | 397.55 | 35.09 | 432.64 | Tamluk Division | Midnapore Mechanical Division | 3.22 | 9.94 | 0 | 0 | 13.16 | 3.22 | 9.94 | 0 | 0 | 13.16 | 3.04 | 15
328 | PURBA MEDINIPUR | SM/15843 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | TSM/018403 | 40056878 | Augmentation | MVS | GO2223014251PH | 20/02/2023 | 452.06 | 35.09 | 487.15 | Tamluk Division | Midnapore Mechanical Division | 84 | 6.19 | 12.05 | 0 | 102.24 | 84 | 6.19 | 12.05 | 0 | 102.24 | 20.99
329 | PURBA MEDINIPUR | SM/16286 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | TSM/018411 | 40056906 | Augmentation | MVS | GO2223014800PH | 23/02/2023 | 425.94 | 35.09 | 461.03 | Tamluk Division | Midnapore Mechanical Division | 226.65 | 20.24 | 0 | 0 | 246.89 | 226.65 | 20.24 | 0 | 0 | 246.89 | 53.55 | 10
330 | PURBA MEDINIPUR | SM/16295 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | TSM/018417 | 40056934 | Augmentation | SVS | GO2223014799PH | 23/02/2023 | 423.14 | 35.09 | 458.23 | Tamluk Division | Midnapore Mechanical Division | 173.56 | 7.38 | 12.05 | 0 | 192.99 | 173.56 | 7.38 | 12.05 | 0 | 192.99 | 42.12 | 35
331 | PURBA MEDINIPUR | SM/18766 | Piped Water Supply Scheme for Sankarpur Zone-I | TSM/017874 | 40053452 | Augmentation | MVS | 2531/PHE/IV/W-635/23 | 23/08/2023 | 301.32 | 68.97 | 370.29 | Tamluk Division | Midnapore Mechanical Division | 85.92 | 19.14 | 0 | 0 | 105.07 | 85.92 | 19.14 | 0 | 0 | 105.07 | 28.37 | 25
332 | PURBA MEDINIPUR | SM/14842 | Piped Water Supply Scheme for Sankarpur Zone-II | TSM/017879 | 40052373 | Augmentation | SVS | GO2223013003PH | 03/02/2023 | 70.89 | 0 | 70.89 | Tamluk Division |  | 18.43 | 0 | 0 | 0 | 18.43 | 18.43 | 0 | 0 | 0 | 18.43 | 26.01 | 10
333 | PURBA MEDINIPUR | SM/15846 | Piped Water Supply Scheme for Sankarpur Zone-III | TSM/017882 | 40053457 | Augmentation | MVS | GO2223014250PH | 20/02/2023 | 269.78 | 68.97 | 338.75 | Tamluk Division | Midnapore Mechanical Division | 4.44 | 18.66 | 12.18 | 0 | 35.28 | 4.44 | 18.66 | 12.18 | 0 | 35.28 | 10.41 | 15
334 | PURBA MEDINIPUR | SM/16305 | Piped Water Supply Scheme for Sankarpur Zone-IV | TSM/017890 | 40053458 | Augmentation | MVS | GO2223014802PH | 23/02/2023 | 271.47 | 68.97 | 340.44 | Tamluk Division | Midnapore Mechanical Division | 74.12 | 32.13 | 0 | 0 | 106.25 | 74.12 | 32.13 | 0 | 0 | 106.25 | 31.21 | 70
335 | PURBA MEDINIPUR | SM/15847 | Piped Water Supply Scheme for Sankarpur Zone-V | TSM/017899 | 40053460 | Augmentation | MVS | GO2223014210PH | 20/02/2023 | 273.55 | 68.97 | 342.52 | Tamluk Division | Midnapore Mechanical Division | 66.89 | 26.05 | 0 | 0 | 92.95 | 66.89 | 26.05 | 0 | 0 | 92.95 | 27.14 | 25
336 | PURBA MEDINIPUR | SM/13886 | POTA PAKURIA AND IT'S ADJOINING MOUJAS | TSM/015859 | 40027022 | New | MVS | GO2223010051PH | 25/11/2022 | 518.66 | 36.67 | 555.33 | Tamluk Division | Midnapore Mechanical Division | 93.43 | 13.44 | 6.03 | 0 | 112.9 | 93.43 | 13.44 | 6.03 | 0 | 112.9 | 20.33 | 10
337 | PURBA MEDINIPUR | SM/13889 | Providing FHTC (Functional Household Tap Connection) with Augmentation of Murisai Water Supply Scheme | TSM/016062 | 40033784 | Augmentation | MVS | GO2223010047PH | 25/11/2022 | 133.52 | 0 | 133.52 | Tamluk Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
338 | PURBA MEDINIPUR | SM/08698 | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | TSM/005356 | 8368870 | New | MVS | GO2122002809PH | 01/09/2021 | 746.17 | 0 | 746.17 | Tamluk Division |  | 630.13 | 0 | 0 | 0 | 630.13 | 630.13 | 0 | 0 | 0 | 630.13 | 84.45 | 95
339 | PURBA MEDINIPUR | SM/18402 | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | TSM/009200 | 40032601 | New | MVS | 1850/PHE-28011/221/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 44328.08 | 5493.48 | 49821.56 | Tamluk Division | Midnapore Mechanical Division | 382.94 | 396.47 | 0 | 0 | 779.41 | 382.94 | 396.47 | 0 | 0 | 779.41 | 1.56 | 10
340 | PURBA MEDINIPUR | SM/12818 | PURANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/014593 | 40024516 | New | MVS | GO2223007967PH | 20/09/2022 | 603.13 | 37.66 | 640.79 | Tamluk Division | Midnapore Mechanical Division | 145.64 | 25.98 | 21.83 | 0 | 193.45 | 145.64 | 25.98 | 21.83 | 0 | 193.45 | 30.19
341 | PURBA MEDINIPUR | SM/13686 | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | TSM/015583 | 40026715 | New | MVS | GO2223009735PH | 14/11/2022 | 483.4 | 36.66 | 520.05 | Tamluk Division | Midnapore Mechanical Division | 156.25 | 29.1 | 23.31 | 0 | 208.66 | 156.25 | 23.15 | 23.31 | 0 | 202.71 | 38.98 | 35
342 | PURBA MEDINIPUR | SM/12507 | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS | TSM/014426 | 40026329 | New | MVS | GO2223007646PH | 13/09/2022 | 554.83 | 38.61 | 593.43 | Tamluk Division | Midnapore Mechanical Division | 102.22 | 14.3 | 28 | 0 | 144.53 | 102.22 | 14.3 | 28 | 0 | 144.53 | 24.36 | 35
343 | PURBA MEDINIPUR | SM/12434 | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | TSM/014736 | 40025929 | New | MVS | GO2223007619PH | 13/09/2022 | 583.29 | 34.44 | 617.73 | Tamluk Division | Midnapore Mechanical Division | 330.98 | 13.38 | 18.74 | 0 | 363.1 | 330.98 | 13.38 | 18.74 | 0 | 363.1 | 58.78 | 65
344 | PURBA MEDINIPUR | SM/14742 | PURBA NUKHA AND ADJOINING MOUJAS | TSM/017102 | 40026648 | New | MVS | GO2223012668PH | 31/01/2023 | 627.55 | 40.73 | 668.28 | Tamluk Division | Midnapore Mechanical Division | 150.23 | 15.01 | 0 | 0 | 165.24 | 150.23 | 15.01 | 0 | 0 | 165.24 | 24.73 | 25
345 | PURBA MEDINIPUR | SM/12154 | PURBA RADHAPUR & ADJOINING MOUZAS | TSM/013212 | 40021786 | New | MVS | GO2223007181PH | 07/09/2022 | 719.21 | 38.85 | 758.06 | Tamluk Division | Midnapore Mechanical Division | 254.92 | 11.57 | 42.86 | 0 | 309.35 | 254.92 | 11.57 | 42.86 | 0 | 309.35 | 40.81 | 25
346 | PURBA MEDINIPUR | SM/15848 | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | TSM/019327 | 40052276 | New | MVS | GO2223014218PH | 20/02/2023 | 230.86 | 10.85 | 241.71 | Tamluk Division | Midnapore Mechanical Division | 40.89 | 3.22 | 1.4 | 24.09 | 69.59 | 40.89 | 3.22 | 1.4 | 24.09 | 69.59 | 28.79 | 80
347 | PURBA MEDINIPUR | SM/12428 | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/014867 | 40025877 | New | MVS | GO2223007617PH | 13/09/2022 | 376.66 | 35.58 | 412.24 | Tamluk Division | Midnapore Mechanical Division | 169.52 | 28.51 | 11.25 | 0 | 209.28 | 169.52 | 28.51 | 11.25 | 0 | 209.28 | 50.77 | 80
348 | PURBA MEDINIPUR | SM/11886 | PUTPUTIA PWSS | TSM/011609 | 40018796 | New | MVS | GO2223006395PH | 17/08/2022 | 543.41 | 38.12 | 581.53 | Tamluk Division | Midnapore Mechanical Division | 237.21 | 29.92 | 20.08 | 0 | 287.21 | 237.21 | 29.92 | 20.08 | 0 | 287.21 | 49.39 | 65
349 | PURBA MEDINIPUR | SM/12156 | RADHABALLAV CHAK & ADJOINING MOUZAS | TSM/013217 | 40021658 | New | MVS | GO2223007164PH | 07/09/2022 | 675.77 | 40.1 | 715.87 | Tamluk Division | Midnapore Mechanical Division | 356.59 | 18.43 | 12.48 | 0 | 387.5 | 356.59 | 18.43 | 12.48 | 0 | 387.5 | 54.13 | 70
350 | PURBA MEDINIPUR | SM/13691 | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | TSM/015571 | 40026758 | New | MVS | GO2223009739PH | 14/11/2022 | 534.38 | 36.7 | 571.07 | Tamluk Division | Midnapore Mechanical Division | 176.75 | 17.71 | 43.39 | 0 | 237.86 | 176.75 | 17.71 | 43.39 | 0 | 237.86 | 41.65 | 10
351 | PURBA MEDINIPUR | SM/12509 | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | TSM/014405 | 40026448 | New | MVS | GO2223007637PH | 13/09/2022 | 644.47 | 38.61 | 683.07 | Tamluk Division | Midnapore Mechanical Division | 292.71 | 10.19 | 18.33 | 41.56 | 362.79 | 292.71 | 10.19 | 18.33 | 41.56 | 362.79 | 53.11 | 35
352 | PURBA MEDINIPUR | SM/12147 | RAMCHANDRAPUR AND ADJOINING MOUJAS | TSM/013184 | 40022440 | New | MVS | GO2223007257PH | 07/09/2022 | 616.62 | 40.1 | 656.72 | Tamluk Division | Midnapore Mechanical Division | 260.6 | 32.07 | 46.91 | 30.82 | 370.4 | 260.6 | 32.07 | 46.91 | 30.82 | 370.4 | 56.4 | 85
353 | PURBA MEDINIPUR | SM/12140 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | TSM/013149 | 40022494 | New | MVS | GO2223007261PH | 07/09/2022 | 544.24 | 37.86 | 582.1 | Tamluk Division | Midnapore Mechanical Division | 310.22 | 18.39 | 29.39 | 0 | 358.01 | 310.22 | 18.39 | 29.39 | 0 | 358.01 | 61.5 | 85
354 | PURBA MEDINIPUR | SM/09272 | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008432 | 8390287 | Augmentation | MVS | GO2122004874PH | 03/11/2021 | 366.83 | 0 | 366.83 | Tamluk Division |  | 319.43 | 0 | 12.11 | 0 | 331.54 | 319.43 | 0 | 12.11 | 0 | 331.54 | 90.38 | 75
355 | PURBA MEDINIPUR | SM/09286 | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | TSM/008436 | 8390338 | Augmentation | MVS | GO2122004881PH | 03/11/2021 | 764.17 | 0 | 764.17 | Tamluk Division |  | 609.09 | 0 | 24.01 | 28.76 | 661.86 | 608.5 | 0 | 24.01 | 28.76 | 661.27 | 86.53 | 90
356 | PURBA MEDINIPUR | SM/09280 | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | TSM/008365 | 8390201 | Augmentation | MVS | GO2122004882PH | 03/11/2021 | 445.45 | 0 | 445.45 | Tamluk Division |  | 220.19 | 0 | 11.07 | 0 | 231.26 | 220.19 | 0 | 11.07 | 0 | 231.26 | 51.91 | 96
357 | PURBA MEDINIPUR | SM/09914 | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008357 | 40001110 | Augmentation | MVS | GO2122006633PH | 10/12/2021 | 1060.63 | 0 | 1060.63 | Tamluk Division | Midnapore Mechanical Division | 788.8 | 0 | 54.81 | 0 | 843.6 | 788.8 | 0 | 54.81 | 0 | 843.6 | 79.54 | 80
358 | PURBA MEDINIPUR | SM/09275 | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | TSM/008433 | 8390301 | Augmentation | MVS | GO2122004880PH | 03/11/2021 | 478.65 | 0 | 478.65 | Tamluk Division |  | 439.21 | 0 | 10.33 | 0 | 449.54 | 439.21 | 0 | 10.33 | 0 | 449.54 | 93.92 | 95
359 | PURBA MEDINIPUR | SM/09279 | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008366 | 8390213 | Augmentation | SVS | GO2122004882PH | 03/11/2021 | 366.62 | 0 | 366.62 | Tamluk Division |  | 349.09 | 0 | 0 | 0 | 349.09 | 349.09 | 0 | 0 | 0 | 349.09 | 95.22 | 95
360 | PURBA MEDINIPUR | SM/09277 | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008364 | 8390191 | Augmentation | MVS | GO2122004883PH | 03/11/2021 | 315.94 | 0 | 315.94 | Tamluk Division |  | 262.85 | 0 | 0 | 0 | 262.85 | 262.85 | 0 | 0 | 0 | 262.85 | 83.2 | 95
361 | PURBA MEDINIPUR | SM/09273 | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | TSM/008373 | 8390278 | Augmentation | MVS | GO2122004874PH | 03/11/2021 | 249.69 | 0 | 249.69 | Tamluk Division |  | 60.3 | 0 | 8.76 | 0 | 69.05 | 60.3 | 0 | 8.76 | 0 | 69.05 | 27.66 | 50
362 | PURBA MEDINIPUR | SM/16670 | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme. | TSM/019337 | 40062324 | Augmentation | MVS | GO2223015936PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 5.82 | 0 | 0 | 5.82 | 0 | 5.82 | 0 | 0 | 5.82 | 46.98
363 | PURBA MEDINIPUR | SM/16653 | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme. | TSM/019340 | 40061465 | Augmentation | MVS | GO2223015944PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 5.47 | 0 | 0 | 5.47 | 0 | 5.47 | 0 | 0 | 5.47 | 44.16
364 | PURBA MEDINIPUR | SM/16662 | Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme. | TSM/019353 | 40062521 | Augmentation | MVS | GO2223015956PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 4.4 | 0 | 0 | 4.4 | 0 | 4.4 | 0 | 0 | 4.4 | 35.5
365 | PURBA MEDINIPUR | SM/16655 | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. | TSM/019351 | 40062595 | Augmentation | MVS | GO2223015954PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.01 | 0 | 0 | 0.01 | 0 | 0.01 | 0 | 0 | 0.01 | 0.05
366 | PURBA MEDINIPUR | SM/16661 | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme. | TSM/019339 | 40062545 | Augmentation | MVS | GO2223015942PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 9.89 | 0 | 0 | 9.89 | 0 | 9.89 | 0 | 0 | 9.89 | 79.82 | 70
367 | PURBA MEDINIPUR | SM/16667 | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme. | TSM/019344 | 40062327 | Augmentation | MVS | GO2223015950PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
368 | PURBA MEDINIPUR | SM/16652 | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019356 | 40061410 | Augmentation | MVS | GO2223015961PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.18 | 0 | 0 | 0.18 | 0 | 0.18 | 0 | 0 | 0.18 | 1.43 | 70
369 | PURBA MEDINIPUR | SM/16668 | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019343 | 40062312 | Augmentation | MVS | GO2223015948PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
370 | PURBA MEDINIPUR | SM/16660 | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019352 | 40062578 | Augmentation | SVS | GO2223015955PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
371 | PURBA MEDINIPUR | SM/16671 | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. | TSM/019345 | 40062330 | Augmentation | SVS | GO2223015951PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 6.88 | 0 | 0 | 6.88 | 0 | 6.88 | 0 | 0 | 6.88 | 55.48
372 | PURBA MEDINIPUR | SM/16650 | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. | TSM/019346 | 40061394 | Augmentation | MVS | GO2223015843PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0.15 | 0 | 0 | 0.15 | 1.21
373 | PURBA MEDINIPUR | SM/16664 | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme. | TSM/019338 | 40062432 | Augmentation | MVS | GO2223015939PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 7.15 | 0 | 0 | 7.15 | 0 | 7.15 | 0 | 0 | 7.15 | 57.66
374 | PURBA MEDINIPUR | SM/16654 | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | TSM/019347 | 40062594 | Augmentation | MVS | GO2223015952PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 9.23 | 0 | 0 | 9.23 | 0 | 9.23 | 0 | 0 | 9.23 | 74.47
375 | PURBA MEDINIPUR | SM/16663 | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019341 | 40062499 | Augmentation | MVS | GO2223015945PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.18 | 0 | 0 | 0.18 | 0 | 0.18 | 0 | 0 | 0.18 | 1.42 | 50
376 | PURBA MEDINIPUR | SM/16659 | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019349 | 40062518 | Augmentation | MVS | GO2223015953PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 10.53 | 0 | 0 | 10.53 | 0 | 10.53 | 0 | 0 | 10.53 | 84.93 | 70
377 | PURBA MEDINIPUR | SM/16666 | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. | TSM/019342 | 40062411 | Augmentation | MVS | GO2223015947PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 7.32 | 0 | 0 | 7.32 | 0 | 7.32 | 0 | 0 | 7.32 | 59.08
378 | PURBA MEDINIPUR | SM/16665 | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019348 | 40062424 | Augmentation | MVS | GO2223015931PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 6.77 | 0 | 0 | 6.77 | 0 | 6.77 | 0 | 0 | 6.77 | 54.63
379 | PURBA MEDINIPUR | SM/16657 | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme. | TSM/019355 | 40062642 | Augmentation | MVS | GO2223015960PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
380 | PURBA MEDINIPUR | SM/16669 | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | TSM/019354 | 40062319 | Augmentation | MVS | GO2223015957PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.26 | 0 | 0 | 0.26 | 0 | 0.26 | 0 | 0 | 0.26 | 2.13 | 70
381 | PURBA MEDINIPUR | SM/08749 | Rejuvenation to accommodate FHTC under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division PHE Dte Purba Medinipur Phase II | TSM/007261 | 8365457 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 65.32 | 0 | 65.32 | Tamluk Division |  | 62.26 | 0 | 0 | 0 | 62.26 | 62.26 | 0 | 0 | 0 | 62.26 | 95.31 | 100
382 | PURBA MEDINIPUR | SM/16658 | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme | TSM/019336 | 40062619 | Augmentation | MVS | GO2223015934PH | 14/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 10.44 | 0 | 0 | 10.44 | 0 | 10.44 | 0 | 0 | 10.44 | 84.21
383 | PURBA MEDINIPUR | SM/11861 | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011778 | 40018774 | Augmentation | MVS | GO2223006398PH | 17/08/2022 | 16.84 | 26.58 | 43.42 | Tamluk Division | Midnapore Mechanical Division | 11.46 | 16.79 | 0 | 0 | 28.25 | 11.46 | 16.79 | 0 | 0 | 28.25 | 65.07 | 90
384 | PURBA MEDINIPUR | SM/11860 | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011779 | 40018771 | Augmentation | MVS | GO2223006398PH | 17/08/2022 | 53.79 | 53.16 | 106.95 | Tamluk Division | Midnapore Mechanical Division | 28.74 | 13.81 | 0 | 0 | 42.55 | 28.74 | 13.81 | 0 | 0 | 42.55 | 39.79 | 22
385 | PURBA MEDINIPUR | SM/11862 | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/010577 | 40018776 | Augmentation | MVS | GO2223006398PH | 17/08/2022 | 43.28 | 26.58 | 69.86 | Tamluk Division | Midnapore Mechanical Division | 31.32 | 25.8 | 3.48 | 0 | 60.6 | 31.32 | 25.8 | 3.48 | 0 | 60.6 | 86.75 | 74
386 | PURBA MEDINIPUR | SM/11949 | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/010578 | 40019015 | Augmentation | MVS | GO2223006677PH | 24/08/2022 | 44.5 | 26.58 | 71.08 | Tamluk Division | Midnapore Mechanical Division | 2.11 | 9.66 | 0 | 0 | 11.77 | 2.11 | 9.66 | 0 | 0 | 11.77 | 16.56 | 10
387 | PURBA MEDINIPUR | SM/11859 | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011780 | 40018770 | Augmentation | MVS | GO2223006398PH | 17/08/2022 | 11.37 | 26.58 | 37.95 | Tamluk Division | Midnapore Mechanical Division | 0 | 8.29 | 0 | 0 | 8.29 | 0 | 8.29 | 0 | 0 | 8.29 | 21.84 | 15
388 | PURBA MEDINIPUR | SM/09055 | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) | TSM/008277 | 8384652 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 71.42 | 0 | 71.42 | Tamluk Division |  | 67.37 | 0 | 0 | 0 | 67.37 | 67.16 | 0 | 0 | 0 | 67.16 | 94.04 | 100
389 | PURBA MEDINIPUR | SM/09054 | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) | TSM/008276 | 8384648 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 50.27 | 0 | 50.27 | Tamluk Division |  | 50 | 0 | 0 | 0 | 50 | 46.55 | 0 | 0 | 0 | 46.55 | 92.6 | 100
390 | PURBA MEDINIPUR | SM/09057 | Retorfitting to accommodate FHTC under JJM in Dulalpur PWSS. | TSM/008402 | 7747556 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 59.18 | 0 | 59.18 | Tamluk Division |  | 57.41 | 0 | 0 | 0 | 57.41 | 57.41 | 0 | 0 | 0 | 57.41 | 97.02 | 98
391 | PURBA MEDINIPUR | SM/09053 | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) | TSM/008275 | 8384645 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 14.94 | 0 | 14.94 | Tamluk Division |  | 12.23 | 0 | 0 | 0 | 12.23 | 12.22 | 0 | 0 | 0 | 12.22 | 81.8 | 100
392 | PURBA MEDINIPUR | SM/09056 | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | TSM/008278 | 7747558 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 88.01 | 0 | 88.01 | Tamluk Division |  | 85.36 | 0 | 0 | 0 | 85.36 | 85.36 | 0 | 0 | 0 | 85.36 | 97 | 80
393 | PURBA MEDINIPUR | SM/12300 | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. | TSM/010962 | 40021611 | Retrofitting | MVS | GO2223007340PH | 09/09/2022 | 94.16 | 0 | 94.16 | Tamluk Division |  | 69.04 | 0 | 0 | 0 | 69.04 | 69.04 | 0 | 0 | 0 | 69.04 | 73.33 | 75
394 | PURBA MEDINIPUR | SM/12301 | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. | TSM/010963 | 40021608 | Retrofitting | MVS | GO2223007340PH | 09/09/2022 | 112.8 | 0 | 112.8 | Tamluk Division |  | 68.76 | 0 | 0 | 0 | 68.76 | 68.76 | 0 | 0 | 0 | 68.76 | 60.96 | 80
395 | PURBA MEDINIPUR | SM/09803 | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. | TSM/009116 | 7940811 | Retrofitting | MVS | GO2122006295PH | 01/12/2021 | 120.85 | 0 | 120.85 | Tamluk Division |  | 105 | 0 | 0 | 0 | 105 | 104.47 | 0 | 0 | 0 | 104.47 | 86.44 | 100
396 | PURBA MEDINIPUR | SM/09802 | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. | TSM/009117 | 7940825 | Retrofitting | MVS | GO2122006295PH | 01/12/2021 | 164.09 | 0 | 164.09 | Tamluk Division |  | 63.79 | 0 | 27.1 | 0 | 90.9 | 63.79 | 0 | 27.1 | 0 | 90.9 | 55.4 | 95
397 | PURBA MEDINIPUR | SM/10346 | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. | TSM/008953 | 7402035 | Retrofitting | MVS | GO2122010930PH | 16/03/2022 | 26.17 | 0 | 26.17 | Tamluk Division |  | 19.06 | 0 | 0 | 0 | 19.06 | 19.06 | 0 | 0 | 0 | 19.06 | 72.83 | 95
398 | PURBA MEDINIPUR | SM/10437 | Retrofitting to Accommodate FHTC (Balance Work) (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-V, Bloc | TSM/009910 | 6328427 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 19.89 | 0 | 19.89 | Tamluk Division |  | 16.09 | 0 | 0 | 0 | 16.09 | 16.09 | 0 | 0 | 0 | 16.09 | 80.89 | 100
399 | PURBA MEDINIPUR | SM/10435 | Retrofitting to Accommodate FHTC (Balance Work) (579 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-IV, Blo | TSM/009912 | 6328427 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 94.29 | 0 | 94.29 | Tamluk Division |  | 65.2 | 0 | 0 | 0 | 65.2 | 65.2 | 0 | 0 | 0 | 65.2 | 69.15 | 100
400 | PURBA MEDINIPUR | SM/08754 | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. | TSM/007251 | 7717937 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 60.34 | 0 | 60.34 | Tamluk Division |  | 56.73 | 0 | 0 | 0 | 56.73 | 56.73 | 0 | 0 | 0 | 56.73 | 94.01 | 100
401 | PURBA MEDINIPUR | SM/08751 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | TSM/007237 | 8365463 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 45.72 | 0 | 45.72 | Tamluk Division |  | 35.17 | 0 | 0 | 9.21 | 44.38 | 35.17 | 0 | 0 | 9.21 | 44.38 | 97.08 | 100
402 | PURBA MEDINIPUR | SM/16453 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | TSM/017483 | 40052435 | Retrofitting | MVS | GO2223015245PH | 03/03/2023 | 115.08 | 0 | 115.08 | Tamluk Division |  | 0 | 0 | 25.27 | 0 | 25.27 | 0 | 0 | 25.27 | 0 | 25.27 | 21.96 | 30
403 | PURBA MEDINIPUR | SM/09801 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. | TSM/009119 | 40010283 | Retrofitting | MVS | GO2122006295PH | 01/12/2021 | 160.98 | 0 | 160.98 | Tamluk Division |  | 144.09 | 0 | 0 | 0 | 144.09 | 144.09 | 0 | 0 | 0 | 144.09 | 89.51 | 98
404 | PURBA MEDINIPUR | SM/08745 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | TSM/007265 | 8365639 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 104.08 | 0 | 104.08 | Tamluk Division |  | 104 | 0 | 0 | 0 | 104 | 101.34 | 0 | 0 | 0 | 101.34 | 97.37 | 100
405 | PURBA MEDINIPUR | SM/10433 | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | TSM/008955 | 40013196 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 136.19 | 42.24 | 178.42 | Tamluk Division | Midnapore Mechanical Division | 72.2 | 0 | 0 | 0 | 72.2 | 72.2 | 0 | 0 | 0 | 72.2 | 40.47 | 70
406 | PURBA MEDINIPUR | SM/12303 | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | TSM/013464 | 40021614 | Retrofitting | MVS | GO2223007340PH | 09/09/2022 | 135.48 | 0 | 135.48 | Tamluk Division |  | 54.34 | 0 | 14.41 | 0 | 68.75 | 54.34 | 0 | 14.41 | 0 | 68.75 | 50.75 | 30
407 | PURBA MEDINIPUR | SM/08752 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II | TSM/007263 | 8365464 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 145.47 | 0 | 145.47 | Tamluk Division |  | 139.86 | 0 | 3.8 | 0 | 143.66 | 139.45 | 0 | 3.8 | 0 | 143.26 | 98.48 | 100
408 | PURBA MEDINIPUR | SM/08753 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK | TSM/007257 | 7734867 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 100.13 | 0 | 100.13 | Tamluk Division |  | 97.49 | 0 | 0 | 0 | 97.49 | 97.49 | 0 | 0 | 0 | 97.49 | 97.36 | 95
409 | PURBA MEDINIPUR | SM/16462 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | TSM/018236 | 40052278 | Augmentation | MVS | GO2223015240PH | 03/03/2023 | 85.82 | 42.24 | 128.06 | Tamluk Division | Midnapore Mechanical Division | 11.35 | 4.32 | 0 | 0 | 15.67 | 11.35 | 4.32 | 0 | 0 | 15.67 | 12.24 | 35
410 | PURBA MEDINIPUR | SM/16465 | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | TSM/015866 | 40052381 | Augmentation | MVS | GO2223015237PH | 03/03/2023 | 70.47 | 51.83 | 122.31 | Tamluk Division | Midnapore Mechanical Division | 13.24 | 11.77 | 0 | 0 | 25.01 | 13.24 | 11.77 | 0 | 0 | 25.01 | 20.45 | 15
411 | PURBA MEDINIPUR | SM/08758 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II | TSM/007236 | 8365470 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 17.38 | 0 | 17.38 | Tamluk Division |  | 15.68 | 0 | 0 | 0 | 15.68 | 15.68 | 0 | 0 | 0 | 15.68 | 90.23 | 100
412 | PURBA MEDINIPUR | SM/08755 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. | TSM/007248 | 7326710 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 91.37 | 0 | 91.37 | Tamluk Division |  | 90.94 | 0 | 0 | 0 | 90.94 | 90.94 | 0 | 0 | 0 | 90.94 | 99.53 | 99
413 | PURBA MEDINIPUR | SM/08756 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. | TSM/007247 | 7326710 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 42.75 | 0 | 42.75 | Tamluk Division |  | 41.31 | 0 | 0 | 0 | 41.31 | 41.31 | 0 | 0 | 0 | 41.31 | 96.63 | 99
414 | PURBA MEDINIPUR | SM/16466 | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) | TSM/018683 | 40049100 | Retrofitting | MVS | GO2223015241PH | 03/03/2023 | 39.56 | 0 | 39.56 | Tamluk Division |  | 25.66 | 0 | 0 | 0 | 25.66 | 25.66 | 0 | 0 | 0 | 25.66 | 64.87 | 50
415 | PURBA MEDINIPUR | SM/09049 | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. | TSM/008271 | 8384629 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 41.88 | 0 | 41.88 | Tamluk Division |  | 40.65 | 0 | 0 | 0 | 40.65 | 40.65 | 0 | 0 | 0 | 40.65 | 97.08 | 100
416 | PURBA MEDINIPUR | SM/09800 | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. | TSM/009108 | 7734869 | Retrofitting | MVS | GO2122006295PH | 01/12/2021 | 149.22 | 0 | 149.22 | Tamluk Division |  | 92.17 | 0 | 14.03 | 0 | 106.19 | 92.17 | 0 | 14.03 | 0 | 106.19 | 71.16 | 95
417 | PURBA MEDINIPUR | SM/08757 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. | TSM/007234 | 8365469 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 25.02 | 0 | 25.02 | Tamluk Division |  | 24 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 24 | 95.93 | 100
418 | PURBA MEDINIPUR | SM/09339 | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | TSM/008499 | 8390185 | Retrofitting | MVS | GO2122005396PH | 12/11/2021 | 125.52 | 0 | 125.52 | Tamluk Division |  | 107.89 | 0 | 0 | 15 | 122.89 | 107.73 | 0 | 0 | 15 | 122.73 | 97.77 | 100
419 | PURBA MEDINIPUR | SM/08747 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II | TSM/007239 | 7326756 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 23.05 | 0 | 23.05 | Tamluk Division |  | 21.15 | 0 | 0 | 0 | 21.15 | 21.15 | 0 | 0 | 0 | 21.15 | 91.77 | 100
420 | PURBA MEDINIPUR | SM/16463 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | TSM/018162 | 40049095 | Augmentation | MVS | GO2223015235PH | 03/03/2023 | 88.03 | 42.24 | 130.27 | Tamluk Division | Midnapore Mechanical Division | 6.52 | 0 | 0 | 0 | 6.52 | 6.52 | 0 | 0 | 0 | 6.52 | 5 | 10
421 | PURBA MEDINIPUR | SM/09052 | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block | TSM/008274 | 8384634 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 76.42 | 0 | 76.42 | Tamluk Division |  | 74 | 0 | 0 | 0 | 74 | 74 | 0 | 0 | 0 | 74 | 96.83 | 100
422 | PURBA MEDINIPUR | SM/16458 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | TSM/018905 | 40052064 | Augmentation | MVS | GO2223015234PH | 03/03/2023 | 127.96 | 42.24 | 170.2 | Tamluk Division | Midnapore Mechanical Division | 7.52 | 3.28 | 0 | 0 | 10.8 | 7.52 | 3.28 | 0 | 0 | 10.8 | 6.35 | 15
423 | PURBA MEDINIPUR | SM/09074 | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. | TSM/008355 | 7326775 | Retrofitting | MVS | GO2122004573PH | 28/10/2021 | 61.29 | 0 | 61.29 | Tamluk Division |  | 28.56 | 0 | 0 | 0 | 28.56 | 28.56 | 0 | 0 | 0 | 28.56 | 46.6 | 100
424 | PURBA MEDINIPUR | SM/10432 | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block | TSM/010126 | 7941368 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 126.97 | 0 | 126.97 | Tamluk Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
425 | PURBA MEDINIPUR | SM/09804 | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | TSM/009110 | 7755526 | Retrofitting | MVS | GO2122006295PH | 01/12/2021 | 166.66 | 0 | 166.66 | Tamluk Division |  | 99.93 | 0 | 15.3 | 0 | 115.23 | 99.93 | 0 | 15.3 | 0 | 115.23 | 69.14 | 80
426 | PURBA MEDINIPUR | SM/12302 | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | TSM/010936 | 40021622 | Retrofitting | SVS | GO2223007340PH | 09/09/2022 | 45.03 | 0 | 45.03 | Tamluk Division |  | 37.68 | 0 | 4.7 | 0 | 42.38 | 37.68 | 0 | 4.7 | 0 | 42.38 | 94.12 | 90
427 | PURBA MEDINIPUR | SM/08746 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK | TSM/007259 | 7734866 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 98.91 | 0 | 98.91 | Tamluk Division |  | 95.93 | 0 | 0 | 0 | 95.93 | 95.93 | 0 | 0 | 0 | 95.93 | 96.99 | 79
428 | PURBA MEDINIPUR | SM/16461 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | TSM/018238 | 40049081 | Augmentation | MVS | GO2223015239PH | 03/03/2023 | 88.94 | 42.24 | 131.18 | Tamluk Division | Midnapore Mechanical Division | 27.05 | 4.37 | 0 | 0 | 31.42 | 27.05 | 4.37 | 0 | 0 | 31.42 | 23.95 | 25
429 | PURBA MEDINIPUR | SM/16460 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | TSM/018245 | 40049070 | Augmentation | MVS | GO2223015238PH | 03/03/2023 | 87.88 | 51.83 | 139.71 | Tamluk Division | Midnapore Mechanical Division | 28.15 | 12.99 | 0 | 0 | 41.14 | 28.15 | 12.99 | 0 | 0 | 41.14 | 29.45 | 25
430 | PURBA MEDINIPUR | SM/10345 | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | TSM/009922 | 40006278 | Retrofitting | MVS | GO2122010930PH | 16/03/2022 | 43.75 | 0 | 43.75 | Tamluk Division |  | 3.52 | 0 | 0 | 0 | 3.52 | 3.52 | 0 | 0 | 0 | 3.52 | 8.05 | 100
431 | PURBA MEDINIPUR | SM/08750 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK | TSM/007235 | 8365459 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 99.92 | 0 | 99.92 | Tamluk Division |  | 96.12 | 0 | 0 | 0 | 96.12 | 96.12 | 0 | 0 | 0 | 96.12 | 96.2 | 100
432 | PURBA MEDINIPUR | SM/16467 | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) | TSM/018682 | 40049115 | Retrofitting | MVS | GO2223015038PH | 03/03/2023 | 72.07 | 0 | 72.07 | Tamluk Division |  | 57.26 | 0 | 0 | 0 | 57.26 | 57.26 | 0 | 0 | 0 | 57.26 | 79.44 | 50
433 | PURBA MEDINIPUR | SM/13238 | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | TSM/014506 | 40026923 | Retrofitting | MVS | GO2223008580PH | 14/10/2022 | 100.94 | 42.24 | 143.18 | Tamluk Division | Midnapore Mechanical Division | 39.82 | 7.35 | 17.54 | 0 | 64.7 | 39.82 | 7.35 | 17.54 | 0 | 64.7 | 45.19 | 45
434 | PURBA MEDINIPUR | SM/12177 | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | TSM/012057 | 7940799 | Retrofitting | MVS | GO2223007266PH | 07/09/2022 | 154.98 | 0 | 154.98 | Tamluk Division |  | 64.87 | 0 | 16.37 | 0 | 81.24 | 64.87 | 0 | 16.37 | 0 | 81.24 | 52.42 | 90
435 | PURBA MEDINIPUR | SM/08748 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | TSM/007238 | 8365635 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 60.25 | 0 | 60.25 | Tamluk Division |  | 56.29 | 0 | 0 | 0 | 56.29 | 56.26 | 0 | 0 | 0 | 56.26 | 93.38 | 100
436 | PURBA MEDINIPUR | SM/09048 | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). | TSM/008270 | 8384621 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 37.06 | 0 | 37.06 | Tamluk Division |  | 35.66 | 0 | 0 | 0 | 35.66 | 35.66 | 0 | 0 | 0 | 35.66 | 96.22 | 100
437 | PURBA MEDINIPUR | SM/09050 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone I (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-I) | TSM/008272 | 6328427 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 61.99 | 0 | 61.99 | Tamluk Division |  | 59.87 | 0 | 0 | 0 | 59.87 | 59.87 | 0 | 0 | 0 | 59.87 | 96.58 | 100
438 | PURBA MEDINIPUR | SM/09051 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone X (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | TSM/008273 | 6328427 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 93.24 | 0 | 93.24 | Tamluk Division |  | 84.01 | 0 | 0 | 0 | 84.01 | 84.01 | 0 | 0 | 0 | 84.01 | 90.1 | 100
439 | PURBA MEDINIPUR | SM/07976 | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | TSM/006350 | 6328427 | Retrofitting | MVS | GO2021005000PH | 21/01/2021 | 1280.9 | 0 | 1280.9 | Tamluk Division |  | 1203.9 | 0 | 0 | 0 | 1203.9 | 1202.42 | 0 | 0 | 0 | 1202.42 | 93.87 | 100
440 | PURBA MEDINIPUR | SM/09047 | Retrofitting to accommodate FHTC under JJM in Uttar Charikhia PWSS under Contai I Block (Phase-II). | TSM/008269 | 7734870 | Retrofitting | MVS | GO2122004662PH | 29/10/2021 | 17.78 | 0 | 17.78 | Tamluk Division |  | 17.26 | 0 | 0 | 0 | 17.26 | 17.26 | 0 | 0 | 0 | 17.26 | 97.06 | 99
441 | PURBA MEDINIPUR | SM/10431 | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | TSM/010148 | 7941364 | Retrofitting | MVS | GO2223000191PH | 12/04/2022 | 106.97 | 0 | 106.97 | Tamluk Division | Midnapore Mechanical Division | 103.86 | 0 | 0 | 0 | 103.86 | 103.86 | 0 | 0 | 0 | 103.86 | 97.09 | 92
442 | PURBA MEDINIPUR | SM/06882 | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme | TSM/005771 | 8047993 | Retrofitting | MVS | GO2021001781PH | 07/10/2020 | 99.43 | 0 | 99.43 | Tamluk Division |  | 97 | 0 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 97 | 97.56 | 100
443 | PURBA MEDINIPUR | SM/06881 | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | TSM/005770 | 8047990 | Retrofitting | MVS | GO2021001779PH | 07/10/2020 | 99.51 | 0 | 99.51 | Tamluk Division |  | 96.5 | 0 | 0 | 0 | 96.5 | 95.79 | 0 | 0 | 0 | 95.79 | 96.27 | 100
444 | PURBA MEDINIPUR | SM/06878 | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | TSM/005767 | 8046275 | Retrofitting | MVS | GO2021001775PH | 07/10/2020 | 77.32 | 0 | 77.32 | Tamluk Division |  | 73.99 | 0 | 0 | 0 | 73.99 | 73.96 | 0 | 0 | 0 | 73.96 | 95.65 | 100
445 | PURBA MEDINIPUR | SM/06879 | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | TSM/005768 | 8046281 | Retrofitting | MVS | GO2021001776PH | 07/10/2020 | 38.01 | 0 | 38.01 | Tamluk Division |  | 37.66 | 0 | 0 | 0 | 37.66 | 37.66 | 0 | 0 | 0 | 37.66 | 99.06 | 100
446 | PURBA MEDINIPUR | SM/06877 | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme | TSM/005766 | 8046262 | Retrofitting | MVS | GO2021001774PH | 07/10/2020 | 99.46 | 0 | 99.46 | Tamluk Division |  | 96.5 | 0 | 0 | 0 | 96.5 | 87.65 | 0 | 0 | 0 | 87.65 | 88.13 | 100
447 | PURBA MEDINIPUR | SM/06883 | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | TSM/005772 | 8047995 | Retrofitting | MVS | GO2021001782PH | 07/10/2020 | 99.43 | 0 | 99.43 | Tamluk Division |  | 96.5 | 0 | 0 | 0 | 96.5 | 95.63 | 0 | 0 | 0 | 95.63 | 96.18 | 100
448 | PURBA MEDINIPUR | SM/06884 | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | TSM/005773 | 8047999 | Retrofitting | MVS | GO2021001784PH | 07/10/2020 | 37.82 | 0 | 37.82 | Tamluk Division |  | 37 | 0 | 0 | 0 | 37 | 35.43 | 0 | 0 | 0 | 35.43 | 93.68 | 100
449 | PURBA MEDINIPUR | SM/06880 | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme | TSM/005769 | 8047986 | Retrofitting | MVS | GO2021001777PH | 07/10/2020 | 81.66 | 0 | 81.66 | Tamluk Division |  | 79 | 0 | 0 | 0 | 79 | 76.77 | 0 | 0 | 0 | 76.77 | 94.01 | 100
450 | PURBA MEDINIPUR | SM/08227 | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | TSM/007095 | 8198170 | Retrofitting | MVS | GO2021006726PH | 09/02/2021 | 27.42 | 0 | 27.42 | Tamluk Division |  | 25.48 | 0 | 0 | 0 | 25.48 | 25.15 | 0 | 0 | 0 | 25.15 | 91.7 | 100
451 | PURBA MEDINIPUR | SM/07484 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. | TSM/006644 | 7717937 | Retrofitting | MVS | GO2021003722PH | 29/12/2020 | 99.86 | 0 | 99.86 | Tamluk Division |  | 96.68 | 0 | 0 | 0 | 96.68 | 96.68 | 0 | 0 | 0 | 96.68 | 96.82 | 100
452 | PURBA MEDINIPUR | SM/07485 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | TSM/006642 | 7717937 | Retrofitting | MVS | GO2021003723PH | 29/12/2020 | 99.81 | 0 | 99.81 | Tamluk Division |  | 99.72 | 0 | 0 | 0 | 99.72 | 98.39 | 0 | 0 | 0 | 98.39 | 98.58 | 100
453 | PURBA MEDINIPUR | SM/08222 | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) | TSM/007092 | 8198049 | Retrofitting | MVS | GO2021006755PH | 09/02/2021 | 92.76 | 0 | 92.76 | Tamluk Division |  | 65.29 | 0 | 0 | 0 | 65.29 | 65.29 | 0 | 0 | 0 | 65.29 | 70.38 | 100
454 | PURBA MEDINIPUR | SM/07652 | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block | TSM/006635 | 8163095 | Retrofitting | MVS | GO2021004241PH | 07/01/2021 | 129.4 | 0 | 129.4 | Tamluk Division |  | 126.08 | 0 | 0 | 0 | 126.08 | 125.97 | 0 | 0 | 0 | 125.97 | 97.35 | 100
455 | PURBA MEDINIPUR | SM/07098 | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | TSM/006245 | 8129356 | Retrofitting | MVS | GO2021002806PH | 26/11/2020 | 99.86 | 0 | 99.86 | Tamluk Division |  | 80 | 0 | 0 | 0 | 80 | 63.71 | 0 | 0 | 0 | 63.71 | 63.81 | 100
456 | PURBA MEDINIPUR | SM/07102 | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | TSM/006250 | 8129368 | Retrofitting | MVS | GO2021002813PH | 26/11/2020 | 99.76 | 0 | 99.76 | Tamluk Division |  | 96.83 | 0 | 0 | 0 | 96.83 | 96.83 | 0 | 0 | 0 | 96.83 | 97.07 | 100
457 | PURBA MEDINIPUR | SM/07094 | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | TSM/006241 | 8128914 | Retrofitting | MVS | GO2021002794PH | 26/11/2020 | 99.43 | 0 | 99.43 | Tamluk Division |  | 96.38 | 0 | 0 | 0 | 96.38 | 96.38 | 0 | 0 | 0 | 96.38 | 96.93 | 100
458 | PURBA MEDINIPUR | SM/08226 | Retrofitting to accomodate FHTC under JJM in Bagmari W/S Scheme Potashpur-II Block (PHASE-II) | TSM/007096 | 8198160 | Retrofitting | MVS | GO2021006750PH | 09/02/2021 | 91.23 | 0 | 91.23 | Tamluk Division |  | 57.72 | 0 | 0 | 0 | 57.72 | 57.72 | 0 | 0 | 0 | 57.72 | 63.26 | 100
459 | PURBA MEDINIPUR | SM/07655 | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. | TSM/006636 | 8163105 | Retrofitting | MVS | GO2021004242PH | 07/01/2021 | 114.11 | 0 | 114.11 | Tamluk Division |  | 62.66 | 0 | 0 | 0 | 62.66 | 62.21 | 0 | 0 | 0 | 62.21 | 54.52 | 100
460 | PURBA MEDINIPUR | SM/08229 | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) | TSM/007091 | 8198066 | Retrofitting | MVS | GO2021006754PH | 09/02/2021 | 31.23 | 0 | 31.23 | Tamluk Division |  | 30.18 | 0 | 0 | 0 | 30.18 | 30.18 | 0 | 0 | 0 | 30.18 | 96.63 | 100
461 | PURBA MEDINIPUR | SM/07100 | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme | TSM/006247 | 8129363 | Retrofitting | MVS | GO2021002809PH | 26/11/2020 | 90.02 | 0 | 90.02 | Tamluk Division |  | 89.5 | 0 | 0 | 0 | 89.5 | 88.18 | 0 | 0 | 0 | 88.18 | 97.96 | 100
462 | PURBA MEDINIPUR | SM/07099 | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme | TSM/006246 | 8129359 | Retrofitting | MVS | GO2021002807PH | 26/11/2020 | 99.16 | 0 | 99.16 | Tamluk Division |  | 99 | 0 | 0 | 0 | 99 | 98.91 | 0 | 0 | 0 | 98.91 | 99.75 | 100
463 | PURBA MEDINIPUR | SM/07105 | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | TSM/006252 | 8130079 | Retrofitting | MVS | GO2021002821PH | 26/11/2020 | 99.66 | 0 | 99.66 | Tamluk Division |  | 96.67 | 0 | 0 | 0 | 96.67 | 96.67 | 0 | 0 | 0 | 96.67 | 97 | 100
464 | PURBA MEDINIPUR | SM/07101 | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme | TSM/006248 | 8129366 | Retrofitting | MVS | GO2021002811PH | 26/11/2020 | 58.04 | 0 | 58.04 | Tamluk Division |  | 53 | 0 | 0 | 0 | 53 | 52.6 | 0 | 0 | 0 | 52.6 | 90.63 | 100
465 | PURBA MEDINIPUR | SM/07097 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme | TSM/006244 | 8129350 | Retrofitting | MVS | GO2021002804PH | 26/11/2020 | 99.87 | 0 | 99.87 | Tamluk Division |  | 99.1 | 0 | 0 | 0 | 99.1 | 99.1 | 0 | 0 | 0 | 99.1 | 99.23 | 100
466 | PURBA MEDINIPUR | SM/08231 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) | TSM/007099 | 8198030 | Retrofitting | MVS | GO2021006757PH | 09/02/2021 | 176.93 | 0 | 176.93 | Tamluk Division |  | 175.93 | 0 | 0 | 0 | 175.93 | 175.93 | 0 | 0 | 0 | 175.93 | 99.44 | 100
467 | PURBA MEDINIPUR | SM/06890 | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | TSM/005760 | 8046114 | Retrofitting | MVS | GO2021001764PH | 07/10/2020 | 90.86 | 0 | 90.86 | Tamluk Division |  | 90 | 0 | 0 | 0 | 90 | 88.17 | 0 | 0 | 0 | 88.17 | 97.04 | 100
468 | PURBA MEDINIPUR | SM/08230 | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) | TSM/007094 | 8197918 | Retrofitting | MVS | GO2021006759PH | 09/02/2021 | 11.32 | 0 | 11.32 | Tamluk Division |  | 10.63 | 0 | 0 | 0 | 10.63 | 10.63 | 0 | 0 | 0 | 10.63 | 93.87 | 100
469 | PURBA MEDINIPUR | SM/07480 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | TSM/006648 | 8156311 | Retrofitting | MVS | GO2021003718PH | 29/12/2020 | 87.9 | 0 | 87.9 | Tamluk Division |  | 87.01 | 0 | 0 | 0 | 87.01 | 86.89 | 0 | 0 | 0 | 86.89 | 98.85 | 100
470 | PURBA MEDINIPUR | SM/07482 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | TSM/006646 | 8156553 | Retrofitting | MVS | GO2021003720PH | 29/12/2020 | 53.02 | 0 | 53.02 | Tamluk Division |  | 51.25 | 0 | 0 | 0 | 51.25 | 51.25 | 0 | 0 | 0 | 51.25 | 96.66 | 100
471 | PURBA MEDINIPUR | SM/07119 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | TSM/006258 | 8129324 | Retrofitting | MVS | GO2021002830PH | 26/11/2020 | 78.45 | 0 | 78.45 | Tamluk Division |  | 77.77 | 0 | 0 | 0 | 77.77 | 77.76 | 0 | 0 | 0 | 77.76 | 99.12 | 100
472 | PURBA MEDINIPUR | SM/07120 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme | TSM/006260 | 8129327 | Retrofitting | SVS | GO2021002831PH | 26/11/2020 | 79 | 0 | 79 | Tamluk Division |  | 76.78 | 0 | 0 | 0 | 76.78 | 76.68 | 0 | 0 | 0 | 76.68 | 97.06 | 100
473 | PURBA MEDINIPUR | SM/06891 | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | TSM/005761 | 8046115 | Retrofitting | MVS | GO2021001765PH | 07/10/2020 | 83.27 | 0 | 83.27 | Tamluk Division |  | 83 | 0 | 0 | 0 | 83 | 82.64 | 0 | 0 | 0 | 82.64 | 99.25 | 100
474 | PURBA MEDINIPUR | SM/07483 | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | TSM/006639 | 7392818 | Retrofitting | MVS | GO2021003721PH | 29/12/2020 | 76.83 | 0 | 76.83 | Tamluk Division |  | 73.99 | 0 | 0 | 0 | 73.99 | 73.99 | 0 | 0 | 0 | 73.99 | 96.31 | 100
475 | PURBA MEDINIPUR | SM/06887 | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | TSM/005764 | 8046118 | Retrofitting | MVS | GO2021001770PH | 07/10/2020 | 99.71 | 0 | 99.71 | Tamluk Division |  | 99 | 0 | 0 | 0 | 99 | 96.73 | 0 | 0 | 0 | 96.73 | 97.01 | 100
476 | PURBA MEDINIPUR | SM/08223 | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I | TSM/007098 | 8197788 | Retrofitting | MVS | GO2021006761PH | 09/02/2021 | 203.44 | 0 | 203.44 | Tamluk Division |  | 197.96 | 0 | 0 | 0 | 197.96 | 197.96 | 0 | 0 | 0 | 197.96 | 97.3 | 100
477 | PURBA MEDINIPUR | SM/07106 | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | TSM/006253 | 8130083 | Retrofitting | MVS | GO2021002823PH | 26/11/2020 | 99.2 | 0 | 99.2 | Tamluk Division |  | 95.92 | 0 | 0 | 0 | 95.92 | 95.87 | 0 | 0 | 0 | 95.87 | 96.64 | 100
478 | PURBA MEDINIPUR | SM/06892 | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme | TSM/005762 | 6853930 | Retrofitting | MVS | GO2021001766PH | 07/10/2020 | 90.8 | 0 | 90.8 | Tamluk Division |  | 90 | 0 | 0 | 0 | 90 | 86.96 | 0 | 0 | 0 | 86.96 | 95.77 | 100
479 | PURBA MEDINIPUR | SM/08224 | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) | TSM/007097 | 8198140 | Retrofitting | MVS | GO2021006751PH | 09/02/2021 | 98.97 | 0 | 98.97 | Tamluk Division |  | 87.23 | 0 | 0 | 0 | 87.23 | 86.69 | 0 | 0 | 0 | 86.69 | 87.6 | 100
480 | PURBA MEDINIPUR | SM/07654 | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block | TSM/006633 | 7326756 | Retrofitting | MVS | GO2021004213PH | 07/01/2021 | 117.41 | 0 | 117.41 | Tamluk Division |  | 86.9 | 0 | 0 | 0 | 86.9 | 86.8 | 0 | 0 | 0 | 86.8 | 73.93 | 100
481 | PURBA MEDINIPUR | SM/07109 | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | TSM/006256 | 8130089 | Retrofitting | MVS | GO2021002829PH | 26/11/2020 | 99.52 | 0 | 99.52 | Tamluk Division |  | 99.52 | 0 | 0 | 0 | 99.52 | 99.19 | 0 | 0 | 0 | 99.19 | 99.67 | 100
482 | PURBA MEDINIPUR | SM/08233 | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block | TSM/007102 | 8197725 | Retrofitting | MVS | GO2021006764PH | 09/02/2021 | 216.57 | 0 | 216.57 | Tamluk Division |  | 172.89 | 0 | 0 | 0 | 172.89 | 172.89 | 0 | 0 | 0 | 172.89 | 79.83 | 100
483 | PURBA MEDINIPUR | SM/07659 | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | TSM/006630 | 7402035 | Retrofitting | MVS | GO2021004236PH | 07/01/2021 | 228.34 | 0 | 228.34 | Tamluk Division |  | 222.75 | 0 | 0 | 0 | 222.75 | 222.75 | 0 | 0 | 0 | 222.75 | 97.55 | 95
484 | PURBA MEDINIPUR | SM/07481 | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. | TSM/006640 | 6904591 | Retrofitting | SVS | GO2021003719PH | 29/12/2020 | 26.99 | 0 | 26.99 | Tamluk Division |  | 7.75 | 0 | 0 | 0 | 7.75 | 7.75 | 0 | 0 | 0 | 7.75 | 28.71 | 100
485 | PURBA MEDINIPUR | SM/06888 | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | TSM/005765 | 8046117 | Retrofitting | MVS | GO2021001771PH | 07/10/2020 | 93.57 | 0 | 93.57 | Tamluk Division |  | 93 | 0 | 0 | 0 | 93 | 90.78 | 0 | 0 | 0 | 90.78 | 97.03 | 100
486 | PURBA MEDINIPUR | SM/07110 | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme | TSM/006257 | 8130099 | Retrofitting | MVS | GO2021002833PH | 26/11/2020 | 72.71 | 0 | 72.71 | Tamluk Division |  | 55 | 0 | 0 | 0 | 55 | 47.29 | 0 | 0 | 0 | 47.29 | 65.04 | 100
487 | PURBA MEDINIPUR | SM/07656 | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur | TSM/006617 | 7402045 | Retrofitting | MVS | GO2021004239PH | 07/01/2021 | 164.81 | 0 | 164.81 | Tamluk Division |  | 152.25 | 0 | 0 | 0 | 152.25 | 152.11 | 0 | 0 | 0 | 152.11 | 92.29 | 100
488 | PURBA MEDINIPUR | SM/07657 | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | TSM/006618 | 7402062 | Retrofitting | MVS | GO2021004238PH | 07/01/2021 | 177.82 | 0 | 177.82 | Tamluk Division |  | 172.13 | 0 | 0 | 0 | 172.13 | 169.2 | 0 | 0 | 0 | 169.2 | 95.16 | 100
489 | PURBA MEDINIPUR | SM/07658 | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | TSM/006634 | 7392404 | Retrofitting | MVS | GO2021004240PH | 07/01/2021 | 178.36 | 0 | 178.36 | Tamluk Division |  | 165.43 | 0 | 0 | 0 | 165.43 | 165.25 | 0 | 0 | 0 | 165.25 | 92.65 | 100
490 | PURBA MEDINIPUR | SM/07107 | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme | TSM/006254 | 8130086 | Retrofitting | MVS | GO2021002824PH | 26/11/2020 | 62.75 | 0 | 62.75 | Tamluk Division |  | 61 | 0 | 0 | 0 | 61 | 60.84 | 0 | 0 | 0 | 60.84 | 96.96 | 100
491 | PURBA MEDINIPUR | SM/07660 | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | TSM/006619 | 7326775 | Retrofitting | MVS | GO2021004237PH | 07/01/2021 | 169.11 | 0 | 169.11 | Tamluk Division |  | 165.63 | 0 | 0 | 0 | 165.63 | 164.82 | 0 | 0 | 0 | 164.82 | 97.46 | 100
492 | PURBA MEDINIPUR | SM/07096 | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | TSM/006243 | 8128929 | Retrofitting | MVS | GO2021002796PH | 26/11/2020 | 34.92 | 0 | 34.92 | Tamluk Division |  | 34 | 0 | 0 | 0 | 34 | 33.44 | 0 | 0 | 0 | 33.44 | 95.75 | 100
493 | PURBA MEDINIPUR | SM/08232 | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme | TSM/007101 | 7734863 | Retrofitting | MVS | GO2021006762PH | 09/02/2021 | 102.22 | 0 | 102.22 | Tamluk Division |  | 97.26 | 0 | 0 | 0 | 97.26 | 97.26 | 0 | 0 | 0 | 97.26 | 95.15 | 98
494 | PURBA MEDINIPUR | SM/07095 | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | TSM/006242 | 8128924 | Retrofitting | MVS | GO2021002795PH | 26/11/2020 | 88.28 | 0 | 88.28 | Tamluk Division |  | 86 | 0 | 0 | 0 | 86 | 56.88 | 0 | 0 | 0 | 56.88 | 64.43 | 100
495 | PURBA MEDINIPUR | SM/06893 | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | TSM/005763 | 6854030 | Retrofitting | MVS | GO2021001768PH | 07/10/2020 | 75.12 | 0 | 75.12 | Tamluk Division |  | 75 | 0 | 0 | 0 | 75 | 72.23 | 0 | 0 | 0 | 72.23 | 96.15 | 100
496 | PURBA MEDINIPUR | SM/08228 | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) | TSM/007100 | 8197942 | Retrofitting | MVS | GO2021006758PH | 09/02/2021 | 37.55 | 0 | 37.55 | Tamluk Division |  | 34.68 | 0 | 0 | 0 | 34.68 | 34.68 | 0 | 0 | 0 | 34.68 | 92.35 | 100
497 | PURBA MEDINIPUR | SM/07104 | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme | TSM/006251 | 8130076 | Retrofitting | MVS | GO2021002818PH | 26/11/2020 | 97.26 | 0 | 97.26 | Tamluk Division |  | 84.71 | 0 | 0 | 0 | 84.71 | 84.71 | 0 | 0 | 0 | 84.71 | 87.1 | 100
498 | PURBA MEDINIPUR | SM/07108 | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme | TSM/006255 | 8130088 | Retrofitting | MVS | GO2021002825PH | 26/11/2020 | 97.82 | 0 | 97.82 | Tamluk Division |  | 96.59 | 0 | 0 | 0 | 96.59 | 93.09 | 0 | 0 | 0 | 93.09 | 95.17 | 100
499 | PURBA MEDINIPUR | SM/06889 | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | TSM/005759 | 8046116 | Retrofitting | MVS | GO2021001757PH | 07/10/2020 | 57.01 | 0 | 57.01 | Tamluk Division |  | 57 | 0 | 0 | 0 | 57 | 57 | 0 | 0 | 0 | 57 | 99.99 | 100
500 | PURBA MEDINIPUR | SM/07479 | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block | TSM/006631 | 8156273 | Retrofitting | MVS | GO2021003717PH | 29/12/2020 | 79.84 | 0 | 79.84 | Tamluk Division |  | 76.95 | 0 | 0 | 0 | 76.95 | 76.67 | 0 | 0 | 0 | 76.67 | 96.03 | 100
501 | PURBA MEDINIPUR | SM/07093 | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme | TSM/006240 | 8128905 | Retrofitting | MVS | GO2021002792PH | 26/11/2020 | 73.12 | 0 | 73.12 | Tamluk Division |  | 71 | 0 | 0 | 0 | 71 | 70.61 | 0 | 0 | 0 | 70.61 | 96.57 | 100
502 | PURBA MEDINIPUR | SM/07653 | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | TSM/006638 | 7326702 | Retrofitting | SVS | GO2021004243PH | 07/01/2021 | 116.61 | 0 | 116.61 | Tamluk Division |  | 114.56 | 0 | 0 | 0 | 114.56 | 114.36 | 0 | 0 | 0 | 114.36 | 98.07 | 95
503 | PURBA MEDINIPUR | SM/07114 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II | TSM/006344 | 6328427 | Retrofitting | MVS | GO2021002787PH | 26/11/2020 | 99.94 | 0 | 99.94 | Tamluk Division |  | 96 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 96 | 96.06 | 100
504 | PURBA MEDINIPUR | SM/07112 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX | TSM/006342 | 6328427 | Retrofitting | SVS | GO2021002785PH | 26/11/2020 | 56.55 | 0 | 56.55 | Tamluk Division |  | 54.91 | 0 | 0 | 0 | 54.91 | 54.91 | 0 | 0 | 0 | 54.91 | 97.1 | 100
505 | PURBA MEDINIPUR | SM/07113 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IXA | TSM/006343 | 6328427 | Retrofitting | MVS | GO2021002786PH | 26/11/2020 | 99.88 | 0 | 99.88 | Tamluk Division |  | 96.71 | 0 | 0 | 0 | 96.71 | 96.7 | 0 | 0 | 0 | 96.7 | 96.82 | 100
506 | PURBA MEDINIPUR | SM/07115 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI | TSM/006345 | 6328427 | Retrofitting | MVS | GO2021002788PH | 26/11/2020 | 99.73 | 0 | 99.73 | Tamluk Division |  | 97.14 | 0 | 0 | 0 | 97.14 | 97.13 | 0 | 0 | 0 | 97.13 | 97.39 | 100
507 | PURBA MEDINIPUR | SM/07111 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VIA | TSM/006341 | 6328427 | Retrofitting | SVS | GO2021002783PH | 26/11/2020 | 54.94 | 0 | 54.94 | Tamluk Division |  | 53 | 0 | 0 | 0 | 53 | 51.1 | 0 | 0 | 0 | 51.1 | 93.01 | 100
508 | PURBA MEDINIPUR | SM/07117 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X | TSM/006347 | 6328427 | Retrofitting | MVS | GO2021002789PH | 26/11/2020 | 99.53 | 0 | 99.53 | Tamluk Division |  | 97 | 0 | 0 | 0 | 97 | 96.92 | 0 | 0 | 0 | 96.92 | 97.38 | 100
509 | PURBA MEDINIPUR | SM/07116 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII | TSM/006348 | 6328427 | Retrofitting | MVS | GO2021002790PH | 26/11/2020 | 99.8 | 0 | 99.8 | Tamluk Division |  | 96.73 | 0 | 0 | 0 | 96.73 | 96.73 | 0 | 0 | 0 | 96.73 | 96.92 | 100
510 | PURBA MEDINIPUR | SM/07118 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XIII | TSM/006349 | 6328427 | Retrofitting | MVS | GO2021002791PH | 26/11/2020 | 99.86 | 0 | 99.86 | Tamluk Division |  | 98.11 | 0 | 0 | 0 | 98.11 | 97.89 | 0 | 0 | 0 | 97.89 | 98.03 | 100
511 | PURBA MEDINIPUR | SM/08790 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII | TSM/006346 | 6328427 | Retrofitting | MVS | GO2122003237PH | 13/09/2021 | 353.17 | 0 | 353.17 | Tamluk Division |  | 342.75 | 0 | 0 | 0 | 342.75 | 342.75 | 0 | 0 | 0 | 342.75 | 97.05 | 100
512 | PURBA MEDINIPUR | SM/07661 | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | TSM/006704 | 6328427 | Retrofitting | MVS | GO2021004244PH | 07/01/2021 | 201.91 | 0 | 201.91 | Tamluk Division |  | 196.51 | 0 | 0 | 0 | 196.51 | 196.51 | 0 | 0 | 0 | 196.51 | 97.33 | 100
513 | PURBA MEDINIPUR | SM/07477 | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | TSM/006637 | 8156207 | Retrofitting | MVS | GO2021003715PH | 29/12/2020 | 45.95 | 0 | 45.95 | Tamluk Division |  | 42.75 | 0 | 0 | 0 | 42.75 | 42.75 | 0 | 0 | 0 | 42.75 | 93.05 | 100
514 | PURBA MEDINIPUR | SM/07478 | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block | TSM/006632 | 7734870 | Retrofitting | MVS | GO2021003716PH | 29/12/2020 | 46.94 | 0 | 46.94 | Tamluk Division |  | 45.25 | 0 | 0 | 0 | 45.25 | 45.25 | 0 | 0 | 0 | 45.25 | 96.4 | 99
515 | PURBA MEDINIPUR | SM/08225 | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) | TSM/007093 | 8198080 | Retrofitting | MVS | GO2021006753PH | 09/02/2021 | 27.04 | 0 | 27.04 | Tamluk Division |  | 23.49 | 0 | 0 | 0 | 23.49 | 23.49 | 0 | 0 | 0 | 23.49 | 86.87 | 100
516 | PURBA MEDINIPUR | SM/06886 | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme | TSM/005775 | 8048006 | Retrofitting | MVS | GO2021001786PH | 07/10/2020 | 99.67 | 0 | 99.67 | Tamluk Division |  | 96.5 | 0 | 0 | 0 | 96.5 | 96.26 | 0 | 0 | 0 | 96.26 | 96.58 | 100
517 | PURBA MEDINIPUR | SM/06885 | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme | TSM/005774 | 8048002 | Retrofitting | MVS | GO2021001788PH | 07/10/2020 | 99.63 | 0 | 99.63 | Tamluk Division |  | 96.5 | 0 | 0 | 0 | 96.5 | 87.27 | 0 | 0 | 0 | 87.27 | 87.59 | 100
518 | PURBA MEDINIPUR | SM/12176 | RUKMINIPUR AND ADJOINING MOUJAS PWSS | TSM/013518 | 40021313 | New | MVS | GO2223007170PH | 07/09/2022 | 700.21 | 38.85 | 739.06 | Tamluk Division | Midnapore Mechanical Division | 204.95 | 22.36 | 29.56 | 0 | 256.88 | 204.95 | 22.36 | 29.56 | 0 | 256.88 | 34.76 | 10
519 | PURBA MEDINIPUR | SM/13690 | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015573 | 40026750 | New | MVS | GO2223009740PH | 14/11/2022 | 444.98 | 19.84 | 464.83 | Tamluk Division | Midnapore Mechanical Division | 101.16 | 19.26 | 3.28 | 0 | 123.71 | 101.16 | 19.26 | 3.28 | 0 | 123.71 | 26.61 | 15
520 | PURBA MEDINIPUR | SM/12296 | SAHARA AND ADJOINING MOUJAS PWSS | TSM/013976 | 40023070 | New | MVS | GO2223007359PH | 09/09/2022 | 464.48 | 36.3 | 500.78 | Tamluk Division | Midnapore Mechanical Division | 136.44 | 24.86 | 11.51 | 0 | 172.81 | 136.44 | 24.86 | 11.51 | 0 | 172.81 | 34.51 | 25
521 | PURBA MEDINIPUR | SM/12151 | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013196 | 40021800 | New | SVS | GO2223007166PH | 07/09/2022 | 649.86 | 37.54 | 687.4 | Tamluk Division | Midnapore Mechanical Division | 0 | 10.66 | 21.48 | 0 | 32.14 | 0 | 10.66 | 21.48 | 0 | 32.14 | 4.68 | 10
522 | PURBA MEDINIPUR | SM/12322 | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | TSM/014333 | 40023276 | New | MVS | GO2223007364PH | 09/09/2022 | 517.27 | 38.73 | 556 | Tamluk Division | Midnapore Mechanical Division | 138.35 | 27.11 | 23.88 | 0 | 189.35 | 138.35 | 27.11 | 23.88 | 0 | 189.35 | 34.06 | 15
523 | PURBA MEDINIPUR | SM/13688 | SAR BERYA AND ADJOINING MOUJAS PWSS | TSM/015727 | 40026683 | New | MVS | GO2223009737PH | 14/11/2022 | 442.98 | 36.7 | 479.68 | Tamluk Division | Midnapore Mechanical Division | 200.86 | 21.13 | 33.89 | 0 | 255.89 | 200.86 | 21.13 | 33.89 | 0 | 255.89 | 53.35 | 95
524 | PURBA MEDINIPUR | SM/12310 | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | TSM/014235 | 40023210 | New | MVS | GO2223007369PH | 09/09/2022 | 859.03 | 39.98 | 899.01 | Tamluk Division | Midnapore Mechanical Division | 375.92 | 26.46 | 16.26 | 46.75 | 465.38 | 375.92 | 26.46 | 16.26 | 46.75 | 465.38 | 51.77 | 48
525 | PURBA MEDINIPUR | SM/14695 | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | TSM/017141 | 40026654 | New | MVS | GO2223012679PH | 31/01/2023 | 337.34 | 36.94 | 374.28 | Tamluk Division | Midnapore Mechanical Division | 58.44 | 14.72 | 14.4 | 0 | 87.56 | 58.44 | 14.72 | 14.4 | 0 | 87.56 | 23.39 | 25
526 | PURBA MEDINIPUR | SM/12163 | SATSATMAL & ADJOINING MOUJAS PWSS | TSM/013315 | 40021621 | New | MVS | GO2223007140PH | 07/09/2022 | 935.21 | 40.49 | 975.7 | Tamluk Division | Midnapore Mechanical Division | 306.53 | 31.71 | 28.03 | 0 | 366.27 | 306.53 | 31.71 | 28.03 | 0 | 366.27 | 37.54 | 15
527 | PURBA MEDINIPUR | SM/12518 | SELMABAD AND ADJOINING MOUJAS PWSS | TSM/014513 | 40026039 | New | MVS | GO2223007596PH | 13/09/2022 | 717.38 | 40.42 | 757.8 | Tamluk Division | Midnapore Mechanical Division | 144.4 | 11.6 | 11.51 | 0 | 167.52 | 144.4 | 11.6 | 11.51 | 0 | 167.52 | 22.11 | 15
528 | PURBA MEDINIPUR | SM/12503 | SHIPUR AND ADJOINING MOUJAS PWSS | TSM/014470 | 40026134 | New | MVS | GO2223007647PH | 13/09/2022 | 659.97 | 38.53 | 698.5 | Tamluk Division | Midnapore Mechanical Division | 183.49 | 23.46 | 17.54 | 0 | 224.48 | 183.49 | 23.46 | 17.54 | 0 | 224.48 | 32.14 | 10
529 | PURBA MEDINIPUR | SM/12496 | SHOULA BHERI AND ADJOINING MOUJAS PWSS | TSM/014514 | 40027264 | New | MVS | GO2223007634PH | 13/09/2022 | 883.13 | 39.82 | 922.95 | Tamluk Division | Midnapore Mechanical Division | 255.59 | 7.82 | 10.98 | 0 | 274.39 | 255.59 | 7.82 | 10.98 | 0 | 274.39 | 29.73 | 5
530 | PURBA MEDINIPUR | SM/12494 | SHWNIA AND ADJOINING MOUJAS PWSS | TSM/014643 | 40025951 | New | MVS | GO2223007638PH | 13/09/2022 | 417.76 | 35.58 | 453.35 | Tamluk Division | Midnapore Mechanical Division | 103.54 | 8.01 | 17.54 | 0 | 129.09 | 103.54 | 8.01 | 17.54 | 0 | 129.09 | 28.48 | 25
531 | PURBA MEDINIPUR | SM/08878 | Shyampur Piped Water Supply Scheme. | TSM/004398 | 8372184 | New | MVS | GO2122003549PH | 24/09/2021 | 762.24 | 37.93 | 800.17 | Tamluk Division | Midnapore Mechanical Division | 516.83 | 28.72 | 43.61 | 13 | 602.16 | 516.83 | 28.72 | 43.61 | 13 | 602.16 | 75.25 | 99
532 | PURBA MEDINIPUR | SM/13856 | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | TSM/015988 | 40026983 | New | MVS | GO2223010102PH | 25/11/2022 | 210.02 | 17.9 | 227.92 | Tamluk Division | Midnapore Mechanical Division | 56.97 | 17.38 | 2.94 | 0 | 77.29 | 56.97 | 17.38 | 2.94 | 0 | 77.29 | 33.91 | 20
533 | PURBA MEDINIPUR | SM/12492 | SIMULYA & IT'S ADJOINING MOUJAS PWSS | TSM/014706 | 40025944 | New | MVS | GO2223007662PH | 13/09/2022 | 878.21 | 39.41 | 917.62 | Tamluk Division | Midnapore Mechanical Division | 210.07 | 34.66 | 53.11 | 0 | 297.84 | 210.07 | 34.66 | 53.11 | 0 | 297.84 | 32.46 | 50
534 | PURBA MEDINIPUR | SM/11612 | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/010581 | 40017036 | Augmentation | MVS | GO2223005571PH | 26/07/2022 | 43.22 | 26.58 | 69.8 | Tamluk Division | Midnapore Mechanical Division | 24.29 | 14.01 | 0 | 0 | 38.3 | 24.29 | 14.01 | 0 | 0 | 38.3 | 54.87 | 28
535 | PURBA MEDINIPUR | SM/11613 | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. | TSM/010580 | 40017037 | Augmentation | MVS | GO2223005571PH | 26/07/2022 | 42.08 | 26.58 | 68.66 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
536 | PURBA MEDINIPUR | SM/08759 | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | TSM/007254 | 8365641 | Retrofitting | MVS | GO2122003140PH | 09/09/2021 | 471.12 | 0 | 471.12 | Tamluk Division |  | 392.24 | 0 | 0 | 0 | 392.24 | 392.24 | 0 | 0 | 0 | 392.24 | 83.26 | 90
537 | PURBA MEDINIPUR | SM/12809 | SOYA DIGHI AND IT'S ADJOINING MOUJAS | TSM/014723 | 40024495 | New | MVS | GO2223007955PH | 20/09/2022 | 516.4 | 37.78 | 554.17 | Tamluk Division | Midnapore Mechanical Division | 74.11 | 5.18 | 17.14 | 0 | 96.42 | 74.11 | 0 | 17.14 | 0 | 91.24 | 16.46 | 40
538 | PURBA MEDINIPUR | SM/12512 | SRIKANTHA AND ADJOINING MOUJAS PWSS | TSM/014392 | 40026463 | New | MVS | GO2223007660PH | 13/09/2022 | 716.74 | 40.25 | 756.99 | Tamluk Division | Midnapore Mechanical Division | 112.48 | 33.22 | 34.82 | 0 | 180.52 | 112.48 | 33.22 | 34.82 | 0 | 180.52 | 23.85 | 40
539 | PURBA MEDINIPUR | SM/19188 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | TSM/015039 | 40032798 | New | MVS | 650/PHE-28011/138/2021-SCHM CELL-Dept. of PHE | 07/03/2024 | 66852.52 | 7303.12 | 74155.64 | Tamluk Division | Midnapore Mechanical Division | 897.62 | 0 | 194.99 | 0 | 1092.6 | 897.62 | 0 | 194.99 | 0 | 1092.6 | 1.47 | 12
540 | PURBA MEDINIPUR | SM/12886 | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/014444 | 40026302 | New | MVS | GO2223008139PH | 23/09/2022 | 495.42 | 36.38 | 531.79 | Tamluk Division | Midnapore Mechanical Division | 16.68 | 11.29 | 23.96 | 0 | 51.93 | 16.68 | 11.29 | 23.96 | 0 | 51.93 | 9.77 | 10
541 | PURBA MEDINIPUR | SM/12284 | TAJPUR AND ADJOINING MOUJAS PWSS | TSM/014247 | 40022902 | New | MVS | GO2223007363PH | 09/09/2022 | 776.34 | 38.85 | 815.19 | Tamluk Division | Midnapore Mechanical Division | 297.09 | 32.37 | 27.55 | 0 | 357.01 | 297.09 | 32.37 | 27.55 | 0 | 357.01 | 43.79 | 20
542 | PURBA MEDINIPUR | SM/12283 | TALADIHA AND ADJOINING MOUJAS PWSS | TSM/014254 | 40027159 | New | SVS | GO2223007350PH | 09/09/2022 | 457.95 | 38.85 | 496.8 | Tamluk Division | Midnapore Mechanical Division | 69.61 | 17.81 | 44.26 | 0 | 131.69 | 69.61 | 17.81 | 44.26 | 0 | 131.69 | 26.51 | 40
543 | PURBA MEDINIPUR | SM/12433 | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | TSM/014777 | 40025904 | New | MVS | GO2223007623PH | 13/09/2022 | 501.34 | 39.62 | 540.95 | Tamluk Division | Midnapore Mechanical Division | 2 | 5.57 | 12.72 | 0 | 20.29 | 2 | 0 | 12.72 | 0 | 14.72 | 2.72 | 15
544 | PURBA MEDINIPUR | SM/12145 | TANIA BILA AND ADJOINING MOUJAS PWSS | TSM/013166 | 40022444 | New | MVS | GO2223007254PH | 07/09/2022 | 472.64 | 37.54 | 510.18 | Tamluk Division | Midnapore Mechanical Division | 165.13 | 24.43 | 7.61 | 0 | 197.17 | 165.13 | 24.43 | 7.61 | 0 | 197.17 | 38.65 | 6
545 | PURBA MEDINIPUR | SM/12319 | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | TSM/014237 | 40023248 | New | MVS | GO2223007373PH | 09/09/2022 | 493.53 | 38.85 | 532.38 | Tamluk Division | Midnapore Mechanical Division | 123.85 | 24.12 | 0 | 0 | 147.97 | 123.85 | 24.12 | 0 | 0 | 147.97 | 27.79 | 5
546 | PURBA MEDINIPUR | SM/12288 | TELAMI AND ADJOINING MOUJAS PWSS | TSM/014226 | 40022992 | New | MVS | GO2223007335PH | 09/09/2022 | 426.4 | 36.36 | 462.76 | Tamluk Division | Midnapore Mechanical Division | 78.06 | 27.98 | 31.87 | 0 | 137.91 | 78.06 | 27.98 | 31.87 | 0 | 137.91 | 29.8 | 40
547 | PURBA MEDINIPUR | SM/12482 | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | TSM/014642 | 40026793 | New | SVS | GO2223007642PH | 13/09/2022 | 961.31 | 39.49 | 1000.8 | Tamluk Division | Midnapore Mechanical Division | 468.05 | 30.71 | 51.92 | 25.04 | 575.72 | 468.05 | 30.71 | 51.92 | 25.04 | 575.72 | 57.53 | 70
548 | PURBA MEDINIPUR | SM/12133 | Tilkhoja & Adjoining mouzas | TSM/013132 | 40022770 | New | MVS | GO2223007251PH | 07/09/2022 | 673.63 | 40.49 | 714.12 | Tamluk Division | Midnapore Mechanical Division | 300.28 | 12.88 | 54.15 | 0 | 367.31 | 300.28 | 12.88 | 54.15 | 0 | 367.31 | 51.44 | 70
549 | PURBA MEDINIPUR | SM/12511 | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/014393 | 40026456 | New | MVS | GO2223007661PH | 13/09/2022 | 486.23 | 38.39 | 524.62 | Tamluk Division | Midnapore Mechanical Division | 110.17 | 7.89 | 14.49 | 0 | 132.54 | 110.17 | 7.89 | 14.49 | 0 | 132.54 | 25.26 | 70
550 | PURBA MEDINIPUR | SM/13698 | URDDHABMAL AND ADJOINING MOUJAS PWSS | TSM/015165 | 40026933 | New | MVS | GO2223009727PH | 14/11/2022 | 765.6 | 37.85 | 803.45 | Tamluk Division | Midnapore Mechanical Division | 259.54 | 35.01 | 24.97 | 0 | 319.51 | 259.54 | 35.01 | 24.97 | 0 | 319.51 | 39.77 | 78
551 | PURBA MEDINIPUR | SM/12166 | URURI AND ADJOINING MOUJAS PWSS | TSM/013484 | 40021612 | New | MVS | GO2223007195PH | 07/09/2022 | 777.83 | 38.85 | 816.68 | Tamluk Division | Midnapore Mechanical Division | 222.3 | 7.38 | 30.74 | 38.28 | 298.7 | 222.3 | 7.38 | 30.74 | 38.28 | 298.7 | 36.57 | 35
552 | PURBA MEDINIPUR | SM/12160 | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS | TSM/013252 | 40021636 | New | MVS | GO2223007169PH | 07/09/2022 | 713.16 | 38.28 | 751.44 | Tamluk Division | Midnapore Mechanical Division | 287.77 | 27.52 | 53.41 | 0 | 368.7 | 287.77 | 27.52 | 53.41 | 0 | 368.7 | 49.07 | 15
553 | PURBA MEDINIPUR | SM/12291 | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | TSM/014130 | 40023020 | New | MVS | GO2223007332PH | 09/09/2022 | 678.41 | 38.61 | 717.02 | Tamluk Division | Midnapore Mechanical Division | 243.96 | 20.83 | 57.19 | 0 | 321.97 | 243.96 | 20.83 | 57.19 | 0 | 321.97 | 44.9 | 60
554 | PURBA MEDINIPUR | SM/13855 | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | TSM/016014 | 40026977 | New | MVS | GO2223010099PH | 25/11/2022 | 747.73 | 39.21 | 786.94 | Tamluk Division | Midnapore Mechanical Division | 396.92 | 7.45 | 17.18 | 52.23 | 473.78 | 396.92 | 7.45 | 17.18 | 52.23 | 473.78 | 60.21 | 35
555 | PURBA MEDINIPUR | SM/14741 | UTTAR SAUTANCHAK Piped Water Supply Scheme. | TSM/016513 | 40026871 | New | SVS | GO2223012667PH | 31/01/2023 | 260.42 | 39.05 | 299.47 | Tamluk Division | Midnapore Mechanical Division | 93.52 | 16.3 | 3.93 | 0 | 113.75 | 93.52 | 16.3 | 3.93 | 0 | 113.75 | 37.98 | 40
556 | PURBA MEDINIPUR | SM/12321 | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | TSM/014330 | 40023265 | New | MVS | GO2223007372PH | 09/09/2022 | 591.22 | 38.85 | 630.08 | Tamluk Division | Midnapore Mechanical Division | 224.96 | 29.45 | 37.13 | 0 | 291.54 | 224.96 | 29.45 | 37.13 | 0 | 291.54 | 46.27 | 15
Total | [9 empty] | 368826.37 | 29739.42 | 398565.79 |  |  | 114237 | 6716.52 | 14126.12 | 2475.61 | 137555.26 | 114104.34 | 6637.09 | 14126.12 | 2460.74 | 137328.29 | 34.46