## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PASCHIM BARDHAMAN) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PASCHIM BARDHAMAN | SM/11986 | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | TSM/012742 | 40023382 | Augmentation | MVS | GO2223006933PH | 01/09/2022 | 997.15 | 0 | 997.15 | RCFA Division I |  | 413.03 | 0 | 416.59 | 0 | 829.62 | 413.03 | 0 | 416.59 | 0 | 829.62 | 83.2 | 90
2 | PASCHIM BARDHAMAN | SM/09875 | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | TSM/008345 | 40006247 | Augmentation | SVS | GO2122006505PH | 07/12/2021 | 1310.24 | 0 | 1310.24 | RCFA Division I | Central Mechanical Division | 1077.42 | 0 | 19.8 | 0 | 1097.22 | 1035.72 | 0 | 19.8 | 0 | 1055.52 | 80.56 | 90
3 | PASCHIM BARDHAMAN | SM/10208 | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) | TSM/009656 | 40006130 | Augmentation | MVS | GO2122009954PH | 24/02/2022 | 669.74 | 30.72 | 700.46 | RCFA Division I | Asansol Mechanical Division | 640.95 | 9.41 | 7.39 | 0 | 657.75 | 640.75 | 0 | 7.39 | 0 | 648.15 | 92.53 | 72
4 | PASCHIM BARDHAMAN | SM/10211 | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | TSM/009659 | 40006306 | Augmentation | MVS | GO2122009958PH | 24/02/2022 | 780.88 | 30.72 | 811.61 | RCFA Division I | Asansol Mechanical Division | 698.87 | 9.58 | 45.42 | 0 | 753.87 | 698.87 | 0 | 45.42 | 0 | 744.29 | 91.71 | 68
5 | PASCHIM BARDHAMAN | SM/10212 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) | TSM/009820 | 40006289 | Augmentation | MVS | GO2122009959PH | 24/02/2022 | 633.25 | 30.72 | 663.97 | RCFA Division I | Asansol Mechanical Division | 604.89 | 1.44 | 1.65 | 0 | 607.98 | 604.25 | 0 | 1.65 | 0 | 605.9 | 91.25 | 68
6 | PASCHIM BARDHAMAN | SM/10209 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009821 | 40006312 | Augmentation | MVS | GO2122009955PH | 24/02/2022 | 459.12 | 30.72 | 489.84 | RCFA Division I | Asansol Mechanical Division | 444.48 | 26.28 | 0.26 | 0 | 471.01 | 444.48 | 26.28 | 0.26 | 0 | 471.01 | 96.16 | 66
7 | PASCHIM BARDHAMAN | SM/10210 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009822 | 40006326 | Augmentation | MVS | GO2122009956PH | 24/02/2022 | 750.05 | 30.72 | 780.77 | RCFA Division I | Central Mechanical Division | 680.16 | 28.55 | 45.86 | 0 | 754.57 | 680.07 | 28.55 | 45.86 | 0 | 754.48 | 96.63 | 72
8 | PASCHIM BARDHAMAN | SM/15639 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017220 | 40061051 | Augmentation | MVS | GO2223014119PH | 17/02/2023 | 871.98 | 117.77 | 989.75 | RCFA Division I | Asansol Mechanical Division | 572.31 | 0 | 0 | 0 | 572.31 | 572.31 | 0 | 0 | 0 | 572.31 | 57.82 | 40
9 | PASCHIM BARDHAMAN | SM/18467 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN | TSM/017310 | 40061411 | Augmentation | MVS | 1970/PHE-28011/87/2023-ESTT CELL-Dept. of PHE | 20/07/2023 | 1312.39 | 88.63 | 1401.03 | RCFA Division I | Asansol Mechanical Division | 614.41 | 7.66 | 20.88 | 0 | 642.95 | 614.41 | 0 | 20.88 | 0 | 635.29 | 45.34 | 57
10 | PASCHIM BARDHAMAN | SM/16903 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017275 | 40065690 | Augmentation | SVS | GO2223015676PH | 13/03/2023 | 47.24 | 17.66 | 64.9 | RCFA Division I | Central Mechanical Division | 11.32 | 0 | 0 | 0 | 11.32 | 11.32 | 0 | 0 | 0 | 11.32 | 17.44 | 33
11 | PASCHIM BARDHAMAN | SM/18877 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020573 | 40067430 | Augmentation | MVS | PHE/IV/3038/W-663/23 | 05/10/2023 | 241.9 | 71.37 | 313.27 | RCFA Division I | Asansol Mechanical Division | 164.5 | 2.7 | 0 | 0 | 167.2 | 164.5 | 2.7 | 0 | 0 | 167.2 | 53.37 | 9
12 | PASCHIM BARDHAMAN | SM/18824 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017278 | 40061393 | Augmentation | MVS | 2749/PHE/IV/W-366/23 | 12/09/2023 | 786.57 | 73.43 | 860 | RCFA Division I | Asansol Mechanical Division | 366.16 | 5.69 | 125.1 | 0 | 496.95 | 365.68 | 0 | 125.1 | 0 | 490.77 | 57.07 | 33
13 | PASCHIM BARDHAMAN | SM/18469 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/018199 | 40061416 | Augmentation | MVS | 1970/PHE-28011/87/2023-ESTT CELL-Dept. of PHE | 20/07/2023 | 1834.41 | 568.89 | 2403.3 | RCFA Division I | Asansol Mechanical Division | 513.73 | 0 | 0 | 0 | 513.73 | 513.73 | 0 | 0 | 0 | 513.73 | 21.38 | 50
14 | PASCHIM BARDHAMAN | SM/16901 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017279 | 40061433 | Augmentation | MVS | GO2223015674PH | 13/03/2023 | 307.36 | 33.43 | 340.79 | RCFA Division I | Asansol Mechanical Division | 173.29 | 0 | 0 | 0 | 173.29 | 173.29 | 0 | 0 | 0 | 173.29 | 50.85 | 45
15 | PASCHIM BARDHAMAN | SM/16902 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017277 | 40061458 | Augmentation | SVS | GO2223015678PH | 13/03/2023 | 76.88 | 17.69 | 94.57 | RCFA Division I | Asansol Mechanical Division | 74.16 | 8.5 | 0 | 0 | 82.66 | 74.16 | 0 | 0 | 0 | 74.16 | 78.41 | 34
16 | PASCHIM BARDHAMAN | SM/16900 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017283 | 40061468 | Augmentation | SVS | GO2223015671PH | 13/03/2023 | 81.14 | 17.69 | 98.83 | RCFA Division I | Asansol Mechanical Division | 53.64 | 0 | 0 | 0 | 53.64 | 53.64 | 0 | 0 | 0 | 53.64 | 54.27 | 49
17 | PASCHIM BARDHAMAN | SM/15659 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017285 | 40061463 | Augmentation | MVS | GO2223014118PH | 17/02/2023 | 136.83 | 20.88 | 157.71 | RCFA Division I | Asansol Mechanical Division | 116.77 | 0 | 0 | 0 | 116.77 | 116.77 | 0 | 0 | 0 | 116.77 | 74.04 | 52
18 | PASCHIM BARDHAMAN | SM/18825 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017244 | 40061476 | Augmentation | MVS | 2749/PHE/IV/W-366/23 | 12/09/2023 | 258.25 | 47.94 | 306.19 | RCFA Division I | Asansol Mechanical Division | 75.5 | 0 | 0 | 0 | 75.5 | 66.05 | 0 | 0 | 0 | 66.05 | 21.57 | 34
19 | PASCHIM BARDHAMAN | SM/18890 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JEMUA, UNDER DURGAPUR W/S DIVISION , BLOCK : DURGAPUR FARIDPUR, DISTRICT : PASCHIM BARDDHAMAN | TSM/020574 | 40067418 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 163.05 | 56.33 | 219.38 | RCFA Division I | Central Mechanical Division | 152.12 | 0 | 0 | 0 | 152.12 | 152.12 | 0 | 0 | 0 | 152.12 | 69.34 | 26
20 | PASCHIM BARDHAMAN | SM/18888 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020575 | 40067431 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 105.7 | 69.6 | 175.3 | RCFA Division I | Asansol Mechanical Division | 2.23 | 0 | 0 | 0 | 2.23 | 2.23 | 0 | 0 | 0 | 2.23 | 1.27 | 9
21 | PASCHIM BARDHAMAN | SM/15663 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017286 | 40061055 | Augmentation | MVS | GO2223014121PH | 17/02/2023 | 206.55 | 20.88 | 227.43 | RCFA Division I | Asansol Mechanical Division | 112.6 | 13.13 | 0 | 0 | 125.73 | 112.6 | 0 | 0 | 0 | 112.6 | 49.51 | 48
22 | PASCHIM BARDHAMAN | SM/15657 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA | TSM/017221 | 40061054 | Augmentation | MVS | GO2223014122PH | 17/02/2023 | 811.51 | 118.46 | 929.97 | RCFA Division I | Asansol Mechanical Division | 483.58 | 8.26 | 0 | 0 | 491.84 | 483.58 | 3.77 | 0 | 0 | 487.35 | 52.41 | 44
23 | PASCHIM BARDHAMAN | SM/18826 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017280 | 40061644 | Augmentation | MVS | 2749/PHE/IV/W-366/23 | 12/09/2023 | 412.13 | 47.98 | 460.11 | RCFA Division I | Asansol Mechanical Division | 270.56 | 0 | 0 | 0 | 270.56 | 270.56 | 0 | 0 | 0 | 270.56 | 58.8 | 45
24 | PASCHIM BARDHAMAN | SM/18886 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020579 | 40067429 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 280.47 | 70.48 | 350.95 | RCFA Division I | Asansol Mechanical Division | 223.1 | 17.26 | 0 | 0 | 240.36 | 222.14 | 17.26 | 0 | 0 | 239.4 | 68.22 | 13
25 | PASCHIM BARDHAMAN | SM/10844 | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | TSM/009728 | 40017941 | Augmentation | MVS | GO2223003660PH | 30/05/2022 | 860.7 | 84.73 | 945.42 | RCFA Division I | Asansol Mechanical Division | 94.28 | 62.07 | 765.15 | 0 | 921.5 | 94.28 | 0 | 765.15 | 0 | 859.43 | 90.9 | 53
26 | PASCHIM BARDHAMAN | SM/10643 | Augmentation of Jamgram Piped Water Supply Scheme. | TSM/010051 | 40017943 | Augmentation | MVS | GO2223000491PH | 22/04/2022 | 718.24 | 55.88 | 774.12 | RCFA Division I | Asansol Mechanical Division | 531.53 | 48.05 | 12.32 | 0 | 591.9 | 530.57 | 48.04 | 12.32 | 0 | 590.93 | 76.34 | 85
27 | PASCHIM BARDHAMAN | SM/15654 | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | TSM/018723 | 40062297 | Augmentation | MVS | GO2223014123PH | 17/02/2023 | 795.87 | 192.37 | 988.24 | RCFA Division I | Asansol Mechanical Division | 390.54 | 100.2 | 0 | 0 | 490.74 | 390.54 | 100.2 | 0 | 0 | 490.74 | 49.66 | 37
28 | PASCHIM BARDHAMAN | SM/10640 | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | TSM/009730 | 40017966 | Augmentation | MVS | GO2223000487PH | 22/04/2022 | 731.11 | 135.39 | 866.51 | RCFA Division I | Asansol Mechanical Division | 146.45 | 0 | 9.24 | 0 | 155.69 | 146.45 | 0 | 9.24 | 0 | 155.69 | 17.97 | 51
29 | PASCHIM BARDHAMAN | SM/10845 | Augmentation of Madantor Water Supply Scheme | TSM/010054 | 40017959 | Augmentation | MVS | GO2223003659PH | 30/05/2022 | 538.42 | 49.02 | 587.44 | RCFA Division I | Asansol Mechanical Division | 300.51 | 11.82 | 25.22 | 0 | 337.55 | 300.51 | 11.82 | 25.22 | 0 | 337.55 | 57.46 | 83
30 | PASCHIM BARDHAMAN | SM/10641 | Augmentation of Ondal (Phase-I) Water Supply Scheme | TSM/010055 | 40017963 | Augmentation | MVS | GO2223000489PH | 22/04/2022 | 796.14 | 91.75 | 887.89 | RCFA Division I | Asansol Mechanical Division | 633.78 | 6.58 | 71.24 | 0 | 711.6 | 633.78 | 6.58 | 71.24 | 0 | 711.6 | 80.14 | 46
31 | PASCHIM BARDHAMAN | SM/10165 | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | TSM/009727 | 40004473 | Augmentation | MVS | GO2122009649PH | 11/02/2022 | 891.48 | 80 | 971.48 | RCFA Division I | Asansol Mechanical Division | 626 | 66.55 | 149.17 | 0 | 841.72 | 626 | 66.55 | 149.17 | 0 | 841.72 | 86.64 | 84
32 | PASCHIM BARDHAMAN | SM/12215 | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | TSM/014885 | 40023030 | Augmentation | MVS | GO2223007148PH | 07/09/2022 | 898.82 | 0 | 898.82 | RCFA Division I |  | 735.46 | 0 | 6.78 | 0 | 742.24 | 735.45 | 0 | 6.78 | 0 | 742.23 | 82.58 | 50
33 | PASCHIM BARDHAMAN | SM/12726 | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | TSM/009489 | 40029587 | Augmentation | MVS | GO2223008057PH | 21/09/2022 | 2645.1 | 187.24 | 2832.34 | RCFA Division I | Asansol Mechanical Division | 1398.82 | 103.9 | 546.84 | 0 | 2049.57 | 1398.82 | 103.9 | 546.84 | 0 | 2049.57 | 72.36 | 83
34 | PASCHIM BARDHAMAN | SM/11454 | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | TSM/009488 | 40018462 | Augmentation | MVS | GO2223004708PH | 12/07/2022 | 2763.35 | 36.28 | 2799.63 | RCFA Division I | Asansol Mechanical Division | 1914.64 | 30.89 | 132.89 | 0 | 2078.42 | 1914.64 | 30.8 | 132.89 | 0 | 2078.33 | 74.24 | 64
35 | PASCHIM BARDHAMAN | SM/18769 | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | TSM/017799 | 40062090 | Augmentation | MVS | 2545/PHE-28011/84/2023-ESTT CELL-Dept. of PHE | 24/08/2023 | 44087.41 | 2317.96 | 46405.37 | RCFA Division I | Asansol Mechanical Division | 10199.67 | 1327.03 | 9524.62 | 0 | 21051.32 | 10199.67 | 895.73 | 9524.62 | 0 | 20620.02 | 44.43 | 4
36 | PASCHIM BARDHAMAN | SM/18468 | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | TSM/018764 | 40062140 | Augmentation | MVS | 1970/PHE-28011/87/2023-ESTT CELL-Dept. of PHE | 20/07/2023 | 2495.44 | 2525.53 | 5020.98 | RCFA Division I | Asansol Mechanical Division | 1265.47 | 1625.17 | 469.56 | 0 | 3360.2 | 1265.47 | 1597.76 | 469.56 | 0 | 3332.78 | 66.38 | 6
37 | PASCHIM BARDHAMAN | SM/10203 | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | TSM/009032 | 40006260 | Augmentation | MVS | GO2122009804PH | 24/02/2022 | 907.44 | 35.67 | 943.11 | RCFA Division I | Asansol Mechanical Division | 691.41 | 20.58 | 36.34 | 0 | 748.33 | 690.04 | 0 | 36.34 | 0 | 726.37 | 77.02 | 97
38 | PASCHIM BARDHAMAN | SM/10642 | Augmentation of Roshna Piped Water Supply Scheme . | TSM/010052 | 40017851 | Augmentation | MVS | GO2223000490PH | 22/04/2022 | 753.48 | 91.19 | 844.67 | RCFA Division I | Asansol Mechanical Division | 580.62 | 27.89 | 42.93 | 0 | 651.43 | 580.62 | 21.61 | 42.93 | 0 | 645.15 | 76.38 | 87
39 | PASCHIM BARDHAMAN | SM/10605 | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | TSM/010518 | 40017154 | Augmentation | MVS | GO2223000412PH | 19/04/2022 | 574.17 | 34.28 | 608.44 | RCFA Division I | Asansol Mechanical Division | 302.75 | 13.68 | 0 | 0 | 316.43 | 302.75 | 9.6 | 0 | 0 | 312.35 | 51.34 | 80
40 | PASCHIM BARDHAMAN | SM/11575 | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | TSM/011412 | 40019369 | Augmentation | MVS | GO2223005398PH | 22/07/2022 | 490.27 | 171.01 | 661.28 | RCFA Division I | Asansol Mechanical Division | 288.16 | 117.53 | 106.94 | 0 | 512.62 | 288.16 | 117.53 | 106.94 | 0 | 512.62 | 77.52 | 31
41 | PASCHIM BARDHAMAN | SM/11576 | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | TSM/011404 | 40019375 | Augmentation | MVS | GO2223005397PH | 22/07/2022 | 808.08 | 0 | 808.08 | RCFA Division I |  | 348.93 | 0 | 329.55 | 0 | 678.49 | 348.93 | 0 | 329.55 | 0 | 678.49 | 83.96 | 30
42 | PASCHIM BARDHAMAN | SM/18887 | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020576 | 40067426 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 65.03 | 155.5 | 220.53 | RCFA Division I | Asansol Mechanical Division | 5.54 | 0 | 0 | 0 | 5.54 | 5.54 | 0 | 0 | 0 | 5.54 | 2.51 | 4
43 | PASCHIM BARDHAMAN | SM/13418 | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | TSM/011402 | 40032821 | Augmentation | MVS | GO2223009173PH | 02/11/2022 | 781.84 | 122.73 | 904.57 | RCFA Division I | Asansol Mechanical Division | 432.89 | 72.08 | 86.94 | 0 | 591.91 | 432.89 | 72.08 | 86.94 | 0 | 591.91 | 65.44 | 61
44 | PASCHIM BARDHAMAN | SM/11205 | Augmentation of Sub-Surface water based Churulia PWSS. | TSM/009729 | 40015113 | Augmentation | MVS | GO2223003880PH | 06/06/2022 | 842.93 | 153.74 | 996.67 | RCFA Division I | Asansol Mechanical Division | 451.42 | 66.08 | 355.1 | 0 | 872.6 | 439.07 | 46.79 | 355.1 | 0 | 840.96 | 84.38 | 70
45 | PASCHIM BARDHAMAN | SM/12219 | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014376 | 40023047 | Augmentation | MVS | GO2223007152PH | 07/09/2022 | 681.87 | 0 | 681.87 | RCFA Division I |  | 468.89 | 0 | 6.78 | 0 | 475.66 | 468.89 | 0 | 6.78 | 0 | 475.66 | 69.76 | 35
46 | PASCHIM BARDHAMAN | SM/12221 | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | TSM/013220 | 40065239 | Augmentation | SVS | GO2223007146PH | 07/09/2022 | 462 | 0 | 462 | RCFA Division I |  | 166.6 | 0 | 6.78 | 0 | 173.37 | 166.6 | 0 | 6.78 | 0 | 173.37 | 37.53 | 40
47 | PASCHIM BARDHAMAN | SM/12225 | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | TSM/013221 | 40062298 | Augmentation | MVS | GO2223007158PH | 07/09/2022 | 424.86 | 0 | 424.86 | RCFA Division I |  | 153.54 | 0 | 6.78 | 0 | 160.31 | 153.54 | 0 | 6.78 | 0 | 160.31 | 37.73 | 15
48 | PASCHIM BARDHAMAN | SM/12222 | Augmentation PWSS of RCFA Part-II (Zone - 9) | TSM/013219 | 40062300 | Augmentation | MVS | GO2223007162PH | 07/09/2022 | 579.22 | 0 | 579.22 | RCFA Division I |  | 354.2 | 0 | 6.78 | 0 | 360.98 | 354.16 | 0 | 6.78 | 0 | 360.94 | 62.31 | 20
49 | PASCHIM BARDHAMAN | SM/12029 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | TSM/014349 | 40022787 | Augmentation | MVS | GO2223006858PH | 01/09/2022 | 771.55 | 0 | 771.55 | RCFA Division I |  | 439.68 | 0 | 6.78 | 0 | 446.45 | 439.68 | 0 | 6.78 | 0 | 446.45 | 57.86 | 25
50 | PASCHIM BARDHAMAN | SM/12210 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | TSM/014889 | 40023044 | Augmentation | MVS | GO2223007131PH | 07/09/2022 | 610.16 | 0 | 610.16 | RCFA Division I |  | 549.64 | 0 | 6.78 | 0 | 556.42 | 549.64 | 0 | 6.78 | 0 | 556.42 | 91.19 | 20
51 | PASCHIM BARDHAMAN | SM/12030 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014350 | 40022790 | Augmentation | MVS | GO2223006859PH | 01/09/2022 | 991.93 | 0 | 991.93 | RCFA Division I |  | 564.99 | 0 | 6.78 | 0 | 571.77 | 564.99 | 0 | 6.78 | 0 | 571.77 | 57.64 | 20
52 | PASCHIM BARDHAMAN | SM/12031 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | TSM/014351 | 40022793 | Augmentation | MVS | GO2223006861PH | 01/09/2022 | 481.52 | 0 | 481.52 | RCFA Division I |  | 311.67 | 0 | 6.78 | 0 | 318.45 | 311.67 | 0 | 6.78 | 0 | 318.45 | 66.13 | 21
53 | PASCHIM BARDHAMAN | SM/12032 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | TSM/014352 | 40022795 | Augmentation | MVS | GO2223006862PH | 01/09/2022 | 731.25 | 0 | 731.25 | RCFA Division I |  | 497.17 | 0 | 6.78 | 0 | 503.94 | 497.17 | 0 | 6.78 | 0 | 503.94 | 68.91 | 30
54 | PASCHIM BARDHAMAN | SM/12033 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014353 | 40022908 | Augmentation | MVS | GO2223006863PH | 01/09/2022 | 809.92 | 0 | 809.92 | RCFA Division I |  | 483.9 | 0 | 6.78 | 0 | 490.67 | 483.9 | 0 | 6.78 | 0 | 490.67 | 60.58 | 40
55 | PASCHIM BARDHAMAN | SM/12039 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | TSM/014354 | 40022913 | Augmentation | MVS | GO2223006865PH | 01/09/2022 | 587.31 | 0 | 587.31 | RCFA Division I |  | 170.53 | 0 | 6.78 | 0 | 177.31 | 170.53 | 0 | 6.78 | 0 | 177.31 | 30.19 | 40
56 | PASCHIM BARDHAMAN | SM/12040 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | TSM/014355 | 40022917 | Augmentation | MVS | GO2223006866PH | 01/09/2022 | 568.7 | 0 | 568.7 | RCFA Division I |  | 441.35 | 0 | 6.78 | 0 | 448.13 | 441.35 | 0 | 6.78 | 0 | 448.13 | 78.8 | 70
57 | PASCHIM BARDHAMAN | SM/12041 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | TSM/014356 | 40022928 | Augmentation | MVS | GO2223006867PH | 01/09/2022 | 896.96 | 0 | 896.96 | RCFA Division I |  | 390.93 | 0 | 6.78 | 0 | 397.71 | 390.93 | 0 | 6.78 | 0 | 397.71 | 44.34 | 20
58 | PASCHIM BARDHAMAN | SM/12042 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | TSM/014357 | 40023064 | Augmentation | MVS | GO2223006868PH | 01/09/2022 | 831.03 | 0 | 831.03 | RCFA Division I |  | 649.93 | 0 | 6.78 | 0 | 656.71 | 649.93 | 0 | 6.78 | 0 | 656.71 | 79.02 | 50
59 | PASCHIM BARDHAMAN | SM/12218 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. | TSM/014890 | 40023062 | Augmentation | MVS | GO2223007235PH | 07/09/2022 | 878.95 | 0 | 878.95 | RCFA Division I |  | 641.83 | 0 | 6.78 | 0 | 648.61 | 641.83 | 0 | 6.78 | 0 | 648.61 | 73.79 | 60
60 | PASCHIM BARDHAMAN | SM/12220 | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | TSM/014878 | 40022968 | Augmentation | MVS | GO2223007143PH | 07/09/2022 | 754.7 | 0 | 754.7 | RCFA Division I |  | 597.05 | 0 | 6.78 | 0 | 603.82 | 597.05 | 0 | 6.78 | 0 | 603.82 | 80.01 | 55
61 | PASCHIM BARDHAMAN | SM/12216 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. | TSM/014880 | 40023025 | Augmentation | MVS | GO2223007141PH | 07/09/2022 | 868.69 | 0 | 868.69 | RCFA Division I |  | 536.56 | 0 | 6.78 | 0 | 543.33 | 536.56 | 0 | 6.78 | 0 | 543.33 | 62.55 | 20
62 | PASCHIM BARDHAMAN | SM/12227 | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | TSM/012782 | 40062299 | Augmentation | MVS | GO2223007153PH | 07/09/2022 | 543.54 | 0 | 543.54 | RCFA Division I |  | 317.49 | 0 | 6.78 | 0 | 324.26 | 317.49 | 0 | 6.78 | 0 | 324.26 | 59.66 | 20
63 | PASCHIM BARDHAMAN | SM/12223 | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | TSM/012791 | 40032957 | Augmentation | MVS | GO2223007157PH | 07/09/2022 | 833.27 | 0 | 833.27 | RCFA Division I |  | 658.29 | 0 | 6.78 | 0 | 665.07 | 658.29 | 0 | 6.78 | 0 | 665.07 | 79.81 | 16
64 | PASCHIM BARDHAMAN | SM/12226 | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman | TSM/012792 | 40065256 | Augmentation | SVS | GO2223007161PH | 07/09/2022 | 440.82 | 0 | 440.82 | RCFA Division I |  | 222.63 | 0 | 6.78 | 0 | 229.41 | 222.63 | 0 | 6.78 | 0 | 229.41 | 52.04 | 25
65 | PASCHIM BARDHAMAN | SM/12025 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | TSM/014345 | 40022718 | Augmentation | MVS | GO2223006869PH | 01/09/2022 | 901.05 | 0 | 901.05 | RCFA Division I |  | 498.99 | 0 | 13.55 | 0 | 512.54 | 498.99 | 0 | 13.55 | 0 | 512.54 | 56.88 | 20
66 | PASCHIM BARDHAMAN | SM/12026 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | TSM/014346 | 40022699 | Augmentation | MVS | GO2223006870PH | 01/09/2022 | 910.23 | 0 | 910.23 | RCFA Division I |  | 422.7 | 0 | 6.78 | 0 | 429.47 | 422.7 | 0 | 6.78 | 0 | 429.47 | 47.18 | 20
67 | PASCHIM BARDHAMAN | SM/12027 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | TSM/014347 | 40022779 | Augmentation | MVS | GO2223006871PH | 01/09/2022 | 818.76 | 0 | 818.76 | RCFA Division I |  | 386.19 | 0 | 6.78 | 0 | 392.97 | 386.19 | 0 | 6.78 | 0 | 392.97 | 48 | 35
68 | PASCHIM BARDHAMAN | SM/12028 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | TSM/014348 | 40022782 | Augmentation | MVS | GO2223006872PH | 01/09/2022 | 530.12 | 0 | 530.12 | RCFA Division I |  | 300.55 | 0 | 6.78 | 0 | 307.32 | 300.55 | 0 | 6.78 | 0 | 307.32 | 57.97 | 20
69 | PASCHIM BARDHAMAN | SM/12224 | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | TSM/012768 | 40065266 | Augmentation | SVS | GO2223007150PH | 07/09/2022 | 689.44 | 0 | 689.44 | RCFA Division I |  | 401.16 | 0 | 6.78 | 0 | 407.93 | 401.16 | 0 | 6.78 | 0 | 407.93 | 59.17 | 18
70 | PASCHIM BARDHAMAN | SM/10144 | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | TSM/009668 | 40005337 | Augmentation | MVS | GO2122009565PH | 09/02/2022 | 0 | 25.6 | 25.6 |  | Asansol Mechanical Division | 0 | 25.02 | 0 | 0 | 25.02 | 0 | 25.02 | 0 | 0 | 25.02 | 97.75 | 0
71 | PASCHIM BARDHAMAN | SM/16250 | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017281 | 40064342 | Augmentation | MVS | GO2223014903PH | 24/02/2023 | 590.74 | 47.98 | 638.71 | RCFA Division I | Asansol Mechanical Division | 308.01 | 0 | 0 | 0 | 308.01 | 308.01 | 0 | 0 | 0 | 308.01 | 48.22 | 51
72 | PASCHIM BARDHAMAN | SM/09916 | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | TSM/004718 | 40006079 | Augmentation | MVS | GO2122006612PH | 10/12/2021 | 10799.12 | 1075 | 11874.12 | RCFA Division I | Asansol Mechanical Division | 7091.95 | 397.18 | 3616.17 | 0 | 11105.3 | 7081.54 | 357.32 | 3616.17 | 0 | 11055.03 | 93.1 | 84
73 | PASCHIM BARDHAMAN | SM/16775 | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | TSM/020338 | 40060656 | Augmentation | MVS | GO2223015680PH | 13/03/2023 | 0 | 198.21 | 198.21 |  | Asansol Mechanical Division | 0 | 136.29 | 0 | 0 | 136.29 | 0 | 136.29 | 0 | 0 | 136.29 | 68.76 | 20
74 | PASCHIM BARDHAMAN | SM/16777 | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | TSM/020344 | 40060654 | Augmentation | MVS | GO2223015679PH | 13/03/2023 | 0 | 204.12 | 204.12 |  | Asansol Mechanical Division | 0 | 145.59 | 0 | 0 | 145.59 | 0 | 145.59 | 0 | 0 | 145.59 | 71.33 | 30
75 | PASCHIM BARDHAMAN | SM/18889 | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | TSM/020567 | 40067486 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 0 | 250.38 | 250.38 |  | Asansol Mechanical Division | 0 | 0.05 | 0 | 0 | 0.05 | 0 | 0.05 | 0 | 0 | 0.05 | 0.02 | 5
76 | PASCHIM BARDHAMAN | SM/14888 | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | TSM/015956 | 40060040 | Augmentation | MVS | GO2223012929PH | 03/02/2023 | 380.98 | 501.68 | 882.66 | RCFA Division I | Asansol Mechanical Division | 204.04 | 293.37 | 0 | 0 | 497.41 | 204.04 | 293.37 | 0 | 0 | 497.41 | 56.35 | 45
77 | PASCHIM BARDHAMAN | SM/18891 | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | TSM/020833 | 40067339 | Augmentation | MVS | PHE/IV/3036/W-664/23 | 05/10/2023 | 707.01 | 234.11 | 941.12 | RCFA Division I | Asansol Mechanical Division | 169.31 | 31.48 | 0 | 0 | 200.79 | 169.31 | 0 | 0 | 0 | 169.31 | 17.99 | 40
78 | PASCHIM BARDHAMAN | SM/13416 | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman | TSM/013416 | 40032856 | Augmentation | MVS | GO2223009174PH | 02/11/2022 | 717.08 | 192.37 | 909.45 | RCFA Division I | Asansol Mechanical Division | 274.79 | 38.26 | 128.48 | 0 | 441.53 | 274.79 | 38.26 | 128.48 | 0 | 441.53 | 48.55 | 27
Total | [9 empty] | 107772.9 | 10862.44 | 118635.33 |  |  | 48553.16 | 4905.83 | 17274.58 | 0 | 70733.57 | 48474.51 | 4203.46 | 17274.58 | 0 | 69952.54 | 58.96