## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | CHENGAMARI | BARA DALDAL | 571 | 571 | 100
2 | CHENGAMARI | CHENGMARI | 409 | 345 | 84.35
3 | CHENGAMARI | DAKSHIN CHENGMARI | 886 | 583 | 65.8
4 | CHENGAMARI | GHAKSAPARA | 721 | 719 | 99.72
5 | CHENGAMARI | HEMAGURI | 182 | 93 | 51.1
6 | KAMAKHYAGURI-I | DAKHIN NARATHALI | 1757 | 160 | 9.11
7 | KAMAKHYAGURI-I | PASCHIM CHAK CHAKA | 346 | 187 | 54.05
8 | KAMAKHYAGURI-I | PASCHIM NARATHALI | 959 | 1 | 0.1
9 | KAMAKHYAGURI-I | TELIPARA | 683 | 378 | 55.34
10 | KAMAKHYAGURI-I | UTTAR KAMAKHYAGURI (CT) | 2836 | 2636 | 92.95
11 | KAMAKHYAGURI-II |  | 2405 | 3 | 0.12
12 | KAMAKHYAGURI-II | DAKHIN KAMAKHYAGURI | 718 | 549 | 76.46
13 | KAMAKHYAGURI-II | MADHYA KAMAKHYAGURI | 927 | 643 | 69.36
14 | KHOAR DANGA-I | DHANTALI | 165 | 0 | 0
15 | KHOAR DANGA-I | LALCHANDPUR | 179 | 149 | 83.24
16 | KHOAR DANGA-I | NARAKHATA | 778 | 504 | 64.78
17 | KHOAR DANGA-I | NARATHALI | 1659 | 1340 | 80.77
18 | KHOAR DANGA-I | PASCHIM CHENGMARI | 750 | 663 | 88.4
19 | KHOAR DANGA-I | UTTAR NARATHALI | 592 | 512 | 86.49
20 | KHOAR DANGA-II | CHUOTA DALDALI | 1001 | 1 | 0.1
21 | KHOAR DANGA-II | GACHAIMARI | 406 | 347 | 85.47
22 | KHOAR DANGA-II | MADHYA NARATHALI | 1146 | 1001 | 87.35
23 | KHOAR DANGA-II | PURBBA NARATHALI | 1060 | 1058 | 99.81
24 | KUMARGRAM | AMARPUR | 708 | 257 | 36.3
25 | KUMARGRAM | DAKSHIN HALDIBARI | 1043 | 212 | 20.33
26 | KUMARGRAM | JAYDEDPUR | 762 | 322 | 42.26
27 | KUMARGRAM | KUMARGRAM | 1565 | 1521 | 97.19
28 | KUMARGRAM | MADHYA HALDIBARI | 1228 | 553 | 45.03
29 | KUMARGRAM | PAGLARHAT | 205 | 0 | 0
30 | KUMARGRAM | PUKHARIGAON | 882 | 47 | 5.33
31 | KUMARGRAM | UTTAR HALDIBARI | 880 | 483 | 54.89
32 | NEWLAND KUMARGRAM SANKOSH | KUMARGRAM TEA GARDEN | 1293 | 1010 | 78.11
33 | NEWLAND KUMARGRAM SANKOSH | NEW LANDS TEA GARDEN | 1305 | 737 | 56.48
34 | NEWLAND KUMARGRAM SANKOSH | SANKOS TEA GARDEN | 1407 | 1193 | 84.79
35 | RAIDAK | KARTIKA TEA GARDEN | 1149 | 1057 | 91.99
36 | RAIDAK | RAHIMABAD TEA GARDEN | 1188 | 1037 | 87.29
37 | RAIDAK | RAYDAK FOREST | 201 | 23 | 11.44
38 | RAIDAK | RAYDAK TEA GARDEN | 1866 | 934 | 50.05
39 | TURTURI KHANDA | CHUNIA JHORA TEA GARDEN | 647 | 647 | 100
40 | TURTURI KHANDA | JAYANTI TEA GARDEN | 1429 | 1308 | 91.53
41 | TURTURI KHANDA | PHASKHAWA TEA GARDEN | 246 | 246 | 100
42 | TURTURI KHANDA | SACHAPHO FOREST | 28 | 28 | 100
43 | TURTURI KHANDA | TURTURI KHANDA | 1226 | 1219 | 99.43
44 | TURTURI KHANDA | TUTURI TEA GARDEN | 729 | 351 | 48.15
45 | VALKA BARABISA-I | BARABISA | 1038 | 1038 | 100
46 | VALKA BARABISA-I | DAKHIN RAMPUR | 1348 | 824 | 61.13
47 | VALKA BARABISA-I | LASKARPARA | 1668 | 1668 | 100
48 | VALKA BARABISA-I | PURBBA CHAKCHAKA | 1078 | 1078 | 100
49 | VALKA BARABISA-I | RADHANAGAR | 489 | 489 | 100
50 | VALKA BARABISA-II | BARUIPARA | 637 | 0 | 0
51 | VALKA BARABISA-II | BHALKA | 985 | 932 | 94.62
52 | VALKA BARABISA-II | MAJHER DABRI | 360 | 0 | 0
53 | VALKA BARABISA-II | PAKRIGURI | 775 | 210 | 27.1
54 | VALKA BARABISA-II | PURBBA SALBARI | 1456 | 1456 | 100
Total |  |  | 50957 | 33323 | 65.39