## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | CHANDPARA | CHANDPARA | 3349 | 3349 | 100
2 | CHANDPARA | DHAKURIA (CT) | 425 | 321 | 75.53
3 | CHANDPARA | DOGACHHIA | 972 | 500 | 51.44
4 | CHANDPARA | MONDALPARA | 1682 | 9 | 0.54
5 | CHANDPARA | SIMULIAPARA | 1816 | 1638 | 90.2
6 | CHANDPARA | SONATIKRI | 1783 | 586 | 32.87
7 | DHARAMPUR-I | AMBAULA | 778 | 585 | 75.19
8 | DHARAMPUR-I | CHARUIGACHHI | 709 | 552 | 77.86
9 | DHARAMPUR-I | DHARMPUR | 1423 | 865 | 60.79
10 | DHARAMPUR-I | GOPALPUR | 362 | 293 | 80.94
11 | DHARAMPUR-I | NAIGACHHI | 443 | 315 | 71.11
12 | DHARAMPUR-I | NALKURA | 157 | 157 | 100
13 | DHARAMPUR-I | NATGRAM | 466 | 349 | 74.89
14 | DHARAMPUR-I | PATABUKA | 1436 | 1107 | 77.09
15 | DHARAMPUR-II | AMANKANDIA | 690 | 411 | 59.57
16 | DHARAMPUR-II | GOPAL BALIADANGA | 212 | 1 | 0.47
17 | DHARAMPUR-II | HANSPUR | 851 | 851 | 100
18 | DHARAMPUR-II | HARPARA | 197 | 166 | 84.26
19 | DHARAMPUR-II | JAYTARA | 441 | 441 | 100
20 | DHARAMPUR-II | KULGHUTI | 287 | 255 | 88.85
21 | DHARAMPUR-II | MARALDANGA | 512 | 431 | 84.18
22 | DHARAMPUR-II | MAYNA | 462 | 348 | 75.32
23 | DHARAMPUR-II | SHIMULIA | 937 | 495 | 52.83
24 | DHARAMPUR-II | SHRIPUR | 697 | 427 | 61.26
25 | DOOMA | BAGOAN | 301 | 73 | 24.25
26 | DOOMA | BARASEHANA | 723 | 656 | 90.73
27 | DOOMA | BYASATI | 90 | 80 | 88.89
28 | DOOMA | CHHEKATI | 1236 | 178 | 14.4
29 | DOOMA | CHHOTA SEHANA | 355 | 179 | 50.42
30 | DOOMA | DEOPULI | 903 | 56 | 6.2
31 | DOOMA | DHANKUNI | 602 | 240 | 39.87
32 | DOOMA | DIANGAMANIK | 374 | 85 | 22.73
33 | DOOMA | DIGHA | 1142 | 593 | 51.93
34 | DOOMA | DUMA | 953 | 146 | 15.32
35 | DOOMA | JHIKRA | 238 | 238 | 100
36 | DOOMA | KAIPUKHARIA | 251 | 218 | 86.85
37 | DOOMA | MALAYAPUR | 235 | 85 | 36.17
38 | DOOMA | SARUIPUR | 474 | 262 | 55.27
39 | DOOMA | TILI | 575 | 237 | 41.22
40 | FULSARA | BAGCHARA | 846 | 710 | 83.92
41 | FULSARA | BAIKARA | 990 | 522 | 52.73
42 | FULSARA | CHAUGACHHA | 778 | 608 | 78.15
43 | FULSARA | KATAKHALI | 269 | 249 | 92.57
44 | FULSARA | PHULSARA | 309 | 309 | 100
45 | FULSARA | RAJAPUR | 993 | 504 | 50.76
46 | ICHHAPUR-I | AMKOLA | 906 | 511 | 56.4
47 | ICHHAPUR-I | BAYASA | 280 | 195 | 69.64
48 | ICHHAPUR-I | GAIGHATA | 1749 | 1140 | 65.18
49 | ICHHAPUR-I | GARIBPUR | 263 | 144 | 54.75
50 | ICHHAPUR-I | ICHHAPUR | 3105 | 2146 | 69.11
51 | ICHHAPUR-I | KAMIA | 287 | 193 | 67.25
52 | ICHHAPUR-I | MATIKOMRA | 881 | 795 | 90.24
53 | ICHHAPUR-I | SHYAMPUR SHRIPUR | 410 | 410 | 100
54 | ICHHAPUR-II | BARA | 1860 | 1611 | 86.61
55 | ICHHAPUR-II | CHIKANPARA | 3284 | 3276 | 99.76
56 | ICHHAPUR-II | GANTI | 1033 | 985 | 95.35
57 | ICHHAPUR-II | GUTRI | 572 | 483 | 84.44
58 | ICHHAPUR-II | HUDASIMULPUR | 358 | 242 | 67.6
59 | ICHHAPUR-II | JAMDANI | 558 | 1 | 0.18
60 | ICHHAPUR-II | KAROLA | 1429 | 945 | 66.13
61 | ICHHAPUR-II | KAYA | 369 | 302 | 81.84
62 | ICHHAPUR-II | PANSHILA | 234 | 234 | 100
63 | JALESWAR-I | BAGHNA | 967 | 697 | 72.08
64 | JALESWAR-I | CHANDIGAR | 882 | 644 | 73.02
65 | JALESWAR-I | JALESHWAR | 1386 | 1081 | 77.99
66 | JALESWAR-I | NARIKELA | 1415 | 1228 | 86.78
67 | JALESWAR-II | BANGLANI | 284 | 253 | 89.08
68 | JALESWAR-II | GAZIPUR | 621 | 349 | 56.2
69 | JALESWAR-II | GHONJA | 426 | 305 | 71.6
70 | JALESWAR-II | NERA GAZIPUR | 297 | 38 | 12.79
71 | JALESWAR-II | RAMPUR | 2949 | 2330 | 79.01
72 | JALESWAR-II | SERGAR | 381 | 341 | 89.5
73 | JALESWAR-II | SONATIKIRI (CT) | 1126 | 453 | 40.23
74 | JALESWAR-II | TENGRA | 738 | 551 | 74.66
75 | JHOWDOGA | ANGRAIL | 1674 | 1503 | 89.78
76 | JHOWDOGA | BARNAGARIA | 1190 | 1190 | 100
77 | JHOWDOGA | GADADHARPUR | 674 | 568 | 84.27
78 | JHOWDOGA | GOAL BATHAN | 480 | 457 | 95.21
79 | JHOWDOGA | JHAUDANGA | 910 | 801 | 88.02
80 | JHOWDOGA | KAHANKIA | 570 | 546 | 95.79
81 | JHOWDOGA | NORADAHA | 250 | 250 | 100
82 | RAMNAGAR | CHAKJHAUDANGA | 92 | 53 | 57.61
83 | RAMNAGAR | GARJALA | 475 | 194 | 40.84
84 | RAMNAGAR | KALANCHI | 303 | 119 | 39.27
85 | RAMNAGAR | PIPLI | 490 | 123 | 25.1
86 | RAMNAGAR | PURANDARPUR | 415 | 22 | 5.3
87 | RAMNAGAR | RAGHUNANDANPUR | 107 | 73 | 68.22
88 | RAMNAGAR | RAMNAGAR | 1628 | 1295 | 79.55
89 | RAMNAGAR | SHASHADANGA | 940 | 266 | 28.3
90 | RAMNAGAR | SUBIDPUR | 132 | 132 | 100
91 | RAMNAGAR | TENTULBARIA | 793 | 273 | 34.43
92 | SIMULPUR | BHADURIA | 626 | 507 | 80.99
93 | SIMULPUR | MAHISHAKATI | 524 | 327 | 62.4
94 | SIMULPUR | MANIKHIRA | 337 | 225 | 66.77
95 | SIMULPUR | RAMCHANDRAPUR | 607 | 406 | 66.89
96 | SIMULPUR | SHIMULPUR | 6976 | 5756 | 82.51
97 | SIMULPUR | SINGJOL | 520 | 348 | 66.92
98 | SUTIA | BARASAT | 1087 | 782 | 71.94
99 | SUTIA | BHARADANGA | 596 | 275 | 46.14
100 | SUTIA | BISHNUPUR | 1065 | 201 | 18.87
101 | SUTIA | FARIDKATI | 189 | 18 | 9.52
102 | SUTIA | GAZNA | 956 | 39 | 4.08
103 | SUTIA | JADABPUR | 628 | 180 | 28.66
104 | SUTIA | MADHUSUDANKATI | 293 | 67 | 22.87
105 | SUTIA | PANCHPOTA | 720 | 384 | 53.33
106 | SUTIA | SHUTIA | 719 | 216 | 30.04
107 | SUTIA | TEGHARIA | 180 | 54 | 30
Total |  |  | 89920 | 60213 | 66.96