## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | JETIA | BALIBHARA (CT) | 2442 | 1003 | 41.07
2 | JETIA | BIJNA | 1900 | 1217 | 64.05
3 | JETIA | BISHWESWAR BATI | 123 | 89 | 72.36
4 | JETIA | JADUNATH BATI | 1016 | 1016 | 100
5 | JETIA | JETIA (CT) | 1564 | 1136 | 72.63
6 | JETIA | MALANCHA (P) | 750 | 750 | 100
7 | JETIA | RAMPUR | 211 | 91 | 43.13
8 | KAMPA-CHAKLA | CHENDUA (P) | 644 | 335 | 52.02
9 | KAMPA-CHAKLA | JAYANPUR (P) | 678 | 623 | 91.89
10 | KAMPA-CHAKLA | KANPA | 1163 | 1163 | 100
11 | KAMPA-CHAKLA | PALLADAHA | 1694 | 1694 | 100
12 | KAWGACHI-I | GARSHYAMNAGAR (CT) | 2223 | 1 | 0.04
13 | KAWGACHI-I | KAUGACHHI (CT) | 3614 | 1 | 0.03
14 | KAWGACHI-I | NOAPARA (P) | 1871 | 1 | 0.05
15 | KAWGACHI-II | BALIAGHATA | 268 | 1 | 0.37
16 | KAWGACHI-II | BASUDEBPUR (P) | 1022 | 1 | 0.1
17 | KAWGACHI-II | GURDAHA (P) | 14 | 1 | 7.14
18 | KAWGACHI-II | HANSIA | 1117 | 1 | 0.09
19 | KAWGACHI-II | KAYRAPUR | 240 | 1 | 0.42
20 | KAWGACHI-II | MATHURAPUR | 398 | 1 | 0.25
21 | KAWGACHI-II | PALTAPARA | 1458 | 1 | 0.07
22 | KAWGACHI-II | RAHUTA (P) | 41 | 1 | 2.44
23 | MAJHIPARA - PALASHI | DAIBAGNAPUR | 244 | 87 | 35.66
24 | MAJHIPARA - PALASHI | DARIALA | 1439 | 2 | 0.14
25 | MAJHIPARA - PALASHI | MAJHI PARA | 1183 | 670 | 56.64
26 | MAJHIPARA - PALASHI | NAGDAHA | 2707 | 2600 | 96.05
27 | MAJHIPARA - PALASHI | NAOABILA | 533 | 294 | 55.16
28 | MAJHIPARA - PALASHI | PALASHI | 2379 | 2149 | 90.33
29 | MAJHIPARA - PALASHI | SIDDHESWARBATI | 39 | 1 | 2.56
30 | MAMUDPUR | BHABAGACHHI | 747 | 650 | 87.01
31 | MAMUDPUR | DOGACHHIA | 1490 | 885 | 59.4
32 | MAMUDPUR | KULIAGOR | 674 | 515 | 76.41
33 | MAMUDPUR | MADARPULI | 628 | 628 | 100
34 | MAMUDPUR | MAMUDPUR | 5978 | 5978 | 100
35 | MAMUDPUR | RAJENDRAPUR | 1345 | 1345 | 100
36 | PANPUR KEUTIA |  | 1255 | 1 | 0.08
37 | PANPUR KEUTIA | ABHIRAMPUR (P) | 5613 | 3 | 0.05
38 | PANPUR KEUTIA | KEUTIA (P) | 1435 | 28 | 1.95
39 | PANPUR KEUTIA | MUKUNDAPUR | 980 | 2 | 0.2
40 | PANPUR KEUTIA | RAMBATI | 730 | 2 | 0.27
41 | SHIBDASPUR | ATISARA | 308 | 249 | 80.84
42 | SHIBDASPUR | BARIKPARA | 152 | 152 | 100
43 | SHIBDASPUR | BUDHURIA | 349 | 349 | 100
44 | SHIBDASPUR | KHANARHAT | 222 | 222 | 100
45 | SHIBDASPUR | MAHABATIPARA | 725 | 583 | 80.41
46 | SHIBDASPUR | RAMCHANDRAPUR | 515 | 515 | 100
47 | SHIBDASPUR | SHALIDAHA | 548 | 496 | 90.51
48 | SHIBDASPUR | SHIBDASPUR | 630 | 630 | 100
Total |  |  | 57299 | 28164 | 49.15