## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | ATURIA | BELGARIA | 621 | 621 | 100
2 | ATURIA | KATIA | 1156 | 1156 | 100
3 | ATURIA | KEFAYETKATI | 508 | 508 | 100
4 | ATURIA | PALTA | 766 | 766 | 100
5 | ATURIA | PASCHIM JAYNAGAR | 796 | 796 | 100
6 | BAGJOLA | BAGJOLA | 686 | 686 | 100
7 | BAGJOLA | BEGAMPUR | 642 | 642 | 100
8 | BAGJOLA | CHANDPUR | 350 | 350 | 100
9 | BAGJOLA | HAIDARPUR | 686 | 686 | 100
10 | BAGJOLA | KANUPUR | 367 | 367 | 100
11 | BAGJOLA | KIRTTIPUR | 1027 | 1027 | 100
12 | BAGJOLA | MANDRA | 165 | 117 | 70.91
13 | BAGJOLA | RAJAPUR | 845 | 845 | 100
14 | BAGJOLA | ROYPUR | 234 | 214 | 91.45
15 | BAGJOLA | RUEY DANGA | 235 | 235 | 100
16 | BAGJOLA | SAIDPUR | 250 | 247 | 98.8
17 | BAJITPUR | BAJITPUR | 1015 | 1015 | 100
18 | BAJITPUR | FATULLAPUR | 2567 | 2567 | 100
19 | BAJITPUR | PUNRA (P) | 2754 | 1269 | 46.08
20 | CHANDIPUR | BENA | 1378 | 1378 | 100
21 | CHANDIPUR | CHANDIPUR | 3175 | 3175 | 100
22 | CHANDIPUR | DAUKI | 177 | 177 | 100
23 | CHANDIPUR | GHORAGACHHA | 469 | 469 | 100
24 | CHANDIPUR | KEUTSA | 768 | 768 | 100
25 | CHANDIPUR | UMAPATIPUR | 638 | 638 | 100
26 | CHANDIPUR | UTTAR SHIBPUR | 208 | 208 | 100
27 | CHHATRA | DAKSHIN CHATRA | 1097 | 1097 | 100
28 | CHHATRA | GHOSHPUR | 1458 | 1458 | 100
29 | CHHATRA | KOTALBER | 117 | 117 | 100
30 | CHHATRA | PAPILA | 438 | 438 | 100
31 | CHHATRA | RASUI | 602 | 577 | 95.85
32 | CHHATRA | SALUA | 1030 | 392 | 38.06
33 | CHHATRA | UTTAR CHATRA | 736 | 736 | 100
34 | JADURHATI DAKSHIN | ATURIA | 1581 | 1326 | 83.87
35 | JADURHATI DAKSHIN | DAKSHIN SHIBPUR | 74 | 43 | 58.11
36 | JADURHATI DAKSHIN | GOKNA | 1000 | 1000 | 100
37 | JADURHATI DAKSHIN | JADURHATI | 708 | 708 | 100
38 | JADURHATI DAKSHIN | JADURHATI KHASPUR | 961 | 864 | 89.91
39 | JADURHATI DAKSHIN | MRIJAPUR UTTAR | 789 | 1 | 0.13
40 | JADURHATI DAKSHIN | RAJBARIA | 850 | 525 | 61.76
41 | JADURHATI DAKSHIN | SERPUR | 1205 | 591 | 49.05
42 | JADURHATI UTTAR | BASUDEBPUR | 268 | 268 | 100
43 | JADURHATI UTTAR | DARI GOBINDAPUR | 312 | 212 | 67.95
44 | JADURHATI UTTAR | JANGALPUR | 2226 | 663 | 29.78
45 | JADURHATI UTTAR | MAMUDPUR | 702 | 320 | 45.58
46 | JADURHATI UTTAR | NARAYANPUR | 740 | 478 | 64.59
47 | JADURHATI UTTAR | NATURIA SRIRAMPUR | 120 | 43 | 35.83
48 | JADURHATI UTTAR | NOWAPARA | 448 | 300 | 66.96
49 | JADURHATI UTTAR | PANJI | 199 | 115 | 57.79
50 | JADURHATI UTTAR | PINGALESWAR | 990 | 990 | 100
51 | JAGANNATHPUR | ARSULA | 706 | 637 | 90.23
52 | JAGANNATHPUR | BISHNUPUR | 125 | 1 | 0.8
53 | JAGANNATHPUR | CHAK KHAMARPUR | 17 | 16 | 94.12
54 | JAGANNATHPUR | DAKSHINDIARA | 350 | 342 | 97.71
55 | JAGANNATHPUR | JAGANNATHPUR | 279 | 279 | 100
56 | JAGANNATHPUR | KHAMARPARA | 1336 | 752 | 56.29
57 | JAGANNATHPUR | MAGURATI SHRIRAMPUR | 1333 | 590 | 44.26
58 | JAGANNATHPUR | MAHESPUR | 363 | 312 | 85.95
59 | JAGANNATHPUR | SHRIKATI | 219 | 125 | 57.08
60 | JAGANNATHPUR | TILDANGA | 719 | 719 | 100
61 | JAGANNATHPUR | UTTAR DIARA | 388 | 1 | 0.26
62 | JASIKATI ATGHARA | ATGHARA | 981 | 981 | 100
63 | JASIKATI ATGHARA | JASHAIKATI | 1858 | 1747 | 94.03
64 | JASIKATI ATGHARA | KALINGA | 649 | 649 | 100
65 | JASIKATI ATGHARA | SANNYA | 452 | 452 | 100
66 | JASIKATI ATGHARA | SHIMLA DURGAPUR | 3037 | 1756 | 57.82
67 | NAYABASTIA MILANI | KANKRASUTI | 1566 | 1345 | 85.89
68 | NAYABASTIA MILANI | KULIA | 1330 | 1244 | 93.53
69 | NAYABASTIA MILANI | MEDIA | 508 | 112 | 22.05
70 | NAYABASTIA MILANI | NABASTIA | 953 | 770 | 80.8
71 | RAGHUNATHPUR | GURUDAHA | 952 | 952 | 100
72 | RAGHUNATHPUR | ISHWARIGACHHA | 1156 | 1156 | 100
73 | RAGHUNATHPUR | MALEAPUR | 1120 | 1120 | 100
74 | RAGHUNATHPUR | NATURIA | 944 | 665 | 70.44
75 | RAGHUNATHPUR | PADMAPUKUR | 194 | 143 | 73.71
76 | RAGHUNATHPUR | RAGHUNATHPUR | 894 | 567 | 63.42
77 | RAMCHANDRAPUR UDAY | ATLIA | 602 | 520 | 86.38
78 | RAMCHANDRAPUR UDAY | BURUJ | 480 | 447 | 93.13
79 | RAMCHANDRAPUR UDAY | HUGLE | 719 | 719 | 100
80 | RAMCHANDRAPUR UDAY | MASIA | 1280 | 1280 | 100
81 | RAMCHANDRAPUR UDAY | NARIKELBERIA | 408 | 272 | 66.67
82 | RAMCHANDRAPUR UDAY | RAMCHANDRAPUR | 1641 | 1603 | 97.68
83 | RAMCHANDRAPUR UDAY | RAMCHANDRAPUR KHASPUR | 533 | 533 | 100
84 | RAMCHANDRAPUR UDAY | SOMPUR | 204 | 112 | 54.9
85 | SAYESTANAGAR-I | CHAK LABANGA | 17 | 1 | 5.88
86 | SAYESTANAGAR-I | JOYPUR | 99 | 49 | 49.49
87 | SAYESTANAGAR-I | KUSADANGA | 315 | 315 | 100
88 | SAYESTANAGAR-I | LABANGA | 926 | 926 | 100
89 | SAYESTANAGAR-I | MAGURALI | 526 | 496 | 94.3
90 | SAYESTANAGAR-I | MAGURALI SATPAI | 234 | 221 | 94.44
91 | SAYESTANAGAR-I | PURBA JAYNAGAR | 806 | 641 | 79.53
92 | SAYESTANAGAR-I | SAFIREBAD | 646 | 646 | 100
93 | SAYESTANAGAR-I | SAYESTANAGAR | 1650 | 1650 | 100
94 | SAYESTANAGAR-II | BAKRA CHANDIRBAOR | 32 | 1 | 3.13
95 | SAYESTANAGAR-II | GANDHARBBAPUR | 944 | 944 | 100
96 | SAYESTANAGAR-II | PIYARA | 1306 | 1306 | 100
Total |  |  | 76931 | 64304 | 83.59