## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | CHAKMAKAMPUR | ATRA | 343 | 112 | 32.65
2 | CHAKMAKAMPUR | ATRAKHI | 131 | 0 | 0
3 | CHAKMAKAMPUR | AYAMACHAK | 40 | 10 | 25
4 | CHAKMAKAMPUR | BAGHAGERE | 135 | 116 | 85.93
5 | CHAKMAKAMPUR | BAJITPUR | 39 | 34 | 87.18
6 | CHAKMAKAMPUR | BAR DOGECHE BATITAKI | 50 | 30 | 60
7 | CHAKMAKAMPUR | BAR DOGECHHE | 20 | 17 | 85
8 | CHAKMAKAMPUR | BARACHU | 276 | 234 | 84.78
9 | CHAKMAKAMPUR | BARDAMU | 92 | 41 | 44.57
10 | CHAKMAKAMPUR | BARGHASIRAM | 41 | 35 | 85.37
11 | CHAKMAKAMPUR | BARGHASIRAM (PART-I) | 116 | 98 | 84.48
12 | CHAKMAKAMPUR | BARGOBINDA (PART-II) | 181 | 118 | 65.19
13 | CHAKMAKAMPUR | BARMATHURI | 90 | 75 | 83.33
14 | CHAKMAKAMPUR | BELAGERE | 49 | 41 | 83.67
15 | CHAKMAKAMPUR | BHAIRABPUR | 135 | 0 | 0
16 | CHAKMAKAMPUR | CHAK HALU | 98 | 56 | 57.14
17 | CHAKMAKAMPUR | CHAKMAKRAMPUR | 1329 | 1042 | 78.4
18 | CHAKMAKAMPUR | CHAKSANDHAR | 61 | 0 | 0
19 | CHAKMAKAMPUR | CHAKSATBANGI | 91 | 75 | 82.42
20 | CHAKMAKAMPUR | CHENGA BENGA | 65 | 55 | 84.62
21 | CHAKMAKAMPUR | FATEMAHAMMAD | 109 | 66 | 60.55
22 | CHAKMAKAMPUR | GOPINATHPUR | 248 | 191 | 77.02
23 | CHAKMAKAMPUR | GUMARIA | 25 | 0 | 0
24 | CHAKMAKAMPUR | ISMAILCHAK | 110 | 98 | 89.09
25 | CHAKMAKAMPUR | JAMUA | 59 | 53 | 89.83
26 | CHAKMAKAMPUR | JETHIA | 240 | 173 | 72.08
27 | CHAKMAKAMPUR | KALAGERYA | 45 | 8 | 17.78
28 | CHAKMAKAMPUR | KALUA | 116 | 93 | 80.17
29 | CHAKMAKAMPUR | KARRACHAK | 74 | 0 | 0
30 | CHAKMAKAMPUR | KRISHNAGERYA | 83 | 69 | 83.13
31 | CHAKMAKAMPUR | KRISHNAPUR | 356 | 0 | 0
32 | CHAKMAKAMPUR | KUNJAGERE | 30 | 25 | 83.33
33 | CHAKMAKAMPUR | MRIJAPUR | 283 | 243 | 85.87
34 | CHAKMAKAMPUR | PANISIULI | 118 | 70 | 59.32
35 | CHAKMAKAMPUR | RATHIKULGERYA | 125 | 0 | 0
36 | CHAKMAKAMPUR | SANKRISHNAPUR | 73 | 0 | 0
37 | CHAKMAKAMPUR | SATRANGI | 281 | 246 | 87.54
38 | CHAKMAKAMPUR | SHYAMCHAKPALASI | 104 | 0 | 0
39 | CHAKMAKAMPUR | SRIMANTAPUR | 225 | 165 | 73.33
40 | CHAKMAKAMPUR | TALASHIBRAMCHAK | 69 | 45 | 65.22
41 | CHAKMAKAMPUR | TALUGOTGERYA | 45 | 0 | 0
42 | CHAKMAKAMPUR | TENTULMURI | 337 | 315 | 93.47
43 | CHAKMAKAMPUR | WARDA | 173 | 163 | 94.22
44 | CHANGUAL | AMCHHATA | 91 | 1 | 1.1
45 | CHANGUAL | AMLATARIA | 260 | 1 | 0.38
46 | CHANGUAL | AMLICHAK | 130 | 113 | 86.92
47 | CHANGUAL | ARASHINI | 584 | 144 | 24.66
48 | CHANGUAL | BELAGERE | 53 | 29 | 54.72
49 | CHANGUAL | CHANGUAL | 1029 | 181 | 17.59
50 | CHANGUAL | CHARDA | 145 | 145 | 100
51 | CHANGUAL | DAKSHINSIMLA | 324 | 0 | 0
52 | CHANGUAL | DEULI PURBA | 60 | 54 | 90
53 | CHANGUAL | DHITPUR | 163 | 0 | 0
54 | CHANGUAL | DIGRA | 323 | 119 | 36.84
55 | CHANGUAL | DOSATINA | 43 | 0 | 0
56 | CHANGUAL | ELASAI RANGA DIGHI | 325 | 0 | 0
57 | CHANGUAL | GANGADHARCHAK | 43 | 0 | 0
58 | CHANGUAL | GANGARAMPUR | 162 | 75 | 46.3
59 | CHANGUAL | GAURANGACHAK | 42 | 32 | 76.19
60 | CHANGUAL | GHARBARPUR | 63 | 1 | 1.59
61 | CHANGUAL | GOPALCHAK | 4 | 0 | 0
62 | CHANGUAL | GOPINATHPURCHAK | 73 | 0 | 0
63 | CHANGUAL | JHAJIA | 153 | 0 | 0
64 | CHANGUAL | KALA CHAK | 34 | 29 | 85.29
65 | CHANGUAL | KANDARPAPUR | 288 | 1 | 0.35
66 | CHANGUAL | KANTAGERYA | 243 | 0 | 0
67 | CHANGUAL | KASHBA | 354 | 95 | 26.84
68 | CHANGUAL | KASHIMALI | 96 | 30 | 31.25
69 | CHANGUAL | MADANMOHAN | 365 | 0 | 0
70 | CHANGUAL | MELERACHAK | 63 | 42 | 66.67
71 | CHANGUAL | NAGRA | 188 | 10 | 5.32
72 | CHANGUAL | NAYABASAN | 74 | 0 | 0
73 | CHANGUAL | RADHABALLAV PUR | 135 | 0 | 0
74 | CHANGUAL | SHALIKA | 94 | 80 | 85.11
75 | CHANGUAL | SHIRSHI | 65 | 0 | 0
76 | CHANGUAL | SHYAMNAGAR | 110 | 15 | 13.64
77 | CHANGUAL | UPARKENTYA | 166 | 0 | 0
78 | KALIARA-I | AKASYA | 52 | 8 | 15.38
79 | KALIARA-I | AKRA MARKANDAPUR | 129 | 98 | 75.97
80 | KALIARA-I | BARBASANTAPUR | 185 | 62 | 33.51
81 | KALIARA-I | BASANTAPUR | 37 | 4 | 10.81
82 | KALIARA-I | BEGUNA | 237 | 210 | 88.61
83 | KALIARA-I | BHAIRABPUR | 191 | 1 | 0.52
84 | KALIARA-I | DAKSHIN DHEKIA | 535 | 535 | 100
85 | KALIARA-I | DURGAPUR EAST | 99 | 1 | 1.01
86 | KALIARA-I | DURGAPUR WEST | 168 | 1 | 0.6
87 | KALIARA-I | KALIARA | 528 | 449 | 85.04
88 | KALIARA-I | KANIKHA | 57 | 1 | 1.75
89 | KALIARA-I | KULARA | 254 | 254 | 100
90 | KALIARA-I | MAHESHPUR | 118 | 118 | 100
91 | KALIARA-I | MENDIPUR | 376 | 196 | 52.13
92 | KALIARA-I | MOMINPUR | 63 | 56 | 88.89
93 | KALIARA-I | PELAGERYA | 618 | 618 | 100
94 | KALIARA-I | RAJSAN | 163 | 134 | 82.21
95 | KALIARA-I | SAORDA | 157 | 4 | 2.55
96 | KALIARA-I | SULTANPUR | 717 | 415 | 57.88
97 | KALIARA-II | AMODPUR | 99 | 51 | 51.52
98 | KALIARA-II | BAR BEGUNIA | 112 | 70 | 62.5
99 | KALIARA-II | BARA KARANJI | 92 | 2 | 2.17
100 | KALIARA-II | BARBETYA | 43 | 0 | 0
101 | KALIARA-II | BISHRIGERYA | 63 | 32 | 50.79
102 | KALIARA-II | BRAHMAN | 27 | 0 | 0
103 | KALIARA-II | CHARKHI | 97 | 86 | 88.66
104 | KALIARA-II | DUBRAJI | 21 | 13 | 61.9
105 | KALIARA-II | ETBARPUR | 23 | 2 | 8.7
106 | KALIARA-II | GHARAIGERYA | 38 | 0 | 0
107 | KALIARA-II | GOALPOTA | 17 | 0 | 0
108 | KALIARA-II | GOMAI | 97 | 52 | 53.61
109 | KALIARA-II | HALDI | 74 | 1 | 1.35
110 | KALIARA-II | HAMIRCHAK | 67 | 39 | 58.21
111 | KALIARA-II | HARINA | 50 | 1 | 2
112 | KALIARA-II | JAYPUR | 21 | 15 | 71.43
113 | KALIARA-II | JHARIA | 47 | 18 | 38.3
114 | KALIARA-II | KAIGERYA | 123 | 70 | 56.91
115 | KALIARA-II | KAISMALI | 49 | 49 | 100
116 | KALIARA-II | KAJICHAK | 127 | 90 | 70.87
117 | KALIARA-II | KALUCHAK | 19 | 19 | 100
118 | KALIARA-II | KAPASGERYA | 57 | 9 | 15.79
119 | KALIARA-II | KENUSI | 119 | 80 | 67.23
120 | KALIARA-II | KESHPUR | 125 | 0 | 0
121 | KALIARA-II | KISMAT BISHRIGERYA | 77 | 11 | 14.29
122 | KALIARA-II | KISMAT RAJPUR | 125 | 66 | 52.8
123 | KALIARA-II | MANIK KHOLA | 169 | 22 | 13.02
124 | KALIARA-II | MUGARCHAK | 39 | 0 | 0
125 | KALIARA-II | MUKSUDPUR | 295 | 0 | 0
126 | KALIARA-II | NARAHARIPUR | 35 | 34 | 97.14
127 | KALIARA-II | PAIKAN KARANJI | 46 | 2 | 4.35
128 | KALIARA-II | PANRUA | 39 | 0 | 0
129 | KALIARA-II | PATGERYA | 43 | 0 | 0
130 | KALIARA-II | PENYACHAK | 85 | 0 | 0
131 | KALIARA-II | PHULGERYA | 34 | 23 | 67.65
132 | KALIARA-II | RADHAKRISHNAPUR | 44 | 0 | 0
133 | KALIARA-II | RAJPURA | 208 | 0 | 0
134 | KALIARA-II | RAMBHADRAPUR | 131 | 0 | 0
135 | KALIARA-II | RASUNCHAK | 31 | 22 | 70.97
136 | KALIARA-II | SANCHANESWARPUR | 45 | 3 | 6.67
137 | KALIARA-II | SANJHARIA | 78 | 60 | 76.92
138 | KALIARA-II | SANKATI | 181 | 14 | 7.73
139 | KALIARA-II | SATBIGHA | 52 | 40 | 76.92
140 | KALIARA-II | SHANRASHIPUR | 26 | 0 | 0
141 | KALIARA-II | SHANRPUR | 12 | 11 | 91.67
142 | KALIARA-II | SIMANA | 36 | 13 | 36.11
143 | LACHHMAPUR | ATSANGRA | 18 | 3 | 16.67
144 | LACHHMAPUR | BALIHATI | 509 | 1 | 0.2
145 | LACHHMAPUR | BAR JANARDANPUR | 170 | 98 | 57.65
146 | LACHHMAPUR | BARADIHA | 489 | 0 | 0
147 | LACHHMAPUR | BARMUNIBGAR | 408 | 0 | 0
148 | LACHHMAPUR | BELI | 191 | 2 | 1.05
149 | LACHHMAPUR | CHAKGANESH | 452 | 8 | 1.77
150 | LACHHMAPUR | CHANSARPUR | 105 | 0 | 0
151 | LACHHMAPUR | DUBGOHAL | 456 | 30 | 6.58
152 | LACHHMAPUR | GADGACHHI | 157 | 1 | 0.64
153 | LACHHMAPUR | GHOLAGERE | 251 | 1 | 0.4
154 | LACHHMAPUR | GOALARA | 339 | 47 | 13.86
155 | LACHHMAPUR | GOBINDANAGAR | 269 | 219 | 81.41
156 | LACHHMAPUR | GOTGERE | 194 | 29 | 14.95
157 | LACHHMAPUR | JAKPUR | 378 | 1 | 0.26
158 | LACHHMAPUR | KAJLA | 341 | 84 | 24.63
159 | LACHHMAPUR | KANCHANTOLA | 162 | 122 | 75.31
160 | LACHHMAPUR | KANCHDIHA | 164 | 11 | 6.71
161 | LACHHMAPUR | KANTAGERE | 128 | 0 | 0
162 | LACHHMAPUR | KHATRANGA | 822 | 487 | 59.25
163 | LACHHMAPUR | KRISHNANAGAR | 125 | 33 | 26.4
164 | LACHHMAPUR | KUKRADA | 69 | 0 | 0
165 | LACHHMAPUR | KUMARDOBA | 45 | 10 | 22.22
166 | LACHHMAPUR | LACHHMAPUR | 552 | 332 | 60.14
167 | LACHHMAPUR | MAISAR | 91 | 37 | 40.66
168 | LACHHMAPUR | MALIPUR | 15 | 0 | 0
169 | LACHHMAPUR | MANIBPUR | 257 | 0 | 0
170 | LACHHMAPUR | MUNIBGAR | 241 | 221 | 91.7
171 | LACHHMAPUR | PAIKNAGARI | 146 | 3 | 2.05
172 | LACHHMAPUR | PATPACHA | 109 | 0 | 0
173 | LACHHMAPUR | RADHAKISHOR | 80 | 5 | 6.25
174 | LACHHMAPUR | RADHANAGAR | 353 | 136 | 38.53
175 | LACHHMAPUR | SAMUDRAPUR | 147 | 0 | 0
176 | LACHHMAPUR | TUTEMUNIBGAR | 209 | 108 | 51.67
177 | LACHHMAPUR | UTTARSHIMLA | 595 | 0 | 0
178 | PALSYA | AMBIBATITAKI | 132 | 12 | 9.09
179 | PALSYA | AMULPUR | 309 | 272 | 88.03
180 | PALSYA | ANDULYA | 192 | 179 | 93.23
181 | PALSYA | ASRAPHPUR | 82 | 49 | 59.76
182 | PALSYA | BANAMALICHAK | 37 | 1 | 2.7
183 | PALSYA | BARAMPUR | 121 | 101 | 83.47
184 | PALSYA | BARDHANU | 50 | 6 | 12
185 | PALSYA | BARGANI | 97 | 60 | 61.86
186 | PALSYA | BARGOKUL | 58 | 49 | 84.48
187 | PALSYA | CHAKKALINDI | 123 | 1 | 0.81
188 | PALSYA | CHAKNARAYAN | 91 | 4 | 4.4
189 | PALSYA | CHAKNARAYANBHANJA | 50 | 0 | 0
190 | PALSYA | CHHOTA KALANKAI | 136 | 1 | 0.74
191 | PALSYA | DUNDARACHAK | 131 | 2 | 1.53
192 | PALSYA | GOKULPUR | 331 | 300 | 90.63
193 | PALSYA | GOTGERYA BATITAKI | 46 | 1 | 2.17
194 | PALSYA | JAMIRA | 153 | 1 | 0.65
195 | PALSYA | JAMJHATIA | 185 | 5 | 2.7
196 | PALSYA | JHILINGA | 304 | 16 | 5.26
197 | PALSYA | JHILINGABATITAKI | 98 | 1 | 1.02
198 | PALSYA | JUNBALIDA | 106 | 6 | 5.66
199 | PALSYA | KANYTA | 285 | 1 | 0.35
200 | PALSYA | KHUNTYA SIMULYA | 136 | 123 | 90.44
201 | PALSYA | KULDIHA | 181 | 1 | 0.55
202 | PALSYA | MADARCHAK | 10 | 5 | 50
203 | PALSYA | MADARCHAK URF ASHUDCHAK | 81 | 12 | 14.81
204 | PALSYA | MAHADIYA | 80 | 11 | 13.75
205 | PALSYA | MANIKPUR | 193 | 151 | 78.24
206 | PALSYA | MIRJJACHAK | 12 | 1 | 8.33
207 | PALSYA | PALSHYA | 487 | 122 | 25.05
208 | PALSYA | PANCHPARA | 317 | 46 | 14.51
209 | PALSYA | PANISIULYA | 323 | 170 | 52.63
210 | PALSYA | RADHABALLAVCHAK | 130 | 1 | 0.77
211 | PALSYA | RAUTMANI | 464 | 23 | 4.96
212 | PALSYA | SAHABANDI | 64 | 1 | 1.56
213 | PALSYA | SAIYADHOSENCHAK | 98 | 1 | 1.02
214 | PALSYA | SALAGERYA | 35 | 3 | 8.57
215 | PALSYA | SALAGERYA 2ND PART | 6 | 0 | 0
216 | PALSYA | SHYAMCHAK | 93 | 81 | 87.1
217 | PALSYA | SHYAMSUNDARPUR | 141 | 1 | 0.71
218 | PALSYA | SWARUPCHAK | 109 | 1 | 0.92
219 | PALSYA | TAPHRIAMBI | 62 | 1 | 1.61
220 | PALSYA | TELICHAK | 69 | 1 | 1.45
221 | PALSYA | UTTARJAGATPUR | 50 | 1 | 2
222 | PAPARARA-I | AMBIGERE | 268 | 257 | 95.9
223 | PAPARARA-I | ARAJI KAPASGERIYA | 38 | 1 | 2.63
224 | PAPARARA-I | BALARAMPUR | 626 | 626 | 100
225 | PAPARARA-I | BALICHATRI | 70 | 1 | 1.43
226 | PAPARARA-I | BARAGERE | 297 | 255 | 85.86
227 | PAPARARA-I | BARBETE | 116 | 66 | 56.9
228 | PAPARARA-I | BHANDARIA | 283 | 14 | 4.95
229 | PAPARARA-I | KAPASGERYA | 75 | 48 | 64
230 | PAPARARA-I | KISMATKAPASGERYA | 35 | 1 | 2.86
231 | PAPARARA-I | KRISHNACHARANPUR | 94 | 94 | 100
232 | PAPARARA-I | LAKSHMISAR | 170 | 169 | 99.41
233 | PAPARARA-I | MADHUGERE | 42 | 1 | 2.38
234 | PAPARARA-I | MADPUR | 1117 | 1117 | 100
235 | PAPARARA-I | MAGURIA | 65 | 65 | 100
236 | PAPARARA-I | PADAMGERE | 55 | 55 | 100
237 | PAPARARA-I | PAPARARA | 1200 | 646 | 53.83
238 | PAPARARA-I | PURULIA | 32 | 31 | 96.88
239 | PAPARARA-I | RAMCHANDRAPUR | 218 | 218 | 100
240 | PAPARARA-I | SHAKMANDAL | 563 | 540 | 95.91
241 | PAPARARA-II | ABHIRAMPUR | 45 | 1 | 2.22
242 | PAPARARA-II | ARJUNCHAK | 69 | 8 | 11.59
243 | PAPARARA-II | BAITA | 117 | 15 | 12.82
244 | PAPARARA-II | BARBANSI | 628 | 261 | 41.56
245 | PAPARARA-II | BARBUDHI | 217 | 73 | 33.64
246 | PAPARARA-II | BARMAMUDPUR | 32 | 1 | 3.13
247 | PAPARARA-II | BARSANIDATTA | 57 | 1 | 1.75
248 | PAPARARA-II | BEGUNI | 41 | 17 | 41.46
249 | PAPARARA-II | BHIMRAMCHAK | 30 | 4 | 13.33
250 | PAPARARA-II | CHAK DANDI | 105 | 1 | 0.95
251 | PAPARARA-II | CHAKBHARAT | 165 | 31 | 18.79
252 | PAPARARA-II | CHAKGURAI | 12 | 0 | 0
253 | PAPARARA-II | CHAKHALDI | 25 | 0 | 0
254 | PAPARARA-II | CHAKPURAN | 103 | 43 | 41.75
255 | PAPARARA-II | CHAMKA | 125 | 1 | 0.8
256 | PAPARARA-II | DINGO | 98 | 1 | 1.02
257 | PAPARARA-II | DISITI | 200 | 1 | 0.5
258 | PAPARARA-II | DURLABHCHAK | 61 | 26 | 42.62
259 | PAPARARA-II | GAURHATI | 52 | 0 | 0
260 | PAPARARA-II | GHORATARA | 128 | 46 | 35.94
261 | PAPARARA-II | HABIBPUR | 20 | 0 | 0
262 | PAPARARA-II | HATIKHOJA | 114 | 20 | 17.54
263 | PAPARARA-II | JAGANATH CHAK | 43 | 9 | 20.93
264 | PAPARARA-II | JAMIRA | 14 | 1 | 7.14
265 | PAPARARA-II | JOGISENBAR | 59 | 19 | 32.2
266 | PAPARARA-II | KADAMGERYA | 91 | 0 | 0
267 | PAPARARA-II | KANCHANPUR | 110 | 13 | 11.82
268 | PAPARARA-II | KANKASAI BATITAKI | 33 | 1 | 3.03
269 | PAPARARA-II | KANKASAL | 66 | 1 | 1.52
270 | PAPARARA-II | KHANJADI | 71 | 1 | 1.41
271 | PAPARARA-II | KHANKARPUR | 12 | 0 | 0
272 | PAPARARA-II | KISMAT KHANKARPUR | 17 | 0 | 0
273 | PAPARARA-II | MAMUDPUR | 32 | 1 | 3.13
274 | PAPARARA-II | MANGLAI | 195 | 10 | 5.13
275 | PAPARARA-II | NIBRA | 149 | 1 | 0.67
276 | PAPARARA-II | NISCHINTAPUR | 56 | 1 | 1.79
277 | PAPARARA-II | PAISITI | 118 | 1 | 0.85
278 | PAPARARA-II | PECHANAGAR | 65 | 24 | 36.92
279 | PAPARARA-II | RAGHUNATHPUR | 71 | 0 | 0
280 | PAPARARA-II | SANCHAKTEURE | 10 | 1 | 10
281 | PAPARARA-II | SARAI | 238 | 24 | 10.08
282 | PAPARARA-II | SATDHIPA | 40 | 1 | 2.5
283 | PAPARARA-II | SHYAMCHAK | 265 | 1 | 0.38
284 | PAPARARA-II | SITIBATITAKI | 111 | 1 | 0.9
285 | PAPARARA-II | SRIRAMPUR | 45 | 0 | 0
286 | PAPARARA-II | SUJANCHAK | 94 | 1 | 1.06
287 | PAPARARA-II | SUNDARPUR | 20 | 5 | 25
288 | PAPARARA-II | SURUNIA | 25 | 1 | 4
289 | PAPARARA-II | TORKO | 190 | 1 | 0.53
290 | SANKOA | AMSARPUR | 219 | 0 | 0
291 | SANKOA | ARUN | 244 | 0 | 0
292 | SANKOA | BALIGERYA | 255 | 0 | 0
293 | SANKOA | BANSPUKHURIA | 130 | 0 | 0
294 | SANKOA | BAR HINDU | 71 | 5 | 7.04
295 | SANKOA | BAR PHAKIR | 30 | 0 | 0
296 | SANKOA | BASUDEBPUR | 33 | 0 | 0
297 | SANKOA | CHAK RAMPAL | 89 | 0 | 0
298 | SANKOA | CHAK SANTRA | 117 | 0 | 0
299 | SANKOA | CHAKABDULA | 94 | 0 | 0
300 | SANKOA | CHAKKESHI | 327 | 160 | 48.93
301 | SANKOA | CHAKMAOA | 54 | 0 | 0
302 | SANKOA | CHAKTURIA | 283 | 43 | 15.19
303 | SANKOA | DHARIMBA | 625 | 0 | 0
304 | SANKOA | HARIPURKISMAT | 205 | 0 | 0
305 | SANKOA | JANGICHAK | 100 | 0 | 0
306 | SANKOA | KHAGRA | 434 | 0 | 0
307 | SANKOA | KHARIGERYA | 74 | 0 | 0
308 | SANKOA | LAKICHAK | 193 | 14 | 7.25
309 | SANKOA | MANTAGERIA | 86 | 0 | 0
310 | SANKOA | MRIJAPUR | 119 | 5 | 4.2
311 | SANKOA | NARASINHAPUR | 141 | 0 | 0
312 | SANKOA | PHATE CHAK | 101 | 0 | 0
313 | SANKOA | SANKOA | 735 | 73 | 9.93
314 | SANKOA | SANMANINATHPUR | 174 | 0 | 0
315 | SANKOA | SHYAMALPUR | 130 | 0 | 0
316 | SANKOA | TENTULMURI | 183 | 0 | 0
Total |  |  | 51766 | 18623 | 35.98