## FHTC Coverage (Since Inception)
FHTC Coverage (Since Inception)
Sl.No. | Gram Panchayat | Village | Total Number of Household | FHTC Provided | % Progress
1 | BADALPUR | ALALPUR | 444 | 444 | 100
2 | BADALPUR | BADALPUR 1ST PART | 1231 | 1231 | 100
3 | BADALPUR | BAND GOBINDAPUR | 501 | 501 | 100
4 | BADALPUR | BARAMUSHAPUR | 91 | 1 | 1.1
5 | BADALPUR | BISHWANATHPUR | 970 | 970 | 100
6 | BADALPUR | JANGIPUR | 60 | 60 | 100
7 | BADALPUR | JUNBANI | 587 | 587 | 100
8 | BADALPUR | KUDBHERI | 557 | 557 | 100
9 | BADALPUR | PASCHIM CHANDANPUR | 663 | 663 | 100
10 | BADALPUR | PASCHIM MANIKPUR | 596 | 596 | 100
11 | DULALPUR | BETBANI | 62 | 62 | 100
12 | DULALPUR | BETGERYA | 253 | 253 | 100
13 | DULALPUR | BHUPATINAGAR | 163 | 121 | 74.23
14 | DULALPUR | DULALPUR | 305 | 305 | 100
15 | DULALPUR | ERYAFATEPUR | 188 | 188 | 100
16 | DULALPUR | GOPAL PUR 2ND PART | 154 | 154 | 100
17 | DULALPUR | HAMIRMAHAL | 142 | 142 | 100
18 | DULALPUR | KACHUA | 273 | 273 | 100
19 | DULALPUR | KANTAI | 534 | 500 | 93.63
20 | DULALPUR | KHALISABHANGA | 198 | 198 | 100
21 | DULALPUR | LASKAR PADA | 177 | 177 | 100
22 | DULALPUR | MAJNA | 1360 | 1359 | 99.93
23 | DULALPUR | MUKUNDAPUR | 460 | 386 | 83.91
24 | DULALPUR | PAYRADWIP | 122 | 122 | 100
25 | DULALPUR | RANI BASAN | 469 | 466 | 99.36
26 | DULALPUR | SILAMPUR | 480 | 480 | 100
27 | DULALPUR | SITALPUR | 330 | 260 | 78.79
28 | DULALPUR | SUJULPUR | 49 | 49 | 100
29 | DULALPUR | TAJPUR | 501 | 501 | 100
30 | HARIPUR | AKANDI | 256 | 256 | 100
31 | HARIPUR | AKGERYA | 62 | 62 | 100
32 | HARIPUR | ANALBERYA | 113 | 1 | 0.88
33 | HARIPUR | BRAJAMAL | 126 | 126 | 100
34 | HARIPUR | DAKSHIN CHARAI KHIA | 521 | 521 | 100
35 | HARIPUR | DAKSHIN KHASDA | 36 | 36 | 100
36 | HARIPUR | DHANESHWARI | 146 | 146 | 100
37 | HARIPUR | DHANGAN | 98 | 98 | 100
38 | HARIPUR | EKTARPUR MADANMOHANBAR | 110 | 110 | 100
39 | HARIPUR | GAGANNATHPUR IST PART | 157 | 157 | 100
40 | HARIPUR | HAIPUR | 456 | 456 | 100
41 | HARIPUR | HARICHAK | 55 | 55 | 100
42 | HARIPUR | IRDA | 213 | 205 | 96.24
43 | HARIPUR | KANCHRA GERYA | 310 | 310 | 100
44 | HARIPUR | KANURAUTBAR | 2 | 1 | 50
45 | HARIPUR | KASHI BHUIANBAR | 17 | 1 | 5.88
46 | HARIPUR | KHOLANASHWARI | 278 | 278 | 100
47 | HARIPUR | KULBARIA | 298 | 298 | 100
48 | HARIPUR | MAISALI | 256 | 252 | 98.44
49 | HARIPUR | MARRA | 130 | 121 | 93.08
50 | HARIPUR | NUNIA | 50 | 50 | 100
51 | HARIPUR | PALTA BERIA | 235 | 235 | 100
52 | HARIPUR | PASCHIM JAGANNATHCHAK | 150 | 115 | 76.67
53 | HARIPUR | PASCHIM TEGHARI | 108 | 1 | 0.93
54 | HARIPUR | RAUTARA | 205 | 205 | 100
55 | HARIPUR | SAHEB KHANKERANIBAR | 194 | 192 | 98.97
56 | HARIPUR | SHILAMPUR | 186 | 0 | 0
57 | HARIPUR | SURUNDIA | 180 | 165 | 91.67
58 | HARIPUR | TEDUBI | 680 | 640 | 94.12
59 | HARIPUR | UGRASENBAR | 249 | 235 | 94.38
60 | HARIPUR | ULU BERE | 68 | 68 | 100
61 | HARIPUR | UTTAR CHARAI KHIA | 172 | 172 | 100
62 | HARIPUR | UTTARKHASDA | 328 | 328 | 100
63 | MAHISAGOT | ADAMBAR | 96 | 1 | 1.04
64 | MAHISAGOT | BADALPUR | 162 | 155 | 95.68
65 | MAHISAGOT | BADALPUR 2ND PART | 108 | 1 | 0.93
66 | MAHISAGOT | BAHULIA | 235 | 1 | 0.43
67 | MAHISAGOT | BELTALYA | 365 | 119 | 32.6
68 | MAHISAGOT | DAKSHIN RAMCHAK | 194 | 194 | 100
69 | MAHISAGOT | GHATUA | 475 | 306 | 64.42
70 | MAHISAGOT | GOPALPUR | 130 | 88 | 67.69
71 | MAHISAGOT | HARIPUR | 150 | 1 | 0.67
72 | MAHISAGOT | HATIBERYA | 62 | 35 | 56.45
73 | MAHISAGOT | KAITALIA | 200 | 192 | 96
74 | MAHISAGOT | KANCHANPUR | 31 | 1 | 3.23
75 | MAHISAGOT | KAPASDA | 455 | 1 | 0.22
76 | MAHISAGOT | MAHISHGOT | 585 | 585 | 100
77 | MAHISAGOT | MURABANIA | 70 | 1 | 1.43
78 | MAHISAGOT | NIMDASBAR | 170 | 1 | 0.59
79 | MAHISAGOT | PASCHIM RASULPUR | 231 | 1 | 0.43
80 | MAHISAGOT | POTAPUKHURIA | 94 | 1 | 1.06
81 | MAHISAGOT | RATANPUR | 154 | 1 | 0.65
82 | MAHISAGOT | SAHAJADAPUR | 320 | 225 | 70.31
83 | MAHISAGOT | SANKARKUNDI | 212 | 212 | 100
84 | MAHISAGOT | SARISHABERYA | 95 | 44 | 46.32
85 | MAHISAGOT | SHRIBACHHIPUR | 110 | 91 | 82.73
86 | MAHISAGOT | SUBARNADIHI | 185 | 1 | 0.54
87 | MAHISAGOT | SURGHANI | 64 | 1 | 1.56
88 | MAHISAGOT | TAGRIA | 341 | 341 | 100
89 | MAHISAGOT | UTTAR BAHULIA | 60 | 1 | 1.67
90 | MAJILAPUR | BACHHIPUR BAR | 57 | 46 | 80.7
91 | MAJILAPUR | BAGURAN | 59 | 48 | 81.36
92 | MAJILAPUR | BAGURAN JALPAI | 331 | 254 | 76.74
93 | MAJILAPUR | BARACHUN FALI | 164 | 164 | 100
94 | MAJILAPUR | BENIPUR | 83 | 83 | 100
95 | MAJILAPUR | BHUIANPADA | 190 | 25 | 13.16
96 | MAJILAPUR | BIRAMPUT | 560 | 560 | 100
97 | MAJILAPUR | CHUAPHALI | 182 | 182 | 100
98 | MAJILAPUR | DAKSHIN DARUA | 40 | 40 | 100
99 | MAJILAPUR | DAKSHIN DAUKI | 178 | 178 | 100
100 | MAJILAPUR | DAKSHIN GOPINATHPUR | 156 | 156 | 100
101 | MAJILAPUR | DESHDATTA BAR | 192 | 192 | 100
102 | MAJILAPUR | GAHIRA BAR | 53 | 53 | 100
103 | MAJILAPUR | HARI PUR | 221 | 40 | 18.1
104 | MAJILAPUR | HUGLI | 98 | 98 | 100
105 | MAJILAPUR | KAMARPUT | 12 | 12 | 100
106 | MAJILAPUR | KANDARAPUR SANNIYASI BAR | 80 | 80 | 100
107 | MAJILAPUR | KHIKINA | 78 | 78 | 100
108 | MAJILAPUR | MAHARAMPUR | 4 | 1 | 25
109 | MAJILAPUR | MAJILA PUR | 704 | 575 | 81.68
110 | MAJILAPUR | MANKARAI PUT | 50 | 1 | 2
111 | MAJILAPUR | NARAYANPUR | 33 | 21 | 63.64
112 | MAJILAPUR | PATHER GHATA | 112 | 112 | 100
113 | MAJILAPUR | PUAN BALI BAR | 176 | 176 | 100
114 | MAJILAPUR | PURBA RAM CHANDRA PUR | 140 | 105 | 75
115 | MAJILAPUR | RAGHU SARDAR BAR | 50 | 9 | 18
116 | MAJILAPUR | RAGHUSARDAR BAR JALPAI | 190 | 1 | 0.53
117 | MAJILAPUR | RANGAMALPUT | 235 | 185 | 78.72
118 | MAJILAPUR | RASULPUR | 55 | 1 | 1.82
119 | MAJILAPUR | SHARAD PUR | 38 | 2 | 5.26
120 | MAJILAPUR | SHILAMPUR | 114 | 114 | 100
121 | MAJILAPUR | SHYAM RAI BAR JALPAI | 150 | 1 | 0.67
122 | MAJILAPUR | SUBDI | 140 | 121 | 86.43
123 | MAJILAPUR | SYAMRAI BAR | 261 | 1 | 0.38
124 | NAYAPUT | AMADPUR | 94 | 1 | 1.06
125 | NAYAPUT | AMARTALYA | 167 | 167 | 100
126 | NAYAPUT | BAGHMARI | 140 | 140 | 100
127 | NAYAPUT | BAKSISPUR | 450 | 1 | 0.22
128 | NAYAPUT | BALBHADRAPUR | 170 | 141 | 82.94
129 | NAYAPUT | BALIARPUR | 137 | 137 | 100
130 | NAYAPUT | BARA RAMMAITI BAR | 116 | 1 | 0.86
131 | NAYAPUT | BATIPUR | 127 | 1 | 0.79
132 | NAYAPUT | BHANDU BASAN | 280 | 1 | 0.36
133 | NAYAPUT | CHANDANPUR | 118 | 118 | 100
134 | NAYAPUT | DAKSHIN GOBINDA PUR | 4 | 1 | 25
135 | NAYAPUT | DAKSHIN RAMPUR | 154 | 154 | 100
136 | NAYAPUT | DAKSHIN SHERPUR | 85 | 9 | 10.59
137 | NAYAPUT | DAMODARPUR | 125 | 42 | 33.6
138 | NAYAPUT | DAMUDARPUR | 221 | 221 | 100
139 | NAYAPUT | DAMUDARPUR JALPAI | 5 | 1 | 20
140 | NAYAPUT | DURGAPUR | 293 | 40 | 13.65
141 | NAYAPUT | FATEPUR | 115 | 114 | 99.13
142 | NAYAPUT | HAMIRPUR | 66 | 66 | 100
143 | NAYAPUT | JAMNA MADHUSUDAN BAR | 116 | 116 | 100
144 | NAYAPUT | JANUBASAN | 64 | 63 | 98.44
145 | NAYAPUT | JHARKOSHBAR | 65 | 1 | 1.54
146 | NAYAPUT | KANDARPAPUR | 145 | 124 | 85.52
147 | NAYAPUT | KARANJI | 280 | 16 | 5.71
148 | NAYAPUT | MACHHALANDAPUR | 103 | 1 | 0.97
149 | NAYAPUT | MADHAB PATTANAYAK BAR | 50 | 1 | 2
150 | NAYAPUT | MADHABPUR | 159 | 1 | 0.63
151 | NAYAPUT | NARASINGAPUR | 130 | 129 | 99.23
152 | NAYAPUT | NAYAPUT | 330 | 1 | 0.3
153 | NAYAPUT | PADMAPUT CHHAKUBANARBAR | 77 | 48 | 62.34
154 | NAYAPUT | PANIPIA | 203 | 1 | 0.49
155 | NAYAPUT | PASCHIM CHECHURA PUT | 202 | 1 | 0.5
156 | NAYAPUT | PATESHWARPUR | 65 | 1 | 1.54
157 | NAYAPUT | PURUSHOTTAMPUR | 30 | 1 | 3.33
158 | NAYAPUT | PURUSHOTTAMPUR | 121 | 1 | 0.83
159 | NAYAPUT | PURUSHOTTAMPUR PURIDASBAR | 215 | 1 | 0.47
160 | NAYAPUT | SERPURJALPAI | 9 | 1 | 11.11
161 | NAYAPUT | SUJANBHUNIA BAR | 8 | 1 | 12.5
162 | RAIPUR PASCHIMBAR | ALIPUR | 50 | 30 | 60
163 | RAIPUR PASCHIMBAR | BADHIE | 445 | 287 | 64.49
164 | RAIPUR PASCHIMBAR | BARBARYA | 309 | 1 | 0.32
165 | RAIPUR PASCHIMBAR | CHANDDIA DUNDIBAR | 200 | 1 | 0.5
166 | RAIPUR PASCHIMBAR | CHANDIA DARBARIKHANIBAR | 12 | 1 | 8.33
167 | RAIPUR PASCHIMBAR | CHANDIA HAIBATBAR | 24 | 1 | 4.17
168 | RAIPUR PASCHIMBAR | CHHATRADHARA | 91 | 91 | 100
169 | RAIPUR PASCHIMBAR | DANDAPUR | 87 | 87 | 100
170 | RAIPUR PASCHIMBAR | ERYA GOBINDAPUR | 119 | 119 | 100
171 | RAIPUR PASCHIMBAR | GIMAGERE | 240 | 193 | 80.42
172 | RAIPUR PASCHIMBAR | JUGI BAR | 95 | 84 | 88.42
173 | RAIPUR PASCHIMBAR | KANCHURI | 78 | 1 | 1.28
174 | RAIPUR PASCHIMBAR | KRISHNACHAK | 150 | 142 | 94.67
175 | RAIPUR PASCHIMBAR | LAUDANDA | 140 | 140 | 100
176 | RAIPUR PASCHIMBAR | NAMAL | 132 | 132 | 100
177 | RAIPUR PASCHIMBAR | NANDABERYA | 30 | 1 | 3.33
178 | RAIPUR PASCHIMBAR | NANDIERYA | 134 | 134 | 100
179 | RAIPUR PASCHIMBAR | NATDIGHI | 321 | 1 | 0.31
180 | RAIPUR PASCHIMBAR | PANIA | 384 | 384 | 100
181 | RAIPUR PASCHIMBAR | RAIPUR | 197 | 107 | 54.31
182 | RAIPUR PASCHIMBAR | RAIPUR PASCHIMBAR | 134 | 6 | 4.48
183 | RAIPUR PASCHIMBAR | RAKTIA | 83 | 83 | 100
184 | RAIPUR PASCHIMBAR | RANIA | 467 | 147 | 31.48
185 | RAIPUR PASCHIMBAR | SARIA | 120 | 1 | 0.83
186 | RAIPUR PASCHIMBAR | SASANIA | 216 | 110 | 50.93
187 | RAIPUR PASCHIMBAR | SIRIA | 111 | 111 | 100
188 | RAIPUR PASCHIMBAR | SRIRAMPUR | 910 | 910 | 100
189 | RAIPUR PASCHIMBAR | TAGARIA GOPALPUR | 150 | 150 | 100
190 | RAIPUR PASCHIMBAR | TENGUNIA | 442 | 442 | 100
191 | RAIPUR PASCHIMBAR | TENTULMURI | 400 | 265 | 66.25
192 | SABAJPUT | BADALPUR | 89 | 65 | 73.03
193 | SABAJPUT | BAGDIAN | 150 | 144 | 96
194 | SABAJPUT | BAIDYAHARANA | 63 | 15 | 23.81
195 | SABAJPUT | BANAMALI PUR | 158 | 140 | 88.61
196 | SABAJPUT | BANKABERYA | 217 | 191 | 88.02
197 | SABAJPUT | CHHOTA EKTARPUR | 34 | 34 | 100
198 | SABAJPUT | DAKSHIN POTAPUKHURIA GOPAL SIBAR | 198 | 198 | 100
199 | SABAJPUT | DAUDPUR | 403 | 403 | 100
200 | SABAJPUT | EKTARPUR | 182 | 1 | 0.55
201 | SABAJPUT | ENAYET CHAK | 34 | 1 | 2.94
202 | SABAJPUT | GAMARTALIA | 269 | 268 | 99.63
203 | SABAJPUT | GOBINDAPUR | 85 | 1 | 1.18
204 | SABAJPUT | JAGANNATHPUR 2ND PART | 180 | 149 | 82.78
205 | SABAJPUT | JAMALPUR | 156 | 156 | 100
206 | SABAJPUT | KEORANALA | 182 | 182 | 100
207 | SABAJPUT | KRISHNA KHAYARTIBAR | 326 | 325 | 99.69
208 | SABAJPUT | KULAIPADIMA | 266 | 266 | 100
209 | SABAJPUT | KULALPADA | 188 | 1 | 0.53
210 | SABAJPUT | LACHHANPUR | 159 | 1 | 0.63
211 | SABAJPUT | MATALPUR | 21 | 20 | 95.24
212 | SABAJPUT | PAILACHHANPUR | 236 | 112 | 47.46
213 | SABAJPUT | PAYRACHALI | 84 | 84 | 100
214 | SABAJPUT | POTA POKHURIA ANANTARAUTBA | 282 | 1 | 0.35
215 | SABAJPUT | RAMCHANDRAPUR | 180 | 146 | 81.11
216 | SABAJPUT | SABAJPUR | 152 | 151 | 99.34
217 | SABAJPUT | SAMUDRAPUR | 422 | 1 | 0.24
218 | SABAJPUT | SAMUDRAPUR JALPAI | 1 | 1 | 100
219 | SABAJPUT | SATBERIA | 62 | 62 | 100
220 | SABAJPUT | SEKH KOCHBAR | 118 | 4 | 3.39
221 | SABAJPUT | SHIKARPUR | 56 | 56 | 100
222 | SABAJPUT | TAKIA HARIPURKHAL | 21 | 1 | 4.76
Total |  |  | 45389 | 33025 | 72.76