## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Ghusuru Piped water Supply Scheme at Naxalbari Block (SM/07423) | SM/07423 | 38.97 | 758 | RETROFITTING | 0 | 0% Physical | 100 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 01/11/2021 | 38.97 | 38.97
2 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Matidhar Bijmillini T.E and Pathoria Habitation of Paschim Madati Piped water Supply Scheme (Part - A) (SM/07031) | SM/07031 | 85.56 | 1649 | RETROFITTING | 0 | 0% Physical | 60 | 13/11/2020 | 31/12/2023 | 12/06/2023 | 18/12/2020 | 51 | 47.59
3 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for kantivita,Dhamnagach, & Purba bansgaon kismath villages under Bandargachh Piped water Supply Scheme (SM/07220) | SM/07220 | 77.54 | 1173 | RETROFITTING | 0 | WO no issued | 0 | 08/12/2020 | 31/12/2023 | 12/06/2023 |  | 0 | 0
4 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme (SM/07033) | SM/07033 | 75.17 | 1524 | RETROFITTING | 0 | 0% Physical | 79 | 24/11/2020 | 31/03/2024 | 12/06/2023 | 03/08/2021 | 59.7 | 47.32
5 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Khopalasi village of Panchkolguri Piped water Supply Scheme (SM/07039) | SM/07039 | 78 | 1194 | RETROFITTING | 0 | WO no issued | 0 | 24/11/2020 | 31/03/2024 | 12/06/2023 |  | 0 | 0
6 | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. (SM/11387) | SM/11387 | 31.49 | 145 | RETROFITTING | 0 | 0% Physical | 97 | 04/07/2022 | 04/10/2022 | 12/06/2023 | 12/07/2022 | 30.57 | 30.57
7 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA (SM/11337) | SM/11337 | 14.29 | 72 | RETROFITTING | 0 | 0% Physical | 79 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 11.23 | 11.23
8 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Mangalsing Piped water Supply Scheme (SM/07029) | SM/07029 | 56.89 | 1096 | RETROFITTING | 0 | 0% Physical | 100 | 13/11/2020 | 31/03/2024 | 12/06/2023 | 06/09/2021 | 56.89 | 56.89
9 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme (SM/07045) | SM/07045 | 92.52 | 1800 | RETROFITTING | 0 | 0% Physical | 65 | 24/11/2020 | 31/12/2023 | 12/06/2023 | 18/12/2020 | 60 | 31.86
10 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] (SM/10262) | SM/10262 | 159.17 | 817 | RETROFITTING | 0 | 0% Physical | 91 | 08/02/2021 | 08/05/2021 | 30/04/2022 |  | 145.57 | 110.69
11 | Creation of gravity based provision of drinking water from spring water source of anganwadi(119 nos) centers under Darjeeling pulbazar block in the district of Darjeeling under Neorakhola water supply & maintenance division, P.H.E. Directorate (SM/10796) | SM/10796 | 429.36 | 0 | ANGANWADI | 0 | 0% Physical | 0 | 25/05/2022 |  | 26/05/2022 | 06/05/2022 | 0 | 0
12 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA (SM/11330) | SM/11330 | 13.49 | 56 | RETROFITTING | 0 | 0% Physical | 92 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 12.44 | 12.44
13 | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. (SM/11300) | SM/11300 | 20.83 | 55 | RETROFITTING | 0 | 0% Physical | 2 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 0.34 | 0.34
14 | Providing Functional households Tap connection under JSP Programme for PWS Scheme Soureni Bazar (SM/11306) | SM/11306 | 23.6 | 166 | RETROFITTING | 0 | 0% Physical | 73 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 17.24 | 17.24
15 | Providing functional household Tap connection under JSP Programme for PWS Scheme Manju Dara Gaon (SM/11307) | SM/11307 | 6.09 | 35 | RETROFITTING | 0 | 0% Physical | 84 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 5.11 | 5.11
16 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA (SM/11331) | SM/11331 | 31.31 | 310 | RETROFITTING | 0 | 0% Physical | 88 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 27.63 | 27.63
17 | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. (SM/11349) | SM/11349 | 79.79 | 175 | NEW | 0 | 0% Physical | 1 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 23/08/2023 | 1.08 | 1.08
18 | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/18878) | SM/18878 | 199.02 | 161 | AUGMENTATION | 0 | 0% Physical | 0 | 05/10/2023 | 05/04/2024 | 06/10/2023 |  | 0 | 0
19 | BHIRGAON DHARGAON PWSS (SM/18714) | SM/18714 | 162.75 | 149 | NEW | 0 | 0% Physical | 0 | 07/08/2023 | 07/02/2025 | 07/08/2023 | 07/08/2023 | 0 | 0
20 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Pelku (JL No-71) & Thiknikata (JL No.-74) Mouzas of Kawakhali Pipe water Supply Scheme (SM/07213) | SM/07213 | 99.9 | 1372 | RETROFITTING | 0 | 0% Physical | 0 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 10/08/2023 | 0 | 0
21 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] (SM/10258) | SM/10258 | 112.63 | 1560 | RETROFITTING | 0 | 0% Physical | 64 | 09/02/2021 | 09/05/2021 | 30/04/2022 | 10/02/2021 | 72.46 | 72.46
22 | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. (SM/11394) | SM/11394 | 199.28 | 1395 | RETROFITTING | 0 | 0% Physical | 32 | 04/07/2022 | 04/10/2022 | 12/06/2023 | 01/11/2022 | 64.16 | 64.16
23 | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme (SM/16142) | SM/16142 | 334.74 | 711 | NEW | 0 | 0% Physical | 1 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 18/07/2023 | 4.38 | 4.38
24 | Augmentation of Nipania Piped Water Supply Scheme. (SM/18881) | SM/18881 | 194.06 | 159 | AUGMENTATION | 0 | 0% Physical | 0 | 05/10/2023 | 05/04/2024 | 06/10/2023 |  | 0 | 0
25 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme (SM/07217) | SM/07217 | 80.78 | 1053 | RETROFITTING | 0 | 0% Physical | 99 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 11/12/2020 | 80 | 71.29
26 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bansgaon village of Purba Bansgaon Piped water Supply Scheme (SM/07040) | SM/07040 | 85.15 | 1347 | RETROFITTING | 0 | 0% Physical | 60 | 24/11/2020 | 31/12/2023 | 12/06/2023 | 11/12/2020 | 51 | 35.86
27 | Providing Functional household tap connection under Jal Jeewan Mission/ Jal Swapno Programme at New Fallodi Tea Garden ( Mandir Goan) (SM/11390) | SM/11390 | 10.66 | 45 | RETROFITTING | 0 | 0% Physical | 0 | 04/07/2022 | 04/10/2022 | 12/06/2023 | 12/07/2022 | 0 | 0
28 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA (SM/11329) | SM/11329 | 19.72 | 156 | RETROFITTING | 0 | 0% Physical | 95 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 18.7 | 18.7
29 | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon (SM/11304) | SM/11304 | 23.72 | 44 | RETROFITTING | 0 | 0% Physical | 86 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 20.39 | 20.39
30 | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate (SM/11360) | SM/11360 | 397.94 | 0 | ANGANWADI | 0 | 0% Physical | 0 | 28/06/2022 |  | 03/07/2022 | 12/07/2022 | 0 | 0
31 | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong (SM/11366) | SM/11366 | 28.59 | 6 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 0 | 0% Physical | 0 | 28/06/2022 |  | 03/07/2022 | 12/07/2022 | 0 | 0
32 | DARJEELING-PULBAZAR PUMPING-I PWSS (SM/18827) | SM/18827 | 17368.24 | 3658 | NEW | 0 | 0% Physical | 0 | 12/09/2023 | 12/03/2026 | 18/09/2023 | 03/09/2024 | 22.53 | 22.53
33 | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME (SM/18879) | SM/18879 | 93.17 | 80 | AUGMENTATION | 0 | 0% Physical | 0 | 05/10/2023 | 05/04/2024 | 06/10/2023 |  | 0 | 0
34 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) (SM/07047) | SM/07047 | 66.13 | 1142 | RETROFITTING | 0 | 0% Physical | 50 | 24/11/2020 | 31/12/2023 | 12/06/2023 | 11/12/2020 | 33.07 | 33.07
35 | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. (SM/10260) | SM/10260 | 269.79 | 3812 | RETROFITTING | 0 | 0% Physical | 75 | 09/02/2021 | 09/05/2021 | 30/04/2022 | 10/02/2021 | 202.06 | 202.06
36 | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M (SM/10687) | SM/10687 | 379.94 | 0 | SCHOOL | 0 | 0% Physical | 0 | 06/05/2022 |  | 06/05/2022 | 06/05/2022 | 0 | 0
37 | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna (SM/11380) | SM/11380 | 10.66 | 45 | RETROFITTING | 0 | 0% Physical | 88 | 04/07/2022 | 04/10/2022 | 12/06/2023 | 12/07/2022 | 9.39 | 9.39
38 | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III (SM/11301) | SM/11301 | 8.63 | 45 | RETROFITTING | 0 | 0% Physical | 91 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 7.83 | 7.83
39 | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Bada kothi (SM/11310) | SM/11310 | 4.51 | 37 | RETROFITTING | 0 | 0% Physical | 81 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 3.64 | 3.64
40 | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. (SM/11352) | SM/11352 | 32.24 | 110 | NEW | 0 | 0% Physical | 0 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 28/09/2022 | 0 | 0
41 | MAHANADI FOREST PIPED WATER SUPPLY SCHEME. (SM/15875) | SM/15875 | 217.84 | 158 | NEW | 0 | WO no issued | 0 | 20/02/2023 | 20/08/2024 | 12/06/2023 |  | 0 | 0
42 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] (SM/10264) | SM/10264 | 108.57 | 1124 | RETROFITTING | 0 | 0% Physical | 70 | 08/02/2021 | 08/05/2021 | 30/04/2022 |  | 76.51 | 76.51
43 | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/18880) | SM/18880 | 197.84 | 190 | AUGMENTATION | 0 | 0% Physical | 0 | 05/10/2023 | 05/04/2024 | 06/10/2023 |  | 0 | 0
44 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block (SM/07425) | SM/07425 | 50.62 | 898 | RETROFITTING | 0 | 0% Physical | 100 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 50.62 | 48.09
45 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block (SM/07426) | SM/07426 | 57.56 | 1336 | RETROFITTING | 0 | 0% Physical | 100 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 02/08/2021 | 57.56 | 57.56
46 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Panchkolguri & Jhauguri village of Panchkolguri Piped water Supply Scheme (SM/07219) | SM/07219 | 55.74 | 735 | RETROFITTING | 0 | WO no issued | 0 | 08/12/2020 | 31/03/2024 | 12/06/2023 |  | 0 | 0
47 | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. (SM/10261) | SM/10261 | 34.5 | 328 | RETROFITTING | 0 | 0% Physical | 57 | 09/02/2021 | 09/05/2021 | 30/04/2022 | 10/02/2021 | 19.62 | 19.62
48 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] (SM/10263) | SM/10263 | 39.28 | 312 | RETROFITTING | 0 | 0% Physical | 93 | 08/02/2021 | 08/05/2021 | 30/04/2022 |  | 36.7 | 36.7
49 | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal swapno programme for Mirjangla,Mirjnaglar Chhat, Birsing, Fakna Mouza of Birsing Piped W/S Scheme at Naxalbari Block under Siliguri Sub Division, P.H.E Dte. ( Phase-II ) (SM/09079) | SM/09079 | 57.6 | 1125 | RETROFITTING | 0 | 0% Physical | 92 | 28/10/2021 | 31/12/2023 | 12/06/2023 | 01/11/2021 | 53.18 | 45.93
50 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. (SM/11314) | SM/11314 | 10.67 | 125 | RETROFITTING | 0 | 0% Physical | 7 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 0.77 | 0.77
51 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Budharugaon village of Budharugaon Piped water Supply Scheme (SM/07041) | SM/07041 | 91.98 | 1546 | RETROFITTING | 0 | 0% Physical | 24 | 24/11/2020 | 31/03/2024 | 12/06/2023 | 02/08/2021 | 21.89 | 21.89
52 | Providing Functional Household Tap connection under JSP Programme for PWS scheme at Kataray forest Busty (SM/11302) | SM/11302 | 9.52 | 56 | RETROFITTING | 0 | 0% Physical | 77 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 7.31 | 7.31
53 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block (SM/07422) | SM/07422 | 18.5 | 286 | RETROFITTING | 0 | 0% Physical | 97 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 01/11/2021 | 17.97 | 17.97
54 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) (SM/07032) | SM/07032 | 31.72 | 508 | RETROFITTING | 0 | 0% Physical | 97 | 13/11/2020 | 31/12/2023 | 12/06/2023 | 18/12/2020 | 30.8 | 30.8
55 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme (SM/07215) | SM/07215 | 59.78 | 872 | RETROFITTING | 0 | 0% Physical | 85 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 02/08/2021 | 51 | 32.97
56 | Extension of Piped Water Supply (PWS) to Anganwadi Centers (AWCs) located within the command area of PWSS under Siliguri W/S Division. (SM/07966) | SM/07966 | 15.95 | 391 | ANGANWADI | 0 | WO no issued | 0 | 08/01/2021 | 08/07/2022 | 30/04/2022 |  | 0 | 0
57 | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme in 5 Habitation ( Ghaiter Busrty, Gurira Zote , Nagar Zote, NDDP Busty , Taluk Zote ) at Village Guria of (SM/09203) | SM/09203 | 66.16 | 1200 | AUGMENTATION | 0 | 0% Physical | 81 | 29/10/2021 | 31/12/2023 | 12/06/2023 | 22/12/2022 | 53.5 | 48.12
58 | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D (SM/09204) | SM/09204 | 21.41 | 450 | AUGMENTATION | 0 | 0% Physical | 97 | 29/10/2021 | 31/12/2023 | 12/06/2023 | 20/07/2022 | 20.79 | 19.89
59 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] (SM/10259) | SM/10259 | 80.55 | 1005 | RETROFITTING | 0 | 0% Physical | 86 | 09/02/2021 | 09/05/2021 | 30/04/2022 | 10/02/2021 | 69.58 | 69.58
60 | Providing Functional Household Tap Connection with distribution networks retrofitting under JSP Programme for PWS Scheme for Chowandhura (SM/11311) | SM/11311 | 11.81 | 41 | RETROFITTING | 0 | 0% Physical | 0 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 0 | 0
61 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA (SM/11336) | SM/11336 | 13.82 | 102 | RETROFITTING | 0 | 0% Physical | 81 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 11.18 | 11.18
62 | KANKIBONG PWSS (SM/18992) | SM/18992 | 836.23 | 672 | NEW | 0 | 0% Physical | 0 | 17/10/2023 |  | 17/10/2023 | 17/10/2023 | 0 | 0
63 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dangarvita Piped water Supply Scheme at Kharibari Block (SM/07424) | SM/07424 | 70.07 | 1334 | RETROFITTING | 0 | WO no issued | 94 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 16/01/2020 | 65.52 | 56.52
64 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Paschim Madati Mouza part of Purba Madati Piped water Supply Scheme (Part-A) (SM/07070) | SM/07070 | 44.75 | 810 | RETROFITTING | 0 | 0% Physical | 96 | 26/11/2020 | 31/12/2023 | 12/06/2023 | 18/12/2020 | 43 | 21.95
65 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Chayan Sing and Bhogbhita village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-B) (SM/07048) | SM/07048 | 42.44 | 744 | RETROFITTING | 0 | 0% Physical | 42 | 24/11/2020 | 31/12/2023 | 12/06/2023 | 02/08/2021 | 17.92 | 17.92
66 | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling (SM/11309) | SM/11309 | 8.98 | 60 | RETROFITTING | 0 | 0% Physical | 83 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 7.44 | 7.44
67 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA (SM/11335) | SM/11335 | 12.77 | 58 | RETROFITTING | 0 | 0% Physical | 75 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 9.52 | 9.52
68 | Creating gravity based Provision Of Drinking water from spring water source for 192 numbers of school under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte (SM/11356) | SM/11356 | 638.99 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 |  | 03/07/2022 | 12/07/2022 | 0 | 0
69 | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11361) | SM/11361 | 106.1 | 0 | ANGANWADI | 0 | 0% Physical | 0 | 28/06/2022 |  | 03/07/2022 | 05/08/2022 | 0 | 0
70 | HATTA PIPED WATER SUPPLY SCHEME. (SM/15883) | SM/15883 | 329.63 | 134 | NEW | 0 | 0% Physical | 0 | 20/02/2023 | 20/08/2024 | 12/06/2023 | 05/06/2023 | 0.83 | 0.83
71 | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA (SM/18917) | SM/18917 | 947.7 | 925 | NEW | 0 | 0% Physical | 0 | 09/10/2023 | 09/04/2025 | 09/10/2023 | 19/09/2024 | 0 | 0
72 | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING (SM/19177) | SM/19177 | 9214.38 | 6430 | NEW | 0 | 0% Physical | 0 | 16/02/2024 |  | 16/02/2024 | 09/09/2024 | 0 | 0
73 | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co (SM/19010) | SM/19010 | 699.39 | 0 | SUPPORT DPR & SURVEY | 0 | 0% Physical | 0 | 19/10/2023 |  | 19/10/2023 | 03/11/2021 | 0 | 0
74 | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . (SM/06627) | SM/06627 | 9.85 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 30/04/2021 | 17/03/2023 | 0 | 0
75 | Proposed Estimate for Construction of Sub - Divisional Water Testing Lab over the existing PHE Division Building at Kurseong (SM/14195) | SM/14195 | 59.93 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/01/2023 |  | 12/01/2023 |  | 0 | 0
76 | Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). (SM/18270) | SM/18270 | 45.27 | 0 | SUPPORT-ADMIN / ESTABLISHMENT | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 | 27/07/2023 | 0 | 0
77 | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA (SM/12737) | SM/12737 | 8.66 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 20/09/2022 |  | 22/09/2022 |  | 0 | 0
78 | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. (SM/11729) | SM/11729 | 12.17 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 03/08/2022 |  | 05/08/2022 |  | 0 | 0
79 | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . (SM/14065) | SM/14065 | 19.05 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 12/12/2022 |  | 15/12/2022 |  | 0 | 0
80 | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. (SM/17179) | SM/17179 | 22.95 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 |  | 0 | 0
81 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Siliguri Mahakuma Parishad (SMP) Darjeeling District. (SM/09029) | SM/09029 | 88 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 30/10/2021 |  | 02/11/2021 | 17/08/2022 | 0 | 0
82 | Operational Charges Of Darjeeling District Laboratory related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission 2023-24 (SM/19262) | SM/19262 | 26.78 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 29/08/2023 | 0 | 0
83 | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C (SM/10732) | SM/10732 | 910.35 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 19/05/2022 |  | 19/05/2022 | 03/11/2021 | 0 | 0
84 | Collection of Drinking Water Samples from various spot sources, PWSS, Schools, Anganwadis, Health Centres and Springs under Darjeeling Hills for water testing at Sindhap sub-district laboratory Darjeeling managed by Neorakhola water supply and maintenance (SM/15668) | SM/15668 | 13.71 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 03/03/2023 | 0 | 0
85 | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE (SM/18534) | SM/18534 | 3073.44 | 6130 | NEW | 1 | Delayed | 11 | 26/07/2023 | 26/07/2025 | 16/10/2023 | 15/01/2024 | 350.21 | 350.21
86 | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) (SM/15927) | SM/15927 | 455.46 | 1622 | NEW | 2 | Delayed | 7 | 22/02/2023 | 22/08/2024 | 11/10/2023 | 20/06/2022 | 32.88 | 32.88
87 | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) (SM/15908) | SM/15908 | 758.56 | 1612 | NEW | 2 | Delayed | 5 | 20/02/2023 | 31/03/2025 | 01/02/2024 | 28/07/2022 | 37 | 37
88 | Augmentation of Hatidoba Piped Water Supply Scheme (SM/13428) | SM/13428 | 267.54 | 500 | AUGMENTATION | 3 | Delayed | 41 | 02/11/2022 | 31/03/2024 | 27/12/2023 | 15/06/2023 | 110.96 | 110.96
89 | Augmentation of Arjunmahal Piped Water Supply Scheme (SM/13395) | SM/13395 | 271.14 | 348 | AUGMENTATION | 3 | Delayed | 24 | 19/10/2022 | 31/03/2024 | 10/10/2023 | 05/06/2023 | 64.34 | 64.34
90 | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) (SM/18321) | SM/18321 | 1713.48 | 3721 | NEW | 3 | Delayed | 8 | 27/06/2023 | 27/06/2025 | 01/02/2024 | 28/07/2022 | 134.29 | 134.29
91 | LOHASING PIPED WATER SUPPLY SCHEME (SM/15926) | SM/15926 | 352.69 | 847 | NEW | 3 | Delayed | 4 | 22/02/2023 | 31/12/2024 | 27/12/2023 | 25/07/2022 | 14.54 | 14.54
92 | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME (SM/18386) | SM/18386 | 1249.24 | 951 | AUGMENTATION | 3 | Delayed | 12 | 11/07/2023 | 31/03/2025 | 01/02/2024 | 10/08/2023 | 144.38 | 144.38
93 | KASHIRAM PIPED WATER SUPPLY SCHEME (SM/18613) | SM/18613 | 1079.19 | 3355 | NEW | 3 | Delayed | 34 | 31/07/2023 | 31/07/2025 | 01/02/2024 | 18/08/2023 | 362.79 | 362.79
94 | BARA GHARIA PIPED WATER SUPLY SCHEME (SM/11774) | SM/11774 | 452.96 | 1086 | NEW | 3 | Delayed | 10 | 03/08/2022 | 31/12/2024 | 28/05/2024 | 01/06/2022 | 45.06 | 45.06
95 | DEBIGANJA PIPED WATER SUPPLY SCHEME (SM/15925) | SM/15925 | 610.74 | 1748 | NEW | 4 | Delayed | 9 | 22/02/2023 | 31/12/2024 | 30/07/2024 | 17/05/2022 | 55.47 | 55.47
96 | JOGIBHITA PIPED WATER SUPPLY SCHEME (SM/15928) | SM/15928 | 368.86 | 867 | NEW | 4 | Delayed | 6 | 22/02/2023 | 31/03/2025 | 16/02/2024 | 28/07/2022 | 20.8 | 20.8
97 | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) (SM/16753) | SM/16753 | 890.47 | 2155 | NEW | 4 | Delayed | 41 | 13/03/2023 | 31/03/2025 | 01/02/2024 | 12/05/2022 | 367.59 | 367.51
98 | M.M.TERAI PIPED WATER SUPPLY SCHEME (SM/11775) | SM/11775 | 157.45 | 350 | NEW | 5 | Delayed | 14 | 03/08/2022 | 31/03/2025 | 27/01/2024 | 22/12/2021 | 22.75 | 22.75
99 | LATPANICHAR PIPED WATER SUPPLY SCHEME (SM/16162) | SM/16162 | 268.11 | 172 | NEW | 5 | Delayed | 27 | 22/02/2023 | 22/08/2024 | 06/12/2023 | 28/04/2023 | 73.36 | 73.36
100 | MANEDARA PIPED WATER SUPPLY SCHEME. (SM/15885) | SM/15885 | 485.98 | 347 | NEW | 5 | Delayed | 55 | 20/02/2023 | 31/12/2023 | 03/08/2023 | 07/06/2023 | 268.86 | 268.86
101 | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (SM/16385) | SM/16385 | 556.38 | 445 | NEW | 5 | Delayed | 71 | 28/02/2023 | 31/01/2024 | 03/08/2023 | 12/07/2023 | 397 | 397
102 | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) (SM/18614) | SM/18614 | 1017.38 | 1748 | NEW | 5 | Delayed | 12 | 31/07/2023 | 31/07/2025 | 17/11/2023 | 08/09/2023 | 121.53 | 121.53
103 | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/18282) | SM/18282 | 1545.44 | 1124 | NEW | 5 | Delayed | 12 | 23/06/2023 | 23/06/2025 | 06/12/2023 | 18/07/2023 | 192.48 | 192.48
104 | HUM TUKDAH KHASMAHAL PWSS (SM/18316) | SM/18316 | 1456.69 | 1616 | NEW | 5 | Delayed | 65 | 26/06/2023 | 31/01/2024 | 03/08/2023 | 12/07/2023 | 952.82 | 952.82
105 | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME (SM/11773) | SM/11773 | 449.92 | 1213 | NEW | 6 | Delayed | 14 | 03/08/2022 | 31/12/2024 | 06/05/2024 | 28/06/2022 | 61.53 | 61.53
106 | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME (SM/15271) | SM/15271 | 148.34 | 0 | AUGMENTATION | 6 | Delayed | 9 | 07/02/2023 | 31/03/2025 | 11/06/2024 | 15/06/2023 | 13.54 | 13.54
107 | RUPSING PIPED WATER SUPPLY SCHEME (SM/11776) | SM/11776 | 386.83 | 1035 | NEW | 6 | Delayed | 15 | 03/08/2022 | 31/12/2024 | 04/06/2024 | 28/06/2022 | 56.37 | 56.37
108 | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME (SM/12035) | SM/12035 | 117.92 | 538 | AUGMENTATION | 6 | Delayed | 4 | 01/09/2022 | 31/03/2025 | 01/02/2024 | 08/05/2023 | 4.56 | 4.56
109 | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME (SM/10476) | SM/10476 | 807.68 | 3189 | AUGMENTATION | 7 | Delayed | 27 | 13/04/2022 | 31/03/2025 | 16/02/2024 | 21/04/2022 | 217.84 | 217.84
110 | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme (SM/13392) | SM/13392 | 294.72 | 332 | AUGMENTATION | 7 | Delayed | 54 | 19/10/2022 | 31/12/2024 | 18/04/2024 | 14/07/2023 | 158.98 | 144.15
111 | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME (SM/15273) | SM/15273 | 188.14 | 0 | AUGMENTATION | 7 | Delayed | 5 | 07/02/2023 | 31/12/2024 | 11/06/2024 | 21/09/2023 | 8.74 | 8.74
112 | HETMURI PIPED WATER SUPPLY SCHEME (SM/12750) | SM/12750 | 754.32 | 1794 | NEW | 7 | Delayed | 10 | 20/09/2022 | 31/03/2025 | 01/12/2024 | 26/05/2022 | 73.12 | 73.12
113 | PANTHABARI FOREST Piped Water Supply Scheme (SM/16143) | SM/16143 | 142.59 | 134 | NEW | 7 | Delayed | 65 | 22/02/2023 | 22/08/2024 | 09/01/2024 | 17/04/2023 | 92.71 | 92.71
114 | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME (SM/11777) | SM/11777 | 164.44 | 652 | NEW | 8 | Delayed | 7 | 03/08/2022 | 31/03/2025 | 20/02/2024 | 20/05/2022 | 11.25 | 11.25
115 | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME (SM/12807) | SM/12807 | 649.84 | 630 | AUGMENTATION | 8 | Delayed | 22 | 20/09/2022 | 31/03/2025 | 02/05/2024 | 15/06/2023 | 141.72 | 141.72
116 | Piped water supply scheme for Lower Bish Acre, Ghayabari. (SM/11397) | SM/11397 | 69.47 | 80 | NEW | 8 | Delayed | 55 | 04/07/2022 | 04/01/2024 | 12/06/2023 | 01/11/2022 | 38.2 | 38.2
117 | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME (SM/15272) | SM/15272 | 106.93 | 0 | AUGMENTATION | 8 | Delayed | 14 | 07/02/2023 | 31/03/2025 | 01/02/2024 | 10/08/2023 | 15.39 | 15.39
118 | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) (SM/15929) | SM/15929 | 741.26 | 1966 | NEW | 9 | Delayed | 21 | 22/02/2023 | 31/03/2025 | 02/05/2024 | 28/07/2022 | 156.54 | 156.54
119 | DARJEELING PULBAZAR PUMPING-II PWSS (SM/18659) | SM/18659 | 8823.99 | 2169 | NEW | 9 | Delayed | 0 | 04/08/2023 | 04/02/2026 | 24/07/2024 |  | 30.87 | 30.87
120 | PWS Scheme for Tindharia & Nurbang Tea Garden (SM/18649) | SM/18649 | 1203.19 | 843 | NEW | 9 | Delayed | 67 | 31/07/2023 | 31/07/2025 | 15/02/2024 | 11/08/2023 | 805.52 | 805.52
121 | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME (SM/15647) | SM/15647 | 656.45 | 1036 | NEW | 9 | Delayed | 3 | 17/02/2023 | 17/08/2024 | 02/07/2024 | 23/03/2023 | 20.37 | 20.37
122 | SUKNA PIPED WATER SUPPLY SCHEME (SM/15653) | SM/15653 | 304.63 | 402 | NEW | 9 | Delayed | 5 | 17/02/2023 | 17/08/2024 | 02/07/2024 | 23/03/2023 | 16.46 | 16.46
123 | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME (SM/10714) | SM/10714 | 849.31 | 381 | AUGMENTATION | 9 | Delayed | 36 | 18/05/2022 | 30/06/2024 | 14/12/2023 | 22/12/2021 | 301.51 | 301.51
124 | PANIGHATA Piped Water Supply Scheme (SM/16144) | SM/16144 | 363.69 | 1222 | NEW | 9 | Delayed | 34 | 22/02/2023 | 22/08/2024 | 20/01/2024 | 28/04/2023 | 123.39 | 123.39
125 | MAHANADI FOREST PIPED WATER SUPPLY SCHEME (SM/15648) | SM/15648 | 230 | 191 | NEW | 9 | Delayed | 8 | 17/02/2023 | 17/08/2024 | 16/10/2023 | 07/06/2023 | 19.26 | 19.26
126 | PWS scheme for St. Mary's & Goethals (SM/15661) | SM/15661 | 338.76 | 675 | NEW | 9 | Delayed | 3 | 17/02/2023 | 17/08/2024 | 16/10/2023 | 01/03/2023 | 9.87 | 7.35
127 | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme (SM/13394) | SM/13394 | 319.83 | 631 | AUGMENTATION | 9 | Delayed | 30 | 19/10/2022 | 31/03/2024 | 06/10/2023 | 16/06/2023 | 96.98 | 96.98
128 | Piped water supply scheme for Singtam Tea Garden (SM/11338) | SM/11338 | 176.87 | 485 | NEW | 10 | Delayed | 69 | 13/06/2022 | 24/03/2024 | 29/09/2023 | 12/07/2023 | 121.76 | 121.76
129 | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme (SM/13433) | SM/13433 | 587.76 | 1363 | AUGMENTATION | 10 | Delayed | 31 | 02/11/2022 | 31/01/2025 | 02/05/2024 | 25/07/2023 | 184.36 | 184.36
130 | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. (SM/18638) | SM/18638 | 1513.58 | 637 | NEW | 10 | Delayed | 60 | 31/07/2023 | 31/07/2025 | 16/10/2023 | 11/08/2023 | 910.59 | 910.59
131 | DARJEELING PULBAZAR PUMPING-III PWSS (SM/18792) | SM/18792 | 7379.87 | 1620 | NEW | 10 | Delayed | 0 | 07/09/2023 | 07/03/2026 | 29/11/2024 | 11/09/2024 | 11.02 | 9.98
132 | CONSTRUCTION OF SOURCE AND OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SONADA TO ACCOMODATE TWO MOUZAS MAINLY SONADA FOREST & SONADA KHASMAHAL UNDER SUKHIA POKHARI BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, PHED. (SM/19039) | SM/19039 | 2250.46 | 2100 | NEW | 10 | Delayed | 0 | 17/11/2023 | 31/03/2025 | 20/11/2024 | 31/07/2024 | 1.12 | 0
133 | Nichitpur Piped Water Supply Scheme (SM/13438) | SM/13438 | 184.33 | 209 | NEW | 10 | Delayed | 44 | 02/11/2022 | 31/01/2025 | 15/01/2024 | 15/06/2023 | 81.29 | 81.29
134 | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/13959) | SM/13959 | 228.01 | 165 | NEW | 10 | Delayed | 2 | 01/12/2022 | 01/06/2024 | 16/10/2023 | 07/02/2023 | 3.96 | 3.96
135 | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME (SM/13439) | SM/13439 | 92.86 | 153 | NEW | 10 | Delayed | 18 | 02/11/2022 | 31/12/2024 | 16/05/2024 | 20/05/2022 | 17.07 | 17.07
136 | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/16161) | SM/16161 | 322.85 | 393 | NEW | 10 | Delayed | 1 | 22/02/2023 | 22/08/2024 | 29/09/2023 | 28/04/2023 | 2.42 | 2.42
137 | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) (SM/15892) | SM/15892 | 161.01 | 133 | NEW | 10 | Delayed | 3 | 20/02/2023 | 20/08/2024 | 18/01/2024 | 28/04/2023 | 5.08 | 5.08
138 | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail (SM/11305) | SM/11305 | 14.68 | 60 | RETROFITTING | 10 | Delayed | 96 | 13/06/2022 | 31/03/2024 | 29/02/2024 | 30/06/2022 | 14.05 | 14.05
139 | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/13960) | SM/13960 | 300.61 | 349 | NEW | 10 | Delayed | 49 | 01/12/2022 | 01/06/2024 | 16/10/2023 | 07/02/2023 | 145.84 | 145.84
140 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/14149) | SM/14149 | 1893.19 | 946 | NEW | 10 | Delayed | 54 | 05/01/2023 | 05/01/2025 | 16/10/2023 | 15/02/2023 | 1030.59 | 1030.59
141 | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. (SM/13955) | SM/13955 | 237.69 | 241 | NEW | 10 | Delayed | 3 | 01/12/2022 | 31/03/2025 | 28/11/2024 | 20/01/2023 | 6.06 | 1.48
142 | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME (SM/15894) | SM/15894 | 295.85 | 259 | NEW | 10 | Delayed | 1 | 20/02/2023 | 31/03/2025 | 16/12/2024 | 28/04/2023 | 1.59 | 1.59
143 | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE (SM/18588) | SM/18588 | 3308.68 | 2153 | NEW | 10 | Delayed | 16 | 31/07/2023 | 31/07/2025 | 19/03/2024 | 11/08/2023 | 534.78 | 534.78
144 | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden (SM/18640) | SM/18640 | 1208.42 | 886 | NEW | 10 | Delayed | 44 | 31/07/2023 | 31/07/2025 | 16/10/2023 | 03/08/2023 | 537.06 | 537.06
145 | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. (SM/11344) | SM/11344 | 32.23 | 120 | NEW | 10 | Delayed | 53 | 28/06/2022 | 31/03/2024 | 18/01/2024 | 24/06/2020 | 17.12 | 17.12
146 | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME (SM/16159) | SM/16159 | 307.56 | 55 | NEW | 10 | Delayed | 44 | 22/02/2023 | 22/08/2024 | 29/09/2023 | 05/06/2023 | 134.94 | 134.94
147 | LODHAMA PIPED WATER SUPPLY SCHEME. (SM/15872) | SM/15872 | 178.54 | 45 | NEW | 10 | Delayed | 0 | 20/02/2023 | 31/12/2023 | 29/09/2023 | 27/04/2023 | 0.45 | 0.45
148 | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) (SM/14150) | SM/14150 | 1709.08 | 3674 | NEW | 11 | Delayed | 12 | 05/01/2023 | 31/12/2025 | 21/06/2024 | 28/07/2022 | 197.09 | 197.09
149 | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME (SM/12799) | SM/12799 | 484.93 | 1334 | AUGMENTATION | 12 | Delayed | 34 | 20/09/2022 | 31/03/2025 | 29/02/2024 | 02/08/2023 | 167.2 | 167.2
150 | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME (SM/14846) | SM/14846 | 847.7 | 2363 | NEW | 13 | Delayed | 14 | 03/02/2023 | 31/12/2025 | 21/06/2024 | 18/05/2022 | 118.01 | 118.01
151 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Dhakpara village of Budharugaon Piped water Supply Scheme (SM/07214) | SM/07214 | 55.85 | 751 | RETROFITTING | 15 | Delayed | 1 | 08/12/2020 | 31/03/2025 | 04/12/2024 | 28/06/2024 | 0.63 | 0
152 | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. (SM/15878) | SM/15878 | 277.07 | 384 | NEW | 15 | Delayed | 30 | 20/02/2023 | 15/02/2024 | 29/09/2023 | 28/04/2023 | 83.12 | 83.12
153 | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA (SM/10809) | SM/10809 | 115.19 | 99 | NEW | 15 | Delayed | 24 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 10/01/2023 | 27.2 | 27.2
154 | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME (SM/10026) | SM/10026 | 1323.79 | 4923 | AUGMENTATION | 15 | Delayed | 22 | 05/01/2022 | 31/03/2025 | 14/03/2024 | 21/03/2022 | 287.07 | 287.07
155 | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/11942) | SM/11942 | 233.67 | 286 | NEW | 15 | Delayed | 45 | 24/08/2022 | 24/02/2024 | 12/06/2023 | 24/02/2023 | 105.39 | 105.39
156 | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME (SM/18421) | SM/18421 | 1259.04 | 921 | AUGMENTATION | 15 | Delayed | 30 | 18/07/2023 | 31/03/2025 | 01/12/2024 | 28/07/2023 | 380.11 | 347.58
157 | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME (SM/15270) | SM/15270 | 148.87 | 0 | AUGMENTATION | 16 | Delayed | 45 | 07/02/2023 | 31/12/2024 | 31/05/2024 | 22/09/2023 | 66.79 | 66.79
158 | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/12749) | SM/12749 | 335.45 | 838 | AUGMENTATION | 17 | Delayed | 57 | 20/09/2022 | 31/03/2024 | 27/12/2023 | 02/03/2023 | 189.79 | 189.79
159 | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME (SM/14835) | SM/14835 | 98.37 | 92 | AUGMENTATION | 17 | Delayed | 25 | 03/02/2023 | 31/12/2024 | 16/05/2024 | 09/08/2023 | 24.64 | 24.64
160 | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA (SM/10802) | SM/10802 | 228.59 | 3231 | NEW | 18 | Delayed | 21 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 26/05/2022 | 47.13 | 47.13
161 | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME (SM/15274) | SM/15274 | 194.82 | 0 | AUGMENTATION | 18 | Delayed | 21 | 07/02/2023 | 31/03/2025 | 20/09/2024 | 03/10/2023 | 41.56 | 41.56
162 | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME (SM/11785) | SM/11785 | 165.38 | 216 | NEW | 19 | Delayed | 11 | 03/08/2022 | 31/12/2024 | 27/05/2024 | 28/06/2022 | 18.99 | 18.99
163 | Mandila Jhar Piped Water Supply Scheme. (SM/18784) | SM/18784 | 623.79 | 1541 | NEW | 20 | Delayed | 47 | 29/08/2023 | 31/03/2025 | 06/08/2024 | 03/10/2023 | 294.65 | 294.65
164 | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME (SM/12034) | SM/12034 | 197.56 | 239 | AUGMENTATION | 20 | Delayed | 10 | 01/09/2022 | 31/12/2024 | 04/10/2024 | 17/08/2023 | 19.18 | 19.18
165 | Sona Chandi Piped Water Supply Scheme (SM/13436) | SM/13436 | 216.92 | 415 | NEW | 20 | Delayed | 18 | 02/11/2022 | 31/03/2025 | 21/06/2024 | 17/08/2023 | 38.03 | 38.03
166 | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME (SM/10724) | SM/10724 | 1047.38 | 982 | AUGMENTATION | 22 | Delayed | 44 | 18/05/2022 | 31/01/2025 | 23/09/2024 | 29/03/2022 | 459.13 | 459.13
167 | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME (SM/15269) | SM/15269 | 189.49 | 0 | AUGMENTATION | 23 | Delayed | 45 | 07/02/2023 | 31/01/2025 | 27/02/2024 | 08/05/2023 | 85.15 | 85.15
168 | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME (SM/13467) | SM/13467 | 647.04 | 194 | AUGMENTATION | 24 | Delayed | 27 | 02/11/2022 | 31/03/2025 | 21/06/2024 | 15/06/2023 | 177.46 | 177.46
169 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin (SM/09078) | SM/09078 | 23.31 | 398 | RETROFITTING | 25 | Delayed | 63 | 28/10/2021 | 30/06/2025 | 20/11/2024 | 20/07/2022 | 14.74 | 14.74
170 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ranidanga & Shaibhita village of Ranidanga-Rangapani Piped water Supply Scheme (SM/07036) | SM/07036 | 79.26 | 1470 | RETROFITTING | 25 | Delayed | 2 | 24/11/2020 | 31/03/2025 | 27/09/2024 | 23/02/2023 | 1.82 | 1.82
171 | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME (SM/18385) | SM/18385 | 2394.79 | 5785 | AUGMENTATION | 27 | Delayed | 27 | 11/07/2023 | 31/03/2025 | 25/09/2024 | 26/07/2023 | 646.34 | 645.12
172 | LOHAGARH WATER SUPPLY SCHEME (SM/09426) | SM/09426 | 170.07 | 430 | NEW | 28 | Delayed | 31 | 17/11/2021 | 17/05/2023 | 12/06/2023 | 14/01/2022 | 53.02 | 53.02
173 | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING (SM/11856) | SM/11856 | 290.75 | 100 | NEW | 28 | Delayed | 67 | 16/08/2022 | 29/03/2024 | 04/01/2024 | 12/07/2023 | 194.43 | 194.43
174 | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME (SM/12773) | SM/12773 | 513.64 | 408 | AUGMENTATION | 29 | Delayed | 52 | 20/09/2022 | 30/06/2024 | 18/12/2023 | 14/07/2023 | 267.89 | 267.26
175 | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME (SM/18637) | SM/18637 | 1581.9 | 680 | AUGMENTATION | 29 | Delayed | 30 | 31/07/2023 | 31/03/2025 | 27/03/2024 | 16/08/2023 | 471.38 | 471.38
176 | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA (SM/10798) | SM/10798 | 226.19 | 233 | NEW | 30 | Delayed | 0 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 01/11/2022 | 1.04 | 1.04
177 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis (SM/11322) | SM/11322 | 14.74 | 174 | RETROFITTING | 30 | Delayed | 7 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 24/06/2020 | 1.07 | 1.07
178 | Khoklong Piped Water Supply Scheme (SM/13437) | SM/13437 | 187.01 | 175 | NEW | 30 | Delayed | 23 | 02/11/2022 | 02/05/2024 | 17/11/2023 | 27/07/2023 | 43.18 | 43.18
179 | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/12751) | SM/12751 | 629.15 | 1023 | NEW | 30 | Delayed | 32 | 20/09/2022 | 31/03/2025 | 07/05/2024 | 26/05/2022 | 199.9 | 199.9
180 | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme (SM/13391) | SM/13391 | 417.78 | 803 | AUGMENTATION | 30 | Delayed | 66 | 19/10/2022 | 31/03/2025 | 01/02/2024 | 05/06/2023 | 275 | 274.94
181 | Augmentation of Rangali Piped Water Supply Scheme (SM/13429) | SM/13429 | 347.93 | 604 | AUGMENTATION | 30 | Delayed | 60 | 02/11/2022 | 31/03/2024 | 25/08/2023 | 24/03/2023 | 210.23 | 210.12
182 | Providing functional Household tap connection from existing PWSS at Khaling dhura & Vah Tukbar( Bhutta Kheti) (SM/13352) | SM/13352 | 62.01 | 249 | RETROFITTING | 30 | Delayed | 0 | 19/10/2022 | 30/01/2024 | 29/09/2023 | 03/11/2022 | 0 | 0
183 | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) (SM/13509) | SM/13509 | 608.67 | 920 | NEW | 30 | Delayed | 57 | 02/11/2022 | 31/03/2025 | 22/03/2024 | 15/06/2023 | 345.6 | 345.6
184 | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME (SM/10469) | SM/10469 | 647.25 | 2165 | AUGMENTATION | 32 | Delayed | 64 | 13/04/2022 | 31/01/2025 | 22/05/2024 | 21/04/2022 | 413.68 | 413.68
185 | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME (SM/15924) | SM/15924 | 858.49 | 803 | AUGMENTATION | 33 | Delayed | 46 | 22/02/2023 | 31/12/2025 | 21/06/2024 | 10/08/2023 | 396.73 | 396.73
186 | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME (SM/12038) | SM/12038 | 119.17 | 200 | AUGMENTATION | 34 | Delayed | 52 | 01/09/2022 | 31/03/2024 | 03/10/2023 | 17/02/2023 | 62.37 | 62.37
187 | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME (SM/10108) | SM/10108 | 640.28 | 3735 | AUGMENTATION | 34 | Delayed | 76 | 02/02/2022 | 31/03/2025 | 15/03/2024 | 13/08/2021 | 488.9 | 488.89
188 | RELLING PIPED WATER SUPPLY SCHEME. (SM/15879) | SM/15879 | 937.57 | 643 | NEW | 35 | Delayed | 33 | 20/02/2023 | 20/02/2024 | 29/09/2023 | 06/06/2023 | 308.98 | 308.98
189 | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10817) | SM/10817 | 379.09 | 989 | NEW | 35 | Delayed | 21 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 30/06/2022 | 79.65 | 79.65
190 | BIJANBARI PIPED WATER SUPPLY SCHEME. (SM/15869) | SM/15869 | 357.73 | 298 | NEW | 35 | Delayed | 46 | 20/02/2023 | 31/12/2023 | 29/09/2023 | 27/04/2023 | 165.14 | 165.14
191 | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME (SM/11786) | SM/11786 | 669.61 | 1763 | NEW | 36 | Delayed | 45 | 03/08/2022 | 31/12/2024 | 30/04/2024 | 26/05/2022 | 300.29 | 300.27
192 | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. (SM/14517) | SM/14517 | 2399.99 | 10542 | AUGMENTATION | 36 | Delayed | 38 | 30/01/2023 | 31/03/2025 | 01/02/2024 | 02/08/2023 | 913.75 | 913.75
193 | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME (SM/14834) | SM/14834 | 111.08 | 0 | AUGMENTATION | 38 | Delayed | 30 | 03/02/2023 | 31/12/2024 | 20/09/2024 | 15/06/2023 | 33.29 | 33.29
194 | MAJUA PIPED WATER SUPPLY SCHEME. (SM/15874) | SM/15874 | 301.04 | 175 | NEW | 40 | Delayed | 78 | 20/02/2023 | 20/08/2024 | 29/09/2023 | 28/04/2023 | 234.97 | 234.97
195 | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (SM/15897) | SM/15897 | 560.14 | 563 | NEW | 40 | Delayed | 89 | 20/02/2023 | 31/03/2024 | 11/09/2023 | 05/06/2023 | 501.17 | 501.17
196 | CHEGRA KHASMAHAL Piped Water Supply Scheme (SM/16141) | SM/16141 | 335.44 | 237 | NEW | 40 | Delayed | 75 | 22/02/2023 | 22/08/2024 | 04/01/2024 | 04/05/2023 | 251.27 | 251.27
197 | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND (SM/10470) | SM/10470 | 701.4 | 975 | NEW | 40 | Delayed | 58 | 13/04/2022 | 31/12/2023 | 12/06/2023 | 08/07/2022 | 405.38 | 405.38
198 | BLOOMFIELD TEA GARDEN PWSS (SM/15910) | SM/15910 | 447.08 | 556 | NEW | 40 | Delayed | 47 | 20/02/2023 | 20/08/2024 | 29/09/2023 | 18/07/2023 | 211.49 | 211.49
199 | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. (SM/12983) | SM/12983 | 1217.59 | 1341 | NEW | 40 | Delayed | 49 | 28/09/2022 | 28/09/2024 | 20/09/2023 | 06/02/2023 | 596.23 | 596.23
200 | BARBATIA KHASMAHAL PWSS (SM/18189) | SM/18189 | 404.81 | 147 | NEW | 40 | Delayed | 12 | 30/03/2023 | 30/09/2024 | 29/09/2023 | 04/05/2023 | 50.09 | 50.09
201 | DANGIA PIPED WATER SUPPLY SCHEME (SM/15896) | SM/15896 | 524.85 | 484 | NEW | 40 | Delayed | 27 | 20/02/2023 | 31/12/2023 | 29/09/2023 | 04/05/2023 | 140.46 | 140.46
202 | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME (SM/16160) | SM/16160 | 237.91 | 196 | NEW | 40 | Delayed | 40 | 22/02/2023 | 22/08/2024 | 29/09/2023 | 28/04/2023 | 94.45 | 94.45
203 | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/18317) | SM/18317 | 1246.59 | 955 | NEW | 41 | Delayed | 80 | 26/06/2023 | 26/06/2025 | 21/09/2023 | 12/07/2023 | 994.12 | 846.33
204 | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME (SM/10025) | SM/10025 | 1506.6 | 5380 | AUGMENTATION | 41 | Delayed | 40 | 05/01/2022 | 31/03/2024 | 28/12/2023 | 21/03/2022 | 604.49 | 604.49
205 | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/14528) | SM/14528 | 1138.22 | 790 | NEW | 41 | Delayed | 48 | 30/01/2023 | 30/01/2025 | 16/10/2023 | 10/05/2023 | 551.08 | 551.08
206 | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. (SM/09828) | SM/09828 | 613.39 | 100 | AUGMENTATION | 42 | Delayed | 65 | 02/12/2021 | 31/03/2024 | 18/08/2023 | 21/03/2022 | 399.96 | 399.96
207 | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/18634) | SM/18634 | 1305.54 | 1128 | NEW | 43 | Delayed | 55 | 31/07/2023 | 31/07/2025 | 15/12/2023 | 07/08/2023 | 714.52 | 714.52
208 | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/18601) | SM/18601 | 2696.35 | 2294 | NEW | 44 | Delayed | 91 | 31/07/2023 | 31/07/2025 | 06/10/2023 | 03/08/2023 | 2464.07 | 2464.07
209 | Augmentation of Buraganja & Jatru Piped Water Supply Scheme (SM/13393) | SM/13393 | 339.93 | 393 | AUGMENTATION | 44 | Delayed | 73 | 19/10/2022 | 31/12/2024 | 21/06/2024 | 08/05/2023 | 249.5 | 249.5
210 | Pathar Hirhirar Chhat Piped Water Supply Scheme (SM/13508) | SM/13508 | 563.65 | 1391 | NEW | 44 | Delayed | 56 | 02/11/2022 | 31/12/2024 | 30/04/2024 | 09/06/2022 | 313.21 | 313.21
211 | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/16628) | SM/16628 | 870.77 | 643 | NEW | 44 | Delayed | 54 | 14/03/2023 | 14/09/2024 | 08/11/2023 | 28/04/2023 | 470.69 | 470.69
212 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme (SM/07034) | SM/07034 | 64.86 | 1032 | RETROFITTING | 45 | Delayed | 18 | 24/11/2020 | 31/03/2025 | 23/09/2024 | 11/01/2023 | 11.74 | 11.74
213 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for mahipal and Bandargachh village of Bandargachh Piped water Supply Scheme (SM/07042) | SM/07042 | 81.93 | 1307 | RETROFITTING | 45 | Delayed | 22 | 24/11/2020 | 31/03/2025 | 31/07/2024 | 14/08/2020 | 18.35 | 18.35
214 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme (SM/07038) | SM/07038 | 89.15 | 1583 | RETROFITTING | 45 | Delayed | 27 | 24/11/2020 | 31/12/2024 | 12/06/2024 | 03/08/2021 | 24.3 | 24.3
215 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Rajajhar & Rangapani village of Ranidanga-Rangapani Piped water Supply Scheme (SM/07037) | SM/07037 | 76.12 | 1403 | RETROFITTING | 45 | Delayed | 7 | 24/11/2020 | 31/03/2025 | 27/03/2024 | 14/08/2020 | 5.12 | 5.12
216 | PWS Scheme for Edenvale Tea Garden (SM/18710) | SM/18710 | 150.23 | 108 | NEW | 45 | Delayed | 77 | 04/08/2023 | 04/02/2025 | 13/10/2023 | 07/08/2023 | 115.52 | 115.52
217 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) (SM/07043) | SM/07043 | 71.82 | 1370 | RETROFITTING | 45 | Delayed | 69 | 24/11/2020 | 31/08/2024 | 15/02/2024 | 18/12/2020 | 49.82 | 49.82
218 | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA (SM/11396) | SM/11396 | 234.66 | 106 | NEW | 45 | Delayed | 44 | 04/07/2022 | 31/12/2023 | 12/07/2023 | 01/11/2022 | 104.17 | 104.17
219 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme (SM/07030) | SM/07030 | 93.81 | 1597 | RETROFITTING | 45 | Delayed | 62 | 13/11/2020 | 31/03/2025 | 27/03/2024 | 11/12/2020 | 58.56 | 58.56
220 | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/16532) | SM/16532 | 1658.37 | 1274 | NEW | 45 | Delayed | 54 | 10/03/2023 | 10/03/2025 | 25/01/2024 | 04/05/2023 | 896.27 | 896.27
221 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) (SM/07049) | SM/07049 | 98.65 | 1825 | RETROFITTING | 45 | Delayed | 63 | 24/11/2020 | 31/05/2024 | 25/01/2024 | 11/12/2020 | 62.28 | 62.28
222 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme (SM/07035) | SM/07035 | 62.07 | 1032 | RETROFITTING | 45 | Delayed | 75 | 24/11/2020 | 31/03/2025 | 27/03/2024 | 02/08/2021 | 46.46 | 46.46
223 | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/16145) | SM/16145 | 442.66 | 346 | NEW | 45 | Delayed | 83 | 22/02/2023 | 22/08/2024 | 04/10/2023 | 12/07/2023 | 369.27 | 369.27
224 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/16534) | SM/16534 | 1531.5 | 389 | NEW | 45 | Delayed | 54 | 10/03/2023 | 10/03/2025 | 01/03/2024 | 17/10/2023 | 832.04 | 831.64
225 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme (SM/07216) | SM/07216 | 61.95 | 399 | RETROFITTING | 46 | Delayed | 38 | 08/12/2020 | 31/12/2024 | 05/06/2024 | 03/08/2021 | 23.8 | 23.8
226 | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/14147) | SM/14147 | 1120.63 | 960 | NEW | 46 | Delayed | 66 | 05/01/2023 | 05/01/2025 | 05/10/2023 | 28/04/2023 | 737.6 | 737.6
227 | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME (SM/10183) | SM/10183 | 1681.3 | 8610 | AUGMENTATION | 46 | Delayed | 70 | 17/02/2022 | 31/03/2024 | 08/08/2023 | 13/08/2021 | 1183.26 | 1183.25
228 | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. (SM/15650) | SM/15650 | 210.61 | 229 | NEW | 46 | Delayed | 61 | 17/02/2023 | 17/08/2024 | 28/05/2024 | 28/02/2023 | 127.76 | 127.76
229 | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) (SM/15649) | SM/15649 | 611 | 348 | NEW | 47 | Delayed | 76 | 17/02/2023 | 17/08/2024 | 15/03/2024 | 17/10/2023 | 464.46 | 464.46
230 | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME (SM/10097) | SM/10097 | 913.6 | 5725 | AUGMENTATION | 47 | Delayed | 59 | 01/02/2022 | 31/12/2023 | 19/07/2023 | 20/07/2022 | 539.02 | 539.02
231 | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA (SM/10829) | SM/10829 | 167.48 | 269 | NEW | 47 | Delayed | 13 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 05/08/2022 | 21.54 | 21.54
232 | RANGMOHAN PIPED WATER SUPPLY SCHEME (SM/15880) | SM/15880 | 327.7 | 172 | NEW | 47 | Delayed | 63 | 20/02/2023 | 20/08/2024 | 11/01/2024 | 01/03/2023 | 207.45 | 207.45
233 | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/12748) | SM/12748 | 255.93 | 598 | AUGMENTATION | 47 | Delayed | 54 | 20/09/2022 | 31/03/2024 | 11/10/2023 | 10/11/2022 | 139.24 | 139.24
234 | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT (SM/16627) | SM/16627 | 954.9 | 854 | NEW | 47 | Delayed | 55 | 14/03/2023 | 14/09/2024 | 11/03/2024 | 10/05/2023 | 521.35 | 521.35
235 | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/16629) | SM/16629 | 610.28 | 333 | NEW | 47 | Delayed | 56 | 14/03/2023 | 14/09/2024 | 20/03/2024 | 28/04/2023 | 343.42 | 343.42
236 | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/18633) | SM/18633 | 1443.98 | 1243 | NEW | 47 | Delayed | 66 | 31/07/2023 | 31/07/2025 | 06/10/2023 | 03/08/2023 | 946.12 | 946.12
237 | PWS Scheme for Sepoy Dhura Tea Garden (SM/15651) | SM/15651 | 525.04 | 378 | NEW | 48 | Delayed | 31 | 17/02/2023 | 17/08/2024 | 17/05/2024 | 02/03/2023 | 161.46 | 161.46
238 | PWS Scheme for Sevok Hill Forest area under Kurseong Block. (SM/15895) | SM/15895 | 496.03 | 598 | NEW | 48 | Delayed | 18 | 20/02/2023 | 20/08/2024 | 11/03/2024 | 06/06/2023 | 91.36 | 91.36
239 | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) (SM/18647) | SM/18647 | 3828.95 | 4639 | NEW | 48 | Delayed | 46 | 31/07/2023 | 31/07/2025 | 04/10/2023 | 11/08/2023 | 1747.52 | 1747.52
240 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/16533) | SM/16533 | 1182.41 | 936 | NEW | 48 | Delayed | 57 | 10/03/2023 | 10/03/2025 | 04/10/2023 | 28/04/2023 | 670.76 | 670.76
241 | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE (SM/18639) | SM/18639 | 1969.93 | 1896 | NEW | 48 | Delayed | 29 | 31/07/2023 | 31/07/2025 | 13/10/2023 | 11/08/2023 | 566.44 | 566.44
242 | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) (SM/18648) | SM/18648 | 2338.45 | 1564 | NEW | 48 | Delayed | 11 | 31/07/2023 | 31/07/2025 | 12/03/2024 | 11/08/2023 | 258.53 | 258.53
243 | PWS Scheme for Selim Hill Tea Garden (SM/15652) | SM/15652 | 967.91 | 384 | NEW | 48 | Delayed | 53 | 17/02/2023 | 17/08/2024 | 30/11/2023 | 09/03/2023 | 511.02 | 511.02
244 | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) (SM/18730) | SM/18730 | 3390 | 3257 | NEW | 48 | Delayed | 53 | 14/08/2023 | 14/08/2025 | 20/01/2024 | 10/10/2023 | 1805.38 | 1805.38
245 | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15655) | SM/15655 | 743.37 | 697 | NEW | 49 | Delayed | 70 | 17/02/2023 | 17/08/2024 | 09/10/2023 | 28/04/2023 | 520.07 | 520.07
246 | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST (SM/18559) | SM/18559 | 1470.02 | 768 | NEW | 49 | Delayed | 64 | 31/07/2023 | 31/07/2025 | 09/10/2023 | 11/08/2023 | 946.45 | 946.45
247 | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING (SM/18635) | SM/18635 | 1907.13 | 1938 | NEW | 49 | Delayed | 61 | 31/07/2023 | 31/07/2025 | 11/01/2024 | 03/08/2023 | 1167.37 | 1167.37
248 | PWS Scheme for Mirik Khasmahal (SM/18650) | SM/18650 | 1261.17 | 1306 | NEW | 49 | Delayed | 58 | 31/07/2023 | 31/07/2025 | 16/02/2024 | 11/08/2023 | 729.73 | 729.73
249 | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN (SM/18651) | SM/18651 | 1262.65 | 1170 | NEW | 49 | Delayed | 58 | 31/07/2023 | 31/07/2025 | 09/11/2023 | 11/08/2023 | 734.23 | 734.23
250 | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME (SM/09827) | SM/09827 | 870.41 | 2315 | AUGMENTATION | 49 | Delayed | 63 | 02/12/2021 | 31/12/2024 | 13/08/2024 | 21/03/2022 | 549.65 | 549.65
251 | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD (SM/18727) | SM/18727 | 1928.5 | 1682 | NEW | 49 | Delayed | 34 | 14/08/2023 | 14/08/2025 | 12/03/2024 | 23/08/2023 | 647.55 | 647.55
252 | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. (SM/18652) | SM/18652 | 1174.35 | 998 | NEW | 49 | Delayed | 12 | 31/07/2023 | 31/07/2025 | 24/05/2024 | 11/08/2023 | 139.53 | 139.53
253 | Providing functional household tap connection under Jal jeewan Mission/Jal swapno Mission for balance household at Fatingtar (SM/11384) | SM/11384 | 27.28 | 95 | RETROFITTING | 50 | Delayed | 73 | 04/07/2022 | 31/03/2024 | 25/01/2024 | 27/07/2023 | 20.01 | 20.01
254 | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme (SM/10818) | SM/10818 | 299.8 | 684 | NEW | 50 | Delayed | 20 | 25/05/2022 | 01/06/2024 | 23/02/2024 | 30/06/2022 | 60.22 | 60.22
255 | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Krishi kunj (SM/11308) | SM/11308 | 5.7 | 27 | RETROFITTING | 50 | Delayed | 96 | 13/06/2022 | 13/09/2022 | 12/06/2023 | 30/06/2022 | 5.48 | 5.48
256 | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. (SM/15909) | SM/15909 | 304.67 | 120 | NEW | 50 | Delayed | 72 | 20/02/2023 | 10/01/2024 | 29/09/2023 | 05/06/2023 | 219.32 | 119.3
257 | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme (SM/16384) | SM/16384 | 557.87 | 384 | NEW | 50 | Delayed | 69 | 28/02/2023 | 31/12/2023 | 06/10/2023 | 12/05/2023 | 385.02 | 385.02
258 | BARA MUNGWA PIPED WATER SUPPLY SCHEME (SM/15893) | SM/15893 | 476.33 | 358 | NEW | 50 | Delayed | 61 | 20/02/2023 | 20/08/2024 | 01/03/2024 | 07/06/2023 | 289.15 | 289.15
259 | LAMAGAON PIPED WATER SUPPLY SCHEME. (SM/15868) | SM/15868 | 752.32 | 628 | NEW | 50 | Delayed | 92 | 20/02/2023 | 31/12/2023 | 29/09/2023 | 10/05/2023 | 694.48 | 694.48
260 | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS (SM/17191) | SM/17191 | 879.54 | 1682 | NEW | 50 | Delayed | 12 | 15/03/2023 | 15/09/2024 | 01/03/2024 | 28/04/2023 | 103.94 | 103.94
261 | LEBONG & MINERAL TEA GARDEN PWSS (SM/18726) | SM/18726 | 1123.93 | 1242 | NEW | 50 | Delayed | 53 | 14/08/2023 | 14/08/2025 | 19/01/2024 | 17/08/2023 | 598.13 | 598.13
262 | KOLBONG KHASMAHAL PWSS (SM/15840) | SM/15840 | 214.49 | 143 | NEW | 50 | Delayed | 72 | 20/02/2023 | 20/08/2024 | 06/10/2023 | 04/05/2023 | 154.64 | 153.64
263 | RESHOP BAZAR PIPED WATER SUPPLY SCHEME (SM/15882) | SM/15882 | 423.41 | 181 | NEW | 50 | Delayed | 27 | 20/02/2023 | 20/08/2024 | 13/12/2023 | 28/04/2023 | 114.76 | 114.76
264 | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING (SM/18821) | SM/18821 | 1262.02 | 869 | NEW | 50 | Delayed | 25 | 11/09/2023 | 11/09/2025 | 28/05/2024 | 22/11/2023 | 315.8 | 315.8
265 | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam (SM/11393) | SM/11393 | 184.74 | 1398 | RETROFITTING | 50 | Delayed | 32 | 04/07/2022 | 31/03/2025 | 04/07/2024 | 12/07/2023 | 59.92 | 59.92
266 | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/13957) | SM/13957 | 451.2 | 175 | NEW | 50 | Delayed | 46 | 01/12/2022 | 01/06/2024 | 15/12/2023 | 20/01/2023 | 206.07 | 206.07
267 | RIMBICK Piped Water Supply Scheme (SM/16123) | SM/16123 | 716.55 | 450 | NEW | 50 | Delayed | 60 | 22/02/2023 | 22/08/2024 | 28/06/2024 | 12/07/2023 | 429.1 | 429.1
268 | GOKE PIPED WATER SUPPLY SCHEME. (SM/15873) | SM/15873 | 932.73 | 1083 | NEW | 50 | Delayed | 34 | 20/02/2023 | 20/08/2024 | 01/08/2024 | 18/07/2023 | 318.73 | 318.73
269 | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. (SM/19033) | SM/19033 | 1424.7 | 1117 | NEW | 50 | On track | 58 | 03/11/2023 | 31/03/2026 | 01/03/2024 | 03/11/2023 | 827.97 | 827.97
270 | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. (SM/18723) | SM/18723 | 2936.38 | 3485 | NEW | 50 | Delayed | 5 | 14/08/2023 | 14/08/2025 | 27/09/2024 | 17/10/2023 | 143.28 | 143.28
271 | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS (SM/18724) | SM/18724 | 1783.75 | 1347 | NEW | 50 | Delayed | 33 | 14/08/2023 | 14/08/2025 | 12/03/2024 | 16/08/2023 | 594.61 | 594.61
272 | Creating gravity based provision of drinking water from spring water source of school (31 nos) under Mirik Block in the District of Darjeeling under Neorakhola water supply & Mtc Division, P.H.E Dte. (SM/10784) | SM/10784 | 102.1 | 0 | SCHOOL | 50 | Delayed | 0 | 25/05/2022 | 31/03/2024 | 13/10/2023 | 26/05/2022 | 0 | 0
273 | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT (SM/18636) | SM/18636 | 1046.24 | 722 | NEW | 50 | Delayed | 88 | 31/07/2023 | 31/07/2025 | 13/12/2023 | 03/08/2023 | 916.88 | 916.88
274 | RONGCHONG AND LABDA PWSS (SM/18729) | SM/18729 | 1302.23 | 594 | NEW | 50 | Delayed | 58 | 14/08/2023 | 14/08/2025 | 12/12/2023 | 16/08/2023 | 757.9 | 757.9
275 | DAWAIPANI & TUKDAH TEA GARDEN PWSS (SM/18752) | SM/18752 | 1141.66 | 1324 | NEW | 50 | Delayed | 74 | 18/08/2023 | 18/08/2025 | 25/01/2024 | 23/08/2023 | 845.24 | 845.24
276 | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. (SM/10774) | SM/10774 | 18.12 | 59 | RETROFITTING | 50 | Delayed | 2 | 23/05/2022 | 31/10/2023 | 29/09/2023 | 26/05/2022 | 0.36 | 0.36
277 | Providing household tap connection from existing scheme at Museykhola & Dokan Dhura (SM/11818) | SM/11818 | 50.5 | 279 | RETROFITTING | 50 | Delayed | 35 | 16/08/2022 | 31/03/2025 | 19/07/2024 | 31/10/2023 | 17.48 | 17.48
278 | Creating gravity based Provision of Drinking water from spring water source for 16 Numbers of Aganwadi Centers in Block- Kurseong, under the District of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte,. (SM/11362) | SM/11362 | 38.79 | 0 | ANGANWADI | 50 | Delayed | 0 | 28/06/2022 | 31/03/2024 | 06/12/2023 | 12/07/2022 | 0 | 0
279 | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/13956) | SM/13956 | 517.62 | 455 | NEW | 50 | Delayed | 29 | 01/12/2022 | 31/03/2025 | 10/09/2024 | 28/04/2023 | 152.25 | 133.44
280 | SITTONG KHASMAHAL PWSS (SM/18336) | SM/18336 | 1082.47 | 635 | NEW | 50 | Delayed | 47 | 03/07/2023 | 03/07/2025 | 19/03/2024 | 27/07/2023 | 504.19 | 504.19
281 | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division (SM/10765) | SM/10765 | 18 | 136 | RETROFITTING | 50 | Delayed | 9 | 23/05/2022 | 23/12/2023 | 29/09/2023 | 24/06/2020 | 1.67 | 1.67
282 | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar (SM/11392) | SM/11392 | 180.91 | 950 | RETROFITTING | 50 | Delayed | 65 | 04/07/2022 | 31/03/2025 | 29/09/2024 | 12/07/2022 | 118.26 | 118.26
283 | Singla Tea Garden water supply scheme. (SM/11339) | SM/11339 | 384.26 | 746 | NEW | 50 | Delayed | 65 | 13/06/2022 | 09/03/2024 | 29/09/2023 | 08/09/2022 | 249.15 | 249.15
284 | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/15876) | SM/15876 | 790.03 | 1198 | NEW | 50 | Delayed | 93 | 20/02/2023 | 20/08/2024 | 27/09/2023 | 12/07/2023 | 736.63 | 736.63
285 | BADAMTAM TEA GARDEN PWSS (SM/18725) | SM/18725 | 1124.76 | 986 | NEW | 50 | Delayed | 52 | 14/08/2023 | 14/08/2025 | 16/05/2024 | 17/08/2023 | 580.84 | 580.84
286 | MAHAL DIRAM TEA GARDEN PWSS (SM/13623) | SM/13623 | 230.73 | 166 | NEW | 50 | Delayed | 35 | 11/11/2022 | 31/03/2025 | 27/08/2024 | 28/02/2023 | 80.54 | 80.54
287 | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING (SM/18822) | SM/18822 | 3724.46 | 2031 | NEW | 50 | Delayed | 57 | 11/09/2023 | 11/09/2025 | 11/01/2024 | 21/09/2023 | 2117.76 | 2117.76
288 | Piped water supply scheme for Daragoan Lekharga. (SM/10836) | SM/10836 | 67.94 | 84 | NEW | 50 | Delayed | 62 | 27/05/2022 | 20/12/2023 | 29/09/2023 | 26/05/2022 | 41.9 | 41.9
289 | TUKDAH FOREST PIPED WATER SUPPLY SCHEME (SM/16157) | SM/16157 | 112.01 | 125 | NEW | 50 | Delayed | 63 | 22/02/2023 | 22/08/2024 | 20/02/2024 | 28/04/2023 | 70.09 | 70.09
290 | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/16352) | SM/16352 | 705.57 | 715 | NEW | 50 | Delayed | 52 | 28/02/2023 | 31/08/2024 | 06/12/2023 | 28/04/2023 | 368.17 | 368.17
291 | SAMALBONG PWSS (SM/18722) | SM/18722 | 1305.89 | 544 | NEW | 50 | Delayed | 63 | 14/08/2023 | 14/08/2025 | 20/01/2024 | 16/08/2023 | 823.98 | 823.98
292 | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED (SM/19038) | SM/19038 | 6918 | 4193 | NEW | 50 | On track | 60 | 17/11/2023 | 31/03/2026 | 01/03/2024 | 03/01/2024 | 4164.88 | 3740.15
293 | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/15884) | SM/15884 | 710.16 | 644 | NEW | 50 | Delayed | 47 | 20/02/2023 | 20/08/2024 | 05/01/2024 | 18/07/2023 | 335.99 | 335.99
294 | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. (SM/16238) | SM/16238 | 133.16 | 43 | NEW | 50 | Delayed | 68 | 24/02/2023 | 31/03/2025 | 04/09/2024 | 17/07/2023 | 90.02 | 90.02
295 | GINGLAM & GIELIE TEA GARDEN PWSS (SM/18721) | SM/18721 | 1070.75 | 908 | NEW | 50 | Delayed | 95 | 14/08/2023 | 14/08/2025 | 12/12/2023 | 11/08/2023 | 1021.15 | 1021.15
296 | PESHOK TEA GARDEN PWSS (SM/18728) | SM/18728 | 1054.98 | 1000 | NEW | 50 | Delayed | 49 | 14/08/2023 | 14/08/2025 | 15/03/2024 | 16/08/2023 | 519.53 | 519.53
297 | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING (SM/18820) | SM/18820 | 2125.19 | 1170 | NEW | 50 | Delayed | 84 | 11/09/2023 | 11/09/2025 | 11/01/2024 | 21/09/2023 | 1795.4 | 1795.4
298 | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME (SM/10073) | SM/10073 | 910.44 | 4904 | AUGMENTATION | 51 | Delayed | 59 | 27/01/2022 | 31/03/2024 | 19/07/2023 | 13/08/2021 | 534.46 | 534.45
299 | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME (SM/10477) | SM/10477 | 335.48 | 321 | AUGMENTATION | 55 | Delayed | 48 | 13/04/2022 | 31/12/2023 | 19/07/2023 | 21/04/2022 | 162.26 | 162.26
300 | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/14530) | SM/14530 | 1651.09 | 1488 | NEW | 57 | Delayed | 29 | 30/01/2023 | 30/01/2025 | 15/03/2024 | 17/10/2023 | 474.57 | 474.57
301 | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME (SM/12036) | SM/12036 | 272.84 | 1162 | AUGMENTATION | 59 | Delayed | 43 | 01/09/2022 | 31/03/2024 | 13/10/2023 | 24/01/2023 | 116.64 | 116.64
302 | Creating gravity based provision of drinking water from spring water source for 87 Nos of School under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong. (SM/11355) | SM/11355 | 273.3 | 202 | SCHOOL | 60 | Delayed | 0 | 28/06/2022 | 31/03/2024 | 08/09/2023 | 12/07/2022 | 0 | 0
303 | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. (SM/10622) | SM/10622 | 480.8 | 0 | DISASTER | 60 | Delayed | 0 | 20/04/2022 | 31/03/2024 | 03/10/2023 | 13/04/2022 | 0 | 0
304 | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA (SM/10800) | SM/10800 | 143.69 | 233 | NEW | 60 | Delayed | 1 | 25/05/2022 | 25/11/2023 | 06/12/2023 | 01/11/2022 | 0.81 | 0.81
305 | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING (SM/10824) | SM/10824 | 542.09 | 794 | NEW | 60 | Delayed | 43 | 27/05/2022 | 31/08/2023 | 12/06/2023 | 21/04/2022 | 233.31 | 233.31
306 | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME (SM/09829) | SM/09829 | 843.24 | 2467 | AUGMENTATION | 60 | Delayed | 53 | 02/12/2021 | 31/03/2024 | 22/08/2023 | 03/02/2022 | 444.86 | 444.86
307 | CHAINPURAY PIPED WATER SUPPLY SCHEME (SM/15881) | SM/15881 | 82.28 | 105 | NEW | 60 | Delayed | 55 | 20/02/2023 | 10/01/2024 | 29/09/2023 | 12/07/2023 | 44.92 | 44.92
308 | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) (SM/13440) | SM/13440 | 240.06 | 536 | NEW | 61 | Delayed | 74 | 02/11/2022 | 31/03/2025 | 16/02/2024 | 14/06/2022 | 177.88 | 177.51
309 | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME (SM/12037) | SM/12037 | 125.17 | 439 | AUGMENTATION | 62 | Delayed | 52 | 01/09/2022 | 31/03/2025 | 21/06/2024 | 10/05/2023 | 64.48 | 64.48
310 | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME (SM/10107) | SM/10107 | 641.16 | 3590 | AUGMENTATION | 63 | Delayed | 81 | 02/02/2022 | 31/03/2024 | 11/10/2023 | 13/08/2021 | 521.72 | 521.72
311 | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) (SM/16386) | SM/16386 | 669.48 | 329 | NEW | 63 | Delayed | 61 | 28/02/2023 | 31/12/2023 | 12/07/2023 | 03/03/2023 | 405.65 | 405.65
312 | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT (SM/14532) | SM/14532 | 1462.38 | 1060 | NEW | 65 | Delayed | 72 | 30/01/2023 | 24/12/2023 | 06/09/2023 | 29/05/2023 | 1047.05 | 1047.05
313 | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. (SM/14529) | SM/14529 | 2347.04 | 1668 | NEW | 65 | Delayed | 84 | 30/01/2023 | 31/12/2023 | 11/08/2023 | 12/07/2023 | 1974.72 | 1974.72
314 | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. (SM/11345) | SM/11345 | 24.77 | 52 | NEW | 65 | Delayed | 53 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 24/06/2020 | 13.24 | 13.24
315 | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. (SM/14148) | SM/14148 | 1646.2 | 1583 | NEW | 65 | Delayed | 43 | 05/01/2023 | 05/01/2025 | 04/01/2024 | 15/02/2023 | 708.94 | 708.94
316 | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA (SM/11399) | SM/11399 | 562.88 | 446 | NEW | 68 | Delayed | 34 | 04/07/2022 | 04/01/2024 | 12/06/2023 | 04/05/2023 | 192.88 | 192.88
317 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Khudiram Pally-I, khudiram Pally-II, Rail cly & Sree Colony Habitation of Dumriguri Piped W/S Supply Scheme ( Part-B ) at Naxalbari Block (SM/07427) | SM/07427 | 82.41 | 1560 | RETROFITTING | 68 | WO no issued | 87 | 30/12/2020 | 31/03/2024 | 12/06/2023 | 14/08/2020 | 71.53 | 71.53
318 | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block (SM/07428) | SM/07428 | 77.59 | 1454 | RETROFITTING | 68 | Delayed | 85 | 30/12/2020 | 30/06/2025 | 20/11/2024 | 22/02/2021 | 66.14 | 66.14
319 | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. (SM/11395) | SM/11395 | 306.47 | 360 | NEW | 68 | Delayed | 0 | 04/07/2022 | 04/01/2024 | 12/06/2023 | 04/05/2023 | 0.74 | 0.74
320 | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA (SM/10827) | SM/10827 | 213.75 | 283 | NEW | 68 | Delayed | 12 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 01/11/2022 | 26.21 | 26.21
321 | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING (SM/10788) | SM/10788 | 244.94 | 1310 | NEW | 70 | Delayed | 63 | 25/05/2022 | 27/02/2024 | 21/07/2023 | 24/06/2020 | 153.53 | 153.53
322 | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA (SM/10825) | SM/10825 | 118.57 | 165 | NEW | 70 | Delayed | 33 | 27/05/2022 | 30/10/2023 | 12/07/2023 | 01/11/2022 | 39.59 | 39.59
323 | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA (SM/10810) | SM/10810 | 151.73 | 233 | NEW | 70 | Delayed | 45 | 25/05/2022 | 30/11/2023 | 07/07/2023 | 26/05/2022 | 68.32 | 68.32
324 | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u (SM/08295) | SM/08295 | 85.65 | 1690 | RETROFITTING | 70 | Delayed | 57 | 26/02/2021 | 31/12/2023 | 12/06/2023 | 03/08/2021 | 48.66 | 45.01
325 | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA (SM/10799) | SM/10799 | 80.89 | 233 | NEW | 70 | Delayed | 51 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 26/05/2022 | 41.46 | 41.46
326 | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. (SM/11353) | SM/11353 | 72.84 | 200 | NEW | 70 | Delayed | 46 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 12/07/2022 | 33.44 | 33.44
327 | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate (SM/10239) | SM/10239 | 389.69 | 0 | SCHOOL | 70 | Delayed | 0 | 24/02/2022 | 31/12/2023 | 21/07/2023 | 28/02/2022 | 0 | 0
328 | BARA CHENGA PIPED WATER SUPPLY SCHEME (SM/10816) | SM/10816 | 422.1 | 584 | NEW | 72 | Delayed | 56 | 25/05/2022 | 01/06/2024 | 23/02/2024 | 30/06/2022 | 235.96 | 235.96
329 | PWS Scheme for Maharani Tea Garden (SM/16474) | SM/16474 | 465.91 | 488 | NEW | 72 | Delayed | 68 | 02/03/2023 | 31/12/2023 | 06/09/2023 | 03/03/2023 | 317.57 | 317.57
330 | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) (SM/07046) | SM/07046 | 98.86 | 1943 | RETROFITTING | 75 | Delayed | 60 | 24/11/2020 | 31/03/2024 | 28/09/2023 | 22/02/2021 | 59.23 | 59.23
331 | Nipania Piped water Supply Scheme. (SM/10815) | SM/10815 | 461.01 | 1314 | NEW | 75 | Delayed | 90 | 25/05/2022 | 25/11/2024 | 23/02/2024 | 30/06/2022 | 412.96 | 412.96
332 | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. (SM/11889) | SM/11889 | 319.88 | 308 | NEW | 75 | Delayed | 69 | 17/08/2022 | 31/12/2023 | 19/07/2023 | 18/10/2022 | 219.99 | 219.99
333 | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS (SM/15224) | SM/15224 | 2098.08 | 910 | NEW | 75 | Delayed | 54 | 07/02/2023 | 07/02/2025 | 04/01/2024 | 12/07/2023 | 1140.94 | 1140.94
334 | Choongtoong & Lizahill Tea Garden water supply scheme (SM/12269) | SM/12269 | 1242.31 | 2635 | NEW | 78 | Delayed | 80 | 09/09/2022 | 31/03/2024 | 29/09/2023 | 01/11/2022 | 999.44 | 999.44
335 | Piped water supply scheme for Thulung Gaon (SM/10830) | SM/10830 | 78.67 | 107 | NEW | 78 | Delayed | 71 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 26/05/2022 | 55.95 | 55.95
336 | Piped water supply scheme for Singbuli factory gaon (SM/10831) | SM/10831 | 77.24 | 211 | NEW | 78 | Delayed | 78 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 26/05/2022 | 60.08 | 60.08
337 | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME (SM/09830) | SM/09830 | 566.48 | 2131 | AUGMENTATION | 79 | Delayed | 69 | 02/12/2021 | 31/03/2025 | 02/05/2024 | 03/02/2022 | 393.63 | 391.77
338 | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA (SM/10826) | SM/10826 | 178.67 | 448 | NEW | 79 | Delayed | 23 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 05/08/2022 | 41.84 | 41.84
339 | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. (SM/10835) | SM/10835 | 218.24 | 242 | NEW | 80 | Delayed | 91 | 27/05/2022 | 15/11/2023 | 09/09/2023 | 05/08/2022 | 199.12 | 199.12
340 | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme (SM/07218) | SM/07218 | 98.75 | 1406 | RETROFITTING | 80 | Delayed | 93 | 08/12/2020 | 31/03/2024 | 28/09/2023 | 09/09/2021 | 91.53 | 91.53
341 | SINGALILA FOREST PWSS (SM/16771) | SM/16771 | 398.31 | 76 | NEW | 80 | Delayed | 81 | 13/03/2023 | 15/11/2024 | 29/09/2023 | 27/04/2023 | 320.91 | 320.91
342 | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA (SM/10803) | SM/10803 | 91.97 | 588 | NEW | 80 | Delayed | 50 | 25/05/2022 | 30/11/2023 | 07/07/2023 | 24/06/2020 | 46.04 | 46.04
343 | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/13958) | SM/13958 | 330.4 | 170 | NEW | 80 | Delayed | 59 | 01/12/2022 | 01/06/2024 | 17/01/2024 | 07/02/2023 | 194.63 | 194.63
344 | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. (SM/15877) | SM/15877 | 150.95 | 35 | NEW | 80 | Delayed | 73 | 20/02/2023 | 20/11/2023 | 09/09/2023 | 15/05/2023 | 110.19 | 110.19
345 | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. (SM/11385) | SM/11385 | 47.07 | 170 | RETROFITTING | 80 | Delayed | 65 | 04/07/2022 | 15/11/2023 | 09/09/2023 | 12/07/2022 | 30.77 | 30.77
346 | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA (SM/10801) | SM/10801 | 163.3 | 233 | NEW | 80 | Delayed | 32 | 25/05/2022 | 31/03/2024 | 01/09/2023 | 05/08/2022 | 52.16 | 52.16
347 | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. (SM/11346) | SM/11346 | 21.35 | 45 | NEW | 81 | Delayed | 64 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 12/07/2022 | 13.63 | 13.63
348 | PWS Scheme for Rohini Tea Garden (SM/11938) | SM/11938 | 408.51 | 614 | NEW | 83 | Delayed | 34 | 24/08/2022 | 01/06/2024 | 23/02/2024 | 28/04/2023 | 137.99 | 137.99
349 | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA (SM/10808) | SM/10808 | 189.33 | 233 | NEW | 83 | Delayed | 44 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 26/05/2022 | 83.29 | 83.29
350 | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA (SM/10807) | SM/10807 | 103.62 | 166 | NEW | 85 | Delayed | 52 | 25/05/2022 | 30/11/2023 | 07/07/2023 | 24/06/2020 | 54.27 | 54.27
351 | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. (SM/13571) | SM/13571 | 1420.81 | 1344 | NEW | 85 | Delayed | 79 | 09/11/2022 | 30/11/2023 | 06/09/2023 | 03/03/2023 | 1128.09 | 1128.09
352 | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District (SM/16535) | SM/16535 | 1055.89 | 1196 | NEW | 85 | Delayed | 66 | 10/03/2023 | 31/12/2023 | 06/09/2023 | 27/04/2023 | 695.65 | 695.65
353 | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. (SM/11398) | SM/11398 | 379.74 | 225 | NEW | 85 | Delayed | 39 | 04/07/2022 | 31/12/2023 | 06/12/2023 | 07/02/2023 | 148.25 | 148.25
354 | Augmentation of source and provding FHTC at Bijanbari Bazaar (SM/11375) | SM/11375 | 42.06 | 50 | AUGMENTATION | 85 | Delayed | 49 | 13/06/2022 | 20/11/2023 | 09/09/2023 | 30/06/2022 | 20.73 | 20.73
355 | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong (SM/10814) | SM/10814 | 263.53 | 0 | SCHOOL | 85 | Delayed | 0 | 26/05/2022 | 31/03/2024 | 04/08/2023 | 06/05/2022 | 0 | 0
356 | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA (SM/10806) | SM/10806 | 122.1 | 588 | NEW | 88 | Delayed | 52 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 24/06/2020 | 63.34 | 63.34
357 | Augmentation of Chuchur Muchur Piped Water Supply Scheme (SM/13427) | SM/13427 | 244.41 | 396 | AUGMENTATION | 90 | On track | 79 | 02/11/2022 | 31/12/2024 | 21/06/2024 | 23/02/2023 | 192.51 | 192.51
358 | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden (SM/10837) | SM/10837 | 101.18 | 160 | NEW | 90 | Delayed | 77 | 27/05/2022 | 27/11/2023 | 29/09/2023 | 24/06/2020 | 77.61 | 77.61
359 | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. (SM/12366) | SM/12366 | 1129.94 | 1358 | NEW | 90 | Delayed | 81 | 13/09/2022 | 13/09/2024 | 12/06/2023 | 01/11/2022 | 911.31 | 911.31
360 | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling (SM/10819) | SM/10819 | 150.71 | 298 | NEW | 90 | Delayed | 63 | 25/05/2022 | 31/12/2023 | 25/07/2023 | 30/06/2022 | 95.27 | 95.27
361 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BAIRAGI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15855) | SM/15855 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
362 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15860) | SM/15860 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
363 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15854) | SM/15854 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
364 | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. (SM/10789) | SM/10789 | 100.65 | 105 | NEW | 90 | Delayed | 67 | 25/05/2022 | 31/12/2023 | 25/07/2023 | 26/05/2022 | 67.28 | 67.28
365 | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. (SM/10790) | SM/10790 | 100.33 | 129 | NEW | 90 | Delayed | 67 | 25/05/2022 | 31/12/2023 | 25/07/2023 | 26/05/2022 | 67.28 | 67.28
366 | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. (SM/11952) | SM/11952 | 884.34 | 898 | NEW | 90 | Delayed | 91 | 24/08/2022 | 31/03/2024 | 13/09/2023 | 01/11/2022 | 805.26 | 805.26
367 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DANGARVITA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15627) | SM/15627 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
368 | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. (SM/12367) | SM/12367 | 1786.06 | 1317 | NEW | 90 | Delayed | 84 | 13/09/2022 | 31/12/2023 | 06/12/2023 | 06/02/2023 | 1508.53 | 1508.53
369 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT OMI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15859) | SM/15859 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
370 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA BANSGAON PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15629) | SM/15629 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
371 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15631) | SM/15631 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
372 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DEBURAM PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15858) | SM/15858 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
373 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15630) | SM/15630 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
374 | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS (SM/11855) | SM/11855 | 408.25 | 228 | NEW | 90 | Delayed | 70 | 16/08/2022 | 15/11/2023 | 09/09/2023 | 17/10/2022 | 285.95 | 285.95
375 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DAMDAMA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15857) | SM/15857 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
376 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15626) | SM/15626 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
377 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT TARBANDHA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15632) | SM/15632 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
378 | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. (SM/11386) | SM/11386 | 122.75 | 474 | RETROFITTING | 90 | Delayed | 86 | 04/07/2022 | 10/10/2023 | 29/09/2023 | 12/07/2022 | 105.36 | 105.36
379 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BIRSING PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15856) | SM/15856 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 20/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
380 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GUABARI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15628) | SM/15628 | 9.14 | 0 | SOLARISATION | 90 | On track | 0 | 16/02/2023 | 31/12/2024 | 04/04/2024 | 14/07/2023 | 0 | 0
381 | RIMBICK WATER SUPPLY SCHEME (SM/09427) | SM/09427 | 627.68 | 1636 | NEW | 95 | Delayed | 95 | 17/11/2021 | 31/08/2023 | 26/07/2023 | 24/06/2020 | 598.46 | 598.46
382 | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. (SM/11943) | SM/11943 | 212.19 | 385 | NEW | 95 | Delayed | 78 | 24/08/2022 | 30/11/2023 | 06/12/2023 | 10/01/2023 | 165.36 | 165.36
383 | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING (SM/11891) | SM/11891 | 865.61 | 759 | NEW | 95 | Delayed | 91 | 17/08/2022 | 17/02/2024 | 04/01/2024 | 29/09/2022 | 787.14 | 787.14
384 | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA (SM/10805) | SM/10805 | 123.11 | 588 | NEW | 95 | Delayed | 53 | 25/05/2022 | 31/10/2023 | 06/12/2023 | 25/11/2022 | 65.36 | 65.36
385 | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING (SM/12736) | SM/12736 | 1292.66 | 990 | NEW | 95 | Delayed | 95 | 21/09/2022 | 21/09/2024 | 04/01/2024 | 01/11/2022 | 1225.41 | 1225.41
386 | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA (SM/10828) | SM/10828 | 117.73 | 303 | NEW | 95 | Delayed | 45 | 27/05/2022 | 27/11/2023 | 12/06/2023 | 01/11/2022 | 53.05 | 53.05
387 | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING (SM/12128) | SM/12128 | 990.4 | 759 | NEW | 95 | Delayed | 95 | 07/09/2022 | 07/03/2024 | 04/01/2024 | 01/11/2022 | 942.19 | 942.19
388 | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING (SM/12178) | SM/12178 | 595.74 | 285 | NEW | 95 | Delayed | 97 | 07/09/2022 | 07/03/2024 | 04/01/2024 | 14/10/2022 | 578.39 | 578.39
389 | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING (SM/11953) | SM/11953 | 768.51 | 527 | NEW | 95 | Delayed | 91 | 24/08/2022 | 24/02/2024 | 04/01/2024 | 31/08/2022 | 698.32 | 698.32
390 | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division (SM/10767) | SM/10767 | 16.01 | 130 | RETROFITTING | 95 | Delayed | 89 | 23/05/2022 | 25/10/2023 | 29/09/2023 | 24/06/2020 | 14.31 | 14.31
391 | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. (SM/11348) | SM/11348 | 27.68 | 150 | NEW | 96 | Delayed | 52 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 25/11/2022 | 14.44 | 14.44
392 | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. (SM/12368) | SM/12368 | 2044.39 | 1738 | NEW | 96 | Delayed | 84 | 13/09/2022 | 13/09/2024 | 15/02/2024 | 07/02/2023 | 1709.39 | 1709.39
393 | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield (SM/10772) | SM/10772 | 15.76 | 96 | RETROFITTING | 97 | Delayed | 4 | 23/05/2022 | 18/10/2023 | 29/09/2023 | 24/05/2022 | 0.59 | 0.59
394 | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta (SM/10768) | SM/10768 | 25.05 | 127 | RETROFITTING | 98 | Delayed | 97 | 23/05/2022 | 15/08/2023 | 25/07/2023 | 24/05/2022 | 24.32 | 24.32
395 | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. (SM/13041) | SM/13041 | 1164.09 | 850 | NEW | 98 | Delayed | 92 | 29/09/2022 | 29/09/2024 | 04/01/2024 | 21/10/2022 | 1070.75 | 1070.75
396 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. (SM/11321) | SM/11321 | 17.13 | 193 | RETROFITTING | 98 | Delayed | 78 | 13/06/2022 | 31/03/2024 | 01/09/2023 | 24/06/2020 | 13.29 | 13.29
397 | Piped water supply scheme for Kolbong (SM/10834) | SM/10834 | 104.23 | 107 | NEW | 100 | 100% Physical | 84 | 27/05/2022 |  | 09/09/2023 | 26/05/2022 | 87.11 | 87.11
398 | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II (SM/10822) | SM/10822 | 19.74 | 28 | RETROFITTING | 100 | 100% Physical | 80 | 27/05/2022 |  | 09/09/2023 | 24/06/2020 | 15.71 | 15.71
399 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. (SM/11315) | SM/11315 | 21.28 | 108 | RETROFITTING | 100 | 100% Physical | 90 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 19.24 | 19.24
400 | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) (SM/11378) | SM/11378 | 40.64 | 0 | RETROFITTING | 100 | 100% Physical | 72 | 04/07/2022 | 04/10/2022 | 29/09/2023 | 12/07/2022 | 29.16 | 29.16
401 | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING (SM/11890) | SM/11890 | 760.91 | 609 | NEW | 100 | 100% Physical | 87 | 17/08/2022 | 17/02/2024 | 04/01/2024 | 01/11/2022 | 662.12 | 662.12
402 | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. (SM/11347) | SM/11347 | 39.89 | 96 | NEW | 100 | 100% Physical | 92 | 28/06/2022 |  | 12/06/2023 | 12/07/2022 | 36.73 | 36.73
403 | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra (SM/10561) | SM/10561 | 16.73 | 111 | RETROFITTING | 100 | 100% Physical | 82 | 18/04/2022 |  | 09/09/2023 | 24/06/2020 | 13.71 | 13.71
404 | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal Swpna Programme for Samar Nagar& Debidanga area of Kalkut Mouza, Uttar Palash and Dakshin Palash area of Palash Mouza and Kalabari Mouza ( Part ) of Kalkut Piped W/S Scheme at (SM/08296) | SM/08296 | 63.28 | 1250 | RETROFITTING | 100 | 100% Physical | 84 | 26/02/2021 | 31/12/2023 | 21/07/2023 | 03/08/2021 | 53.09 | 53.09
405 | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth (SM/10766) | SM/10766 | 7.21 | 35 | RETROFITTING | 100 | 100% Physical | 78 | 23/05/2022 | 15/08/2023 | 29/09/2023 | 25/05/2022 | 5.62 | 5.62
406 | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village (SM/10770) | SM/10770 | 21.64 | 39 | RETROFITTING | 100 | 100% Physical | 74 | 23/05/2022 |  | 09/09/2023 | 24/06/2020 | 15.99 | 15.99
407 | Piped water supply scheme for Pokhriabong Busty 5 No. (SM/10832) | SM/10832 | 98.99 | 85 | NEW | 100 | 100% Physical | 65 | 27/05/2022 | 27/11/2023 | 29/09/2023 | 26/05/2022 | 64.07 | 64.07
408 | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING (SM/12179) | SM/12179 | 663.63 | 447 | NEW | 100 | 100% Physical | 90 | 07/09/2022 | 07/03/2024 | 04/01/2024 | 03/11/2022 | 596.85 | 596.85
409 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA (SM/11333) | SM/11333 | 26.69 | 110 | RETROFITTING | 100 | 100% Physical | 87 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 23.27 | 23.27
410 | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. (SM/11944) | SM/11944 | 923.75 | 818 | NEW | 100 | 100% Physical | 95 | 24/08/2022 | 24/02/2024 | 04/01/2024 | 03/11/2022 | 881.14 | 881.14
411 | Piped Water Supply Scheme For Jhepi & Gurdung. (SM/10833) | SM/10833 | 318.71 | 309 | NEW | 100 | 100% Physical | 94 | 27/05/2022 |  | 28/07/2023 | 30/06/2022 | 300.02 | 300.02
412 | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung (SM/11389) | SM/11389 | 15.54 | 63 | RETROFITTING | 100 | 100% Physical | 85 | 04/07/2022 | 04/10/2022 | 29/09/2023 | 24/06/2020 | 13.25 | 13.25
413 | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) (SM/10773) | SM/10773 | 21.6 | 139 | RETROFITTING | 100 | 100% Physical | 86 | 23/05/2022 | 14/08/2023 | 29/09/2023 | 24/05/2022 | 18.64 | 18.64
414 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. (SM/11318) | SM/11318 | 7.31 | 65 | RETROFITTING | 100 | 100% Physical | 87 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 6.34 | 6.34
415 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA (SM/11327) | SM/11327 | 15.46 | 135 | RETROFITTING | 100 | 100% Physical | 84 | 13/06/2022 | 13/09/2022 | 30/09/2024 | 24/06/2020 | 13.05 | 13.05
416 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA (SM/11334) | SM/11334 | 33.35 | 246 | RETROFITTING | 100 | 100% Physical | 55 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 18.45 | 18.45
417 | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING (SM/11954) | SM/11954 | 333.26 | 215 | NEW | 100 | 100% Physical | 76 | 24/08/2022 | 24/02/2024 | 04/01/2024 | 31/08/2022 | 253.72 | 253.72
418 | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS (SM/11854) | SM/11854 | 942.58 | 716 | NEW | 100 | 100% Physical | 84 | 16/08/2022 | 16/02/2024 | 04/01/2024 | 01/11/2022 | 787.92 | 787.92
419 | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan (SM/10769) | SM/10769 | 22.77 | 76 | RETROFITTING | 100 | 100% Physical | 82 | 23/05/2022 |  | 09/09/2023 | 24/06/2020 | 18.78 | 18.78
420 | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village (SM/10771) | SM/10771 | 14.21 | 23 | RETROFITTING | 100 | 100% Physical | 93 | 23/05/2022 | 20/09/2023 | 26/09/2023 | 24/06/2020 | 13.18 | 13.18
421 | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II (SM/11383) | SM/11383 | 65.26 | 315 | RETROFITTING | 100 | 100% Physical | 85 | 04/07/2022 |  | 28/07/2023 | 28/09/2022 | 55.23 | 55.23
422 | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/10785) | SM/10785 | 13.32 | 6 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 100 | 100% Physical | 0 | 25/05/2022 |  | 08/09/2023 | 12/07/2022 | 0 | 0
423 | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA (SM/10804) | SM/10804 | 123.59 | 588 | NEW | 100 | 100% Physical | 53 | 25/05/2022 | 31/12/2023 | 06/12/2023 | 01/11/2022 | 64.9 | 64.9
424 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. (SM/11317) | SM/11317 | 12.12 | 142 | RETROFITTING | 100 | 100% Physical | 7 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 0.87 | 0.87
425 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. (SM/11320) | SM/11320 | 19.74 | 234 | RETROFITTING | 100 | 100% Physical | 88 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 17.47 | 17.47
426 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div (SM/11323) | SM/11323 | 22.61 | 270 | RETROFITTING | 100 | 100% Physical | 90 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 20.41 | 20.41
427 | Augmentation of source for lower Takbia (SM/11374) | SM/11374 | 28.05 | 0 | AUGMENTATION | 100 | 100% Physical | 85 | 13/06/2022 | 13/12/2022 | 29/09/2023 | 30/06/2022 | 23.9 | 23.9
428 | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong (SM/11365) | SM/11365 | 38.03 | 0 | HEALTH CENTER | 100 | 100% Physical | 0 | 28/06/2022 |  | 08/09/2023 | 12/07/2022 | 0 | 0
429 | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING (SM/13042) | SM/13042 | 1047.9 | 578 | NEW | 100 | 100% Physical | 82 | 29/09/2022 | 29/09/2024 | 04/01/2024 | 01/11/2022 | 858.4 | 858.4
430 | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay (SM/10780) | SM/10780 | 17.18 | 28 | RETROFITTING | 100 | 100% Physical | 91 | 25/05/2022 |  | 09/09/2023 | 24/06/2020 | 15.69 | 15.69
431 | Providing functional household tap connection existing PWSS at Bunkulung (SM/11391) | SM/11391 | 33.5 | 155 | RETROFITTING | 100 | 100% Physical | 62 | 04/07/2022 | 04/10/2022 | 30/09/2024 | 12/07/2022 | 20.87 | 20.87
432 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, (SM/11316) | SM/11316 | 7.68 | 51 | RETROFITTING | 100 | 100% Physical | 4 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 0.31 | 0.31
433 | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS (SM/14418) | SM/14418 | 1660.67 | 1100 | NEW | 100 | 100% Physical | 91 | 20/01/2023 | 15/02/2024 | 04/01/2024 | 15/02/2023 | 1514.72 | 1514.72
434 | Hatta Water Supply Scheme (SM/09449) | SM/09449 | 313.13 | 310 | NEW | 100 | 100% Physical | 97 | 19/11/2021 |  | 05/07/2023 | 24/06/2020 | 303.72 | 303.72
435 | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village (SM/10764) | SM/10764 | 21.15 | 60 | RETROFITTING | 100 | 100% Physical | 89 | 23/05/2022 |  | 09/09/2023 | 24/06/2020 | 18.8 | 18.8
436 | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden (SM/11381) | SM/11381 | 76.94 | 520 | RETROFITTING | 100 | 100% Physical | 70 | 04/07/2022 | 04/10/2022 | 29/09/2023 | 12/07/2022 | 53.64 | 53.64
437 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA (SM/11332) | SM/11332 | 26.39 | 244 | RETROFITTING | 100 | 100% Physical | 93 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 24.5 | 24.5
438 | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. (SM/11351) | SM/11351 | 18.6 | 35 | NEW | 100 | 100% Physical | 97 | 28/06/2022 |  | 12/06/2023 | 01/11/2022 | 18.06 | 18.06
439 | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) (SM/11379) | SM/11379 | 23.39 | 78 | RETROFITTING | 100 | 100% Physical | 6 | 04/07/2022 | 04/10/2022 | 29/09/2023 | 24/06/2020 | 1.44 | 1.44
440 | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar (SM/11382) | SM/11382 | 54.99 | 250 | RETROFITTING | 100 | 100% Physical | 88 | 04/07/2022 | 04/10/2022 | 29/09/2023 | 12/07/2022 | 48.43 | 48.43
441 | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/10795) | SM/10795 | 18.42 | 6 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 100 | 100% Physical | 0 | 25/05/2022 |  | 03/10/2023 | 12/07/2022 | 0 | 0
442 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. (SM/11324) | SM/11324 | 36.13 | 425 | RETROFITTING | 100 | 100% Physical | 81 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 29.31 | 29.31
443 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. (SM/11325) | SM/11325 | 10.69 | 120 | RETROFITTING | 100 | 100% Physical | 92 | 13/06/2022 |  | 12/06/2023 | 24/06/2020 | 9.82 | 9.82
444 | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA (SM/11328) | SM/11328 | 27.54 | 220 | RETROFITTING | 100 | 100% Physical | 83 | 13/06/2022 |  | 01/09/2023 | 24/06/2020 | 22.8 | 22.8
445 | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. (SM/11350) | SM/11350 | 26.38 | 35 | NEW | 100 | 100% Physical | 97 | 28/06/2022 |  | 12/06/2023 | 24/06/2020 | 25.62 | 25.62
Total |  |  | 260789.76 | 355736 | [8 empty] | 104915.71 | 103990.88