## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme (SM/07028) | SM/07028 | 96.79 | 1531 | RETROFITTING | 0 | WO no issued | 73 | 13/11/2020 | 13/02/2021 | 05/05/2023 | 14/08/2020 | 70.34 | 70.34
2 | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME (SM/13682) | SM/13682 | 544.59 | 1332 | NEW | 0 | 0% Physical | 2 | 14/11/2022 | 14/05/2024 | 12/06/2023 | 08/06/2023 | 8.21 | 8.21
3 | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME (SM/15094) | SM/15094 | 125.87 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 04/02/2023 | 04/08/2023 | 12/06/2023 | 18/05/2023 | 0 | 0
4 | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15297) | SM/15297 | 724.23 | 1991 | NEW | 0 | 0% Physical | 2 | 09/02/2023 | 09/08/2024 | 12/06/2023 | 07/06/2023 | 12.26 | 12.26
5 | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN (SM/16492) | SM/16492 | 461.81 | 1078 | NEW | 0 | 0% Physical | 13 | 02/03/2023 | 02/09/2024 | 12/06/2023 | 10/05/2023 | 59.34 | 59.34
6 | BARA GHARIA PIPED WATER SUPPLY SCHEME (SM/15967) | SM/15967 | 703.7 | 1304 | NEW | 0 | 0% Physical | 4 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 25/05/2023 | 24.69 | 24.69
7 | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME (SM/15915) | SM/15915 | 427.23 | 878 | NEW | 0 | 0% Physical | 1 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 01/09/2022 | 5.41 | 5.41
8 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SYLI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15621) | SM/15621 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
9 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF DOMOHINI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15596) | SM/15596 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
10 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHANGARHAT PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15598) | SM/15598 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
11 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BAIKUR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15580) | SM/15580 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
12 | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME (SM/15335) | SM/15335 | 850.7 | 2792 | NEW | 0 | 0% Physical | 6 | 09/02/2023 | 09/08/2024 | 12/06/2023 | 24/07/2023 | 54.26 | 54.26
13 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MADHABDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15615) | SM/15615 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
14 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MATHACHULKA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15617) | SM/15617 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
15 | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14884) | SM/14884 | 710.56 | 2397 | NEW | 0 | 0% Physical | 0 | 03/02/2023 | 03/08/2024 | 12/06/2023 | 04/08/2023 | 0 | 0
16 | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME (SM/15263) | SM/15263 | 399.34 | 1212 | NEW | 0 | 0% Physical | 0 | 07/02/2023 | 07/08/2024 | 12/06/2023 | 10/05/2023 | 0 | 0
17 | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14886) | SM/14886 | 525.39 | 1312 | NEW | 0 | 0% Physical | 0 | 03/02/2023 | 03/08/2024 | 12/06/2023 | 05/06/2023 | 0 | 0
18 | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15980) | SM/15980 | 350.2 | 694 | NEW | 0 | 0% Physical | 1 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 08/08/2023 | 4.28 | 4.28
19 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR NAGRAKATA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15611) | SM/15611 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
20 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT YOUNGTONG TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15625) | SM/15625 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
21 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15604) | SM/15604 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
22 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KARBALA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15613) | SM/15613 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
23 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHAGATPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15597) | SM/15597 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
24 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA DURAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15603) | SM/15603 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
25 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DWARIKAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15608) | SM/15608 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
26 | CHHAR TANDU PIPED WATER SUPPLY SCHEME (SM/15964) | SM/15964 | 330.17 | 573 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 08/08/2023 | 0 | 0
27 | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme (SM/17181) | SM/17181 | 201.66 | 1317 | AUGMENTATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 15/05/2023 | 0 | 0
28 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SAJNAPARA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15620) | SM/15620 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
29 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15605) | SM/15605 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
30 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15607) | SM/15607 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
31 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GATIA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15609) | SM/15609 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
32 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF CHAMURCHI FOREST BUSTY WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15584) | SM/15584 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
33 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MALLICKSOVA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15616) | SM/15616 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
34 | SONAKHULI PIPED WATER SUPPLY SCHEME (SM/15744) | SM/15744 | 446.23 | 732 | NEW | 0 | 0% Physical | 1 | 20/02/2023 | 20/08/2024 | 12/06/2023 | 13/04/2023 | 4.51 | 4.51
35 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF CHARERBARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15606) | SM/15606 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
36 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KILKOTE TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15614) | SM/15614 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
37 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GRASSMORE TEA GARDEN AREA PIPED WATER SUPPLY UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15599) | SM/15599 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
38 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT KUMLAI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15601) | SM/15601 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
39 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15610) | SM/15610 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
40 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF NAGRAKATA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15619) | SM/15619 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
41 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SAOGAON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15623) | SM/15623 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
42 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SONGACHHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15624) | SM/15624 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
43 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KAJALDIGHI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15612) | SM/15612 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
44 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. (SM/07044) | SM/07044 | 93.9 | 1540 | RETROFITTING | 0 | WO no issued | 0 | 24/11/2020 | 24/02/2021 | 05/05/2023 |  | 0 | 0
45 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MOHITNAGAR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15618) | SM/15618 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
46 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF WATER SUPPLY SCHEME OF JITI TEA GARDEN UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15622) | SM/15622 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
47 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BASILARDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15907) | SM/15907 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 20/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
48 | BHEMTIA PIPED WATER SUPPLY SCHEME (SM/16676) | SM/16676 | 414.83 | 667 | NEW | 0 | 0% Physical | 1 | 14/03/2023 | 14/09/2024 | 12/06/2023 | 06/04/2023 | 4.11 | 4.11
49 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT JOGESH CHANDRA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15600) | SM/15600 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 27/09/2023 | 0 | 0
50 | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME (SM/14224) | SM/14224 | 140.42 | 116 | NEW | 0 | 0% Physical | 1 | 10/01/2023 | 10/07/2024 | 12/06/2023 | 08/06/2023 | 0.71 | 0.71
51 | NOWAPARA PIPED WATER SUPPLY SCHEME (SM/18503) | SM/18503 | 1060.21 | 3633 | NEW | 0 | 0% Physical | 2 | 26/07/2023 | 26/07/2025 | 31/07/2023 | 17/08/2023 | 22.38 | 22.38
52 | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P (SM/19171) | SM/19171 | 97.03 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | WO no issued | 0 | 08/02/2024 |  | 15/02/2024 |  | 0 | 0
53 | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. (SM/11170) | SM/11170 | 14.19 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 03/06/2022 |  | 03/06/2022 | 23/11/2022 | 0 | 0
54 | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/16508) | SM/16508 | 38.98 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 20/03/2023 | 0 | 0
55 | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory (SM/08681) | SM/08681 | 9.33 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 13/08/2021 |  | 31/08/2022 | 03/12/2021 | 0 | 0
56 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities related to FHTC under JJM Support Activities at Jalpaiguri District. (SM/09018) | SM/09018 | 44.85 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 30/10/2021 |  | 02/11/2021 | 17/08/2022 | 0 | 0
57 | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/16509) | SM/16509 | 22.45 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 31/03/2023 | 0 | 0
58 | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS and annual maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. (SM/06615) | SM/06615 | 20.19 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 08/08/2022 | 0 | 0
59 | DRINKING WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KITS (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION (SM/13679) | SM/13679 | 22.25 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 14/11/2022 |  | 17/11/2022 |  | 0 | 0
60 | Augmentation of Bhatipara Water Supply Scheme (SM/13277) | SM/13277 | 1483.83 | 5116 | AUGMENTATION | 1 | Delayed | 38 | 19/09/2022 | 31/12/2023 | 03/07/2023 | 22/09/2022 | 566.27 | 566.27
61 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/15060) | SM/15060 | 285.02 | 0 | AUGMENTATION | 1 | Delayed | 10 | 04/02/2023 | 31/01/2024 | 16/10/2023 | 22/05/2023 | 28.93 | 28.93
62 | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME (SM/16779) | SM/16779 | 709.31 | 2238 | NEW | 1 | Delayed | 6 | 13/03/2023 | 13/09/2024 | 24/01/2024 | 28/04/2023 | 40.02 | 40.02
63 | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme (SM/15299) | SM/15299 | 139.34 | 0 | AUGMENTATION | 1 | Delayed | 6 | 09/02/2023 | 31/03/2024 | 16/10/2023 | 09/03/2023 | 8.45 | 8.45
64 | KHAS JANGAL PIPED WATER SUPPLY SCHEME (SM/14907) | SM/14907 | 245.77 | 456 | NEW | 1 | Delayed | 2 | 03/02/2023 | 03/08/2024 | 16/10/2023 | 08/08/2023 | 5.8 | 5.8
65 | BRAHMAPUR PIPED WATER SUPPLY SCHEME (SM/13705) | SM/13705 | 988.14 | 2545 | NEW | 1 | Delayed | 8 | 14/11/2022 | 31/12/2024 | 18/04/2024 | 21/03/2023 | 74.67 | 74.67
66 | REJUVENATION OF DAKSHIN SALBARI PWSS (SM/15087) | SM/15087 | 246.25 | 2129 | AUGMENTATION | 2 | Delayed | 3 | 04/02/2023 | 31/12/2023 | 03/07/2023 | 28/02/2022 | 7.69 | 7.69
67 | CHENGMARIHAT PIPED WATER SUPPLY SCHEME (SM/18358) | SM/18358 | 1399.31 | 3607 | NEW | 2 | On track | 8 | 11/07/2023 | 11/07/2025 | 02/05/2024 | 28/07/2023 | 110.58 | 110.58
68 | Sikarpur Piped Water Supply Scheme. (SM/18836) | SM/18836 | 1910.96 | 6574 | NEW | 2 | Delayed | 0 | 21/09/2023 | 21/09/2025 | 03/01/2024 | 29/11/2023 | 3.89 | 3.89
69 | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME (SM/18355) | SM/18355 | 1573.93 | 5782 | AUGMENTATION | 2 | Delayed | 4 | 11/07/2023 | 11/04/2024 | 04/12/2023 | 07/08/2023 | 61.74 | 61.74
70 | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME (SM/19097) | SM/19097 | 1000.22 | 3357 | NEW | 2 | Delayed | 3 | 08/12/2023 | 31/03/2025 | 29/02/2024 | 14/12/2023 | 34.2 | 34.2
71 | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME (SM/13700) | SM/13700 | 661.12 | 1413 | NEW | 2 | Delayed | 40 | 14/11/2022 | 31/12/2024 | 18/04/2024 | 29/03/2023 | 266.98 | 257.53
72 | PURBA DOBBARI PIPED WATER SUPPLY SCHEME (SM/16776) | SM/16776 | 89.03 | 30 | NEW | 2 | Delayed | 10 | 13/03/2023 | 13/09/2024 | 08/02/2024 | 08/08/2023 | 8.92 | 8.92
73 | Augmentation of Kranti Piped water supply Scheme (SM/09994) | SM/09994 | 1755.8 | 5563 | AUGMENTATION | 3 | Delayed | 55 | 20/12/2021 | 13/09/2024 | 24/11/2023 | 24/01/2022 | 974.1 | 928.06
74 | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME (SM/14883) | SM/14883 | 544.31 | 1611 | NEW | 3 | Delayed | 17 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 10/05/2023 | 92.29 | 92.29
75 | REJUVENATION OF PASCHIM SALBARI PWSS (SM/15076) | SM/15076 | 399.4 | 2840 | AUGMENTATION | 3 | Delayed | 7 | 04/02/2023 | 04/08/2023 | 12/06/2023 | 01/09/2022 | 27.4 | 9.91
76 | TESIMALA PIPED WATER SUPPLY SCHEME (SM/15970) | SM/15970 | 391.74 | 1140 | NEW | 3 | Delayed | 11 | 22/02/2023 | 31/03/2025 | 14/03/2024 | 03/08/2023 | 42.65 | 42.65
77 | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme (SM/09561) | SM/09561 | 681.79 | 1793 | AUGMENTATION | 3 | Delayed | 51 | 22/11/2021 | 31/12/2024 | 18/04/2024 | 24/01/2022 | 345.99 | 347.02
78 | Rejuvenation for Manabari Tea Garden (SM/15082) | SM/15082 | 229.62 | 0 | AUGMENTATION | 3 | Delayed | 9 | 04/02/2023 | 04/03/2024 | 15/09/2023 | 29/03/2023 | 19.92 | 19.92
79 | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/15077) | SM/15077 | 180.27 | 1068 | AUGMENTATION | 3 | Delayed | 8 | 04/02/2023 | 31/03/2024 | 09/10/2023 | 08/06/2023 | 14.11 | 14.11
80 | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME (SM/15971) | SM/15971 | 846.82 | 1963 | NEW | 3 | Delayed | 4 | 22/02/2023 | 31/03/2025 | 14/05/2024 | 05/06/2023 | 31.64 | 31.44
81 | Satkhamar Piped Water Supply Scheme. (SM/18760) | SM/18760 | 2137.78 | 7058 | NEW | 3 | Delayed | 4 | 23/08/2023 | 23/08/2025 | 02/04/2024 | 04/09/2023 | 78.82 | 78.82
82 | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/11812) | SM/11812 | 94.73 | 1206 | AUGMENTATION | 4 | Delayed | 42 | 16/08/2022 | 31/03/2024 | 08/09/2023 | 20/07/2022 | 40.14 | 40.28
83 | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme (SM/15114) | SM/15114 | 255.47 | 0 | AUGMENTATION | 4 | Delayed | 43 | 04/02/2023 | 31/03/2024 | 16/10/2023 | 16/06/2022 | 109.12 | 106.33
84 | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15296) | SM/15296 | 604.63 | 1832 | NEW | 4 | On track | 9 | 09/02/2023 | 31/03/2025 | 16/04/2024 | 08/05/2023 | 56.45 | 56.45
85 | NIRANJANPAT WATER SUPPLY SCHEME (SM/13991) | SM/13991 | 543.63 | 866 | NEW | 4 | Delayed | 20 | 01/12/2022 | 01/06/2024 | 06/12/2023 | 06/06/2023 | 108.33 | 108.33
86 | PATKATA ZONE-III PIPED WATER SUPPLY (SM/14878) | SM/14878 | 727.68 | 2535 | NEW | 4 | Delayed | 6 | 03/02/2023 | 31/03/2025 | 02/04/2024 | 06/06/2023 | 40.18 | 40.18
87 | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme (SM/15059) | SM/15059 | 127.24 | 0 | AUGMENTATION | 4 | Delayed | 24 | 04/02/2023 | 31/12/2024 | 27/12/2023 | 13/10/2020 | 30.21 | 30.21
88 | PIPE WATER SUPPLY SCHEME FOR TANDU (SM/13990) | SM/13990 | 177.66 | 396 | NEW | 4 | Delayed | 24 | 01/12/2022 | 31/12/2024 | 27/12/2023 | 24/03/2023 | 43.29 | 41.11
89 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14880) | SM/14880 | 732.1 | 2050 | NEW | 4 | Delayed | 3 | 03/02/2023 | 31/03/2025 | 02/02/2024 | 08/08/2023 | 22.27 | 22.27
90 | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME (SM/14908) | SM/14908 | 248.15 | 428 | NEW | 4 | Delayed | 4 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 24/03/2023 | 9.5 | 9.5
91 | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme (SM/18713) | SM/18713 | 213.69 | 1019 | AUGMENTATION | 4 | On track | 0 | 04/08/2023 | 31/12/2024 | 17/05/2024 | 10/08/2023 | 0 | 0
92 | Augmentation of Shikarpur Piped Water Supply Scheme (SM/09562) | SM/09562 | 977.54 | 3418 | AUGMENTATION | 4 | Delayed | 12 | 22/11/2021 | 31/12/2024 | 18/04/2024 | 17/02/2022 | 119.84 | 119.84
93 | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME (SM/15339) | SM/15339 | 980.45 | 4224 | NEW | 4 | Delayed | 7 | 09/02/2023 | 31/03/2025 | 02/04/2024 | 02/08/2023 | 71.49 | 71.49
94 | PANI KAURI PIPED WATER SUPPLY SCHEME (SM/14241) | SM/14241 | 1381.36 | 3891 | NEW | 5 | Delayed | 2 | 16/01/2023 | 31/03/2025 | 29/02/2024 | 24/08/2023 | 24.75 | 24.75
95 | CHHOTA FAPRI WATER SUPPLY SCHEME (SM/14494) | SM/14494 | 304.33 | 758 | NEW | 5 | Delayed | 7 | 20/01/2023 | 31/03/2025 | 04/03/2024 | 03/05/2023 | 21.52 | 21.52
96 | Rejuvenation of Mathachulka Piped Water Supply Scheme (SM/15098) | SM/15098 | 175.2 | 0 | AUGMENTATION | 5 | On track | 5 | 04/02/2023 | 31/03/2025 | 02/05/2024 | 13/07/2023 | 8.59 | 4.59
97 | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME (SM/14914) | SM/14914 | 478.22 | 1164 | NEW | 5 | Delayed | 24 | 03/02/2023 | 31/03/2025 | 16/04/2024 | 13/07/2023 | 116.4 | 116.4
98 | Augmentation of Gairkata Piped Water Supply Scheme (SM/09860) | SM/09860 | 480.53 | 1787 | AUGMENTATION | 5 | Delayed | 21 | 06/12/2021 | 31/12/2023 | 03/07/2023 | 01/11/2022 | 98.74 | 85.04
99 | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME (SM/18283) | SM/18283 | 2862.78 | 19720 | AUGMENTATION | 5 | Delayed | 14 | 23/06/2023 | 23/06/2024 | 10/01/2024 | 24/07/2023 | 386.99 | 386.14
100 | REJUVENATION OF METELIBAZAR PWSS (SM/11813) | SM/11813 | 721.07 | 1904 | AUGMENTATION | 5 | Delayed | 12 | 16/08/2022 | 31/03/2024 | 16/10/2023 | 18/02/2022 | 88.11 | 88.11
101 | Saptibari Piped Water Supply Scheme. (SM/18759) | SM/18759 | 2026.68 | 663 | NEW | 6 | Delayed | 26 | 23/08/2023 | 23/08/2025 | 18/04/2024 | 04/09/2023 | 527.85 | 478.8
102 | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme (SM/15117) | SM/15117 | 196.67 | 0 | AUGMENTATION | 6 | On track | 61 | 04/02/2023 | 31/03/2025 | 18/04/2024 | 16/02/2023 | 119.51 | 119.51
103 | KHUKLUNG PIPED WATER SUPPLY SCHEME (SM/15953) | SM/15953 | 119.09 | 118 | NEW | 6 | Delayed | 8 | 22/02/2023 | 22/08/2024 | 23/04/2024 | 13/09/2023 | 9.59 | 9.59
104 | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/19175) | SM/19175 | 1266.28 | 2814 | AUGMENTATION | 6 | On track | 3 | 15/02/2024 | 31/12/2025 | 26/04/2024 | 28/02/2024 | 37.49 | 37.49
105 | REJUVENATION OF PORA PARA PWSS (SM/15101) | SM/15101 | 424.27 | 3934 | AUGMENTATION | 7 | Delayed | 5 | 04/02/2023 | 31/03/2024 | 13/10/2023 | 17/05/2023 | 19.88 | 19.88
106 | Sisubari Tea Garden Piped Water Supply Scheme (SM/16778) | SM/16778 | 326.54 | 663 | NEW | 7 | Delayed | 27 | 13/03/2023 | 13/09/2024 | 24/11/2023 | 13/07/2023 | 88.93 | 10.14
107 | CHHAOAPHALI PIPED WATER SUPPLY SCHEME (SM/13901) | SM/13901 | 236.73 | 462 | NEW | 7 | Delayed | 33 | 25/11/2022 | 31/01/2025 | 05/01/2024 | 28/04/2023 | 78.63 | 78.63
108 | Chapgar Piped Water Supply Scheme. (SM/18492) | SM/18492 | 757.75 | 0 | NEW | 7 | Delayed | 16 | 24/07/2023 | 31/03/2025 | 16/04/2024 | 08/08/2023 | 124.18 | 116.4
109 | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme (SM/15130) | SM/15130 | 182.74 | 1315 | AUGMENTATION | 7 | Delayed | 17 | 04/02/2023 | 31/12/2024 | 27/12/2023 | 18/11/2020 | 30.63 | 30.63
110 | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/18711) | SM/18711 | 584.88 | 1951 | NEW | 7 | Delayed | 19 | 04/08/2023 | 30/06/2025 | 16/04/2024 | 10/08/2023 | 112.69 | 112.69
111 | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME (SM/14881) | SM/14881 | 681.26 | 2106 | NEW | 7 | Delayed | 1 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 24/05/2023 | 9.03 | 9.03
112 | Rejuvenation of Purba Duramari Piped Water Supply Scheme (SM/15326) | SM/15326 | 206.58 | 1409 | AUGMENTATION | 8 | Delayed | 4 | 09/02/2023 | 31/12/2025 | 04/04/2024 | 22/05/2023 | 7.78 | 7.78
113 | BINNAGURI PIPED WATER SUPPLY SCHEME (SM/14198) | SM/14198 | 409.19 | 1553 | NEW | 8 | Delayed | 23 | 10/01/2023 | 31/03/2025 | 16/02/2024 | 04/08/2023 | 92.21 | 85.56
114 | Rejuvenation of Chauhaddi Piped Water Supply Scheme (SM/15033) | SM/15033 | 198.79 | 0 | AUGMENTATION | 8 | Delayed | 15 | 04/02/2023 | 31/01/2025 | 21/03/2024 | 24/05/2023 | 29.2 | 29.2
115 | REJUVENATION OF ARJI GARALBARI PWSS (SM/15030) | SM/15030 | 172.44 | 0 | AUGMENTATION | 8 | Delayed | 37 | 04/02/2023 | 31/03/2024 | 11/10/2023 | 25/04/2023 | 64.6 | 64.6
116 | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. (SM/08578) | SM/08578 | 150.29 | 285 | NEW | 8 | On track | 0 | 10/02/2021 | 31/03/2025 | 17/05/2024 | 23/05/2022 | 0 | 0
117 | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza (SM/09859) | SM/09859 | 114.69 | 0 | AUGMENTATION | 9 | Delayed | 32 | 06/12/2021 | 31/03/2025 | 01/02/2024 | 05/10/2021 | 36.73 | 36.57
118 | BARA DIGHI PIPED WATER SUPPLY SCHEME (SM/13703) | SM/13703 | 156.26 | 210 | NEW | 9 | Delayed | 11 | 14/11/2022 | 14/05/2024 | 13/10/2023 | 25/08/2022 | 17.37 | 17.37
119 | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14911) | SM/14911 | 274.41 | 590 | NEW | 9 | Delayed | 9 | 03/02/2023 | 31/03/2025 | 16/04/2024 | 04/08/2023 | 24.46 | 24.46
120 | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme (SM/15103) | SM/15103 | 149.74 | 0 | AUGMENTATION | 10 | Delayed | 11 | 04/02/2023 | 31/03/2025 | 05/02/2024 | 30/05/2023 | 15.73 | 15.73
121 | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II (SM/18094) | SM/18094 | 185.13 | 0 | AUGMENTATION | 10 | Delayed | 9 | 27/03/2023 | 31/12/2024 | 22/03/2024 | 06/06/2023 | 16.66 | 16.66
122 | Rejuvenation of Ambari Falakata Piped Water Supply Scheme (SM/09487) | SM/09487 | 217.47 | 0 | AUGMENTATION | 10 | Delayed | 26 | 19/11/2021 | 31/12/2024 | 18/04/2024 | 09/03/2022 | 56.99 | 45.76
123 | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15978) | SM/15978 | 391.48 | 988 | NEW | 10 | Delayed | 18 | 22/02/2023 | 31/03/2025 | 03/03/2024 | 23/05/2023 | 70.59 | 70.59
124 | Dakshin Jharalta Piped Water Supply Scheme. (SM/18835) | SM/18835 | 1190.83 | 3531 | NEW | 10 | Delayed | 37 | 21/09/2023 | 21/09/2025 | 12/04/2024 | 23/10/2023 | 440.19 | 368.14
125 | RETROFITTING OF MAHITNAGAR PWSS (SM/15131) | SM/15131 | 180.43 | 0 | RETROFITTING | 10 | Delayed | 39 | 04/02/2023 | 31/12/2024 | 07/03/2024 | 08/06/2023 | 69.94 | 69.94
126 | Augmentation of Sannyasikata Piped Water Supply Scheme (SM/09996) | SM/09996 | 2105.11 | 6379 | AUGMENTATION | 11 | Delayed | 66 | 20/12/2021 | 31/03/2025 | 02/05/2024 | 05/04/2022 | 1393.01 | 1362.93
127 | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME (SM/14826) | SM/14826 | 551.68 | 1067 | NEW | 11 | Delayed | 31 | 04/02/2023 | 31/03/2025 | 20/01/2024 | 25/04/2023 | 171.48 | 171.48
128 | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME (SM/13898) | SM/13898 | 906.72 | 1809 | NEW | 11 | Delayed | 55 | 25/11/2022 | 31/03/2025 | 04/12/2023 | 10/04/2023 | 501.42 | 492.13
129 | AMGURI PIPED WATER SUPPLY SCHEME (SM/13706) | SM/13706 | 891.35 | 2373 | NEW | 11 | Delayed | 41 | 14/11/2022 | 13/09/2024 | 03/01/2024 | 21/03/2023 | 366.57 | 340.75
130 | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME (SM/14664) | SM/14664 | 870.88 | 2319 | NEW | 11 | Delayed | 58 | 31/01/2023 | 31/03/2024 | 26/09/2023 | 16/03/2023 | 505.98 | 505.95
131 | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME (SM/14660) | SM/14660 | 520.46 | 1074 | NEW | 11 | Delayed | 37 | 31/01/2023 | 31/03/2025 | 03/03/2024 | 25/04/2023 | 194.75 | 194.75
132 | Singimari Piped Water Supply Scheme. (SM/18761) | SM/18761 | 1138.97 | 2814 | NEW | 11 | Delayed | 16 | 23/08/2023 | 23/08/2025 | 16/04/2024 | 26/09/2023 | 176.91 | 165.62
133 | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME (SM/18357) | SM/18357 | 1031.07 | 3403 | NEW | 11 | Delayed | 20 | 11/07/2023 | 11/07/2025 | 24/01/2024 | 24/07/2023 | 205.87 | 200.13
134 | GAURGRAM PIPED WATER SUPPLY SCHEME (SM/13701) | SM/13701 | 594.88 | 1472 | NEW | 11 | Delayed | 35 | 14/11/2022 | 31/03/2025 | 27/02/2024 | 08/08/2023 | 211.08 | 200.44
135 | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme (SM/15301) | SM/15301 | 391.48 | 0 | AUGMENTATION | 11 | Delayed | 11 | 09/02/2023 | 31/03/2025 | 02/05/2024 | 24/11/2020 | 41.78 | 0
136 | Bagrakote Tea Garden Area Piped Water Supply Scheme. (SM/08874) | SM/08874 | 518.37 | 4594 | NEW | 11 | Delayed | 28 | 22/09/2021 | 13/09/2024 | 24/11/2023 | 03/02/2022 | 144.75 | 144.01
137 | Rejuvenation of Mainatali Piped Water Supply Scheme (SM/09565) | SM/09565 | 104.11 | 0 | AUGMENTATION | 11 | Delayed | 31 | 22/11/2021 | 31/12/2024 | 18/04/2024 | 29/03/2023 | 31.78 | 31.78
138 | KANTADIGHI KUMARPARA TEA GARDEN (SM/14879) | SM/14879 | 841.22 | 2481 | NEW | 11 | Delayed | 26 | 03/02/2023 | 31/01/2025 | 22/01/2024 | 10/05/2023 | 217.62 | 217.62
139 | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/16773) | SM/16773 | 171.57 | 527 | AUGMENTATION | 11 | Delayed | 30 | 13/03/2023 | 31/03/2025 | 10/05/2024 | 04/08/2023 | 52.25 | 52.25
140 | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme (SM/15300) | SM/15300 | 159.96 | 0 | AUGMENTATION | 11 | Delayed | 21 | 09/02/2023 | 31/12/2024 | 16/05/2024 | 08/06/2023 | 34.02 | 15.04
141 | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/17681) | SM/17681 | 116.16 | 240 | AUGMENTATION | 11 | Delayed | 26 | 17/03/2023 | 31/03/2025 | 02/05/2024 | 08/06/2023 | 30.18 | 30.18
142 | BARAGHARIA Piped Water Supply Scheme. (SM/17649) | SM/17649 | 613.18 | 2063 | NEW | 11 | Delayed | 43 | 22/03/2023 | 22/09/2024 | 07/12/2023 | 25/04/2023 | 263.23 | 263.23
143 | Kumarpara Piped Water Supply Scheme. (SM/18491) | SM/18491 | 845.25 | 2400 | NEW | 11 | Delayed | 39 | 24/07/2023 | 31/03/2025 | 16/04/2024 | 08/08/2023 | 325.61 | 304.99
144 | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme (SM/09863) | SM/09863 | 172.79 | 0 | AUGMENTATION | 11 | Delayed | 59 | 06/12/2021 | 31/03/2025 | 02/05/2024 | 29/04/2022 | 102.16 | 99.18
145 | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme (SM/09483) | SM/09483 | 188.47 | 0 | AUGMENTATION | 12 | Delayed | 14 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 21/01/2022 | 26.53 | 26.53
146 | JHAR SHALBARI PIPED WATER SUPPLY SCHEME (SM/15742) | SM/15742 | 678.84 | 1391 | NEW | 12 | On track | 10 | 20/02/2023 | 31/12/2025 | 04/04/2024 | 28/04/2023 | 68.13 | 62.85
147 | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME (SM/14887) | SM/14887 | 641.1 | 1619 | NEW | 12 | Delayed | 5 | 03/02/2023 | 31/12/2025 | 06/05/2024 | 30/05/2023 | 31.42 | 19.59
148 | Augmentation of Jalapara Piped Water Supply Scheme (SM/10043) | SM/10043 | 620.86 | 1573 | AUGMENTATION | 12 | Delayed | 19 | 20/01/2022 | 20/10/2022 | 12/06/2023 | 01/09/2022 | 120.13 | 119.99
149 | BASUSUBA PIPED WATER SUPPLY SCHEME (SM/18359) | SM/18359 | 1257.66 | 2822 | NEW | 12 | Delayed | 24 | 11/07/2023 | 11/07/2025 | 02/05/2024 | 28/07/2023 | 299.78 | 299.78
150 | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N (SM/13987) | SM/13987 | 756.71 | 2286 | NEW | 12 | Delayed | 33 | 01/12/2022 | 31/01/2025 | 20/01/2024 | 10/05/2023 | 247.78 | 198.51
151 | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS (SM/15068) | SM/15068 | 70.86 | 0 | AUGMENTATION | 12 | Delayed | 24 | 04/02/2023 | 31/03/2025 | 18/04/2024 | 14/07/2023 | 17.32 | 17.32
152 | Augmentation of Odlabari Piped Water Supply Scheme (SM/13790) | SM/13790 | 1003.52 | 3348 | AUGMENTATION | 12 | Delayed | 46 | 21/10/2022 | 31/03/2025 | 20/01/2024 | 05/04/2022 | 464.49 | 464.49
153 | Augmentation of Banerhat Bazar Piped Water Supply Scheme (SM/10044) | SM/10044 | 671.77 | 3913 | AUGMENTATION | 12 | Delayed | 40 | 20/01/2022 | 31/03/2025 | 01/02/2024 | 02/11/2022 | 265.71 | 265.71
154 | CHAR CHARABARI PIPED WATER SUPPLY SCHEME (SM/16042) | SM/16042 | 568.49 | 1370 | NEW | 12 | Delayed | 36 | 22/02/2023 | 31/12/2025 | 04/04/2024 | 08/05/2023 | 204.73 | 204.73
155 | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME (SM/16041) | SM/16041 | 918.46 | 2356 | NEW | 12 | Delayed | 13 | 22/02/2023 | 31/03/2025 | 19/03/2024 | 07/06/2023 | 121.75 | 112.33
156 | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME (SM/18360) | SM/18360 | 1152.06 | 4224 | NEW | 12 | On track | 18 | 11/07/2023 | 11/07/2025 | 19/03/2024 | 10/08/2023 | 203.93 | 195.9
157 | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME (SM/16181) | SM/16181 | 613.74 | 1385 | NEW | 12 | Delayed | 30 | 22/02/2023 | 31/12/2025 | 06/05/2024 | 15/05/2023 | 187.03 | 170.51
158 | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME (SM/14919) | SM/14919 | 366.08 | 892 | NEW | 13 | Delayed | 25 | 03/02/2023 | 31/03/2024 | 10/10/2023 | 27/03/2023 | 89.88 | 71.21
159 | KAOAGAP PIPED WATER SUPPLY SCHEME (SM/14199) | SM/14199 | 647.34 | 984 | NEW | 13 | Delayed | 32 | 10/01/2023 | 31/03/2025 | 18/04/2024 | 21/03/2023 | 210.23 | 205.42
160 | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme (SM/16772) | SM/16772 | 156.25 | 1459 | AUGMENTATION | 13 | Delayed | 10 | 13/03/2023 | 31/03/2025 | 05/02/2024 | 07/06/2023 | 15.27 | 15.27
161 | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME (SM/16040) | SM/16040 | 386.02 | 774 | NEW | 13 | Delayed | 38 | 22/02/2023 | 31/12/2025 | 04/04/2024 | 21/10/2022 | 145.17 | 145.17
162 | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME (SM/13681) | SM/13681 | 807.25 | 2185 | NEW | 13 | On track | 23 | 14/11/2022 | 31/12/2025 | 12/04/2024 | 09/08/2023 | 188.52 | 188.52
163 | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME (SM/14665) | SM/14665 | 417.67 | 425 | NEW | 13 | Delayed | 27 | 31/01/2023 | 31/07/2024 | 10/10/2023 | 27/03/2023 | 110.81 | 109.98
164 | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme (SM/17185) | SM/17185 | 180.04 | 940 | AUGMENTATION | 14 | Delayed | 21 | 15/03/2023 | 31/12/2024 | 27/12/2023 | 26/05/2023 | 38.29 | 38.29
165 | SHAKATI PIPED WATER SUPPLY SCHEME (SM/13704) | SM/13704 | 557.7 | 1179 | NEW | 14 | Delayed | 38 | 14/11/2022 | 31/03/2024 | 10/10/2023 | 25/04/2023 | 211.64 | 204.57
166 | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme (SM/15298) | SM/15298 | 241.44 | 0 | AUGMENTATION | 14 | Delayed | 33 | 09/02/2023 | 31/03/2025 | 05/02/2024 | 13/04/2023 | 80.09 | 80.09
167 | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME (SM/13900) | SM/13900 | 738.1 | 1527 | NEW | 14 | Delayed | 22 | 25/11/2022 | 31/03/2025 | 16/04/2024 | 08/05/2023 | 161.83 | 161.83
168 | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME (SM/15096) | SM/15096 | 119.1 | 0 | AUGMENTATION | 15 | On track | 12 | 04/02/2023 | 31/12/2024 | 06/05/2024 | 14/07/2022 | 13.9 | 10.22
169 | HAIHAIPATHAR PWSS (SM/16852) | SM/16852 | 741.68 | 2306 | NEW | 15 | Delayed | 31 | 13/03/2023 | 31/12/2024 | 18/04/2024 | 08/06/2023 | 231.86 | 231.86
170 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme (SM/06960) | SM/06960 | 99.43 | 1692 | RETROFITTING | 15 | On track | 50 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 29/11/2023 | 50 | 8.94
171 | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme (SM/15075) | SM/15075 | 158.29 | 0 | AUGMENTATION | 15 | On track | 11 | 04/02/2023 | 31/12/2025 | 04/04/2024 | 02/02/2022 | 17.56 | 17.56
172 | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME (SM/15338) | SM/15338 | 121.26 | 0 | AUGMENTATION | 15 | Delayed | 36 | 09/02/2023 | 31/12/2024 | 14/05/2024 | 05/10/2023 | 43.74 | 43.74
173 | Rejuvenation of Bhangarhat Piped Water Supply Scheme (SM/15032) | SM/15032 | 178.3 | 0 | AUGMENTATION | 15 | Delayed | 17 | 04/02/2023 | 31/03/2025 | 16/04/2024 | 24/05/2023 | 29.83 | 29.83
174 | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME (SM/15109) | SM/15109 | 182.13 | 0 | AUGMENTATION | 15 | Delayed | 24 | 04/02/2023 | 31/12/2024 | 06/05/2024 | 26/07/2023 | 43.62 | 15.35
175 | Rejuvenation of Mallicksova Piped water Supply Scheme (SM/09485) | SM/09485 | 178.69 | 0 | AUGMENTATION | 15 | Delayed | 44 | 19/11/2021 | 31/12/2024 | 18/04/2024 | 20/04/2022 | 78.45 | 76.62
176 | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS (SM/15071) | SM/15071 | 177.04 | 1015 | AUGMENTATION | 15 | Delayed | 15 | 04/02/2023 | 31/12/2024 | 18/04/2024 | 01/06/2023 | 25.96 | 25.96
177 | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME (SM/15089) | SM/15089 | 151.59 | 0 | AUGMENTATION | 16 | On track | 13 | 04/02/2023 | 31/12/2025 | 16/04/2024 | 08/06/2023 | 18.98 | 18.98
178 | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS (SM/16937) | SM/16937 | 161.99 | 0 | AUGMENTATION | 16 | Delayed | 12 | 16/03/2023 | 31/12/2024 | 06/05/2024 | 06/06/2023 | 19.17 | 8.2
179 | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza (SM/09865) | SM/09865 | 110.47 | 0 | AUGMENTATION | 16 | Delayed | 54 | 06/12/2021 | 31/12/2023 | 03/07/2023 | 22/07/2022 | 59.89 | 55.79
180 | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme (SM/15078) | SM/15078 | 157.06 | 0 | AUGMENTATION | 16 | Delayed | 12 | 04/02/2023 | 31/03/2025 | 20/02/2024 | 28/04/2023 | 18.79 | 18.79
181 | SALUGARA PIPED WATER SUPPLY SCHEME (SM/18625) | SM/18625 | 1182.82 | 5286 | NEW | 16 | Delayed | 20 | 31/07/2023 | 31/07/2025 | 16/02/2024 | 13/09/2023 | 241.29 | 241.29
182 | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME (SM/13899) | SM/13899 | 772.86 | 1798 | NEW | 17 | Delayed | 40 | 25/11/2022 | 31/03/2025 | 05/02/2024 | 24/05/2023 | 308.84 | 308.84
183 | AUGMENTATION OF LUKSAN BAZAR PWSS (SM/11814) | SM/11814 | 616.25 | 1895 | AUGMENTATION | 17 | Delayed | 28 | 16/08/2022 | 31/03/2024 | 26/09/2023 | 30/03/2022 | 173.81 | 154.55
184 | MAHANBHITA PIPED WATER SUPPLY SCHEME (SM/13702) | SM/13702 | 868.48 | 2113 | NEW | 17 | Delayed | 34 | 14/11/2022 | 31/12/2025 | 07/03/2024 | 25/04/2023 | 292.3 | 292.3
185 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT (SM/10775) | SM/10775 | 536.12 | 783 | NEW | 17 | Delayed | 14 | 23/05/2022 | 31/12/2023 | 03/07/2023 | 01/06/2022 | 74.74 | 74.74
186 | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. (SM/08581) | SM/08581 | 172.9 | 562 | NEW | 17 | On track | 24 | 10/02/2021 | 31/12/2025 | 11/03/2024 | 23/05/2022 | 41.48 | 41.48
187 | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme (SM/15116) | SM/15116 | 194.43 | 0 | AUGMENTATION | 17 | On track | 20 | 04/02/2023 | 04/08/2025 | 16/04/2024 | 25/05/2023 | 38.7 | 38.7
188 | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME (SM/15031) | SM/15031 | 161.99 | 0 | AUGMENTATION | 17 | Delayed | 21 | 04/02/2023 | 31/03/2025 | 18/04/2024 | 16/03/2023 | 34.41 | 34.41
189 | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme (SM/15099) | SM/15099 | 150.59 | 0 | AUGMENTATION | 18 | Delayed | 26 | 04/02/2023 | 31/03/2025 | 05/02/2024 | 31/03/2022 | 38.96 | 38.96
190 | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. (SM/08876) | SM/08876 | 1136.39 | 3422 | AUGMENTATION | 18 | Delayed | 37 | 22/09/2021 | 31/03/2025 | 01/02/2024 | 02/02/2022 | 418.8 | 391.59
191 | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME (SM/15132) | SM/15132 | 189.88 | 0 | RETROFITTING | 18 | Delayed | 28 | 04/02/2023 | 31/03/2024 | 11/10/2023 | 08/06/2023 | 52.94 | 51.35
192 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Pradhanpara Mouza Under Sajnapara Piped Water Supply Scheme (SM/07302) | SM/07302 | 75.74 | 1309 | RETROFITTING | 18 | On track | 100 | 10/12/2020 | 10/03/2021 | 12/06/2023 | 29/11/2023 | 75.74 | 3.5
193 | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME (SM/14882) | SM/14882 | 558.05 | 1110 | NEW | 19 | Delayed | 28 | 04/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 158.1 | 158.1
194 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block (SM/08035) | SM/08035 | 320.18 | 5856 | RETROFITTING | 19 | Delayed | 34 | 02/02/2021 | 02/05/2021 | 12/06/2023 | 13/05/2021 | 109.02 | 104.19
195 | Augmentation of Kathapara Piped Water Supply Scheme (SM/09563) | SM/09563 | 834.88 | 2665 | AUGMENTATION | 20 | Delayed | 37 | 22/11/2021 | 31/12/2023 | 03/07/2023 | 17/03/2022 | 312.42 | 198.41
196 | SAMAR NAGAR PIPED WATER SUPPLY SCHEME (SM/14200) | SM/14200 | 779.1 | 2644 | NEW | 20 | Delayed | 33 | 10/01/2023 | 31/03/2024 | 06/10/2023 | 29/03/2023 | 253.41 | 246.56
197 | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). (SM/08965) | SM/08965 | 479.35 | 0 | ANGANWADI | 20 | Delayed | 0 | 28/10/2021 |  | 05/05/2023 | 03/12/2021 | 0 | 0
198 | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME (SM/14667) | SM/14667 | 464.69 | 469 | NEW | 21 | Delayed | 32 | 31/01/2023 | 13/09/2024 | 22/02/2024 | 21/03/2023 | 147.17 | 147.17
199 | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15990) | SM/15990 | 406.46 | 1096 | NEW | 22 | Delayed | 36 | 22/02/2023 | 31/12/2024 | 18/04/2024 | 13/04/2023 | 145.99 | 145.99
200 | Rejuvenation for Patkidaha Piped Water Supply Scheme (SM/15085) | SM/15085 | 145.15 | 0 | AUGMENTATION | 25 | On track | 23 | 04/02/2023 | 31/03/2025 | 05/02/2024 | 29/11/2021 | 33 | 33
201 | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14666) | SM/14666 | 852.43 | 2390 | NEW | 26 | Delayed | 44 | 31/01/2023 | 31/03/2024 | 12/10/2023 | 31/07/2023 | 370.83 | 364.52
202 | Rejuvenation of Boalmari piped water supply scheme. (SM/09462) | SM/09462 | 113.6 | 0 | AUGMENTATION | 26 | Delayed | 92 | 19/11/2021 | 31/03/2025 | 02/05/2024 | 11/03/2022 | 104.57 | 102.13
203 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block (SM/08078) | SM/08078 | 136.18 | 2090 | RETROFITTING | 27 | Delayed | 18 | 04/02/2021 | 04/05/2021 | 12/06/2023 | 02/07/2021 | 23.97 | 23.97
204 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block (SM/07891) | SM/07891 | 285.66 | 4696 | RETROFITTING | 27 | Delayed | 26 | 19/01/2021 | 19/04/2021 | 12/06/2023 | 23/02/2021 | 74.53 | 74.53
205 | SIMULGURI PIPED WATER SUPPLY SCHEME (SM/14240) | SM/14240 | 1172.27 | 2948 | NEW | 27 | Delayed | 51 | 16/01/2023 | 31/03/2025 | 02/05/2024 | 29/03/2023 | 593.37 | 540.3
206 | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME (SM/15261) | SM/15261 | 545.43 | 966 | NEW | 28 | Delayed | 16 | 08/02/2023 | 31/03/2024 | 27/09/2023 | 29/03/2023 | 87 | 87
207 | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST (SM/13989) | SM/13989 | 143.56 | 360 | NEW | 29 | Delayed | 48 | 01/12/2022 | 31/03/2025 | 02/05/2024 | 29/03/2023 | 68.67 | 68.13
208 | Augmentation of Lataguri Piped Water Supply Scheme (SM/13278) | SM/13278 | 1834.7 | 4977 | AUGMENTATION | 30 | Delayed | 65 | 19/09/2022 | 31/12/2024 | 18/04/2024 | 23/08/2021 | 1195.65 | 1188.64
209 | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. (SM/10071) | SM/10071 | 521.15 | 1235 | AUGMENTATION | 30 | Delayed | 60 | 27/01/2022 | 31/03/2024 | 01/02/2024 | 05/04/2022 | 311.69 | 278.71
210 | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA (SM/13988) | SM/13988 | 355.6 | 1157 | NEW | 30 | Delayed | 49 | 01/12/2022 | 31/03/2024 | 23/08/2023 | 02/08/2023 | 172.66 | 172.66
211 | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15264) | SM/15264 | 345.92 | 1080 | NEW | 32 | Delayed | 44 | 07/02/2023 | 30/06/2024 | 16/04/2024 | 25/01/2022 | 151.17 | 134.55
212 | Augmentation of Binnaguri Piped Water Supply Scheme (SM/09344) | SM/09344 | 871.08 | 2082 | AUGMENTATION | 33 | Delayed | 57 | 12/11/2021 | 31/03/2024 | 03/07/2023 | 02/02/2022 | 495.06 | 376.58
213 | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14885) | SM/14885 | 913.53 | 2665 | NEW | 34 | Delayed | 53 | 03/02/2023 | 13/09/2024 | 24/11/2023 | 28/07/2023 | 484.57 | 484.57
214 | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme (SM/09392) | SM/09392 | 290.82 | 1462 | AUGMENTATION | 34 | Delayed | 45 | 12/11/2021 | 31/12/2023 | 03/07/2023 | 03/03/2022 | 132.13 | 130.93
215 | Rejuvenation of Sajnapara Piped Water Supply Scheme (SM/09391) | SM/09391 | 92.36 | 0 | AUGMENTATION | 35 | Delayed | 39 | 12/11/2021 | 31/12/2023 | 03/07/2023 | 14/09/2022 | 36.15 | 29.35
216 | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/18356) | SM/18356 | 1140.38 | 2798 | NEW | 35 | On track | 12 | 11/07/2023 | 11/07/2025 | 31/01/2024 | 24/07/2023 | 131.32 | 126.51
217 | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15262) | SM/15262 | 635.17 | 1408 | NEW | 37 | Delayed | 39 | 08/02/2023 | 31/12/2024 | 27/12/2023 | 09/08/2023 | 245.9 | 245.9
218 | Rejuvenation of Purbba Salbari Piped Water Supply Scheme (SM/09861) | SM/09861 | 696.59 | 2219 | AUGMENTATION | 39 | Delayed | 83 | 06/12/2021 | 31/12/2023 | 25/07/2023 | 05/04/2022 | 575.18 | 445.07
219 | Augmentation of Kharija-Berubari Water Supply Scheme. (SM/10088) | SM/10088 | 2064.37 | 5781 | AUGMENTATION | 40 | Delayed | 55 | 01/02/2022 | 31/03/2024 | 17/08/2023 | 27/12/2021 | 1127.4 | 1010.52
220 | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza (SM/09862) | SM/09862 | 105.33 | 0 | AUGMENTATION | 42 | Delayed | 89 | 06/12/2021 | 31/12/2023 | 16/10/2023 | 24/02/2022 | 93.55 | 83.78
221 | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme (SM/10069) | SM/10069 | 243.7 | 0 | AUGMENTATION | 43 | Delayed | 58 | 27/01/2022 | 31/03/2024 | 16/10/2023 | 22/12/2022 | 140.2 | 140.2
222 | Augmentation of Porjhar Pipe Water Supply Scheme (SM/15302) | SM/15302 | 597.01 | 2564 | AUGMENTATION | 43 | On track | 8 | 09/02/2023 | 31/03/2025 | 16/04/2024 | 04/08/2023 | 50.32 | 32.38
223 | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. (SM/09564) | SM/09564 | 139.18 | 0 | AUGMENTATION | 44 | Delayed | 43 | 22/11/2021 | 31/12/2023 | 03/07/2023 | 11/01/2022 | 60.43 | 58.06
224 | Rejuvenation of Madhabdanga piped water supply scheme. (SM/09456) | SM/09456 | 125.38 | 0 | AUGMENTATION | 45 | Delayed | 85 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 27/12/2021 | 106.32 | 106.32
225 | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15115) | SM/15115 | 560.37 | 1368 | NEW | 45 | Delayed | 51 | 04/02/2023 | 31/12/2024 | 27/12/2023 | 08/05/2023 | 286.11 | 286.11
226 | Augmentation of Mondalghat Water Supply Scheme. (SM/10087) | SM/10087 | 1095.64 | 3793 | AUGMENTATION | 45 | Delayed | 63 | 01/02/2022 | 31/12/2023 | 03/07/2023 | 24/06/2020 | 693.77 | 640.53
227 | Rejuvenation of Khalaigram Piped Water Supply Scheme (SM/09486) | SM/09486 | 66.14 | 0 | AUGMENTATION | 47 | Delayed | 74 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 21/01/2022 | 48.73 | 48.76
228 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. (SM/09099) | SM/09099 | 163.94 | 1369 | RETROFITTING | 48 | Delayed | 54 | 28/10/2021 | 31/12/2023 | 02/08/2023 | 27/09/2021 | 88.19 | 85.19
229 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block (SM/07893) | SM/07893 | 133.21 | 2191 | RETROFITTING | 49 | Delayed | 55 | 19/01/2021 | 19/04/2021 | 12/06/2023 | 23/02/2021 | 73.51 | 52.02
230 | Rejuvenation of Charerbari piped water supply scheme. (SM/09458) | SM/09458 | 115.93 | 0 | AUGMENTATION | 49 | Delayed | 80 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 27/12/2021 | 93.02 | 93.02
231 | Bhagatpur Tea Garden Area Piped Water Supply Scheme. (SM/09975) | SM/09975 | 385.01 | 1906 | NEW | 50 | Delayed | 51 | 22/09/2021 | 31/12/2023 | 17/07/2023 | 24/01/2022 | 198.13 | 198.17
232 | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. (SM/09518) | SM/09518 | 114.34 | 0 | AUGMENTATION | 50 | Delayed | 69 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 04/04/2022 | 79.04 | 61.16
233 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block (SM/08284) | SM/08284 | 137.5 | 2315 | RETROFITTING | 51 | Delayed | 17 | 09/02/2021 | 09/05/2021 | 12/06/2023 | 01/02/2021 | 23.63 | 19.02
234 | Augmentation of Dakshin Berubari Water Supply Scheme. (SM/10086) | SM/10086 | 1574.27 | 4905 | AUGMENTATION | 52 | Delayed | 65 | 01/02/2022 | 31/12/2023 | 03/07/2023 | 02/02/2022 | 1017.77 | 842.17
235 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (SM/09100) | SM/09100 | 382.83 | 4346 | RETROFITTING | 53 | Delayed | 68 | 28/10/2021 | 31/12/2022 | 12/06/2023 | 21/01/2022 | 260.43 | 247.22
236 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/09858) | SM/09858 | 171.5 | 0 | AUGMENTATION | 55 | Delayed | 59 | 06/12/2021 | 31/12/2023 | 16/10/2023 | 23/03/2022 | 100.73 | 99.67
237 | Rejuvenation of Kajaldighi piped water supply scheme. (SM/09457) | SM/09457 | 116.9 | 0 | AUGMENTATION | 55 | Delayed | 18 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 06/04/2023 | 21.59 | 21.59
238 | Rejuvenation of Chakiavita Piped Water Supply Scheme (SM/09482) | SM/09482 | 119.98 | 0 | AUGMENTATION | 56 | Delayed | 60 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 07/01/2021 | 71.91 | 71.54
239 | Augmentation of Barnes Water Supply Scheme. (SM/10090) | SM/10090 | 1115.54 | 4046 | AUGMENTATION | 56 | Delayed | 84 | 01/02/2022 | 31/12/2023 | 03/07/2023 | 24/06/2020 | 941.44 | 838.19
240 | Indong Tea Garden Area Piped Water Supply Scheme. (SM/08873) | SM/08873 | 311.47 | 1236 | NEW | 56 | Delayed | 42 | 22/09/2021 | 31/12/2023 | 03/07/2023 | 25/01/2022 | 132.02 | 132.02
241 | Augmentation of Purbba Batabari Piped Water Supply Scheme (SM/09864) | SM/09864 | 810.11 | 1795 | AUGMENTATION | 56 | Delayed | 51 | 06/12/2021 | 31/12/2023 | 02/08/2023 | 13/08/2020 | 410.68 | 413.55
242 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme (SM/06937) | SM/06937 | 129.58 | 2431 | RETROFITTING | 57 | Delayed | 97 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 18/01/2021 | 126.3 | 112.72
243 | Ghasmari Piped Water Supply Scheme. (SM/08868) | SM/08868 | 293.24 | 779 | NEW | 57 | Delayed | 58 | 20/09/2021 | 31/03/2024 | 16/10/2023 | 24/01/2022 | 170.19 | 128.92
244 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block (SM/07892) | SM/07892 | 131.79 | 1950 | RETROFITTING | 59 | Delayed | 65 | 19/01/2021 | 19/04/2021 | 12/06/2023 | 23/02/2021 | 85.37 | 54.21
245 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme (SM/08077) | SM/08077 | 62.08 | 1080 | RETROFITTING | 61 | On track | 100 | 04/02/2021 | 04/05/2021 | 12/06/2023 | 13/03/2023 | 62.08 | 61.14
246 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme (SM/06961) | SM/06961 | 75.45 | 1259 | RETROFITTING | 61 | On track | 100 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 29/11/2023 | 75.45 | 35.13
247 | Rejuvenation of Chauhaddi Piped Water Supply Scheme (SM/09484) | SM/09484 | 226.32 | 0 | AUGMENTATION | 62 | Delayed | 91 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 03/02/2022 | 205.68 | 200.74
248 | Rejuvenation of Goralbari Piped Water Supply Scheme (SM/09390) | SM/09390 | 337.55 | 0 | AUGMENTATION | 62 | Delayed | 69 | 12/11/2021 | 31/12/2023 | 03/07/2023 | 30/11/2021 | 232.25 | 327.65
249 | Augmentation of Baikur Piped Water Supply Scheme. (SM/10089) | SM/10089 | 1763.64 | 7173 | AUGMENTATION | 64 | Delayed | 75 | 01/02/2022 | 31/12/2023 | 03/07/2023 | 24/06/2020 | 1327.08 | 1207.47
250 | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme (SM/06842) | SM/06842 | 48.73 | 873 | RETROFITTING | 65 | Delayed | 22 | 06/10/2020 | 06/01/2021 | 12/06/2023 | 02/11/2020 | 10.56 | 10.56
251 | Rejuvenation of Porapara piped water supply scheme. (SM/09463) | SM/09463 | 121.26 | 0 | AUGMENTATION | 65 | Delayed | 92 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 22/04/2022 | 112.12 | 110.62
252 | Augmentation of Sukani Piped Water Supply Scheme (SM/09995) | SM/09995 | 4370.14 | 14294 | AUGMENTATION | 67 | Delayed | 53 | 20/12/2021 | 31/12/2023 | 17/07/2023 | 13/03/2020 | 2315.16 | 2225.41
253 | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. (SM/08579) | SM/08579 | 137.33 | 238 | NEW | 67 | Delayed | 48 | 10/02/2021 | 31/12/2023 | 03/07/2023 | 25/02/2021 | 65.51 | 65.51
254 | Augmentation of Ramsai Water Supply Scheme. (SM/10033) | SM/10033 | 976.19 | 3250 | AUGMENTATION | 67 | Delayed | 76 | 19/01/2022 | 31/12/2023 | 03/07/2023 | 24/06/2020 | 746.66 | 706.28
255 | Augmentation of Domohani Piped Water Supply Scheme (SM/09345) | SM/09345 | 855.56 | 2548 | AUGMENTATION | 70 | Delayed | 66 | 12/11/2021 | 31/12/2023 | 03/07/2023 | 18/04/2022 | 566.31 | 594.37
256 | Rejuvenation of Basilardanga piped water supply scheme. (SM/09460) | SM/09460 | 115.16 | 0 | AUGMENTATION | 71 | Delayed | 91 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 27/12/2021 | 105.01 | 105.01
257 | Augmentation of Madhya Khagrabari Water Supply Scheme. (SM/10028) | SM/10028 | 986.41 | 3594 | AUGMENTATION | 71 | Delayed | 89 | 17/01/2022 | 31/12/2023 | 03/07/2023 | 24/06/2020 | 876.66 | 715.39
258 | Rejuvenation of Hila Tea Garden area piped water supply scheme (SM/10070) | SM/10070 | 208.35 | 0 | AUGMENTATION | 72 | On track | 72 | 27/01/2022 | 31/03/2025 | 02/05/2024 | 29/01/2021 | 149.58 | 140.04
259 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme (SM/06841) | SM/06841 | 89.57 | 1671 | RETROFITTING | 74 | Delayed | 100 | 06/10/2020 | 06/01/2021 | 12/06/2023 | 22/12/2020 | 89.57 | 89.1
260 | Augmentation of Maynaguri Piped Water Supply Scheme. (SM/10042) | SM/10042 | 978.7 | 7191 | AUGMENTATION | 76 | Delayed | 57 | 20/01/2022 | 31/03/2023 | 03/07/2023 | 24/01/2022 | 555.33 | 630.62
261 | Augmentation of Purba Daukimari Piped Water Supply Scheme (SM/09560) | SM/09560 | 545.87 | 1586 | AUGMENTATION | 77 | Delayed | 73 | 22/11/2021 | 31/12/2023 | 03/07/2023 | 02/02/2022 | 401.07 | 433.26
262 | Rejuvenation of Mohitnagar piped water supply scheme. (SM/09519) | SM/09519 | 122.19 | 0 | AUGMENTATION | 79 | Delayed | 96 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 04/01/2022 | 117.33 | 107.71
263 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme (SM/06938) | SM/06938 | 106.41 | 1976 | RETROFITTING | 79 | Delayed | 73 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 15/10/2020 | 78.09 | 71.51
264 | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme (SM/06843) | SM/06843 | 52.3 | 925 | RETROFITTING | 80 | Delayed | 30 | 06/10/2020 | 06/01/2021 | 12/06/2023 | 23/11/2020 | 15.72 | 15.72
265 | Kumlai Tea Garden Area Piped Water Supply Scheme. (SM/08875) | SM/08875 | 303.84 | 991 | NEW | 80 | Delayed | 94 | 22/09/2021 | 31/12/2023 | 03/07/2023 | 08/12/2021 | 286.69 | 250.88
266 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block (SM/08036) | SM/08036 | 349.29 | 6704 | RETROFITTING | 83 | Delayed | 100 | 02/02/2021 | 02/05/2021 | 12/06/2023 | 02/07/2021 | 349.29 | 285.33
267 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme (SM/06839) | SM/06839 | 99.99 | 1671 | RETROFITTING | 85 | Delayed | 81 | 06/10/2020 | 06/01/2021 | 12/06/2023 | 09/10/2020 | 81.35 | 84.11
268 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme (SM/06847) | SM/06847 | 56.03 | 1019 | RETROFITTING | 86 | Delayed | 100 | 06/10/2020 | 31/12/2023 | 16/10/2023 | 18/11/2020 | 56.03 | 45
269 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme (SM/06838) | SM/06838 | 92.26 | 1664 | RETROFITTING | 89 | Delayed | 78 | 06/10/2020 | 06/01/2021 | 12/06/2023 | 15/10/2020 | 71.65 | 66.17
270 | Rejuvenation of Dwarikamari piped water supply scheme. (SM/09459) | SM/09459 | 121.4 | 0 | AUGMENTATION | 89 | Delayed | 94 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 31/12/2021 | 113.55 | 112.31
271 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block (SM/08037) | SM/08037 | 348.32 | 6385 | RETROFITTING | 92 | On track | 100 | 02/02/2021 | 02/05/2021 | 12/06/2023 | 19/09/2023 | 348.32 | 293.31
272 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme (SM/06936) | SM/06936 | 126.48 | 2332 | RETROFITTING | 93 | Delayed | 99 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 31/12/2020 | 124.94 | 111.78
273 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block (SM/06953) | SM/06953 | 48.9 | 917 | RETROFITTING | 96 | Delayed | 100 | 03/11/2020 | 31/12/2023 | 16/10/2023 | 05/01/2021 | 48.9 | 48.83
274 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme (SM/08038) | SM/08038 | 396.46 | 6473 | RETROFITTING | 98 | Delayed | 100 | 02/02/2021 | 02/05/2021 | 12/06/2023 | 28/01/2021 | 396.46 | 407.81
275 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block (SM/07301) | SM/07301 | 30.18 | 240 | RETROFITTING | 99 | Delayed | 100 | 10/12/2020 | 31/03/2024 | 16/10/2023 | 01/02/2021 | 30.18 | 30.12
276 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block (SM/08285) | SM/08285 | 268.15 | 5069 | RETROFITTING | 99 | Delayed | 100 | 09/02/2021 | 09/05/2021 | 12/06/2023 | 13/05/2021 | 268.15 | 266.3
277 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06956) | SM/06956 | 64.77 | 1225 | RETROFITTING | 99 | Delayed | 100 | 03/11/2020 | 03/02/2021 | 12/06/2023 | 01/02/2021 | 64.77 | 64.68
278 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/06844) | SM/06844 | 57.04 | 1082 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 |  | 12/06/2023 | 18/11/2020 | 57.04 | 55.79
279 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06952) | SM/06952 | 65.98 | 1257 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 31/12/2020 | 65.98 | 65.37
280 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06954) | SM/06954 | 34.5 | 607 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 31/12/2020 | 34.5 | 60.16
281 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme (SM/06959) | SM/06959 | 57.13 | 914 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 12/02/2021 | 57.13 | 118.72
282 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme (SM/07304) | SM/07304 | 36.39 | 447 | RETROFITTING | 100 | 100% Physical | 100 | 10/12/2020 |  | 12/06/2023 | 11/02/2021 | 36.39 | 71.86
283 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme (SM/06837) | SM/06837 | 61.53 | 1080 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 |  | 12/06/2023 | 18/11/2020 | 61.53 | 66.16
284 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme (SM/06840) | SM/06840 | 74.02 | 1362 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 |  | 12/06/2023 | 18/11/2020 | 74.02 | 92.52
285 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block (SM/06957) | SM/06957 | 36 | 640 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 19/01/2022 | 36 | 35.97
286 | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. (SM/09461) | SM/09461 | 70.07 | 930 | AUGMENTATION | 100 | 100% Physical | 100 | 19/11/2021 | 31/12/2023 | 03/07/2023 | 10/02/2021 | 70.07 | 88.91
287 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme (SM/06845) | SM/06845 | 60.77 | 1118 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 |  | 12/06/2023 | 18/11/2021 | 60.77 | 68.9
288 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme (SM/07303) | SM/07303 | 89.78 | 1296 | RETROFITTING | 100 | 100% Physical | 69 | 10/12/2020 |  | 12/06/2023 | 08/01/2021 | 62 | 109.28
289 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06955) | SM/06955 | 62.52 | 1205 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 01/02/2021 | 62.52 | 81.43
290 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block (SM/06958) | SM/06958 | 99.31 | 1745 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 |  | 12/06/2023 | 07/01/2021 | 99.31 | 121.12
291 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme (SM/06846) | SM/06846 | 37.11 | 632 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 |  | 12/06/2023 | 15/10/2020 | 37.11 | 40.73
Total |  |  | 126203.52 | 432831 | [8 empty] | 41613.19 | 39477