## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15610) | SM/15610 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
2 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF NAGRAKATA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15619) | SM/15619 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
3 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SAOGAON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15623) | SM/15623 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
4 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SONGACHHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15624) | SM/15624 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
5 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KAJALDIGHI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15612) | SM/15612 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
6 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MOHITNAGAR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15618) | SM/15618 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
7 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF WATER SUPPLY SCHEME OF JITI TEA GARDEN UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15622) | SM/15622 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
8 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BASILARDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15907) | SM/15907 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
9 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT JOGESH CHANDRA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15600) | SM/15600 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
10 | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14884) | SM/14884 | 710.56 | 2397 | NEW | 0 | 0% Physical | 0 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 04/08/2023 | 2.04 | 2.04
11 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR NAGRAKATA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15611) | SM/15611 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
12 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT YOUNGTONG TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15625) | SM/15625 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
13 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15604) | SM/15604 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
14 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KARBALA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15613) | SM/15613 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
15 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHAGATPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15597) | SM/15597 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
16 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA DURAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15603) | SM/15603 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
17 | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. (SM/08579) | SM/08579 | 137.33 | 238 | NEW | 0 | 0% Physical | 54 | 10/02/2021 | 31/03/2026 | 16/05/2025 | 25/02/2021 | 73.63 | 73.63
18 | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/15077) | SM/15077 | 180.27 | 1068 | AUGMENTATION | 0 | 0% Physical | 22 | 04/02/2023 | 31/03/2025 | 16/05/2025 | 08/06/2023 | 39.98 | 39.98
19 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DWARIKAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15608) | SM/15608 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
20 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SAJNAPARA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15620) | SM/15620 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
21 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15605) | SM/15605 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
22 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15607) | SM/15607 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2025 | 16/05/2025 | 27/09/2023 | 0 | 0
23 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GATIA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15609) | SM/15609 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
24 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF CHAMURCHI FOREST BUSTY WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15584) | SM/15584 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2025 | 16/05/2025 | 27/09/2023 | 0 | 0
25 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MALLICKSOVA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15616) | SM/15616 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
26 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF CHARERBARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15606) | SM/15606 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
27 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KILKOTE TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15614) | SM/15614 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
28 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GRASSMORE TEA GARDEN AREA PIPED WATER SUPPLY UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15599) | SM/15599 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2027 | 16/05/2025 | 27/09/2023 | 0 | 0
29 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT KUMLAI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15601) | SM/15601 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
30 | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME (SM/13682) | SM/13682 | 544.59 | 1332 | NEW | 0 | 0% Physical | 8 | 14/11/2022 | 31/03/2025 | 16/05/2025 | 08/06/2023 | 45.08 | 45.08
31 | REJUVENATION OF PORA PARA PWSS (SM/15101) | SM/15101 | 424.27 | 3934 | AUGMENTATION | 0 | 0% Physical | 20 | 04/02/2023 | 30/04/2026 | 16/05/2025 | 17/05/2023 | 84.9 | 84.9
32 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SYLI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15621) | SM/15621 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
33 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF DOMOHINI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15596) | SM/15596 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
34 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHANGARHAT PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15598) | SM/15598 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
35 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BAIKUR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15580) | SM/15580 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/03/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
36 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MADHABDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15615) | SM/15615 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
37 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MATHACHULKA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. (SM/15617) | SM/15617 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/02/2023 | 31/08/2026 | 16/05/2025 | 27/09/2023 | 0 | 0
38 | Sisubari Tea Garden Piped Water Supply Scheme (SM/16778) | SM/16778 | 326.54 | 663 | NEW | 0 | 0% Physical | 34 | 13/03/2023 | 31/03/2026 | 16/05/2025 | 13/07/2023 | 109.59 | 106.61
39 | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P (SM/19171) | SM/19171 | 97.03 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 08/02/2024 |  | 15/02/2024 | 07/08/2024 | 0 | 0
40 | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. (SM/11170) | SM/11170 | 14.19 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 03/06/2022 |  | 03/06/2022 | 23/11/2022 | 0 | 0
41 | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/16508) | SM/16508 | 38.98 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 20/03/2023 | 0 | 0
42 | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory (SM/08681) | SM/08681 | 9.33 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 13/08/2021 |  | 31/08/2022 | 03/12/2021 | 0 | 0
43 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities related to FHTC under JJM Support Activities at Jalpaiguri District. (SM/09018) | SM/09018 | 44.85 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 30/10/2021 |  | 02/11/2021 | 17/08/2022 | 0 | 0
44 | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/16509) | SM/16509 | 22.45 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 31/03/2023 | 0 | 0
45 | Operational charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19319) | SM/19319 | 72.79 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/12/2024 |  | 27/12/2024 |  | 0 | 0
46 | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS and annual maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. (SM/06615) | SM/06615 | 20.19 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 08/08/2022 | 0 | 0
47 | DRINKING WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KITS (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION (SM/13679) | SM/13679 | 22.25 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 14/11/2022 |  | 17/11/2022 |  | 0 | 0
48 | Sikarpur Piped Water Supply Scheme. (SM/18836) | SM/18836 | 1910.96 | 6574 | NEW | 4 | Delayed | 32 | 21/09/2023 | 21/09/2025 | 21/08/2024 | 29/11/2023 | 610.37 | 610.37
49 | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme (SM/17181) | SM/17181 | 201.66 | 1317 | AUGMENTATION | 5 | Delayed | 2 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 15/05/2023 | 4.08 | 4.08
50 | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/19175) | SM/19175 | 1266.28 | 2814 | AUGMENTATION | 5 | Delayed | 4 | 15/02/2024 | 31/12/2025 | 16/05/2025 | 28/02/2024 | 44.57 | 44.57
51 | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN (SM/16492) | SM/16492 | 461.81 | 1078 | NEW | 5 | Delayed | 14 | 02/03/2023 | 31/12/2025 | 16/05/2025 | 10/05/2023 | 65.98 | 65.98
52 | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME (SM/18355) | SM/18355 | 1573.93 | 5782 | AUGMENTATION | 9 | Delayed | 8 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 07/08/2023 | 119.56 | 119.56
53 | NOWAPARA PIPED WATER SUPPLY SCHEME (SM/18503) | SM/18503 | 1060.21 | 3633 | NEW | 10 | Delayed | 6 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 17/08/2023 | 58.41 | 58.41
54 | CHHAR TANDU PIPED WATER SUPPLY SCHEME (SM/15964) | SM/15964 | 330.17 | 573 | NEW | 10 | Delayed | 20 | 22/02/2023 | 08/02/2025 | 16/05/2025 | 08/08/2023 | 64.4 | 64.4
55 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block (SM/07892) | SM/07892 | 131.79 | 1950 | RETROFITTING | 10 | Delayed | 65 | 19/01/2021 | 31/12/2026 | 16/05/2025 | 23/02/2021 | 85.37 | 54.21
56 | KHAS JANGAL PIPED WATER SUPPLY SCHEME (SM/14907) | SM/14907 | 245.77 | 456 | NEW | 20 | Delayed | 5 | 03/02/2023 | 31/12/2025 | 16/05/2025 | 08/08/2023 | 12.35 | 12.35
57 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/15060) | SM/15060 | 285.02 | 0 | AUGMENTATION | 20 | Delayed | 32 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 22/05/2023 | 90.09 | 90.09
58 | SONAKHULI PIPED WATER SUPPLY SCHEME (SM/15744) | SM/15744 | 446.23 | 732 | NEW | 20 | Delayed | 18 | 20/02/2023 | 30/04/2026 | 16/05/2025 | 13/04/2023 | 78.91 | 78.91
59 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14880) | SM/14880 | 732.1 | 2050 | NEW | 22 | Delayed | 16 | 03/02/2023 | 31/12/2025 | 16/05/2025 | 08/08/2023 | 116.36 | 111.46
60 | REJUVENATION OF METELIBAZAR PWSS (SM/11813) | SM/11813 | 721.07 | 1904 | AUGMENTATION | 25 | Delayed | 29 | 16/08/2022 | 31/05/2025 | 16/05/2025 | 18/02/2022 | 206.11 | 206.11
61 | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME (SM/15263) | SM/15263 | 399.34 | 1212 | NEW | 25 | Delayed | 15 | 07/02/2023 | 30/06/2025 | 16/05/2025 | 10/05/2023 | 60.57 | 60.57
62 | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14886) | SM/14886 | 525.39 | 1312 | NEW | 25 | Delayed | 10 | 03/02/2023 | 31/03/2025 | 16/05/2025 | 05/06/2023 | 53.69 | 53.69
63 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block (SM/08284) | SM/08284 | 137.5 | 2315 | RETROFITTING | 25 | Delayed | 17 | 09/02/2021 | 31/07/2025 | 16/05/2025 | 01/02/2021 | 23.63 | 19.02
64 | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME (SM/15915) | SM/15915 | 427.23 | 878 | NEW | 25 | Delayed | 19 | 22/02/2023 | 31/12/2025 | 16/05/2025 | 01/09/2022 | 82.17 | 82.17
65 | CHHOTA FAPRI WATER SUPPLY SCHEME (SM/14494) | SM/14494 | 304.33 | 758 | NEW | 25 | Delayed | 26 | 20/01/2023 | 30/09/2025 | 16/05/2025 | 03/05/2023 | 79.47 | 79.47
66 | REJUVENATION OF PASCHIM SALBARI PWSS (SM/15076) | SM/15076 | 399.4 | 2840 | AUGMENTATION | 25 | Delayed | 12 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 01/09/2022 | 46.34 | 46.34
67 | SALUGARA PIPED WATER SUPPLY SCHEME (SM/18625) | SM/18625 | 1182.82 | 5286 | NEW | 30 | Delayed | 26 | 31/07/2023 | 08/02/2025 | 16/05/2025 | 13/09/2023 | 312.97 | 312.97
68 | Rejuvenation for Manabari Tea Garden (SM/15082) | SM/15082 | 229.62 | 0 | AUGMENTATION | 30 | Delayed | 21 | 04/02/2023 | 31/03/2026 | 16/05/2025 | 29/03/2023 | 48.49 | 48.49
69 | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme (SM/15301) | SM/15301 | 391.48 | 0 | AUGMENTATION | 30 | Delayed | 23 | 09/02/2023 | 30/05/2025 | 16/05/2025 | 24/11/2020 | 91.63 | 91.63
70 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block (SM/08078) | SM/08078 | 136.18 | 2090 | RETROFITTING | 30 | Delayed | 18 | 04/02/2021 | 31/12/2025 | 16/05/2025 | 02/07/2021 | 23.97 | 23.97
71 | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME (SM/15971) | SM/15971 | 846.82 | 1963 | NEW | 31 | Delayed | 21 | 22/02/2023 | 31/05/2026 | 16/05/2025 | 05/06/2023 | 179.38 | 179.38
72 | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. (SM/08578) | SM/08578 | 150.29 | 285 | NEW | 35 | Delayed | 29 | 10/02/2021 | 08/02/2025 | 16/05/2025 | 23/05/2022 | 42.87 | 42.87
73 | NIRANJANPAT WATER SUPPLY SCHEME (SM/13991) | SM/13991 | 543.63 | 866 | NEW | 35 | Delayed | 26 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 06/06/2023 | 138.66 | 138.66
74 | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME (SM/15089) | SM/15089 | 151.59 | 0 | AUGMENTATION | 35 | Delayed | 22 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 33.4 | 33.4
75 | BASUSUBA PIPED WATER SUPPLY SCHEME (SM/18359) | SM/18359 | 1257.66 | 2822 | NEW | 35 | Delayed | 25 | 11/07/2023 | 30/05/2025 | 16/05/2025 | 28/07/2023 | 314.16 | 314.16
76 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block (SM/07891) | SM/07891 | 285.66 | 4696 | RETROFITTING | 35 | Delayed | 26 | 19/01/2021 | 31/05/2025 | 16/05/2025 | 23/02/2021 | 74.53 | 74.53
77 | PANI KAURI PIPED WATER SUPPLY SCHEME (SM/14241) | SM/14241 | 1381.36 | 3891 | NEW | 35 | Delayed | 30 | 16/01/2023 | 08/02/2025 | 16/05/2025 | 24/08/2023 | 409.42 | 409.42
78 | JHAR SHALBARI PIPED WATER SUPPLY SCHEME (SM/15742) | SM/15742 | 678.84 | 1391 | NEW | 35 | Delayed | 31 | 20/02/2023 | 31/03/2025 | 16/05/2025 | 28/04/2023 | 209.92 | 204.64
79 | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15980) | SM/15980 | 350.2 | 694 | NEW | 37 | Delayed | 20 | 22/02/2023 | 31/03/2025 | 16/05/2025 | 08/08/2023 | 69.31 | 66.56
80 | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME (SM/16779) | SM/16779 | 709.31 | 2238 | NEW | 38 | Delayed | 19 | 13/03/2023 | 31/03/2025 | 16/05/2025 | 28/04/2023 | 133.96 | 133.96
81 | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme (SM/18713) | SM/18713 | 213.69 | 1019 | AUGMENTATION | 38 | Delayed | 17 | 04/08/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 35.32 | 35.32
82 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block (SM/06958) | SM/06958 | 99.31 | 1745 | RETROFITTING | 40 | Delayed | 100 | 03/11/2020 | 31/07/2025 | 16/05/2025 | 07/01/2021 | 99.31 | 121.12
83 | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME (SM/18283) | SM/18283 | 2862.78 | 19720 | AUGMENTATION | 40 | Delayed | 23 | 23/06/2023 | 31/12/2025 | 16/05/2025 | 24/07/2023 | 656.71 | 656.71
84 | BRAHMAPUR PIPED WATER SUPPLY SCHEME (SM/13705) | SM/13705 | 988.14 | 2545 | NEW | 40 | Delayed | 32 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 21/03/2023 | 319.44 | 319.44
85 | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME (SM/14224) | SM/14224 | 140.42 | 116 | NEW | 40 | Delayed | 10 | 10/01/2023 | 31/03/2026 | 16/05/2025 | 08/06/2023 | 14.17 | 14.17
86 | Singimari Piped Water Supply Scheme. (SM/18761) | SM/18761 | 1138.97 | 2814 | NEW | 40 | Delayed | 26 | 23/08/2023 | 08/02/2025 | 16/05/2025 | 26/09/2023 | 300.1 | 281.65
87 | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N (SM/13987) | SM/13987 | 756.71 | 2286 | NEW | 40 | Delayed | 37 | 01/12/2022 | 30/04/2026 | 16/05/2025 | 10/05/2023 | 276.56 | 263.21
88 | Chapgar Piped Water Supply Scheme. (SM/18492) | SM/18492 | 757.75 | 0 | NEW | 40 | Delayed | 18 | 24/07/2023 | 30/05/2025 | 16/05/2025 | 08/08/2023 | 136.54 | 128.76
89 | Augmentation of Gairkata Piped Water Supply Scheme (SM/09860) | SM/09860 | 480.53 | 1787 | AUGMENTATION | 40 | Delayed | 24 | 06/12/2021 | 31/03/2025 | 16/05/2025 | 01/11/2022 | 114.28 | 100.58
90 | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME (SM/13681) | SM/13681 | 807.25 | 2185 | NEW | 40 | Delayed | 29 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 09/08/2023 | 233.77 | 233.77
91 | MAHANBHITA PIPED WATER SUPPLY SCHEME (SM/13702) | SM/13702 | 868.48 | 2113 | NEW | 44 | Delayed | 40 | 14/11/2022 | 31/03/2025 | 16/05/2025 | 25/04/2023 | 347.59 | 347.59
92 | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME (SM/15109) | SM/15109 | 182.13 | 0 | AUGMENTATION | 44 | Delayed | 27 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 26/07/2023 | 48.72 | 48.72
93 | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme (SM/15059) | SM/15059 | 127.24 | 0 | AUGMENTATION | 45 | Delayed | 49 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 13/10/2020 | 62.04 | 62.04
94 | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II (SM/18094) | SM/18094 | 185.13 | 0 | AUGMENTATION | 45 | Delayed | 23 | 27/03/2023 | 31/12/2025 | 16/05/2025 | 06/06/2023 | 41.82 | 41.82
95 | Satkhamar Piped Water Supply Scheme. (SM/18760) | SM/18760 | 2137.78 | 7058 | NEW | 45 | Delayed | 28 | 23/08/2023 | 08/02/2025 | 16/05/2025 | 04/09/2023 | 588.35 | 588.35
96 | Rejuvenation of Ambari Falakata Piped Water Supply Scheme (SM/09487) | SM/09487 | 217.47 | 0 | AUGMENTATION | 45 | Delayed | 42 | 19/11/2021 | 31/08/2025 | 16/05/2025 | 09/03/2022 | 92.07 | 92.07
97 | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15978) | SM/15978 | 391.48 | 988 | NEW | 45 | Delayed | 54 | 22/02/2023 | 04/01/2025 | 16/05/2025 | 23/05/2023 | 212.02 | 212.02
98 | Kumarpara Piped Water Supply Scheme. (SM/18491) | SM/18491 | 845.25 | 2400 | NEW | 47 | Delayed | 45 | 24/07/2023 | 30/05/2025 | 16/05/2025 | 08/08/2023 | 376.45 | 376.45
99 | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14911) | SM/14911 | 274.41 | 590 | NEW | 47 | Delayed | 39 | 03/02/2023 | 30/04/2025 | 16/05/2025 | 04/08/2023 | 107.09 | 107.09
100 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme (SM/07028) | SM/07028 | 96.79 | 1531 | RETROFITTING | 48 | Delayed | 73 | 13/11/2020 | 31/03/2025 | 16/05/2025 | 14/08/2020 | 70.76 | 70.76
101 | AUGMENTATION OF LUKSAN BAZAR PWSS (SM/11814) | SM/11814 | 616.25 | 1895 | AUGMENTATION | 48 | Delayed | 36 | 16/08/2022 | 30/04/2025 | 16/05/2025 | 30/03/2022 | 222.77 | 203.51
102 | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME (SM/13900) | SM/13900 | 738.1 | 1527 | NEW | 50 | Delayed | 42 | 25/11/2022 | 30/04/2026 | 16/05/2025 | 08/05/2023 | 311.12 | 311.12
103 | CHENGMARIHAT PIPED WATER SUPPLY SCHEME (SM/18358) | SM/18358 | 1399.31 | 3607 | NEW | 50 | Delayed | 37 | 11/07/2023 | 30/05/2025 | 16/05/2025 | 28/07/2023 | 517.43 | 517.43
104 | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). (SM/08965) | SM/08965 | 479.35 | 0 | ANGANWADI | 50 | Delayed | 0 | 28/10/2021 | 30/06/2025 | 16/05/2025 | 03/12/2021 | 0 | 0
105 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT (SM/10775) | SM/10775 | 536.12 | 783 | NEW | 50 | Delayed | 14 | 23/05/2022 | 31/03/2025 | 16/05/2025 | 01/06/2022 | 74.74 | 74.74
106 | Dakshin Jharalta Piped Water Supply Scheme. (SM/18835) | SM/18835 | 1190.83 | 3531 | NEW | 50 | Delayed | 38 | 21/09/2023 | 31/12/2025 | 16/05/2025 | 23/10/2023 | 448.44 | 448.44
107 | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME (SM/15094) | SM/15094 | 125.87 | 0 | AUGMENTATION | 50 | Delayed | 28 | 04/02/2023 | 30/05/2025 | 16/05/2025 | 18/05/2023 | 35.25 | 35.25
108 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block (SM/07893) | SM/07893 | 133.21 | 2191 | RETROFITTING | 50 | Delayed | 55 | 19/01/2021 | 31/08/2025 | 16/05/2025 | 23/02/2021 | 73.51 | 52.02
109 | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME (SM/16041) | SM/16041 | 918.46 | 2356 | NEW | 51 | Delayed | 30 | 22/02/2023 | 30/04/2026 | 16/05/2025 | 07/06/2023 | 272.06 | 272.06
110 | Augmentation of Shikarpur Piped Water Supply Scheme (SM/09562) | SM/09562 | 977.54 | 3418 | AUGMENTATION | 55 | Delayed | 32 | 22/11/2021 | 31/12/2025 | 16/05/2025 | 17/02/2022 | 309.76 | 309.76
111 | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. (SM/08581) | SM/08581 | 172.9 | 562 | NEW | 55 | Delayed | 26 | 10/02/2021 | 31/03/2025 | 16/05/2025 | 23/05/2022 | 45.12 | 45.12
112 | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME (SM/13700) | SM/13700 | 661.12 | 1413 | NEW | 55 | Delayed | 49 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 29/03/2023 | 325.62 | 325.62
113 | Bagrakote Tea Garden Area Piped Water Supply Scheme. (SM/08874) | SM/08874 | 518.37 | 4594 | NEW | 55 | Delayed | 45 | 22/09/2021 | 31/03/2025 | 16/05/2025 | 03/02/2022 | 232.74 | 232.74
114 | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME (SM/14914) | SM/14914 | 478.22 | 2374 | NEW | 55 | Delayed | 50 | 03/02/2023 | 30/05/2025 | 16/05/2025 | 13/07/2023 | 239.08 | 239.08
115 | TESIMALA PIPED WATER SUPPLY SCHEME (SM/15970) | SM/15970 | 391.74 | 1140 | NEW | 55 | Delayed | 36 | 22/02/2023 | 31/12/2025 | 16/05/2025 | 03/08/2023 | 142.68 | 142.68
116 | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME (SM/15339) | SM/15339 | 980.45 | 4224 | NEW | 60 | Delayed | 24 | 09/02/2023 | 08/02/2025 | 16/05/2025 | 02/08/2023 | 234.75 | 234.75
117 | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME (SM/19097) | SM/19097 | 1000.22 | 3357 | NEW | 60 | On track | 26 | 08/12/2023 | 31/12/2025 | 16/05/2025 | 14/12/2023 | 260.64 | 260.64
118 | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME (SM/18360) | SM/18360 | 1152.06 | 4224 | NEW | 60 | Delayed | 28 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 318.52 | 318.52
119 | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME (SM/16181) | SM/16181 | 613.74 | 1385 | NEW | 60 | Delayed | 43 | 22/02/2023 | 31/12/2025 | 16/05/2025 | 15/05/2023 | 266.62 | 266.62
120 | BHEMTIA PIPED WATER SUPPLY SCHEME (SM/16676) | SM/16676 | 414.83 | 667 | NEW | 60 | Delayed | 13 | 14/03/2023 | 31/12/2025 | 16/05/2025 | 06/04/2023 | 54.36 | 54.36
121 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block (SM/08035) | SM/08035 | 320.18 | 5856 | RETROFITTING | 60 | Delayed | 41 | 02/02/2021 | 31/12/2025 | 16/05/2025 | 13/05/2021 | 130.17 | 125.34
122 | Rejuvenation of Mathachulka Piped Water Supply Scheme (SM/15098) | SM/15098 | 175.2 | 0 | AUGMENTATION | 60 | Delayed | 46 | 04/02/2023 | 06/04/2025 | 16/05/2025 | 13/07/2023 | 81.03 | 81.03
123 | PATKATA ZONE-III PIPED WATER SUPPLY (SM/14878) | SM/14878 | 727.68 | 2535 | NEW | 60 | On track | 36 | 03/02/2023 | 31/03/2027 | 16/05/2025 | 06/06/2023 | 260.09 | 260.09
124 | KHUKLUNG PIPED WATER SUPPLY SCHEME (SM/15953) | SM/15953 | 119.09 | 118 | NEW | 60 | Delayed | 32 | 22/02/2023 | 08/02/2025 | 16/05/2025 | 13/09/2023 | 37.79 | 34.97
125 | Augmentation of Jalapara Piped Water Supply Scheme (SM/10043) | SM/10043 | 620.86 | 1573 | AUGMENTATION | 60 | Delayed | 55 | 20/01/2022 | 31/12/2025 | 16/05/2025 | 01/09/2022 | 341.82 | 341.68
126 | Bhagatpur Tea Garden Area Piped Water Supply Scheme. (SM/09975) | SM/09975 | 385.01 | 1906 | NEW | 60 | Delayed | 58 | 22/09/2021 | 31/03/2025 | 16/05/2025 | 24/01/2022 | 223.85 | 223.89
127 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (SM/09100) | SM/09100 | 382.83 | 4346 | RETROFITTING | 60 | Delayed | 68 | 28/10/2021 | 31/03/2026 | 16/05/2025 | 21/01/2022 | 260.43 | 247.22
128 | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. (SM/08876) | SM/08876 | 1136.39 | 3422 | AUGMENTATION | 60 | Delayed | 64 | 22/09/2021 | 31/12/2025 | 16/05/2025 | 02/02/2022 | 723.82 | 697.03
129 | Rejuvenation of Mainatali Piped Water Supply Scheme (SM/09565) | SM/09565 | 104.11 | 0 | AUGMENTATION | 60 | Delayed | 49 | 22/11/2021 | 30/06/2025 | 16/05/2025 | 29/03/2023 | 51.18 | 51.18
130 | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME (SM/14665) | SM/14665 | 417.67 | 425 | NEW | 60 | Delayed | 43 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 27/03/2023 | 180.92 | 170.84
131 | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME (SM/14826) | SM/14826 | 551.68 | 1067 | NEW | 60 | Delayed | 39 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 25/04/2023 | 216.51 | 216.51
132 | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15297) | SM/15297 | 724.23 | 1991 | NEW | 60 | Delayed | 23 | 09/02/2023 | 31/12/2025 | 16/05/2025 | 07/06/2023 | 165.38 | 165.38
133 | BARA GHARIA PIPED WATER SUPPLY SCHEME (SM/15967) | SM/15967 | 703.7 | 1304 | NEW | 60 | Delayed | 38 | 22/02/2023 | 30/06/2025 | 16/05/2025 | 25/05/2023 | 266.14 | 266.14
134 | HAIHAIPATHAR PWSS (SM/16852) | SM/16852 | 741.68 | 2306 | NEW | 60 | Delayed | 41 | 13/03/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 302.33 | 302.33
135 | Augmentation of Bhatipara Water Supply Scheme (SM/13277) | SM/13277 | 1483.83 | 5116 | AUGMENTATION | 60 | Delayed | 48 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 22/09/2022 | 715.75 | 715.75
136 | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME (SM/14881) | SM/14881 | 681.26 | 2106 | NEW | 62 | Delayed | 23 | 03/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2023 | 158.8 | 158.8
137 | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME (SM/14882) | SM/14882 | 558.05 | 1110 | NEW | 63 | Delayed | 36 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 25/04/2023 | 198.88 | 198.88
138 | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME (SM/14667) | SM/14667 | 464.69 | 469 | NEW | 64 | Delayed | 44 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 21/03/2023 | 205.14 | 205.14
139 | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme (SM/15078) | SM/15078 | 157.06 | 0 | AUGMENTATION | 65 | Delayed | 16 | 04/02/2023 | 30/05/2025 | 16/05/2025 | 28/04/2023 | 25.79 | 25.79
140 | PURBA DOBBARI PIPED WATER SUPPLY SCHEME (SM/16776) | SM/16776 | 89.03 | 30 | NEW | 65 | Delayed | 10 | 13/03/2023 | 30/06/2025 | 16/05/2025 | 08/08/2023 | 9.13 | 9.13
141 | GAURGRAM PIPED WATER SUPPLY SCHEME (SM/13701) | SM/13701 | 594.88 | 1472 | NEW | 65 | Delayed | 57 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 08/08/2023 | 341.63 | 341.63
142 | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. (SM/09564) | SM/09564 | 139.18 | 0 | AUGMENTATION | 65 | On track | 49 | 22/11/2021 | 31/03/2027 | 16/05/2025 | 11/01/2022 | 67.93 | 65.56
143 | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme (SM/09483) | SM/09483 | 188.47 | 0 | AUGMENTATION | 65 | Delayed | 16 | 19/11/2021 | 31/03/2025 | 16/05/2025 | 21/01/2022 | 29.87 | 29.87
144 | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME (SM/13899) | SM/13899 | 772.86 | 1798 | NEW | 65 | Delayed | 68 | 25/11/2022 | 31/03/2025 | 16/05/2025 | 24/05/2023 | 526.56 | 526.56
145 | KAOAGAP PIPED WATER SUPPLY SCHEME (SM/14199) | SM/14199 | 647.34 | 984 | NEW | 65 | Delayed | 46 | 10/01/2023 | 08/02/2025 | 16/05/2025 | 21/03/2023 | 295.94 | 295.94
146 | Augmentation of Binnaguri Piped Water Supply Scheme (SM/09344) | SM/09344 | 871.08 | 2082 | AUGMENTATION | 65 | Delayed | 57 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 02/02/2022 | 495.27 | 376.79
147 | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME (SM/15261) | SM/15261 | 545.43 | 966 | NEW | 65 | Delayed | 30 | 08/02/2023 | 08/02/2025 | 16/05/2025 | 29/03/2023 | 165.53 | 165.53
148 | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME (SM/16040) | SM/16040 | 386.02 | 774 | NEW | 65 | On track | 53 | 22/02/2023 | 31/03/2026 | 16/05/2025 | 21/10/2022 | 202.83 | 202.83
149 | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME (SM/18357) | SM/18357 | 1031.07 | 3403 | NEW | 68 | On track | 54 | 11/07/2023 | 30/04/2026 | 16/05/2025 | 24/07/2023 | 561.7 | 561.7
150 | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME (SM/14908) | SM/14908 | 248.15 | 428 | NEW | 68 | Delayed | 37 | 03/02/2023 | 31/03/2025 | 16/05/2025 | 24/03/2023 | 91 | 91
151 | Rejuvenation of Mallicksova Piped water Supply Scheme (SM/09485) | SM/09485 | 178.69 | 0 | AUGMENTATION | 70 | Delayed | 50 | 19/11/2021 | 31/12/2025 | 16/05/2025 | 20/04/2022 | 89.33 | 88.01
152 | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza (SM/09865) | SM/09865 | 110.47 | 0 | AUGMENTATION | 70 | Delayed | 90 | 06/12/2021 | 30/09/2025 | 16/05/2025 | 22/07/2022 | 99.03 | 94.93
153 | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME (SM/15132) | SM/15132 | 189.88 | 0 | RETROFITTING | 70 | On track | 44 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 83.59 | 83.59
154 | CHAR CHARABARI PIPED WATER SUPPLY SCHEME (SM/16042) | SM/16042 | 568.49 | 1370 | NEW | 70 | Delayed | 44 | 22/02/2023 | 31/08/2025 | 16/05/2025 | 08/05/2023 | 249.58 | 249.58
155 | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/17681) | SM/17681 | 116.16 | 240 | AUGMENTATION | 70 | On track | 61 | 17/03/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 70.92 | 70.27
156 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. (SM/07044) | SM/07044 | 93.9 | 1540 | RETROFITTING | 70 | Delayed | 1 | 24/11/2020 | 31/03/2025 | 16/05/2025 | 16/12/2023 | 0.48 | 0.48
157 | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme (SM/09561) | SM/09561 | 681.79 | 1793 | AUGMENTATION | 70 | Delayed | 56 | 22/11/2021 | 30/04/2025 | 16/05/2025 | 24/01/2022 | 382.46 | 383.49
158 | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME (SM/14660) | SM/14660 | 520.46 | 1074 | NEW | 70 | On track | 40 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 25/04/2023 | 208.11 | 208.11
159 | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15990) | SM/15990 | 406.46 | 1096 | NEW | 70 | Delayed | 43 | 22/02/2023 | 31/03/2025 | 16/05/2025 | 13/04/2023 | 176.08 | 176.08
160 | Augmentation of Purba Daukimari Piped Water Supply Scheme (SM/09560) | SM/09560 | 545.87 | 1586 | AUGMENTATION | 70 | Delayed | 78 | 22/11/2021 | 31/03/2025 | 16/05/2025 | 02/02/2022 | 427.29 | 459.48
161 | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme (SM/09392) | SM/09392 | 290.82 | 1462 | AUGMENTATION | 70 | Delayed | 59 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 03/03/2022 | 171.19 | 169.98
162 | CHHAOAPHALI PIPED WATER SUPPLY SCHEME (SM/13901) | SM/13901 | 236.73 | 462 | NEW | 70 | On track | 46 | 25/11/2022 | 31/12/2025 | 16/05/2025 | 28/04/2023 | 109.62 | 109.62
163 | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme (SM/15130) | SM/15130 | 182.74 | 1315 | AUGMENTATION | 70 | On track | 25 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 18/11/2020 | 46.18 | 46.18
164 | Rejuvenation of Chauhaddi Piped Water Supply Scheme (SM/09484) | SM/09484 | 226.32 | 0 | AUGMENTATION | 70 | Delayed | 93 | 19/11/2021 | 31/03/2025 | 16/05/2025 | 03/02/2022 | 211.1 | 206.16
165 | Augmentation of Kathapara Piped Water Supply Scheme (SM/09563) | SM/09563 | 834.88 | 2665 | AUGMENTATION | 70 | On track | 38 | 22/11/2021 | 31/03/2026 | 16/05/2025 | 17/03/2022 | 321.16 | 218.91
166 | Augmentation of Porjhar Pipe Water Supply Scheme (SM/15302) | SM/15302 | 597.01 | 2564 | AUGMENTATION | 70 | Delayed | 28 | 09/02/2023 | 08/02/2025 | 16/05/2025 | 04/08/2023 | 167.01 | 167.01
167 | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15296) | SM/15296 | 604.63 | 1832 | NEW | 70 | Delayed | 43 | 09/02/2023 | 31/03/2025 | 16/05/2025 | 08/05/2023 | 261.07 | 261.07
168 | Rejuvenation of Purba Duramari Piped Water Supply Scheme (SM/15326) | SM/15326 | 206.58 | 1409 | AUGMENTATION | 70 | Delayed | 25 | 09/02/2023 | 30/06/2025 | 16/05/2025 | 22/05/2023 | 51.4 | 51.4
169 | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme (SM/15099) | SM/15099 | 150.59 | 0 | AUGMENTATION | 70 | Delayed | 26 | 04/02/2023 | 31/07/2025 | 16/05/2025 | 31/03/2022 | 38.96 | 38.96
170 | BINNAGURI PIPED WATER SUPPLY SCHEME (SM/14198) | SM/14198 | 409.19 | 1553 | NEW | 70 | Delayed | 47 | 10/01/2023 | 08/02/2025 | 16/05/2025 | 04/08/2023 | 190.57 | 190.57
171 | Augmentation of Maynaguri Piped Water Supply Scheme. (SM/10042) | SM/10042 | 978.7 | 7191 | AUGMENTATION | 72 | On track | 57 | 20/01/2022 | 31/12/2025 | 16/05/2025 | 24/01/2022 | 559.21 | 634.5
172 | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme (SM/15299) | SM/15299 | 139.34 | 0 | AUGMENTATION | 72 | Delayed | 56 | 09/02/2023 | 31/03/2025 | 16/05/2025 | 09/03/2023 | 77.61 | 77.61
173 | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME (SM/15335) | SM/15335 | 850.7 | 2792 | NEW | 72 | Delayed | 31 | 09/02/2023 | 30/05/2025 | 16/05/2025 | 24/07/2023 | 260.63 | 260.63
174 | Augmentation of Banerhat Bazar Piped Water Supply Scheme (SM/10044) | SM/10044 | 671.77 | 3913 | AUGMENTATION | 75 | On track | 65 | 20/01/2022 | 31/12/2025 | 16/05/2025 | 02/11/2022 | 439.69 | 439.69
175 | SHAKATI PIPED WATER SUPPLY SCHEME (SM/13704) | SM/13704 | 557.7 | 2042 | NEW | 75 | Delayed | 58 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 25/04/2023 | 323.24 | 312.43
176 | Augmentation of Purbba Batabari Piped Water Supply Scheme (SM/09864) | SM/09864 | 810.11 | 1795 | AUGMENTATION | 75 | Delayed | 60 | 06/12/2021 | 31/08/2025 | 16/05/2025 | 13/08/2020 | 484.35 | 487.21
177 | Augmentation of Lataguri Piped Water Supply Scheme (SM/13278) | SM/13278 | 1834.7 | 4977 | AUGMENTATION | 75 | Delayed | 72 | 19/09/2022 | 31/08/2025 | 16/05/2025 | 23/08/2021 | 1320.44 | 1313.97
178 | Augmentation of Kranti Piped water supply Scheme (SM/09994) | SM/09994 | 1755.8 | 5563 | AUGMENTATION | 75 | Delayed | 60 | 20/12/2021 | 31/03/2025 | 16/05/2025 | 24/01/2022 | 1046.86 | 1000.63
179 | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME (SM/14887) | SM/14887 | 641.1 | 1619 | NEW | 75 | Delayed | 45 | 03/02/2023 | 30/06/2025 | 16/05/2025 | 30/05/2023 | 288.43 | 288.43
180 | Augmentation of Sukani Piped Water Supply Scheme (SM/09995) | SM/09995 | 4370.14 | 14294 | AUGMENTATION | 75 | On track | 62 | 20/12/2021 | 31/12/2025 | 16/05/2025 | 13/03/2020 | 2695.24 | 2615.13
181 | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme (SM/15114) | SM/15114 | 255.47 | 0 | AUGMENTATION | 78 | On track | 69 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 16/06/2022 | 177.47 | 177.47
182 | AMGURI PIPED WATER SUPPLY SCHEME (SM/13706) | SM/13706 | 891.35 | 2373 | NEW | 78 | On track | 56 | 14/11/2022 | 30/04/2026 | 16/05/2025 | 21/03/2023 | 502.64 | 502.64
183 | Rejuvenation of Khalaigram Piped Water Supply Scheme (SM/09486) | SM/09486 | 66.14 | 0 | AUGMENTATION | 80 | Delayed | 74 | 19/11/2021 | 31/03/2025 | 16/05/2025 | 21/01/2022 | 49.24 | 49.27
184 | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme (SM/09863) | SM/09863 | 172.79 | 0 | AUGMENTATION | 80 | On track | 68 | 06/12/2021 | 30/04/2026 | 16/05/2025 | 29/04/2022 | 117.92 | 117.92
185 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06952) | SM/06952 | 65.98 | 1257 | RETROFITTING | 80 | Delayed | 100 | 03/11/2020 | 30/04/2025 | 16/05/2025 | 31/12/2020 | 65.98 | 65.37
186 | Ghasmari Piped Water Supply Scheme. (SM/08868) | SM/08868 | 293.24 | 779 | NEW | 80 | Delayed | 65 | 20/09/2021 | 30/06/2025 | 16/05/2025 | 24/01/2022 | 190.52 | 161.57
187 | Augmentation of Madhya Khagrabari Water Supply Scheme. (SM/10028) | SM/10028 | 986.41 | 3594 | AUGMENTATION | 80 | Delayed | 91 | 17/01/2022 | 31/05/2025 | 16/05/2025 | 24/06/2020 | 894.96 | 733.68
188 | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15264) | SM/15264 | 345.92 | 1080 | NEW | 80 | Delayed | 47 | 07/02/2023 | 30/06/2025 | 16/05/2025 | 25/01/2022 | 163.74 | 163.74
189 | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme (SM/15075) | SM/15075 | 158.29 | 0 | AUGMENTATION | 80 | On track | 30 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 02/02/2022 | 48.19 | 48.19
190 | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME (SM/15338) | SM/15338 | 121.26 | 0 | AUGMENTATION | 80 | Delayed | 63 | 09/02/2023 | 08/02/2025 | 16/05/2025 | 05/10/2023 | 76.93 | 76.93
191 | Augmentation of Domohani Piped Water Supply Scheme (SM/09345) | SM/09345 | 855.56 | 2548 | AUGMENTATION | 80 | Delayed | 69 | 12/11/2021 | 31/07/2025 | 16/05/2025 | 18/04/2022 | 588.43 | 616.49
192 | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. (SM/10071) | SM/10071 | 521.15 | 1235 | AUGMENTATION | 80 | Delayed | 63 | 27/01/2022 | 31/07/2025 | 16/05/2025 | 05/04/2022 | 329.97 | 296.98
193 | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME (SM/14919) | SM/14919 | 366.08 | 2306 | NEW | 80 | Delayed | 45 | 03/02/2023 | 30/06/2025 | 16/05/2025 | 27/03/2023 | 163.76 | 163.76
194 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme (SM/06937) | SM/06937 | 129.58 | 2431 | RETROFITTING | 80 | Delayed | 97 | 03/11/2020 | 30/06/2025 | 16/05/2025 | 18/01/2021 | 126.3 | 112.72
195 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. (SM/09099) | SM/09099 | 163.94 | 1369 | RETROFITTING | 80 | Delayed | 71 | 28/10/2021 | 31/05/2025 | 16/05/2025 | 27/09/2021 | 116.68 | 113.68
196 | PIPE WATER SUPPLY SCHEME FOR TANDU (SM/13990) | SM/13990 | 177.66 | 396 | NEW | 80 | Delayed | 53 | 01/12/2022 | 31/07/2025 | 16/05/2025 | 24/03/2023 | 94.15 | 84.38
197 | Rejuvenation for Patkidaha Piped Water Supply Scheme (SM/15085) | SM/15085 | 145.15 | 0 | AUGMENTATION | 80 | On track | 46 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 29/11/2021 | 66.9 | 66.9
198 | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA (SM/13988) | SM/13988 | 355.6 | 1157 | NEW | 80 | Delayed | 73 | 01/12/2022 | 31/07/2025 | 16/05/2025 | 02/08/2023 | 260.78 | 260.78
199 | Rejuvenation of Chauhaddi Piped Water Supply Scheme (SM/15033) | SM/15033 | 198.79 | 0 | AUGMENTATION | 80 | On track | 30 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2023 | 59.42 | 59.42
200 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme (SM/07303) | SM/07303 | 89.78 | 1296 | RETROFITTING | 80 | On track | 69 | 10/12/2020 | 31/12/2026 | 16/05/2025 | 08/01/2021 | 62 | 109.28
201 | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME (SM/14883) | SM/14883 | 544.31 | 1611 | NEW | 80 | On track | 21 | 03/02/2023 | 31/08/2025 | 16/05/2025 | 10/05/2023 | 112.95 | 112.95
202 | SAMAR NAGAR PIPED WATER SUPPLY SCHEME (SM/14200) | SM/14200 | 779.1 | 2644 | NEW | 80 | Delayed | 43 | 10/01/2023 | 08/02/2025 | 16/05/2025 | 29/03/2023 | 334.69 | 327.84
203 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme (SM/06839) | SM/06839 | 99.99 | 1671 | RETROFITTING | 80 | Delayed | 81 | 06/10/2020 | 30/06/2025 | 16/05/2025 | 09/10/2020 | 81.35 | 84.11
204 | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme (SM/16772) | SM/16772 | 156.25 | 1459 | AUGMENTATION | 80 | Delayed | 20 | 13/03/2023 | 31/07/2025 | 16/05/2025 | 07/06/2023 | 31.17 | 31.17
205 | Saptibari Piped Water Supply Scheme. (SM/18759) | SM/18759 | 2026.68 | 663 | NEW | 80 | Delayed | 49 | 23/08/2023 | 08/02/2025 | 16/05/2025 | 04/09/2023 | 991.35 | 991.35
206 | Rejuvenation of Sajnapara Piped Water Supply Scheme (SM/09391) | SM/09391 | 92.36 | 0 | AUGMENTATION | 80 | Delayed | 41 | 12/11/2021 | 31/03/2025 | 16/05/2025 | 14/09/2022 | 37.52 | 30.72
207 | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme (SM/15103) | SM/15103 | 149.74 | 0 | AUGMENTATION | 80 | On track | 54 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 30/05/2023 | 80.74 | 77.07
208 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06954) | SM/06954 | 34.5 | 607 | RETROFITTING | 82 | Delayed | 100 | 03/11/2020 | 31/08/2025 | 16/05/2025 | 31/12/2020 | 34.5 | 60.16
209 | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS (SM/15068) | SM/15068 | 70.86 | 0 | AUGMENTATION | 82 | On track | 51 | 04/02/2023 | 31/08/2025 | 16/05/2025 | 14/07/2023 | 36.31 | 36.31
210 | Augmentation of Baikur Piped Water Supply Scheme. (SM/10089) | SM/10089 | 1763.64 | 7173 | AUGMENTATION | 82 | Delayed | 77 | 01/02/2022 | 30/05/2025 | 16/05/2025 | 24/06/2020 | 1358.72 | 1239.1
211 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme (SM/07304) | SM/07304 | 36.39 | 447 | RETROFITTING | 83 | Delayed | 100 | 10/12/2020 | 31/05/2025 | 16/05/2025 | 11/02/2021 | 36.39 | 71.86
212 | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme (SM/06842) | SM/06842 | 48.73 | 873 | RETROFITTING | 84 | Delayed | 22 | 06/10/2020 | 31/08/2025 | 16/05/2025 | 02/11/2020 | 10.56 | 10.56
213 | Rejuvenation of Purbba Salbari Piped Water Supply Scheme (SM/09861) | SM/09861 | 696.59 | 2219 | AUGMENTATION | 85 | On track | 95 | 06/12/2021 | 31/08/2025 | 16/05/2025 | 05/04/2022 | 663.42 | 561.48
214 | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme (SM/15300) | SM/15300 | 159.96 | 0 | AUGMENTATION | 85 | Delayed | 88 | 09/02/2023 | 30/05/2025 | 16/05/2025 | 08/06/2023 | 140.78 | 140.78
215 | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme (SM/15116) | SM/15116 | 194.43 | 0 | AUGMENTATION | 85 | On track | 57 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 25/05/2023 | 110.93 | 110.93
216 | SIMULGURI PIPED WATER SUPPLY SCHEME (SM/14240) | SM/14240 | 1172.27 | 2948 | NEW | 85 | On track | 65 | 16/01/2023 | 30/06/2025 | 16/05/2025 | 29/03/2023 | 757.94 | 757.94
217 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme (SM/06837) | SM/06837 | 61.53 | 1080 | RETROFITTING | 85 | Delayed | 100 | 06/10/2020 | 31/03/2025 | 16/05/2025 | 18/11/2020 | 61.53 | 66.16
218 | Augmentation of Dakshin Berubari Water Supply Scheme. (SM/10086) | SM/10086 | 1574.27 | 4905 | AUGMENTATION | 85 | Delayed | 65 | 01/02/2022 | 30/04/2025 | 16/05/2025 | 02/02/2022 | 1017.77 | 842.17
219 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/06844) | SM/06844 | 57.04 | 1082 | RETROFITTING | 85 | Delayed | 100 | 06/10/2020 | 30/04/2025 | 16/05/2025 | 18/11/2020 | 57.04 | 55.79
220 | Rejuvenation of Chakiavita Piped Water Supply Scheme (SM/09482) | SM/09482 | 119.98 | 0 | AUGMENTATION | 85 | On track | 92 | 19/11/2021 | 31/12/2025 | 16/05/2025 | 07/01/2021 | 110.5 | 110.12
221 | BARA DIGHI PIPED WATER SUPPLY SCHEME (SM/13703) | SM/13703 | 156.26 | 210 | NEW | 85 | Delayed | 53 | 14/11/2022 | 30/06/2025 | 16/05/2025 | 25/08/2022 | 82.71 | 82.71
222 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06955) | SM/06955 | 62.52 | 1205 | RETROFITTING | 85 | Delayed | 100 | 03/11/2020 | 30/04/2025 | 16/05/2025 | 01/02/2021 | 62.52 | 81.43
223 | Augmentation of Barnes Water Supply Scheme. (SM/10090) | SM/10090 | 1115.54 | 4046 | AUGMENTATION | 85 | On track | 95 | 01/02/2022 | 31/08/2025 | 16/05/2025 | 24/06/2020 | 1054.39 | 951.15
224 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme (SM/06838) | SM/06838 | 92.26 | 1664 | RETROFITTING | 85 | Delayed | 78 | 06/10/2020 | 31/05/2025 | 16/05/2025 | 15/10/2020 | 71.65 | 66.17
225 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block (SM/06957) | SM/06957 | 36 | 640 | RETROFITTING | 85 | On track | 100 | 03/11/2020 | 31/08/2025 | 16/05/2025 | 19/01/2022 | 36 | 35.97
226 | Rejuvenation of Madhabdanga piped water supply scheme. (SM/09456) | SM/09456 | 125.38 | 0 | AUGMENTATION | 85 | Delayed | 85 | 19/11/2021 | 31/05/2025 | 16/05/2025 | 27/12/2021 | 107.18 | 107.18
227 | Augmentation of Sannyasikata Piped Water Supply Scheme (SM/09996) | SM/09996 | 2105.11 | 6379 | AUGMENTATION | 85 | Delayed | 71 | 20/12/2021 | 30/05/2025 | 16/05/2025 | 05/04/2022 | 1484.5 | 1474.47
228 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme (SM/08077) | SM/08077 | 62.08 | 1080 | RETROFITTING | 85 | On track | 100 | 04/02/2021 | 31/08/2025 | 16/05/2025 | 13/03/2023 | 62.08 | 61.14
229 | REJUVENATION OF DAKSHIN SALBARI PWSS (SM/15087) | SM/15087 | 246.25 | 2129 | AUGMENTATION | 85 | Delayed | 12 | 04/02/2023 | 31/05/2025 | 16/05/2025 | 28/02/2022 | 30.24 | 29.94
230 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block (SM/06953) | SM/06953 | 48.9 | 917 | RETROFITTING | 86 | Delayed | 100 | 03/11/2020 | 30/04/2025 | 16/05/2025 | 05/01/2021 | 48.9 | 48.83
231 | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/16773) | SM/16773 | 171.57 | 527 | AUGMENTATION | 86 | Delayed | 57 | 13/03/2023 | 08/02/2025 | 16/05/2025 | 04/08/2023 | 98.44 | 98.44
232 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme (SM/06846) | SM/06846 | 37.11 | 632 | RETROFITTING | 87 | Delayed | 100 | 06/10/2020 | 30/04/2025 | 16/05/2025 | 15/10/2020 | 37.11 | 40.73
233 | Augmentation of Kharija-Berubari Water Supply Scheme. (SM/10088) | SM/10088 | 2064.37 | 5781 | AUGMENTATION | 87 | Delayed | 67 | 01/02/2022 | 30/04/2025 | 16/05/2025 | 27/12/2021 | 1383.77 | 1264.19
234 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block (SM/06956) | SM/06956 | 64.77 | 1225 | RETROFITTING | 88 | Delayed | 100 | 03/11/2020 | 30/04/2025 | 16/05/2025 | 01/02/2021 | 64.77 | 64.68
235 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme (SM/06936) | SM/06936 | 126.48 | 2332 | RETROFITTING | 88 | Delayed | 99 | 03/11/2020 | 31/05/2025 | 16/05/2025 | 31/12/2020 | 124.94 | 111.78
236 | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/18356) | SM/18356 | 1140.38 | 2798 | NEW | 88 | On track | 24 | 11/07/2023 | 30/04/2026 | 16/05/2025 | 24/07/2023 | 277.83 | 277.83
237 | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme (SM/06843) | SM/06843 | 52.3 | 925 | RETROFITTING | 89 | On track | 30 | 06/10/2020 | 31/12/2025 | 16/05/2025 | 23/11/2020 | 15.72 | 15.72
238 | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS (SM/15071) | SM/15071 | 177.04 | 1015 | AUGMENTATION | 90 | On track | 30 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 01/06/2023 | 53.99 | 53.99
239 | BARAGHARIA Piped Water Supply Scheme. (SM/17649) | SM/17649 | 613.18 | 2063 | NEW | 90 | On track | 44 | 22/03/2023 | 31/07/2025 | 16/05/2025 | 25/04/2023 | 267.99 | 267.99
240 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Pradhanpara Mouza Under Sajnapara Piped Water Supply Scheme (SM/07302) | SM/07302 | 75.74 | 1309 | RETROFITTING | 90 | WO no issued | 100 | 10/12/2020 | 31/12/2026 | 16/05/2025 | 29/11/2023 | 75.74 | 3.5
241 | Augmentation of Ramsai Water Supply Scheme. (SM/10033) | SM/10033 | 976.19 | 3250 | AUGMENTATION | 90 | On track | 84 | 19/01/2022 | 31/05/2025 | 16/05/2025 | 24/06/2020 | 816.83 | 776.45
242 | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME (SM/15031) | SM/15031 | 161.99 | 0 | AUGMENTATION | 90 | On track | 63 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 16/03/2023 | 102.58 | 102.58
243 | Rejuvenation of Porapara piped water supply scheme. (SM/09463) | SM/09463 | 121.26 | 0 | AUGMENTATION | 90 | On track | 92 | 19/11/2021 | 30/06/2025 | 16/05/2025 | 22/04/2022 | 112.12 | 110.62
244 | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14666) | SM/14666 | 852.43 | 2390 | NEW | 90 | Delayed | 51 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 31/07/2023 | 434.78 | 428.46
245 | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. (SM/09518) | SM/09518 | 114.34 | 0 | AUGMENTATION | 90 | Delayed | 82 | 19/11/2021 | 31/03/2025 | 16/05/2025 | 04/04/2022 | 94.03 | 76.15
246 | Augmentation of Odlabari Piped Water Supply Scheme (SM/13790) | SM/13790 | 1003.52 | 3348 | AUGMENTATION | 90 | On track | 57 | 21/10/2022 | 31/12/2025 | 16/05/2025 | 05/04/2022 | 567.36 | 567.36
247 | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15262) | SM/15262 | 635.17 | 1408 | NEW | 90 | Delayed | 44 | 08/02/2023 | 08/02/2025 | 16/05/2025 | 09/08/2023 | 281.49 | 281.49
248 | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme (SM/15298) | SM/15298 | 241.44 | 0 | AUGMENTATION | 90 | Delayed | 62 | 09/02/2023 | 30/04/2025 | 16/05/2025 | 13/04/2023 | 148.6 | 148.6
249 | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/18711) | SM/18711 | 584.88 | 1951 | NEW | 90 | Delayed | 39 | 04/08/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 227.03 | 227.03
250 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme (SM/06959) | SM/06959 | 57.13 | 914 | RETROFITTING | 90 | On track | 100 | 03/11/2020 | 31/12/2025 | 16/05/2025 | 12/02/2021 | 57.13 | 118.72
251 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block (SM/07301) | SM/07301 | 30.18 | 240 | RETROFITTING | 90 | On track | 100 | 10/12/2020 | 31/05/2025 | 16/05/2025 | 01/02/2021 | 30.18 | 30.12
252 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block (SM/08285) | SM/08285 | 268.15 | 5069 | RETROFITTING | 90 | On track | 100 | 09/02/2021 | 31/05/2025 | 16/05/2025 | 13/05/2021 | 268.15 | 266.3
253 | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME (SM/13898) | SM/13898 | 906.72 | 1809 | NEW | 90 | On track | 78 | 25/11/2022 | 31/03/2027 | 16/05/2025 | 10/04/2023 | 710.32 | 710.28
254 | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14885) | SM/14885 | 913.53 | 2665 | NEW | 90 | On track | 77 | 03/02/2023 | 31/12/2025 | 16/05/2025 | 28/07/2023 | 704.03 | 704.03
255 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme (SM/06960) | SM/06960 | 99.43 | 1692 | RETROFITTING | 90 | On track | 50 | 03/11/2020 | 31/12/2026 | 16/05/2025 | 29/11/2023 | 50 | 8.94
256 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme (SM/06961) | SM/06961 | 75.45 | 1259 | RETROFITTING | 90 | On track | 100 | 03/11/2020 | 31/05/2025 | 16/05/2025 | 29/11/2023 | 75.45 | 35.13
257 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block (SM/08036) | SM/08036 | 349.29 | 6704 | RETROFITTING | 90 | On track | 100 | 02/02/2021 | 31/05/2025 | 16/05/2025 | 02/07/2021 | 349.29 | 285.33
258 | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST (SM/13989) | SM/13989 | 143.56 | 360 | NEW | 90 | On track | 66 | 01/12/2022 | 31/05/2025 | 16/05/2025 | 29/03/2023 | 94.82 | 94.82
259 | KANTADIGHI KUMARPARA TEA GARDEN (SM/14879) | SM/14879 | 841.22 | 2481 | NEW | 91 | On track | 54 | 03/02/2023 | 30/04/2026 | 16/05/2025 | 10/05/2023 | 456.09 | 456.09
260 | Indong Tea Garden Area Piped Water Supply Scheme. (SM/08873) | SM/08873 | 311.47 | 1236 | NEW | 92 | On track | 74 | 22/09/2021 | 31/07/2025 | 16/05/2025 | 25/01/2022 | 229.08 | 229.08
261 | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza (SM/09859) | SM/09859 | 114.69 | 0 | AUGMENTATION | 92 | On track | 49 | 06/12/2021 | 30/06/2025 | 16/05/2025 | 05/10/2021 | 55.97 | 55.81
262 | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza (SM/09862) | SM/09862 | 105.33 | 0 | AUGMENTATION | 93 | Delayed | 89 | 06/12/2021 | 31/03/2025 | 16/05/2025 | 24/02/2022 | 93.55 | 83.78
263 | REJUVENATION OF ARJI GARALBARI PWSS (SM/15030) | SM/15030 | 172.44 | 0 | AUGMENTATION | 95 | On track | 48 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 25/04/2023 | 83.32 | 83.32
264 | Rejuvenation of Dwarikamari piped water supply scheme. (SM/09459) | SM/09459 | 121.4 | 0 | AUGMENTATION | 95 | On track | 95 | 19/11/2021 | 31/03/2026 | 16/05/2025 | 31/12/2021 | 115.49 | 114.24
265 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme (SM/06847) | SM/06847 | 56.03 | 1019 | RETROFITTING | 95 | On track | 100 | 06/10/2020 | 30/04/2025 | 16/05/2025 | 18/11/2020 | 56.03 | 45
266 | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS (SM/16937) | SM/16937 | 161.99 | 0 | AUGMENTATION | 95 | On track | 32 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 06/06/2023 | 51.79 | 51.79
267 | Rejuvenation of Hila Tea Garden area piped water supply scheme (SM/10070) | SM/10070 | 208.35 | 0 | AUGMENTATION | 95 | On track | 76 | 27/01/2022 | 30/06/2025 | 16/05/2025 | 29/01/2021 | 159.04 | 151.33
268 | Augmentation of Mondalghat Water Supply Scheme. (SM/10087) | SM/10087 | 1095.64 | 3793 | AUGMENTATION | 95 | On track | 68 | 01/02/2022 | 31/12/2025 | 16/05/2025 | 24/06/2020 | 742.98 | 689.74
269 | Rejuvenation of Bhangarhat Piped Water Supply Scheme (SM/15032) | SM/15032 | 178.3 | 0 | AUGMENTATION | 95 | Delayed | 21 | 04/02/2023 | 31/03/2025 | 16/05/2025 | 24/05/2023 | 37.96 | 37.96
270 | Rejuvenation of Kajaldighi piped water supply scheme. (SM/09457) | SM/09457 | 116.9 | 0 | AUGMENTATION | 95 | On track | 57 | 19/11/2021 | 30/04/2025 | 16/05/2025 | 06/04/2023 | 66.48 | 66.48
271 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme (SM/09858) | SM/09858 | 171.5 | 0 | AUGMENTATION | 95 | On track | 59 | 06/12/2021 | 31/03/2025 | 16/05/2025 | 23/03/2022 | 100.73 | 99.67
272 | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/11812) | SM/11812 | 94.73 | 1206 | AUGMENTATION | 95 | On track | 47 | 16/08/2022 | 30/04/2026 | 16/05/2025 | 20/07/2022 | 44.6 | 44.74
273 | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME (SM/15096) | SM/15096 | 119.1 | 0 | AUGMENTATION | 95 | On track | 20 | 04/02/2023 | 31/07/2025 | 16/05/2025 | 14/07/2022 | 24.12 | 24.12
274 | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME (SM/14664) | SM/14664 | 870.88 | 2319 | NEW | 95 | On track | 61 | 31/01/2023 | 30/04/2025 | 16/05/2025 | 16/03/2023 | 530.79 | 530.37
275 | Kumlai Tea Garden Area Piped Water Supply Scheme. (SM/08875) | SM/08875 | 303.84 | 991 | NEW | 97 | On track | 96 | 22/09/2021 | 30/04/2025 | 16/05/2025 | 08/12/2021 | 290.82 | 255.01
276 | Rejuvenation of Basilardanga piped water supply scheme. (SM/09460) | SM/09460 | 115.16 | 0 | AUGMENTATION | 97 | On track | 91 | 19/11/2021 | 31/12/2025 | 16/05/2025 | 27/12/2021 | 105.01 | 105.01
277 | RETROFITTING OF MAHITNAGAR PWSS (SM/15131) | SM/15131 | 180.43 | 0 | RETROFITTING | 98 | On track | 42 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 75.34 | 75.34
278 | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/15115) | SM/15115 | 560.37 | 1368 | NEW | 98 | On track | 53 | 04/02/2023 | 31/03/2025 | 16/05/2025 | 08/05/2023 | 299.43 | 299.43
279 | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme (SM/15117) | SM/15117 | 196.67 | 0 | AUGMENTATION | 98 | On track | 82 | 04/02/2023 | 30/04/2025 | 16/05/2025 | 16/02/2023 | 161.71 | 161.71
280 | Rejuvenation of Charerbari piped water supply scheme. (SM/09458) | SM/09458 | 115.93 | 0 | AUGMENTATION | 98 | On track | 83 | 19/11/2021 | 31/03/2025 | 16/05/2025 | 27/12/2021 | 96.33 | 96.33
281 | Rejuvenation of Goralbari Piped Water Supply Scheme (SM/09390) | SM/09390 | 337.55 | 0 | AUGMENTATION | 98 | On track | 71 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 30/11/2021 | 239.53 | 334.94
282 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme (SM/06840) | SM/06840 | 74.02 | 1362 | RETROFITTING | 99 | On track | 100 | 06/10/2020 | 31/05/2025 | 16/05/2025 | 18/11/2020 | 74.02 | 92.52
283 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme (SM/08038) | SM/08038 | 396.46 | 6473 | RETROFITTING | 99 | On track | 100 | 02/02/2021 | 31/05/2025 | 16/05/2025 | 28/01/2021 | 396.46 | 407.81
284 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block (SM/08037) | SM/08037 | 348.32 | 6385 | RETROFITTING | 99 | On track | 100 | 02/02/2021 | 31/05/2025 | 16/05/2025 | 19/09/2023 | 348.32 | 293.31
285 | Rejuvenation of Boalmari piped water supply scheme. (SM/09462) | SM/09462 | 113.6 | 0 | AUGMENTATION | 99 | On track | 95 | 19/11/2021 | 31/05/2025 | 16/05/2025 | 11/03/2022 | 108.26 | 108.26
286 | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme (SM/17185) | SM/17185 | 180.04 | 940 | AUGMENTATION | 99 | On track | 60 | 15/03/2023 | 31/03/2025 | 16/05/2025 | 26/05/2023 | 107.71 | 107.71
287 | Rejuvenation of Mohitnagar piped water supply scheme. (SM/09519) | SM/09519 | 122.19 | 0 | AUGMENTATION | 99 | On track | 96 | 19/11/2021 | 31/05/2025 | 16/05/2025 | 04/01/2022 | 117.33 | 108.44
288 | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme (SM/10069) | SM/10069 | 243.7 | 0 | AUGMENTATION | 100 | 100% Physical | 70 | 27/01/2022 | 30/04/2025 | 16/05/2025 | 22/12/2022 | 171.25 | 171.25
289 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme (SM/06938) | SM/06938 | 106.41 | 1976 | RETROFITTING | 100 | 100% Physical | 73 | 03/11/2020 | 30/09/2022 | 16/05/2025 | 15/10/2020 | 78.09 | 71.51
290 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme (SM/06841) | SM/06841 | 89.57 | 1671 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 | 30/04/2025 | 16/05/2025 | 22/12/2020 | 89.57 | 89.1
291 | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. (SM/09461) | SM/09461 | 70.07 | 930 | AUGMENTATION | 100 | 100% Physical | 100 | 19/11/2021 | 31/08/2025 | 16/05/2025 | 10/02/2021 | 70.07 | 88.91
292 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme (SM/06845) | SM/06845 | 60.77 | 1118 | RETROFITTING | 100 | 100% Physical | 100 | 06/10/2020 | 31/08/2025 | 16/05/2025 | 18/11/2021 | 60.77 | 68.9
Total |  |  | 126276.31 | 436318 | [8 empty] | 57567.52 | 56102.38