## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Solarisation of WBSEDCL Energised Electrical Installation at Barai Bari PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16633) | SM/16633 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
2 | Solarisation of WBSEDCL Energised Electrical Installation at Bogdabari Kesaibari PWSS and Others in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16634) | SM/16634 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
3 | Solarisation of WBSEDCL Energised Electrical Installation at Chamta PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16635) | SM/16635 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
4 | Solarisation of WBSEDCL Energised Electrical Installation at Kishamat Dasgram PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16637) | SM/16637 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
5 | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS (SM/16154) | SM/16154 | 638.6 | 1442 | NEW | 0 | 0% Physical | 1 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 11/03/2024 | 6.94 | 6.94
6 | Solarisation of WBSEDCL Energised Electrical Installation at Panisala PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16639) | SM/16639 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
7 | Solarisation of WBSEDCL Energised Electrical Installation at Ekmukha PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16636) | SM/16636 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
8 | Solarisation of WBSEDCL Energised Electrical Installation at Rajpur PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16642) | SM/16642 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
9 | Solarisation of WBSEDCL Energised Electrical Installation at Rampur PWSS Zone-II in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16644) | SM/16644 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
10 | Solarisation of WBSEDCL Energised Electrical Installation at Satbhandari PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16645) | SM/16645 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
11 | Solarisation of WBSEDCL Energised Electrical Installation at Petla PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16640) | SM/16640 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
12 | Solarisation of WBSEDCL Energised Electrical Installation at Rampur PWSS Zone-I in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16643) | SM/16643 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 07/11/2025 | 03/04/2025 | 18/07/2023 | 0 | 0
13 | Solarisation of WBSEDCL Energised Electrical Installation at Bara Phalimari PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16631) | SM/16631 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
14 | Solarisation of WBSEDCL Energised Electrical Installation at Maranadirkuthi in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16638) | SM/16638 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
15 | Solarisation of WBSEDCL Energised Electrical Installation at Putimari Phuleshwari PWSS in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16641) | SM/16641 | 9.14 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 14/03/2023 | 11/07/2025 | 13/11/2025 | 18/07/2023 | 0 | 0
16 | Operational charges of Drinking Water Testing laboratory related to water quality monitoring & surveillance under Jal Jeevan Mission (SM/19080) | SM/19080 | 128.43 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
17 | Drinking water sample collection and testing through FTKs & uploading charges related to Water Quality Monitoring & Surveillance under JJM (SM/11939) | SM/11939 | 16.22 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 24/08/2022 |  | 25/08/2022 | 02/01/2023 | 0 | 0
18 | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities (SM/18162) | SM/18162 | 160.04 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 | 04/09/2023 | 0 | 0
19 | Engagement of balance block Community Mobilizer (36 Nos.) through Implementation Support Agency (ISA) for Cooch Behar District. (SM/18163) | SM/18163 | 64.98 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 | 08/08/2023 | 0 | 0
20 | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . (SM/06622) | SM/06622 | 53.58 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 30/04/2021 | 26/09/2022 | 0 | 0
21 | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. (SM/08722) | SM/08722 | 16.27 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 07/09/2021 |  | 28/02/2022 | 14/07/2022 | 0 | 0
22 | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED (SM/11269) | SM/11269 | 73.16 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 24/06/2022 |  | 27/06/2022 | 10/01/2022 | 0 | 0
23 | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTERS AND PRINTERS DEVICE FOR OFFICIAL USE UNDER OFFICE OF EXECUTIVE ENGINEER, COOCH BEHAR DIVISION, P.H.E. DTE. (SM/19011) | SM/19011 | 59.45 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 19/10/2023 |  | 19/10/2023 |  | 0 | 0
24 | Operational Charges of Drinking Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19287) | SM/19287 | 119.06 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
25 | Engagement of Implementation Support Angency (ISA) for implementation of Community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support Activities at Coochbehar District. (SM/11270) | SM/11270 | 184.52 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 24/06/2022 |  | 27/06/2022 | 17/08/2022 | 0 | 0
26 | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTER & PERIPHERAL DEVICE FOR OFFICIAL USE UNDER JAL JEEVAN MISSION UNDER OFFICE OF EXECUTIVE ENGINEER, COOCH BEHAR DIVISION, P.H.E. DTE. (SM/14636) | SM/14636 | 37.07 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 31/01/2023 |  | 03/02/2023 |  | 0 | 0
27 | Operational charges of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/17187) | SM/17187 | 85.95 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 | 31/01/2022 | 0 | 0
28 | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. (SM/09433) | SM/09433 | 927.55 | 277 | ANGANWADI | 10 | Delayed | 0 | 18/11/2021 | 31/12/2025 | 13/11/2025 | 26/07/2021 | 0 | 0
29 | Augmentation of Ground Water Based Dakshin Basrajbala Zone-II PWSS (Haldibari Block) (SM/13152) | SM/13152 | 448.54 | 1357 | AUGMENTATION | 44 | Delayed | 6 | 12/10/2022 | 30/09/2025 | 13/11/2025 | 11/04/2022 | 26.57 | 26.54
30 | AUGMENTATION OF HEMKUMARI PWSS ZONE-III (SM/13150) | SM/13150 | 614.6 | 2117 | AUGMENTATION | 49 | Delayed | 39 | 12/10/2022 | 30/06/2025 | 13/11/2025 | 26/07/2022 | 240.17 | 240.17
31 | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS (SM/16518) | SM/16518 | 564.56 | 1883 | AUGMENTATION | 49 | Delayed | 55 | 03/03/2023 | 31/12/2026 | 13/11/2025 | 28/03/2023 | 312.62 | 312.62
32 | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16515) | SM/16515 | 580.19 | 2154 | AUGMENTATION | 50 | Delayed | 15 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 14/07/2023 | 89.33 | 89.33
33 | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13224) | SM/13224 | 482.9 | 1573 | AUGMENTATION | 50 | Delayed | 34 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 163.5 | 163.5
34 | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-I PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16148) | SM/16148 | 940.17 | 3629 | AUGMENTATION | 53 | Delayed | 20 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 25/07/2023 | 191.05 | 191.05
35 | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . (SM/13148) | SM/13148 | 488.35 | 1546 | AUGMENTATION | 54 | Delayed | 45 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 220.18 | 220.18
36 | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE (SM/15934) | SM/15934 | 885.93 | 4035 | AUGMENTATION | 55 | Delayed | 60 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 18/03/2022 | 531.94 | 531.94
37 | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME (SM/18788) | SM/18788 | 1066.01 | 3370 | AUGMENTATION | 60 | Delayed | 55 | 31/08/2023 | 31/12/2025 | 13/11/2025 | 31/08/2023 | 585.01 | 585.01
38 | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. (SM/13147) | SM/13147 | 851.44 | 2694 | NEW | 60 | Delayed | 52 | 12/10/2022 | 30/06/2025 | 13/11/2025 | 02/03/2023 | 443.06 | 444.48
39 | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. (SM/14936) | SM/14936 | 419.05 | 1074 | NEW | 60 | Delayed | 36 | 03/02/2023 | 31/10/2025 | 13/11/2025 | 10/07/2023 | 152.32 | 152.32
40 | Solarisation of WBSEDCL Energised Electrical Installation at Takoamari in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. (SM/16646) | SM/16646 | 9.14 | 0 | SOLARISATION | 60 | Delayed | 0 | 14/03/2023 | 31/03/2024 | 14/12/2023 | 18/07/2023 | 0 | 0
41 | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. (SM/13163) | SM/13163 | 708.73 | 1912 | NEW | 60 | Delayed | 53 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 06/07/2021 | 375.8 | 375.8
42 | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) (SM/13383) | SM/13383 | 990.25 | 2606 | NEW | 60 | Delayed | 27 | 19/10/2022 | 31/12/2025 | 13/11/2025 | 27/08/2022 | 264.4 | 264.4
43 | AUGMENTATION OF GROUND WATER BASED DALUA DASGIR PWSS COOCHBEHAR - I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16521) | SM/16521 | 487.98 | 1935 | AUGMENTATION | 61 | Delayed | 45 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 218.33 | 218.33
44 | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS (SM/18411) | SM/18411 | 1630.28 | 3760 | NEW | 61 | Delayed | 68 | 12/07/2023 | 31/12/2025 | 13/11/2025 | 25/07/2023 | 1111.44 | 1111.44
45 | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16473) | SM/16473 | 554.02 | 1474 | AUGMENTATION | 61 | Delayed | 35 | 02/03/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 195.95 | 195.95
46 | CHENGERKUTHI KHALISAMARI PWSS (SM/18284) | SM/18284 | 1076.58 | 2835 | NEW | 62 | Delayed | 56 | 23/06/2023 | 31/12/2025 | 13/11/2025 | 25/07/2023 | 603.65 | 603.65
47 | JNANDAS & ITS ADJOINING MOUZAS PWSS (SM/14446) | SM/14446 | 686.15 | 2017 | NEW | 63 | Delayed | 32 | 20/01/2023 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 220.65 | 220.65
48 | ANDARAN KUCHLIBARI PWSS (SM/18140) | SM/18140 | 198.57 | 237 | NEW | 63 | Delayed | 24 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 25/08/2023 | 48.48 | 48.48
49 | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. (SM/13403) | SM/13403 | 2527.51 | 9672 | AUGMENTATION | 63 | Delayed | 43 | 21/10/2022 | 31/12/2025 | 13/11/2025 | 13/05/2022 | 1094.09 | 1094.09
50 | Rejuvenation of LOTAPOTA Water Supply Scheme (SM/10713) | SM/10713 | 93.77 | 631 | AUGMENTATION | 64 | Delayed | 41 | 12/05/2022 | 30/06/2025 | 13/11/2025 | 29/09/2022 | 38.19 | 38.49
51 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II (SM/13288) | SM/13288 | 690.94 | 1192 | NEW | 64 | Delayed | 22 | 17/10/2022 | 31/12/2025 | 13/11/2025 | 23/05/2023 | 152.32 | 152.32
52 | SHUKARUR KUTHI PWSS (SM/18327) | SM/18327 | 1275.13 | 4579 | NEW | 64 | Delayed | 38 | 27/06/2023 | 30/06/2025 | 13/11/2025 | 25/07/2023 | 486.81 | 486.81
53 | DANGA Piped Water Supply Scheme. (SM/14937) | SM/14937 | 948.84 | 2929 | NEW | 64 | Delayed | 33 | 03/02/2023 | 30/06/2025 | 13/11/2025 | 26/09/2022 | 317.73 | 317.73
54 | MOAMARI PIPED WATER SUPPLY SCHEME. (SM/13399) | SM/13399 | 526.17 | 1207 | NEW | 64 | Delayed | 41 | 10/10/2022 | 30/06/2025 | 13/11/2025 | 08/08/2023 | 215.25 | 215.25
55 | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) (SM/13153) | SM/13153 | 576.51 | 1750 | AUGMENTATION | 64 | Delayed | 34 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 10/08/2021 | 198.33 | 198.33
56 | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. (SM/13120) | SM/13120 | 584.09 | 1530 | NEW | 65 | Delayed | 64 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 23/03/2023 | 375.04 | 375.58
57 | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/16146) | SM/16146 | 961.15 | 3871 | AUGMENTATION | 65 | Delayed | 44 | 22/02/2023 | 30/06/2025 | 13/11/2025 | 06/01/2021 | 425.15 | 425.15
58 | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME (SM/11977) | SM/11977 | 2077.66 | 6697 | AUGMENTATION | 65 | Delayed | 49 | 31/08/2022 | 31/10/2025 | 13/11/2025 | 04/03/2022 | 1025.1 | 1025.1
59 | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS (SM/13225) | SM/13225 | 630.23 | 2265 | AUGMENTATION | 65 | Delayed | 50 | 13/10/2022 | 02/06/2025 | 13/11/2025 | 07/04/2022 | 314.78 | 314.78
60 | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. (SM/13289) | SM/13289 | 994.72 | 3356 | AUGMENTATION | 65 | Delayed | 35 | 17/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 343.62 | 230.03
61 | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME (SM/18751) | SM/18751 | 1292.69 | 3239 | NEW | 66 | Delayed | 51 | 18/08/2023 | 31/10/2025 | 13/11/2025 | 02/08/2023 | 653 | 653
62 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B (SM/16164) | SM/16164 | 844.88 | 2168 | NEW | 66 | Delayed | 50 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 13/04/2023 | 420.59 | 421.5
63 | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. (SM/13162) | SM/13162 | 622.41 | 1789 | NEW | 66 | Delayed | 54 | 12/10/2022 | 30/09/2025 | 13/11/2025 | 31/07/2023 | 338.22 | 338.22
64 | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE (SM/16153) | SM/16153 | 317.15 | 3025 | AUGMENTATION | 66 | Delayed | 41 | 22/02/2023 | 30/06/2025 | 13/11/2025 | 30/03/2023 | 131.45 | 131.45
65 | AUGUMENTATION OF GROUND WATER BASED BARAI BARI PWSS MATHABHANGA II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE (SM/16527) | SM/16527 | 521.44 | 1243 | AUGMENTATION | 67 | Delayed | 49 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 253.95 | 253.95
66 | LANKABAR PIPED WATER SUPPLY SCHEME (SM/13618) | SM/13618 | 373.21 | 952 | NEW | 67 | Delayed | 40 | 11/11/2022 | 31/05/2025 | 13/11/2025 | 24/01/2023 | 150.97 | 154.49
67 | SAJHERPAR KHATALBARI (SM/13877) | SM/13877 | 561.56 | 1650 | NEW | 67 | Delayed | 41 | 25/11/2022 | 30/09/2025 | 13/11/2025 | 13/02/2023 | 230.88 | 230.88
68 | KSHETI PIPED WATER SUPPLY SCHEME. (SM/13208) | SM/13208 | 849.21 | 2943 | NEW | 67 | Delayed | 71 | 12/10/2022 | 30/06/2025 | 13/11/2025 | 02/03/2023 | 601.23 | 601.23
69 | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME (SM/18757) | SM/18757 | 1693.56 | 5630 | AUGMENTATION | 67 | Delayed | 60 | 21/08/2023 | 31/10/2025 | 13/11/2025 | 21/08/2023 | 1009.2 | 1009.2
70 | Augmentation of Natabari Pwss (SM/15935) | SM/15935 | 677.63 | 2112 | AUGMENTATION | 68 | Delayed | 34 | 22/02/2023 | 12/06/2025 | 13/11/2025 | 31/12/2021 | 229.17 | 229.17
71 | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13223) | SM/13223 | 435.95 | 1340 | AUGMENTATION | 68 | Delayed | 27 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 116.94 | 116.94
72 | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME (SM/15931) | SM/15931 | 313.71 | 2127 | AUGMENTATION | 68 | Delayed | 35 | 22/02/2023 | 30/06/2025 | 13/11/2025 | 24/05/2022 | 108.63 | 108.63
73 | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. (SM/13402) | SM/13402 | 2511.71 | 6886 | AUGMENTATION | 68 | Delayed | 45 | 21/10/2022 | 30/06/2025 | 13/11/2025 | 29/12/2022 | 1124.57 | 1124.57
74 | Rejuvenation of DEOCHARAI Water Supply Scheme (SM/10364) | SM/10364 | 73.44 | 490 | AUGMENTATION | 69 | Delayed | 20 | 16/03/2022 | 31/12/2025 | 13/11/2025 | 29/03/2022 | 14.83 | 16.35
75 | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME (SM/14134) | SM/14134 | 1454.59 | 3735 | NEW | 70 | Delayed | 69 | 02/01/2023 | 31/12/2025 | 13/11/2025 | 02/03/2023 | 1010.21 | 1010.21
76 | AUGMENTATION OF GROUND WATER BASED BAJRAPUR PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16139) | SM/16139 | 543.27 | 1298 | AUGMENTATION | 70 | Delayed | 51 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 05/04/2023 | 275.46 | 276.35
77 | GROUND WATER BASED KHATERBARI PIPED WATER SUPPLY SCHEME (SM/18135) | SM/18135 | 940.9 | 2225 | NEW | 70 | Delayed | 64 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 12/07/2023 | 603.15 | 404.08
78 | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) (SM/13156) | SM/13156 | 932.83 | 3410 | AUGMENTATION | 70 | Delayed | 47 | 12/10/2022 | 31/10/2025 | 13/11/2025 | 02/03/2023 | 436.02 | 436.02
79 | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/14933) | SM/14933 | 985.67 | 9385 | AUGMENTATION | 70 | Delayed | 42 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 07/04/2022 | 412.34 | 392.81
80 | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16149) | SM/16149 | 595.27 | 1628 | AUGMENTATION | 70 | Delayed | 54 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 06/01/2021 | 323.85 | 323.85
81 | Augmentation of Tutiarkuthi Piped Water Supply Scheme. (SM/15930) | SM/15930 | 616.66 | 4749 | AUGMENTATION | 71 | Delayed | 58 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 29/09/2022 | 360.44 | 360.43
82 | NUTANBAS PIPED WATER SUPPLY SCHEME (SM/14453) | SM/14453 | 678.94 | 932 | NEW | 71 | Delayed | 36 | 20/01/2023 | 31/12/2025 | 13/11/2025 | 03/02/2023 | 243.15 | 244.88
83 | AUGMENTATION OF GROUND WATER BASED BASKOTAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13222) | SM/13222 | 294.45 | 646 | AUGMENTATION | 71 | Delayed | 50 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 146.11 | 146.11
84 | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16523) | SM/16523 | 240.36 | 421 | AUGMENTATION | 72 | Delayed | 20 | 03/03/2023 | 30/06/2025 | 13/11/2025 | 02/06/2023 | 46.9 | 48.81
85 | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME (SM/09293) | SM/09293 | 184.05 | 2251 | AUGMENTATION | 72 | Delayed | 87 | 09/11/2021 | 30/06/2025 | 13/11/2025 | 24/12/2021 | 160.21 | 160.21
86 | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. (SM/13157) | SM/13157 | 948.34 | 3575 | AUGMENTATION | 72 | Delayed | 55 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 13/08/2021 | 519.33 | 504.19
87 | Daribash Pratham Khanda (SM/14948) | SM/14948 | 482.38 | 579 | NEW | 72 | Delayed | 66 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 03/10/2023 | 317.38 | 317.38
88 | Tanapakha Piped Water Supply Scheme (SM/16152) | SM/16152 | 204.43 | 136 | NEW | 72 | Delayed | 65 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 17/04/2023 | 133.69 | 133.69
89 | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. (SM/14904) | SM/14904 | 603.05 | 486 | AUGMENTATION | 73 | Delayed | 66 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 06/08/2021 | 401.02 | 401.68
90 | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16140) | SM/16140 | 575.24 | 1687 | AUGMENTATION | 73 | Delayed | 45 | 22/02/2023 | 31/10/2025 | 13/11/2025 | 28/03/2023 | 257.61 | 259.36
91 | GROUND WATER BASED SARAHATI PIPED WATER SUPPLY SCHEME. (SM/13390) | SM/13390 | 488.88 | 1259 | NEW | 74 | Delayed | 38 | 19/10/2022 | 31/10/2025 | 13/11/2025 | 08/08/2023 | 186.03 | 186.03
92 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI (SM/14138) | SM/14138 | 1823.04 | 4183 | NEW | 74 | On track | 42 | 02/01/2023 | 31/12/2026 | 13/11/2025 | 02/03/2023 | 759.55 | 760.41
93 | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. (SM/18240) | SM/18240 | 1231.66 | 3109 | NEW | 74 | Delayed | 47 | 16/06/2023 | 30/06/2025 | 13/11/2025 | 12/07/2023 | 578.83 | 581.21
94 | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME (SM/17439) | SM/17439 | 218.09 | 2660 | AUGMENTATION | 74 | Delayed | 65 | 18/03/2023 | 31/12/2025 | 13/11/2025 | 17/04/2023 | 141.95 | 141.95
95 | CHANDAMARI PWSS (SM/18138) | SM/18138 | 293.28 | 327 | NEW | 74 | Delayed | 59 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 12/07/2023 | 171.83 | 171.83
96 | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. (SM/15912) | SM/15912 | 725.42 | 1932 | NEW | 74 | Delayed | 42 | 22/02/2023 | 30/06/2025 | 13/11/2025 | 17/03/2023 | 302.7 | 302.7
97 | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME (SM/18133) | SM/18133 | 467.56 | 736 | NEW | 74 | Delayed | 41 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 12/07/2023 | 191.87 | 192.41
98 | PESTARJHAR PWSS (SM/18248) | SM/18248 | 1394.07 | 3499 | NEW | 75 | Delayed | 49 | 16/06/2023 | 31/10/2025 | 13/11/2025 | 12/07/2023 | 679.96 | 679.95
99 | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme (SM/10362) | SM/10362 | 134.86 | 1360 | AUGMENTATION | 75 | Delayed | 53 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 71.6 | 71.6
100 | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/15933) | SM/15933 | 445.03 | 1225 | AUGMENTATION | 75 | Delayed | 43 | 22/02/2023 | 30/09/2025 | 13/11/2025 | 28/03/2023 | 193.3 | 194.17
101 | SHIKARPUR PIPED WATER SUPPLY SCHEME. (SM/13614) | SM/13614 | 528.07 | 1784 | NEW | 75 | Delayed | 61 | 11/11/2022 | 30/06/2025 | 13/11/2025 | 23/06/2022 | 322.25 | 322.25
102 | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. (SM/13137) | SM/13137 | 931.09 | 1817 | NEW | 75 | Delayed | 52 | 12/10/2022 | 30/06/2025 | 13/11/2025 | 02/03/2023 | 488.43 | 490.79
103 | Atpukhari Piped Water Supply Scheme. (SM/14250) | SM/14250 | 1775.8 | 1333 | NEW | 75 | Delayed | 49 | 16/01/2023 | 30/06/2025 | 13/11/2025 | 21/02/2023 | 871.98 | 875.54
104 | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block (SM/13459) | SM/13459 | 744.73 | 1655 | NEW | 75 | Delayed | 38 | 02/11/2022 | 30/06/2025 | 13/11/2025 | 13/02/2023 | 284.56 | 284.56
105 | HOKADAHA PRATHAM KHANDA PWSS (SM/14938) | SM/14938 | 482.38 | 984 | NEW | 75 | Delayed | 52 | 03/02/2023 | 31/05/2025 | 13/11/2025 | 13/02/2023 | 248.97 | 252.48
106 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK (SM/13684) | SM/13684 | 996.96 | 3222 | AUGMENTATION | 76 | Delayed | 39 | 14/11/2022 | 31/10/2025 | 13/11/2025 | 16/08/2022 | 390 | 390
107 | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS (SM/16516) | SM/16516 | 523.99 | 525 | AUGMENTATION | 76 | Delayed | 27 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 08/08/2023 | 142.59 | 143.46
108 | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. (SM/13211) | SM/13211 | 299.26 | 744 | NEW | 78 | Delayed | 80 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 13/02/2023 | 239.28 | 239.28
109 | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block (SM/13380) | SM/13380 | 898.7 | 3436 | AUGMENTATION | 78 | Delayed | 43 | 19/10/2022 | 31/10/2025 | 13/11/2025 | 02/03/2023 | 389.06 | 389.06
110 | BARA ADABARI PIPED WATER SUPPLY SCHEME (SM/14731) | SM/14731 | 657.19 | 1972 | NEW | 78 | Delayed | 51 | 31/01/2023 | 30/06/2025 | 13/11/2025 | 06/03/2023 | 332.83 | 336.29
111 | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13181) | SM/13181 | 517.02 | 2538 | AUGMENTATION | 78 | Delayed | 96 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 24/01/2023 | 497.97 | 501.49
112 | BARA MADHUSUDAN PWSS (SM/16524) | SM/16524 | 445.75 | 1030 | NEW | 78 | Delayed | 59 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 08/08/2023 | 261.88 | 261.88
113 | AUGMENTATION OF GROUND WATER BASED NAKKATI PWSS COOCH BEHAR-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/14934) | SM/14934 | 488.42 | 3196 | AUGMENTATION | 78 | Delayed | 25 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 13/05/2022 | 124.44 | 124.44
114 | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. (SM/13389) | SM/13389 | 952.82 | 2510 | NEW | 78 | Delayed | 56 | 19/10/2022 | 31/12/2025 | 13/11/2025 | 27/12/2021 | 529.72 | 529.72
115 | FALIMARI PIPED WATER SUPPLY SCHEME (SM/18616) | SM/18616 | 1373.12 | 2854 | NEW | 78 | Delayed | 46 | 31/07/2023 | 31/12/2025 | 13/11/2025 | 08/08/2023 | 635.71 | 635.71
116 | PANIGRAM PIPED WATER SUPPLY SCHEME (SM/12271) | SM/12271 | 1535.1 | 5168 | NEW | 78 | Delayed | 73 | 09/09/2022 | 30/06/2025 | 13/11/2025 | 09/09/2022 | 1123.41 | 1126.88
117 | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. (SM/13212) | SM/13212 | 551.62 | 1807 | NEW | 78 | Delayed | 64 | 12/10/2022 | 30/06/2025 | 13/11/2025 | 13/02/2023 | 355.27 | 355.27
118 | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/14928) | SM/14928 | 461.74 | 2968 | AUGMENTATION | 78 | Delayed | 21 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 95.81 | 95.81
119 | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. (SM/13229) | SM/13229 | 646.74 | 1756 | AUGMENTATION | 79 | Delayed | 40 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 261.62 | 261.62
120 | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) (SM/14137) | SM/14137 | 1324.12 | 3362 | NEW | 79 | Delayed | 68 | 02/01/2023 | 31/10/2025 | 13/11/2025 | 02/03/2023 | 899.13 | 900.91
121 | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME (SM/15932) | SM/15932 | 457.49 | 2935 | AUGMENTATION | 79 | Delayed | 71 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 23/06/2022 | 325.01 | 325.01
122 | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS (SM/14449) | SM/14449 | 618.21 | 1972 | NEW | 79 | Delayed | 66 | 20/01/2023 | 31/10/2025 | 13/11/2025 | 13/02/2023 | 407.16 | 408.94
123 | BHOGDABARI PIPED WATER SUPPLY SCHEME. (SM/13164) | SM/13164 | 600.53 | 1600 | NEW | 79 | Delayed | 55 | 12/10/2022 | 31/10/2025 | 13/11/2025 | 23/05/2023 | 330.35 | 330.35
124 | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME (SM/16156) | SM/16156 | 120.36 | 1332 | AUGMENTATION | 79 | Delayed | 67 | 22/02/2023 | 31/10/2025 | 13/11/2025 | 03/12/2021 | 80.42 | 80.42
125 | Rejuvenation of Payamari Water Supply Scheme (SM/09824) | SM/09824 | 358.73 | 2558 | AUGMENTATION | 79 | Delayed | 37 | 01/12/2021 | 31/12/2025 | 13/11/2025 | 28/09/2020 | 131.09 | 131.07
126 | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME (SM/14183) | SM/14183 | 1895.41 | 6863 | AUGMENTATION | 79 | Delayed | 64 | 02/01/2023 | 31/05/2025 | 13/11/2025 | 18/03/2022 | 1208.93 | 1208.93
127 | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/16150) | SM/16150 | 525.64 | 1226 | AUGMENTATION | 79 | Delayed | 61 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 29/03/2022 | 318.75 | 318.7
128 | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION (SM/18122) | SM/18122 | 488.35 | 2480 | AUGMENTATION | 79 | Delayed | 47 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 228.3 | 228.3
129 | BARA MARICHA PIPED WATER SUPPLY SCHEME (SM/13286) | SM/13286 | 553.04 | 2000 | NEW | 79 | Delayed | 75 | 17/10/2022 | 31/12/2025 | 13/11/2025 | 17/03/2023 | 415.8 | 416.69
130 | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. (SM/16147) | SM/16147 | 141.87 | 934 | AUGMENTATION | 79 | Delayed | 19 | 22/02/2023 | 31/10/2025 | 13/11/2025 | 14/03/2023 | 27.65 | 27.65
131 | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. (SM/14139) | SM/14139 | 1851.84 | 4247 | NEW | 80 | Delayed | 38 | 02/01/2023 | 31/10/2025 | 13/11/2025 | 05/06/2023 | 710.29 | 710.25
132 | MADHURBHASA PIPED WATER SUPPLY SCHEME (SM/13765) | SM/13765 | 165.05 | 318 | NEW | 80 | Delayed | 58 | 18/11/2022 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 95.59 | 96.77
133 | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS (SM/14206) | SM/14206 | 937.55 | 2143 | NEW | 80 | Delayed | 68 | 10/01/2023 | 31/05/2025 | 13/11/2025 | 02/03/2023 | 640.13 | 617.58
134 | NENDARPAR PWSS (SM/18137) | SM/18137 | 538.1 | 913 | NEW | 80 | On track | 68 | 29/03/2023 | 31/12/2027 | 13/11/2025 | 25/08/2023 | 368.05 | 368.05
135 | Rejuvenation of HARI BHANGA Piped Water Supply Scheme (SM/10160) | SM/10160 | 209.84 | 3106 | AUGMENTATION | 80 | Delayed | 45 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 29/03/2022 | 94.32 | 94.32
136 | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. (SM/13136) | SM/13136 | 590.02 | 1537 | NEW | 80 | Delayed | 69 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 19/01/2023 | 408.31 | 411.17
137 | Augmentatin of Bajejama Chilakhana Zone-III PWSS Accomodate FHTC in TFG-I BLOCK (SM/13378) | SM/13378 | 496.18 | 1486 | AUGMENTATION | 80 | Delayed | 59 | 19/10/2022 | 31/05/2025 | 13/11/2025 | 24/01/2023 | 291.27 | 291.27
138 | Rejuvenation of BHANGA MORE Water Supply Scheme (SM/10712) | SM/10712 | 180.12 | 652 | AUGMENTATION | 80 | Delayed | 55 | 12/05/2022 | 31/05/2025 | 13/11/2025 | 13/02/2023 | 99.64 | 99.64
139 | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme (SM/10361) | SM/10361 | 99.56 | 765 | AUGMENTATION | 80 | Delayed | 54 | 16/03/2022 | 30/06/2025 | 13/11/2025 | 07/04/2022 | 53.61 | 53.61
140 | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16519) | SM/16519 | 539.21 | 1539 | AUGMENTATION | 80 | Delayed | 53 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 284.57 | 284.57
141 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK (SM/13316) | SM/13316 | 999.75 | 3932 | AUGMENTATION | 80 | On track | 46 | 17/10/2022 | 31/12/2026 | 13/11/2025 | 02/03/2023 | 456.64 | 456.64
142 | ASAKBARI PRATHAM KHANDA PWSS (SM/14203) | SM/14203 | 914.53 | 2765 | NEW | 81 | Delayed | 62 | 10/01/2023 | 31/10/2025 | 13/11/2025 | 02/03/2023 | 569.96 | 531.26
143 | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME (SM/18412) | SM/18412 | 1218.17 | 2739 | NEW | 81 | Delayed | 55 | 12/07/2023 | 31/10/2025 | 13/11/2025 | 25/07/2023 | 666.24 | 666.24
144 | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME (SM/16472) | SM/16472 | 271.23 | 250 | AUGMENTATION | 81 | Delayed | 51 | 02/03/2023 | 31/05/2025 | 13/11/2025 | 10/07/2023 | 137.89 | 137.89
145 | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16166) | SM/16166 | 329.42 | 416 | AUGMENTATION | 81 | Delayed | 42 | 22/02/2023 | 31/05/2025 | 13/11/2025 | 23/05/2023 | 137.82 | 137.82
146 | JORE SIMULI PIPED WATER SUPPLY SCHEME (SM/16541) | SM/16541 | 1052.45 | 3228 | NEW | 81 | Delayed | 41 | 10/03/2023 | 31/10/2025 | 13/11/2025 | 22/03/2023 | 434.13 | 334.13
147 | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. (SM/13138) | SM/13138 | 296.22 | 514 | NEW | 81 | Delayed | 49 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 27/06/2022 | 145.94 | 152.99
148 | Kuchni Pratham Khanda Piped Water Supply Scheme. (SM/18781) | SM/18781 | 478.21 | 1383 | NEW | 81 | Delayed | 68 | 29/08/2023 | 31/10/2025 | 13/11/2025 | 31/08/2023 | 324.37 | 324.37
149 | Nandina Piped Water Supply Scheme. (SM/18750) | SM/18750 | 646.86 | 1530 | NEW | 81 | Delayed | 53 | 18/08/2023 | 30/09/2025 | 13/11/2025 | 22/08/2023 | 342.56 | 342.56
150 | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) (SM/13287) | SM/13287 | 241.38 | 258 | NEW | 81 | Delayed | 38 | 17/10/2022 | 30/09/2025 | 13/11/2025 | 29/12/2022 | 90.69 | 90.69
151 | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME (SM/14452) | SM/14452 | 477.54 | 1206 | NEW | 81 | Delayed | 43 | 20/01/2023 | 31/12/2025 | 13/11/2025 | 11/03/2024 | 204.27 | 206.05
152 | JHINGAPUNI PIPED WATER SUPPLY SCHEME (SM/13881) | SM/13881 | 444.27 | 1013 | NEW | 81 | Delayed | 53 | 25/11/2022 | 31/10/2025 | 13/11/2025 | 24/01/2023 | 234.14 | 235.92
153 | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16522) | SM/16522 | 306.15 | 494 | AUGMENTATION | 81 | Delayed | 9 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 16/08/2023 | 26.46 | 27.93
154 | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) (SM/13154) | SM/13154 | 496.67 | 1558 | AUGMENTATION | 82 | Delayed | 35 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 174.14 | 174.14
155 | CHHITRI BARI PIPED WATER SUPPLY SCHEME. (SM/13213) | SM/13213 | 452.25 | 1271 | NEW | 82 | Delayed | 66 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 19/01/2023 | 297.15 | 298.84
156 | DAKSHIN KHARIJA GITALDAHA PWSS (SM/14204) | SM/14204 | 739.64 | 2469 | NEW | 82 | Delayed | 50 | 10/01/2023 | 31/05/2025 | 13/11/2025 | 03/02/2023 | 369.15 | 371.51
157 | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. (SM/13816) | SM/13816 | 628.46 | 1272 | NEW | 82 | Delayed | 53 | 23/11/2022 | 30/06/2025 | 13/11/2025 | 19/01/2023 | 331.21 | 331.21
158 | JAIGIR CHILAKHANA Piped Water Supply Scheme (SM/16155) | SM/16155 | 909.76 | 3264 | NEW | 82 | Delayed | 47 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 25/07/2023 | 424.42 | 425.3
159 | NAKARJAN AND ITS ADJOINING MOUZAS PWSS (SM/18239) | SM/18239 | 1059.63 | 2520 | NEW | 82 | Delayed | 41 | 16/06/2023 | 31/10/2025 | 13/11/2025 | 12/07/2023 | 433.03 | 434.77
160 | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. (SM/18369) | SM/18369 | 1054.46 | 2650 | NEW | 82 | Delayed | 80 | 11/07/2023 | 31/05/2025 | 13/11/2025 | 14/07/2023 | 844.65 | 844.59
161 | KHARIJA KHAWARDARA PIPED WATER SUPPLY SCHEME (SM/18132) | SM/18132 | 468.19 | 792 | NEW | 82 | Delayed | 41 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 25/08/2023 | 192.42 | 193.28
162 | MAHISHCHARU PIPED WATER SUPPLY SCHEME. (SM/13207) | SM/13207 | 798.83 | 2539 | NEW | 83 | On track | 70 | 12/10/2022 | 31/12/2026 | 13/11/2025 | 02/03/2023 | 555.94 | 557.72
163 | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME (SM/16350) | SM/16350 | 635.08 | 2132 | AUGMENTATION | 83 | Delayed | 82 | 28/02/2023 | 31/12/2025 | 13/11/2025 | 13/05/2022 | 522.22 | 522.22
164 | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME (SM/18299) | SM/18299 | 1076.42 | 5300 | AUGMENTATION | 83 | Delayed | 72 | 26/06/2023 | 31/12/2025 | 13/11/2025 | 14/07/2023 | 775.28 | 779.96
165 | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME (SM/13227) | SM/13227 | 436.97 | 1604 | AUGMENTATION | 83 | Delayed | 48 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 04/03/2022 | 210.09 | 210.09
166 | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) (SM/13155) | SM/13155 | 798.13 | 3874 | AUGMENTATION | 83 | Delayed | 21 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 07/01/2021 | 166.3 | 166.3
167 | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme (SM/10159) | SM/10159 | 883.16 | 0 | AUGMENTATION | 83 | Delayed | 57 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 501.22 | 501.13
168 | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE (SM/16520) | SM/16520 | 493.6 | 1903 | AUGMENTATION | 83 | Delayed | 72 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 27/08/2022 | 357.33 | 357.33
169 | Augmentation of Dakshin Bajejama Water Supply Scheme. (SM/09807) | SM/09807 | 337.36 | 2091 | AUGMENTATION | 83 | Delayed | 67 | 01/12/2021 | 30/09/2025 | 13/11/2025 | 09/02/2022 | 224.88 | 227.49
170 | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme (SM/10708) | SM/10708 | 154.34 | 267 | AUGMENTATION | 83 | Delayed | 79 | 12/05/2022 | 31/12/2025 | 13/11/2025 | 10/03/2022 | 122.03 | 123.81
171 | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME (SM/18134) | SM/18134 | 326.89 | 375 | NEW | 83 | Delayed | 48 | 29/03/2023 | 02/12/2025 | 13/11/2025 | 10/07/2023 | 156.39 | 159.16
172 | Augmentation of bajejama chilakhana zone-II PWSS (SM/13386) | SM/13386 | 461.75 | 1107 | AUGMENTATION | 83 | Delayed | 57 | 19/10/2022 | 31/10/2025 | 13/11/2025 | 10/01/2022 | 261.36 | 261.36
173 | AUGMENTATION OF GROUND WATER BASED NAJIRAN DEUTIKATA PWSS TAFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/15981) | SM/15981 | 455.1 | 2944 | AUGMENTATION | 83 | Delayed | 58 | 22/02/2023 | 31/10/2025 | 13/11/2025 | 28/03/2023 | 264.96 | 264.96
174 | Rejuvenation of KHAPAIDANGA Water Supply Scheme (SM/10363) | SM/10363 | 100.03 | 998 | AUGMENTATION | 84 | Delayed | 58 | 16/03/2022 | 31/12/2025 | 13/11/2025 | 13/05/2022 | 57.83 | 57.83
175 | KHARI ANALDHONDRA PWSS (SM/14136) | SM/14136 | 1124.16 | 2792 | NEW | 84 | Delayed | 67 | 02/01/2023 | 30/06/2025 | 13/11/2025 | 02/03/2023 | 753.74 | 756.71
176 | BHALKA PIPED WATER SUPPLY SCHEME (SM/15237) | SM/15237 | 523.63 | 1431 | NEW | 84 | Delayed | 76 | 07/02/2023 | 31/05/2025 | 13/11/2025 | 23/05/2023 | 395.51 | 395.51
177 | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13860) | SM/13860 | 473.77 | 2784 | AUGMENTATION | 84 | Delayed | 58 | 25/11/2022 | 31/12/2025 | 13/11/2025 | 09/02/2022 | 275.56 | 277.78
178 | INDRA NARAYAN PWSS (SM/14205) | SM/14205 | 580.49 | 1948 | NEW | 84 | Delayed | 66 | 10/01/2023 | 31/12/2025 | 13/11/2025 | 03/02/2023 | 384.77 | 384.77
179 | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME (SM/09297) | SM/09297 | 412.88 | 1468 | AUGMENTATION | 84 | Delayed | 81 | 09/11/2021 | 31/12/2025 | 13/11/2025 | 24/12/2021 | 335.22 | 339.18
180 | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. (SM/13161) | SM/13161 | 490.18 | 1492 | NEW | 84 | Delayed | 75 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 24/05/2022 | 366.56 | 369.2
181 | Ground water based KURSHAMARI PWSS (SM/18139) | SM/18139 | 508.36 | 1074 | NEW | 84 | Delayed | 68 | 29/03/2023 | 31/12/2025 | 13/11/2025 | 25/08/2023 | 344.46 | 337.01
182 | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. (SM/13145) | SM/13145 | 950.27 | 4355 | NEW | 84 | Delayed | 56 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 23/05/2023 | 532.41 | 535.08
183 | Rejuvenation of KUMIRGHAT Water Supply Scheme (SM/10360) | SM/10360 | 81.91 | 554 | AUGMENTATION | 84 | Delayed | 89 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 10/03/2022 | 72.74 | 72.73
184 | Augmentation of GHUGHUMARI Piped Water Supply Scheme (SM/16531) | SM/16531 | 1547.57 | 6473 | AUGMENTATION | 84 | On track | 65 | 10/03/2023 | 31/03/2026 | 13/11/2025 | 10/03/2022 | 1007.26 | 1008.45
185 | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. (SM/13385) | SM/13385 | 468.31 | 1628 | AUGMENTATION | 84 | Delayed | 53 | 19/10/2022 | 31/10/2025 | 13/11/2025 | 24/01/2023 | 249.85 | 250.73
186 | CHHIT BARA LAUKUTHI PWSS (SM/13865) | SM/13865 | 302.56 | 535 | NEW | 84 | Delayed | 61 | 25/11/2022 | 31/12/2025 | 13/11/2025 | 06/10/2023 | 184.03 | 184.03
187 | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION (SM/13149) | SM/13149 | 461.59 | 1294 | AUGMENTATION | 84 | Delayed | 44 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 204.96 | 204.96
188 | Rejuvenation of BARO PINJARERJHAR Water Supply Scheme (SM/11258) | SM/11258 | 118.06 | 124 | AUGMENTATION | 84 | Delayed | 53 | 23/06/2022 | 31/12/2025 | 13/11/2025 | 23/05/2023 | 62.69 | 62.69
189 | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME (SM/13284) | SM/13284 | 821.73 | 2410 | NEW | 84 | Delayed | 72 | 17/10/2022 | 31/12/2025 | 13/11/2025 | 02/03/2023 | 589.32 | 589.31
190 | CHAUDANGA PIPED WATER SUPPLY SCHEME. (SM/13146) | SM/13146 | 491.65 | 1037 | NEW | 84 | Delayed | 42 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 03/02/2023 | 208.43 | 208.43
191 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK (SM/13379) | SM/13379 | 850.86 | 2671 | AUGMENTATION | 84 | Delayed | 50 | 19/10/2022 | 31/05/2025 | 13/11/2025 | 16/08/2022 | 422.22 | 423.09
192 | Augmentation of Panisala PWSS. (SM/16526) | SM/16526 | 133.17 | 230 | AUGMENTATION | 84 | Delayed | 84 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 27/08/2022 | 112.1 | 112.1
193 | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME (SM/09296) | SM/09296 | 496.33 | 1107 | AUGMENTATION | 85 | Delayed | 89 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 31/12/2021 | 444.01 | 444.01
194 | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME (SM/13490) | SM/13490 | 639.34 | 1704 | NEW | 85 | Delayed | 58 | 02/11/2022 | 31/12/2025 | 13/11/2025 | 24/01/2023 | 372.99 | 372.99
195 | KHENGCHI PIPED WATER SUPPLY SCHEME. (SM/13209) | SM/13209 | 516.26 | 1412 | NEW | 85 | Delayed | 85 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 03/02/2023 | 440.95 | 442.68
196 | GABUA PIPED WATER SUPPLY SCHEME (SM/13458) | SM/13458 | 677.63 | 1575 | NEW | 85 | Delayed | 70 | 02/11/2022 | 31/05/2025 | 13/11/2025 | 23/05/2023 | 477.46 | 480.78
197 | Mansai Piped Water Supply Scheme. (SM/18764) | SM/18764 | 574.57 | 793 | NEW | 85 | On track | 82 | 23/08/2023 | 31/03/2026 | 13/11/2025 | 25/08/2023 | 470.7 | 473.35
198 | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13226) | SM/13226 | 544.88 | 2419 | AUGMENTATION | 85 | Delayed | 62 | 13/10/2022 | 31/05/2025 | 13/11/2025 | 16/08/2022 | 338.98 | 338.98
199 | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) (SM/13230) | SM/13230 | 476.16 | 1542 | AUGMENTATION | 85 | Delayed | 46 | 13/10/2022 | 31/12/2025 | 13/11/2025 | 11/04/2022 | 218.6 | 218.6
200 | BIJLICHATKA PIPED WATER SUPPLY SCHEME. (SM/13215) | SM/13215 | 617.06 | 2239 | NEW | 85 | Delayed | 70 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 19/01/2023 | 432.13 | 432.13
201 | Augmentation of MARADANGA Piped Water Supply Scheme (SM/14112) | SM/14112 | 1640.51 | 5550 | AUGMENTATION | 85 | Delayed | 65 | 15/12/2022 | 31/12/2025 | 13/11/2025 | 09/02/2022 | 1061.44 | 1062.32
202 | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. (SM/10158) | SM/10158 | 305.36 | 1880 | AUGMENTATION | 85 | Delayed | 94 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 287.07 | 287.05
203 | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. (SM/13859) | SM/13859 | 276.66 | 1416 | AUGMENTATION | 85 | Delayed | 80 | 25/11/2022 | 31/12/2025 | 13/11/2025 | 10/08/2021 | 222.54 | 222.54
204 | ICHAMARI PIPED WATER SUPPLY SCHEME. (SM/13119) | SM/13119 | 536.65 | 1178 | NEW | 85 | Delayed | 62 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 19/01/2023 | 335.15 | 337.47
205 | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. (SM/13118) | SM/13118 | 476.17 | 1171 | NEW | 85 | Delayed | 59 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 25/08/2023 | 280.05 | 280.05
206 | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME (SM/12371) | SM/12371 | 1689.1 | 6354 | AUGMENTATION | 85 | On track | 73 | 13/09/2022 | 31/12/2027 | 13/11/2025 | 02/05/2022 | 1241.18 | 1241.73
207 | PETLAEPRA PIPED WATER SUPPLY SCHEME (SM/13285) | SM/13285 | 833.61 | 2353 | NEW | 85 | Delayed | 53 | 17/10/2022 | 31/05/2025 | 13/11/2025 | 19/01/2023 | 443 | 446.49
208 | PAKHIHAGA PIPED WATER SUPPLY SCHEME. (SM/13165) | SM/13165 | 568.34 | 1301 | NEW | 85 | On track | 62 | 12/10/2022 | 31/12/2027 | 13/11/2025 | 26/07/2023 | 353.91 | 359.18
209 | AUGMENTATION OF GROUND WATER BASED SHILGHAGRI PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16167) | SM/16167 | 284.75 | 489 | AUGMENTATION | 85 | Delayed | 66 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 02/06/2023 | 187.03 | 187.03
210 | SHALBARI PIPED WATER SUPPLY SCHEME (SM/18370) | SM/18370 | 1211.5 | 2797 | NEW | 85 | Delayed | 73 | 11/07/2023 | 31/05/2025 | 13/11/2025 | 04/09/2023 | 884.33 | 884.33
211 | Augmentation of Guriahati Pwss (SM/18297) | SM/18297 | 1441.79 | 5986 | AUGMENTATION | 85 | Delayed | 30 | 26/06/2023 | 31/05/2025 | 13/11/2025 | 14/07/2023 | 436.3 | 447.24
212 | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . (SM/13382) | SM/13382 | 440.96 | 1032 | AUGMENTATION | 85 | Delayed | 56 | 19/10/2022 | 31/05/2025 | 13/11/2025 | 17/04/2023 | 248.17 | 248.17
213 | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME (SM/09810) | SM/09810 | 743.36 | 2372 | AUGMENTATION | 85 | Delayed | 86 | 01/12/2021 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 640.55 | 640.55
214 | Augmentation of Takagach piped water supply scheme. (SM/09301) | SM/09301 | 616.11 | 0 | AUGMENTATION | 85 | Delayed | 94 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 27/12/2021 | 581.06 | 581.06
215 | PATCHHARA PWSS (SM/18368) | SM/18368 | 1412.01 | 3925 | NEW | 85 | Delayed | 56 | 11/07/2023 | 31/05/2025 | 13/11/2025 | 14/07/2023 | 784.8 | 784.8
216 | BAILPARI PIPED WATER SUPPLY SCHEME. (SM/13463) | SM/13463 | 806.99 | 2000 | NEW | 85 | Delayed | 82 | 02/11/2022 | 31/05/2025 | 13/11/2025 | 24/03/2023 | 663.27 | 663.21
217 | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. (SM/13400) | SM/13400 | 688.35 | 1973 | NEW | 85 | Delayed | 60 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 01/08/2023 | 409.74 | 409.74
218 | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME (SM/13619) | SM/13619 | 906.99 | 2276 | NEW | 85 | Delayed | 64 | 11/11/2022 | 31/05/2025 | 13/11/2025 | 02/03/2023 | 581.75 | 581.75
219 | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. (SM/13228) | SM/13228 | 835.55 | 2874 | AUGMENTATION | 85 | On track | 57 | 13/10/2022 | 31/12/2027 | 13/11/2025 | 13/08/2021 | 479.84 | 480.73
220 | KISMAT MOKARARI PWSS (SM/14201) | SM/14201 | 906.42 | 2470 | NEW | 85 | Delayed | 73 | 10/01/2023 | 31/12/2025 | 13/11/2025 | 15/02/2022 | 659.74 | 664.95
221 | Augumentation of Nalangibari Water Supply scheme (SM/09823) | SM/09823 | 435.26 | 3796 | AUGMENTATION | 86 | Delayed | 96 | 01/12/2021 | 31/05/2025 | 13/11/2025 | 04/01/2022 | 418.65 | 418.65
222 | DHANG DHINGGURI PWSS (SM/13460) | SM/13460 | 600.46 | 1732 | NEW | 86 | Delayed | 51 | 02/11/2022 | 31/12/2025 | 13/11/2025 | 19/01/2023 | 305.04 | 305.04
223 | KHAGRIBARI PIPED WATER SUPPLY SCHEME (SM/13882) | SM/13882 | 356.54 | 560 | NEW | 86 | Delayed | 74 | 25/11/2022 | 31/10/2025 | 13/11/2025 | 13/02/2023 | 264.85 | 266.61
224 | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT (SM/16165) | SM/16165 | 551.8 | 1273 | AUGMENTATION | 86 | Delayed | 62 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 341.01 | 341.01
225 | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. (SM/13290) | SM/13290 | 418.12 | 1262 | NEW | 86 | Delayed | 77 | 17/10/2022 | 31/10/2025 | 13/11/2025 | 31/07/2023 | 321.37 | 323.15
226 | Rejuvination of Takoamari water supply scheme (SM/09294) | SM/09294 | 104.14 | 1188 | AUGMENTATION | 86 | Delayed | 42 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 10/03/2022 | 43.46 | 43.46
227 | BARARANGRAS PIPED WATER SUPPLY SCHEME (SM/14135) | SM/14135 | 2246.26 | 5746 | NEW | 86 | Delayed | 82 | 02/01/2023 | 31/05/2025 | 13/11/2025 | 02/03/2023 | 1835.58 | 1839.13
228 | Garbhadanga Piped Water Supply Scheme. (SM/18749) | SM/18749 | 849.76 | 0 | NEW | 86 | Delayed | 42 | 18/08/2023 | 31/05/2025 | 13/11/2025 | 22/08/2023 | 355.1 | 356.87
229 | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME (SM/13160) | SM/13160 | 535.85 | 2258 | AUGMENTATION | 86 | Delayed | 59 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 10/01/2022 | 315.07 | 315.07
230 | AUGMENTATION OF GROUND WATER BASED NAKKATIGACHHI PIPED WATER SUPPLY SCHEME TUFANGANJ - I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. (SM/16151) | SM/16151 | 415 | 1298 | AUGMENTATION | 86 | Delayed | 48 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 14/07/2023 | 200.05 | 194.35
231 | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block (SM/13381) | SM/13381 | 704.23 | 2774 | AUGMENTATION | 86 | Delayed | 49 | 19/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 344.83 | 344.83
232 | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) (SM/13159) | SM/13159 | 622.83 | 2650 | AUGMENTATION | 86 | Delayed | 67 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 24/01/2023 | 414.85 | 414.85
233 | AUGMENTATION OF GROUND WATER BASED CHIKLIGURI PIPED WATER SUPPLY SCHEME TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. (SM/14935) | SM/14935 | 157.45 | 168 | AUGMENTATION | 87 | Delayed | 36 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 29/12/2022 | 56.59 | 56.59
234 | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. (SM/13214) | SM/13214 | 985.9 | 2849 | NEW | 87 | Delayed | 85 | 12/10/2022 | 08/05/2025 | 13/11/2025 | 19/01/2023 | 834 | 841.02
235 | JHURIPARA PIPED WATER SUPPLY SCHEME (SM/14439) | SM/14439 | 688.69 | 1581 | NEW | 87 | Delayed | 59 | 20/01/2023 | 31/12/2025 | 13/11/2025 | 24/07/2023 | 404.77 | 404.77
236 | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme (SM/10161) | SM/10161 | 524.8 | 1467 | AUGMENTATION | 87 | Delayed | 69 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 27/01/2022 | 359.82 | 358.38
237 | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME (SM/09303) | SM/09303 | 655.03 | 1920 | AUGMENTATION | 87 | Delayed | 86 | 09/11/2021 | 01/06/2025 | 13/11/2025 | 10/08/2021 | 566.29 | 566.23
238 | Augmentation of PURBA FULKARDABRI Piped water supply schemes. (SM/10162) | SM/10162 | 485.38 | 0 | AUGMENTATION | 87 | Delayed | 83 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 04/03/2022 | 403.5 | 403.5
239 | Augmentation of RAMPUR Piped Water Supply Scheme (SM/11272) | SM/11272 | 1696.48 | 6826 | AUGMENTATION | 87 | Delayed | 72 | 24/06/2022 | 31/12/2025 | 13/11/2025 | 30/09/2021 | 1218.45 | 1218.45
240 | BHORAM PIPED WATER SUPPLY SCHEME (SM/18720) | SM/18720 | 1206.98 | 3776 | NEW | 87 | Delayed | 73 | 10/08/2023 | 31/10/2025 | 13/11/2025 | 10/08/2023 | 880.22 | 881.35
241 | Rejuvenation of BHANDIJALAS Water Supply Scheme (SM/10365) | SM/10365 | 60.23 | 109 | AUGMENTATION | 87 | Delayed | 86 | 16/03/2022 | 31/12/2025 | 13/11/2025 | 29/03/2022 | 51.51 | 51.51
242 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme (SM/08154) | SM/08154 | 99.54 | 1104 | RETROFITTING | 88 | Delayed | 96 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 95.57 | 95.57
243 | Rejuvenation of CHUNGERKHATA KHAGRIBARI Water Supply Scheme (SM/10711) | SM/10711 | 99.98 | 215 | AUGMENTATION | 88 | On track | 63 | 12/05/2022 | 31/12/2025 | 13/11/2025 | 10/03/2022 | 62.79 | 62.79
244 | KOCHABARI PIPED WATER SUPPLY SCHEME. (SM/13342) | SM/13342 | 596.28 | 1630 | NEW | 88 | Delayed | 77 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 19/01/2023 | 459.47 | 461.25
245 | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME (SM/16525) | SM/16525 | 540.91 | 2533 | AUGMENTATION | 88 | On track | 87 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 26/07/2022 | 471.44 | 420.05
246 | Augmentation of Dumniguru Piped Water Supply Scheme. (SM/10008) | SM/10008 | 780.83 | 2519 | NEW | 88 | Delayed | 71 | 22/12/2021 | 31/05/2025 | 13/11/2025 | 10/03/2022 | 556.45 | 562.33
247 | Rejuvination of Chhatoa water supply scheme (SM/09819) | SM/09819 | 140.37 | 1724 | AUGMENTATION | 88 | On track | 87 | 01/12/2021 | 31/12/2025 | 13/11/2025 | 27/12/2021 | 122.42 | 122.42
248 | TATERKUTHI PIPED WATER SUPPLY SCHEME. (SM/13158) | SM/13158 | 296.28 | 675 | NEW | 88 | On track | 56 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 17/03/2023 | 165.58 | 167.36
249 | DAKSHIN SAMILABAS PWSS (SM/18183) | SM/18183 | 191.14 | 179 | NEW | 88 | Delayed | 64 | 31/03/2023 | 31/05/2025 | 13/11/2025 | 08/08/2023 | 122.25 | 122.25
250 | Augmentation of Gosanimari piped water supply scheme. (SM/10150) | SM/10150 | 1764.97 | 8450 | AUGMENTATION | 88 | Delayed | 94 | 10/02/2022 | 31/05/2025 | 13/11/2025 | 24/03/2022 | 1654.66 | 1654.66
251 | Rejuvenation of NAGARERBARI Piped Water Supply Scheme (SM/10219) | SM/10219 | 510.22 | 7552 | AUGMENTATION | 88 | Delayed | 52 | 24/02/2022 | 31/05/2025 | 13/11/2025 | 10/03/2022 | 265.89 | 272.31
252 | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE (SM/16517) | SM/16517 | 321.78 | 553 | AUGMENTATION | 88 | On track | 67 | 03/03/2023 | 31/12/2025 | 13/11/2025 | 28/03/2023 | 215.18 | 215.18
253 | AUGMENTATION OF GROUND WATER BASED ALOKJHARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION (SM/14932) | SM/14932 | 344.1 | 2627 | AUGMENTATION | 88 | On track | 51 | 03/02/2023 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 176.8 | 176.8
254 | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. (SM/10221) | SM/10221 | 770.33 | 0 | AUGMENTATION | 89 | Delayed | 89 | 24/02/2022 | 31/05/2025 | 13/11/2025 | 24/05/2022 | 686.88 | 685.19
255 | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME (SM/11983) | SM/11983 | 1121.34 | 3031 | AUGMENTATION | 89 | On track | 88 | 01/09/2022 | 31/12/2025 | 13/11/2025 | 13/08/2021 | 990.06 | 990.06
256 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme (SM/08148) | SM/08148 | 99.39 | 977 | RETROFITTING | 90 | Delayed | 78 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 06/07/2021 | 77.32 | 77.31
257 | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE (SM/18093) | SM/18093 | 329.99 | 788 | AUGMENTATION | 90 | Delayed | 74 | 27/03/2023 | 31/05/2025 | 13/11/2025 | 31/03/2023 | 244.43 | 244.43
258 | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. (SM/18251) | SM/18251 | 1163.9 | 3747 | NEW | 90 | Delayed | 60 | 16/06/2023 | 31/05/2025 | 13/11/2025 | 12/07/2023 | 701.43 | 701.31
259 | DUAI SUAI PIPED WATER SUPPLY SCHEME. (SM/15911) | SM/15911 | 999.87 | 3036 | NEW | 90 | On track | 61 | 22/02/2023 | 31/12/2025 | 13/11/2025 | 24/03/2023 | 610.4 | 612.14
260 | Augmentation of Bajejama Chilakhana ZONE-I PWSS (SM/16931) | SM/16931 | 392.61 | 1186 | AUGMENTATION | 90 | Delayed | 33 | 16/03/2023 | 31/05/2025 | 13/11/2025 | 27/07/2023 | 130.65 | 130.65
261 | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07148) | SM/07148 | 99.38 | 1596 | RETROFITTING | 90 | On track | 89 | 01/12/2020 | 31/12/2025 | 13/11/2025 | 08/01/2021 | 88.51 | 88.51
262 | RUIER KHUTHI PIPED WATER SUPPLY SCHEME (SM/13317) | SM/13317 | 745.04 | 1974 | NEW | 90 | On track | 72 | 17/10/2022 | 31/12/2025 | 13/11/2025 | 24/01/2023 | 532.8 | 536.31
263 | Augmentation of Rasikbil piped water supply scheme. (SM/09300) | SM/09300 | 883.58 | 3191 | AUGMENTATION | 90 | Delayed | 91 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 24/12/2021 | 807.16 | 807.16
264 | Maidam Piped Water Supply Scheme (SM/16981) | SM/16981 | 300.7 | 234 | NEW | 90 | On track | 74 | 16/03/2023 | 31/12/2025 | 13/11/2025 | 17/04/2023 | 221.22 | 221.22
265 | ABUAR PATHAR PWSS (SM/14202) | SM/14202 | 909.64 | 2428 | NEW | 90 | On track | 59 | 10/01/2023 | 31/12/2025 | 13/11/2025 | 23/05/2023 | 538.29 | 538.29
266 | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME (SM/09299) | SM/09299 | 423.73 | 908 | AUGMENTATION | 90 | Delayed | 89 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 31/12/2021 | 376.46 | 376.46
267 | DINHATA(P) PIPED WATER SUPPLY SCHEME. (SM/13401) | SM/13401 | 530.66 | 1994 | NEW | 90 | Delayed | 86 | 10/10/2022 | 31/05/2025 | 13/11/2025 | 20/06/2022 | 455.4 | 455.4
268 | PHALIMARI PIPED WATER SUPPLY SCHEME. (SM/18371) | SM/18371 | 1287.78 | 3108 | NEW | 90 | Delayed | 53 | 11/07/2023 | 31/05/2025 | 13/11/2025 | 25/07/2023 | 682.74 | 682.74
269 | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme (SM/10141) | SM/10141 | 619.92 | 3342 | AUGMENTATION | 92 | Delayed | 56 | 09/02/2022 | 31/05/2025 | 13/11/2025 | 26/07/2021 | 348.53 | 348.49
270 | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME (SM/10050) | SM/10050 | 2035.06 | 8205 | AUGMENTATION | 92 | Delayed | 70 | 24/01/2022 | 31/05/2025 | 13/11/2025 | 30/09/2021 | 1421.86 | 1421.69
271 | Augmentation of Singimari Bhetaguri piped water supply scheme. (SM/10149) | SM/10149 | 1373.45 | 5509 | AUGMENTATION | 92 | Delayed | 85 | 10/02/2022 | 31/05/2025 | 13/11/2025 | 10/08/2021 | 1161.37 | 1161.37
272 | Rejuvenation of MARICHBARI Water Supply Scheme (SM/10369) | SM/10369 | 96.65 | 885 | AUGMENTATION | 92 | Delayed | 78 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 29/03/2022 | 75.46 | 75.46
273 | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme (SM/10231) | SM/10231 | 591.57 | 4465 | AUGMENTATION | 92 | Delayed | 62 | 24/02/2022 | 31/05/2025 | 13/11/2025 | 10/03/2022 | 367.33 | 367.33
274 | Rejuvenation of KALAPANI Water Supply Scheme (SM/10359) | SM/10359 | 57.32 | 180 | AUGMENTATION | 92 | Delayed | 86 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 49.33 | 49.33
275 | BHUTKURA PIPED WATER SUPPLY SCHEME (SM/14730) | SM/14730 | 757.77 | 2370 | NEW | 92 | On track | 72 | 31/01/2023 | 31/12/2025 | 13/11/2025 | 08/02/2023 | 543.27 | 543.27
276 | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME (SM/10049) | SM/10049 | 1206.57 | 0 | AUGMENTATION | 92 | On track | 87 | 24/01/2022 | 31/12/2025 | 13/11/2025 | 30/09/2021 | 1053.48 | 1053.48
277 | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME (SM/10152) | SM/10152 | 1885.38 | 0 | AUGMENTATION | 92 | Delayed | 95 | 10/02/2022 | 31/05/2025 | 13/11/2025 | 24/06/2020 | 1790.36 | 1790.36
278 | Rejuvenation of PANISALA Water Supply Scheme (SM/10368) | SM/10368 | 104.08 | 1187 | AUGMENTATION | 92 | Delayed | 93 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 96.78 | 96.78
279 | DEBGRAM PIPED WATER SUPPLY SCHEME (SM/13880) | SM/13880 | 528.58 | 1246 | NEW | 92 | On track | 89 | 25/11/2022 | 31/12/2025 | 13/11/2025 | 13/02/2023 | 470.27 | 470.27
280 | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. (SM/13462) | SM/13462 | 523.53 | 1343 | NEW | 92 | On track | 88 | 02/11/2022 | 31/12/2025 | 13/11/2025 | 13/02/2023 | 461.29 | 461.29
281 | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME (SM/09298) | SM/09298 | 375.12 | 0 | AUGMENTATION | 93 | On track | 78 | 09/11/2021 | 31/03/2026 | 13/11/2025 | 27/08/2021 | 291.76 | 291.76
282 | Augmentation of Sitai piped water supply scheme. (SM/10147) | SM/10147 | 1734.93 | 7771 | AUGMENTATION | 93 | Delayed | 73 | 10/02/2022 | 31/05/2025 | 13/11/2025 | 15/03/2022 | 1268.46 | 1268.46
283 | AUGMENTATION OF Chhota Godaikhora Pwss (SM/17443) | SM/17443 | 195.52 | 1547 | AUGMENTATION | 93 | Delayed | 55 | 18/03/2023 | 31/05/2025 | 13/11/2025 | 13/08/2021 | 107.43 | 107.43
284 | DAKHSHIN DIGHALTARI PWSS (SM/13388) | SM/13388 | 479.26 | 1577 | NEW | 93 | On track | 92 | 19/10/2022 | 31/12/2025 | 13/11/2025 | 14/03/2023 | 440.43 | 442.21
285 | GORBHANGA PIPED WATER SUPPLY SCHEME. (SM/13210) | SM/13210 | 321.62 | 366 | NEW | 93 | Delayed | 65 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 17/03/2023 | 208.87 | 208.87
286 | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME (SM/09809) | SM/09809 | 192.5 | 2489 | AUGMENTATION | 94 | On track | 93 | 01/12/2021 | 31/12/2025 | 13/11/2025 | 09/02/2022 | 179.47 | 182.06
287 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem (SM/08145) | SM/08145 | 98.31 | 1194 | RETROFITTING | 94 | Delayed | 96 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 29/12/2021 | 94.21 | 94.21
288 | Augmentation of NIJTARAF Piped water supply schemes (SM/10163) | SM/10163 | 420.74 | 51 | AUGMENTATION | 94 | Delayed | 97 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 04/03/2022 | 406.3 | 404.79
289 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme (SM/08161) | SM/08161 | 99.78 | 1285 | RETROFITTING | 95 | Delayed | 95 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 94.59 | 94.59
290 | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. (SM/13461) | SM/13461 | 738.83 | 2566 | NEW | 95 | On track | 74 | 02/11/2022 | 31/12/2025 | 13/11/2025 | 19/01/2023 | 544.08 | 545.86
291 | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme (SM/07161) | SM/07161 | 99.21 | 1466 | RETROFITTING | 95 | Delayed | 97 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 29/03/2022 | 96.32 | 91.89
292 | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme (SM/07162) | SM/07162 | 97.26 | 1193 | RETROFITTING | 95 | Delayed | 97 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 07/10/2021 | 94.43 | 94.43
293 | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme (SM/10006) | SM/10006 | 1719.81 | 8517 | RETROFITTING | 95 | Delayed | 84 | 22/12/2021 | 31/05/2025 | 13/11/2025 | 24/12/2021 | 1453.07 | 1453.07
294 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme (SM/08153) | SM/08153 | 82.63 | 1212 | RETROFITTING | 95 | Delayed | 97 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 06/08/2021 | 80.22 | 78.41
295 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme (SM/08156) | SM/08156 | 97.67 | 1000 | RETROFITTING | 95 | Delayed | 98 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 07/07/2022 | 96.19 | 94.37
296 | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. (SM/10157) | SM/10157 | 366.11 | 1775 | AUGMENTATION | 95 | On track | 96 | 11/02/2022 | 31/12/2025 | 13/11/2025 | 06/07/2021 | 352.68 | 352.68
297 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme (SM/08160) | SM/08160 | 99.93 | 1150 | RETROFITTING | 95 | Delayed | 97 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 13/08/2021 | 97.02 | 97.02
298 | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme (SM/07158) | SM/07158 | 95.27 | 803 | RETROFITTING | 95 | Delayed | 97 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 29/09/2022 | 92.49 | 92.49
299 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme (SM/08155) | SM/08155 | 87.78 | 1081 | RETROFITTING | 95 | Delayed | 97 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 24/06/2020 | 84.89 | 84.89
300 | Rejuvenation of JAMALDAH HAT Water Supply Scheme (SM/10709) | SM/10709 | 168.66 | 173 | AUGMENTATION | 95 | On track | 95 | 12/05/2022 | 31/12/2025 | 13/11/2025 | 24/05/2022 | 159.94 | 159.94
301 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme (SM/08164) | SM/08164 | 86.77 | 1104 | RETROFITTING | 95 | Delayed | 97 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 06/07/2021 | 84.24 | 84.24
302 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme (SM/08165) | SM/08165 | 93.89 | 1625 | RETROFITTING | 95 | Delayed | 77 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 72.17 | 72.17
303 | Rejuvination of Sathbhandari water supply scheme (SM/09821) | SM/09821 | 162.76 | 1719 | AUGMENTATION | 95 | On track | 66 | 01/12/2021 | 31/12/2025 | 13/11/2025 | 17/08/2020 | 107.91 | 107.91
304 | Rejuvenation of RAMTHANGA Water Supply Scheme (SM/10710) | SM/10710 | 169.95 | 336 | AUGMENTATION | 95 | Delayed | 95 | 12/05/2022 | 31/05/2025 | 13/11/2025 | 23/02/2018 | 161.03 | 161.03
305 | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07163) | SM/07163 | 96.35 | 1382 | RETROFITTING | 95 | Delayed | 94 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 90.27 | 82.45
306 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme (SM/08158) | SM/08158 | 58.94 | 544 | RETROFITTING | 95 | Delayed | 97 | 09/02/2021 | 31/05/2025 | 13/11/2025 |  | 57.22 | 57.22
307 | Rejuvination of Salbari Water Supply Scheme (SM/09818) | SM/09818 | 185.28 | 2470 | AUGMENTATION | 95 | Delayed | 86 | 01/12/2021 | 31/05/2025 | 13/11/2025 | 15/02/2022 | 159.91 | 159.91
308 | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. (SM/10164) | SM/10164 | 439.11 | 2432 | AUGMENTATION | 95 | Delayed | 93 | 11/02/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 407.95 | 407.95
309 | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME (SM/11486) | SM/11486 | 505.77 | 1374 | AUGMENTATION | 96 | On track | 85 | 14/07/2022 | 31/12/2025 | 13/11/2025 | 19/01/2023 | 432.15 | 432.15
310 | Augmentation of Bhogmara Piped Water Supply Scheme. (SM/10007) | SM/10007 | 549.15 | 1920 | NEW | 96 | On track | 87 | 22/12/2021 | 31/12/2025 | 13/11/2025 | 10/03/2022 | 478.51 | 478.51
311 | Augmentation of Chilakhana piped water supply scheme. (SM/10148) | SM/10148 | 1128.23 | 6406 | AUGMENTATION | 96 | Delayed | 80 | 10/02/2022 | 31/05/2025 | 13/11/2025 | 15/02/2022 | 904.75 | 904.75
312 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme (SM/08159) | SM/08159 | 97.85 | 959 | RETROFITTING | 96 | Delayed | 97 | 09/02/2021 | 31/05/2025 | 13/11/2025 | 09/02/2022 | 95 | 95
313 | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07167) | SM/07167 | 96.01 | 1231 | RETROFITTING | 97 | Delayed | 100 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 29/03/2022 | 96 | 96
314 | Augmentation of BARA KAIMARI Piped Water Supply Scheme (SM/10142) | SM/10142 | 564.24 | 1671 | AUGMENTATION | 97 | Delayed | 97 | 09/02/2022 | 31/05/2025 | 13/11/2025 | 09/08/2021 | 546.93 | 546.93
315 | Augmentation of JHAUKUTHI Piped Water Supply Scheme (SM/10220) | SM/10220 | 327.91 | 962 | AUGMENTATION | 97 | Delayed | 85 | 24/02/2022 | 31/05/2025 | 13/11/2025 | 17/03/2022 | 278.61 | 278.46
316 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme (SM/08152) | SM/08152 | 98.54 | 1591 | RETROFITTING | 97 | Delayed | 92 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 04/01/2022 | 90.33 | 88.51
317 | Rejuvenation of Salmara water supply scheme (SM/09820) | SM/09820 | 520.16 | 3389 | AUGMENTATION | 97 | Delayed | 97 | 01/12/2021 | 31/05/2025 | 13/11/2025 | 27/12/2021 | 506.77 | 506.77
318 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme (SM/08149) | SM/08149 | 77.36 | 666 | RETROFITTING | 98 | On track | 97 | 08/02/2021 | 31/12/2025 | 13/11/2025 | 13/08/2021 | 75.11 | 75.11
319 | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. (SM/13151) | SM/13151 | 473.94 | 1597 | AUGMENTATION | 98 | On track | 72 | 12/10/2022 | 31/12/2025 | 13/11/2025 | 10/01/2022 | 339.55 | 339.55
320 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme (SM/08157) | SM/08157 | 97.91 | 1250 | RETROFITTING | 98 | On track | 94 | 09/02/2021 | 31/12/2025 | 13/11/2025 | 06/07/2021 | 92.2 | 92.2
321 | Augumentation of Petla Water Supply Scheme. (SM/09295) | SM/09295 | 361.71 | 1365 | AUGMENTATION | 98 | Delayed | 91 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 16/10/2020 | 329.19 | 329.19
322 | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme (SM/10367) | SM/10367 | 70.79 | 490 | AUGMENTATION | 98 | Delayed | 88 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 07/04/2022 | 62.2 | 62.2
323 | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. (SM/09832) | SM/09832 | 847.71 | 5193 | RETROFITTING | 98 | On track | 99 | 02/12/2021 | 31/12/2025 | 13/11/2025 | 24/12/2021 | 837.44 | 837.44
324 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme (SM/08163) | SM/08163 | 206.7 | 2600 | RETROFITTING | 98 | On track | 97 | 09/02/2021 | 31/12/2025 | 13/11/2025 | 04/01/2022 | 200.68 | 200.68
325 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kharimala Khagrabari(CT) Water Supply Scheme (SM/08146) | SM/08146 | 91.07 | 1596 | RETROFITTING | 98 | On track | 81 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 13/05/2022 | 73.94 | 72.95
326 | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME (SM/09292) | SM/09292 | 148.97 | 1815 | AUGMENTATION | 98 | On track | 85 | 09/11/2021 | 31/12/2025 | 13/11/2025 | 24/12/2021 | 126.86 | 126.86
327 | Augmentation of dhaluabari water supply scheme (SM/09822) | SM/09822 | 636.85 | 2018 | AUGMENTATION | 98 | Delayed | 84 | 01/12/2021 | 31/05/2025 | 13/11/2025 | 27/12/2021 | 534.75 | 534.75
328 | AUGMENTATION OF BARA KODALI ZONE-II PWSS (SM/13182) | SM/13182 | 487.92 | 1846 | AUGMENTATION | 99 | Delayed | 58 | 12/10/2022 | 31/05/2025 | 13/11/2025 | 16/08/2022 | 283.86 | 283.86
329 | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME (SM/09302) | SM/09302 | 598.93 | 1813 | AUGMENTATION | 99 | Delayed | 85 | 09/11/2021 | 31/05/2025 | 13/11/2025 | 10/08/2021 | 507.24 | 507.24
330 | Rejuvenation of CHHAGALBER Water Supply Scheme (SM/10366) | SM/10366 | 110.72 | 1316 | AUGMENTATION | 99 | Delayed | 93 | 16/03/2022 | 31/05/2025 | 13/11/2025 | 29/08/2022 | 103.16 | 103.12
331 | Augmentation of Kauardara Water Supply Scheme (SM/09808) | SM/09808 | 417.23 | 2926 | AUGMENTATION | 99 | On track | 98 | 01/12/2021 | 31/12/2025 | 13/11/2025 | 27/02/2020 | 410.37 | 410.37
332 | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme (SM/07157) | SM/07157 | 98.83 | 1360 | RETROFITTING | 100 | 100% Physical | 92 | 01/12/2020 | 31/12/2025 | 13/11/2025 | 31/12/2021 | 90.44 | 90.44
333 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme (SM/09831) | SM/09831 | 743.04 | 4449 | RETROFITTING | 100 | 100% Physical | 97 | 02/12/2021 | 31/05/2025 | 13/11/2025 | 31/12/2021 | 723.05 | 723.03
334 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najiran Deutikhata Water Supply Scheme (SM/08147) | SM/08147 | 90.78 | 1307 | RETROFITTING | 100 | 100% Physical | 100 | 08/02/2021 | 31/12/2025 | 13/11/2025 | 09/02/2022 | 90.78 | 90.78
335 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bara Soulmari Water Supply Scheme (SM/08144) | SM/08144 | 99.27 | 2398 | RETROFITTING | 100 | 100% Physical | 98 | 08/02/2021 | 31/12/2025 | 13/11/2025 | 29/12/2021 | 96.88 | 96.86
336 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme (SM/08162) | SM/08162 | 95.45 | 1234 | RETROFITTING | 100 | 100% Physical | 100 | 09/02/2021 | 31/12/2025 | 13/11/2025 | 06/08/2021 | 95.41 | 93.17
337 | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme (SM/07159) | SM/07159 | 97.31 | 1389 | RETROFITTING | 100 | 100% Physical | 100 | 01/12/2020 | 31/12/2025 | 13/11/2025 |  | 97.31 | 97.31
338 | Retrofitting of existing Basraja Pratham Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07147) | SM/07147 | 97.91 | 1548 | RETROFITTING | 100 | 100% Physical | 100 | 01/12/2020 | 31/05/2025 | 13/11/2025 |  | 97.91 | 97.91
339 | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07165) | SM/07165 | 98.97 | 1412 | RETROFITTING | 100 | 100% Physical | 96 | 01/12/2020 | 31/12/2025 | 13/11/2025 | 08/01/2021 | 95.4 | 95.4
340 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme (SM/08150) | SM/08150 | 99.72 | 1319 | RETROFITTING | 100 | 100% Physical | 94 | 08/02/2021 | 31/12/2025 | 13/11/2025 | 04/01/2022 | 93.39 | 93.39
341 | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme (SM/07156) | SM/07156 | 87.4 | 1087 | RETROFITTING | 100 | 100% Physical | 97 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 27/08/2022 | 84.79 | 84.79
342 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme (SM/08143) | SM/08143 | 99.02 | 2187 | RETROFITTING | 100 | 100% Physical | 100 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 13/05/2022 | 99.02 | 99.02
343 | Rejuvenation of PAKHIHAGA Water Supply Scheme (SM/10707) | SM/10707 | 128.32 | 880 | AUGMENTATION | 100 | 100% Physical | 69 | 12/05/2022 | 31/12/2025 | 13/11/2025 | 06/07/2021 | 87.9 | 87.9
344 | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07164) | SM/07164 | 79.55 | 618 | RETROFITTING | 100 | 100% Physical | 93 | 01/12/2020 | 31/05/2025 | 13/11/2025 | 07/10/2021 | 74.11 | 74.11
345 | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme (SM/07160) | SM/07160 | 95.99 | 1290 | RETROFITTING | 100 | 100% Physical | 98 | 01/12/2020 | 04/06/2025 | 13/11/2025 | 29/12/2021 | 93.96 | 93.96
346 | Retrofitting of existing Bhurkush Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme (SM/07166) | SM/07166 | 94.92 | 1231 | RETROFITTING | 100 | 100% Physical | 100 | 01/12/2020 | 31/12/2025 | 13/11/2025 | 17/03/2022 | 94.92 | 94.92
347 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme (SM/08151) | SM/08151 | 97.72 | 2202 | RETROFITTING | 100 | 100% Physical | 97 | 08/02/2021 | 31/05/2025 | 13/11/2025 | 04/01/2022 | 94.87 | 94.87
Total |  |  | 195712.32 | 669703 | [8 empty] | 117987.63 | 117569.09