## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division (SM/18123) | SM/18123 | 231.67 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 29/03/2023 | 29/09/2023 | 12/06/2023 | 07/07/2023 | 0 | 0
2 | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs (SM/06641) | SM/06641 | 24.56 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 10/09/2021 | 0 | 0
3 | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. (SM/10390) | SM/10390 | 11.88 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 24/03/2022 |  | 24/03/2022 | 28/05/2022 | 0 | 0
4 | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. (SM/11804) | SM/11804 | 102.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/08/2022 |  | 08/08/2022 | 10/09/2021 | 0 | 0
5 | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTER & PERIPHERALS FOR OFFICIAL USE UNRED RAIGANJ DIVISION, P.H.E. DTE. (SM/19115) | SM/19115 | 9.51 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 22/12/2023 |  | 22/12/2023 |  | 0 | 0
6 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Uttar Dinajpur District. (SM/08980) | SM/08980 | 208.78 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 17/08/2022 | 0 | 0
7 | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. (SM/08982) | SM/08982 | 14.04 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 |  | 0 | 0
8 | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. (SM/10615) | SM/10615 | 2.08 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 20/04/2022 |  | 21/04/2022 | 15/07/2022 | 0 | 0
9 | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. (SM/19074) | SM/19074 | 79.08 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
10 | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. (SM/10636) | SM/10636 | 14.25 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 21/04/2022 |  | 22/04/2022 | 31/01/2022 | 0 | 0
11 | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div (SM/11803) | SM/11803 | 29.14 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/08/2022 |  | 08/08/2022 | 14/01/2022 | 0 | 0
12 | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen (SM/11226) | SM/11226 | 20.94 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 16/06/2022 |  | 16/06/2022 | 26/08/2021 | 0 | 0
13 | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). (SM/06640) | SM/06640 | 22.11 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 13/12/2021 | 0 | 0
14 | Survey and Water Sample Collection from School and Anganwadis at various block in the district, Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/11619) | SM/11619 | 8.64 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/07/2022 |  | 28/07/2022 | 22/08/2022 | 0 | 0
15 | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. (SM/19073) | SM/19073 | 58.73 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
16 | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La (SM/19075) | SM/19075 | 50.75 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 04/04/2024 | 0 | 0
17 | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11520) | SM/11520 | 977.22 | 1632 | NEW | 1 | Delayed | 0 | 19/07/2022 | 31/03/2024 | 09/01/2024 | 08/05/2023 | 0 | 0
18 | Laying of additional pipe line for retrofitting of Barobilla for installation of FHTC. (SM/09135) | SM/09135 | 2.23 | 0 | RETROFITTING | 1 | Delayed | 0 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 0 | 0
19 | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. (SM/11517) | SM/11517 | 975.54 | 1442 | NEW | 1 | Delayed | 1 | 19/07/2022 | 31/03/2024 | 09/01/2024 | 08/05/2023 | 9.51 | 9.51
20 | Laying of additional pipe line for retrofitting of Sherpur for installation of FHTC. (SM/09167) | SM/09167 | 4.7 | 0 | RETROFITTING | 1 | Delayed | 0 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 0 | 0
21 | KATAGAON Piped Water Supply Scheme at Chopra Block (SM/12082) | SM/12082 | 381.86 | 1113 | NEW | 1 | Delayed | 6 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/07/2023 | 24.5 | 24.5
22 | FASHIA DIATION PIPED WATER SUPPLY SCHEME (SM/14129) | SM/14129 | 607.1 | 2201 | NEW | 1 | Delayed | 2 | 02/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 14.25 | 14.25
23 | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11521) | SM/11521 | 565.81 | 1057 | NEW | 1 | Delayed | 3 | 19/07/2022 | 31/03/2024 | 09/01/2024 | 08/05/2023 | 14.16 | 14.16
24 | BARA DOPAHARU Piped Water Supply Scheme (SM/12396) | SM/12396 | 460.65 | 1310 | NEW | 1 | Delayed | 6 | 13/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 25.83 | 25.83
25 | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11516) | SM/11516 | 969.86 | 1622 | NEW | 1 | Delayed | 0 | 19/07/2022 | 31/03/2024 | 09/01/2024 | 19/05/2023 | 0 | 0
26 | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11519) | SM/11519 | 976.8 | 1627 | NEW | 1 | Delayed | 4 | 19/07/2022 | 31/03/2024 | 09/01/2024 | 08/05/2023 | 38.04 | 38.04
27 | Restoration of Pipe line for providing FHTC for Mahinagar Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10498) | SM/10498 | 9.85 | 0 | RETROFITTING | 1 | Delayed | 62 | 13/04/2022 | 31/03/2024 | 05/12/2023 | 17/02/2023 | 6.08 | 6.08
28 | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12784) | SM/12784 | 594.32 | 1478 | NEW | 1 | Delayed | 2 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 11.1 | 11.1
29 | SARJAPUR Piped Water Supply Scheme (SM/15127) | SM/15127 | 931.52 | 2809 | NEW | 1 | Delayed | 2 | 04/02/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 17.3 | 17.3
30 | Laying of additional pipe line for retrofitting of Choprabari WSS for installation of FHTC. (SM/09134) | SM/09134 | 1.42 | 0 | RETROFITTING | 1 | Delayed | 97 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 1.38 | 1.38
31 | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. (SM/16471) | SM/16471 | 393.91 | 1004 | NEW | 2 | Delayed | 2 | 02/03/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 6.18 | 6.18
32 | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18148) | SM/18148 | 377.79 | 1035 | NEW | 2 | Delayed | 4 | 29/03/2023 | 16/04/2024 | 04/10/2023 | 16/08/2023 | 13.34 | 6.38
33 | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16647) | SM/16647 | 651.61 | 2196 | NEW | 2 | Delayed | 4 | 14/03/2023 | 31/12/2024 | 12/04/2024 | 10/08/2023 | 24.35 | 24.35
34 | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block (SM/12085) | SM/12085 | 762.95 | 2173 | NEW | 2 | Delayed | 2 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/07/2023 | 13.39 | 13.39
35 | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. (SM/18149) | SM/18149 | 178.3 | 484 | NEW | 2 | Delayed | 2 | 29/03/2023 | 31/12/2024 | 12/04/2024 | 29/05/2023 | 2.68 | 2.68
36 | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18155) | SM/18155 | 65.75 | 116 | NEW | 2 | Delayed | 1 | 29/03/2023 | 31/12/2024 | 09/04/2024 | 29/05/2023 | 0.71 | 0.71
37 | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12650) | SM/12650 | 52.98 | 150 | AUGMENTATION | 2 | Delayed | 19 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 9.98 | 9.98
38 | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18165) | SM/18165 | 93.53 | 227 | NEW | 2 | Delayed | 1 | 29/03/2023 | 31/12/2024 | 12/04/2024 | 14/08/2023 | 1.4 | 1.4
39 | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18147) | SM/18147 | 100.04 | 250 | NEW | 2 | Delayed | 3 | 29/03/2023 | 31/12/2024 | 09/04/2024 | 29/05/2023 | 2.7 | 1.68
40 | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18159) | SM/18159 | 276.37 | 905 | NEW | 2 | Delayed | 2 | 29/03/2023 | 31/12/2024 | 12/04/2024 | 08/05/2023 | 5.52 | 5.52
41 | CHOUKAI Pipe Water Supply Scheme (SM/15304) | SM/15304 | 766.71 | 2030 | NEW | 2 | Delayed | 4 | 09/02/2023 | 31/12/2024 | 12/04/2024 | 11/09/2023 | 32.57 | 12.5
42 | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. (SM/16227) | SM/16227 | 724.68 | 3775 | NEW | 2 | Delayed | 7 | 24/02/2023 | 31/12/2024 | 12/04/2024 | 08/05/2023 | 54.19 | 54.19
43 | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. (SM/18828) | SM/18828 | 214.61 | 0 | AUGMENTATION | 2 | Delayed | 0 | 12/09/2023 | 31/03/2024 | 09/01/2024 | 20/09/2023 | 0 | 0
44 | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14232) | SM/14232 | 49.54 | 50 | AUGMENTATION | 3 | Delayed | 22 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 10.85 | 10.85
45 | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block (SM/12089) | SM/12089 | 400.31 | 884 | NEW | 3 | Delayed | 9 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/07/2023 | 37.82 | 37.82
46 | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14231) | SM/14231 | 49.75 | 50 | AUGMENTATION | 3 | Delayed | 1 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 0.31 | 0.31
47 | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12647) | SM/12647 | 56.37 | 100 | AUGMENTATION | 4 | Delayed | 16 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 9.18 | 9.18
48 | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12794) | SM/12794 | 560.31 | 1750 | NEW | 4 | Delayed | 9 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 01/09/2023 | 48.88 | 29.76
49 | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12795) | SM/12795 | 423.08 | 1036 | NEW | 4 | Delayed | 16 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 68 | 64.63
50 | BASATPUT Piped Water Supply Scheme (SM/15129) | SM/15129 | 933.62 | 3305 | NEW | 4 | Delayed | 13 | 04/02/2023 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 125.6 | 20.36
51 | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12781) | SM/12781 | 417.17 | 1208 | NEW | 4 | Delayed | 7 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 27.2 | 27.2
52 | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12796) | SM/12796 | 303.76 | 665 | NEW | 4 | Delayed | 11 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 34.85 | 16.49
53 | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11518) | SM/11518 | 978.29 | 1649 | NEW | 4 | Delayed | 0 | 19/07/2022 | 31/03/2024 | 05/12/2023 | 08/05/2023 | 0 | 0
54 | KADERGANJ Pipe Water Supply Scheme (SM/15307) | SM/15307 | 708.54 | 2492 | NEW | 5 | Delayed | 3 | 09/02/2023 | 31/12/2024 | 12/04/2024 | 24/07/2023 | 20.71 | 20.71
55 | BUDHRA PWSS (SM/19012) | SM/19012 | 586.89 | 1680 | NEW | 5 | Delayed | 2 | 27/10/2023 | 31/12/2024 | 12/04/2024 | 30/10/2023 | 14.4 | 10.35
56 | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14164) | SM/14164 | 667.17 | 2116 | NEW | 5 | Delayed | 6 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 17/03/2023 | 38.89 | 38.89
57 | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR (SM/18160) | SM/18160 | 378.98 | 1029 | NEW | 5 | Delayed | 3 | 29/03/2023 | 31/12/2024 | 09/04/2024 | 11/08/2023 | 12.28 | 6.34
58 | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14145) | SM/14145 | 1007.08 | 2612 | NEW | 5 | Delayed | 4 | 02/01/2023 | 31/12/2024 | 12/04/2024 | 22/03/2023 | 39.45 | 39.45
59 | DAKSHIN ARIAGAON Pipe Water Supply Scheme (SM/15305) | SM/15305 | 670.23 | 1900 | NEW | 5 | Delayed | 2 | 09/02/2023 | 31/12/2024 | 12/04/2024 | 10/08/2023 | 11.7 | 11.7
60 | BILASPUR Piped Water Supply Scheme (SM/16563) | SM/16563 | 642.24 | 1402 | NEW | 5 | Delayed | 5 | 10/03/2023 | 31/12/2024 | 12/04/2024 | 17/08/2023 | 29.38 | 8.64
61 | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12791) | SM/12791 | 717.37 | 2369 | NEW | 5 | Delayed | 5 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 35.13 | 35.13
62 | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12110) | SM/12110 | 814.52 | 2601 | NEW | 5 | Delayed | 2 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 19.09 | 7.82
63 | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18168) | SM/18168 | 268.43 | 838 | NEW | 5 | Delayed | 2 | 29/03/2023 | 31/12/2024 | 17/05/2024 | 12/05/2023 | 5.16 | 5.16
64 | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12654) | SM/12654 | 58.53 | 150 | AUGMENTATION | 5 | Delayed | 0 | 19/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 0 | 0
65 | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17741) | SM/17741 | 169.13 | 482 | AUGMENTATION | 6 | Delayed | 3 | 17/03/2023 | 30/09/2024 | 09/04/2024 | 27/03/2023 | 5.47 | 5.47
66 | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12638) | SM/12638 | 56.37 | 100 | AUGMENTATION | 6 | Delayed | 1 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 0.52 | 0.52
67 | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14168) | SM/14168 | 726.29 | 1516 | NEW | 6 | Delayed | 4 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 28.46 | 28.46
68 | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13738) | SM/13738 | 819.76 | 2652 | NEW | 6 | Delayed | 6 | 17/11/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 47.41 | 47.41
69 | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. (SM/18290) | SM/18290 | 1425.54 | 3395 | AUGMENTATION | 7 | Delayed | 5 | 26/06/2023 | 30/09/2024 | 09/04/2024 | 13/07/2023 | 72.52 | 72.52
70 | GUNJARIA PWSS (SM/18296) | SM/18296 | 1032.42 | 3298 | NEW | 7 | Delayed | 2 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 20.32 | 20.32
71 | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18161) | SM/18161 | 91.89 | 250 | NEW | 7 | Delayed | 3 | 29/03/2023 | 31/12/2024 | 17/05/2024 | 29/05/2023 | 2.67 | 1.54
72 | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15215) | SM/15215 | 897.34 | 2187 | NEW | 7 | Delayed | 4 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 10/08/2023 | 34.1 | 34.1
73 | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. (SM/12443) | SM/12443 | 347.81 | 964 | NEW | 8 | Delayed | 21 | 13/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 71.66 | 53.31
74 | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12652) | SM/12652 | 56.37 | 100 | AUGMENTATION | 8 | Delayed | 43 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 24.35 | 24.35
75 | DIGHALGAON PWSS (SM/18292) | SM/18292 | 1056.59 | 3406 | NEW | 8 | Delayed | 2 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 13/07/2023 | 20.98 | 20.98
76 | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block (SM/12083) | SM/12083 | 378.6 | 967 | NEW | 9 | Delayed | 14 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/07/2023 | 51.44 | 51.44
77 | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. (SM/18298) | SM/18298 | 1068.47 | 2297 | NEW | 9 | Delayed | 13 | 26/06/2023 | 31/12/2024 | 09/04/2024 | 13/07/2023 | 142.99 | 142.99
78 | Balia Piped Water Supply Scheme. (SM/18493) | SM/18493 | 713.08 | 2372 | NEW | 9 | Delayed | 2 | 24/07/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 14.61 | 14.61
79 | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18167) | SM/18167 | 133.59 | 279 | NEW | 10 | Delayed | 4 | 29/03/2023 | 31/12/2024 | 09/04/2024 | 29/05/2023 | 5.41 | 1.72
80 | Sripur Piped Water Supply Scheme (SM/17226) | SM/17226 | 126.21 | 163 | NEW | 10 | Delayed | 5 | 15/03/2023 | 31/12/2024 | 09/04/2024 | 27/03/2023 | 5.71 | 0.78
81 | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17740) | SM/17740 | 181.42 | 509 | AUGMENTATION | 10 | Delayed | 3 | 17/03/2023 | 30/09/2024 | 09/04/2024 | 27/03/2023 | 5.7 | 5.7
82 | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14225) | SM/14225 | 49.75 | 50 | AUGMENTATION | 10 | Delayed | 1 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 0.31 | 0.31
83 | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12644) | SM/12644 | 54.98 | 200 | AUGMENTATION | 10 | Delayed | 38 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 21.05 | 21.05
84 | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15214) | SM/15214 | 970.73 | 2916 | NEW | 10 | Delayed | 2 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 17.96 | 17.96
85 | BHABANIPUR PWSS (SM/18629) | SM/18629 | 1372.82 | 3893 | NEW | 10 | Delayed | 5 | 31/07/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 69.69 | 69.69
86 | JAGDISHPUR PWSS (SM/18287) | SM/18287 | 1067.42 | 3803 | NEW | 11 | Delayed | 14 | 23/06/2023 | 31/12/2024 | 12/04/2024 | 13/07/2023 | 152.64 | 152.64
87 | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14166) | SM/14166 | 906.05 | 3056 | NEW | 12 | Delayed | 16 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 141.06 | 28.83
88 | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13020) | SM/13020 | 56.37 | 100 | AUGMENTATION | 12 | Delayed | 43 | 28/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 24.37 | 24.37
89 | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. (SM/17631) | SM/17631 | 546 | 2159 | NEW | 12 | Delayed | 8 | 22/03/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 43.15 | 43.15
90 | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12649) | SM/12649 | 56.37 | 100 | AUGMENTATION | 12 | Delayed | 16 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 9.12 | 9.12
91 | DAMODARKHURI Piped Water Supply Scheme (SM/13236) | SM/13236 | 602.24 | 1871 | NEW | 12 | Delayed | 6 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 34.69 | 34.69
92 | BALARAMPUR PIPED WATER SUPPLY SCHEME (SM/13520) | SM/13520 | 432.26 | 1122 | NEW | 12 | Delayed | 6 | 04/11/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 27.07 | 27.07
93 | MIRJADPUR Piped Water Supply Scheme (SM/14627) | SM/14627 | 626.74 | 2289 | NEW | 12 | Delayed | 2 | 31/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 14.1 | 14.1
94 | JHITKAI PWSS (SM/18476) | SM/18476 | 1183.35 | 3425 | NEW | 12 | Delayed | 8 | 24/07/2023 | 31/03/2025 | 12/04/2024 | 04/08/2023 | 95.01 | 95.01
95 | DULEPUR PWSS (SM/18293) | SM/18293 | 1063.92 | 3048 | NEW | 13 | Delayed | 3 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 32.33 | 32.33
96 | BARA MIRCHA Piped Water Supply Scheme (SM/12397) | SM/12397 | 328.74 | 737 | NEW | 13 | Delayed | 18 | 13/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 60.46 | 60.46
97 | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14144) | SM/14144 | 690.18 | 2016 | NEW | 13 | Delayed | 29 | 02/01/2023 | 31/12/2024 | 12/04/2024 | 17/03/2023 | 198.88 | 168.94
98 | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18170) | SM/18170 | 168.56 | 421 | NEW | 13 | Delayed | 11 | 29/03/2023 | 31/12/2024 | 09/04/2024 | 29/05/2023 | 18.4 | 18.4
99 | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12655) | SM/12655 | 56.53 | 100 | AUGMENTATION | 14 | Delayed | 7 | 19/09/2022 | 31/12/2024 | 12/04/2024 | 28/10/2022 | 4.01 | 4.01
100 | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/14239) | SM/14239 | 1369.11 | 3947 | NEW | 15 | Delayed | 2 | 16/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 24.31 | 24.31
101 | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/16228) | SM/16228 | 1042.17 | 2889 | NEW | 15 | Delayed | 4 | 23/02/2023 | 30/09/2024 | 12/04/2024 | 26/05/2023 | 44.07 | 42.49
102 | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. (SM/16220) | SM/16220 | 571.4 | 946 | NEW | 15 | Delayed | 34 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 191.96 | 191.96
103 | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16222) | SM/16222 | 624.52 | 1300 | NEW | 15 | Delayed | 6 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 38.66 | 38.66
104 | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12645) | SM/12645 | 56.65 | 100 | AUGMENTATION | 15 | Delayed | 33 | 19/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 18.7 | 18.7
105 | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. (SM/14827) | SM/14827 | 122.62 | 193 | NEW | 15 | Delayed | 8 | 03/02/2023 | 31/12/2024 | 09/04/2024 | 22/02/2023 | 9.39 | 3.65
106 | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14165) | SM/14165 | 689.32 | 2269 | NEW | 15 | Delayed | 10 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 17/03/2023 | 69.06 | 30.46
107 | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12783) | SM/12783 | 311.92 | 502 | NEW | 15 | Delayed | 12 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 38.02 | 34.93
108 | BHOMRA PWSS (SM/18627) | SM/18627 | 1301.95 | 4067 | NEW | 16 | Delayed | 20 | 31/07/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 254 | 32.36
109 | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17256) | SM/17256 | 185.7 | 457 | NEW | 16 | Delayed | 28 | 15/03/2023 | 31/12/2024 | 09/04/2024 | 29/03/2023 | 51.73 | 3.9
110 | TUNIBHITA PWSS (SM/18291) | SM/18291 | 1226.41 | 3213 | NEW | 17 | Delayed | 16 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 195.51 | 195.51
111 | BELAN Piped Water Supply Scheme (SM/13233) | SM/13233 | 773.92 | 2942 | NEW | 17 | Delayed | 15 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 118.28 | 118.28
112 | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15213) | SM/15213 | 927.83 | 2660 | NEW | 17 | Delayed | 16 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 24/07/2023 | 145.51 | 145.51
113 | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12648) | SM/12648 | 56.37 | 100 | AUGMENTATION | 17 | Delayed | 27 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 15.19 | 6.01
114 | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14227) | SM/14227 | 49.54 | 50 | AUGMENTATION | 17 | Delayed | 48 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 23.98 | 23.98
115 | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14230) | SM/14230 | 49.54 | 50 | AUGMENTATION | 17 | Delayed | 47 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 23.5 | 23.5
116 | MANORA Piped Water Supply Scheme (SM/15126) | SM/15126 | 1000.28 | 3398 | NEW | 17 | Delayed | 7 | 04/02/2023 | 31/12/2024 | 12/04/2024 | 24/07/2023 | 70.98 | 70.98
117 | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District (SM/18450) | SM/18450 | 1127.27 | 2238 | NEW | 19 | Delayed | 22 | 20/07/2023 | 31/12/2024 | 09/04/2024 | 31/07/2023 | 242.48 | 242.48
118 | JAMIRA Piped Water Supply Scheme (SM/14179) | SM/14179 | 789 | 2909 | NEW | 19 | Delayed | 30 | 09/01/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 233.7 | 223.69
119 | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16491) | SM/16491 | 538.04 | 1988 | NEW | 19 | Delayed | 6 | 02/03/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 32.3 | 22.28
120 | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14226) | SM/14226 | 49.54 | 50 | AUGMENTATION | 19 | Delayed | 29 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 14.56 | 14.56
121 | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12787) | SM/12787 | 339.28 | 742 | NEW | 19 | Delayed | 13 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 28/07/2023 | 42.75 | 42.75
122 | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16505) | SM/16505 | 132.68 | 156 | NEW | 19 | Delayed | 26 | 02/03/2023 | 31/12/2024 | 09/04/2024 | 06/03/2023 | 34.3 | 34.3
123 | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. (SM/18295) | SM/18295 | 1248.45 | 3442 | AUGMENTATION | 19 | Delayed | 22 | 26/06/2023 | 30/09/2024 | 09/04/2024 | 13/07/2023 | 280.22 | 253.81
124 | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/18341) | SM/18341 | 2257.53 | 5716 | NEW | 20 | Delayed | 17 | 04/07/2023 | 31/12/2024 | 10/05/2024 | 27/07/2023 | 390.5 | 238.13
125 | KUCHILA PWSS (SM/18325) | SM/18325 | 1101.08 | 2923 | NEW | 20 | Delayed | 23 | 27/06/2023 | 31/12/2024 | 15/04/2024 | 13/07/2023 | 249 | 249
126 | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12106) | SM/12106 | 781.36 | 2691 | NEW | 21 | Delayed | 15 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 121.05 | 121.05
127 | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14229) | SM/14229 | 49.54 | 50 | AUGMENTATION | 21 | Delayed | 73 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 36.31 | 36.31
128 | AGDIMTI Piped Water Supply Scheme at Islampur Block (SM/12091) | SM/12091 | 741.95 | 2151 | NEW | 21 | Delayed | 45 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 04/04/2023 | 335.56 | 335.56
129 | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16223) | SM/16223 | 674.95 | 1330 | NEW | 22 | Delayed | 22 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 150.36 | 150.36
130 | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16490) | SM/16490 | 519.67 | 2042 | NEW | 22 | Delayed | 26 | 02/03/2023 | 31/12/2024 | 12/04/2024 | 11/09/2023 | 134.36 | 134.36
131 | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14167) | SM/14167 | 840.92 | 2762 | NEW | 22 | Delayed | 30 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 11/09/2023 | 253.86 | 243.86
132 | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12651) | SM/12651 | 58.53 | 150 | AUGMENTATION | 23 | Delayed | 20 | 19/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 11.44 | 11.44
133 | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. (SM/12707) | SM/12707 | 487.59 | 1384 | NEW | 23 | Delayed | 24 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 28/07/2023 | 117.63 | 77.12
134 | RAUTARA Pipe Water Supply Scheme (SM/15306) | SM/15306 | 753.03 | 2073 | NEW | 23 | Delayed | 3 | 09/02/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 21.21 | 12.77
135 | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. (SM/16229) | SM/16229 | 470.99 | 790 | NEW | 23 | Delayed | 26 | 23/02/2023 | 31/12/2024 | 12/04/2024 | 10/08/2023 | 123.57 | 123.57
136 | KOKRA Piped Water Supply Scheme (SM/14175) | SM/14175 | 476.42 | 1199 | NEW | 24 | Delayed | 6 | 09/01/2023 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 27.76 | 27.76
137 | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12643) | SM/12643 | 54.48 | 200 | AUGMENTATION | 24 | Delayed | 38 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 20.94 | 20.94
138 | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. (SM/15146) | SM/15146 | 714.17 | 1910 | NEW | 24 | Delayed | 22 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 158.57 | 158.57
139 | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. (SM/16226) | SM/16226 | 358.44 | 688 | NEW | 24 | Delayed | 12 | 23/02/2023 | 31/12/2024 | 12/04/2024 | 14/08/2023 | 42.21 | 42.21
140 | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16495) | SM/16495 | 607.74 | 1568 | NEW | 25 | Delayed | 24 | 02/03/2023 | 31/12/2024 | 12/04/2024 | 24/07/2023 | 143.98 | 124.06
141 | SADIPUR PWSS (SM/18994) | SM/18994 | 915.05 | 2615 | NEW | 25 | Delayed | 3 | 17/10/2023 | 31/12/2024 | 19/04/2024 | 17/10/2023 | 25.21 | 25.21
142 | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12780) | SM/12780 | 600.64 | 2533 | NEW | 25 | Delayed | 13 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 75.78 | 75.78
143 | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12793) | SM/12793 | 752.34 | 2764 | NEW | 25 | Delayed | 17 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 03/08/2023 | 124.27 | 83.87
144 | PRATAPPUR PIPED WATER SUPPLY SCHEME (SM/14128) | SM/14128 | 613.01 | 2096 | NEW | 25 | Delayed | 35 | 02/01/2023 | 31/12/2024 | 12/04/2024 | 01/09/2023 | 216.22 | 144.95
145 | BALDIABASA Piped Water Supply Scheme (SM/13234) | SM/13234 | 396.51 | 1362 | NEW | 26 | Delayed | 22 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 87.62 | 52.37
146 | MALKOT Pipe Water Supply Scheme (SM/15303) | SM/15303 | 764.07 | 2259 | NEW | 26 | Delayed | 4 | 09/02/2023 | 31/12/2024 | 12/04/2024 | 21/07/2023 | 33.41 | 33.41
147 | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. (SM/16219) | SM/16219 | 706.61 | 1475 | NEW | 26 | Delayed | 33 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 234.09 | 213.33
148 | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13503) | SM/13503 | 612.92 | 1889 | NEW | 26 | Delayed | 19 | 02/11/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 114.5 | 114.5
149 | GODASAMAL Piped Water Supply Scheme (SM/15128) | SM/15128 | 1005.02 | 3549 | NEW | 26 | Delayed | 20 | 04/02/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 205.42 | 205.42
150 | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12786) | SM/12786 | 603.43 | 2242 | NEW | 27 | Delayed | 25 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 28/07/2023 | 153.85 | 57.56
151 | BARA SINGHANATH Piped Water Supply Scheme (SM/12529) | SM/12529 | 922.51 | 2136 | NEW | 27 | Delayed | 15 | 13/09/2022 | 30/09/2024 | 12/04/2024 | 04/08/2023 | 139.92 | 96.96
152 | Sathaur Piped Water Supply Scheme (SM/13231) | SM/13231 | 445.66 | 1795 | NEW | 27 | Delayed | 32 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 141.55 | 141.55
153 | BAJARGAON PWSS (SM/18626) | SM/18626 | 1290.63 | 3375 | NEW | 27 | Delayed | 6 | 31/07/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 71.31 | 71.31
154 | KABUTARKHOPI Piped Water Supply Scheme (SM/13235) | SM/13235 | 627.6 | 2602 | NEW | 27 | Delayed | 25 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 159.62 | 159.62
155 | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/16225) | SM/16225 | 480.89 | 944 | NEW | 27 | Delayed | 19 | 23/02/2023 | 30/09/2024 | 12/04/2024 | 19/05/2023 | 92.95 | 92.95
156 | Dwipnagar Piped Water Supply Scheme. (SM/18180) | SM/18180 | 531.76 | 2217 | NEW | 28 | Delayed | 26 | 30/03/2023 | 31/12/2024 | 12/04/2024 | 24/04/2023 | 135.77 | 135.77
157 | ILLUABARI PWSS (SM/18449) | SM/18449 | 1911.1 | 3914 | NEW | 28 | Delayed | 1 | 20/07/2023 | 31/12/2024 | 17/05/2024 | 04/08/2023 | 13.81 | 13.81
158 | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13502) | SM/13502 | 638.08 | 2490 | NEW | 28 | Delayed | 30 | 02/11/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 188.73 | 188.73
159 | Gorahar Piped Water Supply Scheme. (SM/14640) | SM/14640 | 594.44 | 1183 | NEW | 28 | Delayed | 15 | 31/01/2023 | 31/12/2024 | 09/04/2024 | 23/02/2023 | 88.38 | 88.38
160 | IKARCHALA PWSS (SM/18294) | SM/18294 | 1200.16 | 3760 | NEW | 29 | Delayed | 8 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 11/08/2023 | 95.19 | 92.2
161 | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/14642) | SM/14642 | 847.33 | 1778 | NEW | 29 | Delayed | 17 | 31/01/2023 | 31/12/2024 | 09/04/2024 | 04/08/2023 | 141.75 | 141.75
162 | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/17255) | SM/17255 | 704.46 | 1461 | NEW | 29 | Delayed | 22 | 15/03/2023 | 31/03/2024 | 09/01/2024 | 08/05/2023 | 158.21 | 158.21
163 | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16493) | SM/16493 | 496.17 | 1567 | NEW | 29 | Delayed | 37 | 02/03/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 183.42 | 158.29
164 | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12789) | SM/12789 | 536.84 | 1871 | NEW | 29 | Delayed | 25 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 132.3 | 107.45
165 | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10500) | SM/10500 | 65.12 | 0 | RETROFITTING | 30 | Delayed | 20 | 13/04/2022 | 31/03/2024 | 05/12/2023 | 31/03/2023 | 12.72 | 12.72
166 | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12782) | SM/12782 | 561.35 | 2030 | NEW | 30 | Delayed | 17 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 28/07/2023 | 92.63 | 92.63
167 | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18164) | SM/18164 | 271.95 | 866 | NEW | 30 | Delayed | 4 | 29/03/2023 | 31/12/2024 | 12/04/2024 | 13/07/2023 | 10.46 | 5.33
168 | TOPAMARI PWSS (SM/18243) | SM/18243 | 1112.55 | 3482 | NEW | 30 | Delayed | 31 | 16/06/2023 | 31/12/2024 | 15/05/2024 | 13/07/2023 | 339.59 | 310.39
169 | DAKSHIN RAMPUR Piped Water Supply Scheme (SM/13232) | SM/13232 | 592.79 | 2380 | NEW | 30 | Delayed | 34 | 13/10/2022 | 31/12/2024 | 12/04/2024 | 11/09/2023 | 204.13 | 85.16
170 | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. (SM/15516) | SM/15516 | 1297.89 | 3922 | NEW | 31 | Delayed | 17 | 16/02/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 224.12 | 141.3
171 | BHIKHANPUR PWSS (SM/18628) | SM/18628 | 1156.17 | 3085 | NEW | 31 | Delayed | 30 | 31/07/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 346.17 | 346.17
172 | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13550) | SM/13550 | 831.68 | 2927 | NEW | 31 | Delayed | 18 | 04/11/2022 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 150.14 | 150.14
173 | BARAKHANTI Piped Water Supply Scheme at Islampur Block (SM/12093) | SM/12093 | 893.92 | 2310 | NEW | 32 | Delayed | 20 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 174.52 | 174.52
174 | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12641) | SM/12641 | 49.56 | 60 | AUGMENTATION | 32 | Delayed | 43 | 19/09/2022 | 31/03/2024 | 05/12/2023 | 28/10/2022 | 21.35 | 21.35
175 | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12646) | SM/12646 | 49.11 | 50 | AUGMENTATION | 32 | Delayed | 68 | 19/09/2022 | 31/03/2024 | 05/12/2023 | 28/10/2022 | 33.61 | 33.61
176 | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/12788) | SM/12788 | 736.56 | 1864 | NEW | 32 | Delayed | 19 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 141.01 | 141.01
177 | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18169) | SM/18169 | 96.73 | 236 | NEW | 32 | Delayed | 7 | 29/03/2023 | 31/12/2024 | 26/04/2024 | 29/05/2023 | 7.17 | 7.17
178 | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12778) | SM/12778 | 693.47 | 2529 | NEW | 32 | Delayed | 24 | 20/09/2022 | 31/03/2025 | 12/04/2024 | 04/08/2023 | 168.37 | 127.47
179 | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME (SM/11725) | SM/11725 | 883.67 | 2755 | AUGMENTATION | 33 | Delayed | 28 | 03/08/2022 | 30/09/2024 | 09/04/2024 | 26/08/2022 | 247.87 | 247.87
180 | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14163) | SM/14163 | 974.62 | 3112 | NEW | 34 | Delayed | 17 | 05/01/2023 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 168.29 | 161.8
181 | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13012) | SM/13012 | 979.94 | 2805 | NEW | 35 | Delayed | 24 | 28/09/2022 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 237.81 | 237.81
182 | RANIGANJ Piped Water Supply Scheme (SM/14181) | SM/14181 | 833.07 | 3028 | NEW | 35 | Delayed | 23 | 09/01/2023 | 31/12/2024 | 12/04/2024 | 22/02/2023 | 188.64 | 159.75
183 | BASUDEBPUR Piped Water Supply Scheme (SM/14182) | SM/14182 | 809.69 | 1806 | NEW | 36 | Delayed | 30 | 09/01/2023 | 31/12/2024 | 12/04/2024 | 23/02/2023 | 243.12 | 243.12
184 | PANDITPOTA PIPED WATER SUPPLY SCHEME (SM/13542) | SM/13542 | 540.87 | 1260 | NEW | 36 | Delayed | 22 | 04/11/2022 | 31/12/2024 | 12/04/2024 | 16/01/2023 | 121.39 | 121.39
185 | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18166) | SM/18166 | 72.22 | 129 | NEW | 36 | Delayed | 31 | 29/03/2023 | 30/09/2024 | 12/04/2024 | 14/08/2023 | 22.57 | 22.57
186 | Replacement T/W for 4 Nos. water supply scheme. (SM/18227) | SM/18227 | 137.5 | 0 | AUGMENTATION | 36 | Delayed | 10 | 16/03/2023 | 31/03/2024 | 21/09/2023 | 16/12/2021 | 13.18 | 13.18
187 | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12099) | SM/12099 | 741.1 | 2423 | NEW | 36 | Delayed | 36 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 270.46 | 257.15
188 | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17199) | SM/17199 | 755.97 | 1496 | NEW | 36 | Delayed | 30 | 15/03/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 228.56 | 220.47
189 | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17743) | SM/17743 | 155.24 | 375 | AUGMENTATION | 36 | Delayed | 3 | 17/03/2023 | 30/09/2024 | 09/04/2024 | 27/03/2023 | 4.7 | 3.7
190 | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. (SM/13456) | SM/13456 | 710.31 | 2656 | NEW | 37 | Delayed | 30 | 02/11/2022 | 31/12/2024 | 12/04/2024 | 01/09/2023 | 213.48 | 188.57
191 | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12653) | SM/12653 | 54.98 | 200 | AUGMENTATION | 37 | Delayed | 49 | 19/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 26.91 | 26.91
192 | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12109) | SM/12109 | 732.1 | 2257 | NEW | 38 | Delayed | 29 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/01/2021 | 215.29 | 215.29
193 | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME (SM/15125) | SM/15125 | 602.98 | 2112 | AUGMENTATION | 38 | Delayed | 17 | 04/02/2023 | 30/09/2024 | 12/04/2024 | 01/11/2022 | 102.28 | 102.28
194 | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. (SM/14146) | SM/14146 | 719.4 | 1416 | NEW | 38 | Delayed | 30 | 02/01/2023 | 31/12/2024 | 09/04/2024 | 23/02/2023 | 213.25 | 213.25
195 | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12103) | SM/12103 | 733.2 | 2063 | NEW | 38 | Delayed | 30 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 216.48 | 208.98
196 | Restoration of Pipe line for providing FHTC for Pirojpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10445) | SM/10445 | 101.69 | 0 | RETROFITTING | 38 | Delayed | 25 | 12/04/2022 | 31/03/2024 | 05/12/2023 | 24/06/2022 | 25.87 | 25.87
197 | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13739) | SM/13739 | 786.9 | 2128 | NEW | 38 | Delayed | 20 | 17/11/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 159.41 | 159.41
198 | Kashimpur Piped Water Supply Scheme. (SM/18182) | SM/18182 | 564.01 | 2253 | NEW | 38 | Delayed | 19 | 31/03/2023 | 31/12/2024 | 09/04/2024 | 24/04/2023 | 108.89 | 108.89
199 | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15211) | SM/15211 | 546.12 | 1287 | NEW | 39 | Delayed | 1 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 14/08/2023 | 7.93 | 7.93
200 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11727) | SM/11727 | 1057.12 | 2488 | AUGMENTATION | 39 | Delayed | 19 | 03/08/2022 | 30/09/2024 | 09/04/2024 | 26/08/2022 | 204.09 | 204.09
201 | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. (SM/12394) | SM/12394 | 900.04 | 2145 | AUGMENTATION | 39 | Delayed | 16 | 13/09/2022 | 30/09/2024 | 12/04/2024 | 01/11/2022 | 144.66 | 144.66
202 | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR (SM/11821) | SM/11821 | 605.48 | 1901 | NEW | 40 | Delayed | 41 | 16/08/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 247.42 | 202.59
203 | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/15148) | SM/15148 | 770.95 | 2412 | NEW | 40 | Delayed | 31 | 07/02/2023 | 31/12/2024 | 09/04/2024 | 23/02/2023 | 237.1 | 224.81
204 | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17437) | SM/17437 | 412.36 | 920 | NEW | 40 | Delayed | 22 | 18/03/2023 | 31/12/2024 | 09/04/2024 | 13/07/2023 | 91.44 | 91.44
205 | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13717) | SM/13717 | 1171.44 | 3186 | NEW | 40 | Delayed | 12 | 17/11/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 139.56 | 139.56
206 | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15212) | SM/15212 | 700.5 | 2006 | NEW | 40 | Delayed | 13 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 17/03/2023 | 90.06 | 90.06
207 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. (SM/09193) | SM/09193 | 25.39 | 395 | RETROFITTING | 40 | Delayed | 38 | 28/10/2021 | 31/03/2024 | 12/06/2023 | 14/09/2021 | 9.74 | 9.74
208 | BANIKANER ALISA RAHATPUR PWSS (SM/12522) | SM/12522 | 414.11 | 748 | NEW | 41 | Delayed | 30 | 13/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 123.85 | 123.85
209 | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. (SM/11897) | SM/11897 | 503.57 | 2458 | NEW | 41 | Delayed | 44 | 18/08/2022 | 31/12/2024 | 12/04/2024 | 12/05/2023 | 221.66 | 206.51
210 | DURGAPUR Piped Water Supply Scheme at Islampur Block (SM/12087) | SM/12087 | 558.58 | 1365 | NEW | 41 | Delayed | 27 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 153.11 | 153.11
211 | Palaibari Piped Water Supply Scheme. (SM/18181) | SM/18181 | 813.02 | 3420 | NEW | 42 | Delayed | 19 | 31/03/2023 | 31/12/2024 | 09/04/2024 | 24/04/2023 | 157.26 | 157.26
212 | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12639) | SM/12639 | 59.14 | 300 | AUGMENTATION | 42 | Delayed | 53 | 19/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 31.35 | 31.35
213 | Khalsi Piped Water Supply Scheme. (SM/18179) | SM/18179 | 512.31 | 2610 | NEW | 42 | Delayed | 28 | 31/03/2023 | 31/03/2025 | 12/04/2024 | 24/04/2023 | 141.84 | 141.84
214 | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME (SM/15124) | SM/15124 | 776.11 | 2906 | AUGMENTATION | 43 | Delayed | 20 | 04/02/2023 | 30/09/2024 | 12/04/2024 | 01/11/2022 | 158.31 | 158.31
215 | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12097) | SM/12097 | 576.88 | 1577 | NEW | 43 | Delayed | 34 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 18/01/2021 | 196.14 | 196.14
216 | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14228) | SM/14228 | 49.66 | 50 | AUGMENTATION | 43 | Delayed | 70 | 10/01/2023 | 30/09/2024 | 12/04/2024 | 16/01/2023 | 34.84 | 34.84
217 | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12640) | SM/12640 | 64.44 | 425 | AUGMENTATION | 43 | Delayed | 14 | 19/09/2022 | 31/03/2024 | 05/12/2023 | 28/10/2022 | 9.07 | 9.07
218 | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12102) | SM/12102 | 458.89 | 887 | NEW | 43 | Delayed | 36 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 164.99 | 164.99
219 | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block (SM/12094) | SM/12094 | 952.55 | 2314 | NEW | 44 | Delayed | 34 | 02/09/2022 | 31/03/2024 | 05/12/2023 | 01/11/2022 | 327.46 | 280.99
220 | MACHHALI PWSS (SM/18289) | SM/18289 | 1229.16 | 3378 | NEW | 44 | Delayed | 26 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 315.76 | 315.76
221 | ATGHARA PIPED WATER SUPPLY SCHEME (SM/13796) | SM/13796 | 1298.23 | 3730 | NEW | 44 | Delayed | 57 | 22/11/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 739.1 | 661.05
222 | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/14641) | SM/14641 | 885.92 | 1740 | NEW | 44 | Delayed | 20 | 31/01/2023 | 31/12/2024 | 09/04/2024 | 23/02/2023 | 177.88 | 177.88
223 | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block (SM/12095) | SM/12095 | 874.21 | 2465 | NEW | 45 | Delayed | 47 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 410.66 | 395.09
224 | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12105) | SM/12105 | 895.79 | 2789 | NEW | 45 | Delayed | 27 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 18/01/2021 | 241.32 | 241.32
225 | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT (SM/11824) | SM/11824 | 1178.23 | 3169 | NEW | 45 | Delayed | 35 | 16/08/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 417.92 | 416.75
226 | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/18451) | SM/18451 | 1352.83 | 2019 | NEW | 45 | Delayed | 26 | 20/07/2023 | 31/12/2024 | 09/04/2024 | 27/07/2023 | 351.09 | 254.06
227 | Restoration of Pipe Line for providing FHTC at Jaingaon Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10547) | SM/10547 | 14.12 | 0 | RETROFITTING | 45 | Delayed | 95 | 18/04/2022 | 31/03/2024 | 09/01/2024 | 12/05/2022 | 13.36 | 13.36
228 | PURBBA GOMAIDIGHI PWSS (SM/18448) | SM/18448 | 1012.28 | 2508 | NEW | 45 | On track | 33 | 20/07/2023 | 31/12/2024 | 12/04/2024 | 24/08/2023 | 337.45 | 337.45
229 | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12101) | SM/12101 | 562.28 | 1484 | NEW | 45 | Delayed | 30 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 166.74 | 166.74
230 | Laying of additional pipe line for retrofitting of Dakshin Kundal Pukur for installation of FHTC. (SM/09120) | SM/09120 | 13.59 | 0 | RETROFITTING | 45 | Delayed | 76 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 24/12/2021 | 10.37 | 10.37
231 | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. (SM/16258) | SM/16258 | 921.63 | 2024 | NEW | 46 | Delayed | 26 | 24/02/2023 | 31/12/2024 | 09/04/2024 | 16/03/2023 | 238.04 | 233.14
232 | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME (SM/10040) | SM/10040 | 381.45 | 950 | AUGMENTATION | 47 | Delayed | 50 | 19/01/2022 | 30/09/2024 | 09/04/2024 | 25/02/2022 | 189.39 | 151.8
233 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/13115) | SM/13115 | 1519.65 | 5083 | AUGMENTATION | 47 | Delayed | 17 | 10/10/2022 | 31/12/2024 | 12/04/2024 | 12/07/2022 | 264.79 | 249.22
234 | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/16221) | SM/16221 | 705.61 | 1373 | NEW | 47 | Delayed | 33 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 233.45 | 221.16
235 | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12104) | SM/12104 | 403.41 | 1077 | NEW | 47 | Delayed | 37 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 147.64 | 147.64
236 | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12642) | SM/12642 | 63.86 | 425 | AUGMENTATION | 47 | Delayed | 31 | 19/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 20.11 | 20.11
237 | POTHIA Piped Water Supply Scheme at Islampur Block (SM/12088) | SM/12088 | 731.84 | 2183 | NEW | 47 | Delayed | 35 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 254.86 | 254.86
238 | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/16536) | SM/16536 | 1427.38 | 3752 | NEW | 48 | Delayed | 33 | 10/03/2023 | 31/12/2024 | 12/04/2024 | 11/04/2023 | 464.33 | 372.8
239 | KUNDARGAON Piped Water Supply Scheme at Islampur Block (SM/12086) | SM/12086 | 545.87 | 1299 | NEW | 48 | Delayed | 26 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 143.56 | 143.56
240 | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13015) | SM/13015 | 53.17 | 150 | AUGMENTATION | 48 | Delayed | 57 | 28/09/2022 | 30/09/2024 | 12/04/2024 | 28/10/2022 | 30.26 | 30.25
241 | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district (SM/12115) | SM/12115 | 837.26 | 2604 | NEW | 48 | Delayed | 44 | 02/09/2022 | 31/03/2024 | 04/10/2023 | 01/11/2022 | 368.63 | 320.86
242 | HEMENPUR Piped Water Supply Scheme (SM/14180) | SM/14180 | 564.15 | 1426 | NEW | 49 | Delayed | 28 | 09/01/2023 | 31/12/2024 | 12/04/2024 | 17/03/2023 | 157.85 | 157.85
243 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11798) | SM/11798 | 695.38 | 1806 | AUGMENTATION | 49 | Delayed | 20 | 05/08/2022 | 31/12/2024 | 12/04/2024 | 31/08/2022 | 137.08 | 137.08
244 | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13021) | SM/13021 | 58.49 | 150 | AUGMENTATION | 49 | Delayed | 44 | 28/09/2022 | 30/09/2024 | 09/04/2024 | 28/10/2022 | 25.51 | 25.51
245 | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12100) | SM/12100 | 656.05 | 2107 | NEW | 49 | Delayed | 40 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 03/09/2019 | 259.38 | 259.38
246 | Laying of additional pipe line for retrofitting of Matikunda (Part-I/II) WSS for installation of FHTC. (SM/09130) | SM/09130 | 11.88 | 0 | RETROFITTING | 50 | Delayed | 50 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 24/12/2021 | 5.89 | 5.89
247 | Restoration of Pipe Line for providing FHTC of Intia Piped Water Supply Scheme for installation of FHTC under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10447) | SM/10447 | 6.79 | 0 | RETROFITTING | 50 | Delayed | 93 | 12/04/2022 | 31/03/2024 | 09/01/2024 | 12/05/2022 | 6.32 | 6.32
248 | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16494) | SM/16494 | 879.93 | 1993 | NEW | 50 | On track | 20 | 02/03/2023 | 31/03/2025 | 09/04/2024 | 16/03/2023 | 178.93 | 176.86
249 | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR (SM/11642) | SM/11642 | 898.8 | 3431 | NEW | 50 | Delayed | 48 | 27/07/2022 | 31/12/2024 | 12/04/2024 | 26/08/2022 | 432.09 | 385.8
250 | Dhamdhol Piped Water Supply Scheme. (SM/14639) | SM/14639 | 706.27 | 1314 | NEW | 50 | Delayed | 25 | 31/01/2023 | 31/12/2024 | 09/04/2024 | 23/02/2023 | 173.2 | 173.2
251 | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block (SM/12096) | SM/12096 | 484.82 | 1031 | NEW | 50 | Delayed | 38 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 31/01/2022 | 183.33 | 183.33
252 | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME (SM/10548) | SM/10548 | 380.61 | 1180 | AUGMENTATION | 50 | Delayed | 35 | 18/04/2022 | 30/09/2024 | 09/04/2024 | 14/07/2022 | 132.14 | 132.14
253 | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12098) | SM/12098 | 404.9 | 763 | NEW | 51 | Delayed | 46 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 03/09/2019 | 187.33 | 184.03
254 | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. (SM/15147) | SM/15147 | 752.32 | 2122 | NEW | 51 | Delayed | 22 | 07/02/2023 | 31/12/2024 | 12/04/2024 | 16/03/2023 | 168.12 | 119.43
255 | ALIGANJ Piped Water Supply Scheme at Islampur Block (SM/12090) | SM/12090 | 1029.88 | 2409 | NEW | 51 | Delayed | 21 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 221.03 | 221.03
256 | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/13795) | SM/13795 | 1311.18 | 3098 | NEW | 51 | Delayed | 41 | 22/11/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 535.59 | 535.09
257 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11721) | SM/11721 | 1029.67 | 2892 | AUGMENTATION | 51 | Delayed | 26 | 03/08/2022 | 30/09/2024 | 12/04/2024 | 31/08/2022 | 264 | 245.77
258 | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11865) | SM/11865 | 750.86 | 1870 | NEW | 52 | Delayed | 40 | 17/08/2022 | 31/12/2024 | 12/04/2024 | 14/11/2022 | 300.63 | 300.63
259 | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17436) | SM/17436 | 625.89 | 1301 | NEW | 52 | Delayed | 28 | 18/03/2023 | 31/12/2024 | 09/04/2024 | 08/05/2023 | 173.03 | 173.03
260 | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME (SM/11795) | SM/11795 | 678.08 | 2632 | AUGMENTATION | 52 | Delayed | 43 | 05/08/2022 | 31/12/2024 | 15/04/2024 | 26/08/2022 | 289.88 | 289.88
261 | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district (SM/12112) | SM/12112 | 650.8 | 1882 | NEW | 53 | Delayed | 47 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 308.48 | 297.72
262 | GAISAL Piped Water Supply Scheme at Islampur Block (SM/12092) | SM/12092 | 821.68 | 2554 | NEW | 53 | Delayed | 44 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 357.78 | 357.78
263 | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/12792) | SM/12792 | 870.25 | 2602 | NEW | 53 | Delayed | 37 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 321.25 | 321.25
264 | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. (SM/12779) | SM/12779 | 557.76 | 1451 | NEW | 53 | Delayed | 26 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 16/03/2022 | 142.92 | 142.92
265 | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16224) | SM/16224 | 812.41 | 1682 | NEW | 54 | Delayed | 27 | 23/02/2023 | 31/12/2024 | 09/04/2024 | 21/03/2023 | 216.94 | 210.42
266 | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12790) | SM/12790 | 83.86 | 305 | NEW | 54 | Delayed | 71 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 22/02/2023 | 59.59 | 59.59
267 | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12108) | SM/12108 | 580.75 | 1719 | NEW | 54 | Delayed | 43 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 252.02 | 252.02
268 | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT (SM/11825) | SM/11825 | 840.56 | 3083 | NEW | 54 | Delayed | 28 | 16/08/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 239.42 | 229.95
269 | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12107) | SM/12107 | 573.51 | 1535 | NEW | 54 | Delayed | 42 | 02/09/2022 | 31/03/2024 | 09/01/2024 | 01/11/2022 | 240.58 | 240.58
270 | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13014) | SM/13014 | 781.32 | 1880 | NEW | 54 | Delayed | 26 | 28/09/2022 | 31/12/2024 | 12/04/2024 | 20/01/2023 | 201.27 | 201.27
271 | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11961) | SM/11961 | 687.72 | 2986 | NEW | 55 | Delayed | 43 | 25/08/2022 | 31/12/2024 | 12/04/2024 | 14/11/2022 | 294.15 | 286.47
272 | Restoration of Pipe line for providing FHTC for Sherpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10494) | SM/10494 | 5.97 | 0 | RETROFITTING | 55 | Delayed | 97 | 13/04/2022 | 31/03/2024 | 09/01/2024 | 12/05/2022 | 5.76 | 5.76
273 | Restoration of Pipe line for providing FHTC for Maslandpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10463) | SM/10463 | 7.55 | 0 | RETROFITTING | 55 | Delayed | 97 | 13/04/2022 | 31/03/2024 | 09/01/2024 | 12/05/2022 | 7.32 | 7.32
274 | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ (SM/11643) | SM/11643 | 425.83 | 1698 | NEW | 55 | Delayed | 51 | 27/07/2022 | 24/02/2024 | 09/01/2024 | 31/08/2022 | 216.13 | 216.13
275 | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13013) | SM/13013 | 747.35 | 2310 | NEW | 56 | Delayed | 30 | 28/09/2022 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 221.59 | 221.59
276 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09194) | SM/09194 | 23.34 | 360 | RETROFITTING | 56 | Delayed | 52 | 28/10/2021 | 31/03/2024 | 21/09/2023 | 14/09/2021 | 12.17 | 12.17
277 | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. (SM/12395) | SM/12395 | 631.31 | 1487 | AUGMENTATION | 56 | Delayed | 27 | 13/09/2022 | 30/09/2024 | 12/04/2024 | 01/11/2022 | 172.54 | 160.14
278 | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME (SM/11797) | SM/11797 | 723.84 | 3392 | AUGMENTATION | 57 | Delayed | 38 | 05/08/2022 | 30/09/2024 | 12/04/2024 | 26/08/2022 | 275.69 | 275.69
279 | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/15904) | SM/15904 | 913.58 | 1963 | NEW | 57 | On track | 14 | 20/02/2023 | 31/12/2024 | 12/04/2024 | 01/11/2022 | 124.03 | 124.03
280 | Restoration of Pipe Line for providing FHTC at Pokharia Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10449) | SM/10449 | 7.24 | 0 | RETROFITTING | 58 | Delayed | 88 | 11/04/2022 | 31/03/2024 | 09/01/2024 | 12/05/2022 | 6.37 | 6.37
281 | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR (SM/11820) | SM/11820 | 751.83 | 2009 | NEW | 59 | Delayed | 48 | 16/08/2022 | 31/12/2024 | 12/04/2024 | 14/11/2022 | 364.27 | 350.45
282 | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME (SM/11796) | SM/11796 | 741.87 | 2030 | AUGMENTATION | 59 | Delayed | 35 | 05/08/2022 | 31/12/2024 | 09/04/2024 | 26/08/2022 | 258.18 | 258.18
283 | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/16199) | SM/16199 | 138.64 | 239 | NEW | 59 | On track | 11 | 24/02/2023 | 31/12/2024 | 09/04/2024 | 06/03/2023 | 15.42 | 15.42
284 | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. (SM/10545) | SM/10545 | 283.68 | 0 | AUGMENTATION | 60 | Delayed | 95 | 18/04/2022 | 31/03/2024 | 09/01/2024 | 03/11/2021 | 269.31 | 269.3
285 | Baje Bindol PWSS in Raiganj Block in North Dinajpur District (SM/11644) | SM/11644 | 654.21 | 2254 | NEW | 60 | Delayed | 48 | 27/07/2022 | 31/12/2024 | 12/04/2024 | 26/08/2022 | 311.5 | 293.89
286 | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11728) | SM/11728 | 707.96 | 1800 | AUGMENTATION | 61 | Delayed | 28 | 03/08/2022 | 30/09/2024 | 12/04/2024 | 26/08/2022 | 201.11 | 201.11
287 | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME (SM/11726) | SM/11726 | 791.06 | 2457 | AUGMENTATION | 61 | Delayed | 43 | 03/08/2022 | 30/09/2024 | 12/04/2024 | 31/08/2022 | 340.69 | 340.69
288 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11794) | SM/11794 | 767.67 | 1680 | AUGMENTATION | 62 | Delayed | 31 | 05/08/2022 | 30/09/2024 | 12/04/2024 | 21/07/2022 | 238.89 | 216.01
289 | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. (SM/12785) | SM/12785 | 930.19 | 2866 | NEW | 64 | On track | 31 | 20/09/2022 | 31/12/2024 | 12/04/2024 | 15/03/2022 | 284.27 | 284.27
290 | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK (SM/11863) | SM/11863 | 461.61 | 1373 | NEW | 65 | Delayed | 43 | 17/08/2022 | 30/09/2024 | 12/04/2024 | 31/08/2022 | 197.36 | 197.36
291 | UTTAR SHAHAPUR PWSS (SM/18475) | SM/18475 | 1131 | 3076 | NEW | 67 | On track | 23 | 24/07/2023 | 31/12/2024 | 12/04/2024 | 04/08/2023 | 265.5 | 235.78
292 | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR (SM/11819) | SM/11819 | 467.12 | 1335 | NEW | 68 | On track | 39 | 16/08/2022 | 31/12/2024 | 12/04/2024 | 14/11/2022 | 182.19 | 180.21
293 | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. (SM/12393) | SM/12393 | 778.79 | 2114 | AUGMENTATION | 68 | Delayed | 15 | 13/09/2022 | 30/09/2024 | 12/04/2024 | 01/11/2022 | 119.22 | 119.22
294 | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. (SM/17742) | SM/17742 | 203.43 | 341 | AUGMENTATION | 70 | Delayed | 2 | 17/03/2023 | 31/03/2024 | 09/01/2024 | 27/03/2023 | 4.92 | 4.92
295 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11801) | SM/11801 | 1037.52 | 3033 | AUGMENTATION | 70 | On track | 23 | 05/08/2022 | 31/12/2024 | 12/04/2024 | 07/07/2022 | 237.66 | 237.66
296 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. (SM/09187) | SM/09187 | 80.61 | 1240 | RETROFITTING | 71 | Delayed | 32 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 25.53 | 25.53
297 | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10424) | SM/10424 | 14.48 | 0 | RETROFITTING | 73 | Delayed | 97 | 08/04/2022 | 31/03/2024 | 07/08/2023 | 09/12/2021 | 14.06 | 14.06
298 | Augmentation Dilwarpur Piped Water Supply Scheme. (SM/09989) | SM/09989 | 429.52 | 989 | AUGMENTATION | 73 | Delayed | 48 | 16/12/2021 | 31/03/2024 | 05/12/2023 | 07/01/2022 | 208 | 208
299 | Augmentation of Chopra Water Supply Scheme. (SM/10129) | SM/10129 | 1382.11 | 3136 | AUGMENTATION | 73 | Delayed | 28 | 08/02/2022 | 30/09/2024 | 12/04/2024 | 10/02/2022 | 381 | 381
300 | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME (SM/11724) | SM/11724 | 623.82 | 2535 | AUGMENTATION | 74 | On track | 42 | 03/08/2022 | 30/09/2024 | 12/04/2024 | 26/08/2022 | 263.8 | 263.8
301 | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME (SM/11196) | SM/11196 | 798.69 | 2946 | AUGMENTATION | 76 | On track | 33 | 03/06/2022 | 31/12/2024 | 12/04/2024 | 25/07/2022 | 262.89 | 262.89
302 | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). (SM/09129) | SM/09129 | 41.15 | 0 | RETROFITTING | 76 | Delayed | 87 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 07/07/2021 | 35.8 | 35.8
303 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (SM/11800) | SM/11800 | 866.75 | 3014 | AUGMENTATION | 77 | On track | 32 | 05/08/2022 | 29/12/2024 | 12/04/2024 | 26/08/2022 | 276.16 | 228.09
304 | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme (SM/07141) | SM/07141 | 81.83 | 1578 | RETROFITTING | 79 | Delayed | 100 | 27/11/2020 | 31/03/2024 | 09/01/2024 | 11/12/2020 | 81.83 | 76.5
305 | DOHASO PWSS (SM/18304) | SM/18304 | 1767.14 | 4064 | NEW | 79 | On track | 48 | 26/06/2023 | 31/12/2024 | 12/04/2024 | 27/07/2023 | 847.77 | 847.77
306 | Restoration of Pipe line for providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10496) | SM/10496 | 14.63 | 0 | RETROFITTING | 80 | Delayed | 72 | 13/04/2022 | 31/03/2024 | 05/12/2023 | 12/05/2022 | 10.6 | 10.6
307 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11799) | SM/11799 | 1021.76 | 3105 | AUGMENTATION | 80 | On track | 34 | 05/08/2022 | 30/09/2024 | 09/04/2024 | 31/08/2022 | 342.67 | 342.67
308 | Laying of additional pipe line for retrofitting of Dakshin Jibhokati for installation of FHTC. (SM/09138) | SM/09138 | 1.42 | 0 | RETROFITTING | 80 | Delayed | 97 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 1.38 | 1.38
309 | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. (SM/09114) | SM/09114 | 13 | 0 | RETROFITTING | 80 | Delayed | 84 | 29/10/2021 | 31/03/2024 | 05/12/2023 | 12/11/2021 | 10.86 | 9.79
310 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. (SM/09183) | SM/09183 | 29.49 | 455 | RETROFITTING | 81 | Delayed | 47 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 13.89 | 13.89
311 | MANIKPUR Piped Water Supply Scheme at Islampur Block (SM/12084) | SM/12084 | 733.37 | 1646 | NEW | 82 | On track | 50 | 02/09/2022 | 31/12/2024 | 12/04/2024 | 16/01/2023 | 368.24 | 368.24
312 | Laying of additional pipe line for retrofitting of Bhagabati for installation of FHTC. (SM/09139) | SM/09139 | 2.84 | 0 | RETROFITTING | 82 | Delayed | 0 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 0 | 0
313 | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. (SM/09128) | SM/09128 | 12.79 | 0 | RETROFITTING | 83 | Delayed | 69 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 8.81 | 8.81
314 | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. (SM/09131) | SM/09131 | 21.71 | 0 | RETROFITTING | 84 | Delayed | 85 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 18.41 | 18.41
315 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11802) | SM/11802 | 894.05 | 2840 | AUGMENTATION | 84 | On track | 29 | 05/08/2022 | 31/12/2024 | 12/04/2024 | 26/08/2022 | 255.58 | 254.64
316 | Laying of additional pipe line for retrofitting of Ghirnigaonfor installation of FHTC. (SM/09122) | SM/09122 | 92.44 | 0 | RETROFITTING | 85 | Delayed | 91 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 23/12/2020 | 83.8 | 83.58
317 | Laying of additional pipe line for retrofitting of Jaingaon WSS for installation of FHTC. (SM/09126) | SM/09126 | 45.99 | 0 | RETROFITTING | 85 | Delayed | 96 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 44.16 | 44.16
318 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. (SM/09191) | SM/09191 | 15.8 | 245 | RETROFITTING | 85 | Delayed | 78 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 12.25 | 12.25
319 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. (SM/09181) | SM/09181 | 25.2 | 388 | RETROFITTING | 86 | Delayed | 48 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 12.02 | 10.88
320 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09186) | SM/09186 | 25.17 | 388 | RETROFITTING | 86 | Delayed | 44 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 11.07 | 11.07
321 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09184) | SM/09184 | 29.76 | 458 | RETROFITTING | 86 | Delayed | 68 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 20.16 | 20.16
322 | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block (SM/07390) | SM/07390 | 2444.58 | 44879 | RETROFITTING | 86 | Delayed | 71 | 21/12/2020 | 31/03/2024 | 09/01/2024 | 23/12/2020 | 1726.02 | 1726.02
323 | Augmentation of Sitalgaon Piped Water Supply Scheme. (SM/09990) | SM/09990 | 535.16 | 1165 | AUGMENTATION | 88 | On track | 32 | 16/12/2021 | 30/09/2024 | 12/04/2024 | 07/01/2022 | 169.85 | 168.62
324 | Restoration of Pipe line for providing FHTC for Shridharpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10442) | SM/10442 | 7.8 | 0 | RETROFITTING | 90 | Delayed | 55 | 12/04/2022 | 17/02/2024 | 12/09/2023 | 12/05/2022 | 4.3 | 4.3
325 | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10444) | SM/10444 | 10.7 | 0 | RETROFITTING | 90 | Delayed | 85 | 12/04/2022 | 31/03/2024 | 05/12/2023 | 17/02/2023 | 9.06 | 9.06
326 | Laying of additional pipe line for retrofitting of Bindal WSS for installation of FHTC. (SM/09116) | SM/09116 | 13.3 | 0 | RETROFITTING | 90 | Delayed | 97 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 17/11/2021 | 12.83 | 12.83
327 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09188) | SM/09188 | 46.39 | 715 | RETROFITTING | 91 | Delayed | 61 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 14/09/2021 | 28.46 | 28.46
328 | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block (SM/07389) | SM/07389 | 1512.6 | 26407 | RETROFITTING | 92 | Delayed | 73 | 21/12/2020 | 31/03/2024 | 09/01/2024 | 24/12/2020 | 1111.13 | 1092.75
329 | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block (SM/07073) | SM/07073 | 68.13 | 1479 | RETROFITTING | 93 | Delayed | 100 | 27/11/2020 | 31/03/2024 | 09/01/2024 | 26/02/2021 | 68.13 | 62.07
330 | Augmentation of Kanki Matiari Piped Water Supply Scheme. (SM/09985) | SM/09985 | 340.27 | 577 | AUGMENTATION | 93 | On track | 55 | 16/12/2021 | 30/09/2024 | 12/04/2024 | 07/01/2022 | 187.24 | 187.16
331 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. (SM/09182) | SM/09182 | 52.94 | 815 | RETROFITTING | 94 | Delayed | 62 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 23/12/2020 | 32.76 | 32.76
332 | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte (SM/07977) | SM/07977 | 502.08 | 9907 | RETROFITTING | 95 | On track | 75 | 22/01/2021 | 31/03/2024 | 05/12/2023 | 18/06/2021 | 375.3 | 351.61
333 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09189) | SM/09189 | 26.54 | 410 | RETROFITTING | 95 | Delayed | 86 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 22.75 | 22.75
334 | Laying of additional pipe line for retrofitting of Pokheria WSS for installation of FHTC. (SM/09132) | SM/09132 | 3.92 | 0 | RETROFITTING | 95 | Delayed | 84 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 3.28 | 3.28
335 | Laying of additional pipe line for retrofitting of Intia WSS for installation of FHTC (Part-A & B) . (SM/09125) | SM/09125 | 20.85 | 0 | RETROFITTING | 95 | Delayed | 77 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 16.08 | 16.08
336 | Laying of additional pipe line for retrofitting of Kaliganj WSS for installation of FHTC. (SM/09149) | SM/09149 | 7.36 | 0 | RETROFITTING | 95 | Delayed | 89 | 29/10/2021 | 31/03/2024 | 05/12/2023 | 03/11/2021 | 6.57 | 6.57
337 | Laying of additional pipe line for retrofitting of Gopalpur for installation of FHTC. (SM/09151) | SM/09151 | 9.49 | 0 | RETROFITTING | 95 | Delayed | 90 | 29/10/2021 | 31/03/2024 | 05/12/2023 | 03/11/2021 | 8.59 | 8.46
338 | Laying of additional pipe line for retrofitting of Gunabari for installation of FHTC. (SM/09124) | SM/09124 | 6.72 | 0 | RETROFITTING | 95 | Delayed | 75 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 17/11/2021 | 5.03 | 5.03
339 | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. (SM/07933) | SM/07933 | 222.19 | 9023 | ANGANWADI | 95 | Delayed | 0 | 19/01/2021 | 16/11/2023 | 07/07/2023 | 24/06/2021 | 0 | 0
340 | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme (SM/06723) | SM/06723 | 99.83 | 1788 | RETROFITTING | 95 | Delayed | 100 | 18/09/2020 | 31/03/2024 | 09/01/2024 | 16/10/2020 | 99.83 | 48.76
341 | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) (SM/07384) | SM/07384 | 51.74 | 841 | RETROFITTING | 96 | On track | 79 | 27/11/2020 | 31/03/2024 | 09/01/2024 | 04/02/2021 | 40.78 | 40.78
342 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09190) | SM/09190 | 47.07 | 725 | RETROFITTING | 96 | On track | 51 | 28/10/2021 | 31/03/2024 | 09/01/2024 | 02/11/2021 | 24.17 | 24.17
343 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09174) | SM/09174 | 55.54 | 855 | RETROFITTING | 96 | On track | 62 | 28/10/2021 | 31/03/2024 | 05/12/2023 | 02/11/2021 | 34.34 | 34.34
344 | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09173) | SM/09173 | 24.36 | 375 | RETROFITTING | 97 | On track | 92 | 28/10/2021 | 31/03/2024 | 05/12/2023 | 02/11/2021 | 22.53 | 22.53
345 | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. (SM/09171) | SM/09171 | 17.94 | 280 | RETROFITTING | 98 | On track | 91 | 28/10/2021 | 31/03/2024 | 05/12/2023 | 02/11/2021 | 16.28 | 16.28
346 | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block (SM/07385) | SM/07385 | 88.74 | 1481 | RETROFITTING | 99 | On track | 74 | 27/11/2020 | 31/03/2024 | 05/12/2023 | 09/12/2020 | 65.88 | 55.64
347 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. (SM/09175) | SM/09175 | 50.13 | 775 | RETROFITTING | 99 | On track | 89 | 28/10/2021 | 31/03/2024 | 05/12/2023 | 02/11/2021 | 44.72 | 44.72
348 | Laying of additional pipe line for retrofitting of Goagaon for installation of FHTC. (SM/09123) | SM/09123 | 3.47 | 0 | RETROFITTING | 99 | On track | 78 | 29/10/2021 | 31/03/2024 | 09/01/2024 | 12/11/2021 | 2.69 | 2.69
349 | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block (SM/07072) | SM/07072 | 60.91 | 1139 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/06/2022 | 12/06/2023 | 01/11/2020 | 60.91 | 42.05
350 | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme (SM/07142) | SM/07142 | 91.79 | 1788 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 16/11/2023 | 04/10/2023 | 11/12/2020 | 91.79 | 76.88
351 | Laying of additional pipe line for retrofitting of Udaypur for installation of FHTC. (SM/09158) | SM/09158 | 15.69 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 28/12/2023 | 16/10/2023 | 03/11/2021 | 15.2 | 15.2
352 | Laying of additional pipe line for retrofitting of Baruna WSS for installation of FHTC. (SM/09142) | SM/09142 | 5.32 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 5.15 | 5.15
353 | Laying of additional pipe line for retrofitting of Bheur WSS for installation of FHTC. (SM/09147) | SM/09147 | 9.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2023 | 16/10/2023 | 03/11/2021 | 8.81 | 8.81
354 | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). (SM/09111) | SM/09111 | 8.11 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 12/11/2021 | 7.8 | 7.8
355 | Restoration of Pipe Line for providing FHTC for Barua Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10448) | SM/10448 | 11.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 11/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 10.93 | 10.91
356 | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10426) | SM/10426 | 10.57 | 0 | RETROFITTING | 100 | 100% Physical | 95 | 08/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 10.07 | 10.07
357 | Restoration of Pipe line for providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10465) | SM/10465 | 5.97 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 5.79 | 5.79
358 | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme (SM/07140) | SM/07140 | 72.75 | 1458 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/11/2023 | 04/10/2023 | 11/12/2020 | 72.75 | 55.78
359 | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme (SM/06726) | SM/06726 | 76.53 | 1218 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 30/06/2022 | 12/06/2023 | 16/10/2020 | 76.53 | 69.91
360 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09177) | SM/09177 | 16.25 | 250 | RETROFITTING | 100 | 100% Physical | 89 | 28/10/2021 | 30/06/2022 | 12/06/2023 | 02/11/2021 | 14.41 | 14.41
361 | Laying of additional pipe line for retrofitting of Poaltair WSS for installation of FHTC. (SM/09144) | SM/09144 | 16.4 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 15.9 | 15.9
362 | Laying of additional pipe line for retrofitting of Maslandapur for installation of FHTC. (SM/09166) | SM/09166 | 19.84 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 19.22 | 19.22
363 | Laying of additional pipe line for retrofitting of Mahammadpur WSS for installation of FHTC. (SM/09117) | SM/09117 | 18.81 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 29/12/2023 | 16/10/2023 | 17/11/2021 | 18.06 | 18.06
364 | Restoration of Pipe Line for Retrofitting FHTC of Mahadevpur Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10450) | SM/10450 | 9.67 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 11/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 9.37 | 9.37
365 | Restoration of Damaged Pipe Line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10487) | SM/10487 | 16.04 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 15.56 | 15.56
366 | Solarisation of WBSEDCL energised Pump house with Supply and Installation of Grid Connected Rooftop solar PV systems with Net metering for Sahavita water Supply scheme in the district of Uttar Dinajpur under malda Mechanical Division, PHE Dte. (SM/10232) | SM/10232 | 5.87 | 0 | SOLARISATION | 100 | 100% Physical | 0 | 24/02/2022 | 31/10/2023 | 12/06/2023 | 28/03/2022 | 0 | 0
367 | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. (SM/09113) | SM/09113 | 7.24 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 17/11/2021 | 7 | 7
368 | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block (SM/07071) | SM/07071 | 94.34 | 1847 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/06/2022 | 12/06/2023 | 11/12/2020 | 94.34 | 69.25
369 | Laying of additional pipe line for retrofitting of Nalbithi for installation of FHTC. (SM/09155) | SM/09155 | 8.45 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 8.19 | 8.19
370 | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme (SM/07139) | SM/07139 | 72.77 | 1389 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 23/11/2023 | 04/10/2023 | 11/12/2020 | 72.77 | 69.78
371 | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme (SM/06725) | SM/06725 | 90.72 | 1651 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 23/08/2023 | 12/09/2023 | 16/10/2020 | 90.72 | 82.56
372 | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme (SM/06729) | SM/06729 | 76.33 | 1302 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 16/10/2020 | 76.33 | 76.33
373 | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme (SM/06731) | SM/06731 | 75.13 | 1281 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 16/11/2023 | 04/10/2023 | 16/10/2020 | 75.13 | 40.83
374 | Laying of additional pipe line for retrofitting of Kotar for installation of FHTC. (SM/09169) | SM/09169 | 7.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 7.1 | 7.1
375 | Laying of additional pipe line for retrofitting of Sripur for installation of FHTC. (SM/09163) | SM/09163 | 9.78 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 9.24 | 9.24
376 | Laying of additional pipe line for retrofitting of Tungail for installation of FHTC. (SM/09164) | SM/09164 | 4.69 | 0 | RETROFITTING | 100 | 100% Physical | 68 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 12/11/2021 | 3.17 | 3.17
377 | Laying of additional pipe line for retrofitting of Pakhuriya for installation of FHTC. (SM/09165) | SM/09165 | 33.01 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 24/11/2023 | 16/10/2023 | 03/11/2021 | 31.79 | 31.67
378 | Laying of additional pipe line for retrofitting of Phulatti WSS for installation of FHTC. (SM/09146) | SM/09146 | 6.77 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 6.56 | 6.56
379 | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. (SM/09115) | SM/09115 | 11.97 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 12/11/2021 | 11.61 | 11.61
380 | Restoration of Pipe line for providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10495) | SM/10495 | 4.99 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 30/11/2022 | 12/06/2023 | 11/05/2022 | 4.83 | 4.83
381 | Restoration of Pipe line for providing FHTC for Bindol Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/18993) | SM/18993 | 10.57 | 1875 | RETROFITTING | 100 | 100% Physical | 80 | 17/10/2023 |  | 11/03/2024 | 17/10/2023 | 8.41 | 8.41
382 | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme (SM/07146) | SM/07146 | 60.22 | 1125 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/12/2021 | 12/06/2023 | 11/12/2020 | 60.22 | 53.64
383 | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem (SM/06728) | SM/06728 | 80.84 | 1175 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 16/10/2020 | 80.84 | 77.01
384 | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme (SM/06730) | SM/06730 | 85.81 | 1452 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 16/10/2020 | 85.81 | 81.09
385 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. (SM/09179) | SM/09179 | 21.4 | 330 | RETROFITTING | 100 | 100% Physical | 98 | 28/10/2021 | 30/11/2022 | 12/06/2023 | 02/11/2021 | 21.07 | 19.81
386 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09180) | SM/09180 | 18.97 | 295 | RETROFITTING | 100 | 100% Physical | 94 | 28/10/2021 |  | 12/06/2023 | 14/09/2021 | 17.87 | 18.42
387 | Laying of additional pipe line for retrofitting of Bamair WSS for installation of FHTC. (SM/09143) | SM/09143 | 9.08 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 8.78 | 8.78
388 | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. (SM/09121) | SM/09121 | 10.93 | 0 | RETROFITTING | 100 | 100% Physical | 86 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 12/11/2021 | 9.44 | 9.44
389 | Restoration of Pipe line for providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10499) | SM/10499 | 8.06 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 29/12/2023 | 04/10/2023 | 12/05/2022 | 7.73 | 7.73
390 | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme (SM/07143) | SM/07143 | 50.55 | 1004 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 23/11/2023 | 04/10/2023 | 11/12/2020 | 50.55 | 56.87
391 | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme (SM/07144) | SM/07144 | 89.5 | 1740 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/12/2021 | 12/06/2023 | 11/12/2020 | 89.5 | 84.6
392 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09172) | SM/09172 | 24.16 | 375 | RETROFITTING | 100 | 100% Physical | 96 | 28/10/2021 |  | 12/06/2023 | 02/11/2021 | 23.25 | 23.24
393 | Laying of additional pipe line for retrofitting of Pirojpur for installation of FHTC. (SM/09157) | SM/09157 | 11.58 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 11.21 | 11.21
394 | Laying of additional pipe line for retrofitting of Malgaon for installation of FHTC. (SM/09162) | SM/09162 | 14.14 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 24/12/2021 | 13.63 | 13.63
395 | Laying of additional pipe line for retrofitting of Siripur for installation of FHTC. (SM/09136) | SM/09136 | 8.46 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 17/11/2021 | 8.21 | 8.21
396 | Laying of additional pipe line for retrofitting of Gutin WSS for installation of FHTC. (SM/09141) | SM/09141 | 9.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 8.79 | 8.79
397 | Laying of additional pipe line for retrofitting of SridharpurWSS for installation of FHTC. (SM/09150) | SM/09150 | 11.73 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 11.28 | 11.28
398 | Restoration of Pipe line for providing FHTC for Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10466) | SM/10466 | 8.52 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 8.24 | 8.16
399 | Restoration of Pipe Line for Retrofitting FHTC of Deona Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10427) | SM/10427 | 2.08 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 08/04/2022 | 30/11/2022 | 12/06/2023 | 11/05/2022 | 1.96 | 1.96
400 | Restoration of Pipe line for providing FHTC for Sahavita Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10443) | SM/10443 | 8.95 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 29/12/2023 | 05/12/2023 | 12/05/2022 | 8.68 | 8.68
401 | Restoration of Pipe line for providing FHTC for Bheur Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10497) | SM/10497 | 6.78 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 29/12/2023 | 04/10/2023 | 12/05/2022 | 6.54 | 6.54
402 | Restoration of Pipe line for providing FHTC for Bamair Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10493) | SM/10493 | 3.62 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 30/11/2022 | 12/06/2023 | 11/05/2022 | 3.51 | 3.51
403 | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme (SM/06727) | SM/06727 | 85.49 | 1506 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 30/11/2022 | 12/06/2023 | 16/10/2020 | 85.49 | 77.46
404 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09178) | SM/09178 | 25.46 | 392 | RETROFITTING | 100 | 100% Physical | 100 | 28/10/2021 | 16/11/2023 | 05/12/2023 | 02/11/2021 | 25.46 | 25.46
405 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09185) | SM/09185 | 28.92 | 448 | RETROFITTING | 100 | 100% Physical | 78 | 28/10/2021 | 30/06/2022 | 12/06/2023 | 02/11/2021 | 22.57 | 22.57
406 | Laying of additional pipe line for retrofitting of Paharajpur WSS for installation of FHTC. (SM/09145) | SM/09145 | 8.7 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 24/12/2021 | 8.18 | 8.18
407 | Laying of additional pipe line for retrofitting of Mahinagar for installation of FHTC. (SM/09156) | SM/09156 | 5.87 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 03/11/2021 | 5.66 | 5.66
408 | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). (SM/09109) | SM/09109 | 20.54 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 17/11/2021 | 19.82 | 19.82
409 | Laying of additional pipe line for retrofitting of Majhihar WSS for installation of FHTC. (SM/09110) | SM/09110 | 9.77 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 12/11/2021 | 9.45 | 9.45
410 | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). (SM/09127) | SM/09127 | 11.28 | 0 | RETROFITTING | 100 | 100% Physical | 53 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 17/11/2021 | 6 | 5.76
411 | Restoration of Pipe line for providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10446) | SM/10446 | 6.2 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 29/12/2023 | 05/12/2023 | 12/05/2022 | 6.02 | 6.02
412 | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. (SM/09160) | SM/09160 | 16.43 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 15.95 | 15.93
413 | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme (SM/07145) | SM/07145 | 57.58 | 1291 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/11/2022 | 12/06/2023 | 11/12/2020 | 57.58 | 56.72
414 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09192) | SM/09192 | 21.06 | 325 | RETROFITTING | 100 | 100% Physical | 87 | 28/10/2021 | 31/03/2022 | 12/06/2023 | 02/11/2021 | 18.24 | 18.24
415 | Laying of additional pipe line for retrofitting of Surun for installation of FHTC. (SM/09168) | SM/09168 | 10.3 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 9.96 | 9.96
416 | Laying of additional pipe line for retrofitting of Biprit WSS for installation of FHTC. (SM/09133) | SM/09133 | 1.42 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 12/11/2021 | 1.37 | 1.37
417 | Laying of additional pipe line for retrofitting of Debiganj for installation of FHTC. (SM/09137) | SM/09137 | 2.64 | 0 | RETROFITTING | 100 | WO no issued | 0 | 29/10/2021 | 31/08/2023 | 12/06/2023 |  | 0 | 0
418 | Laying of additional pipe line for retrofitting of Majlishpur for installation of FHTC. (SM/09140) | SM/09140 | 2.23 | 0 | RETROFITTING | 100 | 100% Physical | 0 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 12/11/2021 | 0 | 0
419 | Laying of additional pipe line for retrofitting of Chotparua WSS for installation of FHTC. (SM/09148) | SM/09148 | 9.65 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 03/11/2021 | 9.34 | 9.34
420 | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. (SM/09118) | SM/09118 | 21.78 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 17/11/2021 | 21.14 | 21.07
421 | Restoration of Pipe line for providing FHTC for Kaliganj Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10464) | SM/10464 | 7.77 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 31/03/2024 | 05/12/2023 | 31/03/2023 | 7.45 | 7.44
422 | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme (SM/06722) | SM/06722 | 99.82 | 1763 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 16/11/2023 | 04/10/2023 | 16/10/2020 | 99.82 | 76.36
423 | Restoration of Pipe Line for providing FHTC for Lodhan Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10425) | SM/10425 | 5.68 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 08/04/2022 | 30/11/2022 | 12/06/2023 | 12/05/2022 | 5.44 | 5.44
424 | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme (SM/06724) | SM/06724 | 91.76 | 1573 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 23/11/2023 | 05/12/2023 | 16/10/2020 | 91.76 | 83.29
425 | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. (SM/09170) | SM/09170 | 22.39 | 345 | RETROFITTING | 100 | 100% Physical | 100 | 28/10/2021 |  | 12/06/2023 | 02/11/2021 | 22.28 | 22.28
426 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09176) | SM/09176 | 20.04 | 309 | RETROFITTING | 100 | 100% Physical | 92 | 28/10/2021 |  | 12/06/2023 | 02/11/2021 | 18.5 | 18.5
427 | Laying of additional pipe line for retrofitting of Piplan for installation of FHTC. (SM/09161) | SM/09161 | 8.07 | 0 | RETROFITTING | 100 | 100% Physical | 95 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 03/11/2021 | 7.69 | 7.69
428 | Laying of additional pipe line for retrofitting of Purba Durlavpur WSS for installation of FHTC. (SM/09112) | SM/09112 | 11.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/06/2022 | 12/06/2023 | 12/11/2021 | 10.75 | 10.75
429 | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. (SM/09119) | SM/09119 | 17.05 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 17/11/2021 | 16.45 | 16.45
430 | Restoration of Pipe line for providing FHTC for Sripur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10441) | SM/10441 | 5.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/03/2024 | 05/12/2023 | 12/05/2022 | 5.15 | 5.15
431 | Laying of additional pipe line for retrofitting of Noabari for installation of FHTC. (SM/09159) | SM/09159 | 14.36 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 30/11/2022 | 12/06/2023 | 03/11/2021 | 13.86 | 13.86
Total |  |  | 186109.06 | 634085 | [8 empty] | 44055.53 | 41213.16