## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/18910) | SM/18910 | 133.47 | 0 | AUGMENTATION | 0 | WO no issued | 0 | 09/10/2023 | 09/04/2024 | 09/10/2023 |  | 0 | 0
2 | Providing Functional Household Tap Connection (FHTC) under command area of Panchanadapur and Hamidpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11913) | SM/11913 | 324.56 | 6480 | RETROFITTING | 0 | WO no issued | 0 | 22/08/2022 | 31/10/2023 | 12/06/2023 | 14/08/2023 | 0 | 0
3 | PARO PWSS (SM/12195) | SM/12195 | 442.87 | 1995 | NEW | 0 | WO no issued | 4 | 07/09/2022 | 31/03/2024 | 12/06/2023 | 18/07/2023 | 19.14 | 6.43
4 | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10241) | SM/10241 | 106.94 | 0 | SCHOOL | 0 | WO no issued | 0 | 24/02/2022 |  | 25/02/2022 | 06/04/2022 | 0 | 0
5 | KISMAT BAROL Piped Water Supply Scheme (SM/12190) | SM/12190 | 605.67 | 2326 | NEW | 0 | WO no issued | 9 | 07/09/2022 | 31/03/2024 | 12/06/2023 | 06/06/2023 | 57.43 | 57.43
6 | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11911) | SM/11911 | 883.96 | 15538 | RETROFITTING | 0 | WO no issued | 0 | 22/08/2022 | 31/10/2023 | 12/06/2023 | 14/08/2023 | 0 | 0
7 | Providing Functional Household Tap Connection (FHTC) under command area of Paramanandapur, Biswambhar Binodpur, Bishnupur Shrirampara, Kamalpur, Paschim Narayanpur, Enayetpur and Gouripurr Zone Water Supply Scheme at Manikchak Block under Malda Arsenic Ar (SM/11917) | SM/11917 | 490.7 | 7515 | RETROFITTING | 0 | WO no issued | 0 | 22/08/2022 | 22/11/2022 | 12/06/2023 | 14/08/2023 | 0 | 0
8 | PERAPUR PWSS (SM/18420) | SM/18420 | 1202.32 | 3213 | NEW | 0 | WO no issued | 0 | 18/07/2023 | 18/07/2025 | 20/07/2023 | 08/08/2023 | 2.04 | 2.04
9 | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11914) | SM/11914 | 198.97 | 3749 | RETROFITTING | 0 | WO no issued | 0 | 22/08/2022 | 31/10/2023 | 12/06/2023 | 14/08/2023 | 0 | 0
10 | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/10430) | SM/10430 | 546.45 | 12750 | RETROFITTING | 0 | WO no issued | 0 | 12/04/2022 | 12/07/2022 | 12/06/2023 | 14/08/2023 | 0 | 0
11 | SOURCE AUGMENTATION TROUGH INTRODUCING ROLLING TYPE BARGE FOR RAW WATER LIFTING FROM RIVER FULHAR AT INTAKE STATION OF BALUPUR WATER SUPPLY SCHEME UNDER RATUA-I BLOCK IN THE DISTRICT OF MALDA UNDER MALDA MECHANICAL DIVISION, PHE DTE. (SM/18911) | SM/18911 | 109.49 | 0 | AUGMENTATION | 0 | WO no issued | 0 | 09/10/2023 | 09/04/2024 | 09/10/2023 | 07/03/2024 | 0 | 0
12 | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/16382) | SM/16382 | 989.61 | 500 | AUGMENTATION | 0 | WO no issued | 8 | 28/02/2023 | 31/03/2024 | 12/06/2023 | 11/08/2023 | 75.39 | 75.39
13 | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. (SM/10733) | SM/10733 | 13.14 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 19/05/2022 |  | 19/05/2022 | 03/07/2022 | 0 | 0
14 | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. (SM/12272) | SM/12272 | 46.86 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 09/09/2022 |  | 12/09/2022 | 31/08/2021 | 0 | 0
15 | Drinking water samples collection & testing through Field Test Kit (FTKs) & uploading charges related to Water Quality Monitoring & Surveillance programme under JJM in the district of Malda under Malda Division. (SM/08972) | SM/08972 | 20.92 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 03/01/2022 | 0 | 0
16 | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. (SM/12119) | SM/12119 | 6.25 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 06/09/2022 |  | 11/09/2022 | 21/01/2022 | 0 | 0
17 | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Malda District. (SM/08973) | SM/08973 | 11.43 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 21/02/2022 | 0 | 0
18 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Malda District. (SM/09645) | SM/09645 | 338.24 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 23/11/2021 |  | 25/11/2021 | 18/08/2022 | 0 | 0
19 | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19086) | SM/19086 | 76.24 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 | 15/03/2024 | 0 | 0
20 | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission (SM/18275) | SM/18275 | 136.69 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 23/06/2023 |  | 27/06/2023 | 06/12/2023 | 0 | 0
21 | Procurement of chemicals & consumables, glassware etc. required for smooth running of the laboratories under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/06639) | SM/06639 | 7.76 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/02/2020 |  | 31/05/2021 | 10/06/2020 | 0 | 0
22 | Procurement of Computer and peripherals for office use in Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. (SM/10479) | SM/10479 | 7.66 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 13/04/2022 |  | 18/04/2022 | 22/06/2022 | 0 | 0
23 | Procurement of chemicals, Instruments and glassware including Annual Computer Maintenance and peripherals for Dariapur Water Treatment Plant Laboratory under Malda Arsenic Area Water Supply Division, P.H.E.Dte (SM/12843) | SM/12843 | 23.84 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 22/09/2022 |  | 23/09/2022 |  | 0 | 0
24 | Supply, Delivery and Installation of Computer & peripherals through GEMS for official use under office of the Executive Engineer, Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11869) | SM/11869 | 7.18 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 17/08/2022 |  | 18/08/2022 | 20/11/2022 | 0 | 0
25 | KHARANGAPUR JABRA Piped Water Supply Scheme (SM/12183) | SM/12183 | 273.29 | 781 | NEW | 1 | WO no issued | 6 | 07/09/2022 | 31/03/2024 | 07/07/2023 | 17/02/2023 | 15.97 | 15.97
26 | PARAHAR PWSS (SM/18432) | SM/18432 | 1277.12 | 2983 | NEW | 1 | WO no issued | 1 | 18/07/2023 | 18/07/2025 | 07/03/2024 | 02/08/2023 | 14.31 | 14.31
27 | DAKSHIN BHAKURIA Piped Water Supply Scheme (SM/12186) | SM/12186 | 312.99 | 969 | NEW | 1 | WO no issued | 6 | 06/09/2022 | 31/03/2024 | 28/06/2023 | 17/11/2022 | 18.99 | 9.57
28 | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) (SM/15142) | SM/15142 | 622.76 | 0 | AUGMENTATION | 2 | WO no issued | 85 | 06/02/2023 | 31/03/2024 | 21/07/2023 | 15/02/2023 | 529.15 | 503.28
29 | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11587) | SM/11587 | 510.87 | 1395 | NEW | 2 | WO no issued | 12 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 22/03/2022 | 61.74 | 41.31
30 | PARAIL PWSS (SM/18431) | SM/18431 | 1203.22 | 3263 | NEW | 2 | WO no issued | 2 | 18/07/2023 | 18/07/2025 | 14/03/2024 | 07/08/2023 | 29.37 | 25.94
31 | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11912) | SM/11912 | 303.28 | 5765 | RETROFITTING | 3 | WO no issued | 0 | 22/08/2022 | 31/12/2024 | 17/05/2024 | 14/08/2023 | 0 | 0
32 | KHARBA PIPED WATER SUPPLY SCHEME. (SM/13793) | SM/13793 | 1072.98 | 5400 | NEW | 3 | WO no issued | 39 | 22/11/2022 | 31/03/2024 | 22/08/2023 | 20/03/2023 | 423.82 | 414.69
33 | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. (SM/15960) | SM/15960 | 49.53 | 106 | NEW | 4 | WO no issued | 2 | 22/02/2023 | 22/08/2024 | 29/02/2024 | 30/03/2023 | 1.03 | 1.03
34 | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED (SM/18418) | SM/18418 | 1309.89 | 3327 | NEW | 4 | WO no issued | 4 | 13/07/2023 | 13/07/2025 | 04/04/2024 | 01/08/2023 | 49.87 | 31.05
35 | Augmentation of Jatradanga Piped water supply scheme (SM/12734) | SM/12734 | 390.21 | 1133 | AUGMENTATION | 4 | WO no issued | 18 | 20/09/2022 | 31/03/2023 | 12/06/2023 | 28/12/2020 | 70.95 | 70.95
36 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) (SM/10234) | SM/10234 | 514.63 | 0 | ANGANWADI | 5 | WO no issued | 0 | 24/02/2022 | 30/09/2023 | 26/07/2023 | 01/04/2022 | 0 | 0
37 | MATIHARPUR Piped Water Supply Scheme (SM/12769) | SM/12769 | 929.69 | 3531 | NEW | 5 | WO no issued | 21 | 20/09/2022 | 31/03/2024 | 12/06/2023 | 10/03/2023 | 194.66 | 194.66
38 | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED (SM/15140) | SM/15140 | 768.6 | 2662 | NEW | 5 | WO no issued | 10 | 06/02/2023 | 31/03/2024 | 13/09/2023 | 04/05/2023 | 74.71 | 74.71
39 | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED (SM/15949) | SM/15949 | 734.03 | 2088 | NEW | 5 | WO no issued | 2 | 22/02/2023 | 31/03/2024 | 02/02/2024 | 06/04/2023 | 14.35 | 14.35
40 | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) (SM/10202) | SM/10202 | 609.64 | 0 | ANGANWADI | 5 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 29/11/2023 | 01/04/2022 | 0 | 0
41 | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE (SM/11916) | SM/11916 | 496.83 | 11515 | RETROFITTING | 5 | WO no issued | 15 | 22/08/2022 | 31/07/2023 | 27/06/2023 | 10/05/2022 | 76.44 | 76.44
42 | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED (SM/12708) | SM/12708 | 545.51 | 1867 | NEW | 5 | WO no issued | 22 | 20/09/2022 | 31/03/2024 | 07/07/2023 | 12/09/2022 | 117.45 | 117.45
43 | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED (SM/13451) | SM/13451 | 794.47 | 2345 | NEW | 5 | WO no issued | 11 | 02/11/2022 | 31/03/2024 | 07/07/2023 | 08/09/2022 | 86.35 | 86.35
44 | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED (SM/12709) | SM/12709 | 705.84 | 2904 | NEW | 5 | WO no issued | 13 | 20/09/2022 | 31/03/2024 | 07/07/2023 | 12/09/2022 | 95 | 95
45 | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10238) | SM/10238 | 842.66 | 0 | SCHOOL | 5 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 27/07/2023 | 22/04/2022 | 0 | 0
46 | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11915) | SM/11915 | 645.62 | 12637 | RETROFITTING | 5 | WO no issued | 3 | 22/08/2022 | 31/03/2024 | 01/02/2024 | 14/08/2023 | 22.09 | 22.09
47 | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. (SM/10386) | SM/10386 | 558.44 | 0 | SCHOOL | 6 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 08/12/2023 | 18/01/2021 | 0 | 0
48 | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED (SM/15141) | SM/15141 | 131.66 | 550 | AUGMENTATION | 6 | WO no issued | 50 | 06/02/2023 | 31/03/2024 | 31/08/2023 | 27/09/2022 | 65.88 | 65.88
49 | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte (SM/15521) | SM/15521 | 1310.98 | 4378 | NEW | 6 | WO no issued | 1 | 16/02/2023 | 27/09/2024 | 05/03/2024 | 04/05/2023 | 14.32 | 14.32
50 | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) (SM/18660) | SM/18660 | 80427.62 | 0 | AUGMENTATION | 6 | WO no issued | 16 | 04/08/2023 | 04/02/2025 | 10/01/2024 | 14/08/2023 | 13087.15 | 11672.82
51 | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14097) | SM/14097 | 1023.19 | 3524 | NEW | 7 | WO no issued | 16 | 15/12/2022 | 31/03/2024 | 10/08/2023 | 22/03/2022 | 160.03 | 160.03
52 | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED (SM/15946) | SM/15946 | 507.92 | 858 | NEW | 7 | WO no issued | 10 | 22/02/2023 | 31/07/2024 | 15/05/2024 | 14/07/2023 | 52.25 | 4.37
53 | RAJARAM CHAK PIPED WATER SUPPLY SCHEME (SM/14461) | SM/14461 | 440.06 | 1274 | NEW | 7 | WO no issued | 33 | 20/01/2023 | 31/03/2025 | 24/04/2024 | 20/03/2023 | 146 | 138.16
54 | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. (SM/17177) | SM/17177 | 967 | 2406 | NEW | 7 | WO no issued | 16 | 15/03/2023 | 31/03/2024 | 12/06/2023 | 28/03/2023 | 158.82 | 158.82
55 | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. (SM/12267) | SM/12267 | 654.95 | 2534 | NEW | 7 | WO no issued | 38 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 08/06/2023 | 249.36 | 249.36
56 | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12317) | SM/12317 | 268.41 | 1275 | AUGMENTATION | 7 | WO no issued | 32 | 09/09/2022 | 31/03/2024 | 20/09/2023 | 10/11/2022 | 85.62 | 85.62
57 | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. (SM/13721) | SM/13721 | 1066.35 | 2846 | NEW | 8 | WO no issued | 5 | 17/11/2022 | 31/12/2024 | 06/03/2024 | 11/08/2023 | 56.19 | 36.88
58 | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15308) | SM/15308 | 853.57 | 340 | AUGMENTATION | 8 | WO no issued | 12 | 10/02/2023 | 31/03/2024 | 04/01/2024 | 03/05/2023 | 101.06 | 101.06
59 | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED (SM/15950) | SM/15950 | 491.4 | 850 | NEW | 8 | WO no issued | 12 | 22/02/2023 | 31/03/2024 | 16/10/2023 | 24/03/2023 | 60.52 | 36.77
60 | BANGRUA PWSS (SM/12193) | SM/12193 | 265.83 | 900 | NEW | 8 | WO no issued | 9 | 07/09/2022 | 31/03/2024 | 13/10/2023 | 17/02/2023 | 24.64 | 17.42
61 | Uttar Mahinagar Piped Water Supply Scheme (SM/12765) | SM/12765 | 377.31 | 919 | NEW | 8 | WO no issued | 44 | 20/09/2022 | 31/03/2024 | 15/12/2023 | 22/03/2023 | 166.45 | 166.45
62 | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14420) | SM/14420 | 164.92 | 0 | AUGMENTATION | 8 | WO no issued | 5 | 20/01/2023 | 31/03/2024 | 16/10/2023 | 02/02/2023 | 7.48 | 7.48
63 | BETAHAL Piped Water Supply Scheme (SM/12191) | SM/12191 | 473.27 | 1550 | NEW | 8 | WO no issued | 24 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 17/11/2022 | 112.56 | 112.56
64 | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme (SM/14099) | SM/14099 | 1983.76 | 5251 | AUGMENTATION | 8 | WO no issued | 4 | 15/12/2022 | 31/03/2024 | 17/10/2023 | 24/07/2023 | 72.97 | 72.97
65 | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. (SM/06637) | SM/06637 | 89.78 | 0 | SUPPORT-WQMSP | 8 | WO no issued | 0 | 05/02/2020 | 31/03/2024 | 24/11/2023 | 31/05/2022 | 0 | 0
66 | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit (SM/07971) | SM/07971 | 36.36 | 0 | SUPPORT-WQMSP | 8 | WO no issued | 0 | 21/01/2021 | 31/03/2024 | 10/11/2023 | 19/05/2021 | 0 | 0
67 | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED (SM/17178) | SM/17178 | 855.71 | 2134 | NEW | 9 | WO no issued | 9 | 15/03/2023 | 31/03/2024 | 01/02/2024 | 01/08/2023 | 77.55 | 66.67
68 | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/15944) | SM/15944 | 571.17 | 833 | NEW | 9 | WO no issued | 26 | 22/02/2023 | 01/08/2024 | 30/11/2023 | 01/08/2023 | 148.26 | 148.26
69 | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED (SM/15947) | SM/15947 | 875.39 | 2472 | NEW | 9 | WO no issued | 1 | 22/02/2023 | 31/12/2024 | 04/04/2024 | 01/08/2023 | 12.38 | 12.38
70 | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10237) | SM/10237 | 530.47 | 0 | ANGANWADI | 9 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 29/11/2023 | 01/04/2022 | 0 | 0
71 | SUJAPUR PIPED WATER SUPPLY SCHEME (SM/15962) | SM/15962 | 579.04 | 1287 | NEW | 9 | WO no issued | 12 | 22/02/2023 | 31/03/2024 | 15/01/2024 | 07/06/2023 | 71.93 | 71.93
72 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) (SM/10235) | SM/10235 | 546.3 | 0 | ANGANWADI | 9 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 20/09/2023 | 01/04/2022 | 0 | 0
73 | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block (SM/10233) | SM/10233 | 570.05 | 0 | ANGANWADI | 10 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 23/11/2023 | 23/05/2022 | 0 | 0
74 | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) (SM/10205) | SM/10205 | 492.74 | 0 | SCHOOL | 10 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 09/10/2023 | 24/05/2022 | 0 | 0
75 | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/15275) | SM/15275 | 994.39 | 2458 | NEW | 10 | WO no issued | 20 | 04/02/2023 | 01/08/2024 | 27/02/2024 | 31/05/2023 | 194.86 | 194.86
76 | SERBABAR BALARAMPUR Piped Water Supply Scheme (SM/12184) | SM/12184 | 761.34 | 2967 | NEW | 10 | WO no issued | 35 | 07/09/2022 | 31/03/2024 | 12/06/2023 | 18/05/2023 | 267.86 | 246.67
77 | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/18232) | SM/18232 | 1365.35 | 2545 | NEW | 10 | WO no issued | 25 | 12/06/2023 | 31/03/2024 | 20/12/2023 | 13/07/2023 | 338.44 | 303.14
78 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block (SM/09655) | SM/09655 | 986.55 | 22779 | RETROFITTING | 10 | WO no issued | 14 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 136.77 | 136.77
79 | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED (SM/15144) | SM/15144 | 144.97 | 600 | AUGMENTATION | 10 | WO no issued | 15 | 06/02/2023 | 31/03/2024 | 20/12/2023 | 13/04/2023 | 22.36 | 22.36
80 | SAIDPUR Piped Water Supply Scheme (SM/12766) | SM/12766 | 798.32 | 2570 | NEW | 11 | WO no issued | 40 | 20/09/2022 | 31/08/2024 | 16/01/2024 | 08/06/2023 | 315.5 | 313.55
81 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) (SM/10236) | SM/10236 | 562.14 | 0 | ANGANWADI | 11 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 01/02/2024 | 01/04/2022 | 0 | 0
82 | MABARAKPUR PWSS (SM/12197) | SM/12197 | 614.73 | 2608 | NEW | 11 | WO no issued | 34 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 19/05/2023 | 211.74 | 206.19
83 | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15073) | SM/15073 | 96.31 | 0 | AUGMENTATION | 11 | WO no issued | 25 | 04/02/2023 | 31/03/2024 | 09/11/2023 | 17/02/2023 | 23.89 | 23.89
84 | Augmentation of Samsi PWSS. (SM/18447) | SM/18447 | 2165.6 | 6805 | AUGMENTATION | 11 | WO no issued | 1 | 20/07/2023 | 20/07/2024 | 20/03/2024 | 08/08/2023 | 31.67 | 31.67
85 | JAMALPUR Piped Water Supply Scheme. (SM/12879) | SM/12879 | 988.74 | 4212 | NEW | 11 | WO no issued | 18 | 23/09/2022 | 31/03/2024 | 12/06/2023 | 15/03/2023 | 178.82 | 178.82
86 | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15057) | SM/15057 | 64.27 | 0 | AUGMENTATION | 11 | WO no issued | 7 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 4.63 | 4.63
87 | FATEPUR Piped Water Supply Scheme (SM/14173) | SM/14173 | 1472.95 | 4277 | NEW | 11 | WO no issued | 10 | 09/01/2023 | 31/03/2024 | 12/06/2023 | 13/03/2023 | 141.01 | 135.99
88 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED (SM/15145) | SM/15145 | 31.42 | 0 | AUGMENTATION | 11 | WO no issued | 65 | 06/02/2023 | 06/08/2023 | 12/06/2023 | 06/03/2023 | 20.31 | 20.31
89 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED (SM/15143) | SM/15143 | 270.23 | 0 | AUGMENTATION | 11 | WO no issued | 58 | 06/02/2023 | 31/03/2024 | 14/07/2023 | 21/01/2021 | 156.48 | 156.48
90 | Augmentation of Adina Zone-I Piped Water Supply Scheme (SM/15958) | SM/15958 | 543.44 | 972 | AUGMENTATION | 12 | WO no issued | 6 | 22/02/2023 | 31/03/2024 | 12/06/2023 | 22/03/2022 | 32.19 | 32.19
91 | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division (SM/18124) | SM/18124 | 231.67 | 0 | SOLARISATION | 12 | WO no issued | 0 | 29/03/2023 | 31/03/2024 | 21/12/2023 | 07/07/2023 | 0 | 0
92 | BISHANPUR PIPED WATER SUPPLY SCHEME (SM/13507) | SM/13507 | 637.86 | 2698 | NEW | 12 | WO no issued | 35 | 02/11/2022 | 31/08/2024 | 09/01/2024 | 11/05/2023 | 224.06 | 82.29
93 | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME (SM/15188) | SM/15188 | 390.5 | 2641 | AUGMENTATION | 13 | WO no issued | 24 | 07/02/2023 | 31/03/2024 | 19/09/2023 | 21/03/2023 | 95.45 | 55.06
94 | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10387) | SM/10387 | 665.38 | 0 | SCHOOL | 13 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 11/01/2024 | 21/07/2022 | 0 | 0
95 | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme (SM/13792) | SM/13792 | 2616.08 | 11149 | AUGMENTATION | 13 | WO no issued | 11 | 22/11/2022 | 31/03/2024 | 12/06/2023 | 13/03/2023 | 288.02 | 288.02
96 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl (SM/09656) | SM/09656 | 598.68 | 13790 | RETROFITTING | 13 | WO no issued | 11 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 63.15 | 63.15
97 | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. (SM/12741) | SM/12741 | 197.49 | 0 | SUPPORT-WQMSP | 13 | WO no issued | 0 | 20/09/2022 | 31/03/2024 | 15/01/2024 | 26/08/2020 | 0 | 0
98 | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME (SM/15948) | SM/15948 | 254.87 | 733 | AUGMENTATION | 14 | WO no issued | 15 | 22/02/2023 | 31/03/2024 | 13/10/2023 | 08/06/2023 | 39.47 | 30.6
99 | Alal Zone-I Piped Water Supply Scheme (SM/12075) | SM/12075 | 732.76 | 1971 | NEW | 14 | WO no issued | 30 | 02/09/2022 | 31/03/2024 | 24/03/2024 | 22/03/2022 | 217.8 | 217.8
100 | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15083) | SM/15083 | 75.97 | 0 | AUGMENTATION | 14 | WO no issued | 15 | 04/02/2023 | 31/03/2024 | 07/08/2023 | 17/02/2023 | 11.48 | 11.48
101 | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12760) | SM/12760 | 208.4 | 0 | AUGMENTATION | 15 | WO no issued | 0 | 20/09/2022 | 31/03/2024 | 10/08/2023 | 07/12/2022 | 0.27 | 0.27
102 | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15108) | SM/15108 | 100.43 | 150 | AUGMENTATION | 15 | WO no issued | 39 | 04/02/2023 | 31/03/2024 | 11/10/2023 | 23/03/2023 | 39.39 | 39.39
103 | Augmentation of Deotala Water Supply Scheme (SM/09986) | SM/09986 | 842.06 | 2446 | AUGMENTATION | 15 | WO no issued | 22 | 16/12/2021 | 31/08/2024 | 10/01/2024 | 15/06/2021 | 182.78 | 182.78
104 | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15091) | SM/15091 | 84.27 | 0 | AUGMENTATION | 15 | WO no issued | 42 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 35.36 | 35.36
105 | Augmentation of Mahishbathani Piped Water Supply Scheme (SM/16383) | SM/16383 | 328.05 | 1587 | AUGMENTATION | 16 | WO no issued | 24 | 28/02/2023 | 31/12/2024 | 14/03/2024 | 17/05/2023 | 77.78 | 77.78
106 | DILALBATI Piped Water Supply Scheme. (SM/15903) | SM/15903 | 289.35 | 521 | NEW | 16 | WO no issued | 39 | 20/02/2023 | 31/05/2024 | 14/03/2024 | 20/03/2023 | 113.93 | 104.14
107 | MATHURAPUR PIPED WATER SUPPLY SCHEME (SM/15248) | SM/15248 | 572.13 | 2416 | NEW | 16 | WO no issued | 30 | 07/02/2023 | 31/03/2024 | 16/01/2024 | 12/05/2023 | 170.36 | 170.36
108 | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10385) | SM/10385 | 639.24 | 0 | SCHOOL | 16 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 13/09/2023 | 18/01/2021 | 0 | 0
109 | MALIOR PWSS (SM/12192) | SM/12192 | 651.07 | 2789 | NEW | 16 | WO no issued | 35 | 07/09/2022 | 31/03/2024 | 31/01/2024 | 17/11/2022 | 226.88 | 226.88
110 | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14098) | SM/14098 | 1429.91 | 4588 | NEW | 17 | WO no issued | 31 | 15/12/2022 | 31/08/2024 | 09/01/2024 | 22/03/2022 | 440.28 | 440.28
111 | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/18558) | SM/18558 | 3085.32 | 9132 | AUGMENTATION | 17 | WO no issued | 10 | 31/07/2023 | 31/12/2024 | 20/03/2024 | 09/08/2023 | 294.26 | 285.32
112 | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED (SM/17201) | SM/17201 | 714.72 | 1855 | NEW | 18 | WO no issued | 12 | 15/03/2023 | 31/03/2024 | 22/09/2023 | 30/03/2023 | 88.42 | 71.54
113 | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10216) | SM/10216 | 787.99 | 0 | ANGANWADI | 18 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 12/10/2023 | 13/06/2022 | 0 | 0
114 | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15079) | SM/15079 | 166.09 | 350 | AUGMENTATION | 19 | WO no issued | 56 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 23/03/2023 | 93.29 | 93.29
115 | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/16053) | SM/16053 | 600.59 | 125 | AUGMENTATION | 19 | WO no issued | 24 | 22/02/2023 | 31/03/2024 | 31/01/2024 | 26/04/2023 | 143.29 | 143.29
116 | SWARUPGANJ Piped Water Supply Scheme (SM/12185) | SM/12185 | 686.89 | 3192 | NEW | 19 | WO no issued | 36 | 07/09/2022 | 31/03/2024 | 24/03/2024 | 28/02/2023 | 244.78 | 244.78
117 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme (SM/06853) | SM/06853 | 61.62 | 1125 | RETROFITTING | 19 | WO no issued | 14 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 8.75 | 8.75
118 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block (SM/09661) | SM/09661 | 883.23 | 20500 | RETROFITTING | 19 | WO no issued | 18 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 156.45 | 156.45
119 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha (SM/09658) | SM/09658 | 505.89 | 11500 | RETROFITTING | 19 | WO no issued | 18 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 90.82 | 90.82
120 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc (SM/09659) | SM/09659 | 246.4 | 5400 | RETROFITTING | 20 | WO no issued | 70 | 23/11/2021 | 31/10/2023 | 23/06/2023 | 24/11/2021 | 172.28 | 172.28
121 | NABAGRAM Piped Water Supply Scheme (SM/12767) | SM/12767 | 825.74 | 3517 | NEW | 20 | WO no issued | 34 | 20/09/2022 | 31/08/2024 | 10/01/2024 | 02/05/2023 | 280.84 | 280.84
122 | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15201) | SM/15201 | 196.28 | 450 | AUGMENTATION | 20 | WO no issued | 47 | 06/02/2023 | 31/03/2024 | 03/01/2024 | 20/03/2023 | 92.15 | 92.15
123 | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15193) | SM/15193 | 961.22 | 420 | AUGMENTATION | 21 | WO no issued | 16 | 06/02/2023 | 31/10/2024 | 08/02/2024 | 02/06/2023 | 157.93 | 157.93
124 | SRI CHANDRAPUR Piped Water Supply Scheme (SM/12764) | SM/12764 | 656.15 | 2782 | NEW | 22 | WO no issued | 33 | 20/09/2022 | 31/08/2024 | 31/01/2024 | 02/05/2023 | 219.45 | 218.43
125 | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme (SM/14190) | SM/14190 | 498.84 | 1245 | AUGMENTATION | 22 | WO no issued | 7 | 10/01/2023 | 31/12/2024 | 05/04/2024 | 20/03/2023 | 36.83 | 35.53
126 | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10303) | SM/10303 | 705.27 | 0 | ANGANWADI | 22 | WO no issued | 0 | 02/03/2022 | 31/03/2024 | 10/10/2023 | 03/09/2019 | 0 | 0
127 | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda (SM/12338) | SM/12338 | 611.23 | 1607 | NEW | 22 | WO no issued | 16 | 12/09/2022 | 31/03/2024 | 12/06/2023 | 21/09/2022 | 96.67 | 77.33
128 | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte (SM/12304) | SM/12304 | 567.57 | 1823 | NEW | 22 | WO no issued | 57 | 09/09/2022 | 31/08/2024 | 09/01/2024 | 03/05/2023 | 322.17 | 316.33
129 | Sharanpur Piped Water Supply Scheme (SM/12631) | SM/12631 | 345.19 | 1080 | NEW | 22 | WO no issued | 26 | 19/09/2022 | 31/08/2024 | 31/01/2024 | 17/11/2022 | 90.28 | 90.28
130 | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15106) | SM/15106 | 149.47 | 1658 | AUGMENTATION | 22 | WO no issued | 8 | 04/02/2023 | 31/03/2024 | 06/07/2023 | 17/02/2023 | 12.02 | 12.02
131 | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10243) | SM/10243 | 503.77 | 0 | ANGANWADI | 22 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 16/10/2023 | 18/01/2021 | 0 | 0
132 | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block (SM/18685) | SM/18685 | 15363.32 | 12384 | NEW | 22 | WO no issued | 9 | 04/08/2023 | 04/02/2026 | 17/05/2024 | 11/08/2023 | 1410.04 | 1410.04
133 | Alal Zone-II Piped Water Supply Scheme (SM/12877) | SM/12877 | 596.19 | 1413 | NEW | 22 | WO no issued | 7 | 23/09/2022 | 28/02/2025 | 22/04/2024 | 22/03/2022 | 42.28 | 33.59
134 | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10380) | SM/10380 | 836.73 | 0 | ANGANWADI | 23 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 16/10/2023 | 18/01/2021 | 0 | 0
135 | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15093) | SM/15093 | 196.91 | 950 | AUGMENTATION | 23 | WO no issued | 17 | 04/02/2023 | 31/03/2024 | 11/10/2023 | 21/03/2023 | 32.68 | 32.68
136 | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10307) | SM/10307 | 570.94 | 0 | ANGANWADI | 23 | WO no issued | 0 | 02/03/2022 | 31/03/2024 | 01/08/2023 | 31/08/2022 | 0 | 0
137 | HORGOA Piped Water Supply Scheme (SM/13432) | SM/13432 | 643.41 | 1714 | NEW | 23 | WO no issued | 40 | 02/11/2022 | 31/03/2024 | 08/12/2023 | 08/05/2023 | 260.23 | 239.74
138 | Augmentation of Alal Zone-III Piped Water Supply Scheme (SM/15951) | SM/15951 | 425.25 | 683 | AUGMENTATION | 24 | WO no issued | 23 | 22/02/2023 | 31/03/2024 | 05/03/2024 | 22/03/2022 | 96.12 | 91.71
139 | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10246) | SM/10246 | 812.74 | 0 | ANGANWADI | 24 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 16/10/2023 | 03/09/2019 | 0 | 0
140 | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10305) | SM/10305 | 503.66 | 0 | ANGANWADI | 24 | WO no issued | 0 | 02/03/2022 | 31/03/2024 | 23/11/2023 | 07/09/2022 | 0 | 0
141 | BABUPUR PWSS (SM/18433) | SM/18433 | 1594.57 | 5617 | NEW | 25 | WO no issued | 33 | 18/07/2023 | 18/07/2025 | 06/03/2024 | 09/08/2023 | 531.03 | 531.03
142 | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15074) | SM/15074 | 83.83 | 0 | AUGMENTATION | 26 | WO no issued | 44 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 36.7 | 36.7
143 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc (SM/09657) | SM/09657 | 356.57 | 8012 | RETROFITTING | 26 | WO no issued | 29 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 102.56 | 102.56
144 | Augmentation of Khusida Piped Water Supply Scheme (SM/10397) | SM/10397 | 1114.1 | 4712 | AUGMENTATION | 26 | WO no issued | 34 | 31/03/2022 | 31/03/2024 | 16/01/2024 | 24/05/2022 | 376.95 | 376.95
145 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha (SM/09590) | SM/09590 | 235.98 | 5193 | RETROFITTING | 26 | WO no issued | 40 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 14/10/2020 | 95.01 | 95.01
146 | ALINAGAR Piped Water Supply Scheme (SM/13431) | SM/13431 | 683.89 | 2356 | NEW | 26 | WO no issued | 50 | 02/11/2022 | 31/03/2024 | 05/09/2023 | 27/02/2023 | 342.52 | 342.52
147 | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11590) | SM/11590 | 554.79 | 2789 | NEW | 26 | WO no issued | 33 | 22/07/2022 | 31/08/2024 | 10/01/2024 | 22/03/2022 | 184.49 | 184.49
148 | Augmentation of Maheshpur piped water supply scheme (SM/12362) | SM/12362 | 1414.74 | 0 | AUGMENTATION | 26 | WO no issued | 45 | 13/09/2022 | 31/08/2024 | 10/01/2024 | 23/12/2022 | 633.99 | 633.99
149 | Mahil Piped Water Supply Scheme (SM/13733) | SM/13733 | 1779.92 | 4895 | NEW | 27 | WO no issued | 38 | 17/11/2022 | 31/08/2024 | 10/01/2024 | 01/11/2022 | 682.24 | 647.92
150 | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15223) | SM/15223 | 2175.5 | 8288 | NEW | 27 | WO no issued | 47 | 07/02/2023 | 31/01/2025 | 15/04/2024 | 15/06/2021 | 1019.86 | 988.08
151 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme (SM/06861) | SM/06861 | 89.31 | 1675 | RETROFITTING | 28 | WO no issued | 25 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 22.71 | 22.71
152 | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. (SM/10389) | SM/10389 | 297.04 | 0 | SCHOOL | 28 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 11/12/2023 | 21/07/2022 | 0 | 0
153 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B (SM/09662) | SM/09662 | 446.64 | 10136 | RETROFITTING | 28 | WO no issued | 46 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 203.92 | 203.92
154 | Augmentation of Nasipur Piped Water Supply Scheme (SM/15952) | SM/15952 | 868.83 | 2049 | AUGMENTATION | 29 | WO no issued | 26 | 22/02/2023 | 31/12/2024 | 30/01/2024 | 14/07/2023 | 222.47 | 222.47
155 | EMAMNAGAR PIPED WATER SUPPLY SCHEME. (SM/13720) | SM/13720 | 1386.39 | 3632 | NEW | 29 | WO no issued | 55 | 17/11/2022 | 31/08/2024 | 09/01/2024 | 13/03/2023 | 762.81 | 762.81
156 | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15062) | SM/15062 | 93.1 | 0 | AUGMENTATION | 29 | WO no issued | 44 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 40.8 | 40.8
157 | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15112) | SM/15112 | 84.77 | 0 | AUGMENTATION | 30 | WO no issued | 19 | 04/02/2023 | 31/03/2024 | 11/07/2023 | 17/02/2023 | 16.09 | 6.87
158 | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME (SM/15155) | SM/15155 | 398.39 | 1413 | AUGMENTATION | 30 | WO no issued | 38 | 07/02/2023 | 31/03/2024 | 11/12/2023 | 21/03/2023 | 150.49 | 123.41
159 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT (SM/18686) | SM/18686 | 68069.12 | 56048 | NEW | 30 | WO no issued | 9 | 04/08/2023 | 04/08/2026 | 24/03/2024 | 16/08/2023 | 5963.37 | 5190.71
160 | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda (SM/12762) | SM/12762 | 142.91 | 736 | AUGMENTATION | 31 | WO no issued | 38 | 20/09/2022 | 31/08/2024 | 10/01/2024 | 07/12/2022 | 54.42 | 54.42
161 | Choupaldanga pipe water Supply Scheme (SM/12076) | SM/12076 | 790.19 | 3482 | NEW | 31 | WO no issued | 48 | 02/09/2022 | 31/08/2024 | 09/01/2024 | 13/10/2022 | 379.66 | 379.66
162 | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. (SM/12632) | SM/12632 | 293.04 | 698 | NEW | 31 | WO no issued | 43 | 19/09/2022 | 31/08/2024 | 09/01/2024 | 17/11/2022 | 127.01 | 127.01
163 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte (SM/07973) | SM/07973 | 5777.65 | 110880 | RETROFITTING | 31 | WO no issued | 26 | 26/01/2021 | 31/03/2024 | 10/01/2024 | 16/09/2020 | 1500 | 1463.1
164 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik (SM/09663) | SM/09663 | 506.2 | 12315 | RETROFITTING | 32 | WO no issued | 36 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 179.94 | 179.94
165 | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15090) | SM/15090 | 102.52 | 0 | AUGMENTATION | 32 | WO no issued | 43 | 04/02/2023 | 31/08/2024 | 10/01/2024 | 17/02/2023 | 44.26 | 44.26
166 | JIGIN Piped Water Supply Scheme (SM/13430) | SM/13430 | 213.28 | 459 | NEW | 33 | WO no issued | 64 | 02/11/2022 | 31/08/2024 | 10/01/2024 | 20/03/2023 | 136.75 | 117.71
167 | OLTARA PIPED WATER SUPPLY SCHEME. (SM/13718) | SM/13718 | 1147.12 | 3535 | NEW | 33 | WO no issued | 61 | 17/11/2022 | 31/08/2024 | 10/01/2024 | 22/03/2023 | 698.41 | 698.41
168 | Augmentation of Mirzapur Piped Water Supply Scheme (SM/10317) | SM/10317 | 875.13 | 4880 | AUGMENTATION | 33 | WO no issued | 57 | 04/03/2022 | 31/08/2024 | 10/01/2024 | 15/06/2021 | 498.26 | 498.26
169 | UTTAR BHAKURIA Piped Water Supply Scheme. (SM/12881) | SM/12881 | 80.18 | 215 | NEW | 33 | WO no issued | 52 | 23/09/2022 | 31/08/2024 | 10/01/2024 | 19/01/2023 | 41.34 | 41.34
170 | WARI Piped Water Supply Scheme (SM/12077) | SM/12077 | 944.1 | 3903 | NEW | 33 | WO no issued | 54 | 02/09/2022 | 31/08/2024 | 09/01/2024 | 14/10/2022 | 510.54 | 510.54
171 | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15102) | SM/15102 | 104.31 | 0 | AUGMENTATION | 33 | WO no issued | 41 | 04/02/2023 | 30/08/2024 | 09/01/2024 | 20/03/2023 | 43.12 | 36.96
172 | Hatinda Piped Water Supply Scheme. (SM/12078) | SM/12078 | 959.77 | 4783 | NEW | 33 | WO no issued | 45 | 02/09/2022 | 31/03/2024 | 12/06/2023 | 11/10/2022 | 432.2 | 425.58
173 | KRISHNAPUR PIPED WATER SUPPLY SCHEME. (SM/13746) | SM/13746 | 832.12 | 2560 | NEW | 34 | WO no issued | 59 | 17/11/2022 | 31/08/2024 | 10/01/2024 | 10/04/2023 | 493.4 | 493.4
174 | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12312) | SM/12312 | 131.81 | 0 | AUGMENTATION | 34 | WO no issued | 49 | 09/09/2022 | 31/08/2024 | 09/01/2024 | 03/11/2022 | 64.5 | 64.5
175 | GAURIA Piped Water Supply Scheme. (SM/12079) | SM/12079 | 916.6 | 4278 | NEW | 34 | WO no issued | 43 | 02/09/2022 | 31/08/2024 | 11/01/2024 | 22/09/2022 | 394.25 | 394.25
176 | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15111) | SM/15111 | 272.73 | 869 | AUGMENTATION | 34 | WO no issued | 40 | 04/02/2023 | 31/08/2024 | 10/01/2024 | 20/03/2023 | 107.91 | 107.91
177 | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12323) | SM/12323 | 172.5 | 1906 | AUGMENTATION | 35 | WO no issued | 39 | 09/09/2022 | 31/08/2024 | 09/01/2024 | 10/11/2022 | 66.71 | 66.71
178 | Pukuria Piped Water Supply Scheme (SM/14100) | SM/14100 | 1716.45 | 5771 | NEW | 35 | WO no issued | 21 | 15/12/2022 | 31/12/2024 | 02/04/2024 | 22/03/2022 | 355.76 | 355.76
179 | BAIRAT Piped Water Supply Scheme (SM/12743) | SM/12743 | 884.02 | 3235 | NEW | 36 | WO no issued | 58 | 20/09/2022 | 31/08/2024 | 10/01/2024 | 17/11/2022 | 509.26 | 509.26
180 | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11589) | SM/11589 | 547.19 | 1856 | NEW | 36 | WO no issued | 43 | 22/07/2022 | 31/08/2024 | 10/01/2024 | 22/03/2022 | 234.95 | 208.9
181 | ARAZI JALSA PIPED WATER SUPPLY SCHEME. (SM/13734) | SM/13734 | 1315.09 | 3312 | NEW | 36 | WO no issued | 50 | 17/11/2022 | 30/08/2024 | 09/01/2024 | 17/05/2023 | 654.51 | 647.24
182 | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) (SM/10204) | SM/10204 | 742.68 | 0 | SCHOOL | 36 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 25/07/2023 | 28/04/2022 | 0 | 0
183 | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10242) | SM/10242 | 866.48 | 0 | ANGANWADI | 37 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 07/12/2023 | 07/09/2022 | 0 | 0
184 | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15063) | SM/15063 | 124.6 | 250 | AUGMENTATION | 37 | WO no issued | 50 | 04/02/2023 | 31/08/2024 | 10/01/2024 | 21/03/2023 | 62.09 | 51.67
185 | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12315) | SM/12315 | 156.56 | 0 | AUGMENTATION | 38 | WO no issued | 48 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 10/11/2022 | 75.2 | 75.2
186 | MEHERPUR PIPED WATER SUPPLY SCHEME (SM/15222) | SM/15222 | 1107.06 | 4342 | NEW | 38 | WO no issued | 50 | 06/02/2023 | 31/08/2024 | 09/01/2024 | 13/03/2023 | 552.74 | 552.74
187 | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10215) | SM/10215 | 671.69 | 0 | ANGANWADI | 38 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 09/10/2023 | 24/06/2020 | 0 | 0
188 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl (SM/09651) | SM/09651 | 189.35 | 3940 | RETROFITTING | 39 | WO no issued | 57 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 107.65 | 107.65
189 | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10382) | SM/10382 | 521.68 | 0 | SCHOOL | 39 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 11/12/2023 | 18/01/2021 | 0 | 0
190 | MORGRAM PWSS (SM/18557) | SM/18557 | 1084.68 | 3767 | NEW | 39 | WO no issued | 22 | 31/07/2023 | 31/07/2025 | 09/02/2024 | 10/08/2023 | 235.72 | 231.18
191 | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. (SM/10383) | SM/10383 | 760.43 | 0 | SCHOOL | 39 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 01/12/2023 | 18/01/2021 | 0 | 0
192 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09650) | SM/09650 | 589.71 | 12985 | RETROFITTING | 39 | WO no issued | 37 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 12/05/2022 | 219.54 | 219.54
193 | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15110) | SM/15110 | 119.4 | 130 | AUGMENTATION | 39 | WO no issued | 41 | 04/02/2023 | 31/03/2024 | 14/10/2023 | 29/03/2023 | 48.43 | 44.3
194 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar (SM/09649) | SM/09649 | 213.41 | 4560 | RETROFITTING | 39 | WO no issued | 77 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 164.83 | 164.83
195 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme (SM/06851) | SM/06851 | 96.17 | 1811 | RETROFITTING | 39 | WO no issued | 42 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 40.32 | 31.43
196 | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15190) | SM/15190 | 103.91 | 0 | AUGMENTATION | 40 | WO no issued | 63 | 06/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 65.85 | 65.85
197 | CHAKSUKUR PIPED WATER SUPPLY SCHEME. (SM/13719) | SM/13719 | 1050.75 | 2824 | NEW | 40 | WO no issued | 53 | 17/11/2022 | 31/08/2024 | 09/01/2024 | 13/03/2023 | 557.4 | 557.4
198 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block (SM/06848) | SM/06848 | 85.66 | 1733 | RETROFITTING | 40 | WO no issued | 100 | 08/10/2020 | 30/11/2021 | 12/06/2023 | 14/10/2020 | 85.66 | 85.66
199 | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15113) | SM/15113 | 261.08 | 1251 | AUGMENTATION | 41 | WO no issued | 49 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 20/03/2023 | 129.18 | 129.18
200 | SULTANNAGAR PWSS (SM/12196) | SM/12196 | 445.36 | 1659 | NEW | 42 | WO no issued | 51 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 17/11/2022 | 228.6 | 176.71
201 | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12316) | SM/12316 | 167.81 | 1748 | AUGMENTATION | 42 | WO no issued | 49 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 03/11/2022 | 82 | 82
202 | SAHAPUR Piped Water Supply Scheme (SM/12187) | SM/12187 | 104.61 | 397 | NEW | 43 | WO no issued | 56 | 06/09/2022 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 58.75 | 58.75
203 | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15105) | SM/15105 | 212.37 | 0 | AUGMENTATION | 44 | WO no issued | 77 | 04/02/2023 | 31/08/2024 | 09/01/2024 | 17/02/2023 | 162.64 | 162.64
204 | Augmentation of Bhaluka Fatepur Piped water supply scheme (SM/10137) | SM/10137 | 944.43 | 4734 | AUGMENTATION | 44 | WO no issued | 43 | 08/02/2022 | 31/08/2024 | 10/01/2024 | 15/06/2021 | 405.1 | 405.1
205 | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12313) | SM/12313 | 132.82 | 1008 | AUGMENTATION | 44 | WO no issued | 50 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 03/11/2022 | 66.91 | 66.91
206 | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12761) | SM/12761 | 282.13 | 364 | AUGMENTATION | 45 | WO no issued | 51 | 20/09/2022 | 31/03/2025 | 09/02/2024 | 07/12/2022 | 144.73 | 144.73
207 | Augmentation of Adina Zone-II Piped Water Supply Scheme (SM/15956) | SM/15956 | 355.78 | 649 | AUGMENTATION | 45 | WO no issued | 43 | 22/02/2023 | 31/03/2024 | 03/10/2023 | 02/05/2023 | 154.42 | 154.42
208 | HATNAGAR PIPED WATER SUPPLY SCHEME (SM/18496) | SM/18496 | 1232.77 | 2677 | NEW | 45 | WO no issued | 28 | 26/07/2023 | 26/07/2025 | 01/02/2024 | 10/08/2023 | 341.13 | 332.88
209 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme (SM/06867) | SM/06867 | 92.99 | 1748 | RETROFITTING | 46 | WO no issued | 55 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 51.25 | 51.25
210 | AUGMENTATION OF MALATIPUR PWSS (SM/09987) | SM/09987 | 588.11 | 2301 | AUGMENTATION | 46 | WO no issued | 52 | 16/12/2021 | 31/08/2024 | 10/01/2024 | 01/08/2022 | 307.23 | 307.23
211 | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12305) | SM/12305 | 142.62 | 0 | AUGMENTATION | 46 | WO no issued | 49 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 20/12/2022 | 70.51 | 70.51
212 | KALUARI PWSS (SM/18427) | SM/18427 | 1366.3 | 4894 | NEW | 46 | WO no issued | 28 | 18/07/2023 | 18/07/2025 | 15/05/2024 | 08/08/2023 | 388.99 | 2.29
213 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme (SM/06862) | SM/06862 | 49.15 | 878 | RETROFITTING | 46 | WO no issued | 41 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 13/08/2021 | 20.07 | 20.07
214 | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12311) | SM/12311 | 305.67 | 1504 | AUGMENTATION | 46 | WO no issued | 42 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 10/11/2022 | 127.99 | 124.91
215 | JIBJALSAR Piped Water Supply Scheme (SM/12182) | SM/12182 | 69.34 | 146 | NEW | 47 | WO no issued | 70 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 01/11/2022 | 48.58 | 48.58
216 | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. (SM/15197) | SM/15197 | 164.65 | 0 | AUGMENTATION | 48 | WO no issued | 82 | 06/02/2023 | 31/08/2024 | 10/01/2024 | 21/02/2023 | 134.36 | 134.36
217 | Augmentation of Uttar Harishandropur piped water supply scheme. (SM/10291) | SM/10291 | 2014.31 | 8400 | AUGMENTATION | 48 | WO no issued | 33 | 28/02/2022 | 31/03/2024 | 26/09/2023 | 03/09/2019 | 654.83 | 654.61
218 | PUTIA PWSS (SM/12194) | SM/12194 | 73.96 | 132 | NEW | 48 | WO no issued | 72 | 07/09/2022 | 31/08/2024 | 10/01/2024 | 27/02/2023 | 53.51 | 53.51
219 | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12314) | SM/12314 | 124.51 | 0 | AUGMENTATION | 49 | WO no issued | 44 | 09/09/2022 | 31/08/2024 | 10/01/2024 | 20/12/2022 | 55.2 | 55.2
220 | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12763) | SM/12763 | 353.11 | 750 | AUGMENTATION | 50 | WO no issued | 45 | 20/09/2022 | 31/08/2024 | 10/01/2024 | 07/12/2022 | 158.49 | 158.41
221 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block (SM/09587) | SM/09587 | 154.36 | 3660 | RETROFITTING | 50 | WO no issued | 81 | 23/11/2021 | 31/10/2023 | 23/06/2023 | 14/09/2021 | 125.39 | 125.34
222 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl (SM/09652) | SM/09652 | 450.25 | 9700 | RETROFITTING | 50 | WO no issued | 60 | 23/11/2021 | 31/10/2023 | 23/06/2023 | 24/11/2021 | 272.23 | 272.23
223 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar (SM/09589) | SM/09589 | 67.89 | 1542 | RETROFITTING | 51 | WO no issued | 50 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 33.89 | 33.89
224 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme (SM/06850) | SM/06850 | 68.82 | 1268 | RETROFITTING | 51 | WO no issued | 46 | 07/10/2020 | 30/11/2021 | 12/06/2023 | 31/12/2021 | 32 | 24.59
225 | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem (SM/07972) | SM/07972 | 2518.77 | 47698 | RETROFITTING | 51 | WO no issued | 43 | 26/01/2021 | 31/03/2024 | 15/01/2024 | 30/09/2020 | 1094.92 | 1094.92
226 | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE (SM/10304) | SM/10304 | 597.8 | 0 | ANGANWADI | 51 | WO no issued | 0 | 02/03/2022 | 31/03/2024 | 06/12/2023 | 18/01/2021 | 0 | 0
227 | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10244) | SM/10244 | 792.59 | 0 | ANGANWADI | 52 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 09/10/2023 | 27/12/2021 | 0 | 0
228 | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. (SM/15086) | SM/15086 | 116.57 | 0 | AUGMENTATION | 52 | WO no issued | 80 | 04/02/2023 | 31/08/2024 | 10/01/2024 | 17/02/2023 | 93.75 | 93.75
229 | BHADAR Piped Water Supply Scheme (SM/12768) | SM/12768 | 621.21 | 2064 | NEW | 52 | WO no issued | 75 | 20/09/2022 | 31/08/2024 | 10/01/2024 | 17/05/2023 | 464.91 | 412.54
230 | TALPUKUR Piped Water Supply Scheme (SM/12189) | SM/12189 | 663.8 | 2190 | NEW | 53 | WO no issued | 55 | 07/09/2022 | 31/08/2024 | 09/01/2024 | 10/05/2023 | 366.73 | 366.73
231 | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME (SM/10181) | SM/10181 | 1896 | 7524 | AUGMENTATION | 53 | WO no issued | 44 | 17/02/2022 | 31/03/2024 | 26/09/2023 | 26/08/2021 | 840.28 | 817.54
232 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo (SM/09647) | SM/09647 | 363.53 | 8220 | RETROFITTING | 53 | WO no issued | 56 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 202.48 | 202.48
233 | Sanjail PWSS in Old Malda Block in District Malda (SM/12337) | SM/12337 | 342.88 | 750 | NEW | 54 | WO no issued | 74 | 12/09/2022 | 31/08/2024 | 10/01/2024 | 16/09/2022 | 254.12 | 254.12
234 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme (SM/07007) | SM/07007 | 86.07 | 1583 | RETROFITTING | 55 | WO no issued | 67 | 18/11/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 57.73 | 57.73
235 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block (SM/09591) | SM/09591 | 145.97 | 3174 | RETROFITTING | 55 | WO no issued | 58 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 84.4 | 84.4
236 | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15065) | SM/15065 | 216.09 | 0 | AUGMENTATION | 55 | WO no issued | 71 | 04/02/2023 | 31/08/2024 | 10/01/2024 | 17/02/2023 | 152.68 | 152.68
237 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- (SM/09592) | SM/09592 | 440.8 | 9584 | RETROFITTING | 55 | WO no issued | 57 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 250.41 | 250.41
238 | RAHIMPUR Piped Water Supply Scheme (SM/14174) | SM/14174 | 1018.51 | 2638 | NEW | 56 | WO no issued | 55 | 09/01/2023 | 31/08/2024 | 10/01/2024 | 10/04/2023 | 563.44 | 563.44
239 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme (SM/06852) | SM/06852 | 90.94 | 1707 | RETROFITTING | 56 | WO no issued | 49 | 07/10/2020 | 30/11/2021 | 12/06/2023 | 28/01/2021 | 45 | 42.52
240 | Augmentation of Tilasan Piped water supply scheme (SM/09567) | SM/09567 | 331.85 | 1568 | AUGMENTATION | 57 | WO no issued | 56 | 22/11/2021 | 31/08/2024 | 10/01/2024 | 09/09/2021 | 186.33 | 185.97
241 | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15149) | SM/15149 | 865.47 | 375 | AUGMENTATION | 58 | WO no issued | 16 | 06/02/2023 | 25/09/2024 | 21/03/2024 | 14/07/2023 | 140.64 | 135.14
242 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl (SM/09593) | SM/09593 | 538.36 | 12090 | RETROFITTING | 58 | WO no issued | 52 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 278.49 | 278.49
243 | Augmentation of Bamongram piped water supply scheme. (SM/10138) | SM/10138 | 879.05 | 3481 | AUGMENTATION | 58 | WO no issued | 74 | 08/02/2022 | 31/08/2024 | 10/01/2024 | 15/06/2021 | 647.9 | 647.9
244 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block (SM/09660) | SM/09660 | 152.57 | 3600 | RETROFITTING | 58 | WO no issued | 56 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 85.19 | 85.19
245 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme (SM/06857) | SM/06857 | 91.69 | 1722 | RETROFITTING | 59 | WO no issued | 52 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 05/05/2021 | 47.4 | 47.4
246 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme (SM/06870) | SM/06870 | 92.34 | 1735 | RETROFITTING | 59 | WO no issued | 54 | 08/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 50 | 45.91
247 | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo (SM/08760) | SM/08760 | 183.54 | 2649 | RETROFITTING | 59 | WO no issued | 58 | 08/09/2021 | 31/10/2023 | 12/06/2023 | 03/11/2021 | 106.52 | 106.52
248 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme (SM/06864) | SM/06864 | 64.66 | 1186 | RETROFITTING | 60 | WO no issued | 60 | 07/10/2020 | 31/03/2021 | 12/06/2023 | 31/08/2020 | 39 | 39
249 | DAHIL Piped Water Supply Scheme. (SM/18461) | SM/18461 | 1502.54 | 4422 | NEW | 62 | WO no issued | 22 | 20/07/2023 | 20/07/2025 | 22/03/2024 | 08/08/2023 | 336.44 | 336.44
250 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme (SM/06866) | SM/06866 | 79.87 | 1488 | RETROFITTING | 65 | WO no issued | 73 | 07/10/2020 | 31/08/2024 | 10/01/2024 | 10/11/2020 | 58.6 | 58.6
251 | Augmentation of Bulbulchandi PWSS. (SM/09422) | SM/09422 | 981.06 | 4929 | AUGMENTATION | 66 | WO no issued | 50 | 17/11/2021 | 31/03/2024 | 16/10/2023 | 19/05/2022 | 491.57 | 491.57
252 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme (SM/06860) | SM/06860 | 93.04 | 1749 | RETROFITTING | 67 | WO no issued | 58 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 29/09/2020 | 54.36 | 54.36
253 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme (SM/06855) | SM/06855 | 73.75 | 1366 | RETROFITTING | 69 | WO no issued | 64 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 47.52 | 36.6
254 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09646) | SM/09646 | 351.94 | 7024 | RETROFITTING | 69 | WO no issued | 77 | 23/11/2021 | 23/02/2022 | 12/06/2023 | 27/12/2021 | 272.17 | 272.17
255 | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10247) | SM/10247 | 644.82 | 0 | ANGANWADI | 69 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 14/10/2023 | 12/07/2022 | 0 | 0
256 | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10207) | SM/10207 | 535.59 | 0 | SCHOOL | 70 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 23/06/2023 | 01/04/2022 | 0 | 0
257 | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10388) | SM/10388 | 594.09 | 0 | SCHOOL | 70 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 19/09/2023 | 18/01/2021 | 0 | 0
258 | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10306) | SM/10306 | 859.76 | 0 | ANGANWADI | 71 | WO no issued | 0 | 02/03/2022 | 31/03/2024 | 11/12/2023 | 24/06/2020 | 0 | 0
259 | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10384) | SM/10384 | 565.76 | 0 | SCHOOL | 72 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 09/11/2023 | 18/01/2021 | 0 | 0
260 | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10245) | SM/10245 | 731.13 | 0 | ANGANWADI | 74 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 16/08/2023 | 18/01/2021 | 0 | 0
261 | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10381) | SM/10381 | 665.38 | 0 | SCHOOL | 77 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 10/01/2024 | 18/01/2021 | 0 | 0
262 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme (SM/06868) | SM/06868 | 61.47 | 1122 | RETROFITTING | 79 | WO no issued | 72 | 08/10/2020 | 30/11/2022 | 12/06/2023 | 10/12/2020 | 44.5 | 44.5
263 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme (SM/06869) | SM/06869 | 87.63 | 1642 | RETROFITTING | 79 | WO no issued | 76 | 08/10/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 66.83 | 66.83
264 | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. (SM/10379) | SM/10379 | 725.43 | 0 | ANGANWADI | 79 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 10/01/2024 | 27/01/2021 | 0 | 0
265 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme (SM/06859) | SM/06859 | 71.47 | 1321 | RETROFITTING | 79 | WO no issued | 76 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 54.45 | 53.37
266 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc (SM/09588) | SM/09588 | 354.85 | 8954 | RETROFITTING | 80 | WO no issued | 83 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 293.09 | 293.09
267 | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10206) | SM/10206 | 357.06 | 0 | SCHOOL | 80 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 23/06/2023 | 26/04/2022 | 0 | 0
268 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme (SM/06871) | SM/06871 | 54.06 | 975 | RETROFITTING | 81 | WO no issued | 76 | 08/10/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 41.26 | 41.26
269 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme (SM/06865) | SM/06865 | 43.73 | 770 | RETROFITTING | 81 | WO no issued | 94 | 07/10/2020 | 31/03/2021 | 12/06/2023 | 12/10/2020 | 41.01 | 41.01
270 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo (SM/09654) | SM/09654 | 63.53 | 1423 | RETROFITTING | 82 | WO no issued | 77 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 49 | 49
271 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme (SM/06849) | SM/06849 | 73.35 | 1548 | RETROFITTING | 82 | WO no issued | 82 | 08/10/2020 | 31/03/2024 | 23/06/2023 | 09/11/2020 | 60 | 60
272 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme (SM/06854) | SM/06854 | 84.53 | 1580 | RETROFITTING | 83 | WO no issued | 80 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 10/11/2020 | 67.28 | 67.28
273 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme (SM/06872) | SM/06872 | 87.48 | 1639 | RETROFITTING | 83 | WO no issued | 80 | 08/10/2020 | 30/11/2022 | 12/06/2023 | 12/10/2020 | 69.69 | 65.71
274 | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. (SM/13237) | SM/13237 | 123.52 | 0 | AUGMENTATION | 84 | WO no issued | 83 | 14/10/2022 | 31/03/2024 | 10/08/2023 | 05/12/2022 | 102.17 | 102.17
275 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09653) | SM/09653 | 445.56 | 9815 | RETROFITTING | 87 | WO no issued | 83 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 368.34 | 368.34
276 | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15080) | SM/15080 | 213.72 | 0 | AUGMENTATION | 92 | WO no issued | 44 | 04/02/2023 | 31/12/2024 | 07/03/2024 | 20/03/2023 | 94.55 | 94.55
277 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block (SM/08283) | SM/08283 | 406.26 | 9031 | RETROFITTING | 92 | WO no issued | 100 | 01/02/2021 | 31/03/2024 | 23/06/2023 | 15/01/2021 | 404.85 | 404.85
278 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme (SM/06863) | SM/06863 | 54.86 | 991 | RETROFITTING | 97 | WO no issued | 97 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 31/08/2020 | 53 | 52.35
279 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme (SM/06858) | SM/06858 | 59.54 | 1084 | RETROFITTING | 97 | WO no issued | 97 | 07/10/2020 | 30/11/2022 | 12/06/2023 | 11/12/2020 | 57.78 | 46.32
280 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme (SM/06856) | SM/06856 | 86.33 | 1616 | RETROFITTING | 98 | WO no issued | 98 | 07/10/2020 | 30/11/2021 | 12/06/2023 | 10/11/2020 | 85.02 | 85.02
281 | Sahapur Piped Water Supply Scheme (SM/11968) | SM/11968 | 1135.04 | 7669 | NEW | 100 | WO no issued | 20 | 26/08/2022 |  | 12/06/2023 | 09/09/2021 | 229.29 | 229.29
282 | PASCHIM BHAGABANPUR Piped Water Supply Scheme (SM/12188) | SM/12188 | 791.25 | 2609 | NEW | 100 | WO no issued | 46 | 07/09/2022 | 31/03/2024 | 12/06/2023 | 17/05/2023 | 366.06 | 360.74
283 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme (SM/06986) | SM/06986 | 35.94 | 790 | RETROFITTING | 100 | WO no issued | 97 | 11/11/2020 | 30/11/2021 | 12/06/2023 | 11/11/2020 | 34.96 | 34.96
284 | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11588) | SM/11588 | 798.84 | 2912 | NEW | 100 | WO no issued | 10 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 22/03/2022 | 81.9 | 81.9
285 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo (SM/09648) | SM/09648 | 242.47 | 4934 | RETROFITTING | 100 | WO no issued | 100 | 23/11/2021 | 31/10/2023 | 12/06/2023 | 24/11/2021 | 242.26 | 242.26
Total |  |  | 322283.59 | 913276 | [8 empty] | 61385.54 | 57814.07