## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II (SM/10797) | SM/10797 | 762.78 | 5068 | AUGMENTATION | 0 | 0% Physical | 3 | 25/05/2022 | 25/02/2023 | 12/06/2023 | 10/08/2023 | 24.4 | 24.4
2 | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744,314745,314746,314747,314753,314754,314755,314756) of Purusottampur under ground w (SM/11216) | SM/11216 | 162.44 | 304 | AUGMENTATION | 0 | 0% Physical | 0 | 15/06/2022 | 15/12/2022 | 12/06/2023 | 04/02/2021 | 0 | 0
3 | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur, (313919, 313910, 313912, 313920) of Madna under Ground water based water supply scheme for arsenic affected areas of Suti-I Block (SM/11217) | SM/11217 | 288.41 | 1795 | AUGMENTATION | 0 | 0% Physical | 0 | 15/06/2022 | 15/12/2022 | 12/06/2023 | 11/05/2022 | 0 | 0
4 | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Sinkaipur (314775) of Azamatpur Ground water based water supply scheme for arsenic affected areas of Raninagar - I Block in Murshidabad District under Murshidabad Division, P.H.E.D (SM/11219) | SM/11219 | 72.82 | 2 | AUGMENTATION | 0 | 0% Physical | 0 | 15/06/2022 | 15/12/2022 | 12/06/2023 | 28/06/2021 | 0 | 0
5 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at SURANGAPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. (SM/15352) | SM/15352 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
6 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KAKRAMARI ZONE I Ground water Based PWSS, Block-Suti-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15343) | SM/15343 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
7 | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-III, Block- Nawda, District- Murshidabad. (SM/16436) | SM/16436 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
8 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. (SM/16497) | SM/16497 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
9 | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-II, Block- Lalgola, District- Murshidabad. (SM/16211) | SM/16211 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
10 | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. (SM/16169) | SM/16169 | 832.44 | 150 | AUGMENTATION | 0 | 0% Physical | 6 | 22/02/2023 | 22/11/2023 | 12/06/2023 | 10/08/2023 | 52.54 | 52.54
11 | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. (SM/15743) | SM/15743 | 480.14 | 931 | AUGMENTATION | 0 | 0% Physical | 3 | 20/02/2023 | 31/10/2024 | 12/06/2023 | 09/10/2023 | 15.63 | 15.63
12 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. (SM/16674) | SM/16674 | 996.89 | 12602 | RETROFITTING | 0 | 0% Physical | 0 | 14/03/2023 | 14/06/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
13 | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) (SM/18916) | SM/18916 | 8264.61 | 16539 | NEW | 0 | 0% Physical | 0 | 09/10/2023 | 09/04/2026 | 09/10/2023 | 14/12/2023 | 0 | 0
14 | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16265) | SM/16265 | 429.02 | 2 | AUGMENTATION | 0 | 0% Physical | 3 | 24/02/2023 | 24/08/2023 | 12/06/2023 | 03/02/2022 | 12.57 | 12.57
15 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Ramkantapur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. (SM/15342) | SM/15342 | 7.55 | 0 | SOLARISATION | 0 | WO no issued | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 |  | 0 | 0
16 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at NABIPUR Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15346) | SM/15346 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
17 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at MALIBARI Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15347) | SM/15347 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
18 | Mini piped water supply scheme (maximum 100 households) Village-Arazi Saikuli, Block-Murshidabad -Jiaganj, District- Murshidabad. (SM/16431) | SM/16431 | 38.81 | 84 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
19 | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. (SM/16433) | SM/16433 | 31.51 | 28 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
20 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. (SM/16437) | SM/16437 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
21 | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. (SM/16442) | SM/16442 | 81.23 | 252 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
22 | Mini piped water supply scheme (Maximum 100 house holds) Village- Alighata, Block- Lalgola, District- Murshidabad. (SM/16496) | SM/16496 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
23 | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-II, Block- Nawda, District- Murshidabad. (SM/16498) | SM/16498 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
24 | Mini piped water supply scheme (maximum 100 households) Village-Sibnagar Zone-V, Block-Nawda, District- Murshidabad. (SM/16501) | SM/16501 | 33.09 | 40 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
25 | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. (SM/16504) | SM/16504 | 81.23 | 225 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
26 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16672) | SM/16672 | 998.65 | 12105 | RETROFITTING | 0 | 0% Physical | 0 | 14/03/2023 | 14/06/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
27 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16985) | SM/16985 | 965.79 | 10688 | RETROFITTING | 0 | 0% Physical | 0 | 16/03/2023 | 16/06/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
28 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IV)to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16987) | SM/16987 | 950.83 | 10197 | RETROFITTING | 0 | On track | 0 | 16/03/2023 | 16/06/2023 | 12/06/2023 | 26/11/2024 | 0 | 0
29 | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS (SM/16867) | SM/16867 | 209.46 | 448 | NEW | 0 | 0% Physical | 0 | 13/03/2023 | 13/09/2024 | 12/06/2023 | 25/08/2023 | 0 | 0
30 | BHATPARA AND ADJOINING MOUJAS (SM/18430) | SM/18430 | 1170.19 | 3444 | NEW | 0 | 0% Physical | 10 | 18/07/2023 | 18/07/2025 | 20/07/2023 | 21/07/2023 | 116.2 | 116.2
31 | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. (SM/19122) | SM/19122 | 1550.75 | 2091 | AUGMENTATION | 0 | 0% Physical | 0 | 03/01/2024 |  | 03/01/2024 | 18/01/2024 | 0 | 0
32 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagharpur Ramna (314665) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-V) (SM/07671) | SM/07671 | 138.2 | 1840 | RETROFITTING | 0 | 0% Physical | 7 | 08/01/2021 | 08/04/2021 | 12/06/2023 |  | 10.04 | 10.04
33 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram (SM/07682) | SM/07682 | 131.02 | 1684 | RETROFITTING | 0 | 0% Physical | 47 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 30/09/2020 | 61.17 | 61.17
34 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brahmanigram ( 314319 ) and Bergram ( 314328 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of (SM/09747) | SM/09747 | 94.96 | 1217 | RETROFITTING | 0 | 0% Physical | 0 | 29/11/2021 | 28/02/2022 | 12/06/2023 | 22/12/2021 | 0 | 0
35 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KHAYRAMARI Part-B Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. (SM/15293) | SM/15293 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
36 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Mirzapur Ground water Based PWSS, Block-Raghunathganj-I , Dist- Murshidabad under MEDB, PHE Dte. (SM/15351) | SM/15351 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
37 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bahadurpur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. (SM/15341) | SM/15341 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
38 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jorgacha Part-I, Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. (SM/15350) | SM/15350 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 29/12/2023 | 0 | 0
39 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. (SM/16429) | SM/16429 | 113.82 | 209 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 17/05/2023 | 0 | 0
40 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAK CHANDPARA , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. (SM/16440) | SM/16440 | 38.92 | 85 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
41 | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME (SM/16555) | SM/16555 | 789.76 | 1340 | AUGMENTATION | 0 | 0% Physical | 4 | 10/03/2023 | 31/07/2024 | 12/06/2023 | 10/05/2022 | 34.41 | 28.75
42 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. (SM/16050) | SM/16050 | 37.34 | 65 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
43 | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. (SM/15728) | SM/15728 | 534.48 | 797 | AUGMENTATION | 0 | 0% Physical | 0 | 20/02/2023 | 20/11/2023 | 12/06/2023 | 04/09/2023 | 0 | 0
44 | Source Augmentation of Functional Household Tap Connections (FHTC) of Mouza Habaspur (314487) of Habaspur under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Bhagwangola-I Block of Murshidabad District Under Murshidabad Division Phe (SM/11162) | SM/11162 | 480.32 | 4287 | AUGMENTATION | 0 | 0% Physical | 0 | 02/06/2022 | 02/12/2022 | 12/06/2023 | 02/08/2024 | 0 | 0
45 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dakshin Sekhhalipur Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15292) | SM/15292 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
46 | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. (SM/16435) | SM/16435 | 33.9 | 46 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
47 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. (SM/16441) | SM/16441 | 38.14 | 78 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
48 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-I, Block- Berhampore, District- Murshidabad. (SM/16044) | SM/16044 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
49 | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. (SM/16172) | SM/16172 | 471.99 | 360 | AUGMENTATION | 0 | 0% Physical | 11 | 22/02/2023 | 31/12/2024 | 12/06/2023 | 06/07/2023 | 52.8 | 52.8
50 | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. (SM/16173) | SM/16173 | 471.99 | 360 | AUGMENTATION | 0 | 0% Physical | 1 | 22/02/2023 | 31/12/2024 | 12/06/2023 | 10/05/2022 | 3.31 | 3.31
51 | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. (SM/16210) | SM/16210 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
52 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VIII & XII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16989) | SM/16989 | 999.61 | 11796 | RETROFITTING | 0 | 0% Physical | 0 | 16/03/2023 | 16/06/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
53 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16990) | SM/16990 | 928.12 | 10370 | RETROFITTING | 0 | 0% Physical | 0 | 16/03/2023 | 16/06/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
54 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Santoshpur (314329) &Chandanbati ( 314330 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of M (SM/09850) | SM/09850 | 91.63 | 1173 | RETROFITTING | 0 | 0% Physical | 0 | 02/12/2021 | 02/03/2022 | 12/06/2023 | 03/11/2023 | 0 | 0
55 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. (SM/13114) | SM/13114 | 1270.06 | 2427 | AUGMENTATION | 0 | 0% Physical | 0 | 10/10/2022 | 10/07/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
56 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at GODHANPARA PWSS (ZONE- I ) Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15291) | SM/15291 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
57 | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. (SM/15064) | SM/15064 | 997.95 | 309 | AUGMENTATION | 0 | 0% Physical | 0 | 04/02/2023 | 04/11/2023 | 12/06/2023 | 01/11/2022 | 2.92 | 2.92
58 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dogachhi Zone - I Ground water Based PWSS, Block-Samserganj , Dist- Murshidabad under MEDB, PHE Dte. (SM/15344) | SM/15344 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
59 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jotkamal Zone - II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15348) | SM/15348 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
60 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Kasiadanga Zone- I & II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15349) | SM/15349 | 15.1 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
61 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-I, Block- Berhampore, District- Murshidabad. (SM/16432) | SM/16432 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
62 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Chhalimpur, Block- Murshidabad Jiaganj, District- Murshidabad. (SM/16048) | SM/16048 | 31.8 | 30 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
63 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. (SM/16049) | SM/16049 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
64 | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-I, Block- Nawda, District- Murshidabad. (SM/16499) | SM/16499 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
65 | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. (SM/16214) | SM/16214 | 81.23 | 210 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
66 | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. (SM/15741) | SM/15741 | 636.25 | 769 | AUGMENTATION | 0 | 0% Physical | 1 | 20/02/2023 | 31/03/2025 | 12/06/2023 | 21/09/2023 | 4.08 | 0
67 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16988) | SM/16988 | 934.56 | 9981 | RETROFITTING | 0 | 0% Physical | 0 | 16/03/2023 | 16/06/2023 | 12/06/2023 | 14/09/2023 | 0 | 0
68 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl (SM/09752) | SM/09752 | 46.25 | 648 | RETROFITTING | 0 | 0% Physical | 0 | 30/11/2021 | 28/02/2022 | 12/06/2023 | 07/02/2022 | 0 | 0
69 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bachhara Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15295) | SM/15295 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
70 | SANTOSHPUR AND ADJOINING MOUJAS PWSS (SM/16248) | SM/16248 | 394.39 | 1033 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 16/06/2023 | 0 | 0
71 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KARIMPUR JALANGI Zone-I Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. (SM/15353) | SM/15353 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
72 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JITPUR (ZONE II) Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. (SM/15354) | SM/15354 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 29/12/2023 | 0 | 0
73 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dhulauri Part-I Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. (SM/15355) | SM/15355 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 29/12/2023 | 0 | 0
74 | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. (SM/16239) | SM/16239 | 820.76 | 967 | AUGMENTATION | 0 | 0% Physical | 15 | 23/02/2023 | 30/11/2024 | 12/06/2023 | 10/05/2022 | 119.44 | 119.44
75 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE ¿ BILGOBRA , BLOCK- BHAGAWANGOLA-I, DISTRICT MURSHIDABAD. (SM/16439) | SM/16439 | 36.06 | 55 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 17/05/2023 | 0 | 0
76 | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. (SM/16443) | SM/16443 | 81.23 | 244 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
77 | Mini piped water supply scheme (maximum 100 households) Village-Sona Diar Zone-II, Block-Berhampore, District- Murshidabad. (SM/16047) | SM/16047 | 35.93 | 54 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
78 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Kuchidanga, Block- Lalgola, District- Murshidabad. (SM/16503) | SM/16503 | 31.65 | 29 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
79 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-III, Block- Berhampore, District- Murshidabad. (SM/16812) | SM/16812 | 34.04 | 47 | NEW | 0 | 0% Physical | 0 | 13/03/2023 | 13/09/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
80 | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. (SM/16864) | SM/16864 | 863.66 | 2634 | AUGMENTATION | 0 | 0% Physical | 9 | 13/03/2023 | 13/12/2023 | 12/06/2023 | 05/05/2022 | 77.19 | 77.19
81 | Source Augumentation& Functional Household Tap Connections (FHTC) of Mouza Radhakrishanapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148, 314149, 314150, 314151, 314153 ) of Lalgola Under Ground Water Based Water Supply Scheme For Arse (SM/19019) | SM/19019 | 872.83 | 9966 | AUGMENTATION | 0 | 0% Physical | 0 | 27/10/2023 |  | 27/10/2023 | 29/12/2023 | 0 | 0
82 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debottar Lakshminarayanpur ( 314678 ) of Jitpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District und (SM/09843) | SM/09843 | 44.72 | 562 | RETROFITTING | 0 | WO no issued | 0 | 02/12/2021 | 02/03/2022 | 12/06/2023 |  | 0 | 0
83 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Amarkunda, Bagor, Nandigram, Madhunia, Chayan Nagar, Sankuria, Rainda ( ) of Amarkundu under Ground Water Based Water Supply Scheme for arsenic affected areas of Nabagram Block of (SM/11230) | SM/11230 | 273.1 | 1556 | AUGMENTATION | 0 | 0% Physical | 0 | 22/06/2022 | 22/12/2022 | 12/06/2023 | 27/12/2021 | 0 | 0
84 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JALANGI Zone-I, Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. (SM/15282) | SM/15282 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
85 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at EDRAKPUR Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. (SM/15327) | SM/15327 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
86 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at CHANDPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. (SM/15331) | SM/15331 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
87 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Manigram Ground water Based PWSS, Block-Sagardighi , Dist- Murshidabad under MEDB, PHE Dte. (SM/15345) | SM/15345 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 03/11/2023 | 0 | 0
88 | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. (SM/16430) | SM/16430 | 75.32 | 135 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
89 | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone- III, Block- Lalgola, District- Murshidabad. (SM/16434) | SM/16434 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
90 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Pashchim Gobindapur, Block- Murshidabad Jiaganj, District- Murshidabad. (SM/16438) | SM/16438 | 34.17 | 48 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 08/08/2023 | 0 | 0
91 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-III, Block- Berhampore, District- Murshidabad. (SM/16045) | SM/16045 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
92 | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. (SM/16178) | SM/16178 | 800.76 | 2014 | AUGMENTATION | 0 | 0% Physical | 1 | 22/02/2023 | 22/11/2023 | 12/06/2023 | 03/02/2022 | 8.31 | 7.11
93 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Darura, Block- Murshidabad Jiaganj, District- Murshidabad. (SM/16212) | SM/16212 | 32.81 | 38 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
94 | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. (SM/16215) | SM/16215 | 162.46 | 498 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 25/07/2023 | 0 | 0
95 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis (SM/07513) | SM/07513 | 61.91 | 807 | RETROFITTING | 0 | 0% Physical | 100 | 29/12/2020 | 29/03/2021 | 12/06/2023 | 04/02/2021 | 61.91 | 61.91
96 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ratanpur ( 313841 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Mursh (SM/09745) | SM/09745 | 210.01 | 2242 | RETROFITTING | 0 | 0% Physical | 6 | 30/11/2021 | 28/02/2022 | 12/06/2023 |  | 13.05 | 13.05
97 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Saktipur (ZONE- I ) Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. (SM/15294) | SM/15294 | 7.55 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 29/12/2023 | 0 | 0
98 | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at FATELLAPUR Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. (SM/15340) | SM/15340 | 7.55 | 0 | SOLARISATION | 0 | WO no issued | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 |  | 0 | 0
99 | GOPJAN(P) PIPED WATER SUPPLY SCHEME, BLOCK- BERHAMPORE , DISTRICT- MURSHIDABAD. (SM/16444) | SM/16444 | 40.62 | 120 | NEW | 0 | 0% Physical | 0 | 28/02/2023 | 31/08/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
100 | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-II, Block- Berhampore, District- Murshidabad. (SM/16046) | SM/16046 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 22/02/2023 | 22/08/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
101 | Mini piped water supply scheme (maximum 100 households) Village-Sonadiar Zone-I, Block-Berhampore, District- Murshidabad. (SM/16500) | SM/16500 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 16/05/2023 | 0 | 0
102 | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Arazi Narayanpur, Block- Lalgola, District- Murshidabad. (SM/16502) | SM/16502 | 38.62 | 75 | NEW | 0 | 0% Physical | 0 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
103 | Mini piped water supply scheme (Maximum 100 house holds) Village- Lahari, Block- Bhagwangola-II, District- Murshidabad. (SM/16213) | SM/16213 | 40.62 | 100 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 15/05/2023 | 0 | 0
104 | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. (SM/16416) | SM/16416 | 541.33 | 1729 | AUGMENTATION | 0 | 0% Physical | 0 | 28/02/2023 | 30/11/2023 | 12/06/2023 | 04/09/2023 | 0 | 0
105 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/16752) | SM/16752 | 778.66 | 2723 | RETROFITTING | 0 | 0% Physical | 3 | 13/03/2023 | 31/03/2025 | 12/06/2023 | 05/10/2021 | 24.47 | 24.47
106 | HABASPUR AND ADJOINING MOUJAS PWSS (SM/18238) | SM/18238 | 1547.96 | 4643 | NEW | 0 | WO no issued | 0 | 15/06/2023 | 15/06/2025 | 16/06/2023 |  | 0 | 0
107 | Augmentation of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundabag GP Murshidabad District under Murshidabad Division PHE Dte . (SM/18393) | SM/18393 | 1119.66 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 11/07/2023 | 11/04/2024 | 14/07/2023 | 31/10/2023 | 0 | 0
108 | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. (SM/06630) | SM/06630 | 98.27 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 30/04/2021 | 08/03/2019 | 0 | 0
109 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Murshidabad District Under Murshidabad Division (16 nos) Block (SM/09856) | SM/09856 | 333.41 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 06/12/2021 | 09/11/2022 | 0 | 0
110 | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En (SM/13045) | SM/13045 | 69.53 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/09/2022 |  | 07/10/2022 | 29/12/2022 | 0 | 0
111 | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. (SM/12985) | SM/12985 | 315.67 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 28/09/2022 |  | 06/10/2022 | 03/11/2021 | 0 | 0
112 | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. (SM/15310) | SM/15310 | 48.52 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 09/02/2023 |  | 14/02/2023 |  | 0 | 0
113 | Drinking water sample collection & testing through Field Test Kits (FTKs) & data uploding charges related to water Quality Monitoring & Surveillance Activities Under Jal Jeevan Mission . (SM/19077) | SM/19077 | 192.49 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
114 | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERD RURAL AREA OF MURSHIDABAD DISTRICT IN WEST BENGAL (SM/14638) | SM/14638 | 632.51 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 31/01/2023 |  | 03/02/2023 | 03/11/2021 | 0 | 0
115 | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. (SM/18195) | SM/18195 | 619.27 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 17/02/2023 |  | 05/04/2023 | 05/04/2023 | 0 | 0
116 | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid (SM/08685) | SM/08685 | 15.23 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 23/08/2021 |  | 30/06/2022 | 03/09/2021 | 0 | 0
117 | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Executive Engineer, Mechanical/Electrical Division Berhampore, PHE Dte. (SM/17192) | SM/17192 | 7.4 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 |  | 0 | 0
118 | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. (SM/19076) | SM/19076 | 658.47 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 17/02/2023 | 0 | 0
119 | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . (SM/18272) | SM/18272 | 216.7 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 | 25/06/2023 | 0 | 0
120 | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. (SM/13044) | SM/13044 | 108.58 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/09/2022 |  | 07/10/2022 | 23/02/2022 | 0 | 0
121 | Operational Charges Of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Activities under JJM of Different Water Testing Laboratories under Murshidabad Division P.H.E. Dte. (SM/19260) | SM/19260 | 175.13 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
122 | JASOHARI PIPE WATER SUPPLY SCHEME. (SM/13728) | SM/13728 | 478.24 | 2016 | NEW | 1 | Delayed | 9 | 17/11/2022 | 31/07/2024 | 22/04/2024 | 20/02/2023 | 41.7 | 41.7
123 | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. (SM/14950) | SM/14950 | 509.81 | 673 | AUGMENTATION | 1 | Delayed | 10 | 03/02/2023 | 31/12/2024 | 21/05/2024 | 24/03/2023 | 49.85 | 49.85
124 | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. (SM/16240) | SM/16240 | 541.38 | 529 | AUGMENTATION | 1 | Delayed | 3 | 24/02/2023 | 31/12/2024 | 30/09/2024 | 06/07/2023 | 17.65 | 0
125 | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. (SM/16411) | SM/16411 | 587.59 | 2104 | AUGMENTATION | 1 | Delayed | 47 | 28/02/2023 | 31/03/2024 | 02/02/2024 | 03/02/2022 | 278.19 | 278.19
126 | Augmentation of Basudevpur Zone-II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. (SM/16180) | SM/16180 | 591.55 | 651 | AUGMENTATION | 1 | Delayed | 1 | 22/02/2023 | 31/03/2024 | 12/07/2023 | 03/02/2022 | 4.05 | 4.05
127 | BAHARAGACHI PIPE WATER SUPPLY SCHEME. (SM/15939) | SM/15939 | 719.97 | 857 | NEW | 1 | Delayed | 7 | 22/02/2023 | 31/07/2024 | 18/03/2024 | 16/06/2023 | 50.13 | 50.13
128 | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. (SM/15726) | SM/15726 | 763.92 | 3091 | AUGMENTATION | 1 | Delayed | 19 | 20/02/2023 | 20/11/2023 | 15/10/2023 | 03/02/2022 | 144.16 | 144.16
129 | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. (SM/15747) | SM/15747 | 534.48 | 797 | AUGMENTATION | 1 | Delayed | 3 | 20/02/2023 | 20/11/2023 | 15/10/2023 | 03/02/2022 | 16.78 | 16.78
130 | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. (SM/16765) | SM/16765 | 479.79 | 1444 | AUGMENTATION | 1 | Delayed | 9 | 13/03/2023 | 31/03/2024 | 12/09/2023 | 03/02/2022 | 45.15 | 31.84
131 | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/18732) | SM/18732 | 1278.27 | 2 | AUGMENTATION | 1 | Delayed | 20 | 14/08/2023 | 14/05/2024 | 12/03/2024 | 25/08/2023 | 257.21 | 257.21
132 | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. (SM/18556) | SM/18556 | 1383.64 | 3683 | NEW | 1 | Delayed | 3 | 31/07/2023 | 31/03/2024 | 07/09/2023 | 11/11/2022 | 38.29 | 38.29
133 | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. (SM/18444) | SM/18444 | 1407.24 | 5016 | AUGMENTATION | 1 | Delayed | 14 | 20/07/2023 | 31/03/2024 | 24/08/2023 | 25/07/2023 | 202.42 | 202.42
134 | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/18736) | SM/18736 | 1945.44 | 4 | AUGMENTATION | 1 | Delayed | 11 | 17/08/2023 | 31/12/2024 | 20/08/2024 | 24/08/2023 | 212.7 | 212.7
135 | BAHUTULI PIPRD WATER SUPPLY SCHEME. (SM/18693) | SM/18693 | 1754.34 | 3879 | NEW | 1 | Delayed | 16 | 04/08/2023 | 31/12/2024 | 16/04/2024 | 11/11/2022 | 277.3 | 271.12
136 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11792) | SM/11792 | 902.45 | 1457 | AUGMENTATION | 1 | Delayed | 40 | 05/08/2022 | 31/03/2024 | 13/07/2023 | 03/09/2021 | 364.01 | 355.06
137 | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/13993) | SM/13993 | 689.2 | 556 | AUGMENTATION | 1 | Delayed | 11 | 01/12/2022 | 31/03/2024 | 05/10/2023 | 16/06/2023 | 78.48 | 78.48
138 | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/13995) | SM/13995 | 621.73 | 3226 | AUGMENTATION | 1 | Delayed | 31 | 01/12/2022 | 31/07/2024 | 18/03/2024 | 19/06/2023 | 189.87 | 189.87
139 | MARURA AND ADJOINING MOUJAS PWSS (SM/14235) | SM/14235 | 1168.32 | 3572 | NEW | 1 | Delayed | 7 | 16/01/2023 | 31/03/2024 | 20/09/2023 | 11/01/2023 | 79.18 | 79.18
140 | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. (SM/16247) | SM/16247 | 541.38 | 1514 | AUGMENTATION | 1 | Delayed | 0 | 24/02/2023 | 31/03/2024 | 12/09/2023 | 06/07/2023 | 0 | 0
141 | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. (SM/16179) | SM/16179 | 898.14 | 666 | AUGMENTATION | 1 | Delayed | 21 | 22/02/2023 | 31/08/2024 | 06/05/2024 | 03/02/2022 | 188.52 | 188.52
142 | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/16556) | SM/16556 | 221.25 | 1061 | AUGMENTATION | 1 | Delayed | 2 | 10/03/2023 | 31/01/2024 | 28/09/2023 | 04/09/2023 | 4.47 | 4.47
143 | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/16558) | SM/16558 | 275.73 | 494 | AUGMENTATION | 1 | Delayed | 24 | 10/03/2023 | 31/03/2024 | 28/09/2023 | 22/05/2023 | 66.86 | 66.86
144 | RANAGRAM AND ADJOINIG MOUJAS PWSS (SM/16052) | SM/16052 | 198.62 | 510 | NEW | 1 | Delayed | 23 | 22/02/2023 | 31/03/2024 | 22/01/2024 | 08/08/2023 | 45.41 | 45.41
145 | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. (SM/15749) | SM/15749 | 999.15 | 5176 | AUGMENTATION | 1 | Delayed | 41 | 20/02/2023 | 31/07/2024 | 22/04/2024 | 05/10/2021 | 407.72 | 406.68
146 | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. (SM/16766) | SM/16766 | 959.64 | 818 | AUGMENTATION | 1 | Delayed | 33 | 13/03/2023 | 31/03/2024 | 10/10/2023 | 01/12/2020 | 318.84 | 318.84
147 | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/17850) | SM/17850 | 469.54 | 1424 | AUGMENTATION | 1 | Delayed | 29 | 17/03/2023 | 31/12/2024 | 28/10/2024 | 10/05/2022 | 134.62 | 116.46
148 | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. (SM/18413) | SM/18413 | 1029.02 | 1729 | NEW | 1 | Delayed | 1 | 12/07/2023 | 31/03/2024 | 03/08/2023 | 11/11/2022 | 6.44 | 6.44
149 | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. (SM/18774) | SM/18774 | 1593.91 | 2411 | AUGMENTATION | 1 | Delayed | 8 | 25/08/2023 | 25/05/2024 | 11/10/2023 | 10/05/2022 | 128.44 | 128.44
150 | UMARPUR PIPED WATER SUPPLY SCHEME . (SM/18472) | SM/18472 | 1936.25 | 5123 | NEW | 1 | Delayed | 19 | 20/07/2023 | 31/08/2024 | 04/04/2024 | 11/11/2022 | 364.07 | 364.07
151 | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME (SM/16398) | SM/16398 | 422.27 | 1019 | AUGMENTATION | 1 | Delayed | 9 | 28/02/2023 | 31/05/2025 | 04/04/2024 | 10/05/2022 | 37.57 | 37.57
152 | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. (SM/18755) | SM/18755 | 1126.44 | 2310 | AUGMENTATION | 1 | Delayed | 2 | 21/08/2023 | 31/03/2024 | 06/02/2024 | 03/02/2022 | 17.85 | 17.85
153 | KUMAR SANDA AND ADJOINING MOUJAS PWSS (SM/14238) | SM/14238 | 1000.77 | 4073 | NEW | 1 | Delayed | 5 | 16/01/2023 | 31/03/2024 | 20/09/2023 | 11/01/2023 | 52.59 | 52.59
154 | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. (SM/16245) | SM/16245 | 657.87 | 557 | AUGMENTATION | 1 | Delayed | 11 | 24/02/2023 | 31/12/2024 | 04/06/2024 | 10/05/2022 | 70.58 | 70.58
155 | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16545) | SM/16545 | 889.36 | 4386 | AUGMENTATION | 1 | Delayed | 19 | 10/03/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 169.38 | 169.38
156 | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. (SM/16547) | SM/16547 | 996.9 | 243 | AUGMENTATION | 1 | Delayed | 4 | 10/03/2023 | 31/03/2024 | 12/07/2023 | 03/02/2022 | 40.97 | 40.97
157 | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. (SM/16550) | SM/16550 | 979.6 | 2165 | NEW | 1 | Delayed | 5 | 10/03/2023 | 31/10/2024 | 17/04/2024 | 16/06/2023 | 48.14 | 48.14
158 | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16406) | SM/16406 | 951.83 | 3199 | AUGMENTATION | 1 | Delayed | 1 | 28/02/2023 | 31/03/2024 | 29/09/2023 | 05/10/2021 | 13.53 | 13.53
159 | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. (SM/16415) | SM/16415 | 541.33 | 1729 | AUGMENTATION | 1 | Delayed | 5 | 28/02/2023 | 31/12/2024 | 12/12/2023 | 10/05/2022 | 25.25 | 25.25
160 | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. (SM/16391) | SM/16391 | 927.36 | 1920 | NEW | 1 | Delayed | 3 | 28/02/2023 | 31/03/2024 | 12/07/2023 | 31/03/2023 | 32.35 | 32.35
161 | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15917) | SM/15917 | 998.29 | 1390 | AUGMENTATION | 1 | Delayed | 8 | 22/02/2023 | 31/03/2024 | 05/03/2024 | 10/05/2022 | 78.18 | 78.18
162 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. (SM/18542) | SM/18542 | 1898.34 | 1075 | AUGMENTATION | 1 | Delayed | 0 | 26/07/2023 | 31/12/2024 | 04/06/2024 | 04/09/2023 | 5.52 | 5.52
163 | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. (SM/19121) | SM/19121 | 1667.04 | 4363 | NEW | 1 | Delayed | 1 | 03/01/2024 | 31/12/2024 | 18/01/2024 | 09/01/2024 | 12.5 | 12.5
164 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. (SM/18662) | SM/18662 | 2059.61 | 6034 | AUGMENTATION | 1 | Delayed | 0 | 04/08/2023 | 31/10/2024 | 12/10/2023 | 04/09/2023 | 5.21 | 5.21
165 | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. (SM/18694) | SM/18694 | 1333.05 | 3339 | AUGMENTATION | 1 | Delayed | 3 | 04/08/2023 | 31/03/2024 | 24/08/2023 | 03/02/2022 | 37.14 | 37.14
166 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10611) | SM/10611 | 738.67 | 349 | AUGMENTATION | 1 | Delayed | 64 | 19/04/2022 | 31/03/2024 | 19/02/2024 | 17/11/2022 | 472.46 | 472.46
167 | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. (SM/13824) | SM/13824 | 638.6 | 739 | AUGMENTATION | 1 | Delayed | 33 | 25/11/2022 | 29/02/2024 | 28/09/2023 | 03/02/2022 | 208.87 | 208.87
168 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. (SM/14631) | SM/14631 | 488.47 | 101 | AUGMENTATION | 1 | Delayed | 29 | 31/01/2023 | 31/03/2024 | 12/09/2023 | 03/02/2022 | 139.4 | 139.4
169 | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/14942) | SM/14942 | 666.8 | 1823 | AUGMENTATION | 1 | Delayed | 7 | 03/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 46.9 | 46.9
170 | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16405) | SM/16405 | 907.34 | 1788 | AUGMENTATION | 1 | Delayed | 2 | 28/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 15.75 | 11.75
171 | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15919) | SM/15919 | 780.33 | 2308 | AUGMENTATION | 1 | Delayed | 40 | 22/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 314.43 | 314.43
172 | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16560) | SM/16560 | 492.65 | 568 | AUGMENTATION | 1 | Delayed | 5 | 10/03/2023 | 30/09/2024 | 22/05/2024 | 16/06/2023 | 24.44 | 24.44
173 | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. (SM/16565) | SM/16565 | 803.55 | 1078 | AUGMENTATION | 1 | Delayed | 24 | 10/03/2023 | 30/04/2025 | 23/03/2024 | 22/02/2022 | 196.31 | 196.31
174 | Augmentation of Dakshin Kanda Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. (SM/16425) | SM/16425 | 556.98 | 1085 | AUGMENTATION | 1 | Delayed | 2 | 28/02/2023 | 31/03/2025 | 03/12/2024 | 21/09/2023 | 9.18 | 0
175 | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. (SM/15750) | SM/15750 | 697.42 | 646 | AUGMENTATION | 1 | Delayed | 5 | 20/02/2023 | 20/11/2023 | 15/10/2023 | 03/02/2022 | 34.98 | 34.98
176 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/16986) | SM/16986 | 733.3 | 7403 | RETROFITTING | 1 | Delayed | 11 | 16/03/2023 | 31/03/2025 | 08/02/2024 | 25/08/2023 | 79.4 | 79.4
177 | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . (SM/19123) | SM/19123 | 1029.17 | 522 | AUGMENTATION | 1 | Delayed | 8 | 03/01/2024 | 31/12/2025 | 04/04/2024 | 15/01/2024 | 78.86 | 78.86
178 | CHACHANDA PIPED WATER SUPPLY SCHEME. (SM/18382) | SM/18382 | 1131.75 | 3653 | NEW | 1 | Delayed | 1 | 11/07/2023 | 31/03/2024 | 03/08/2023 | 11/11/2022 | 7.09 | 7.09
179 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. (SM/18515) | SM/18515 | 3298.88 | 8111 | AUGMENTATION | 1 | Delayed | 1 | 26/07/2023 | 31/12/2025 | 04/04/2024 | 10/08/2023 | 49.11 | 49.11
180 | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. (SM/18691) | SM/18691 | 1102.97 | 2733 | NEW | 1 | Delayed | 1 | 04/08/2023 | 31/03/2024 | 07/09/2023 | 11/11/2022 | 12.38 | 12.38
181 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B (SM/18768) | SM/18768 | 905.71 | 193 | NEW | 1 | Delayed | 6 | 23/08/2023 | 23/02/2025 | 12/09/2024 | 29/09/2023 | 53.63 | 52.95
182 | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . (SM/18536) | SM/18536 | 1196.31 | 531 | AUGMENTATION | 1 | Delayed | 24 | 26/07/2023 | 26/04/2024 | 29/09/2023 | 02/08/2023 | 290.26 | 290.26
183 | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10627) | SM/10627 | 774.74 | 2845 | AUGMENTATION | 1 | Delayed | 59 | 20/04/2022 | 31/03/2024 | 08/08/2023 | 03/06/2021 | 459.03 | 459.03
184 | KANDARA AND ADJOINING MOUJAS PWSS (SM/13487) | SM/13487 | 938.24 | 4166 | NEW | 1 | Delayed | 18 | 02/11/2022 | 31/07/2024 | 26/06/2024 | 10/01/2023 | 172.05 | 157.05
185 | MADHUPUR PIPED WATER SUPPLY SCHEME. (SM/15955) | SM/15955 | 900.63 | 1771 | NEW | 1 | Delayed | 6 | 22/02/2023 | 30/06/2025 | 14/05/2024 | 11/11/2022 | 54.43 | 33.31
186 | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15920) | SM/15920 | 610.97 | 284 | AUGMENTATION | 1 | Delayed | 7 | 22/02/2023 | 31/03/2024 | 05/02/2024 | 10/05/2022 | 44.98 | 44.98
187 | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16394) | SM/16394 | 242.17 | 925 | NEW | 1 | Delayed | 10 | 28/02/2023 | 31/12/2024 | 22/05/2024 | 28/03/2023 | 23.83 | 13.98
188 | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15746) | SM/15746 | 975.16 | 3268 | AUGMENTATION | 1 | Delayed | 25 | 20/02/2023 | 31/03/2025 | 06/01/2025 | 05/10/2021 | 246.78 | 246.78
189 | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS (SM/16816) | SM/16816 | 549.36 | 1183 | NEW | 1 | Delayed | 14 | 13/03/2023 | 13/09/2024 | 22/01/2024 | 03/11/2023 | 78.61 | 78.61
190 | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. (SM/18687) | SM/18687 | 1027.21 | 2619 | NEW | 1 | Delayed | 2 | 04/08/2023 | 31/03/2024 | 07/09/2023 | 11/11/2022 | 22.53 | 22.53
191 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis (SM/07925) | SM/07925 | 69.2 | 241 | RETROFITTING | 1 | Delayed | 67 | 19/01/2021 | 31/12/2025 | 04/04/2024 | 05/10/2023 | 46.08 | 23.55
192 | TENTULIA AND ADJOINING MOUJAS PWSS (SM/13998) | SM/13998 | 337.8 | 654 | NEW | 1 | Delayed | 35 | 01/12/2022 | 31/03/2024 | 16/02/2024 | 13/01/2023 | 117.17 | 117.17
193 | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/13927) | SM/13927 | 758.89 | 835 | AUGMENTATION | 1 | Delayed | 7 | 29/11/2022 | 31/03/2024 | 12/07/2023 | 13/01/2021 | 52.83 | 52.83
194 | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. (SM/14945) | SM/14945 | 941.94 | 4045 | AUGMENTATION | 1 | Delayed | 21 | 03/02/2023 | 31/03/2024 | 12/07/2023 | 03/02/2022 | 197.17 | 197.17
195 | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. (SM/16409) | SM/16409 | 800.01 | 1014 | AUGMENTATION | 1 | Delayed | 23 | 28/02/2023 | 31/03/2026 | 11/12/2024 | 10/08/2023 | 180.4 | 157.59
196 | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/15916) | SM/15916 | 982.94 | 182 | AUGMENTATION | 1 | Delayed | 50 | 22/02/2023 | 31/03/2024 | 28/09/2023 | 03/02/2022 | 486.65 | 486.65
197 | BADUA AND IT'S ADJOINING MOUJAS (SM/15682) | SM/15682 | 736.24 | 2253 | NEW | 1 | Delayed | 2 | 20/02/2023 | 31/03/2024 | 12/09/2023 | 08/05/2023 | 14.75 | 14.75
198 | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/16770) | SM/16770 | 981.89 | 2 | AUGMENTATION | 1 | Delayed | 21 | 13/03/2023 | 31/12/2024 | 15/04/2024 | 17/03/2023 | 204.04 | 204.04
199 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI (SM/19017) | SM/19017 | 102.66 | 984 | AUGMENTATION | 1 | Delayed | 4 | 27/10/2023 | 31/03/2025 | 09/11/2023 | 05/10/2021 | 4.48 | 4.48
200 | BHABKI PIPED WATER SUPPLY SCHEME. (SM/18555) | SM/18555 | 1047.42 | 2197 | NEW | 1 | Delayed | 10 | 31/07/2023 | 31/03/2024 | 06/02/2024 | 11/11/2022 | 99.61 | 99.61
201 | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. (SM/18688) | SM/18688 | 1068.33 | 910 | AUGMENTATION | 1 | Delayed | 30 | 04/08/2023 | 31/03/2024 | 12/09/2023 | 19/01/2022 | 316.75 | 316.75
202 | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/18773) | SM/18773 | 994.52 | 4 | AUGMENTATION | 1 | Delayed | 1 | 25/08/2023 | 31/12/2025 | 25/09/2024 | 01/09/2023 | 8.36 | 8.36
203 | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. (SM/16243) | SM/16243 | 660.65 | 1419 | AUGMENTATION | 1 | Delayed | 9 | 23/02/2023 | 31/03/2024 | 25/07/2023 | 01/11/2022 | 60.98 | 25.62
204 | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/15838) | SM/15838 | 745.29 | 313 | AUGMENTATION | 1 | Delayed | 68 | 20/02/2023 | 31/03/2024 | 28/09/2023 | 08/01/2021 | 506.06 | 506.06
205 | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. (SM/16171) | SM/16171 | 819.74 | 967 | AUGMENTATION | 1 | Delayed | 9 | 22/02/2023 | 28/02/2025 | 04/04/2024 | 10/08/2023 | 72.49 | 72.49
206 | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15923) | SM/15923 | 633 | 439 | AUGMENTATION | 1 | Delayed | 8 | 22/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 50.72 | 50.72
207 | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16274) | SM/16274 | 932.74 | 3629 | NEW | 1 | Delayed | 3 | 24/02/2023 | 31/03/2024 | 12/09/2023 | 16/06/2023 | 28.7 | 28.7
208 | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. (SM/16419) | SM/16419 | 692.82 | 870 | AUGMENTATION | 1 | Delayed | 8 | 28/02/2023 | 30/06/2024 | 19/03/2024 | 10/08/2023 | 55.54 | 55.54
209 | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15918) | SM/15918 | 518.94 | 2308 | AUGMENTATION | 1 | Delayed | 2 | 22/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 8.66 | 8.66
210 | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. (SM/16899) | SM/16899 | 575.4 | 445 | AUGMENTATION | 1 | Delayed | 6 | 13/03/2023 | 13/12/2023 | 15/10/2023 | 03/02/2022 | 35.35 | 26.95
211 | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. (SM/16870) | SM/16870 | 945.91 | 2315 | AUGMENTATION | 1 | Delayed | 2 | 13/03/2023 | 31/12/2024 | 12/12/2023 | 10/08/2023 | 22.31 | 22.31
212 | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15752) | SM/15752 | 863.23 | 5674 | AUGMENTATION | 1 | Delayed | 4 | 20/02/2023 | 31/03/2024 | 22/01/2024 | 10/05/2022 | 37.53 | 37.53
213 | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. (SM/18471) | SM/18471 | 1118.46 | 2622 | AUGMENTATION | 1 | Delayed | 0 | 20/07/2023 | 31/03/2024 | 24/08/2023 | 03/02/2022 | 3.68 | 3.68
214 | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. (SM/19016) | SM/19016 | 826.01 | 2 | AUGMENTATION | 1 | Delayed | 4 | 27/10/2023 | 31/03/2024 | 18/01/2024 | 28/10/2023 | 31.76 | 31.76
215 | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. (SM/18982) | SM/18982 | 220.24 | 834 | AUGMENTATION | 1 | Delayed | 0 | 11/10/2023 | 31/03/2025 | 22/02/2024 | 08/01/2024 | 0 | 0
216 | CHARKA PIPE WATER SUPPLY SCHEME. (SM/18465) | SM/18465 | 1020.87 | 2278 | NEW | 1 | Delayed | 3 | 20/07/2023 | 31/03/2024 | 03/08/2023 | 11/11/2022 | 32 | 32
217 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10631) | SM/10631 | 607.53 | 351 | AUGMENTATION | 1 | Delayed | 21 | 20/04/2022 | 31/03/2024 | 13/03/2024 | 10/08/2021 | 130.08 | 130.08
218 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10633) | SM/10633 | 939.08 | 364 | AUGMENTATION | 1 | Delayed | 81 | 20/04/2022 | 31/03/2024 | 08/08/2023 | 16/08/2022 | 758.96 | 758.96
219 | GHORAMARA PIPED WATER SUPPLY SCHEME. (SM/15049) | SM/15049 | 704.88 | 567 | NEW | 1 | Delayed | 3 | 04/02/2023 | 31/03/2024 | 12/07/2023 | 10/02/2023 | 24.47 | 24.47
220 | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/15061) | SM/15061 | 807.52 | 1034 | AUGMENTATION | 1 | Delayed | 7 | 04/02/2023 | 31/03/2024 | 06/02/2024 | 10/05/2022 | 59.77 | 59.77
221 | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/15267) | SM/15267 | 888.21 | 3225 | AUGMENTATION | 1 | Delayed | 6 | 07/02/2023 | 31/03/2024 | 05/10/2023 | 28/08/2023 | 54.29 | 54.29
222 | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/16546) | SM/16546 | 541.56 | 312 | AUGMENTATION | 1 | Delayed | 1 | 10/03/2023 | 30/04/2024 | 28/09/2023 | 04/09/2023 | 4.47 | 4.47
223 | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. (SM/16209) | SM/16209 | 40.62 | 107 | NEW | 1 | Delayed | 6 | 23/02/2023 | 31/03/2024 | 28/09/2023 | 01/11/2022 | 2.37 | 2.37
224 | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/16624) | SM/16624 | 606.43 | 772 | AUGMENTATION | 1 | Delayed | 13 | 14/03/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 79.13 | 79.13
225 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10632) | SM/10632 | 567.12 | 366 | AUGMENTATION | 2 | Delayed | 22 | 20/04/2022 | 31/03/2024 | 26/09/2023 | 28/06/2022 | 124.1 | 106.16
226 | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I (SM/14924) | SM/14924 | 881.94 | 3275 | AUGMENTATION | 2 | Delayed | 14 | 03/02/2023 | 31/12/2024 | 21/05/2024 | 14/06/2023 | 125.11 | 125.11
227 | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. (SM/15047) | SM/15047 | 828.25 | 1536 | NEW | 2 | Delayed | 6 | 04/02/2023 | 31/12/2024 | 06/08/2024 | 11/11/2022 | 48.58 | 43.45
228 | SITARAMPUR PIPED WATER SUPPLY SCHEME. (SM/15048) | SM/15048 | 864.73 | 1401 | NEW | 2 | Delayed | 24 | 04/02/2023 | 31/12/2024 | 29/04/2024 | 10/04/2023 | 204.41 | 204.41
229 | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16402) | SM/16402 | 681.2 | 2 | AUGMENTATION | 2 | Delayed | 13 | 28/02/2023 | 31/03/2024 | 29/02/2024 | 10/05/2022 | 89.54 | 89.54
230 | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. (SM/16174) | SM/16174 | 641.72 | 557 | AUGMENTATION | 2 | Delayed | 5 | 22/02/2023 | 31/12/2025 | 25/09/2024 | 06/07/2023 | 31.08 | 31.08
231 | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. (SM/16420) | SM/16420 | 890.75 | 1370 | AUGMENTATION | 2 | Delayed | 10 | 28/02/2023 | 30/06/2024 | 19/03/2024 | 10/08/2023 | 86.21 | 86.21
232 | GHOLLA AND ADJOINING MOUJAS PWSS (SM/18581) | SM/18581 | 1544.31 | 4831 | NEW | 2 | Delayed | 3 | 31/07/2023 | 31/07/2025 | 15/04/2024 | 08/08/2023 | 40.9 | 40.9
233 | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. (SM/19126) | SM/19126 | 1098.41 | 3357 | NEW | 2 | Delayed | 10 | 03/01/2024 | 31/03/2025 | 25/11/2024 | 16/01/2024 | 105 | 105
234 | BAHAGALPUR PIPED WATER SUPPLY SCHEME. (SM/18516) | SM/18516 | 1348.64 | 3715 | NEW | 2 | Delayed | 17 | 26/07/2023 | 31/03/2024 | 29/02/2024 | 11/11/2022 | 229.8 | 229.8
235 | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. (SM/14427) | SM/14427 | 679.22 | 379 | AUGMENTATION | 2 | Delayed | 18 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 125.57 | 125.57
236 | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. (SM/16412) | SM/16412 | 466.43 | 1108 | AUGMENTATION | 2 | Delayed | 8 | 28/02/2023 | 31/12/2025 | 27/03/2024 | 05/10/2021 | 36.09 | 36.09
237 | KOHETPUR PIPE WATER SUPPLY SCHEME. (SM/15945) | SM/15945 | 824.91 | 1358 | NEW | 2 | Delayed | 24 | 22/02/2023 | 30/04/2025 | 02/07/2024 | 11/11/2022 | 200.34 | 200.34
238 | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16768) | SM/16768 | 792.83 | 879 | AUGMENTATION | 2 | Delayed | 7 | 13/03/2023 | 31/12/2024 | 14/11/2024 | 10/05/2022 | 57.09 | 53.62
239 | BHAGWANGOLA AND ADJOING MOUJAS PWSS (SM/16780) | SM/16780 | 991.57 | 2896 | NEW | 2 | Delayed | 3 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 32.85 | 32.85
240 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. (SM/18364) | SM/18364 | 1761.66 | 356 | AUGMENTATION | 2 | Delayed | 16 | 11/07/2023 | 11/04/2024 | 29/09/2023 | 10/08/2023 | 288.98 | 288.98
241 | BAIDYNATHPUR ADJOINING MOUJA PWSS (SM/18580) | SM/18580 | 1218.84 | 4264 | NEW | 2 | Delayed | 15 | 31/07/2023 | 31/07/2025 | 15/01/2024 | 04/08/2023 | 181.38 | 181.38
242 | KHAMARDIAR AND ADJOINING MOUJAS PWSS (SM/18690) | SM/18690 | 1308.69 | 3022 | NEW | 2 | Delayed | 40 | 04/08/2023 | 04/08/2025 | 03/06/2024 | 10/08/2023 | 522.57 | 522.57
243 | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. (SM/18705) | SM/18705 | 1703.43 | 766 | AUGMENTATION | 2 | Delayed | 19 | 04/08/2023 | 31/05/2025 | 25/11/2024 | 24/08/2023 | 323.2 | 305.64
244 | MOLLA PIPED WATER SUPPLY SCHEME (SM/14947) | SM/14947 | 492.25 | 1203 | NEW | 2 | Delayed | 16 | 04/02/2023 | 31/03/2024 | 16/02/2024 | 10/02/2023 | 77.54 | 77.54
245 | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. (SM/16246) | SM/16246 | 855.97 | 1183 | AUGMENTATION | 2 | Delayed | 9 | 23/02/2023 | 30/06/2024 | 19/03/2024 | 22/02/2022 | 75.16 | 75.16
246 | MAHISHASTHALI AND ADJOINING MOUJAS PWSS (SM/16015) | SM/16015 | 803.16 | 2236 | NEW | 2 | Delayed | 4 | 22/02/2023 | 31/12/2024 | 21/05/2024 | 15/05/2023 | 35 | 35
247 | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. (SM/16544) | SM/16544 | 841.25 | 1555 | AUGMENTATION | 2 | Delayed | 6 | 10/03/2023 | 31/03/2025 | 03/12/2024 | 05/04/2023 | 47.96 | 47.96
248 | BAJITPUR PIPED WATER SUPPLY SCHEME. (SM/16216) | SM/16216 | 497.21 | 899 | NEW | 2 | Delayed | 22 | 23/02/2023 | 31/03/2025 | 30/12/2024 | 11/11/2022 | 108.96 | 108.96
249 | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16113) | SM/16113 | 245.5 | 523 | NEW | 2 | Delayed | 29 | 22/02/2023 | 31/12/2024 | 16/04/2024 | 14/07/2023 | 72.36 | 72.36
250 | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. (SM/15745) | SM/15745 | 558.5 | 532 | AUGMENTATION | 2 | Delayed | 26 | 20/02/2023 | 31/03/2025 | 03/12/2024 | 03/02/2022 | 146.28 | 140.77
251 | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. (SM/19125) | SM/19125 | 1124.55 | 1844 | AUGMENTATION | 2 | Delayed | 1 | 03/01/2024 | 31/12/2025 | 30/09/2024 | 11/01/2024 | 8.49 | 8.49
252 | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. (SM/18832) | SM/18832 | 2107.4 | 6026 | NEW | 2 | Delayed | 2 | 21/09/2023 | 21/09/2025 | 13/12/2024 | 29/09/2023 | 39.19 | 13.19
253 | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/18756) | SM/18756 | 974.86 | 212 | AUGMENTATION | 2 | Delayed | 19 | 21/08/2023 | 31/03/2025 | 25/11/2024 | 24/08/2023 | 180.98 | 176.64
254 | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. (SM/10811) | SM/10811 | 694.67 | 174 | AUGMENTATION | 2 | Delayed | 36 | 25/05/2022 | 31/12/2023 | 12/06/2023 | 05/04/2023 | 251.4 | 251.4
255 | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. (SM/15837) | SM/15837 | 408.6 | 5 | AUGMENTATION | 2 | Delayed | 45 | 20/02/2023 | 31/03/2024 | 12/09/2023 | 02/03/2023 | 185.43 | 185.43
256 | BAURIPUNI PIPED WATER SUPPLY SCHEME. (SM/16551) | SM/16551 | 813.92 | 1222 | NEW | 2 | Delayed | 8 | 10/03/2023 | 31/03/2024 | 29/02/2024 | 16/06/2023 | 68.52 | 68.52
257 | SERPUR (CT) PIPE WATER SUPPLY SCHEME. (SM/16481) | SM/16481 | 938.46 | 2301 | NEW | 2 | Delayed | 16 | 02/03/2023 | 31/12/2024 | 02/07/2024 | 11/11/2022 | 151.12 | 151.12
258 | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE (SM/16408) | SM/16408 | 784.86 | 1593 | AUGMENTATION | 2 | Delayed | 5 | 28/02/2023 | 31/03/2025 | 22/07/2024 | 10/05/2022 | 39.77 | 39.77
259 | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16376) | SM/16376 | 666.66 | 1374 | NEW | 2 | Delayed | 7 | 28/02/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 47.89 | 47.89
260 | DHANDANGA AMD IT'S ADJOINING MOUJAS (SM/16392) | SM/16392 | 258.1 | 855 | NEW | 2 | Delayed | 7 | 28/02/2023 | 31/08/2024 | 06/05/2024 | 16/03/2023 | 17.81 | 17.81
261 | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/16397) | SM/16397 | 828.77 | 1356 | AUGMENTATION | 2 | Delayed | 51 | 28/02/2023 | 31/03/2024 | 22/01/2024 | 11/05/2023 | 419.26 | 413.77
262 | KALIAGACHHI AND ADJOINING MOUJAS PWSS (SM/16789) | SM/16789 | 390.77 | 458 | NEW | 2 | Delayed | 3 | 13/03/2023 | 13/09/2024 | 21/05/2024 | 10/08/2023 | 12.24 | 10.22
263 | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. (SM/15748) | SM/15748 | 789.55 | 1050 | AUGMENTATION | 2 | Delayed | 17 | 20/02/2023 | 31/05/2024 | 18/03/2024 | 09/08/2023 | 137.47 | 137.47
264 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. (SM/16764) | SM/16764 | 373.08 | 91 | AUGMENTATION | 2 | Delayed | 25 | 13/03/2023 | 31/12/2024 | 14/06/2024 | 03/02/2022 | 91.9 | 91.9
265 | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. (SM/16863) | SM/16863 | 556.98 | 1085 | AUGMENTATION | 2 | Delayed | 20 | 13/03/2023 | 31/12/2025 | 27/03/2024 | 09/10/2023 | 113.28 | 113.28
266 | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, (SM/18775) | SM/18775 | 1549.76 | 3986 | AUGMENTATION | 2 | Delayed | 7 | 25/08/2023 | 31/03/2025 | 28/11/2024 | 03/10/2023 | 102.46 | 33.51
267 | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. (SM/19124) | SM/19124 | 3659.55 | 1468 | AUGMENTATION | 2 | Delayed | 0 | 03/01/2024 | 31/10/2025 | 26/11/2024 | 11/01/2024 | 11.34 | 0
268 | NASIPUR AND ADJOINIONG MOUJAS PWSS (SM/18517) | SM/18517 | 1865.49 | 6219 | NEW | 2 | Delayed | 4 | 26/07/2023 | 26/07/2025 | 21/05/2024 | 11/08/2023 | 67.56 | 67.56
269 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A (SM/18767) | SM/18767 | 980.49 | 1453 | NEW | 2 | Delayed | 7 | 23/08/2023 | 23/02/2025 | 26/12/2024 | 07/09/2023 | 64.67 | 59.46
270 | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . (SM/16242) | SM/16242 | 500.75 | 528 | AUGMENTATION | 2 | Delayed | 1 | 24/02/2023 | 30/04/2025 | 30/05/2024 | 10/05/2022 | 3.82 | 3.82
271 | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . (SM/16217) | SM/16217 | 898.14 | 1961 | NEW | 2 | Delayed | 5 | 23/02/2023 | 31/12/2024 | 02/07/2024 | 11/11/2022 | 42.19 | 42.19
272 | Augmentation of Salar Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. (SM/16423) | SM/16423 | 540.61 | 445 | AUGMENTATION | 2 | Delayed | 0 | 28/02/2023 | 31/12/2025 | 27/03/2024 | 21/09/2023 | 1.62 | 1.62
273 | MASLA AND ADJOINING MOUJAS PWSS (SM/16529) | SM/16529 | 367.21 | 945 | NEW | 2 | Delayed | 23 | 02/03/2023 | 31/03/2024 | 29/02/2024 | 19/06/2023 | 83.83 | 83.83
274 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. (SM/18543) | SM/18543 | 1120.71 | 594 | AUGMENTATION | 2 | Delayed | 2 | 26/07/2023 | 31/12/2024 | 04/06/2024 | 10/08/2023 | 18.04 | 18.04
275 | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) (SM/19189) | SM/19189 | 38369 | 32512 | AUGMENTATION | 2 | Delayed | 8 | 07/03/2024 | 31/12/2024 | 09/09/2024 | 15/03/2024 | 3200.77 | 3109.4
276 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. (SM/18702) | SM/18702 | 1288.62 | 3406 | AUGMENTATION | 2 | Delayed | 2 | 04/08/2023 | 04/05/2024 | 12/10/2023 | 19/07/2022 | 21.78 | 21.78
277 | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. (SM/14735) | SM/14735 | 915.51 | 954 | AUGMENTATION | 2 | Delayed | 8 | 31/01/2023 | 31/12/2024 | 21/05/2024 | 19/06/2023 | 74.8 | 74.8
278 | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . (SM/14737) | SM/14737 | 808.29 | 1059 | AUGMENTATION | 2 | Delayed | 22 | 31/01/2023 | 31/12/2024 | 21/05/2024 | 24/03/2023 | 177.76 | 177.76
279 | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . (SM/14739) | SM/14739 | 244.16 | 797 | AUGMENTATION | 2 | Delayed | 30 | 31/01/2023 | 31/12/2024 | 21/05/2024 | 17/02/2023 | 74.04 | 74.04
280 | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. (SM/15067) | SM/15067 | 959.55 | 2416 | AUGMENTATION | 2 | Delayed | 22 | 04/02/2023 | 31/08/2025 | 13/12/2024 | 01/11/2022 | 210.14 | 188.23
281 | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. (SM/15069) | SM/15069 | 998.83 | 1912 | AUGMENTATION | 2 | Delayed | 66 | 04/02/2023 | 31/12/2024 | 15/04/2024 | 01/11/2022 | 659.14 | 659.14
282 | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. (SM/18777) | SM/18777 | 1121.12 | 1915 | AUGMENTATION | 2 | Delayed | 22 | 25/08/2023 | 31/12/2024 | 28/11/2024 | 29/08/2023 | 247.56 | 226.15
283 | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/18740) | SM/18740 | 553.64 | 1439 | AUGMENTATION | 2 | Delayed | 24 | 17/08/2023 | 17/05/2024 | 01/02/2024 | 22/08/2023 | 134.54 | 134.54
284 | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. (SM/18704) | SM/18704 | 1031.59 | 895 | AUGMENTATION | 2 | Delayed | 26 | 04/08/2023 | 31/12/2024 | 01/10/2024 | 18/08/2023 | 267.29 | 258.7
285 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10612) | SM/10612 | 480.94 | 1440 | AUGMENTATION | 2 | Delayed | 94 | 19/04/2022 | 31/03/2024 | 28/09/2023 | 22/04/2022 | 450.03 | 450.03
286 | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II (SM/12580) | SM/12580 | 244.68 | 631 | AUGMENTATION | 2 | Delayed | 25 | 15/09/2022 | 31/03/2024 | 15/09/2023 | 02/03/2023 | 60.06 | 60.06
287 | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. (SM/15519) | SM/15519 | 969.51 | 385 | AUGMENTATION | 2 | Delayed | 16 | 16/02/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 156.66 | 156.66
288 | CHANDAMARI PIPED WATER SUPPLY SCHEME. (SM/16218) | SM/16218 | 520.98 | 786 | NEW | 2 | Delayed | 3 | 23/02/2023 | 31/12/2024 | 02/07/2024 | 11/11/2022 | 14.83 | 10.52
289 | GUNDIRIA AND ADJIONING MOUJAS PWSS (SM/16110) | SM/16110 | 216.8 | 687 | NEW | 2 | Delayed | 6 | 22/02/2023 | 31/03/2024 | 06/02/2024 | 17/07/2023 | 12.82 | 12.82
290 | KESABPUR AND ADJOINING MOUJAS PWSS (SM/16788) | SM/16788 | 661.59 | 1256 | NEW | 2 | Delayed | 25 | 13/03/2023 | 13/09/2024 | 29/02/2024 | 17/05/2023 | 168.58 | 168.58
291 | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/16754) | SM/16754 | 526.89 | 10 | AUGMENTATION | 2 | Delayed | 18 | 13/03/2023 | 31/12/2024 | 23/07/2024 | 16/06/2023 | 95.39 | 95.39
292 | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10630) | SM/10630 | 953.7 | 990 | AUGMENTATION | 2 | Delayed | 63 | 20/04/2022 | 31/03/2024 | 13/03/2024 | 07/07/2022 | 602.63 | 602.63
293 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. (SM/12589) | SM/12589 | 442.96 | 373 | AUGMENTATION | 2 | Delayed | 16 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 70.32 | 70.32
294 | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. (SM/16241) | SM/16241 | 291.78 | 329 | AUGMENTATION | 2 | Delayed | 18 | 24/02/2023 | 31/03/2025 | 05/12/2024 | 10/08/2023 | 53.81 | 25.61
295 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . (SM/15268) | SM/15268 | 820.5 | 1159 | AUGMENTATION | 2 | Delayed | 4 | 07/02/2023 | 31/08/2025 | 27/03/2024 | 03/02/2022 | 35.22 | 35.22
296 | GOKUL CHAK PIPED WATER SUPPLY SCHEME . (SM/16043) | SM/16043 | 413.88 | 834 | NEW | 2 | Delayed | 3 | 22/02/2023 | 31/03/2025 | 06/01/2025 | 01/11/2022 | 13.34 | 13.34
297 | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. (SM/16175) | SM/16175 | 765.79 | 400 | AUGMENTATION | 2 | Delayed | 34 | 22/02/2023 | 31/03/2024 | 12/03/2024 | 22/05/2023 | 261.46 | 261.46
298 | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16377) | SM/16377 | 439.33 | 814 | NEW | 2 | Delayed | 17 | 28/02/2023 | 31/08/2024 | 05/08/2024 | 28/04/2023 | 73.35 | 73.35
299 | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. (SM/18590) | SM/18590 | 1563.27 | 1178 | AUGMENTATION | 2 | Delayed | 12 | 31/07/2023 | 31/12/2025 | 11/11/2024 | 24/08/2023 | 184.54 | 184.54
300 | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. (SM/18689) | SM/18689 | 2084.84 | 6026 | NEW | 2 | Delayed | 7 | 04/08/2023 | 31/03/2025 | 03/12/2024 | 11/11/2022 | 138.77 | 130.05
301 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. (SM/18703) | SM/18703 | 2237.11 | 1626 | AUGMENTATION | 2 | Delayed | 3 | 04/08/2023 | 31/12/2024 | 20/08/2024 | 19/07/2022 | 68.36 | 68.36
302 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. (SM/11231) | SM/11231 | 150.76 | 172 | AUGMENTATION | 3 | Delayed | 21 | 22/06/2022 | 31/03/2024 | 28/09/2023 | 10/05/2022 | 32.07 | 32.07
303 | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16375) | SM/16375 | 620.94 | 1198 | NEW | 3 | Delayed | 31 | 28/02/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 191.6 | 191.6
304 | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/15070) | SM/15070 | 847.95 | 335 | AUGMENTATION | 3 | Delayed | 62 | 04/02/2023 | 31/03/2024 | 08/02/2024 | 03/02/2022 | 526.62 | 518.53
305 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . (SM/18529) | SM/18529 | 1074.75 | 1091 | AUGMENTATION | 3 | Delayed | 37 | 26/07/2023 | 26/04/2024 | 18/03/2024 | 04/08/2023 | 400.52 | 400.52
306 | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. (SM/14943) | SM/14943 | 733.18 | 1391 | AUGMENTATION | 3 | Delayed | 4 | 04/02/2023 | 31/03/2024 | 12/07/2023 | 03/02/2022 | 28.33 | 28.33
307 | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. (SM/16177) | SM/16177 | 662.59 | 735 | AUGMENTATION | 3 | Delayed | 10 | 22/02/2023 | 31/12/2025 | 30/09/2024 | 27/04/2022 | 67.27 | 67.27
308 | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. (SM/16380) | SM/16380 | 994.64 | 1169 | AUGMENTATION | 3 | Delayed | 16 | 28/02/2023 | 31/03/2024 | 29/02/2024 | 25/04/2023 | 161.79 | 155.79
309 | NEZAMPUR PIPED WATER SUPPLY SCHEME. (SM/18185) | SM/18185 | 613.23 | 704 | NEW | 3 | Delayed | 7 | 31/03/2023 | 31/12/2024 | 06/08/2024 | 16/06/2023 | 40.68 | 36.46
310 | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . (SM/14738) | SM/14738 | 857.82 | 863 | AUGMENTATION | 3 | Delayed | 16 | 31/01/2023 | 31/12/2024 | 26/11/2024 | 24/03/2023 | 133.66 | 116.9
311 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . (SM/14051) | SM/14051 | 360.07 | 57 | AUGMENTATION | 3 | Delayed | 16 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 20/02/2023 | 56.22 | 56.22
312 | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/13997) | SM/13997 | 390.02 | 1415 | AUGMENTATION | 3 | Delayed | 42 | 01/12/2022 | 31/12/2024 | 30/08/2024 | 10/05/2022 | 162 | 162
313 | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16395) | SM/16395 | 246.58 | 909 | NEW | 3 | Delayed | 28 | 28/02/2023 | 31/03/2024 | 15/01/2024 | 10/04/2023 | 68.13 | 68.13
314 | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. (SM/16427) | SM/16427 | 687.2 | 1163 | AUGMENTATION | 3 | Delayed | 13 | 28/02/2023 | 30/04/2025 | 30/07/2024 | 29/03/2023 | 91.46 | 91.46
315 | ALAMPUR AND ADJOINING MOPUJAS PWSS (SM/16813) | SM/16813 | 444.78 | 960 | NEW | 3 | Delayed | 34 | 13/03/2023 | 13/09/2024 | 16/02/2024 | 22/10/2023 | 150.16 | 150.16
316 | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16769) | SM/16769 | 220.12 | 615 | AUGMENTATION | 3 | Delayed | 8 | 13/03/2023 | 31/03/2025 | 03/12/2024 | 10/05/2022 | 17.23 | 17.23
317 | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. (SM/18692) | SM/18692 | 1499.1 | 3283 | NEW | 3 | Delayed | 27 | 04/08/2023 | 31/07/2024 | 26/06/2024 | 11/11/2022 | 400.31 | 400.31
318 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar (SM/12579) | SM/12579 | 995.02 | 1965 | AUGMENTATION | 3 | Delayed | 3 | 15/09/2022 | 31/03/2025 | 31/07/2024 | 17/08/2023 | 26.08 | 21.29
319 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. (SM/18384) | SM/18384 | 2055.8 | 1712 | AUGMENTATION | 3 | Delayed | 3 | 11/07/2023 | 31/08/2025 | 04/04/2024 | 10/08/2023 | 59.28 | 59.28
320 | HAMIDPUR AND ADJOINING MOUJAS PWSS (SM/14867) | SM/14867 | 271.8 | 978 | NEW | 3 | Delayed | 36 | 03/02/2023 | 31/08/2024 | 03/06/2024 | 27/03/2023 | 98.64 | 98.64
321 | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16549) | SM/16549 | 641.21 | 2133 | NEW | 4 | Delayed | 5 | 10/03/2023 | 31/03/2024 | 22/01/2024 | 24/03/2023 | 35.22 | 25.62
322 | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. (SM/12586) | SM/12586 | 512.37 | 552 | AUGMENTATION | 4 | Delayed | 23 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 117.84 | 117.84
323 | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. (SM/14426) | SM/14426 | 501.29 | 216 | AUGMENTATION | 4 | Delayed | 10 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 51.39 | 51.39
324 | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. (SM/14944) | SM/14944 | 548.31 | 650 | AUGMENTATION | 4 | Delayed | 14 | 04/02/2023 | 30/06/2024 | 09/11/2023 | 03/02/2022 | 76.26 | 76.26
325 | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. (SM/14069) | SM/14069 | 988.06 | 889 | AUGMENTATION | 4 | Delayed | 46 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 25/04/2023 | 451.13 | 451.13
326 | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . (SM/15227) | SM/15227 | 804.99 | 342 | AUGMENTATION | 4 | Delayed | 0 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 20/04/2023 | 0 | 0
327 | Augmentation of Bali Zone-III pipe water supply scheme . (SM/15228) | SM/15228 | 842.2 | 363 | AUGMENTATION | 4 | Delayed | 14 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 19/04/2023 | 118.84 | 118.84
328 | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16407) | SM/16407 | 969.05 | 213 | AUGMENTATION | 4 | Delayed | 1 | 28/02/2023 | 31/03/2024 | 12/07/2023 | 10/05/2022 | 13.98 | 13.98
329 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. (SM/16418) | SM/16418 | 578.91 | 370 | AUGMENTATION | 4 | Delayed | 16 | 28/02/2023 | 31/03/2024 | 19/03/2024 | 03/02/2022 | 90.26 | 90.26
330 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I (SM/11164) | SM/11164 | 284.98 | 1687 | AUGMENTATION | 4 | Delayed | 26 | 02/06/2022 | 31/12/2024 | 23/03/2024 | 16/01/2023 | 72.83 | 72.83
331 | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. (SM/14951) | SM/14951 | 557.12 | 121 | AUGMENTATION | 4 | Delayed | 0 | 04/02/2023 | 31/12/2024 | 21/05/2024 | 20/04/2023 | 2.56 | 2.56
332 | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS (SM/16787) | SM/16787 | 562.54 | 782 | NEW | 4 | Delayed | 21 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 115.57 | 115.57
333 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . (SM/14066) | SM/14066 | 613 | 299 | AUGMENTATION | 4 | Delayed | 32 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 195.56 | 195.56
334 | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS (SM/15996) | SM/15996 | 415.43 | 577 | NEW | 4 | Delayed | 9 | 22/02/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 39.41 | 39.41
335 | NAMOORAHAR AND ADJOINING MOUJAS PWSS (SM/18186) | SM/18186 | 613.13 | 1042 | NEW | 4 | Delayed | 27 | 30/03/2023 | 31/12/2024 | 21/05/2024 | 16/08/2023 | 165.67 | 165.67
336 | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME (SM/18699) | SM/18699 | 4390.37 | 11693 | AUGMENTATION | 4 | Delayed | 10 | 04/08/2023 | 31/08/2025 | 15/09/2023 | 05/09/2023 | 440.22 | 440.22
337 | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III (SM/15231) | SM/15231 | 527.09 | 330 | AUGMENTATION | 4 | Delayed | 1 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 22/03/2023 | 7.74 | 7.74
338 | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . (SM/15234) | SM/15234 | 624.73 | 558 | AUGMENTATION | 4 | Delayed | 6 | 07/02/2023 | 31/12/2024 | 26/06/2024 | 14/03/2023 | 38.41 | 38.41
339 | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. (SM/16456) | SM/16456 | 478.54 | 243 | AUGMENTATION | 4 | Delayed | 2 | 02/03/2023 | 31/03/2024 | 12/07/2023 | 03/02/2022 | 11.31 | 11.31
340 | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/15922) | SM/15922 | 522.7 | 2 | AUGMENTATION | 4 | Delayed | 35 | 22/02/2023 | 31/03/2024 | 04/10/2023 | 03/02/2022 | 180.85 | 180.85
341 | NABADURGA AND ADJOINING MOUJAS PWSS (SM/13934) | SM/13934 | 917.51 | 2909 | NEW | 4 | Delayed | 26 | 29/11/2022 | 31/03/2024 | 07/03/2024 | 20/03/2023 | 241.68 | 232.68
342 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. (SM/15232) | SM/15232 | 903.97 | 1576 | AUGMENTATION | 4 | Delayed | 2 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 25/04/2023 | 15.09 | 15.09
343 | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha (SM/12581) | SM/12581 | 582.29 | 1154 | AUGMENTATION | 5 | Delayed | 6 | 15/09/2022 | 31/12/2024 | 20/05/2024 | 08/03/2022 | 32.06 | 32.06
344 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11570) | SM/11570 | 943.42 | 1081 | AUGMENTATION | 5 | Delayed | 30 | 22/07/2022 | 31/03/2024 | 22/01/2024 | 03/09/2021 | 284.93 | 284.93
345 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. (SM/14632) | SM/14632 | 631.26 | 711 | AUGMENTATION | 5 | Delayed | 24 | 31/01/2023 | 31/12/2024 | 20/09/2024 | 03/02/2022 | 153.42 | 143.42
346 | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16111) | SM/16111 | 124.95 | 274 | NEW | 5 | Delayed | 37 | 22/02/2023 | 31/12/2024 | 16/04/2024 | 18/07/2023 | 45.61 | 39.92
347 | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/11008) | SM/11008 | 231.96 | 1203 | AUGMENTATION | 5 | Delayed | 93 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 22/04/2022 | 215.36 | 215.36
348 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. (SM/12590) | SM/12590 | 188.66 | 212 | AUGMENTATION | 5 | Delayed | 33 | 15/09/2022 | 31/12/2024 | 26/06/2024 | 08/03/2022 | 61.42 | 61.42
349 | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. (SM/14047) | SM/14047 | 797.62 | 300 | AUGMENTATION | 5 | Delayed | 27 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 04/05/2023 | 218.54 | 218.54
350 | PUNRAPARA AND ADJOINING MOUJAS PWSS (SM/13932) | SM/13932 | 597.39 | 2494 | NEW | 5 | Delayed | 30 | 29/11/2022 | 31/12/2024 | 03/06/2024 | 16/03/2023 | 177.67 | 177.67
351 | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. (SM/14923) | SM/14923 | 775.12 | 369 | AUGMENTATION | 5 | Delayed | 10 | 03/02/2023 | 31/12/2024 | 21/05/2024 | 02/03/2023 | 80.07 | 70.32
352 | KOGRAM AND ADJOINING MOUJAS PWSS (SM/14507) | SM/14507 | 790.62 | 2256 | NEW | 5 | Delayed | 25 | 20/01/2023 | 31/03/2024 | 15/01/2024 | 10/04/2023 | 201.42 | 201.42
353 | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/14045) | SM/14045 | 753.28 | 410 | AUGMENTATION | 5 | Delayed | 37 | 12/12/2022 | 31/12/2024 | 20/05/2024 | 02/03/2023 | 279.19 | 279.19
354 | BISWANATHPUR PIPED WATER SUPPLY SCHEME. (SM/16553) | SM/16553 | 245.29 | 820 | NEW | 5 | Delayed | 28 | 10/03/2023 | 31/03/2024 | 22/01/2024 | 20/07/2023 | 69.79 | 69.79
355 | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. (SM/16283) | SM/16283 | 785.06 | 49 | AUGMENTATION | 5 | Delayed | 40 | 24/02/2023 | 31/03/2025 | 11/11/2024 | 01/11/2022 | 313.63 | 305.63
356 | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. (SM/16417) | SM/16417 | 709.24 | 2889 | AUGMENTATION | 5 | Delayed | 16 | 28/02/2023 | 31/12/2024 | 16/04/2024 | 10/05/2022 | 114.5 | 114.5
357 | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. (SM/16622) | SM/16622 | 603 | 176 | AUGMENTATION | 5 | Delayed | 12 | 14/03/2023 | 31/03/2024 | 19/03/2024 | 03/02/2022 | 73.45 | 73.45
358 | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. (SM/16051) | SM/16051 | 203.08 | 532 | NEW | 5 | Delayed | 26 | 22/02/2023 | 31/12/2024 | 30/10/2024 | 02/08/2023 | 52.12 | 48.65
359 | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. (SM/18831) | SM/18831 | 2130.14 | 1263 | AUGMENTATION | 5 | Delayed | 18 | 21/09/2023 | 31/12/2024 | 14/11/2024 | 28/01/2022 | 373.87 | 361.44
360 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . (SM/14736) | SM/14736 | 677.36 | 688 | AUGMENTATION | 5 | Delayed | 50 | 31/01/2023 | 31/12/2024 | 26/11/2024 | 14/03/2023 | 335.47 | 324.12
361 | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. (SM/12587) | SM/12587 | 671.73 | 1907 | AUGMENTATION | 5 | Delayed | 6 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 38.34 | 38.34
362 | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. (SM/14433) | SM/14433 | 838.18 | 671 | AUGMENTATION | 5 | Delayed | 10 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 14/03/2023 | 84.75 | 84.75
363 | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. (SM/14434) | SM/14434 | 770.8 | 1100 | AUGMENTATION | 5 | Delayed | 8 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 14/03/2023 | 61.8 | 61.8
364 | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/14044) | SM/14044 | 759.79 | 375 | AUGMENTATION | 5 | Delayed | 16 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 23/12/2022 | 118.3 | 118.3
365 | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. (SM/16566) | SM/16566 | 254.4 | 105 | AUGMENTATION | 5 | Delayed | 11 | 10/03/2023 | 31/03/2024 | 07/08/2023 | 17/11/2022 | 26.86 | 26.86
366 | KISMATTATLA AND ADJOINING MOUJAS PWSS (SM/16786) | SM/16786 | 517.85 | 890 | NEW | 5 | Delayed | 11 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 55.4 | 55.4
367 | GAYSABAD AND ADJOINING MOUJAS PWSS (SM/18453) | SM/18453 | 1240.43 | 4256 | NEW | 5 | Delayed | 28 | 20/07/2023 | 20/07/2025 | 06/02/2024 | 21/07/2023 | 344.23 | 342.43
368 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In (SM/07704) | SM/07704 | 64.01 | 5380 | RETROFITTING | 5 | Delayed | 0 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 18/10/2023 | 0 | 0
369 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur (SM/12584) | SM/12584 | 354.9 | 349 | AUGMENTATION | 5 | Delayed | 8 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 27.42 | 27.42
370 | SAMSASKAR AND ADJOINING MOUJAS PWSS (SM/16454) | SM/16454 | 758.25 | 1624 | NEW | 5 | Delayed | 9 | 02/03/2023 | 31/12/2024 | 21/05/2024 | 31/03/2023 | 71.64 | 71.64
371 | SIDDHESWARI & ADJOINING MOUJAS PWSS (SM/18312) | SM/18312 | 1223.05 | 3140 | NEW | 5 | Delayed | 34 | 26/06/2023 | 26/06/2025 | 20/09/2024 | 04/07/2023 | 412.29 | 412.29
372 | PAIKPARA AND ADJOINING MOUJAS PWSS (SM/18579) | SM/18579 | 1596.9 | 4532 | NEW | 5 | Delayed | 33 | 31/07/2023 | 31/07/2025 | 18/03/2024 | 04/08/2023 | 519.11 | 519.11
373 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Naopukuria (Zone-K) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/07702) | SM/07702 | 240.81 | 3269 | RETROFITTING | 5 | Delayed | 0 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/05/2023 | 0 | 0
374 | SAHAPUR AND ADJOINING MOUJAS PWSS (SM/18396) | SM/18396 | 1115.39 | 4588 | NEW | 5 | Delayed | 32 | 12/07/2023 | 12/07/2025 | 05/02/2024 | 17/07/2023 | 352.68 | 305.9
375 | BRAHMANDIHI AND ADJOINING MOUJAS PWSS (SM/13729) | SM/13729 | 758.82 | 2931 | NEW | 5 | Delayed | 17 | 17/11/2022 | 31/03/2024 | 05/02/2024 | 04/01/2023 | 125.35 | 125.35
376 | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. (SM/14432) | SM/14432 | 649.29 | 1303 | AUGMENTATION | 5 | Delayed | 7 | 20/01/2023 | 31/12/2024 | 02/07/2024 | 14/03/2023 | 47.88 | 47.88
377 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I (SM/15230) | SM/15230 | 540.38 | 1093 | AUGMENTATION | 5 | Delayed | 5 | 07/02/2023 | 31/12/2024 | 22/05/2024 | 14/03/2023 | 26.84 | 26.84
378 | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16112) | SM/16112 | 226.02 | 565 | NEW | 5 | Delayed | 31 | 22/02/2023 | 31/03/2024 | 15/01/2024 | 28/06/2023 | 69.79 | 54.79
379 | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. (SM/12738) | SM/12738 | 231.37 | 299 | AUGMENTATION | 5 | Delayed | 8 | 20/09/2022 | 31/12/2024 | 21/05/2024 | 09/08/2023 | 19.29 | 19.29
380 | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. (SM/14428) | SM/14428 | 338.02 | 355 | AUGMENTATION | 5 | Delayed | 21 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 17/02/2023 | 70.45 | 70.45
381 | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME (SM/14067) | SM/14067 | 998.3 | 1601 | AUGMENTATION | 5 | Delayed | 21 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 23/12/2022 | 209.85 | 208.89
382 | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. (SM/14068) | SM/14068 | 995.8 | 719 | AUGMENTATION | 5 | Delayed | 32 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 13/12/2022 | 322.41 | 322.41
383 | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. (SM/18830) | SM/18830 | 1419.76 | 2029 | AUGMENTATION | 5 | Delayed | 6 | 21/09/2023 | 26/06/2025 | 11/06/2024 | 26/09/2023 | 91.73 | 91.73
384 | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. (SM/18602) | SM/18602 | 1478.49 | 1095 | AUGMENTATION | 5 | Delayed | 26 | 31/07/2023 | 30/04/2024 | 05/03/2024 | 09/08/2023 | 387.44 | 387.44
385 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur (SM/12583) | SM/12583 | 851.94 | 2348 | AUGMENTATION | 6 | Delayed | 8 | 15/09/2022 | 31/12/2024 | 30/09/2024 | 17/01/2023 | 71.41 | 69.08
386 | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . (SM/14049) | SM/14049 | 662.31 | 312 | AUGMENTATION | 6 | Delayed | 35 | 12/12/2022 | 31/03/2025 | 26/11/2024 | 24/03/2023 | 231.56 | 228.07
387 | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. (SM/10626) | SM/10626 | 525.47 | 0 | AUGMENTATION | 6 | Delayed | 73 | 20/04/2022 | 31/12/2024 | 24/07/2024 | 17/11/2021 | 384.91 | 384.91
388 | JAJAN AND ADJOINING MOUJAS PWSS (SM/13925) | SM/13925 | 467.74 | 1544 | NEW | 6 | Delayed | 42 | 29/11/2022 | 30/09/2024 | 12/04/2024 | 16/03/2023 | 195.92 | 195.92
389 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Jamna (315232) of Mahalandi Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Kandi Block of Murshidabad District Under Murshidabad Division PheDte. (SM/11233) | SM/11233 | 222.96 | 498 | AUGMENTATION | 6 | Delayed | 9 | 22/06/2022 | 31/03/2025 | 16/04/2024 | 17/11/2022 | 20.69 | 20.69
390 | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/14920) | SM/14920 | 933.72 | 748 | AUGMENTATION | 6 | Delayed | 32 | 03/02/2023 | 31/03/2025 | 26/11/2024 | 14/03/2023 | 296.72 | 287.38
391 | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS (SM/16783) | SM/16783 | 711.04 | 1482 | NEW | 6 | Delayed | 24 | 13/03/2023 | 31/12/2024 | 03/06/2024 | 17/05/2023 | 168.25 | 168.25
392 | KURULIA AND ADJOINING MOUJAS PWSS (SM/18324) | SM/18324 | 1442.05 | 4374 | NEW | 6 | Delayed | 33 | 27/06/2023 | 27/06/2025 | 07/03/2024 | 04/08/2023 | 479.2 | 479.2
393 | GOBINDAPUR PWSS (SM/16784) | SM/16784 | 422.85 | 755 | NEW | 6 | Delayed | 17 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 15/05/2023 | 71 | 71
394 | BERBARI AND ADJOINING MOUJAS PWSS (SM/15694) | SM/15694 | 146.43 | 359 | NEW | 6 | Delayed | 11 | 20/02/2023 | 31/03/2024 | 29/02/2024 | 28/03/2023 | 16.25 | 16.25
395 | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. (SM/10629) | SM/10629 | 498.55 | 1342 | AUGMENTATION | 6 | Delayed | 38 | 20/04/2022 | 31/05/2024 | 13/03/2024 | 31/12/2021 | 186.96 | 171.63
396 | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/14048) | SM/14048 | 713.71 | 1389 | AUGMENTATION | 6 | Delayed | 24 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 16/12/2022 | 172.98 | 172.98
397 | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/14046) | SM/14046 | 686.91 | 255 | AUGMENTATION | 6 | Delayed | 16 | 12/12/2022 | 31/03/2025 | 25/11/2024 | 13/03/2023 | 111.3 | 101.18
398 | BABARPUR AND ADJOINING MOUJAS PWSS (SM/16814) | SM/16814 | 255.65 | 766 | NEW | 6 | Delayed | 35 | 13/03/2023 | 13/09/2024 | 07/03/2024 | 17/07/2023 | 89.48 | 89.48
399 | SHUKUR PUKUR PWSS (SM/16782) | SM/16782 | 391.07 | 601 | NEW | 6 | Delayed | 9 | 13/03/2023 | 31/12/2024 | 05/08/2024 | 17/05/2023 | 36.18 | 36.18
400 | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. (SM/18603) | SM/18603 | 1060.31 | 919 | AUGMENTATION | 6 | Delayed | 2 | 31/07/2023 | 31/12/2024 | 05/08/2024 | 04/01/2023 | 20.45 | 20.45
401 | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/14829) | SM/14829 | 550.94 | 2 | AUGMENTATION | 7 | Delayed | 3 | 03/02/2023 | 31/03/2024 | 28/02/2024 | 03/02/2022 | 19 | 19
402 | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16277) | SM/16277 | 842.7 | 3012 | NEW | 7 | Delayed | 34 | 24/02/2023 | 31/08/2024 | 06/05/2024 | 16/06/2023 | 283.9 | 272.76
403 | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. (SM/16353) | SM/16353 | 998.86 | 678 | AUGMENTATION | 7 | Delayed | 34 | 28/02/2023 | 31/12/2024 | 21/05/2024 | 14/03/2023 | 340.31 | 340.31
404 | KULGACHI AND ITS ADJOINING MOUJAS PWSS (SM/16302) | SM/16302 | 589.74 | 1286 | NEW | 8 | Delayed | 23 | 23/02/2023 | 31/12/2024 | 21/05/2024 | 10/05/2023 | 138.18 | 138.18
405 | BASANTAPUR AND ADJOINING MOUJAS PWSS (SM/15940) | SM/15940 | 161.21 | 417 | NEW | 8 | Delayed | 45 | 22/02/2023 | 31/08/2025 | 14/05/2024 | 31/03/2023 | 72.74 | 72.74
406 | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16396) | SM/16396 | 710.31 | 3690 | NEW | 8 | Delayed | 39 | 28/02/2023 | 31/03/2024 | 05/02/2024 | 10/08/2023 | 277.32 | 277.32
407 | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. (SM/18700) | SM/18700 | 3550.58 | 3052 | AUGMENTATION | 8 | Delayed | 20 | 04/08/2023 | 31/12/2024 | 15/04/2024 | 09/08/2023 | 727.25 | 690.6
408 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . (SM/14050) | SM/14050 | 202.23 | 86 | AUGMENTATION | 8 | Delayed | 29 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 13/03/2023 | 59.23 | 59.23
409 | BADDA AND IT'S ADJOINING MOUJAS (SM/15678) | SM/15678 | 813.42 | 2297 | NEW | 8 | Delayed | 46 | 20/02/2023 | 31/03/2024 | 02/02/2024 | 28/06/2023 | 375.54 | 375.54
410 | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME (SM/16400) | SM/16400 | 503.35 | 641 | AUGMENTATION | 8 | Delayed | 20 | 28/02/2023 | 30/11/2023 | 15/10/2023 | 31/12/2021 | 99.96 | 99.96
411 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur (SM/09768) | SM/09768 | 60.39 | 793 | RETROFITTING | 8 | Delayed | 12 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 01/11/2022 | 7.52 | 7.52
412 | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. (SM/14070) | SM/14070 | 507.83 | 810 | AUGMENTATION | 8 | Delayed | 37 | 12/12/2022 | 31/12/2024 | 21/05/2024 | 02/03/2023 | 186.16 | 186.16
413 | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. (SM/13996) | SM/13996 | 739.79 | 919 | AUGMENTATION | 8 | Delayed | 26 | 01/12/2022 | 31/03/2024 | 09/10/2023 | 03/02/2022 | 190.7 | 190.7
414 | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. (SM/15943) | SM/15943 | 849.64 | 1316 | NEW | 8 | Delayed | 31 | 22/02/2023 | 30/09/2025 | 14/05/2024 | 16/06/2023 | 265.49 | 265.49
415 | AOCHA AND ADJJOINING MOUJAS PWSS (SM/18470) | SM/18470 | 1040.98 | 3819 | NEW | 8 | Delayed | 37 | 20/07/2023 | 20/07/2025 | 07/03/2024 | 02/08/2023 | 380.22 | 380.22
416 | GAYSEPUR PIPED WATER SUPPLY SCHEME (SM/16018) | SM/16018 | 396.07 | 491 | NEW | 8 | Delayed | 2 | 22/02/2023 | 31/12/2024 | 21/05/2024 | 15/05/2023 | 7.8 | 7.8
417 | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. (SM/18737) | SM/18737 | 1052.46 | 3636 | AUGMENTATION | 9 | Delayed | 36 | 17/08/2023 | 31/03/2025 | 07/02/2024 | 18/08/2023 | 383.47 | 373.47
418 | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/14722) | SM/14722 | 820.33 | 1558 | AUGMENTATION | 9 | Delayed | 36 | 31/01/2023 | 31/03/2024 | 20/09/2023 | 03/02/2022 | 295.85 | 295.85
419 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi (SM/11232) | SM/11232 | 128.48 | 708 | AUGMENTATION | 9 | Delayed | 28 | 22/06/2022 | 31/03/2024 | 31/08/2023 | 22/12/2022 | 35.65 | 35.65
420 | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I (SM/15233) | SM/15233 | 980.83 | 1469 | AUGMENTATION | 9 | Delayed | 27 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 260.45 | 260.45
421 | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. (SM/18663) | SM/18663 | 2018.37 | 176 | AUGMENTATION | 9 | Delayed | 40 | 04/08/2023 | 31/03/2025 | 14/05/2024 | 25/08/2023 | 806.48 | 407.91
422 | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16278) | SM/16278 | 702.59 | 2500 | NEW | 9 | Delayed | 31 | 24/02/2023 | 31/08/2024 | 06/05/2024 | 23/03/2023 | 220.33 | 204.25
423 | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. (SM/15066) | SM/15066 | 853.48 | 266 | AUGMENTATION | 9 | Delayed | 29 | 04/02/2023 | 31/05/2024 | 15/03/2024 | 01/11/2022 | 249.32 | 249.32
424 | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. (SM/16866) | SM/16866 | 587.32 | 417 | AUGMENTATION | 9 | Delayed | 31 | 13/03/2023 | 31/12/2024 | 17/01/2024 | 22/05/2023 | 183.89 | 183.89
425 | ANDULIA AND ADJOININNG MOUJAS PWSS (SM/13723) | SM/13723 | 821.59 | 3482 | NEW | 10 | Delayed | 23 | 17/11/2022 | 31/03/2024 | 15/01/2024 | 17/01/2023 | 185.69 | 185.69
426 | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. (SM/17389) | SM/17389 | 563.21 | 2062 | AUGMENTATION | 10 | Delayed | 22 | 15/03/2023 | 25/06/2025 | 10/06/2024 | 10/08/2023 | 124.27 | 124.27
427 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In (SM/08907) | SM/08907 | 674.11 | 6191 | RETROFITTING | 10 | Delayed | 0 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 09/03/2023 | 3.16 | 3.16
428 | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/13994) | SM/13994 | 564.45 | 1034 | AUGMENTATION | 10 | Delayed | 22 | 01/12/2022 | 30/09/2024 | 12/04/2024 | 10/05/2022 | 121.89 | 121.89
429 | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16267) | SM/16267 | 948.13 | 2619 | NEW | 10 | Delayed | 18 | 24/02/2023 | 24/08/2024 | 03/06/2024 | 17/05/2023 | 173.71 | 173.71
430 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa (SM/08282) | SM/08282 | 497.66 | 6670 | RETROFITTING | 10 | Delayed | 36 | 19/02/2021 | 31/12/2024 | 12/02/2024 | 08/12/2020 | 181.47 | 181.47
431 | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS (SM/18695) | SM/18695 | 1265.2 | 3460 | NEW | 10 | Delayed | 14 | 04/08/2023 | 31/08/2025 | 03/09/2024 | 08/08/2023 | 173.62 | 173.62
432 | BHARWAN AND ADJOINING MOUJAS PWSS (SM/18452) | SM/18452 | 1267.95 | 3505 | NEW | 10 | Delayed | 35 | 20/07/2023 | 20/07/2025 | 15/01/2024 | 21/07/2023 | 442.85 | 442.85
433 | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS (SM/18464) | SM/18464 | 1754.46 | 5878 | NEW | 10 | Delayed | 20 | 20/07/2023 | 20/07/2025 | 09/09/2024 | 23/08/2023 | 345.16 | 334.76
434 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P (SM/08115) | SM/08115 | 552.45 | 3458 | RETROFITTING | 10 | Delayed | 69 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 383.12 | 325.67
435 | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. (SM/16424) | SM/16424 | 528.16 | 931 | AUGMENTATION | 10 | Delayed | 3 | 28/02/2023 | 31/12/2025 | 03/12/2024 | 09/10/2023 | 13.54 | 13.54
436 | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/19111) | SM/19111 | 1111.29 | 9 | AUGMENTATION | 10 | Delayed | 26 | 20/12/2023 | 31/03/2025 | 03/12/2024 | 26/12/2023 | 290.63 | 282.57
437 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshid (SM/08910) | SM/08910 | 487.62 | 6147 | RETROFITTING | 10 | Delayed | 0 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 31/03/2023 | 0 | 0
438 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. (SM/12740) | SM/12740 | 102.8 | 138 | AUGMENTATION | 10 | Delayed | 53 | 20/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 54.38 | 54.38
439 | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16388) | SM/16388 | 436.24 | 1069 | NEW | 10 | Delayed | 41 | 28/02/2023 | 31/03/2024 | 15/01/2024 | 16/06/2023 | 178.36 | 178.36
440 | SERPUR AND ADJOINING MOUJAS PWSS (SM/13930) | SM/13930 | 764.95 | 2965 | NEW | 10 | Delayed | 12 | 29/11/2022 | 30/09/2024 | 15/04/2024 | 19/06/2023 | 91.14 | 91.14
441 | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/14828) | SM/14828 | 628.88 | 691 | AUGMENTATION | 10 | Delayed | 3 | 03/02/2023 | 31/12/2025 | 11/12/2024 | 03/02/2022 | 20.11 | 20.11
442 | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. (SM/16445) | SM/16445 | 121.85 | 383 | NEW | 10 | Delayed | 53 | 28/02/2023 | 31/08/2024 | 06/05/2024 | 02/08/2023 | 65.17 | 65.17
443 | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . (SM/16815) | SM/16815 | 81.23 | 204 | NEW | 10 | Delayed | 37 | 13/03/2023 | 31/03/2025 | 22/07/2024 | 02/08/2023 | 29.77 | 29.18
444 | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. (SM/19018) | SM/19018 | 187.45 | 137 | AUGMENTATION | 10 | Delayed | 43 | 27/10/2023 | 31/03/2025 | 16/04/2024 | 30/10/2023 | 80.31 | 80.31
445 | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. (SM/18701) | SM/18701 | 1931.29 | 6632 | AUGMENTATION | 10 | Delayed | 20 | 04/08/2023 | 31/03/2025 | 10/06/2024 | 19/10/2023 | 383.51 | 383.51
446 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur (SM/12582) | SM/12582 | 902.24 | 2310 | AUGMENTATION | 10 | Delayed | 32 | 15/09/2022 | 31/12/2024 | 03/09/2024 | 08/03/2022 | 289.85 | 289.85
447 | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. (SM/12588) | SM/12588 | 698.71 | 1866 | AUGMENTATION | 10 | Delayed | 23 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 17/01/2023 | 157.29 | 157.29
448 | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS (SM/13488) | SM/13488 | 640.11 | 3631 | NEW | 10 | Delayed | 33 | 02/11/2022 | 31/12/2024 | 14/03/2024 | 22/12/2022 | 208.78 | 208.78
449 | GARULIA AND IT'S ADJOINING MOUJAS PWSS (SM/13924) | SM/13924 | 770.8 | 3016 | NEW | 10 | Delayed | 65 | 29/11/2022 | 31/03/2024 | 02/02/2024 | 17/01/2023 | 498.49 | 498.49
450 | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. (SM/14430) | SM/14430 | 982.3 | 1298 | AUGMENTATION | 10 | Delayed | 2 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 17.3 | 17.3
451 | DIAR FATEPUR PWSS (SM/16781) | SM/16781 | 915.29 | 3118 | NEW | 10 | Delayed | 32 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 291.02 | 287.52
452 | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. (SM/15836) | SM/15836 | 762.57 | 5 | AUGMENTATION | 10 | Delayed | 70 | 20/02/2023 | 30/09/2024 | 22/05/2024 | 03/02/2022 | 531.74 | 531.74
453 | Retrofitting of Ground Water Based Water Supply Scheme for Kamalakantapur and its Adjoining Mouzas to provided last mile connectivety and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . (SM/18488) | SM/18488 | 135.04 | 1518 | RETROFITTING | 10 | Delayed | 27 | 24/07/2023 | 31/12/2024 | 16/03/2024 | 11/08/2023 | 36.32 | 36.32
454 | INDRANI AND ADJOINING MOUJAS PWSS (SM/18466) | SM/18466 | 1476.45 | 6117 | NEW | 10 | Delayed | 32 | 20/07/2023 | 20/07/2025 | 22/01/2024 | 21/07/2023 | 478.38 | 478.38
455 | BUNDI AND ADJOINING MOUJAS PWSS (SM/13732) | SM/13732 | 623.31 | 2048 | NEW | 11 | Delayed | 27 | 17/11/2022 | 31/03/2024 | 07/03/2024 | 15/02/2023 | 170.77 | 170.77
456 | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16266) | SM/16266 | 904.77 | 2334 | NEW | 11 | Delayed | 22 | 24/02/2023 | 31/12/2024 | 03/06/2024 | 03/05/2023 | 199.19 | 194.89
457 | KUNDAL AND ADJOINING MOUJAS PWSS (SM/18454) | SM/18454 | 1083.25 | 3600 | NEW | 11 | Delayed | 23 | 20/07/2023 | 20/07/2025 | 15/01/2024 | 25/07/2023 | 244.05 | 244.05
458 | PALITPARA AND ADJOINING MOUJAS PWSS (SM/18709) | SM/18709 | 1472.99 | 4386 | NEW | 11 | Delayed | 9 | 04/08/2023 | 04/08/2025 | 20/05/2024 | 10/08/2023 | 137.43 | 137.43
459 | SUKURIA AND ADJOINING MOUJAS PWSS (SM/15941) | SM/15941 | 698.09 | 1781 | NEW | 11 | Delayed | 43 | 22/02/2023 | 31/03/2024 | 22/01/2024 | 13/04/2023 | 303.15 | 298.95
460 | MIRHATI AND ADJOINING MOUJAS PWSS (SM/14869) | SM/14869 | 232.44 | 590 | NEW | 12 | Delayed | 34 | 03/02/2023 | 31/03/2024 | 15/01/2024 | 21/03/2023 | 78.75 | 78.75
461 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ (SM/11229) | SM/11229 | 568.17 | 3094 | AUGMENTATION | 12 | Delayed | 18 | 22/06/2022 | 31/12/2023 | 12/06/2023 | 05/10/2021 | 100.16 | 100.16
462 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) (SM/07678) | SM/07678 | 109.83 | 1332 | RETROFITTING | 13 | Delayed | 63 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 10/05/2021 | 69.5 | 69.5
463 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi (SM/09744) | SM/09744 | 186.4 | 1974 | RETROFITTING | 13 | Delayed | 29 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 18/02/2021 | 54.85 | 54.85
464 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M (SM/09742) | SM/09742 | 191.97 | 2241 | RETROFITTING | 13 | Delayed | 36 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 10/02/2022 | 69.5 | 69.5
465 | KAPASDANGA & ADJOINING MOUJAS PWSS (SM/15054) | SM/15054 | 593 | 1416 | NEW | 13 | Delayed | 25 | 04/02/2023 | 31/03/2024 | 02/02/2024 | 11/04/2023 | 149.97 | 149.97
466 | MUNIGRAM AND ADJOINING MOUJAS PWSS (SM/13935) | SM/13935 | 389.65 | 1029 | NEW | 13 | Delayed | 41 | 29/11/2022 | 31/03/2024 | 15/01/2024 | 19/06/2023 | 160.84 | 154.21
467 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh (SM/09838) | SM/09838 | 25.62 | 323 | RETROFITTING | 14 | Delayed | 97 | 02/12/2021 | 02/03/2022 | 12/06/2023 | 11/05/2022 | 24.87 | 3.33
468 | GUNANANDABATI AND ADJOINING MOUJAS PWSS (SM/13731) | SM/13731 | 605.27 | 2306 | NEW | 14 | Delayed | 28 | 17/11/2022 | 31/03/2024 | 15/01/2024 | 16/01/2023 | 171.42 | 171.42
469 | BATI AND IT'S ADJOINING MOUJAS PWSS (SM/14496) | SM/14496 | 569.98 | 1447 | NEW | 14 | Delayed | 31 | 20/01/2023 | 31/03/2024 | 06/02/2024 | 13/01/2023 | 175 | 174.43
470 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. (SM/14630) | SM/14630 | 466.17 | 300 | AUGMENTATION | 14 | Delayed | 29 | 31/01/2023 | 31/03/2024 | 12/09/2023 | 03/02/2022 | 137.14 | 130.54
471 | SYAMPUR AND ADJOINING MOUJAS PWSS (SM/16475) | SM/16475 | 590.51 | 1831 | NEW | 14 | Delayed | 29 | 02/03/2023 | 31/03/2024 | 15/01/2024 | 22/03/2023 | 168.95 | 168.95
472 | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. (SM/16543) | SM/16543 | 543.46 | 1618 | AUGMENTATION | 14 | Delayed | 28 | 10/03/2023 | 31/03/2025 | 19/03/2024 | 03/02/2022 | 152.69 | 152.69
473 | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. (SM/18665) | SM/18665 | 2200.3 | 360 | AUGMENTATION | 15 | Delayed | 22 | 04/08/2023 | 31/03/2025 | 30/09/2024 | 25/08/2023 | 474.11 | 474.11
474 | LOKAIPUR PIPED WATER SUPPLY SCHEME. (SM/16552) | SM/16552 | 660.39 | 665 | NEW | 15 | Delayed | 26 | 10/03/2023 | 31/07/2024 | 04/04/2024 | 11/11/2022 | 174.33 | 174.33
475 | KELAI AND IT'S ADJOINING MOUJAS (SM/15680) | SM/15680 | 801.52 | 3136 | NEW | 15 | Delayed | 29 | 20/02/2023 | 31/03/2024 | 07/03/2024 | 16/03/2023 | 229.32 | 229.32
476 | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme (SM/16263) | SM/16263 | 724.68 | 1596 | NEW | 15 | Delayed | 35 | 24/02/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 254.53 | 254.53
477 | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. (SM/15734) | SM/15734 | 709.71 | 1612 | AUGMENTATION | 15 | Delayed | 17 | 20/02/2023 | 31/05/2025 | 13/12/2024 | 03/02/2022 | 121.77 | 121.77
478 | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. (SM/13825) | SM/13825 | 843.11 | 3 | AUGMENTATION | 15 | Delayed | 74 | 25/11/2022 | 31/03/2024 | 22/01/2024 | 02/03/2023 | 619.73 | 613.43
479 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. (SM/14734) | SM/14734 | 546.4 | 721 | AUGMENTATION | 15 | Delayed | 20 | 31/01/2023 | 31/12/2024 | 21/05/2024 | 24/03/2023 | 107.13 | 107.13
480 | GHORSALA PIPED WATER SUPPLY SCHEME. (SM/16281) | SM/16281 | 856.53 | 1493 | NEW | 16 | Delayed | 38 | 24/02/2023 | 31/03/2024 | 12/07/2023 | 21/03/2023 | 322.91 | 322.91
481 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc (SM/09751) | SM/09751 | 71.75 | 963 | RETROFITTING | 18 | Delayed | 76 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 03/11/2023 | 54.26 | 54.26
482 | AMJUA AND ADJOINING MOUJAS PWSS (SM/14495) | SM/14495 | 973.05 | 3817 | NEW | 18 | Delayed | 23 | 20/01/2023 | 31/03/2024 | 15/01/2024 | 08/02/2023 | 220.39 | 213.99
483 | EROALI AND ADJOINING MOUJAS PWSS (SM/14236) | SM/14236 | 1141.76 | 4429 | NEW | 18 | Delayed | 35 | 16/01/2023 | 31/12/2024 | 16/04/2024 | 11/01/2023 | 402.39 | 392.39
484 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11571) | SM/11571 | 995.43 | 1169 | AUGMENTATION | 18 | Delayed | 32 | 22/07/2022 | 31/03/2024 | 19/01/2024 | 03/09/2021 | 318.41 | 318.41
485 | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. (SM/14921) | SM/14921 | 989.95 | 715 | AUGMENTATION | 18 | Delayed | 45 | 03/02/2023 | 31/12/2024 | 21/05/2024 | 13/03/2023 | 440.98 | 435.98
486 | GAYESPUR AND ADJOINING MOUJAS PWSS (SM/15690) | SM/15690 | 427.3 | 1295 | NEW | 18 | Delayed | 30 | 20/02/2023 | 31/03/2024 | 16/03/2024 | 28/06/2023 | 128.01 | 128.01
487 | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/16455) | SM/16455 | 779.3 | 2 | AUGMENTATION | 19 | Delayed | 48 | 03/03/2023 | 31/03/2024 | 19/01/2024 | 03/02/2022 | 374.57 | 374.57
488 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. (SM/12585) | SM/12585 | 892.32 | 5483 | AUGMENTATION | 20 | Delayed | 14 | 15/09/2022 | 31/12/2024 | 21/05/2024 | 29/09/2022 | 121.9 | 121.9
489 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. (SM/16673) | SM/16673 | 998.82 | 12601 | RETROFITTING | 20 | Delayed | 0 | 14/03/2023 | 31/12/2025 | 13/01/2025 | 25/08/2023 | 0 | 0
490 | KIRTTIPUR AND ADJOINING MOUJAS PWSS (SM/15691) | SM/15691 | 460.95 | 1599 | NEW | 20 | Delayed | 45 | 20/02/2023 | 31/12/2024 | 15/01/2024 | 20/03/2023 | 209.1 | 209.1
491 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-J) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/08107) | SM/08107 | 383.46 | 2282 | RETROFITTING | 20 | Delayed | 0 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 31/03/2023 | 0 | 0
492 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D (SM/09766) | SM/09766 | 13.96 | 116 | RETROFITTING | 20 | Delayed | 72 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 03/02/2022 | 10 | 9.67
493 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11560) | SM/11560 | 786.26 | 1011 | AUGMENTATION | 20 | Delayed | 35 | 22/07/2022 | 31/03/2024 | 19/01/2024 | 03/09/2021 | 271.5 | 271.5
494 | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. (SM/13928) | SM/13928 | 946.46 | 573 | AUGMENTATION | 20 | Delayed | 14 | 29/11/2022 | 31/12/2024 | 15/04/2024 | 22/02/2022 | 129.65 | 129.65
495 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/08906) | SM/08906 | 505.26 | 3294 | RETROFITTING | 20 | Delayed | 1 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 13/10/2023 | 5.88 | 5.88
496 | SINGADDA AND ADJOINING MOUJAS PWSS (SM/13722) | SM/13722 | 695.52 | 2086 | NEW | 20 | Delayed | 62 | 17/11/2022 | 31/03/2024 | 09/02/2024 | 11/01/2023 | 434.63 | 427.63
497 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/08909) | SM/08909 | 460.21 | 9496 | RETROFITTING | 20 | Delayed | 0 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 31/03/2023 | 0 | 0
498 | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. (SM/16170) | SM/16170 | 471.99 | 360 | AUGMENTATION | 20 | Delayed | 12 | 22/02/2023 | 31/12/2024 | 16/04/2024 | 27/08/2021 | 55.04 | 55.04
499 | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. (SM/12823) | SM/12823 | 553.93 | 1630 | AUGMENTATION | 20 | Delayed | 15 | 22/09/2022 | 31/12/2024 | 21/05/2024 | 02/03/2023 | 83.79 | 83.79
500 | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. (SM/14633) | SM/14633 | 573.57 | 637 | AUGMENTATION | 20 | Delayed | 29 | 31/01/2023 | 31/07/2024 | 07/04/2024 | 10/05/2022 | 164.8 | 164.8
501 | MALIPUR PIPED WATER SUPPLY SCHEME. (SM/16785) | SM/16785 | 421.98 | 446 | NEW | 21 | Delayed | 26 | 13/03/2023 | 31/12/2024 | 21/05/2024 | 17/05/2023 | 109.13 | 109.13
502 | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. (SM/15839) | SM/15839 | 599.09 | 2614 | AUGMENTATION | 21 | Delayed | 2 | 20/02/2023 | 31/12/2025 | 13/01/2025 | 01/11/2022 | 10.2 | 10.2
503 | SANTOSHPUR AND ADJOINING MOUJAS PWSS (SM/13931) | SM/13931 | 669.58 | 2218 | NEW | 21 | Delayed | 23 | 29/11/2022 | 31/03/2024 | 16/02/2024 | 18/01/2023 | 153.92 | 149.12
504 | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. (SM/15921) | SM/15921 | 963.3 | 193 | AUGMENTATION | 22 | Delayed | 19 | 22/02/2023 | 31/03/2024 | 19/03/2024 | 03/02/2022 | 186.46 | 186.46
505 | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur (SM/12739) | SM/12739 | 833.08 | 1858 | AUGMENTATION | 22 | Delayed | 30 | 20/09/2022 | 31/12/2024 | 21/05/2024 | 08/03/2022 | 252.6 | 252.6
506 | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. (SM/16621) | SM/16621 | 842.44 | 324 | AUGMENTATION | 22 | Delayed | 13 | 14/03/2023 | 31/03/2024 | 19/03/2024 | 24/03/2023 | 105.36 | 105.36
507 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11791) | SM/11791 | 698.06 | 1385 | AUGMENTATION | 23 | Delayed | 56 | 05/08/2022 | 31/03/2024 | 12/06/2023 | 03/09/2021 | 392.83 | 392.83
508 | BAYRA AND ITS ADJOINING MOUJAS PWSS (SM/18414) | SM/18414 | 1356.19 | 3902 | NEW | 23 | Delayed | 7 | 12/07/2023 | 12/07/2025 | 21/05/2024 | 25/07/2023 | 100.09 | 100.09
509 | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. (SM/16176) | SM/16176 | 133.85 | 68 | AUGMENTATION | 23 | Delayed | 16 | 22/02/2023 | 31/12/2024 | 11/06/2024 | 12/12/2023 | 21.6 | 21.6
510 | JHILLI AND ADJOINING MOUJAS PWSS (SM/14505) | SM/14505 | 831.53 | 3213 | NEW | 24 | Delayed | 21 | 20/01/2023 | 31/03/2024 | 15/01/2024 | 16/01/2023 | 173.94 | 162.74
511 | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-B) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/16554) | SM/16554 | 302 | 568 | AUGMENTATION | 24 | Delayed | 43 | 10/03/2023 | 30/06/2024 | 11/03/2024 | 05/04/2023 | 131.01 | 131.01
512 | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. (SM/16410) | SM/16410 | 453.71 | 1149 | AUGMENTATION | 24 | Delayed | 45 | 28/02/2023 | 31/12/2024 | 16/04/2024 | 16/03/2023 | 202.33 | 202.33
513 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi (SM/09764) | SM/09764 | 313.08 | 4333 | RETROFITTING | 24 | Delayed | 8 | 30/11/2021 | 31/12/2023 | 12/06/2023 | 27/08/2021 | 23.48 | 23.48
514 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD (SM/12360) | SM/12360 | 33305.51 | 75536 | NEW | 24 | Delayed | 56 | 13/09/2022 | 30/09/2024 | 07/04/2024 | 01/11/2022 | 18560.88 | 18559.38
515 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat (SM/12578) | SM/12578 | 579.64 | 976 | AUGMENTATION | 25 | Delayed | 39 | 15/09/2022 | 31/03/2024 | 15/02/2024 | 08/03/2022 | 225.17 | 225.17
516 | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. (SM/12824) | SM/12824 | 937.92 | 1238 | AUGMENTATION | 25 | Delayed | 12 | 22/09/2022 | 31/12/2024 | 02/07/2024 | 29/09/2022 | 115.75 | 115.75
517 | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE (SM/10013) | SM/10013 | 274.1 | 199 | AUGMENTATION | 25 | Delayed | 7 | 27/12/2021 | 31/03/2024 | 20/07/2023 | 19/02/2021 | 20.49 | 20.49
518 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh (SM/07679) | SM/07679 | 122.92 | 1491 | RETROFITTING | 25 | Delayed | 71 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 10/05/2021 | 86.98 | 86.98
519 | Augmentation of Sadhukhali Zone-I pipe water supply scheme . (SM/15518) | SM/15518 | 436.62 | 250 | AUGMENTATION | 25 | Delayed | 33 | 15/02/2023 | 21/05/2025 | 30/12/2024 | 13/03/2023 | 145.07 | 145.07
520 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) (SM/07675) | SM/07675 | 173.36 | 2377 | RETROFITTING | 25 | Delayed | 50 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 01/12/2021 | 87.54 | 87.54
521 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) (SM/08201) | SM/08201 | 548.73 | 7129 | RETROFITTING | 25 | Delayed | 39 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 19/02/2021 | 216.06 | 216.06
522 | SADPUR PIPE WATER SUPPLY SCHEME. (SM/14946) | SM/14946 | 558.72 | 1930 | NEW | 25 | Delayed | 45 | 04/02/2023 | 31/03/2024 | 16/02/2024 | 10/02/2023 | 252.86 | 235
523 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan (315979) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Buwan Block of Murshidabad District under Murshidabad Divisi (SM/09835) | SM/09835 | 13.03 | 146 | RETROFITTING | 25 | Delayed | 0 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 07/12/2020 | 0 | 0
524 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di (SM/09763) | SM/09763 | 184.33 | 2439 | RETROFITTING | 26 | Delayed | 61 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 05/01/2022 | 113.27 | 113.27
525 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. (SM/11967) | SM/11967 | 1295.09 | 65 | AUGMENTATION | 26 | Delayed | 12 | 26/08/2022 | 31/03/2024 | 09/11/2023 | 19/02/2021 | 159.84 | 159.84
526 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M (SM/09765) | SM/09765 | 79.54 | 909 | RETROFITTING | 26 | Delayed | 74 | 30/11/2021 | 31/12/2024 | 09/02/2024 | 27/08/2021 | 58.5 | 57.53
527 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . (SM/14832) | SM/14832 | 821.37 | 2054 | AUGMENTATION | 26 | Delayed | 9 | 03/02/2023 | 31/03/2024 | 19/03/2024 | 24/12/2020 | 77.52 | 77.52
528 | SIJGRAM AND ADJOINING MOUJAS PWSS (SM/13730) | SM/13730 | 635.19 | 2160 | NEW | 27 | Delayed | 48 | 17/11/2022 | 30/06/2024 | 18/03/2024 | 16/01/2023 | 301.84 | 301.84
529 | KHESAR AND IT'S ADJOINING MOUJAS PWSS (SM/13937) | SM/13937 | 892.38 | 3593 | NEW | 27 | Delayed | 46 | 29/11/2022 | 30/06/2024 | 15/05/2024 | 04/01/2023 | 413.58 | 398.58
530 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II (SM/09746) | SM/09746 | 328.18 | 4417 | RETROFITTING | 27 | Delayed | 12 | 29/11/2021 | 31/03/2024 | 12/06/2023 | 10/02/2022 | 38.39 | 38.39
531 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid (SM/08273) | SM/08273 | 665.47 | 9199 | RETROFITTING | 28 | Delayed | 27 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 10/05/2021 | 180.15 | 180.15
532 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B (SM/07287) | SM/07287 | 72.14 | 984 | RETROFITTING | 28 | Delayed | 86 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 19/08/2021 | 61.77 | 61.77
533 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do (SM/07289) | SM/07289 | 78.74 | 1109 | RETROFITTING | 28 | Delayed | 36 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 01/04/2022 | 27.96 | 27.96
534 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi (SM/07774) | SM/07774 | 205.5 | 2712 | RETROFITTING | 29 | Delayed | 61 | 07/01/2021 | 31/03/2024 | 12/06/2023 | 08/02/2021 | 124.88 | 124.88
535 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M (SM/09748) | SM/09748 | 157.21 | 2183 | RETROFITTING | 29 | Delayed | 0 | 29/11/2021 | 31/03/2024 | 12/06/2023 | 10/02/2022 | 0 | 0
536 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh (SM/09767) | SM/09767 | 107.76 | 1394 | RETROFITTING | 29 | Delayed | 90 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 12/04/2022 | 96.47 | 96.47
537 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad (SM/09741) | SM/09741 | 11.7 | 167 | RETROFITTING | 29 | Delayed | 0 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 02/08/2024 | 0 | 0
538 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/07701) | SM/07701 | 169.75 | 2301 | RETROFITTING | 30 | Delayed | 0 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 31/01/2022 | 0 | 0
539 | LOHADAHA AND ADJOINING MOUJAS PWSS (SM/13727) | SM/13727 | 690.38 | 2489 | NEW | 30 | Delayed | 53 | 17/11/2022 | 30/09/2024 | 13/03/2024 | 17/01/2023 | 365.15 | 275.66
540 | GAFULIA AND ADJOINING MOUJAS PWSS (SM/14626) | SM/14626 | 674.05 | 2018 | NEW | 30 | Delayed | 39 | 31/01/2023 | 31/03/2024 | 15/01/2024 | 01/03/2023 | 266.22 | 259.82
541 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . (SM/14833) | SM/14833 | 474.11 | 349 | AUGMENTATION | 30 | Delayed | 22 | 03/02/2023 | 31/03/2024 | 19/03/2024 | 03/02/2022 | 105.62 | 105.62
542 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M (SM/07924) | SM/07924 | 66.03 | 1222 | RETROFITTING | 30 | Delayed | 61 | 19/01/2021 | 31/03/2024 | 15/10/2023 | 01/08/2023 | 40.14 | 38.17
543 | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. (SM/14431) | SM/14431 | 591.27 | 653 | AUGMENTATION | 31 | Delayed | 14 | 20/01/2023 | 31/12/2024 | 20/05/2024 | 28/02/2023 | 82.95 | 82.95
544 | MANDALSAR AND ADJOINING MOUJAS PWSS (SM/15938) | SM/15938 | 479.13 | 1322 | NEW | 31 | Delayed | 52 | 22/02/2023 | 31/12/2024 | 16/04/2024 | 03/03/2023 | 251.24 | 251.24
545 | MAHISAR AND ADJOINING MOUJAS PWSS (SM/13725) | SM/13725 | 852.84 | 3006 | NEW | 31 | Delayed | 22 | 17/11/2022 | 31/03/2024 | 15/01/2024 | 04/01/2023 | 189.67 | 185.37
546 | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS (SM/14497) | SM/14497 | 770.2 | 2262 | NEW | 32 | Delayed | 40 | 20/01/2023 | 31/03/2024 | 02/02/2024 | 13/01/2023 | 311.89 | 311.07
547 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . (SM/14830) | SM/14830 | 499.1 | 1375 | AUGMENTATION | 32 | Delayed | 19 | 03/02/2023 | 31/03/2024 | 19/03/2024 | 03/02/2022 | 93.78 | 93.78
548 | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. (SM/13926) | SM/13926 | 721.32 | 2658 | AUGMENTATION | 33 | Delayed | 45 | 29/11/2022 | 31/03/2024 | 22/02/2024 | 05/10/2021 | 322.33 | 322.33
549 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur (SM/07684) | SM/07684 | 112.77 | 1479 | RETROFITTING | 33 | Delayed | 39 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 10/12/2020 | 43.73 | 43.73
550 | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16393) | SM/16393 | 615.3 | 2038 | NEW | 34 | Delayed | 44 | 28/02/2023 | 31/12/2024 | 15/01/2024 | 09/03/2023 | 271.13 | 271.13
551 | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD (SM/18896) | SM/18896 | 16379.52 | 5982 | AUGMENTATION | 34 | Delayed | 1 | 06/10/2023 | 06/04/2025 | 21/08/2024 | 31/10/2023 | 237.3 | 237.3
552 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II (SM/07683) | SM/07683 | 158.56 | 2122 | RETROFITTING | 35 | Delayed | 20 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 17/08/2021 | 31.16 | 31.16
553 | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. (SM/10011) | SM/10011 | 962.13 | 5492 | AUGMENTATION | 35 | Delayed | 43 | 27/12/2021 | 31/03/2024 | 19/01/2024 | 05/10/2021 | 415.85 | 415.85
554 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. (SM/12822) | SM/12822 | 899.98 | 2695 | AUGMENTATION | 35 | Delayed | 24 | 22/09/2022 | 31/12/2024 | 05/08/2024 | 17/01/2023 | 215.86 | 215.86
555 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs (SM/07686) | SM/07686 | 200.91 | 2798 | RETROFITTING | 35 | Delayed | 43 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 04/02/2021 | 86.29 | 86.29
556 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Srikrishnapur ( 314737 ) of Aminabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshid (SM/09846) | SM/09846 | 67.42 | 845 | RETROFITTING | 35 | Delayed | 58 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 22/12/2020 | 38.99 | 38.99
557 | BIPRA SEKHAR AND ADJOING MOUJAS PWSS (SM/14868) | SM/14868 | 864.73 | 2162 | NEW | 35 | Delayed | 62 | 03/02/2023 | 31/03/2024 | 02/02/2024 | 23/03/2023 | 532.19 | 532.19
558 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III (SM/07514) | SM/07514 | 45.43 | 591 | RETROFITTING | 35 | Delayed | 55 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 09/02/2021 | 25 | 24.36
559 | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. (SM/16268) | SM/16268 | 32.73 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 35 | Delayed | 0 | 24/02/2023 | 30/11/2023 | 17/07/2023 |  | 0 | 0
560 | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. (SM/14922) | SM/14922 | 855.81 | 618 | AUGMENTATION | 37 | Delayed | 34 | 03/02/2023 | 31/12/2024 | 21/05/2024 | 28/02/2023 | 294.03 | 294.03
561 | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/16389) | SM/16389 | 261.03 | 860 | NEW | 38 | Delayed | 50 | 28/02/2023 | 31/03/2024 | 15/01/2024 | 15/03/2023 | 130.21 | 107.87
562 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagdanga ( 314725 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV (SM/07916) | SM/07916 | 61.03 | 767 | RETROFITTING | 38 | Delayed | 34 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 08/01/2021 | 20.67 | 20.67
563 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) (SM/07291) | SM/07291 | 51.34 | 665 | RETROFITTING | 38 | Delayed | 30 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 06/11/2023 | 15.4 | 15.4
564 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II (SM/07920) | SM/07920 | 95.93 | 1686 | RETROFITTING | 38 | Delayed | 36 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 31/03/2022 | 34.42 | 34.42
565 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR (SM/07508) | SM/07508 | 58.94 | 813 | RETROFITTING | 38 | Delayed | 72 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 09/02/2021 | 42.39 | 42.39
566 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba (SM/09758) | SM/09758 | 76.56 | 1009 | RETROFITTING | 38 | Delayed | 46 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 23/02/2022 | 35.15 | 35.15
567 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District (SM/07721) | SM/07721 | 53.33 | 607 | RETROFITTING | 38 | Delayed | 78 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 41.84 | 41.07
568 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected (SM/08185) | SM/08185 | 329.04 | 4666 | RETROFITTING | 38 | Delayed | 25 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 04/12/2020 | 83.02 | 83.02
569 | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/13992) | SM/13992 | 978.6 | 2087 | AUGMENTATION | 39 | Delayed | 25 | 01/12/2022 | 31/03/2024 | 06/02/2024 | 10/05/2022 | 239.85 | 239.85
570 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhulauri (314671) of Dhulauri under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) (SM/07673) | SM/07673 | 142.93 | 1671 | RETROFITTING | 39 | Delayed | 0 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 02/08/2024 | 0 | 0
571 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad (SM/07295) | SM/07295 | 93.16 | 1229 | RETROFITTING | 39 | Delayed | 54 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 22/11/2021 | 50.22 | 50.22
572 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of (SM/07280) | SM/07280 | 97.62 | 1276 | RETROFITTING | 39 | Delayed | 30 | 10/12/2020 | 31/03/2024 | 12/06/2023 |  | 29.29 | 29.29
573 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) (SM/07512) | SM/07512 | 66.82 | 878 | RETROFITTING | 39 | Delayed | 65 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 18/02/2021 | 43.57 | 43.57
574 | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/16244) | SM/16244 | 715.32 | 823 | AUGMENTATION | 39 | Delayed | 62 | 23/02/2023 | 31/03/2024 | 08/08/2023 | 06/03/2023 | 440.06 | 440.06
575 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bamuha (313962) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad D (SM/09759) | SM/09759 | 64.56 | 845 | RETROFITTING | 39 | Delayed | 0 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 28/02/2022 | 0 | 0
576 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II (SM/07915) | SM/07915 | 98.09 | 1252 | RETROFITTING | 39 | Delayed | 66 | 19/01/2021 | 31/03/2024 | 12/06/2023 |  | 65.22 | 65.22
577 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur Chak ( 314703 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (SM/07914) | SM/07914 | 63.09 | 795 | RETROFITTING | 39 | Delayed | 0 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 08/01/2021 | 0 | 0
578 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) (SM/07276) | SM/07276 | 95.4 | 1305 | RETROFITTING | 40 | Delayed | 95 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 10/08/2021 | 90.78 | 90.78
579 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) (SM/07909) | SM/07909 | 114.54 | 1469 | RETROFITTING | 40 | Delayed | 38 | 19/01/2021 | 31/03/2025 | 18/01/2024 | 26/07/2021 | 43.3 | 43.3
580 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs (SM/07773) | SM/07773 | 139.17 | 1798 | RETROFITTING | 40 | Delayed | 56 | 07/01/2021 | 31/03/2024 | 12/06/2023 | 09/02/2021 | 77.48 | 77.48
581 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No (SM/10036) | SM/10036 | 1037.9 | 14709 | RETROFITTING | 40 | Delayed | 10 | 19/01/2022 | 31/03/2024 | 12/06/2023 | 22/02/2022 | 105.04 | 105.04
582 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) (SM/07290) | SM/07290 | 99.96 | 1322 | RETROFITTING | 40 | Delayed | 94 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 17/08/2021 | 94.43 | 94.43
583 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block (SM/08114) | SM/08114 | 312.34 | 9240 | RETROFITTING | 40 | Delayed | 54 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 01/02/2022 | 168.87 | 168.87
584 | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS (SM/15942) | SM/15942 | 540.51 | 1605 | NEW | 40 | Delayed | 68 | 22/02/2023 | 31/08/2025 | 14/05/2024 | 03/03/2023 | 369.24 | 362.84
585 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water (SM/08281) | SM/08281 | 434.98 | 6168 | RETROFITTING | 40 | Delayed | 33 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 05/02/2021 | 142.07 | 142.07
586 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of (SM/08196) | SM/08196 | 532.59 | 7823 | RETROFITTING | 40 | Delayed | 42 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 09/08/2021 | 225.05 | 225.05
587 | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 (SM/08867) | SM/08867 | 2776.84 | 12711 | NEW | 41 | Delayed | 42 | 20/09/2021 | 31/03/2024 | 07/03/2024 | 23/03/2022 | 1165.59 | 1155.89
588 | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS (SM/14503) | SM/14503 | 277.07 | 620 | NEW | 42 | Delayed | 56 | 20/01/2023 | 31/03/2024 | 02/02/2024 | 02/03/2023 | 155.27 | 155.27
589 | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. (SM/16413) | SM/16413 | 720.5 | 2801 | AUGMENTATION | 42 | Delayed | 52 | 28/02/2023 | 31/12/2024 | 24/09/2024 | 03/02/2022 | 376.91 | 373.31
590 | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS (SM/13936) | SM/13936 | 440.16 | 1372 | NEW | 43 | Delayed | 30 | 29/11/2022 | 31/03/2024 | 22/02/2024 | 17/01/2023 | 133.86 | 133.86
591 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) (SM/07725) | SM/07725 | 119.17 | 1722 | RETROFITTING | 43 | Delayed | 62 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 74.44 | 74.44
592 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo (SM/08908) | SM/08908 | 384.82 | 3493 | RETROFITTING | 43 | Delayed | 87 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 01/02/2022 | 336.05 | 336.05
593 | PUNIA AND ADJOINING MOUJAS PWSS (SM/13933) | SM/13933 | 714.78 | 2799 | NEW | 43 | Delayed | 54 | 29/11/2022 | 31/03/2024 | 16/03/2024 | 17/01/2023 | 386 | 376.8
594 | PETARI AND ADJOINING MOUJAS PWSS (SM/14237) | SM/14237 | 1012.65 | 2616 | NEW | 44 | Delayed | 54 | 16/01/2023 | 31/03/2024 | 13/03/2024 | 10/01/2023 | 549.14 | 549.14
595 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Taraf Rasulpur (314679) of P.T. Rasulpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) (SM/08186) | SM/08186 | 357.84 | 4803 | RETROFITTING | 44 | Delayed | 0 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 02/08/2024 | 0 | 0
596 | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16280) | SM/16280 | 252.27 | 620 | NEW | 44 | Delayed | 73 | 24/02/2023 | 31/03/2024 | 22/01/2024 | 03/03/2023 | 184.79 | 184.79
597 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-II) (SM/07681) | SM/07681 | 290.84 | 2805 | RETROFITTING | 45 | Delayed | 22 | 08/01/2021 | 08/04/2021 | 12/06/2023 | 02/06/2022 | 63.06 | 63.06
598 | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE (SM/14629) | SM/14629 | 680.05 | 754 | AUGMENTATION | 45 | Delayed | 39 | 31/01/2023 | 31/03/2024 | 25/07/2023 | 10/05/2022 | 262.69 | 262.69
599 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par (SM/07275) | SM/07275 | 21.9 | 267 | RETROFITTING | 45 | Delayed | 87 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 27/04/2022 | 18.97 | 18.97
600 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- (SM/07921) | SM/07921 | 91.1 | 1131 | RETROFITTING | 45 | Delayed | 69 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 09/02/2021 | 63.01 | 63.01
601 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) (SM/07296) | SM/07296 | 90.93 | 1261 | RETROFITTING | 45 | Delayed | 97 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 27/04/2022 | 88.28 | 88.28
602 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Batkamari ( 314689 ) of Jorgachha under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad (SM/09842) | SM/09842 | 34.36 | 419 | RETROFITTING | 47 | Delayed | 65 | 02/12/2021 | 31/03/2024 | 12/06/2023 |  | 22.28 | 22.28
603 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff (SM/07285) | SM/07285 | 87.45 | 1201 | RETROFITTING | 47 | Delayed | 90 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 29/06/2021 | 78.32 | 78.32
604 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu (SM/07286) | SM/07286 | 98.3 | 1505 | RETROFITTING | 47 | Delayed | 97 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 19/08/2021 | 95.43 | 95.43
605 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- (SM/08116) | SM/08116 | 823.92 | 4583 | RETROFITTING | 47 | Delayed | 79 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 16/07/2021 | 652.17 | 652.17
606 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - (SM/08190) | SM/08190 | 1045.27 | 10200 | RETROFITTING | 47 | Delayed | 51 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 02/08/2021 | 529.04 | 529.04
607 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagw (SM/07793) | SM/07793 | 157.17 | 1305 | RETROFITTING | 48 | Delayed | 0 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 31/01/2022 | 0 | 0
608 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block (SM/07787) | SM/07787 | 76.68 | 1220 | RETROFITTING | 48 | Delayed | 84 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 64.25 | 64.25
609 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo (SM/07785) | SM/07785 | 44.45 | 649 | RETROFITTING | 48 | Delayed | 63 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 28.1 | 28.1
610 | BATHUR AND ADJOINING MOUJAS PWSS (SM/15265) | SM/15265 | 206.5 | 547 | NEW | 49 | Delayed | 77 | 07/02/2023 | 31/12/2024 | 15/01/2024 | 01/03/2023 | 158.21 | 158.21
611 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Malipara Village (Code-314452), Saaragachi Village (Code-314453),Chainpara Village (Code-314457),Rameswarbati Village (Code-31445 (SM/07728) | SM/07728 | 63.18 | 872 | RETROFITTING | 49 | Delayed | 60 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 37.79 | 37.79
612 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- (SM/08111) | SM/08111 | 1011.33 | 2534 | RETROFITTING | 49 | Delayed | 40 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 07/07/2021 | 400.52 | 400.52
613 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of (SM/07279) | SM/07279 | 68.99 | 840 | RETROFITTING | 50 | Delayed | 63 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 09/11/2021 | 43.27 | 43.27
614 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh (SM/09841) | SM/09841 | 36.56 | 460 | RETROFITTING | 50 | Delayed | 65 | 02/12/2021 | 02/03/2022 | 12/06/2023 | 27/08/2021 | 23.83 | 23.83
615 | JUGASWARA AND ADJOINING MOUJAS PWSS (SM/13724) | SM/13724 | 369.94 | 792 | NEW | 50 | Delayed | 34 | 17/11/2022 | 31/03/2024 | 02/02/2024 | 15/02/2023 | 126.15 | 126.15
616 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi (SM/07281) | SM/07281 | 99.11 | 1296 | RETROFITTING | 50 | Delayed | 33 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 08/02/2021 | 32.91 | 32.91
617 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) (SM/07767) | SM/07767 | 285.68 | 4077 | RETROFITTING | 50 | Delayed | 21 | 07/01/2021 | 31/03/2024 | 12/06/2023 | 30/07/2021 | 60.12 | 60.12
618 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj (SM/08197) | SM/08197 | 521.6 | 7197 | RETROFITTING | 50 | Delayed | 68 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 02/08/2021 | 352.67 | 352.67
619 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di (SM/09837) | SM/09837 | 34.02 | 382 | RETROFITTING | 50 | Delayed | 97 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 11/12/2020 | 32.91 | 32.91
620 | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. (SM/11234) | SM/11234 | 159.1 | 230 | AUGMENTATION | 50 | Delayed | 24 | 22/06/2022 | 31/03/2024 | 12/06/2023 | 08/01/2021 | 37.78 | 37.78
621 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur (SM/09739) | SM/09739 | 96.99 | 1216 | RETROFITTING | 50 | Delayed | 57 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 27/08/2021 | 54.94 | 54.94
622 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block (SM/09753) | SM/09753 | 389.19 | 3246 | RETROFITTING | 50 | Delayed | 55 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 25/01/2022 | 214.88 | 206.01
623 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad (SM/09761) | SM/09761 | 43.78 | 530 | RETROFITTING | 50 | Delayed | 16 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 27/08/2021 | 7.08 | 7.08
624 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric (SM/07917) | SM/07917 | 97.32 | 1222 | RETROFITTING | 50 | Delayed | 72 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 09/02/2021 | 69.64 | 69.64
625 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs (SM/07277) | SM/07277 | 51.55 | 572 | RETROFITTING | 50 | Delayed | 91 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 18/08/2021 | 46.73 | 46.73
626 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I (SM/07507) | SM/07507 | 63.33 | 873 | RETROFITTING | 50 | Delayed | 83 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 22/12/2021 | 52.26 | 52.26
627 | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. (SM/16623) | SM/16623 | 801.92 | 390 | AUGMENTATION | 50 | Delayed | 18 | 14/03/2023 | 31/12/2024 | 19/09/2024 | 03/02/2022 | 143.18 | 143.18
628 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) (SM/07731) | SM/07731 | 94.33 | 1398 | RETROFITTING | 51 | Delayed | 35 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 32.65 | 32.65
629 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District (SM/10459) | SM/10459 | 835.07 | 8295 | RETROFITTING | 52 | Delayed | 12 | 13/04/2022 | 31/03/2024 | 12/06/2023 | 05/02/2021 | 101.35 | 101.35
630 | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. (SM/10012) | SM/10012 | 640.21 | 4 | AUGMENTATION | 52 | Delayed | 61 | 27/12/2021 | 31/03/2024 | 05/03/2024 | 05/10/2021 | 389.84 | 383.61
631 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) (SM/07700) | SM/07700 | 164.71 | 2460 | RETROFITTING | 52 | Delayed | 8 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 27/01/2022 | 13.51 | 13.51
632 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri (SM/07278) | SM/07278 | 88.35 | 999 | RETROFITTING | 53 | Delayed | 79 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 18/08/2021 | 70.12 | 70.12
633 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) (SM/07723) | SM/07723 | 89.7 | 1041 | RETROFITTING | 53 | Delayed | 55 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 48.98 | 48.98
634 | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/16767) | SM/16767 | 852.05 | 106 | AUGMENTATION | 53 | Delayed | 50 | 13/03/2023 | 31/03/2024 | 19/03/2024 | 05/04/2023 | 423.16 | 423.16
635 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) (SM/07727) | SM/07727 | 49.3 | 675 | RETROFITTING | 54 | Delayed | 60 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 29.48 | 29.48
636 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo (SM/07790) | SM/07790 | 89.83 | 1349 | RETROFITTING | 54 | Delayed | 50 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 44.98 | 44.98
637 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gobindotala Village (Code-314454), Paschim Rampur (Code-314455) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (SM/07783) | SM/07783 | 88.5 | 1231 | RETROFITTING | 54 | Delayed | 75 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 66.78 | 66.78
638 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of (SM/07515) | SM/07515 | 89.95 | 1170 | RETROFITTING | 54 | Delayed | 28 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 07/12/2020 | 25.19 | 25.19
639 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) (SM/07768) | SM/07768 | 281.95 | 3864 | RETROFITTING | 55 | Delayed | 50 | 07/01/2021 | 31/03/2024 | 12/06/2023 | 21/12/2021 | 140.94 | 140.94
640 | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. (SM/10010) | SM/10010 | 971.89 | 1834 | AUGMENTATION | 55 | Delayed | 44 | 27/12/2021 | 31/03/2024 | 19/03/2024 | 05/10/2021 | 425.25 | 422.65
641 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) (SM/08272) | SM/08272 | 385.47 | 5406 | RETROFITTING | 55 | Delayed | 35 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 15/12/2022 | 133.19 | 133.19
642 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di (SM/07919) | SM/07919 | 235.36 | 6465 | RETROFITTING | 55 | Delayed | 72 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 18/02/2021 | 168.9 | 168.9
643 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid (SM/07294) | SM/07294 | 95.06 | 1255 | RETROFITTING | 55 | Delayed | 51 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 01/10/2020 | 48.5 | 48.5
644 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA (SM/07685) | SM/07685 | 146.33 | 1955 | RETROFITTING | 55 | Delayed | 40 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 25/08/2021 | 58.55 | 58.55
645 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad (SM/07786) | SM/07786 | 16.62 | 386 | RETROFITTING | 56 | Delayed | 57 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 9.51 | 9.51
646 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect (SM/08108) | SM/08108 | 1063.3 | 4593 | RETROFITTING | 57 | Delayed | 54 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 19/02/2021 | 575.1 | 575.09
647 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B (SM/08202) | SM/08202 | 873.95 | 11350 | RETROFITTING | 57 | Delayed | 44 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 11/12/2020 | 381.7 | 381.7
648 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par (SM/08911) | SM/08911 | 717.96 | 6259 | RETROFITTING | 57 | Delayed | 52 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 20/01/2021 | 371.06 | 371.06
649 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C (SM/07724) | SM/07724 | 99.92 | 1454 | RETROFITTING | 58 | Delayed | 66 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 66.39 | 66.39
650 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) (SM/07722) | SM/07722 | 43.55 | 506 | RETROFITTING | 58 | Delayed | 54 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 23.41 | 23.41
651 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) (SM/07771) | SM/07771 | 113.58 | 1516 | RETROFITTING | 58 | Delayed | 66 | 07/01/2021 | 07/04/2021 | 12/06/2023 | 16/02/2022 | 75.21 | 70.42
652 | Extension of pipe line from existing PWSS to different Anganwadi Centers (AWCs), located within the command area of PWSS. (SM/09026) | SM/09026 | 542.67 | 0 | ANGANWADI | 58 | Delayed | 0 | 30/10/2021 | 31/03/2024 | 30/06/2023 | 30/07/2021 | 0 | 0
653 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- (SM/08195) | SM/08195 | 480.62 | 6736 | RETROFITTING | 58 | Delayed | 29 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 31/12/2021 | 141.45 | 141.45
654 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (SM/08117) | SM/08117 | 533.01 | 6844 | RETROFITTING | 59 | Delayed | 60 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 318.98 | 317.85
655 | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM (SM/08919) | SM/08919 | 183.43 | 2752 | RETROFITTING | 59 | Delayed | 35 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 64.8 | 64.8
656 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa (SM/08916) | SM/08916 | 1325.56 | 20292 | RETROFITTING | 59 | Delayed | 56 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 05/10/2021 | 742.81 | 742.81
657 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Manganpara Village (Code-315662) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-A) (SM/07717) | SM/07717 | 53.68 | 678 | RETROFITTING | 60 | Delayed | 56 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 29.89 | 29.89
658 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa (SM/08187) | SM/08187 | 489.6 | 6610 | RETROFITTING | 60 | Delayed | 26 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 06/01/2021 | 125.94 | 125.94
659 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari (314589) of Katlamari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District (PART-I) (SM/08188) | SM/08188 | 578.36 | 3900 | RETROFITTING | 60 | Delayed | 0 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 03/09/2021 | 0 | 0
660 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp (SM/07703) | SM/07703 | 65.9 | 856 | RETROFITTING | 60 | Delayed | 42 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 28/06/2021 | 28 | 28
661 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) (SM/07665) | SM/07665 | 197.42 | 2805 | RETROFITTING | 60 | WO no issued | 0 | 08/01/2021 | 31/03/2024 | 15/09/2023 |  | 0 | 0
662 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block (SM/07677) | SM/07677 | 248.75 | 3431 | RETROFITTING | 60 | Delayed | 55 | 08/01/2021 | 31/03/2024 | 18/07/2023 | 24/03/2021 | 137.1 | 137.1
663 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P (SM/07772) | SM/07772 | 295.16 | 3923 | RETROFITTING | 60 | Delayed | 66 | 07/01/2021 | 31/03/2024 | 28/07/2023 | 09/02/2021 | 194.13 | 194.13
664 | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . (SM/15229) | SM/15229 | 303.6 | 328 | AUGMENTATION | 61 | Delayed | 45 | 07/02/2023 | 31/12/2024 | 21/05/2024 | 02/03/2023 | 137.98 | 137.98
665 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate (SM/06976) | SM/06976 | 72.72 | 1169 | RETROFITTING | 61 | Delayed | 30 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 23/11/2020 | 21.82 | 9.78
666 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa (SM/08915) | SM/08915 | 983.07 | 1622 | RETROFITTING | 61 | Delayed | 37 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 363.8 | 363.8
667 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) (SM/08200) | SM/08200 | 380.89 | 5019 | RETROFITTING | 62 | Delayed | 37 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 02/08/2021 | 141.86 | 141.86
668 | PARULIA AND ADJOINING MOUJAS PWSS (SM/13726) | SM/13726 | 963.23 | 3586 | NEW | 62 | Delayed | 40 | 17/11/2022 | 31/03/2024 | 16/03/2024 | 17/01/2023 | 383.29 | 383.29
669 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par (SM/08112) | SM/08112 | 777.42 | 6837 | RETROFITTING | 62 | Delayed | 72 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 558.74 | 530.17
670 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part (SM/08912) | SM/08912 | 995.85 | 5194 | RETROFITTING | 62 | Delayed | 52 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 05/10/2021 | 521.28 | 521.28
671 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( (SM/08110) | SM/08110 | 1021.1 | 6504 | RETROFITTING | 62 | Delayed | 40 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 411.73 | 411.73
672 | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. (SM/15638) | SM/15638 | 827.89 | 986 | AUGMENTATION | 64 | Delayed | 30 | 20/02/2023 | 12/12/2024 | 19/03/2024 | 08/01/2021 | 248.72 | 248.72
673 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A (SM/08184) | SM/08184 | 376.23 | 5031 | RETROFITTING | 65 | Delayed | 49 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 13/05/2021 | 186.07 | 186.07
674 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par (SM/08914) | SM/08914 | 870.99 | 7620 | RETROFITTING | 65 | Delayed | 63 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 05/10/2021 | 547.03 | 547.03
675 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad (SM/09757) | SM/09757 | 86.3 | 1142 | RETROFITTING | 65 | Delayed | 12 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 31/12/2020 | 9.99 | 9.99
676 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad (SM/07662) | SM/07662 | 170.09 | 2269 | RETROFITTING | 65 | Delayed | 90 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 11/12/2020 | 152.85 | 152.71
677 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bilaspur (314681) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) (SM/07516) | SM/07516 | 79.12 | 1028 | RETROFITTING | 65 | Delayed | 4 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 28/01/2022 | 3.46 | 3.46
678 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sekhalipara (314580) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) (SM/07517) | SM/07517 | 77.39 | 1005 | RETROFITTING | 65 | Delayed | 65 | 29/12/2020 | 29/03/2021 | 12/06/2023 | 11/05/2022 | 50.08 | 50.08
679 | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. (SM/10014) | SM/10014 | 441.86 | 372 | AUGMENTATION | 65 | Delayed | 46 | 27/12/2021 | 31/03/2024 | 19/03/2024 | 16/12/2020 | 203.17 | 203.17
680 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water (SM/07726) | SM/07726 | 76.06 | 1065 | RETROFITTING | 67 | Delayed | 60 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 45.74 | 45.74
681 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- (SM/08106) | SM/08106 | 360.94 | 5699 | RETROFITTING | 68 | Delayed | 36 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 10/02/2021 | 129.61 | 129.61
682 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) (SM/07680) | SM/07680 | 207.09 | 2836 | RETROFITTING | 68 | Delayed | 25 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 21/12/2021 | 51.46 | 51.15
683 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, (SM/08905) | SM/08905 | 650.52 | 4492 | RETROFITTING | 69 | Delayed | 63 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 07/10/2021 | 407.37 | 407.37
684 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) (SM/07274) | SM/07274 | 85.16 | 1028 | RETROFITTING | 69 | Delayed | 97 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 28/01/2022 | 82.42 | 82.42
685 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11564) | SM/11564 | 949.24 | 2259 | RETROFITTING | 69 | Delayed | 27 | 22/07/2022 | 31/03/2024 | 05/03/2024 | 05/10/2021 | 260.97 | 260.97
686 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P (SM/08917) | SM/08917 | 865.34 | 4488 | RETROFITTING | 69 | Delayed | 48 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 20/01/2021 | 412.79 | 412.79
687 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11565) | SM/11565 | 556.61 | 1142 | AUGMENTATION | 70 | Delayed | 39 | 22/07/2022 | 31/07/2024 | 28/08/2023 | 05/10/2021 | 218.28 | 218.28
688 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of (SM/07676) | SM/07676 | 150.4 | 1936 | RETROFITTING | 70 | Delayed | 35 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 08/01/2021 | 52.6 | 52.6
689 | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF (SM/08918) | SM/08918 | 229.8 | 2821 | RETROFITTING | 70 | Delayed | 59 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 136.63 | 136.63
690 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio (SM/11218) | SM/11218 | 178.49 | 379 | AUGMENTATION | 70 | On track | 11 | 15/06/2022 | 15/12/2022 | 12/06/2023 | 11/05/2022 | 19.56 | 19.56
691 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme (SM/06981) | SM/06981 | 94.89 | 1473 | RETROFITTING | 70 | Delayed | 60 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 57.27 | 57.27
692 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jhikra (Code-314512), Ranitala (Code-314513) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-A) Un (SM/07795) | SM/07795 | 83.47 | 1161 | RETROFITTING | 71 | Delayed | 64 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 53.37 | 53.37
693 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR (SM/11457) | SM/11457 | 514.74 | 1010 | AUGMENTATION | 71 | Delayed | 37 | 12/07/2022 | 31/12/2024 | 24/07/2023 | 13/01/2023 | 187.93 | 187.93
694 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) (SM/07732) | SM/07732 | 118.61 | 1906 | RETROFITTING | 72 | Delayed | 81 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 08/10/2021 | 95.85 | 95.85
695 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U (SM/08902) | SM/08902 | 304.14 | 4396 | RETROFITTING | 72 | Delayed | 68 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 07/10/2021 | 207.87 | 207.87
696 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc (SM/07789) | SM/07789 | 115.48 | 1738 | RETROFITTING | 72 | Delayed | 68 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 78.84 | 78.84
697 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sundarpur (Code-314445) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-B) (SM/07730) | SM/07730 | 68.76 | 1000 | RETROFITTING | 73 | Delayed | 74 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 51.13 | 51.13
698 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) (SM/07792) | SM/07792 | 94.73 | 1430 | RETROFITTING | 73 | Delayed | 63 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 13/01/2021 | 59.74 | 59.74
699 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In (SM/07788) | SM/07788 | 99.99 | 1635 | RETROFITTING | 74 | Delayed | 87 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 87.33 | 87.33
700 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply (SM/07794) | SM/07794 | 82.35 | 1195 | RETROFITTING | 74 | Delayed | 59 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 48.54 | 48.54
701 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . (SM/14429) | SM/14429 | 427.57 | 467 | AUGMENTATION | 74 | Delayed | 47 | 20/01/2023 | 31/12/2024 | 21/05/2024 | 16/02/2023 | 200.62 | 200.62
702 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) (SM/07282) | SM/07282 | 99.99 | 1325 | RETROFITTING | 75 | Delayed | 76 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 17/08/2021 | 75.8 | 75.8
703 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, (SM/08903) | SM/08903 | 362.25 | 5343 | RETROFITTING | 75 | Delayed | 67 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 08/10/2021 | 244.29 | 244.27
704 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part (SM/07718) | SM/07718 | 93.76 | 1238 | RETROFITTING | 75 | Delayed | 72 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 67.96 | 67.96
705 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme (SM/06980) | SM/06980 | 80.61 | 1275 | RETROFITTING | 75 | Delayed | 79 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 12/02/2021 | 63.68 | 63.68
706 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- (SM/07907) | SM/07907 | 263.57 | 3406 | RETROFITTING | 77 | Delayed | 75 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 18/08/2021 | 198.62 | 198.62
707 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II (SM/08109) | SM/08109 | 886.86 | 7938 | RETROFITTING | 78 | Delayed | 66 | 09/02/2021 | 31/12/2024 | 21/05/2024 | 12/02/2021 | 584.51 | 584.51
708 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme (SM/07233) | SM/07233 | 97.22 | 2022 | RETROFITTING | 79 | Delayed | 60 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 12/02/2021 | 58.68 | 58.68
709 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola (SM/07791) | SM/07791 | 63.22 | 940 | RETROFITTING | 79 | Delayed | 69 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 43.32 | 43.32
710 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) (SM/07729) | SM/07729 | 64.96 | 959 | RETROFITTING | 79 | Delayed | 67 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 11/08/2021 | 43.27 | 43.27
711 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P (SM/08901) | SM/08901 | 310.52 | 4844 | RETROFITTING | 79 | Delayed | 68 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 08/10/2021 | 211.95 | 211.95
712 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme (SM/07224) | SM/07224 | 52.11 | 715 | RETROFITTING | 80 | Delayed | 58 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 10/12/2020 | 30.04 | 30.04
713 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr (SM/07688) | SM/07688 | 98.85 | 1587 | RETROFITTING | 80 | Delayed | 63 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 25/07/2019 | 62 | 62
714 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 (SM/06978) | SM/06978 | 90.08 | 1389 | RETROFITTING | 80 | Delayed | 96 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 23/11/2020 | 86.54 | 68.03
715 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme (SM/06979) | SM/06979 | 46.15 | 717 | RETROFITTING | 80 | Delayed | 82 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 37.69 | 36.83
716 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground (SM/07720) | SM/07720 | 92.89 | 1199 | RETROFITTING | 80 | Delayed | 65 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 60.17 | 60.17
717 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme (SM/07223) | SM/07223 | 59.03 | 882 | RETROFITTING | 80 | Delayed | 58 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 07/06/2021 | 34.35 | 34.35
718 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) (SM/07693) | SM/07693 | 131.51 | 1771 | RETROFITTING | 80 | Delayed | 54 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 70.91 | 70.91
719 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist (SM/07288) | SM/07288 | 99.99 | 1297 | RETROFITTING | 80 | Delayed | 47 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 01/10/2020 | 47.04 | 47.04
720 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric (SM/07292) | SM/07292 | 63.73 | 782 | RETROFITTING | 80 | Delayed | 97 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 01/10/2020 | 61.87 | 61.87
721 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa (SM/07695) | SM/07695 | 119.21 | 1884 | RETROFITTING | 80 | Delayed | 89 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 105.71 | 105.71
722 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) (SM/07719) | SM/07719 | 85.64 | 1113 | RETROFITTING | 80 | Delayed | 66 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 56.45 | 56.45
723 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Sahebnagar (VillageCode-314609) under command area of Kazipara ground water supply scheme (Part-A) (SM/07222) | SM/07222 | 66.28 | 1000 | RETROFITTING | 80 | Delayed | 0 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 10/12/2021 | 0 | 0
724 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P (SM/07697) | SM/07697 | 168.17 | 2056 | RETROFITTING | 80 | Delayed | 34 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 17/08/2021 | 57.28 | 57.28
725 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) (SM/07908) | SM/07908 | 63.81 | 822 | RETROFITTING | 80 | Delayed | 67 | 19/01/2021 | 31/03/2024 | 18/07/2023 | 18/02/2021 | 42.78 | 42.78
726 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme (SM/06982) | SM/06982 | 71.77 | 1163 | RETROFITTING | 80 | Delayed | 75 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 53.57 | 53.57
727 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code (SM/06977) | SM/06977 | 99.54 | 1544 | RETROFITTING | 80 | Delayed | 80 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 79.84 | 79.84
728 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kulberia Village (Code-315685) Under Command Area Of Andulberia Ground Water Supply Scheme (Part-A) (SM/07696) | SM/07696 | 57.19 | 804 | RETROFITTING | 80 | Delayed | 55 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 31.27 | 31.27
729 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu (SM/07698) | SM/07698 | 95.9 | 1363 | RETROFITTING | 80 | Delayed | 56 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 53.88 | 53.88
730 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) (SM/07236) | SM/07236 | 58.14 | 837 | RETROFITTING | 80 | Delayed | 68 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 28/12/2020 | 39.68 | 39.68
731 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni (SM/07663) | SM/07663 | 121.53 | 1313 | RETROFITTING | 80 | Delayed | 29 | 08/01/2021 | 31/03/2024 | 20/07/2023 | 03/02/2022 | 35.3 | 35.3
732 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh (SM/07510) | SM/07510 | 97.32 | 1287 | RETROFITTING | 80 | Delayed | 80 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 16/11/2021 | 77.44 | 77.44
733 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) (SM/07770) | SM/07770 | 162.06 | 2167 | RETROFITTING | 80 | Delayed | 97 | 07/01/2021 | 31/03/2024 | 12/06/2023 | 06/06/2022 | 156.7 | 136.17
734 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) (SM/07687) | SM/07687 | 99.51 | 1461 | RETROFITTING | 80 | Delayed | 74 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 73.75 | 73.75
735 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr (SM/07691) | SM/07691 | 84.54 | 1207 | RETROFITTING | 80 | Delayed | 56 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 47 | 46.98
736 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) (SM/06983) | SM/06983 | 93.43 | 1453 | RETROFITTING | 80 | Delayed | 81 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 24/02/2021 | 75.82 | 47.79
737 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) (SM/07699) | SM/07699 | 96.83 | 1343 | RETROFITTING | 80 | Delayed | 65 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 07/07/2021 | 62.88 | 62.88
738 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme (SM/07226) | SM/07226 | 87.91 | 1410 | RETROFITTING | 80 | Delayed | 71 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 07/07/2021 | 62 | 62
739 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District (SM/07273) | SM/07273 | 44.21 | 507 | RETROFITTING | 80 | Delayed | 96 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 11/12/2020 | 42.42 | 42.42
740 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme (SM/07231) | SM/07231 | 71.2 | 1069 | RETROFITTING | 80 | Delayed | 79 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 21/12/2021 | 56.41 | 56.41
741 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme (SM/07232) | SM/07232 | 21.55 | 250 | RETROFITTING | 80 | Delayed | 62 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 13.39 | 12.99
742 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District (SM/07692) | SM/07692 | 283.13 | 4345 | RETROFITTING | 80 | Delayed | 72 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 18/08/2021 | 202.73 | 202.73
743 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba (SM/07784) | SM/07784 | 82.98 | 1243 | RETROFITTING | 81 | Delayed | 74 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 10/02/2021 | 61.35 | 61.35
744 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid (SM/07284) | SM/07284 | 74.76 | 1021 | RETROFITTING | 81 | Delayed | 98 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 24/03/2021 | 72.9 | 72.9
745 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part (SM/07889) | SM/07889 | 49.64 | 629 | RETROFITTING | 82 | Delayed | 0 | 19/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 0 | 0
746 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I (SM/07890) | SM/07890 | 173.44 | 4583 | RETROFITTING | 82 | Delayed | 0 | 19/01/2021 | 31/12/2024 | 21/05/2024 | 23/08/2022 | 0 | 0
747 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s (SM/07234) | SM/07234 | 87.8 | 1305 | RETROFITTING | 82 | Delayed | 69 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 18/01/2021 | 60.85 | 60.85
748 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate (SM/07796) | SM/07796 | 92.37 | 1278 | RETROFITTING | 82 | Delayed | 65 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 60 | 57.79
749 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division (SM/08904) | SM/08904 | 385.71 | 4655 | RETROFITTING | 82 | Delayed | 44 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 07/10/2021 | 169.25 | 169.25
750 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A (SM/08687) | SM/08687 | 601.79 | 8286 | RETROFITTING | 82 | Delayed | 42 | 13/07/2021 | 31/03/2024 | 12/06/2023 | 25/02/2021 | 250.82 | 250.82
751 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) (SM/08280) | SM/08280 | 305.04 | 4099 | RETROFITTING | 83 | Delayed | 43 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 22/05/2021 | 131.25 | 131.25
752 | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. (SM/11714) | SM/11714 | 907.4 | 2504 | AUGMENTATION | 84 | Delayed | 21 | 03/08/2022 | 30/11/2024 | 03/05/2024 | 03/02/2022 | 190.36 | 190.36
753 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) (SM/07672) | SM/07672 | 161.68 | 2133 | RETROFITTING | 85 | Delayed | 50 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 23/02/2022 | 81.63 | 81.63
754 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe (SM/07667) | SM/07667 | 241.98 | 2718 | RETROFITTING | 85 | Delayed | 42 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 28/05/2021 | 100.47 | 100.47
755 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P (SM/07715) | SM/07715 | 69.44 | 897 | RETROFITTING | 85 | Delayed | 60 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 41.97 | 41.97
756 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) (SM/07690) | SM/07690 | 129.56 | 1920 | RETROFITTING | 85 | Delayed | 79 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 06/07/2021 | 102.89 | 102.89
757 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme (SM/06984) | SM/06984 | 99.87 | 1668 | RETROFITTING | 85 | Delayed | 51 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 18/01/2021 | 50.56 | 38.64
758 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part (SM/07293) | SM/07293 | 99.3 | 1313 | RETROFITTING | 85 | Delayed | 72 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 22/07/2021 | 71.41 | 71.41
759 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) (SM/07714) | SM/07714 | 79.62 | 1130 | RETROFITTING | 85 | Delayed | 94 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 12/02/2021 | 74.82 | 74.82
760 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M (SM/07888) | SM/07888 | 162.87 | 2294 | RETROFITTING | 85 | Delayed | 59 | 19/01/2021 | 31/12/2024 | 21/05/2024 | 07/10/2021 | 96.08 | 96.08
761 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba (SM/07705) | SM/07705 | 143.18 | 2126 | RETROFITTING | 85 | Delayed | 92 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 06/07/2021 | 131.88 | 109.88
762 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag (SM/07694) | SM/07694 | 83.34 | 1290 | RETROFITTING | 85 | Delayed | 45 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 21/06/2021 | 37.16 | 37.16
763 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) (SM/07716) | SM/07716 | 12.33 | 150 | RETROFITTING | 85 | Delayed | 70 | 08/01/2021 | 31/12/2024 | 21/05/2024 | 04/02/2021 | 8.62 | 8.62
764 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) (SM/07511) | SM/07511 | 62.34 | 821 | RETROFITTING | 85 | Delayed | 79 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 26/05/2021 | 49.17 | 49.17
765 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme (SM/07228) | SM/07228 | 84.17 | 1135 | RETROFITTING | 85 | Delayed | 54 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 13/11/2020 | 45.64 | 45.64
766 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Ramchandrapur (Code-314219) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-B) (SM/07733) | SM/07733 | 55.09 | 250 | RETROFITTING | 85 | Delayed | 20 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 11.14 | 11.14
767 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme (SM/07225) | SM/07225 | 30.52 | 420 | RETROFITTING | 85 | Delayed | 55 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 19/01/2021 | 16.81 | 16.81
768 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat (SM/07666) | SM/07666 | 299.57 | 4377 | RETROFITTING | 85 | Delayed | 14 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 18/12/2020 | 41.47 | 41.47
769 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) (SM/07668) | SM/07668 | 241.26 | 3297 | RETROFITTING | 85 | Delayed | 53 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 19/01/2022 | 128.06 | 128.06
770 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri (SM/08198) | SM/08198 | 348.01 | 4733 | RETROFITTING | 85 | Delayed | 49 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 28/02/2022 | 170.91 | 170.91
771 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur (SM/07664) | SM/07664 | 183.02 | 2281 | RETROFITTING | 85 | Delayed | 23 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 22/12/2020 | 42.3 | 42.3
772 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu (SM/08899) | SM/08899 | 373.6 | 5677 | RETROFITTING | 85 | Delayed | 58 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 216.15 | 206.51
773 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II (SM/07669) | SM/07669 | 151.27 | 1980 | RETROFITTING | 85 | Delayed | 68 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 26/08/2021 | 103.01 | 103.01
774 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Digha (VillageCode-314460) under command area under Digha ground water supply scheme (Part-A) (SM/06975) | SM/06975 | 86.87 | 1415 | RETROFITTING | 85 | Delayed | 64 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 03/02/2021 | 55.61 | 29.55
775 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) (SM/07670) | SM/07670 | 155.88 | 1854 | RETROFITTING | 85 | Delayed | 47 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 08/07/2021 | 72.78 | 72.78
776 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) (SM/07689) | SM/07689 | 32.25 | 449 | RETROFITTING | 85 | Delayed | 72 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 15/07/2021 | 23.33 | 23.33
777 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor (SM/08900) | SM/08900 | 579.45 | 5783 | RETROFITTING | 86 | Delayed | 44 | 29/09/2021 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 256.47 | 256.47
778 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o (SM/07235) | SM/07235 | 81.52 | 1312 | RETROFITTING | 86 | Delayed | 75 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 18/01/2021 | 61.37 | 61.37
779 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kolan Radhakantapur (314523) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis (SM/09754) | SM/09754 | 94.97 | 1260 | RETROFITTING | 87 | Delayed | 34 | 30/11/2021 | 31/03/2024 | 12/06/2023 |  | 31.97 | 31.97
780 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11562) | SM/11562 | 836.5 | 1425 | AUGMENTATION | 88 | Delayed | 24 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 200.5 | 193.99
781 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba (SM/08183) | SM/08183 | 389.91 | 5229 | RETROFITTING | 88 | Delayed | 73 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 08/12/2020 | 282.9 | 282.9
782 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Maiya Village (Code-314146) In The Command Area Of Maiya Ground Water Supply Scheme (Part-A) (SM/07734) | SM/07734 | 215.11 | 3230 | RETROFITTING | 89 | Delayed | 51 | 07/01/2021 | 31/12/2024 | 21/05/2024 | 13/01/2021 | 109.18 | 109.18
783 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme (SM/07229) | SM/07229 | 18.59 | 202 | RETROFITTING | 90 | Delayed | 72 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 28/12/2021 | 13.34 | 13.34
784 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) (SM/07230) | SM/07230 | 74.26 | 1095 | RETROFITTING | 90 | Delayed | 64 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 31/08/2021 | 47.4 | 46.21
785 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme (SM/07227) | SM/07227 | 92.47 | 1413 | RETROFITTING | 90 | Delayed | 80 | 08/12/2020 | 31/12/2024 | 21/05/2024 | 19/01/2021 | 74.36 | 74.36
786 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of (SM/07674) | SM/07674 | 295.52 | 3899 | RETROFITTING | 90 | Delayed | 71 | 08/01/2021 | 31/03/2024 | 12/06/2023 | 24/06/2021 | 210.09 | 210.09
787 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme (SM/06985) | SM/06985 | 99.86 | 1227 | RETROFITTING | 91 | Delayed | 50 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 50.05 | 50.05
788 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas (SM/08278) | SM/08278 | 517.99 | 6500 | RETROFITTING | 91 | Delayed | 53 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 19/01/2021 | 276.31 | 276.31
789 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply (SM/06974) | SM/06974 | 91.48 | 1403 | RETROFITTING | 92 | On track | 83 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 76.08 | 76.08
790 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand (SM/08191) | SM/08191 | 333.13 | 4609 | RETROFITTING | 95 | Delayed | 26 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 18/09/2020 | 88.2 | 88.2
791 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) (SM/07769) | SM/07769 | 173.5 | 2369 | RETROFITTING | 95 | Delayed | 95 | 07/01/2021 | 31/03/2024 | 07/08/2023 | 24/12/2021 | 165.21 | 165.21
792 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 (SM/08192) | SM/08192 | 349.63 | 4879 | RETROFITTING | 95 | Delayed | 33 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 15/01/2021 | 116.45 | 116.45
793 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) (SM/06973) | SM/06973 | 50.08 | 786 | RETROFITTING | 95 | On track | 80 | 09/11/2020 | 31/12/2024 | 21/05/2024 | 17/12/2020 | 40.07 | 40.07
794 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11566) | SM/11566 | 939.3 | 364 | AUGMENTATION | 98 | Delayed | 22 | 22/07/2022 | 31/03/2024 | 06/03/2024 | 05/10/2021 | 209.52 | 209.52
795 | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION (SM/11568) | SM/11568 | 936.21 | 709 | AUGMENTATION | 98 | Delayed | 44 | 22/07/2022 | 31/03/2024 | 20/03/2024 | 05/10/2021 | 411.28 | 411.28
796 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh (SM/08271) | SM/08271 | 423.18 | 5464 | RETROFITTING | 98 | Delayed | 40 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 23/06/2021 | 169.89 | 169.89
797 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba (SM/09762) | SM/09762 | 85.85 | 1790 | RETROFITTING | 98 | Delayed | 97 | 30/11/2021 | 31/12/2023 | 12/06/2023 | 12/04/2022 | 83.35 | 83.35
798 | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. (SM/13486) | SM/13486 | 655.64 | 766 | AUGMENTATION | 98 | Delayed | 37 | 02/11/2022 | 31/03/2024 | 07/03/2024 | 03/02/2022 | 242.06 | 242.06
799 | NAPARA PIPED WATER SUPPLY SCHEME. (SM/15051) | SM/15051 | 758.85 | 817 | NEW | 98 | On track | 24 | 04/02/2023 | 31/12/2024 | 22/05/2024 | 11/11/2022 | 181.42 | 181.42
800 | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10609) | SM/10609 | 929.25 | 500 | AUGMENTATION | 99 | Delayed | 30 | 19/04/2022 | 31/03/2024 | 29/02/2024 | 07/07/2022 | 279.75 | 279.75
801 | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. (SM/11713) | SM/11713 | 766.32 | 2376 | AUGMENTATION | 99 | Delayed | 20 | 03/08/2022 | 31/03/2024 | 22/02/2024 | 03/02/2022 | 150.33 | 141.56
802 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs (SM/07509) | SM/07509 | 97.74 | 1276 | RETROFITTING | 99 | Delayed | 3 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 28/05/2021 | 2.9 | 2.9
803 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara (SM/08193) | SM/08193 | 494.79 | 6813 | RETROFITTING | 99 | Delayed | 31 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 24/12/2020 | 152.81 | 152.81
804 | SALINDA AND ADJOINING MOUJAS PWSS (SM/13620) | SM/13620 | 927.78 | 2776 | NEW | 99 | Delayed | 68 | 11/11/2022 | 31/03/2024 | 12/06/2023 | 22/12/2022 | 627.97 | 627.97
805 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) (SM/07911) | SM/07911 | 167.77 | 2146 | RETROFITTING | 100 | 100% Physical | 7 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 25/11/2021 | 11.77 | 11.77
806 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) (SM/07927) | SM/07927 | 48 | 473 | RETROFITTING | 100 | 100% Physical | 65 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 07/02/2022 | 31.41 | 31.41
807 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area (SM/08199) | SM/08199 | 386.05 | 7777 | RETROFITTING | 100 | 100% Physical | 18 | 05/02/2021 | 31/03/2024 | 12/06/2023 | 28/01/2021 | 70.93 | 70.93
808 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Pakamati Mahula ( 315353 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under (SM/09740) | SM/09740 | 9.7 | 95 | RETROFITTING | 100 | 100% Physical | 43 | 30/11/2021 |  | 12/06/2023 | 27/08/2021 | 4.16 | 4.16
809 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under (SM/09755) | SM/09755 | 81.3 | 1078 | RETROFITTING | 100 | 100% Physical | 42 | 30/11/2021 |  | 12/06/2023 | 11/05/2022 | 34.33 | 34.33
810 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Palasi Sonadanga (314527) and Ramnapara (314496) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Bloc (SM/09756) | SM/09756 | 87.01 | 1154 | RETROFITTING | 100 | 100% Physical | 47 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 10/12/2020 | 40.79 | 40.79
811 | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10997) | SM/10997 | 332.05 | 470 | AUGMENTATION | 100 | 100% Physical | 34 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 27/12/2021 | 113.93 | 113.93
812 | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10628) | SM/10628 | 999.92 | 500 | AUGMENTATION | 100 | 100% Physical | 81 | 20/04/2022 | 31/12/2023 | 12/06/2023 | 22/04/2022 | 808.18 | 808.18
813 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11563) | SM/11563 | 993.35 | 1657 | AUGMENTATION | 100 | 100% Physical | 12 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 123.94 | 123.94
814 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11561) | SM/11561 | 930.14 | 812 | RETROFITTING | 100 | 100% Physical | 42 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 388.3 | 388.3
815 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F (SM/08113) | SM/08113 | 746.48 | 2600 | RETROFITTING | 100 | 100% Physical | 48 | 09/02/2021 | 31/03/2024 | 12/06/2023 | 20/01/2021 | 355.76 | 355.76
816 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) (SM/07910) | SM/07910 | 38.44 | 492 | RETROFITTING | 100 | 100% Physical | 60 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 10/08/2021 | 23.04 | 22.66
817 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida (SM/08100) | SM/08100 | 420.14 | 5365 | RETROFITTING | 100 | 100% Physical | 16 | 08/02/2021 |  | 12/06/2023 | 03/09/2021 | 65.42 | 65.42
818 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) (SM/08189) | SM/08189 | 2032.59 | 28496 | RETROFITTING | 100 | 100% Physical | 54 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 29/06/2021 | 1092.72 | 1092.72
819 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under (SM/08274) | SM/08274 | 384.16 | 5022 | RETROFITTING | 100 | 100% Physical | 60 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 05/01/2021 | 231.94 | 231.94
820 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad (SM/09743) | SM/09743 | 251.5 | 2145 | RETROFITTING | 100 | 100% Physical | 7 | 30/11/2021 | 31/03/2024 | 12/06/2023 | 27/08/2021 | 18.23 | 18.23
821 | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio (SM/11163) | SM/11163 | 195.5 | 319 | AUGMENTATION | 100 | 100% Physical | 5 | 02/06/2022 | 31/03/2024 | 12/06/2023 | 10/05/2022 | 9.6 | 9.6
822 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D (SM/09840) | SM/09840 | 29.12 | 361 | RETROFITTING | 100 | 100% Physical | 97 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 19/02/2021 | 28.27 | 28.27
823 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Paraspur ( 314616 ) of Muradpur-Jalangi (Zone-I, Zone - II & Zone - III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block o (SM/09845) | SM/09845 | 16.64 | 192 | RETROFITTING | 100 | 100% Physical | 50 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 07/12/2020 | 8.24 | 8.24
824 | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. (SM/10015) | SM/10015 | 965.82 | 4227 | AUGMENTATION | 100 | 100% Physical | 25 | 27/12/2021 | 31/03/2024 | 02/02/2024 | 05/10/2021 | 239.18 | 239.18
825 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) (SM/07221) | SM/07221 | 62.74 | 929 | RETROFITTING | 100 | 100% Physical | 77 | 08/12/2020 | 31/03/2024 | 12/06/2023 | 02/09/2021 | 48.51 | 48.51
826 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD (SM/10812) | SM/10812 | 705.89 | 3873 | AUGMENTATION | 100 | 100% Physical | 7 | 25/05/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 51.63 | 51.63
827 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas (SM/08279) | SM/08279 | 340.16 | 4389 | RETROFITTING | 100 | 100% Physical | 63 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 04/02/2021 | 213.06 | 213.06
828 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P (SM/07906) | SM/07906 | 291.34 | 3781 | RETROFITTING | 100 | 100% Physical | 51 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 03/02/2022 | 149.55 | 149.55
829 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- (SM/07923) | SM/07923 | 152.87 | 1840 | RETROFITTING | 100 | 100% Physical | 46 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 09/12/2020 | 69.65 | 69.65
830 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur (SM/08194) | SM/08194 | 442.13 | 6073 | RETROFITTING | 100 | 100% Physical | 67 | 18/02/2021 | 31/03/2024 | 12/06/2023 | 08/07/2021 | 297.11 | 297.11
831 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) (SM/08275) | SM/08275 | 558.86 | 7747 | RETROFITTING | 100 | 100% Physical | 32 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 22/12/2021 | 179.85 | 179.85
832 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad (SM/09836) | SM/09836 | 32.06 | 396 | RETROFITTING | 100 | 100% Physical | 97 | 02/12/2021 | 31/03/2023 | 12/06/2023 | 27/08/2021 | 31.13 | 31.13
833 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh (SM/09839) | SM/09839 | 17.46 | 205 | RETROFITTING | 100 | 100% Physical | 97 | 02/12/2021 |  | 12/06/2023 | 04/12/2020 | 16.95 | 14.47
834 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di (SM/09847) | SM/09847 | 67.61 | 776 | RETROFITTING | 100 | 100% Physical | 19 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 05/01/2021 | 13.15 | 13.15
835 | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. (SM/11715) | SM/11715 | 998.51 | 9386 | AUGMENTATION | 100 | 100% Physical | 1 | 03/08/2022 | 31/03/2024 | 12/06/2023 | 27/01/2021 | 10.96 | 10.96
836 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11567) | SM/11567 | 723.92 | 105 | AUGMENTATION | 100 | 100% Physical | 18 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 127.52 | 127.52
837 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( (SM/07913) | SM/07913 | 96.61 | 1234 | RETROFITTING | 100 | 100% Physical | 19 | 19/01/2021 |  | 12/06/2023 | 08/01/2021 | 18.1 | 18.1
838 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( (SM/07918) | SM/07918 | 79.52 | 992 | RETROFITTING | 100 | 100% Physical | 59 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 28/06/2021 | 47.22 | 47.22
839 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District (SM/07200) | SM/07200 | 57.01 | 731 | RETROFITTING | 100 | 100% Physical | 100 | 08/12/2020 | 31/03/2024 | 12/06/2023 | 27/08/2021 | 57.01 | 57.01
840 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi (SM/07506) | SM/07506 | 83.51 | 1153 | RETROFITTING | 100 | 100% Physical | 85 | 29/12/2020 | 31/03/2024 | 12/06/2023 | 21/06/2021 | 70.8 | 70.8
841 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B (SM/09750) | SM/09750 | 265.85 | 3979 | RETROFITTING | 100 | 100% Physical | 1 | 29/11/2021 |  | 12/06/2023 | 25/02/2021 | 2.38 | 2.38
842 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh (SM/09844) | SM/09844 | 9.41 | 89 | RETROFITTING | 100 | 100% Physical | 42 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 28/06/2021 | 3.97 | 3.97
843 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis (SM/09760) | SM/09760 | 66.1 | 847 | RETROFITTING | 100 | 100% Physical | 58 | 30/11/2021 | 31/12/2023 | 12/06/2023 | 17/02/2022 | 38.52 | 38.52
844 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida (SM/09849) | SM/09849 | 44.53 | 899 | RETROFITTING | 100 | 100% Physical | 56 | 02/12/2021 | 31/12/2023 | 12/06/2023 | 24/03/2022 | 24.76 | 24.76
845 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under (SM/09851) | SM/09851 | 28.53 | 392 | RETROFITTING | 100 | 100% Physical | 97 | 02/12/2021 | 31/03/2024 | 12/06/2023 | 27/08/2021 | 27.7 | 9
846 | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. (SM/11569) | SM/11569 | 512.1 | 551 | AUGMENTATION | 100 | 100% Physical | 52 | 22/07/2022 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 263.82 | 263.82
847 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl (SM/08277) | SM/08277 | 418.69 | 5674 | RETROFITTING | 100 | 100% Physical | 24 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 23/11/2021 | 101.55 | 101.55
848 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) (SM/07926) | SM/07926 | 38.41 | 427 | RETROFITTING | 100 | 100% Physical | 97 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 08/01/2021 | 37.29 | 37.29
849 | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. (SM/08721) | SM/08721 | 782.35 | 5 | ANGANWADI | 100 | 100% Physical | 0 | 07/09/2021 | 31/03/2024 | 12/06/2023 | 22/02/2021 | 0 | 0
850 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II (SM/11198) | SM/11198 | 592.03 | 1544 | AUGMENTATION | 100 | 100% Physical | 9 | 03/06/2022 | 31/03/2024 | 12/06/2023 | 25/01/2021 | 52.57 | 52.57
851 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) (SM/07922) | SM/07922 | 105.77 | 1302 | RETROFITTING | 100 | 100% Physical | 97 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 29/06/2021 | 102.69 | 102.69
852 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV (SM/07283) | SM/07283 | 52.54 | 563 | RETROFITTING | 100 | 100% Physical | 56 | 10/12/2020 | 31/03/2024 | 12/06/2023 | 25/01/2021 | 29.21 | 29.21
853 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan (SM/09737) | SM/09737 | 875.99 | 7358 | RETROFITTING | 100 | 100% Physical | 20 | 29/11/2021 | 31/03/2024 | 12/06/2023 | 27/05/2021 | 176.19 | 176.19
854 | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10610) | SM/10610 | 567.92 | 890 | AUGMENTATION | 100 | 100% Physical | 75 | 19/04/2022 | 31/03/2024 | 12/06/2023 | 10/05/2022 | 424.67 | 424.67
855 | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. (SM/11716) | SM/11716 | 174.5 | 357 | AUGMENTATION | 100 | 100% Physical | 24 | 03/08/2022 | 31/03/2024 | 12/06/2023 | 03/02/2022 | 41.89 | 41.89
856 | MOKTARPUR PIPED WATER SUPPLY SCHEME (SM/11620) | SM/11620 | 300.98 | 436 | NEW | 100 | 100% Physical | 29 | 26/07/2022 |  | 12/06/2023 | 10/05/2023 | 87.9 | 87.9
857 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I (SM/11220) | SM/11220 | 417.3 | 3301 | AUGMENTATION | 100 | 100% Physical | 2 | 15/06/2022 | 31/03/2024 | 12/06/2023 | 03/09/2021 | 7.54 | 7.54
858 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P (SM/08913) | SM/08913 | 964.85 | 5663 | RETROFITTING | 100 | 100% Physical | 66 | 29/09/2021 | 31/03/2024 | 12/06/2023 | 05/10/2021 | 632.36 | 632.36
859 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc (SM/08688) | SM/08688 | 461.79 | 7015 | RETROFITTING | 100 | 100% Physical | 39 | 13/07/2021 | 31/03/2024 | 12/06/2023 | 05/01/2021 | 182.1 | 182.1
860 | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph (SM/10606) | SM/10606 | 575.23 | 7626 | RETROFITTING | 100 | 100% Physical | 58 | 19/04/2022 | 31/03/2024 | 12/06/2023 | 08/02/2021 | 332.5 | 332.5
861 | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. (SM/11712) | SM/11712 | 361.5 | 148 | AUGMENTATION | 100 | 100% Physical | 19 | 03/08/2022 | 31/03/2024 | 12/06/2023 | 03/02/2022 | 69.8 | 69.8
862 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kusbaria (314722) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) (SM/07912) | SM/07912 | 105.04 | 1342 | RETROFITTING | 100 | 100% Physical | 66 | 19/01/2021 | 31/03/2024 | 12/06/2023 | 25/08/2021 | 68.95 | 68.95
863 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme (SM/08276) | SM/08276 | 342.72 | 4370 | RETROFITTING | 100 | 100% Physical | 54 | 19/02/2021 | 31/03/2024 | 12/06/2023 | 28/01/2021 | 184.18 | 184.18
864 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis (SM/09749) | SM/09749 | 81.3 | 1078 | RETROFITTING | 100 | 100% Physical | 42 | 29/11/2021 | 31/03/2024 | 12/06/2023 | 18/08/2021 | 34.05 | 34.05
865 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D (SM/09848) | SM/09848 | 34.24 | 435 | RETROFITTING | 100 | 100% Physical | 61 | 02/12/2021 |  | 12/06/2023 | 24/03/2021 | 20.78 | 20.73
866 | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10634) | SM/10634 | 620.12 | 472 | AUGMENTATION | 100 | 100% Physical | 47 | 20/04/2022 | 31/03/2024 | 12/06/2023 | 22/04/2022 | 288.56 | 288.56
867 | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. (SM/11161) | SM/11161 | 205.19 | 268 | AUGMENTATION | 100 | 100% Physical | 0 | 02/06/2022 | 31/03/2024 | 12/06/2023 | 25/08/2021 | 0 | 0
868 | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/10679) | SM/10679 | 989.12 | 2843 | AUGMENTATION | 100 | 100% Physical | 77 | 29/04/2022 | 31/03/2024 | 12/06/2023 | 27/12/2021 | 758.46 | 758.46
869 | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. (SM/11197) | SM/11197 | 595.94 | 1804 | AUGMENTATION | 100 | 100% Physical | 14 | 03/06/2022 | 31/03/2024 | 12/06/2023 | 22/04/2022 | 85.64 | 85.64
870 | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Nimtita (313863) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District under Murshidabad Division PheDte. (SM/11215) | SM/11215 | 164.09 | 489 | AUGMENTATION | 100 | 100% Physical | 15 | 15/06/2022 | 31/03/2024 | 12/06/2023 | 18/02/2021 | 24.27 | 24.27
871 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u (SM/09738) | SM/09738 | 54.13 | 720 | RETROFITTING | 100 | 100% Physical | 67 | 29/11/2021 | 31/12/2023 | 12/06/2023 | 10/08/2021 | 36.29 | 36.29
872 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( (SM/08099) | SM/08099 | 366.99 | 4690 | RETROFITTING | 100 | 100% Physical | 44 | 08/02/2021 | 31/03/2024 | 12/06/2023 | 03/06/2022 | 160.31 | 160.31
Total |  |  | 555323.04 | 1794841 | [8 empty] | 129657.27 | 127769.1