## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | LAYEKPUR PIPED WATER SUPPLY SCHEME (SM/18361) | SM/18361 | 1217.25 | 3872 | NEW | 0 | 0% Physical | 0 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 21/09/2023 | 0 | 0
2 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. (SM/13374) | SM/13374 | 14.22 | 215 | RETROFITTING | 0 | WO no issued | 0 | 19/10/2022 | 08/02/2025 | 16/05/2025 |  | 0 | 0
3 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum (SM/18783) | SM/18783 | 99.79 | 1303 | RETROFITTING | 0 | 0% Physical | 60 | 29/08/2023 | 30/06/2025 | 16/05/2025 | 21/09/2023 | 60.04 | 60.04
4 | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT (SM/14675) | SM/14675 | 950.21 | 2321 | NEW | 0 | 0% Physical | 8 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 17/04/2023 | 78.96 | 44.86
5 | New Pipe Testing Laboratory for testing of UPVC and HDPE pipes at Suri, Birbhum under Birbhum Division. (SM/16483) | SM/16483 | 194.37 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 25/07/2023 | 0 | 0
6 | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. (SM/19263) | SM/19263 | 76.18 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 27/01/2025 | 0 | 0
7 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/08981) | SM/08981 | 25.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 |  | 0 | 0
8 | Procurement of Computer and Peripherals for the office use in Bolpur Mechanical Division, AE-III Central Mechanical Division, Birbhum Mechanical Sub-Division (Drilling) PHE Dte. (SM/18141) | SM/18141 | 21.47 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 |  | 0 | 0
9 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. (SM/06632) | SM/06632 | 71.7 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 05/07/2021 | 0 | 0
10 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratory. (SM/06628) | SM/06628 | 7.35 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 23/07/2021 | 0 | 0
11 | Operational charges of PHED managed Laboratories related to water quality monitoring & surveillance under Jal Jeevan Mission for 2024-25 (SM/19316) | SM/19316 | 11.56 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 26/12/2024 |  | 27/12/2024 |  | 0 | 0
12 | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM (SM/15636) | SM/15636 | 50.89 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 30/06/2023 | 0 | 0
13 | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. (SM/18278) | SM/18278 | 12.02 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 |  | 0 | 0
14 | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission (SM/19083) | SM/19083 | 63.6 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
15 | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. (SM/09199) | SM/09199 | 10.32 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 29/10/2021 |  | 04/11/2021 | 31/12/2020 | 0 | 0
16 | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. (SM/15637) | SM/15637 | 90.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 24/01/2022 | 0 | 0
17 | Procurement Chemicals & Consumables, Glassware etc. Required for smooth running of the Different Laboratories under JJM under Birbhum Division PHE Dte. (SM/19268) | SM/19268 | 102.97 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
18 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Birbhum District. (SM/09198) | SM/09198 | 290.12 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 04/11/2021 | 19/08/2022 | 0 | 0
19 | TATINAPARA PIPED WATER SUPPLY SCHEME (SM/13979) | SM/13979 | 880.48 | 2460 | NEW | 1 | Delayed | 1 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 21/09/2023 | 4.59 | 4.59
20 | Salan Piped Water Supply Scheme. (SM/14207) | SM/14207 | 778.17 | 2622 | NEW | 2 | Delayed | 10 | 10/01/2023 | 08/02/2025 | 16/05/2025 | 25/08/2023 | 74.13 | 74.13
21 | RANIPARA PIPED WATER SUPPLY SCHEME (SM/16276) | SM/16276 | 540.82 | 876 | NEW | 2 | Delayed | 1 | 24/02/2023 | 08/02/2025 | 16/05/2025 | 11/05/2022 | 7.92 | 7.92
22 | Masra Piped Water Supply Scheme. (SM/18463) | SM/18463 | 1206.76 | 3940 | NEW | 2 | Delayed | 0 | 20/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 0 | 0
23 | Radipur Piped Water Supply Scheme. (SM/14027) | SM/14027 | 519.73 | 1716 | NEW | 3 | Delayed | 2 | 05/12/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 11.68 | 11.68
24 | Charkalgram Piped Water Supply Scheme (SM/13481) | SM/13481 | 953.48 | 2189 | NEW | 3 | Delayed | 2 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 14.75 | 14.75
25 | CHUNPALASHI PIPED WATER SUPPLY SCHEME (SM/13637) | SM/13637 | 740.04 | 1863 | NEW | 5 | Delayed | 7 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 31/03/2022 | 54.26 | 54.26
26 | MADDA PIPED WATER SUPPLY SCHEME (SM/15255) | SM/15255 | 639.56 | 1390 | NEW | 5 | Delayed | 2 | 07/02/2023 | 08/02/2025 | 16/05/2025 | 31/03/2022 | 12.26 | 12.26
27 | GOPINATHPUR PIPED WATER SUPPLY SCHEME (SM/14897) | SM/14897 | 727.26 | 1914 | NEW | 5 | Delayed | 3 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 06/04/2023 | 24.09 | 24.09
28 | Hatikata Piped Water Supply Scheme (SM/16198) | SM/16198 | 290.59 | 619 | NEW | 5 | Delayed | 5 | 23/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 14.48 | 14.48
29 | SHIRSHA PIPED WATER SUPPLY SCHEME (SM/13647) | SM/13647 | 974.04 | 2439 | NEW | 5 | Delayed | 5 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 10/08/2023 | 46.4 | 46.4
30 | NAWADA PALANDI PIPED WATER SUPPLY SCHEME (SM/14682) | SM/14682 | 1029.06 | 2203 | NEW | 5 | Delayed | 4 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 43.16 | 43.16
31 | Dhananjaypur Piped Water Supply Scheme. (SM/12688) | SM/12688 | 701.06 | 1773 | NEW | 5 | Delayed | 4 | 21/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 31.3 | 31.3
32 | KAHINAGAR PIPED WATER SUPPLY SCHME (SM/12887) | SM/12887 | 807.08 | 2309 | NEW | 5 | Delayed | 1 | 23/09/2022 | 31/10/2025 | 16/05/2025 | 25/04/2023 | 12.05 | 12.05
33 | FEUGRAM PIPED WATER SUPPLY SCHEME (SM/13477) | SM/13477 | 813.8 | 1734 | NEW | 5 | Delayed | 6 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 10/03/2022 | 47.9 | 47.9
34 | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME (SM/13950) | SM/13950 | 800.41 | 1812 | NEW | 5 | Delayed | 2 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 05/05/2022 | 15.81 | 15.81
35 | MONACHITURA PIPED WATER SUPPLY SCHEME (SM/14450) | SM/14450 | 846.93 | 2499 | NEW | 5 | Delayed | 1 | 20/01/2023 | 08/02/2025 | 16/05/2025 | 15/03/2022 | 4.39 | 4.39
36 | SAJNOR PIPED WATER SUPPLY SCHEME (SM/14678) | SM/14678 | 872.23 | 2296 | NEW | 5 | Delayed | 4 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 25/08/2023 | 30.6 | 30.6
37 | THIBA PIPEED WATER SUPPLY SCHEME (SM/14968) | SM/14968 | 538.07 | 1010 | NEW | 5 | Delayed | 4 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 25/05/2022 | 20.79 | 20.79
38 | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME (SM/14534) | SM/14534 | 1071.04 | 2281 | NEW | 5 | Delayed | 4 | 30/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 46.75 | 46.75
39 | Budhigram Piped Water Supply Scheme (SM/16762) | SM/16762 | 763.84 | 1888 | NEW | 5 | Delayed | 5 | 13/03/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 38.61 | 38.61
40 | BHEPUR PIPED WATER SUPPLY SCHEME (SM/13759) | SM/13759 | 705.69 | 1502 | NEW | 5 | Delayed | 5 | 18/11/2022 | 08/02/2025 | 16/05/2025 | 12/04/2022 | 37.22 | 37.22
41 | SANTOSHPUR PIPED WATER SUPPLY SCHEME (SM/14895) | SM/14895 | 777.41 | 1649 | NEW | 5 | Delayed | 4 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 25/05/2022 | 31.8 | 31.8
42 | PANCHPARA PIPED WATER SUPPLY SCHEME (SM/13951) | SM/13951 | 639.73 | 1851 | NEW | 5 | Delayed | 2 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 05/05/2022 | 14.57 | 14.57
43 | KHAYERBANI PIPED WATER SUPPLY SCHEME (SM/14677) | SM/14677 | 522.91 | 1169 | NEW | 5 | Delayed | 5 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 25/04/2022 | 27.89 | 27.89
44 | GOALDIHI PIPED WATER SUPPLY SCHEME (SM/15528) | SM/15528 | 523.1 | 1042 | NEW | 5 | Delayed | 3 | 15/02/2023 | 08/02/2025 | 16/05/2025 | 22/03/2022 | 13.37 | 13.37
45 | RAYEN PIPED WATER SUPPLY SCHEME (SM/14957) | SM/14957 | 452.46 | 698 | NEW | 5 | Delayed | 5 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 19/05/2022 | 20.81 | 20.81
46 | BENGA CHATRA PIPED WATER SUPPLY SCHEME (SM/13408) | SM/13408 | 716.72 | 1526 | NEW | 5 | Delayed | 5 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 25/03/2022 | 35.13 | 35.13
47 | BALIARA PIPED WATER SUPPLY SCHEME (SM/14847) | SM/14847 | 709.05 | 1576 | NEW | 5 | Delayed | 4 | 03/02/2023 | 31/03/2026 | 16/05/2025 | 25/04/2023 | 27.87 | 27.87
48 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. (SM/13375) | SM/13375 | 34.41 | 432 | RETROFITTING | 5 | WO no issued | 0 | 19/10/2022 | 08/02/2025 | 16/05/2025 |  | 0 | 0
49 | ANGORA PIPED WATER SUPPLY SCHEME (SM/13971) | SM/13971 | 911.87 | 1822 | NEW | 5 | Delayed | 3 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 31.37 | 31.37
50 | Khanpur Piped Water Supply Scheme. (SM/14085) | SM/14085 | 846.77 | 2489 | NEW | 5 | Delayed | 25 | 12/12/2022 | 30/11/2025 | 16/05/2025 | 20/04/2023 | 208.41 | 208.41
51 | SHEKHAMPUR PIPED WATER SUPPLY SCHEME (SM/14956) | SM/14956 | 744.62 | 1672 | NEW | 5 | Delayed | 4 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 17/05/2022 | 32.26 | 32.26
52 | Sekupur piped water supply scheme. (SM/13650) | SM/13650 | 349.5 | 762 | NEW | 5 | Delayed | 4 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 12.93 | 12.93
53 | RANIBAZAR PIPED WATER SUPPLY SCHEME (SM/14850) | SM/14850 | 646 | 1440 | NEW | 5 | Delayed | 3 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 11/05/2022 | 18.23 | 18.23
54 | DULA SAHAPUR PIPED WATER SUPPLY SCHEME (SM/14746) | SM/14746 | 999.21 | 3496 | NEW | 5 | Delayed | 3 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 28.34 | 28.34
55 | Kashtagara Piped Water Supply Scheme. (SM/18733) | SM/18733 | 1262.41 | 4375 | NEW | 5 | Delayed | 1 | 14/08/2023 | 08/02/2025 | 16/05/2025 | 03/10/2023 | 17.3 | 17.3
56 | Mayandal Piped Water Supply Scheme (SM/16273) | SM/16273 | 158.49 | 342 | NEW | 8 | Delayed | 7 | 23/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 11.82 | 11.82
57 | Ninga Piped Water Supply Scheme (SM/14089) | SM/14089 | 844.34 | 2013 | NEW | 8 | Delayed | 7 | 12/12/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 62.17 | 62.17
58 | Nichinta Piped Water Supply Scheme (Khoyrasole Block) (SM/16271) | SM/16271 | 145.99 | 237 | NEW | 8 | Delayed | 1 | 24/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 0.82 | 0.82
59 | Tilai piped water supply scheme. (SM/13127) | SM/13127 | 404.7 | 1247 | NEW | 10 | Delayed | 7 | 10/10/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 28.48 | 28.48
60 | Srikantapur piped water supply scheme. (SM/13652) | SM/13652 | 774.31 | 2142 | NEW | 10 | Delayed | 7 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 53.03 | 53.03
61 | KADOA PIPED WAYER SUPPLY SCHEME (SM/14668) | SM/14668 | 594.33 | 1039 | NEW | 10 | Delayed | 6 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 18/04/2022 | 37.52 | 37.52
62 | BENAGRAM PIPED WATER SUPPLY SCHEME (SM/13377) | SM/13377 | 624.74 | 1334 | NEW | 10 | Delayed | 8 | 18/10/2022 | 08/02/2025 | 16/05/2025 | 27/04/2022 | 50.24 | 50.24
63 | GOPINATHPUR PIPED WATER SUPPLY SCHEME (SM/15253) | SM/15253 | 649.94 | 1633 | NEW | 10 | Delayed | 8 | 06/02/2023 | 08/02/2025 | 16/05/2025 | 07/04/2022 | 50 | 50
64 | Dakhalbati Piped Water Supply Scheme. (SM/18363) | SM/18363 | 2553.67 | 6565 | NEW | 10 | Delayed | 6 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 11/10/2023 | 158.14 | 158.14
65 | Daskalgram Piped Water Supply Scheme (SM/18353) | SM/18353 | 1197.31 | 2564 | NEW | 10 | Delayed | 8 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 90.53 | 90.53
66 | Harinduba Piped Water Supply Scheme. (SM/12692) | SM/12692 | 739.16 | 1850 | NEW | 10 | Delayed | 9 | 20/09/2022 | 30/09/2025 | 16/05/2025 | 20/04/2023 | 69.26 | 69.26
67 | JIJIGRAM PIPED WATER SUPPLY SCHEME. (SM/12837) | SM/12837 | 900.37 | 2677 | NEW | 10 | Delayed | 56 | 22/09/2022 | 31/03/2026 | 16/05/2025 | 14/07/2023 | 503.35 | 503.35
68 | Dakshin Madanpur Piped Water Supply Scheme. (SM/12687) | SM/12687 | 473.11 | 1121 | NEW | 10 | Delayed | 7 | 21/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 31.24 | 31.24
69 | MATIKONA PIPED WATER SUPPLY SCHEME (SM/13643) | SM/13643 | 860.82 | 2153 | NEW | 10 | Delayed | 9 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 10/08/2023 | 80.91 | 80.91
70 | PAPURI PIPED WATER SUPPLY SCHEME (SM/14691) | SM/14691 | 889.54 | 1966 | NEW | 10 | Delayed | 6 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 52.72 | 52.72
71 | Chhora Piped Water Supply Scheme. (SM/16761) | SM/16761 | 497.37 | 1817 | NEW | 10 | Delayed | 9 | 13/03/2023 | 08/02/2025 | 16/05/2025 | 03/10/2023 | 45.23 | 45.23
72 | Ekpara Piped Water Supply Scheme. (SM/12690) | SM/12690 | 289.55 | 618 | NEW | 10 | Delayed | 9 | 20/09/2022 | 12/04/2025 | 16/05/2025 | 08/06/2023 | 27.49 | 27.49
73 | Dakshin Kasila Piped Water Supply Scheme. (SM/12686) | SM/12686 | 909.45 | 2600 | NEW | 10 | Delayed | 5 | 21/09/2022 | 31/03/2026 | 16/05/2025 | 25/04/2023 | 43.58 | 43.58
74 | Bergram Piped Water Supply Scheme. (SM/13482) | SM/13482 | 527.4 | 1351 | NEW | 10 | Delayed | 12 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 60.92 | 60.92
75 | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) (SM/16270) | SM/16270 | 153.88 | 272 | NEW | 10 | Delayed | 9 | 24/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 14.36 | 14.36
76 | MANIKPUR PIPED WATER SUPPLY SCHEME (SM/18509) | SM/18509 | 1125.72 | 3406 | NEW | 10 | Delayed | 9 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 100.48 | 100.48
77 | KURUMBA PIPED WATER SUPPLY SCHEME (SM/14743) | SM/14743 | 674.03 | 2184 | NEW | 10 | Delayed | 10 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 22/03/2023 | 68.06 | 60.67
78 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) (SM/07647) | SM/07647 | 64.73 | 1050 | RETROFITTING | 10 | Delayed | 9 | 07/01/2021 | 08/02/2025 | 16/05/2025 | 28/07/2023 | 5.85 | 5.85
79 | Bidhyadharpur Piped Water Supply Scheme. (SM/13708) | SM/13708 | 621.16 | 1761 | NEW | 10 | Delayed | 9 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 53.25 | 53.25
80 | BHETER PIPED WATER SUPPLY SCHEME (SM/14848) | SM/14848 | 507.47 | 1132 | NEW | 10 | Delayed | 8 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 21/03/2022 | 38.44 | 38.44
81 | Demurtita Piped Water Supply Scheme. (SM/14981) | SM/14981 | 279.34 | 588 | NEW | 10 | Delayed | 10 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 27.52 | 27.52
82 | Majhkanda Piped Water Supply Scheme. (SM/14896) | SM/14896 | 653.84 | 2709 | NEW | 10 | Delayed | 7 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 45.86 | 45.86
83 | Kusumba Piped Water Supply Scheme. (SM/18362) | SM/18362 | 1173.23 | 4056 | NEW | 10 | Delayed | 5 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 64.05 | 64.05
84 | Prasadpur Piped Water Supply Scheme (SM/13478) | SM/13478 | 833.6 | 2277 | NEW | 10 | Delayed | 29 | 02/11/2022 | 31/12/2025 | 16/05/2025 | 26/07/2023 | 244.53 | 244.53
85 | Sandhyajol Piped Water Supply Scheme (SM/13981) | SM/13981 | 775.21 | 2016 | NEW | 10 | Delayed | 8 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 62.74 | 62.74
86 | Chora Piped Water Supply Scheme (SM/15523) | SM/15523 | 248.08 | 482 | NEW | 10 | Delayed | 10 | 16/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 25.17 | 25.17
87 | Meherpur and Adjoining Mouzas PWSS (SM/12457) | SM/12457 | 488.08 | 1520 | NEW | 12 | Delayed | 10 | 13/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 48.68 | 48.68
88 | Balijuri Piped Water Supply Scheme. (SM/12682) | SM/12682 | 940.28 | 2567 | NEW | 15 | Delayed | 14 | 21/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 134.51 | 134.51
89 | Tamra Piped Water Supply Scheme (SM/18739) | SM/18739 | 284.35 | 627 | NEW | 15 | Delayed | 12 | 17/08/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 34.28 | 34.28
90 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMRITAPUR AND MAJHARA MOUZAS UNDER MURARAI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11908) | SM/11908 | 85 | 182 | NEW | 15 | Delayed | 3 | 22/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 2.8 | 0
91 | Sahapur Piped Water Supply Scheme. (SM/18520) | SM/18520 | 1609.49 | 4720 | NEW | 15 | Delayed | 14 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 232.31 | 232.31
92 | Bhadulia Piped Water Supply Scheme (SM/14674) | SM/14674 | 474.51 | 985 | NEW | 15 | Delayed | 16 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 77.03 | 77.03
93 | Monoharpur Piped Water Supply Scheme. (SM/13511) | SM/13511 | 391.63 | 835 | NEW | 15 | Delayed | 20 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 78.35 | 78.35
94 | Kukutia piped water supply scheme. (SM/13601) | SM/13601 | 549.6 | 1341 | NEW | 15 | Delayed | 15 | 09/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 83.49 | 83.49
95 | FARIDPUR PIPED WATER SUPPLY SCHEME (SM/14971) | SM/14971 | 725.24 | 1444 | NEW | 15 | Delayed | 11 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 12/04/2022 | 79.93 | 79.93
96 | Barua Gopalpur Piped Water Supply Scheme. (SM/14421) | SM/14421 | 1288.16 | 3708 | NEW | 15 | Delayed | 11 | 20/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 139.98 | 139.98
97 | BHATRA PIPED WATER SUPPLY SCHEME (SM/14958) | SM/14958 | 785.97 | 2391 | NEW | 15 | Delayed | 10 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 07/04/2022 | 75.58 | 75.58
98 | Gokrui Piped Water Supply Scheme. (SM/13631) | SM/13631 | 426.79 | 826 | NEW | 16 | Delayed | 14 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 60.12 | 60.12
99 | Ekura Piped Water Supply Scheme. (SM/13949) | SM/13949 | 461.93 | 667 | NEW | 18 | Delayed | 16 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 71.78 | 71.78
100 | Aliat Piped Water Supply Scheme (SM/14083) | SM/14083 | 414.62 | 804 | NEW | 19 | Delayed | 17 | 12/12/2022 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 70.04 | 70.04
101 | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/14208) | SM/14208 | 407.65 | 851 | NEW | 20 | Delayed | 4 | 10/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 17.65 | 17.65
102 | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district (SM/18510) | SM/18510 | 1188.4 | 2733 | NEW | 20 | Delayed | 11 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 126.33 | 83.37
103 | Metegaon and Adjoining Mouzas PWSS (SM/12700) | SM/12700 | 653.76 | 1309 | NEW | 20 | Delayed | 18 | 21/09/2022 | 30/09/2025 | 16/05/2025 | 06/04/2023 | 120.69 | 120.69
104 | Kanduri Piped Water Supply Scheme. (SM/14824) | SM/14824 | 543.12 | 1977 | NEW | 20 | Delayed | 5 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 03/10/2023 | 29.1 | 29.1
105 | Penchalia Piped Water Supply Scheme (SM/16282) | SM/16282 | 389.54 | 831 | NEW | 20 | Delayed | 16 | 24/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 61.18 | 61.18
106 | HATIKRA PIPED WATER SUPPLY SCHEME. (SM/12893) | SM/12893 | 460.73 | 1587 | NEW | 20 | Delayed | 21 | 23/09/2022 | 31/03/2026 | 16/05/2025 | 12/04/2023 | 97.4 | 97.4
107 | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) (SM/14854) | SM/14854 | 582.15 | 1544 | NEW | 20 | Delayed | 22 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 127.52 | 127.52
108 | Rupaspur Piped Water Supply Scheme. (SM/14081) | SM/14081 | 436.17 | 975 | NEW | 20 | Delayed | 19 | 12/12/2022 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 80.85 | 80.85
109 | Majhara piped water supply scheme (SM/12698) | SM/12698 | 443.6 | 1109 | NEW | 20 | Delayed | 10 | 21/09/2022 | 31/12/2025 | 16/05/2025 | 19/04/2023 | 42.92 | 42.92
110 | HATKALUA PIPED WATER SUPPLY SCHEME (SM/14115) | SM/14115 | 674.17 | 1845 | NEW | 20 | Delayed | 16 | 02/01/2023 | 31/12/2025 | 16/05/2025 | 06/04/2023 | 107.48 | 107.48
111 | RAGHABPUR PIPED WATER SUPPLY SCHEME (SM/14747) | SM/14747 | 379.11 | 575 | NEW | 20 | Delayed | 17 | 31/01/2023 | 31/03/2026 | 16/05/2025 | 22/03/2023 | 64.63 | 64.63
112 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sadasibpur (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/13373) | SM/13373 | 13.41 | 207 | RETROFITTING | 20 | WO no issued | 0 | 19/10/2022 | 31/05/2025 | 16/05/2025 | 22/12/2022 | 0 | 0
113 | Ayas Piped Water Supply Scheme. (SM/18669) | SM/18669 | 2251.52 | 6861 | NEW | 20 | Delayed | 17 | 04/08/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 377.62 | 377.62
114 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. (SM/12662) | SM/12662 | 42.93 | 826 | RETROFITTING | 20 | Delayed | 18 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 02/05/2023 | 7.57 | 7.57
115 | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) (SM/14851) | SM/14851 | 475.95 | 1165 | NEW | 20 | Delayed | 19 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 91.64 | 91.64
116 | Banior Piped Water Supply Scheme. (SM/14688) | SM/14688 | 2842.94 | 5908 | NEW | 20 | Delayed | 29 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 836.25 | 836.25
117 | Paratpur Piped Water Supply Scheme. (SM/13474) | SM/13474 | 806.88 | 2066 | NEW | 20 | Delayed | 17 | 02/11/2022 | 31/03/2026 | 16/05/2025 | 08/08/2023 | 135.53 | 135.53
118 | Sekedda Piped Water Supply Scheme. (SM/14683) | SM/14683 | 2443.77 | 6637 | NEW | 20 | Delayed | 19 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 463.64 | 463.64
119 | BHUBANESWAR PIPED WATER SUPPLY SCHEME (SM/13387) | SM/13387 | 911.71 | 2288 | NEW | 20 | Delayed | 18 | 18/10/2022 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 167.16 | 167.16
120 | Majuria Piped Water Supply Scheme. (SM/13632) | SM/13632 | 998.5 | 2503 | NEW | 21 | Delayed | 19 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 191.87 | 191.87
121 | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. (SM/09341) | SM/09341 | 896.76 | 13825 | RETROFITTING | 22 | Delayed | 12 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 07/12/2021 | 107.49 | 98.34
122 | Paniara Piped Water Supply Scheme. (SM/12907) | SM/12907 | 124.83 | 497 | NEW | 24 | Delayed | 23 | 22/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 28.11 | 28.11
123 | Bhaddi Piped Water Supply Scheme (SM/14114) | SM/14114 | 422.65 | 897 | NEW | 24 | Delayed | 22 | 02/01/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 94.64 | 94.64
124 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08891) | SM/08891 | 176.25 | 2882 | RETROFITTING | 25 | Delayed | 15 | 29/09/2021 | 31/12/2025 | 16/05/2025 | 13/12/2021 | 26.35 | 26.35
125 | Lakshmi Narayanpur and Adjoining Mouzas PWSS (SM/12696) | SM/12696 | 846.97 | 1987 | NEW | 25 | Delayed | 20 | 21/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 166.99 | 166.99
126 | Nanubazar Piped Water Supply Scheme (SM/12673) | SM/12673 | 615.54 | 1536 | NEW | 25 | Delayed | 24 | 19/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 146.54 | 146.54
127 | ULANDI PIPED WATER SUPPLY SCHEME (SM/13654) | SM/13654 | 626.02 | 1568 | NEW | 25 | Delayed | 22 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 18/04/2022 | 135.23 | 135.23
128 | Baraban Piped Water Supply Scheme (Khoyrasole Block) (SM/14852) | SM/14852 | 585.66 | 1408 | NEW | 25 | Delayed | 21 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 124.38 | 124.38
129 | Loba Piped Water Supply Scheme. (SM/18511) | SM/18511 | 2382.48 | 5713 | NEW | 25 | Delayed | 31 | 26/07/2023 | 31/03/2026 | 16/05/2025 | 08/08/2023 | 746.03 | 567.2
130 | Hazaripur Piped Water Supply Scheme (SM/14679) | SM/14679 | 764.93 | 2390 | NEW | 25 | Delayed | 12 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 02/08/2023 | 93.73 | 93.73
131 | Kasba Piped Water Supply Scheme. (SM/13713) | SM/13713 | 779.81 | 2304 | NEW | 25 | Delayed | 7 | 14/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 52.28 | 51.48
132 | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. (SM/14424) | SM/14424 | 1516.41 | 3204 | NEW | 25 | Delayed | 19 | 20/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 292.23 | 292.23
133 | CHHATAR BANDI PIPED WATER SUPPLY SCHEME (SM/18354) | SM/18354 | 1021.7 | 2743 | NEW | 25 | Delayed | 16 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 159.23 | 159.23
134 | Madhupur Water Supply Scheme (SM/13644) | SM/13644 | 676.32 | 1359 | NEW | 25 | Delayed | 15 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 104.39 | 81.13
135 | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division (SM/13982) | SM/13982 | 698.94 | 1488 | NEW | 25 | Delayed | 11 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 73.83 | 73.83
136 | Parsundi Piped Water Supply Scheme (SM/14855) | SM/14855 | 506.23 | 1178 | NEW | 25 | Delayed | 22 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 111.88 | 111.88
137 | HANSAN PIPED WATER SUPPLY SCHEME (SM/14900) | SM/14900 | 900.67 | 1932 | NEW | 25 | Delayed | 9 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 80.16 | 57.7
138 | PUNNA PIPED WATER SUPPLY SCHEME (SM/14903) | SM/14903 | 996.36 | 3136 | NEW | 25 | Delayed | 13 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 30/03/2023 | 128.94 | 128.94
139 | DHANASAHA PIPED WATER SUPPLY SCHEME (SM/18352) | SM/18352 | 1202.1 | 3030 | NEW | 25 | Delayed | 22 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 265.69 | 265.69
140 | Patalpur Piped Water Supply Scheme (SM/14955) | SM/14955 | 209.38 | 219 | NEW | 25 | Delayed | 6 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 03/10/2023 | 11.94 | 4.68
141 | Bagahola Piped Water Supply Scheme (SM/14084) | SM/14084 | 389.21 | 514 | NEW | 25 | Delayed | 21 | 12/12/2022 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 81.9 | 81.9
142 | DALIMA PIPED WATER SUPPLY SCHEME. (SM/12592) | SM/12592 | 662.48 | 1957 | NEW | 25 | Delayed | 11 | 15/09/2022 | 31/08/2025 | 16/05/2025 | 25/04/2023 | 75.45 | 75.45
143 | Ruppur and adjoining mouzas Piped Water Supply Scheme. (SM/14686) | SM/14686 | 1387.78 | 3231 | NEW | 25 | Delayed | 23 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 316.35 | 316.35
144 | MAHESWARPUR PIPED WATER SUPPLY SCHEME (SM/15254) | SM/15254 | 471.69 | 1055 | NEW | 30 | Delayed | 26 | 06/02/2023 | 31/08/2025 | 16/05/2025 | 10/04/2023 | 124.96 | 124.96
145 | Bautia piped water supply scheme (SM/14536) | SM/14536 | 1467.55 | 3437 | NEW | 30 | Delayed | 29 | 30/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 421.42 | 421.42
146 | Barshal piped water supply scheme. (SM/14535) | SM/14535 | 1768.83 | 4730 | NEW | 30 | Delayed | 32 | 30/01/2023 | 31/12/2025 | 16/05/2025 | 10/08/2023 | 563.13 | 428.53
147 | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT (SM/18489) | SM/18489 | 814.18 | 2006 | NEW | 30 | Delayed | 11 | 24/07/2023 | 30/11/2025 | 16/05/2025 | 07/11/2023 | 93.5 | 93.5
148 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Danghara (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12665) | SM/12665 | 17.6 | 272 | RETROFITTING | 30 | WO no issued | 0 | 19/09/2022 | 30/06/2025 | 16/05/2025 |  | 0 | 0
149 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR TALA AND OTHER 25 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14039) | SM/14039 | 974.91 | 1554 | NEW | 30 | Delayed | 37 | 12/12/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 361.68 | 361.68
150 | Bhabani Water Supply Scheme (SM/18351) | SM/18351 | 1451.76 | 3650 | NEW | 30 | Delayed | 10 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 19/10/2023 | 147.36 | 147.36
151 | BANSANKHA PIPED WATER SUPPLY SCHEME. (SM/12889) | SM/12889 | 386.07 | 1357 | NEW | 30 | Delayed | 19 | 23/09/2022 | 31/03/2026 | 16/05/2025 | 12/04/2023 | 72.65 | 48.41
152 | Chormara Piped Water Supply Scheme. (SM/14030) | SM/14030 | 402.81 | 881 | NEW | 30 | Delayed | 8 | 05/12/2022 | 31/12/2025 | 16/05/2025 | 31/05/2023 | 32.12 | 32.12
153 | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. (SM/18787) | SM/18787 | 880.39 | 2363 | AUGMENTATION | 30 | Delayed | 20 | 29/08/2023 | 08/02/2025 | 16/05/2025 | 03/01/2024 | 177.6 | 159.31
154 | PAKURIA PIPED WATER SUPPLY SCHEME. (SM/12596) | SM/12596 | 578.57 | 1868 | NEW | 30 | Delayed | 40 | 15/09/2022 | 31/12/2025 | 16/05/2025 | 03/08/2023 | 233.72 | 170.69
155 | Chanchali piped water supply scheme. (SM/12683) | SM/12683 | 1034.33 | 2580 | NEW | 30 | Delayed | 42 | 21/09/2022 | 31/10/2025 | 16/05/2025 | 25/04/2023 | 433.17 | 433.17
156 | Paduma Piped Water Supply Scheme. (SM/14544) | SM/14544 | 1611.92 | 3934 | NEW | 30 | Delayed | 6 | 30/01/2023 | 30/09/2025 | 16/05/2025 | 25/04/2023 | 98 | 98
157 | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. (SM/09363) | SM/09363 | 188.82 | 2910 | RETROFITTING | 35 | Delayed | 32 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 02/05/2022 | 59.52 | 51.97
158 | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. (SM/14960) | SM/14960 | 715.34 | 3733 | AUGMENTATION | 35 | Delayed | 30 | 04/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 214.42 | 214.42
159 | Mostala Piped Water Supply Scheme. (SM/18519) | SM/18519 | 1209.99 | 3889 | NEW | 35 | Delayed | 31 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 369.72 | 369.72
160 | Nabagram Piped Water Supply Scheme. (SM/13646) | SM/13646 | 628.41 | 1353 | NEW | 35 | Delayed | 20 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 11/08/2023 | 125.07 | 74.62
161 | Sahapur Piped water Supply Scheme. (SM/13649) | SM/13649 | 988.96 | 1721 | NEW | 35 | Delayed | 28 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 23/03/2023 | 275.7 | 275.7
162 | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. (SM/14744) | SM/14744 | 907.13 | 4098 | AUGMENTATION | 35 | Delayed | 33 | 31/01/2023 | 08/02/2025 | 16/05/2025 | 24/07/2023 | 299.65 | 299.65
163 | Haripur Piped Water Supply Scheme (SM/14853) | SM/14853 | 934.11 | 2142 | NEW | 35 | Delayed | 34 | 03/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 319.16 | 319.16
164 | Dhalla Piped Water Supply Scheme (SM/15256) | SM/15256 | 960.39 | 2260 | NEW | 35 | Delayed | 10 | 07/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 96.96 | 96.96
165 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12074) | SM/12074 | 998 | 1328 | NEW | 35 | Delayed | 31 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 305.51 | 305.51
166 | Charicha Piped Water Supply Scheme. (SM/18512) | SM/18512 | 1514.48 | 2905 | NEW | 35 | Delayed | 32 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 486.68 | 486.68
167 | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division (SM/09559) | SM/09559 | 416.43 | 0 | ANGANWADI | 40 | Delayed | 0 | 17/11/2021 | 31/08/2025 | 16/05/2025 | 23/08/2021 | 0 | 0
168 | NOHNA PIPED WATER SUPPLY SCHEME (SM/13645) | SM/13645 | 813.39 | 1848 | NEW | 40 | Delayed | 37 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 10/08/2023 | 301.82 | 301.82
169 | BIRSINGHA PIPED WATER SUPPLY SCHEME. (SM/12830) | SM/12830 | 411.72 | 1269 | NEW | 40 | Delayed | 26 | 22/09/2022 | 31/03/2026 | 16/05/2025 | 29/11/2022 | 109.08 | 109.08
170 | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area (SM/06946) | SM/06946 | 97.74 | 1510 | RETROFITTING | 40 | Delayed | 39 | 03/11/2020 | 30/04/2026 | 16/05/2025 | 16/07/2021 | 38.5 | 38.5
171 | Nawapara Piped Water Supply Scheme (SM/13479) | SM/13479 | 720.04 | 2357 | NEW | 40 | Delayed | 28 | 02/11/2022 | 31/03/2026 | 16/05/2025 | 26/07/2023 | 205.17 | 205.17
172 | Albandha Piped Water Supply Scheme. (SM/14533) | SM/14533 | 1247.73 | 2929 | NEW | 40 | Delayed | 37 | 30/01/2023 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 456.18 | 456.18
173 | Kamarkhul Piped Water Supply Scheme. (SM/12693) | SM/12693 | 766.32 | 2268 | NEW | 40 | Delayed | 6 | 21/09/2022 | 30/10/2025 | 16/05/2025 | 10/08/2023 | 46.98 | 46.98
174 | MASTALI PIPED WATER SUPPLY SCHEME (SM/16275) | SM/16275 | 486.59 | 696 | NEW | 40 | Delayed | 27 | 23/02/2023 | 08/02/2025 | 16/05/2025 | 29/04/2022 | 132.1 | 132.1
175 | Kendangal Piped Water Supply Scheme. (SM/13642) | SM/13642 | 620.79 | 1921 | NEW | 40 | Delayed | 21 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 130.68 | 130.68
176 | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) (SM/16272) | SM/16272 | 249.14 | 538 | NEW | 40 | Delayed | 39 | 24/02/2023 | 08/02/2025 | 16/05/2025 | 17/10/2023 | 95.95 | 95.95
177 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR CHANDANPUR AND OTHER 5 NOS. MOUZAS UNDER MURARAI-I & NALHATI-I BLOCKS UNDER BIRBHUM DIVISION, PHE DTE. (SM/14043) | SM/14043 | 217 | 429 | NEW | 45 | Delayed | 46 | 12/12/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 100.42 | 87.59
178 | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07153) | SM/07153 | 99.72 | 1408 | RETROFITTING | 45 | Delayed | 77 | 01/12/2020 | 30/06/2025 | 16/05/2025 | 23/12/2020 | 76.43 | 76.43
179 | Kayera Water Supply Scheme (SM/13641) | SM/13641 | 488.23 | 1231 | NEW | 45 | Delayed | 22 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 15/03/2022 | 108.22 | 108.22
180 | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME (SM/18514) | SM/18514 | 1186.83 | 2600 | NEW | 45 | Delayed | 18 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 216.79 | 151.63
181 | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. (SM/12677) | SM/12677 | 661.51 | 10178 | RETROFITTING | 45 | Delayed | 37 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 02/05/2023 | 244.79 | 244.79
182 | Khamedda Piped Water Supply Scheme (SM/13980) | SM/13980 | 737.11 | 2017 | NEW | 45 | Delayed | 6 | 01/12/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 42.12 | 42.12
183 | MITRAPUR WATER SUPPLY SCHEME. (SM/12892) | SM/12892 | 1170.21 | 3936 | NEW | 45 | Delayed | 9 | 23/09/2022 | 30/09/2025 | 16/05/2025 | 10/08/2023 | 100.86 | 100.86
184 | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area (SM/06944) | SM/06944 | 97.37 | 1500 | RETROFITTING | 45 | Delayed | 97 | 03/11/2020 | 30/06/2025 | 16/05/2025 | 25/10/2021 | 94.53 | 41.82
185 | Shaspur Piped Water Supply Scheme. (SM/13651) | SM/13651 | 794.81 | 1371 | NEW | 45 | Delayed | 23 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 11/08/2023 | 183.55 | 183.55
186 | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION (SM/18513) | SM/18513 | 1122.66 | 2393 | NEW | 45 | Delayed | 15 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 166.86 | 166.86
187 | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. (SM/18366) | SM/18366 | 1040.7 | 1410 | AUGMENTATION | 45 | Delayed | 34 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 349.35 | 349.35
188 | DELORA PIPED WATER SUPPLY SCHEME (SM/13600) | SM/13600 | 388.22 | 1052 | NEW | 45 | Delayed | 16 | 09/11/2022 | 31/07/2025 | 16/05/2025 | 12/04/2023 | 60.52 | 60.52
189 | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division (SM/10320) | SM/10320 | 7907.91 | 31155 | AUGMENTATION | 50 | Delayed | 45 | 07/03/2022 | 31/12/2025 | 16/05/2025 | 17/03/2022 | 3554.96 | 3545.4
190 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UTTAR BHAGABATIPUR AND OTHER 8 NOS. MOUZAS UNDER MAYURESWAR-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12071) | SM/12071 | 343 | 571 | NEW | 50 | Delayed | 69 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 237.69 | 237.69
191 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR SIMJURI AND OTHER 19 NOS. MOUZAS UNDER KHOYRASOLE BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12072) | SM/12072 | 712 | 2051 | NEW | 50 | Delayed | 49 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 348.78 | 348.78
192 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kurumgram (Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12668) | SM/12668 | 11.63 | 179 | RETROFITTING | 50 | WO no issued | 0 | 19/09/2022 | 08/02/2025 | 16/05/2025 |  | 0 | 0
193 | Math Basori Piped Water Supply Scheme. (SM/13627) | SM/13627 | 564.3 | 1616 | NEW | 50 | Delayed | 15 | 11/11/2022 | 31/03/2026 | 16/05/2025 | 14/07/2023 | 83.77 | 83.77
194 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme (SM/12658) | SM/12658 | 13.68 | 211 | RETROFITTING | 50 | Delayed | 38 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 20/04/2023 | 5.16 | 0
195 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08895) | SM/08895 | 94.58 | 1500 | RETROFITTING | 50 | Delayed | 45 | 29/09/2021 | 30/06/2025 | 16/05/2025 | 13/12/2021 | 42.31 | 42.31
196 | Beloa Piped Water Supply Scheme (SM/18522) | SM/18522 | 1076.07 | 3051 | NEW | 50 | Delayed | 31 | 26/07/2023 | 30/11/2025 | 16/05/2025 | 02/08/2023 | 338.91 | 338.91
197 | Mahurapur and Adjoining Mouzas PWSS (SM/12697) | SM/12697 | 1066.63 | 3051 | NEW | 50 | Delayed | 13 | 21/09/2022 | 31/03/2026 | 16/05/2025 | 25/04/2023 | 139.97 | 139.97
198 | BILASPUR PIPED WATER SUPPLY SCHEME. (SM/12594) | SM/12594 | 862.54 | 2738 | NEW | 50 | Delayed | 19 | 15/09/2022 | 31/08/2025 | 16/05/2025 | 14/07/2023 | 163.63 | 109.4
199 | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/14141) | SM/14141 | 1206.94 | 2714 | NEW | 50 | Delayed | 24 | 02/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 283.77 | 283.77
200 | SARIHA PIPED WATER SUPPLY SCHEME (SM/12900) | SM/12900 | 807.12 | 2296 | NEW | 50 | Delayed | 21 | 22/09/2022 | 31/12/2025 | 16/05/2025 | 20/04/2023 | 169.06 | 169.06
201 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALPUR AND OTHER 5 NOS. MOUZAS UNDER NALHATI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14038) | SM/14038 | 225 | 425 | NEW | 50 | Delayed | 9 | 12/12/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 20.58 | 20.58
202 | Dakshin Chandipur Piped Water Supply Scheme. (SM/12685) | SM/12685 | 556.73 | 1416 | NEW | 55 | Delayed | 12 | 21/09/2022 | 31/12/2025 | 16/05/2025 | 20/04/2023 | 64.87 | 64.87
203 | PURBA SIUR PIPED WATER SUPPLY SCHEME. (SM/12598) | SM/12598 | 497.79 | 1464 | NEW | 55 | Delayed | 16 | 15/09/2022 | 30/09/2025 | 16/05/2025 | 12/07/2023 | 79.2 | 79.2
204 | SEHANA PIPED WATER SUPPLY SCHEME. (SM/12890) | SM/12890 | 526.76 | 1860 | NEW | 55 | Delayed | 21 | 23/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 108.01 | 108.01
205 | Abhirampur and Adjoining Mouzas PWSS (SM/12536) | SM/12536 | 377.57 | 973 | NEW | 55 | Delayed | 50 | 13/09/2022 | 31/10/2025 | 16/05/2025 | 25/04/2023 | 188.02 | 188.02
206 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR PARKANDI AND OTHER 7 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11935) | SM/11935 | 313 | 483 | NEW | 55 | Delayed | 60 | 24/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 186.46 | 186.46
207 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) (SM/06743) | SM/06743 | 97.37 | 1760 | RETROFITTING | 55 | Delayed | 53 | 18/09/2020 | 31/03/2026 | 16/05/2025 | 16/07/2021 | 52 | 52
208 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. (SM/13371) | SM/13371 | 33.38 | 392 | RETROFITTING | 55 | Delayed | 54 | 19/10/2022 | 31/12/2025 | 16/05/2025 | 24/11/2021 | 17.94 | 17.94
209 | MAJHKALITHA PIPED WATER SUPPLY SCHEME. (SM/12838) | SM/12838 | 999.45 | 3063 | NEW | 55 | Delayed | 23 | 22/09/2022 | 31/12/2025 | 16/05/2025 | 20/04/2023 | 229.03 | 229.03
210 | Atkulia Piped Water Supply Scheme (SM/18301) | SM/18301 | 1007.63 | 2807 | NEW | 55 | Delayed | 39 | 26/06/2023 | 31/12/2025 | 16/05/2025 | 25/07/2023 | 395.27 | 395.27
211 | MATIARA PIPED WATER SUPPLY SCHEME. (SM/12674) | SM/12674 | 386.92 | 1248 | NEW | 55 | Delayed | 9 | 19/09/2022 | 31/03/2026 | 16/05/2025 | 17/04/2023 | 36.07 | 36.07
212 | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division (SM/14088) | SM/14088 | 913.88 | 2095 | NEW | 55 | Delayed | 28 | 12/12/2022 | 31/12/2025 | 16/05/2025 | 10/08/2023 | 251.59 | 251.59
213 | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME (SM/13516) | SM/13516 | 288.36 | 239 | NEW | 58 | Delayed | 39 | 02/11/2022 | 31/08/2025 | 16/05/2025 | 15/03/2022 | 113.37 | 113.37
214 | Ahmadpur Piped Water Supply Scheme (SM/14889) | SM/14889 | 896.86 | 1737 | NEW | 59 | Delayed | 58 | 03/02/2023 | 30/06/2025 | 16/05/2025 | 31/05/2023 | 518.67 | 518.67
215 | KUSHIPUR PIPES WATER SUPPLY SCHEME. (SM/12599) | SM/12599 | 667.02 | 3966 | NEW | 60 | Delayed | 43 | 15/09/2022 | 31/12/2025 | 16/05/2025 | 31/03/2023 | 289.42 | 289.42
216 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme (SM/12664) | SM/12664 | 58.66 | 909 | RETROFITTING | 60 | Delayed | 97 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 14/12/2022 | 56.95 | 56.95
217 | Kanaipur piped water supply scheme. (SM/13640) | SM/13640 | 801.2 | 2508 | NEW | 60 | Delayed | 33 | 11/11/2022 | 31/08/2025 | 16/05/2025 | 26/07/2023 | 266.88 | 266.88
218 | Kulara Piped Water Supply Scheme. (SM/12695) | SM/12695 | 481.59 | 2968 | NEW | 60 | On track | 38 | 21/09/2022 | 31/03/2026 | 16/05/2025 | 06/04/2023 | 181.49 | 181.49
219 | Behira and Adjoining Mouzas PWSS (SM/12456) | SM/12456 | 313.84 | 841 | NEW | 60 | Delayed | 27 | 13/09/2022 | 31/03/2026 | 16/05/2025 | 25/04/2023 | 84.41 | 84.41
220 | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT (SM/14676) | SM/14676 | 435.64 | 665 | NEW | 60 | Delayed | 41 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 177.5 | 177.5
221 | SAMSA PIPED WATER SUPPLY SCHEME. (SM/12597) | SM/12597 | 552.71 | 1842 | NEW | 60 | Delayed | 14 | 15/09/2022 | 31/12/2025 | 16/05/2025 | 25/04/2023 | 77.27 | 77.27
222 | Palsa piped water supply scheme. (SM/12906) | SM/12906 | 549.14 | 1387 | NEW | 60 | Delayed | 23 | 22/09/2022 | 30/06/2025 | 16/05/2025 | 02/05/2023 | 123.86 | 123.86
223 | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13476) | SM/13476 | 754.73 | 1639 | NEW | 60 | Delayed | 22 | 02/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 164.07 | 164.07
224 | Bahadurpur Piped Water Supply Scheme. (SM/12681) | SM/12681 | 749.3 | 2221 | NEW | 60 | Delayed | 29 | 21/09/2022 | 30/06/2025 | 16/05/2025 | 21/03/2023 | 217.22 | 209.65
225 | BANGJITA PIPED WATER SUPPLY SCHEME. (SM/12829) | SM/12829 | 489.13 | 1717 | NEW | 60 | Delayed | 12 | 22/09/2022 | 30/09/2025 | 16/05/2025 | 17/04/2023 | 59.38 | 59.38
226 | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07154) | SM/07154 | 99.92 | 1510 | RETROFITTING | 60 | Delayed | 84 | 01/12/2020 | 31/03/2026 | 16/05/2025 | 16/08/2021 | 83.72 | 83.72
227 | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. (SM/09369) | SM/09369 | 77.81 | 1199 | RETROFITTING | 60 | Delayed | 32 | 12/11/2021 | 30/09/2025 | 16/05/2025 | 07/12/2021 | 25.18 | 25.18
228 | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. (SM/09362) | SM/09362 | 259.6 | 4002 | RETROFITTING | 60 | Delayed | 58 | 12/11/2021 | 31/10/2025 | 16/05/2025 | 10/03/2022 | 150.93 | 148.62
229 | Gaganpur piped water supply scheme. (SM/12691) | SM/12691 | 913.35 | 2859 | NEW | 60 | Delayed | 27 | 20/09/2022 | 30/11/2025 | 16/05/2025 | 25/08/2023 | 243.86 | 243.86
230 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12666) | SM/12666 | 99.4 | 1404 | RETROFITTING | 60 | Delayed | 19 | 19/09/2022 | 31/08/2025 | 16/05/2025 | 01/04/2022 | 18.79 | 18.79
231 | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. (SM/13626) | SM/13626 | 478.35 | 1756 | NEW | 60 | Delayed | 34 | 11/11/2022 | 31/03/2026 | 16/05/2025 | 25/04/2023 | 162.72 | 162.72
232 | Ikshudhara piped water supply scheme. (SM/13639) | SM/13639 | 997.9 | 2543 | NEW | 60 | Delayed | 63 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 627.83 | 627.83
233 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. (SM/08896) | SM/08896 | 206.23 | 3305 | RETROFITTING | 60 | Delayed | 51 | 29/09/2021 | 31/07/2025 | 16/05/2025 | 03/11/2021 | 105.58 | 105.58
234 | NARAYANPUR PIPED WATER SUPPLY SCHEME. (SM/13625) | SM/13625 | 525.66 | 1545 | NEW | 60 | Delayed | 18 | 11/11/2022 | 30/06/2025 | 16/05/2025 | 10/08/2023 | 94.03 | 94.03
235 | Amlachaturi Piped Water Supply Scheme (SM/16387) | SM/16387 | 904.87 | 1427 | NEW | 60 | Delayed | 29 | 28/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 262.8 | 243.53
236 | Kachujore Piped Water Supply Scheme. (SM/13016) | SM/13016 | 173.49 | 354 | NEW | 60 | Delayed | 60 | 28/09/2022 | 30/06/2025 | 16/05/2025 | 06/04/2023 | 104.18 | 104.18
237 | Rajpur Piped Water Supply Scheme (SM/14026) | SM/14026 | 732.55 | 1269 | NEW | 60 | Delayed | 21 | 05/12/2022 | 31/12/2025 | 16/05/2025 | 20/04/2023 | 154.34 | 154.34
238 | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division (SM/14160) | SM/14160 | 1185.64 | 2646 | NEW | 60 | Delayed | 17 | 05/01/2023 | 30/06/2025 | 16/05/2025 | 08/06/2023 | 199.43 | 199.43
239 | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. (SM/12591) | SM/12591 | 544.87 | 1573 | NEW | 60 | Delayed | 37 | 15/09/2022 | 31/05/2025 | 16/05/2025 | 12/04/2023 | 202.6 | 202.6
240 | Dumugram piped water supply scheme. (SM/12689) | SM/12689 | 894.92 | 2559 | NEW | 60 | Delayed | 29 | 21/09/2022 | 31/12/2025 | 16/05/2025 | 25/04/2023 | 258.92 | 258.92
241 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR NISHPARUN AND OTHER 4 NOS. MOUZAS UNDER RAMPURHAT-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11901) | SM/11901 | 206 | 1631 | NEW | 60 | Delayed | 51 | 22/08/2022 | 30/06/2025 | 16/05/2025 | 28/11/2022 | 104.19 | 104.19
242 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme (SM/12663) | SM/12663 | 108.02 | 1465 | RETROFITTING | 60 | Delayed | 48 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 06/01/2022 | 51.38 | 51.38
243 | KOGRAM PIPED WATER SUPPLY SCHEME. (SM/12894) | SM/12894 | 721.43 | 2150 | NEW | 60 | Delayed | 47 | 23/09/2022 | 30/09/2025 | 16/05/2025 | 31/03/2023 | 340.01 | 340.01
244 | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09367) | SM/09367 | 453.12 | 6979 | RETROFITTING | 60 | Delayed | 59 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 24/06/2020 | 266.71 | 266.71
245 | KASHERHAT PIPED WATER SUPPLY SCHEME. (SM/12903) | SM/12903 | 578.88 | 2235 | NEW | 60 | Delayed | 44 | 22/09/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 254.74 | 209.43
246 | Nohana and Adjoining Mouzas PWSS (SM/12905) | SM/12905 | 301.26 | 751 | NEW | 62 | Delayed | 41 | 22/09/2022 | 30/06/2025 | 16/05/2025 | 02/05/2023 | 122.29 | 122.29
247 | Augmentation of Margram piped water supply scheme. (SM/18372) | SM/18372 | 1979.65 | 7205 | AUGMENTATION | 65 | Delayed | 7 | 11/07/2023 | 08/02/2025 | 16/05/2025 | 28/07/2023 | 135.15 | 88.4
248 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR MAJURIA AND OTHER 19 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12073) | SM/12073 | 775 | 1417 | NEW | 65 | Delayed | 36 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 281.43 | 281.43
249 | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte (SM/18425) | SM/18425 | 4901.98 | 16046 | NEW | 65 | Delayed | 57 | 18/07/2023 | 08/02/2025 | 16/05/2025 | 03/10/2023 | 2793.56 | 2793.56
250 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) (SM/06742) | SM/06742 | 98.25 | 1830 | RETROFITTING | 65 | Delayed | 58 | 18/09/2020 | 31/03/2026 | 16/05/2025 | 10/12/2021 | 57 | 57
251 | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. (SM/12595) | SM/12595 | 886.16 | 3542 | NEW | 65 | Delayed | 25 | 15/09/2022 | 30/09/2025 | 16/05/2025 | 25/08/2023 | 218.56 | 189.37
252 | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. (SM/13376) | SM/13376 | 794.01 | 1613 | NEW | 65 | Delayed | 25 | 18/10/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 195.06 | 195.06
253 | BHEJENA PIPED WATER SUPPLY SCHEME. (SM/12833) | SM/12833 | 244.52 | 528 | NEW | 65 | Delayed | 53 | 22/09/2022 | 31/07/2025 | 16/05/2025 | 05/06/2023 | 130.2 | 130.2
254 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. (SM/08898) | SM/08898 | 147.83 | 2377 | RETROFITTING | 65 | Delayed | 58 | 29/09/2021 | 31/08/2025 | 16/05/2025 | 29/10/2021 | 85.77 | 85.77
255 | Jashoda Piped Water Supply Scheme. (SM/12891) | SM/12891 | 363.96 | 1345 | NEW | 65 | Delayed | 44 | 23/09/2022 | 30/06/2025 | 16/05/2025 | 12/04/2023 | 159.2 | 159.2
256 | Siur Piped Water Supply Scheme. (SM/14537) | SM/14537 | 1169.86 | 2832 | NEW | 65 | Delayed | 43 | 30/01/2023 | 31/12/2025 | 16/05/2025 | 23/03/2023 | 501.55 | 473.84
257 | KAMARDANGAL PIPED WATER SUPPLY SCHEME. (SM/12675) | SM/12675 | 238.09 | 652 | NEW | 65 | On track | 55 | 19/09/2022 | 31/05/2026 | 16/05/2025 | 21/03/2023 | 131.25 | 116.91
258 | Chakpara piped water supply scheme. (SM/13638) | SM/13638 | 640.93 | 1721 | NEW | 65 | Delayed | 21 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 134.35 | 134.35
259 | Gulalgachi Piped Supply Scheme (SM/18419) | SM/18419 | 1267.58 | 3333 | NEW | 65 | Delayed | 56 | 18/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 715.54 | 688.24
260 | Augmentation of Panchiara Piped Water Supply Scheme (SM/10314) | SM/10314 | 921.39 | 4179 | AUGMENTATION | 68 | Delayed | 66 | 04/03/2022 | 31/12/2025 | 16/05/2025 | 24/06/2020 | 611.82 | 611.82
261 | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09364) | SM/09364 | 234.01 | 3622 | RETROFITTING | 70 | Delayed | 63 | 12/11/2021 | 31/08/2025 | 16/05/2025 | 17/01/2022 | 148.19 | 148.19
262 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block (SM/07645) | SM/07645 | 93.68 | 1478 | RETROFITTING | 70 | Delayed | 69 | 07/01/2021 | 31/08/2025 | 16/05/2025 | 11/01/2021 | 65.01 | 65.01
263 | RAUTARA PIPED WATER SUPPLY SCHEME. (SM/12888) | SM/12888 | 247.15 | 835 | NEW | 70 | Delayed | 53 | 23/09/2022 | 30/06/2025 | 16/05/2025 | 22/03/2023 | 131.93 | 130.82
264 | PHULUR PIPED WATER SUPPLY SCHEME. (SM/12901) | SM/12901 | 653.75 | 2406 | NEW | 70 | On track | 18 | 22/09/2022 | 31/12/2025 | 16/05/2025 | 12/07/2023 | 118.29 | 118.29
265 | Shitalgram Piped Water Supply Scheme (SM/14087) | SM/14087 | 585.33 | 1460 | NEW | 70 | On track | 42 | 12/12/2022 | 31/10/2025 | 16/05/2025 | 25/07/2023 | 247.49 | 247.49
266 | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. (SM/12659) | SM/12659 | 149.48 | 2304 | RETROFITTING | 70 | Delayed | 29 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 03/08/2023 | 44 | 43.2
267 | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. (SM/15236) | SM/15236 | 738.45 | 705 | AUGMENTATION | 70 | Delayed | 39 | 07/02/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 285.65 | 285.65
268 | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area (SM/06948) | SM/06948 | 99.22 | 1520 | RETROFITTING | 70 | Delayed | 99 | 03/11/2020 | 31/03/2026 | 16/05/2025 | 23/12/2020 | 97.91 | 97.91
269 | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. (SM/09491) | SM/09491 | 149.02 | 2295 | RETROFITTING | 70 | Delayed | 72 | 19/11/2021 | 31/08/2025 | 16/05/2025 | 17/12/2021 | 107.1 | 107.1
270 | Kankalitala piped water supply scheme. (SM/18518) | SM/18518 | 1174.7 | 2793 | NEW | 70 | Delayed | 40 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 465.54 | 465.54
271 | Dadpur Piped Water Supply Scheme. (SM/12684) | SM/12684 | 593.51 | 1487 | NEW | 70 | On track | 45 | 21/09/2022 | 31/03/2026 | 16/05/2025 | 16/03/2023 | 269.44 | 246.02
272 | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division (SM/10321) | SM/10321 | 6683.63 | 28764 | AUGMENTATION | 70 | Delayed | 65 | 07/03/2022 | 31/12/2025 | 16/05/2025 | 03/11/2021 | 4313.13 | 4293.13
273 | CHAUTI PIPED WATER SUPPLY SCHEME. (SM/12835) | SM/12835 | 574.46 | 1647 | NEW | 70 | Delayed | 39 | 22/09/2022 | 30/06/2025 | 16/05/2025 | 01/03/2023 | 224.35 | 224.35
274 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR DHEKA AND OTHER 21 NOS. MOUZAS UNDER MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11910) | SM/11910 | 840 | 1573 | NEW | 70 | On track | 56 | 22/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 472.26 | 333.91
275 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14015) | SM/14015 | 570 | 5004 | NEW | 70 | On track | 69 | 05/12/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 392.72 | 392.72
276 | Deoash and Adjoining Mouzas PWSS (SM/12670) | SM/12670 | 643 | 2323 | NEW | 70 | On track | 72 | 19/09/2022 | 31/03/2026 | 16/05/2025 | 12/04/2023 | 465.62 | 465.62
277 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. (SM/08893) | SM/08893 | 293.51 | 6050 | RETROFITTING | 70 | Delayed | 97 | 29/09/2021 | 31/05/2025 | 16/05/2025 | 29/10/2021 | 284.96 | 284.96
278 | PARULIA PIPED WATER SUPPLY SCHEME. (SM/14538) | SM/14538 | 1104.48 | 2335 | NEW | 70 | Delayed | 49 | 30/01/2023 | 30/06/2025 | 16/05/2025 | 25/04/2023 | 537.55 | 480.91
279 | Augmentation of Ahmedpur Piped Water Supply Scheme (SM/10313) | SM/10313 | 766.3 | 4884 | AUGMENTATION | 70 | Delayed | 62 | 04/03/2022 | 30/09/2025 | 16/05/2025 | 23/05/2022 | 472.95 | 472.95
280 | Abdullahpur Piped Water Supply Scheme. (SM/12679) | SM/12679 | 799.1 | 2283 | NEW | 70 | Delayed | 23 | 21/09/2022 | 30/06/2025 | 16/05/2025 | 20/04/2023 | 182.96 | 182.96
281 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. (SM/12657) | SM/12657 | 23.91 | 376 | RETROFITTING | 70 | Delayed | 70 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 08/09/2022 | 16.74 | 16.74
282 | Naoadangal and Adjoining Mouzas PWSS (SM/12904) | SM/12904 | 722.04 | 1314 | NEW | 70 | Delayed | 61 | 22/09/2022 | 30/09/2025 | 16/05/2025 | 23/03/2023 | 442.57 | 424.23
283 | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division (SM/18521) | SM/18521 | 1043.88 | 2325 | NEW | 70 | Delayed | 34 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 356.61 | 356.61
284 | Augmentation of Mathpalsa Piped Water Supply Scheme (SM/10315) | SM/10315 | 283.04 | 1605 | AUGMENTATION | 72 | Delayed | 70 | 04/03/2022 | 31/12/2025 | 16/05/2025 | 23/05/2022 | 197.62 | 197.62
285 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GANUTIA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11903) | SM/11903 | 849 | 2805 | NEW | 75 | On track | 67 | 22/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 571.45 | 477.44
286 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS (SM/06744) | SM/06744 | 99.59 | 957 | RETROFITTING | 75 | Delayed | 95 | 18/09/2020 | 31/12/2025 | 16/05/2025 | 08/02/2021 | 94.81 | 73.61
287 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) (SM/10543) | SM/10543 | 68.88 | 1063 | RETROFITTING | 75 | On track | 74 | 13/04/2022 | 31/12/2025 | 16/05/2025 | 01/10/2021 | 50.97 | 50.97
288 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMDAHARA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11902) | SM/11902 | 754 | 4440 | NEW | 75 | On track | 68 | 22/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 514.07 | 514.07
289 | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division (SM/13630) | SM/13630 | 903.87 | 2008 | NEW | 75 | Delayed | 48 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 437.37 | 386.36
290 | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District (SM/14016) | SM/14016 | 191.26 | 656 | NEW | 75 | On track | 56 | 05/12/2022 | 31/12/2025 | 16/05/2025 | 06/12/2022 | 106.99 | 106.99
291 | Chinpai Piped Water Supply Scheme. (SM/18462) | SM/18462 | 1443.97 | 3866 | NEW | 75 | On track | 36 | 20/07/2023 | 30/09/2025 | 16/05/2025 | 08/08/2023 | 515.78 | 486.9
292 | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13653) | SM/13653 | 537.6 | 1126 | NEW | 75 | Delayed | 20 | 11/11/2022 | 08/02/2025 | 16/05/2025 | 07/11/2023 | 109.58 | 109.58
293 | JIUI PIPED WATER SUPPLY SCHEME. (SM/12902) | SM/12902 | 599.1 | 2853 | NEW | 75 | Delayed | 33 | 22/09/2022 | 30/06/2025 | 16/05/2025 | 12/04/2023 | 195.82 | 195.82
294 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum (SM/08172) | SM/08172 | 95.12 | 1520 | RETROFITTING | 75 | On track | 95 | 08/02/2021 | 31/03/2026 | 16/05/2025 | 26/02/2021 | 89.98 | 89.98
295 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12070) | SM/12070 | 901 | 2738 | NEW | 75 | On track | 69 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 623.54 | 623.54
296 | JOGAI PIPED WATER SUPPLY SCHEME. (SM/12593) | SM/12593 | 514.78 | 1521 | NEW | 75 | On track | 39 | 15/09/2022 | 31/03/2026 | 16/05/2025 | 19/04/2023 | 202.26 | 202.26
297 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. (SM/12661) | SM/12661 | 43.64 | 700 | RETROFITTING | 75 | Delayed | 83 | 19/09/2022 | 09/01/2025 | 16/05/2025 | 08/06/2023 | 36.03 | 31.68
298 | Sadanandapur piped water supply scheme. (SM/13648) | SM/13648 | 448.06 | 1233 | NEW | 75 | On track | 48 | 11/11/2022 | 31/12/2025 | 16/05/2025 | 06/06/2023 | 215.17 | 215.17
299 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. (SM/09792) | SM/09792 | 771.82 | 12114 | RETROFITTING | 75 | Delayed | 52 | 30/11/2021 | 31/03/2025 | 16/05/2025 | 24/06/2020 | 398.74 | 398.74
300 | PURBA BANKATI PIPED WATER SUPPLY SCHEME. (SM/13470) | SM/13470 | 178.79 | 358 | NEW | 75 | On track | 67 | 02/11/2022 | 31/12/2025 | 16/05/2025 | 01/03/2023 | 120.09 | 120.09
301 | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09365) | SM/09365 | 120.18 | 1851 | RETROFITTING | 78 | On track | 77 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 04/01/2022 | 92.33 | 92.33
302 | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. (SM/09490) | SM/09490 | 299.8 | 4634 | RETROFITTING | 78 | Delayed | 0 | 19/11/2021 | 30/09/2025 | 16/05/2025 | 12/08/2020 | 0 | 0
303 | Shankarpur Piped Water Scheme (SM/14082) | SM/14082 | 717.8 | 1071 | NEW | 79 | On track | 37 | 12/12/2022 | 31/12/2025 | 16/05/2025 | 06/04/2023 | 267.48 | 227.71
304 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block (SM/07649) | SM/07649 | 99.46 | 1745 | RETROFITTING | 80 | Delayed | 97 | 07/01/2021 | 30/06/2025 | 16/05/2025 | 06/01/2022 | 96.57 | 96.57
305 | Paschim Naopara and Adjoining Mouzas PWSS (SM/12458) | SM/12458 | 466.85 | 1347 | NEW | 80 | On track | 76 | 13/09/2022 | 31/12/2025 | 16/05/2025 | 12/07/2023 | 353.98 | 353.98
306 | Madhura and Adjoining mouzas PWSS (SM/12671) | SM/12671 | 780.79 | 1985 | NEW | 80 | Delayed | 53 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 12/04/2023 | 410.46 | 410.46
307 | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division (SM/13480) | SM/13480 | 534.51 | 1118 | NEW | 80 | Delayed | 30 | 02/11/2022 | 30/06/2025 | 16/05/2025 | 06/04/2023 | 161.13 | 161.13
308 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum (SM/07532) | SM/07532 | 179.67 | 2702 | RETROFITTING | 80 | Delayed | 88 | 31/12/2020 | 30/06/2025 | 16/05/2025 | 09/02/2022 | 157.86 | 157.86
309 | BHALIAN PIPED WATER SUPPLY SCHME. (SM/12834) | SM/12834 | 573.21 | 2093 | NEW | 80 | On track | 30 | 22/09/2022 | 31/12/2025 | 16/05/2025 | 17/04/2023 | 169.31 | 167.51
310 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum (SM/08171) | SM/08171 | 97.14 | 1525 | RETROFITTING | 80 | Delayed | 85 | 08/02/2021 | 30/06/2025 | 16/05/2025 | 04/01/2022 | 82.11 | 82.11
311 | Augmentation of Nagari Piped Water Supply Scheme (SM/10312) | SM/10312 | 272.8 | 969 | AUGMENTATION | 80 | On track | 63 | 04/03/2022 | 31/10/2025 | 16/05/2025 | 11/01/2023 | 172.28 | 172.28
312 | Monai Piped Water Supply Scheme. (SM/12701) | SM/12701 | 437.26 | 1785 | NEW | 80 | On track | 35 | 20/09/2022 | 30/09/2025 | 16/05/2025 | 25/04/2023 | 153.42 | 153.42
313 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12069) | SM/12069 | 291 | 570 | NEW | 80 | Delayed | 50 | 02/09/2022 | 30/06/2025 | 16/05/2025 | 28/11/2022 | 146.21 | 88.08
314 | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/16373) | SM/16373 | 751.53 | 1577 | NEW | 80 | Delayed | 48 | 28/02/2023 | 30/06/2025 | 16/05/2025 | 22/03/2023 | 358.26 | 336.22
315 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. (SM/08894) | SM/08894 | 148.29 | 2299 | RETROFITTING | 80 | Delayed | 75 | 29/09/2021 | 30/09/2025 | 16/05/2025 | 14/12/2021 | 111.16 | 111.16
316 | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09370) | SM/09370 | 145.06 | 2238 | RETROFITTING | 80 | Delayed | 68 | 12/11/2021 | 31/08/2025 | 16/05/2025 | 09/03/2022 | 98.55 | 98.55
317 | KANIOR PIPED WATER SUPPLY SCHEME. (SM/12831) | SM/12831 | 600.79 | 1819 | NEW | 80 | On track | 52 | 22/09/2022 | 31/03/2026 | 16/05/2025 | 31/03/2023 | 314.61 | 314.61
318 | Modapa Piped Water Supply Scheme. (SM/13517) | SM/13517 | 346.07 | 922 | NEW | 80 | Delayed | 63 | 02/11/2022 | 30/06/2025 | 16/05/2025 | 19/04/2023 | 217.22 | 217.22
319 | Haridaspur Piped Water Supply Scheme. (SM/14028) | SM/14028 | 977.13 | 4143 | NEW | 80 | Delayed | 25 | 05/12/2022 | 08/02/2025 | 16/05/2025 | 17/07/2023 | 240.3 | 240.3
320 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14037) | SM/14037 | 831.2 | 1514 | NEW | 80 | Delayed | 31 | 12/12/2022 | 31/05/2025 | 16/05/2025 | 28/11/2022 | 259.74 | 259.74
321 | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. (SM/09438) | SM/09438 | 762.27 | 3546 | AUGMENTATION | 80 | On track | 73 | 29/10/2021 | 31/03/2026 | 16/05/2025 | 24/06/2020 | 553.23 | 553.23
322 | Kurumsaha Piped Water Supply Scheme. (SM/13628) | SM/13628 | 301.71 | 896 | NEW | 80 | Delayed | 63 | 11/11/2022 | 30/06/2025 | 16/05/2025 | 17/04/2023 | 190.32 | 190.32
323 | Gaytha Piped Water Supply Scheme (SM/13712) | SM/13712 | 533.16 | 1164 | NEW | 80 | On track | 32 | 14/11/2022 | 31/12/2025 | 16/05/2025 | 19/04/2023 | 171.35 | 171.35
324 | Khanpur piped water supply scheme. (SM/13539) | SM/13539 | 875.43 | 2543 | NEW | 80 | Delayed | 40 | 04/11/2022 | 31/05/2025 | 16/05/2025 | 25/04/2023 | 351.49 | 351.49
325 | DERPUR PIPED WATER SUPPLY SCHEME. (SM/12832) | SM/12832 | 477.52 | 2033 | NEW | 80 | On track | 74 | 22/09/2022 | 30/09/2025 | 16/05/2025 | 29/11/2022 | 355.22 | 346.24
326 | Kamdebnala piped water supply scheme. (SM/12694) | SM/12694 | 476.19 | 1188 | NEW | 80 | On track | 35 | 21/09/2022 | 31/08/2025 | 16/05/2025 | 19/04/2023 | 165.04 | 165.04
327 | Asenga Piped Water Supply Scheme. (SM/12680) | SM/12680 | 617.4 | 2144 | NEW | 80 | On track | 63 | 20/09/2022 | 31/08/2025 | 16/05/2025 | 20/04/2023 | 389.17 | 389.17
328 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. (SM/12667) | SM/12667 | 24.91 | 382 | RETROFITTING | 80 | On track | 78 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 17/11/2022 | 19.43 | 19.43
329 | KANAIPUR and Adjoining Mouzas PWSS (SM/12672) | SM/12672 | 844.4 | 2817 | NEW | 80 | On track | 48 | 19/09/2022 | 31/08/2025 | 16/05/2025 | 20/04/2023 | 401.95 | 401.95
330 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR NAYIT AND OTHER 3 NOS. MOUZAS UNDER MURARAI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11907) | SM/11907 | 151 | 706 | NEW | 85 | On track | 82 | 22/08/2022 | 31/03/2026 | 16/05/2025 | 28/11/2022 | 123.22 | 123.22
331 | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division (SM/14119) | SM/14119 | 399.02 | 869 | NEW | 85 | Delayed | 36 | 02/01/2023 | 08/01/2025 | 16/05/2025 | 31/05/2023 | 143.76 | 143.76
332 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR SABASIDANGA AND OTHER 4 NOS. MOUZAS UNDER NALHATI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11904) | SM/11904 | 189 | 221 | NEW | 85 | On track | 67 | 22/08/2022 | 31/03/2026 | 16/05/2025 | 28/11/2022 | 126.66 | 114.34
333 | NETURI PIPED WATER SUPPLY SCHEME. (SM/12656) | SM/12656 | 496.1 | 2138 | NEW | 85 | On track | 77 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 04/11/2022 | 381.96 | 381.96
334 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. (SM/12660) | SM/12660 | 21.01 | 319 | RETROFITTING | 85 | On track | 82 | 19/09/2022 | 31/03/2026 | 16/05/2025 | 19/04/2023 | 17.31 | 17.31
335 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) (SM/06740) | SM/06740 | 99.84 | 1875 | RETROFITTING | 85 | Delayed | 96 | 18/09/2020 | 30/06/2025 | 16/05/2025 | 21/09/2020 | 95.63 | 95.63
336 | Melanpur Piped Water Supply Scheme. (SM/12699) | SM/12699 | 522.74 | 1312 | NEW | 85 | On track | 46 | 21/09/2022 | 30/06/2025 | 16/05/2025 | 20/04/2023 | 239.37 | 203.18
337 | Moubelia Piped Water Supply Scheme. (SM/14899) | SM/14899 | 409.66 | 742 | NEW | 85 | On track | 71 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 12/04/2023 | 289.96 | 281.22
338 | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area (SM/06951) | SM/06951 | 72.24 | 1135 | RETROFITTING | 85 | Delayed | 74 | 03/11/2020 | 30/06/2025 | 16/05/2025 | 18/08/2021 | 53.11 | 53.11
339 | Augmentation of Tejhati PWSS (SM/10166) | SM/10166 | 367.8 | 1953 | AUGMENTATION | 85 | Delayed | 69 | 11/02/2022 | 31/05/2025 | 16/05/2025 | 10/08/2021 | 255.52 | 255.52
340 | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division (SM/10319) | SM/10319 | 11639.45 | 56246 | AUGMENTATION | 85 | Delayed | 91 | 07/03/2022 | 30/06/2025 | 16/05/2025 | 22/07/2021 | 10609.72 | 10592.54
341 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR KATUNIA AND OTHER 2 NOS. MOUZAS UNDER MD. BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11909) | SM/11909 | 102 | 112 | NEW | 85 | Delayed | 79 | 22/08/2022 | 31/05/2025 | 16/05/2025 | 28/11/2022 | 80.27 | 80.27
342 | Simgram Piped Water Supply Scheme. (SM/12908) | SM/12908 | 125.88 | 399 | NEW | 85 | On track | 60 | 22/09/2022 | 31/03/2026 | 16/05/2025 | 12/05/2023 | 75.9 | 65.82
343 | Dhamara Piped Water Supply Scheme. (SM/14898) | SM/14898 | 471.2 | 1473 | NEW | 85 | On track | 46 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 17/04/2023 | 215.32 | 215.32
344 | Augmentation of Purandarpur Piped Water Supply Scheme (SM/09437) | SM/09437 | 679.4 | 3060 | AUGMENTATION | 88 | On track | 87 | 12/11/2021 | 30/09/2025 | 16/05/2025 | 24/06/2020 | 593.3 | 593.3
345 | Augmentation of Khoyrasole Piped Water Supply Scheme (SM/10343) | SM/10343 | 1265.98 | 783 | AUGMENTATION | 88 | On track | 73 | 14/03/2022 | 30/06/2025 | 16/05/2025 | 03/03/2022 | 930.36 | 926.83
346 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum (SM/07530) | SM/07530 | 296.93 | 5328 | RETROFITTING | 89 | On track | 96 | 31/12/2020 | 31/03/2026 | 16/05/2025 | 25/01/2022 | 285.55 | 285.55
347 | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division (SM/13634) | SM/13634 | 336.69 | 1500 | NEW | 90 | On track | 66 | 11/11/2022 | 31/07/2025 | 16/05/2025 | 01/03/2023 | 223.43 | 223.43
348 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11936) | SM/11936 | 394 | 903 | NEW | 90 | On track | 85 | 24/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 335.06 | 316.98
349 | Podda Piped Water Supply Scheme (SM/13714) | SM/13714 | 424.09 | 889 | NEW | 90 | Delayed | 34 | 14/11/2022 | 12/01/2025 | 16/05/2025 | 19/04/2023 | 143.44 | 143.44
350 | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT (SM/14894) | SM/14894 | 326.46 | 401 | NEW | 90 | On track | 59 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 22/03/2023 | 192.73 | 192.73
351 | Dhitora Right side and adjoining mouzas piped water supply scheme. (SM/17633) | SM/17633 | 445.95 | 1276 | NEW | 90 | On track | 43 | 22/03/2023 | 31/12/2025 | 16/05/2025 | 10/04/2023 | 193.25 | 193.25
352 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08897) | SM/08897 | 109.18 | 1682 | RETROFITTING | 90 | On track | 83 | 29/09/2021 | 30/06/2025 | 16/05/2025 | 07/10/2021 | 91.01 | 91.01
353 | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09366) | SM/09366 | 181.79 | 2805 | RETROFITTING | 90 | On track | 76 | 12/11/2021 | 30/06/2025 | 16/05/2025 | 22/03/2022 | 137.64 | 137.64
354 | ANDHARGRAM PIPED WATER SUPPLY SCHEME. (SM/12676) | SM/12676 | 300.02 | 2082 | NEW | 90 | On track | 83 | 19/09/2022 | 30/06/2025 | 16/05/2025 | 12/04/2023 | 249.99 | 249.99
355 | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13475) | SM/13475 | 445.39 | 902 | NEW | 90 | On track | 50 | 02/11/2022 | 01/03/2026 | 16/05/2025 | 06/04/2023 | 223.71 | 223.71
356 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme (SM/13372) | SM/13372 | 20.61 | 320 | RETROFITTING | 90 | On track | 97 | 19/10/2022 | 31/03/2026 | 16/05/2025 | 21/03/2023 | 20.01 | 20.01
357 | PAIKPARA WATER SUPPLY SCHEME. (SM/12836) | SM/12836 | 924.31 | 2727 | NEW | 90 | On track | 46 | 22/09/2022 | 31/08/2025 | 16/05/2025 | 12/04/2023 | 424.31 | 362.29
358 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block (SM/07650) | SM/07650 | 53.59 | 848 | RETROFITTING | 90 | On track | 95 | 07/01/2021 | 30/09/2025 | 16/05/2025 | 02/09/2021 | 50.84 | 50.84
359 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS (SM/06734) | SM/06734 | 94.74 | 1645 | RETROFITTING | 90 | On track | 72 | 18/09/2020 | 31/12/2025 | 16/05/2025 | 04/11/2020 | 68.47 | 68.47
360 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) (SM/07006) | SM/07006 | 99.48 | 1393 | RETROFITTING | 90 | On track | 95 | 13/11/2020 | 31/03/2026 | 16/05/2025 | 16/11/2021 | 94.77 | 94.77
361 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11905) | SM/11905 | 458 | 2966 | NEW | 90 | On track | 95 | 22/08/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 433.29 | 335.84
362 | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area (SM/06950) | SM/06950 | 99.83 | 1658 | RETROFITTING | 90 | On track | 97 | 03/11/2020 | 31/05/2025 | 16/05/2025 | 24/11/2021 | 96.92 | 96.92
363 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS (SM/06736) | SM/06736 | 99.68 | 1265 | RETROFITTING | 90 | On track | 85 | 18/09/2020 | 31/03/2026 | 16/05/2025 | 15/06/2021 | 85.19 | 85.19
364 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte (SM/07533) | SM/07533 | 206.39 | 2864 | RETROFITTING | 90 | On track | 89 | 31/12/2020 | 30/06/2025 | 16/05/2025 | 05/02/2021 | 183.35 | 183.35
365 | PARKUTA PIPED WATER SUPPLY SCHEME (SM/14959) | SM/14959 | 271.5 | 8299 | NEW | 90 | On track | 54 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 20/04/2023 | 146.82 | 146.82
366 | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07155) | SM/07155 | 94.45 | 1290 | RETROFITTING | 90 | On track | 97 | 01/12/2020 | 31/05/2025 | 16/05/2025 | 26/02/2020 | 91.7 | 91.7
367 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum (SM/07531) | SM/07531 | 190.61 | 3721 | RETROFITTING | 90 | On track | 97 | 31/12/2020 | 30/06/2025 | 16/05/2025 | 11/06/2021 | 185.06 | 185.06
368 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block (SM/08286) | SM/08286 | 865 | 14748 | RETROFITTING | 90 | On track | 94 | 09/02/2021 | 31/03/2026 | 16/05/2025 | 28/10/2021 | 813.49 | 811.49
369 | Banhat Piped Water Supply Scheme. (SM/14029) | SM/14029 | 484.07 | 2002 | NEW | 90 | On track | 58 | 05/12/2022 | 31/12/2025 | 16/05/2025 | 22/03/2023 | 281.12 | 281.12
370 | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. (SM/09368) | SM/09368 | 68.35 | 1054 | RETROFITTING | 90 | On track | 88 | 12/11/2021 | 31/05/2025 | 16/05/2025 | 04/01/2022 | 60.36 | 60.36
371 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme (SM/10665) | SM/10665 | 58.24 | 903 | RETROFITTING | 90 | On track | 97 | 22/04/2022 | 31/12/2025 | 16/05/2025 | 21/09/2022 | 56.54 | 56.54
372 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11900) | SM/11900 | 448 | 1209 | NEW | 90 | On track | 64 | 22/08/2022 | 31/03/2026 | 16/05/2025 | 28/11/2022 | 285.2 | 258.29
373 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BAMUNDIHA AND OTHER 14 NOS. MOUZAS UNDER MD BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12068) | SM/12068 | 541 | 900 | NEW | 90 | On track | 63 | 02/09/2022 | 31/12/2025 | 16/05/2025 | 28/11/2022 | 342.83 | 214.04
374 | Purba Anantapur Piped Water Supply Scheme (SM/13715) | SM/13715 | 586.12 | 2388 | NEW | 90 | On track | 46 | 14/11/2022 | 31/12/2025 | 16/05/2025 | 12/04/2023 | 269.87 | 269.87
375 | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/14125) | SM/14125 | 1110.9 | 2667 | NEW | 90 | Delayed | 30 | 02/01/2023 | 08/02/2025 | 16/05/2025 | 10/08/2023 | 335.83 | 335.83
376 | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area (SM/06949) | SM/06949 | 99.96 | 1530 | RETROFITTING | 90 | On track | 97 | 03/11/2020 | 31/05/2025 | 16/05/2025 | 16/08/2021 | 97.05 | 97.05
377 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) (SM/12637) | SM/12637 | 34.45 | 530 | RETROFITTING | 90 | On track | 58 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 19.93 | 19.93
378 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHICHUNRI AND OTHER 3 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11906) | SM/11906 | 127 | 1006 | NEW | 90 | On track | 79 | 22/08/2022 | 31/03/2026 | 16/05/2025 | 28/11/2022 | 100.03 | 100.03
379 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS (SM/07648) | SM/07648 | 99.48 | 1750 | RETROFITTING | 90 | On track | 76 | 07/01/2021 | 30/11/2025 | 16/05/2025 | 13/04/2022 | 75.48 | 75.48
380 | Chandrapur Piped Water Supply Scheme (SM/14893) | SM/14893 | 653.22 | 1003 | NEW | 90 | On track | 67 | 04/02/2023 | 30/06/2025 | 16/05/2025 | 06/04/2023 | 437.93 | 437.93
381 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BABUPUR AND OTHER 5 NOS. MOUZAS UNDER SURI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11899) | SM/11899 | 222 | 591 | NEW | 90 | On track | 91 | 22/08/2022 | 31/03/2026 | 16/05/2025 | 28/11/2022 | 201.54 | 201.54
382 | Paikpara Piped Water Supply Scheme. (SM/12669) | SM/12669 | 355.1 | 806 | NEW | 90 | On track | 42 | 19/09/2022 | 31/12/2025 | 16/05/2025 | 03/08/2023 | 148.69 | 148.69
383 | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/13710) | SM/13710 | 979.98 | 2004 | NEW | 90 | On track | 50 | 14/11/2022 | 31/12/2025 | 16/05/2025 | 14/07/2023 | 487.03 | 487.03
384 | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. (SM/13983) | SM/13983 | 447.36 | 588 | NEW | 90 | Delayed | 46 | 01/12/2022 | 08/01/2025 | 16/05/2025 | 27/02/2023 | 203.64 | 203.64
385 | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area (SM/06947) | SM/06947 | 99.28 | 1520 | RETROFITTING | 92 | On track | 95 | 03/11/2020 | 31/12/2025 | 16/05/2025 | 13/01/2021 | 94.25 | 89.96
386 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) (SM/06732) | SM/06732 | 99.79 | 777 | RETROFITTING | 95 | On track | 93 | 18/09/2020 | 31/03/2026 | 16/05/2025 | 07/07/2021 | 92.81 | 92.81
387 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) (SM/06733) | SM/06733 | 99.93 | 1860 | RETROFITTING | 95 | On track | 95 | 18/09/2020 | 31/12/2025 | 16/05/2025 | 21/09/2020 | 95.17 | 95.17
388 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block (SM/07646) | SM/07646 | 82.04 | 1396 | RETROFITTING | 95 | On track | 97 | 07/01/2021 | 30/11/2025 | 16/05/2025 | 26/02/2021 | 79.66 | 79.66
389 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. (SM/08892) | SM/08892 | 96.68 | 1500 | RETROFITTING | 95 | On track | 75 | 29/09/2021 | 30/03/2026 | 16/05/2025 | 23/09/2021 | 72.23 | 72.23
390 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) (SM/06741) | SM/06741 | 99.97 | 1860 | RETROFITTING | 95 | On track | 97 | 18/09/2020 | 31/12/2025 | 16/05/2025 | 05/10/2021 | 97.06 | 93.37
391 | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area (SM/06943) | SM/06943 | 97.5 | 1520 | RETROFITTING | 95 | On track | 97 | 03/11/2020 | 31/03/2026 | 16/05/2025 | 10/12/2021 | 94.66 | 94.66
392 | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09371) | SM/09371 | 105.12 | 1622 | RETROFITTING | 95 | On track | 97 | 12/11/2021 | 31/12/2025 | 16/05/2025 | 07/03/2022 | 102.06 | 102.06
393 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) (SM/06735) | SM/06735 | 99.99 | 1860 | RETROFITTING | 95 | On track | 89 | 18/09/2020 | 31/03/2026 | 16/05/2025 | 01/10/2020 | 89.34 | 94.11
394 | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07152) | SM/07152 | 65.97 | 851 | RETROFITTING | 100 | 100% Physical | 81 | 01/12/2020 | 30/06/2025 | 16/05/2025 | 21/09/2020 | 53.3 | 53.3
395 | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area (SM/06945) | SM/06945 | 98.81 | 1510 | RETROFITTING | 100 | 100% Physical | 57 | 04/11/2020 | 31/05/2025 | 16/05/2025 | 16/07/2021 | 56.55 | 73.85
396 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) (SM/06737) | SM/06737 | 95.3 | 1752 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/05/2025 | 16/05/2025 | 16/07/2021 | 95.3 | 93.59
397 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) (SM/06739) | SM/06739 | 96.06 | 1755 | RETROFITTING | 100 | 100% Physical | 93 | 18/09/2020 | 31/12/2025 | 16/05/2025 | 21/09/2020 | 89.61 | 90.4
398 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block (SM/07651) | SM/07651 | 99.95 | 1760 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 31/03/2026 | 16/05/2025 | 15/06/2021 | 97.04 | 97.04
399 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS (SM/06738) | SM/06738 | 99.99 | 1755 | RETROFITTING | 100 | 100% Physical | 97 | 18/09/2020 | 30/06/2025 | 16/05/2025 | 21/09/2020 | 96.79 | 96.79
400 | Preparation of DPR for Drinking Water Supply Schemes within the different blocks of Birbhum District under Birbhum Division, PHE Dte. (SM/18987) | SM/18987 | 559.97 | 0 | SUPPORT DPR & SURVEY | 100 | 100% Physical | 0 | 12/10/2023 |  | 12/10/2023 | 27/12/2021 | 0 | 0
Total |  |  | 256437.06 | 901136 | [8 empty] | 83898.38 | 81852.86