## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Sekupur piped water supply scheme. (SM/13650) | SM/13650 | 349.5 | 762 | NEW | 0 | 0% Physical | 4 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 10/08/2023 | 12.93 | 12.93
2 | Radipur Piped Water Supply Scheme. (SM/14027) | SM/14027 | 519.73 | 1716 | NEW | 0 | 0% Physical | 2 | 05/12/2022 | 05/06/2024 | 12/06/2023 | 10/08/2023 | 11.68 | 11.68
3 | Charicha Piped Water Supply Scheme. (SM/18512) | SM/18512 | 1514.48 | 2905 | NEW | 0 | 0% Physical | 32 | 26/07/2023 | 26/07/2025 | 31/07/2023 | 10/08/2023 | 486.68 | 486.68
4 | Dakshin Madanpur Piped Water Supply Scheme. (SM/12687) | SM/12687 | 473.11 | 1121 | NEW | 0 | 0% Physical | 7 | 21/09/2022 | 21/03/2024 | 12/06/2023 | 10/08/2023 | 31.24 | 31.24
5 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kurumgram (Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12668) | SM/12668 | 11.63 | 179 | RETROFITTING | 0 | WO no issued | 0 | 19/09/2022 | 19/12/2022 | 12/06/2023 |  | 0 | 0
6 | Barua Gopalpur Piped Water Supply Scheme. (SM/14421) | SM/14421 | 1288.16 | 3708 | NEW | 0 | 0% Physical | 11 | 20/01/2023 | 20/01/2025 | 12/06/2023 | 10/08/2023 | 139.98 | 139.98
7 | Kanduri Piped Water Supply Scheme. (SM/14824) | SM/14824 | 543.12 | 1977 | NEW | 0 | 0% Physical | 4 | 04/02/2023 | 04/08/2024 | 12/06/2023 | 03/10/2023 | 21.25 | 21.25
8 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. (SM/13374) | SM/13374 | 14.22 | 215 | RETROFITTING | 0 | WO no issued | 0 | 19/10/2022 | 19/01/2023 | 12/06/2023 |  | 0 | 0
9 | Masra Piped Water Supply Scheme. (SM/18463) | SM/18463 | 1206.76 | 3940 | NEW | 0 | 0% Physical | 0 | 20/07/2023 | 20/07/2025 | 20/07/2023 | 10/08/2023 | 0 | 0
10 | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. (SM/09490) | SM/09490 | 299.8 | 4634 | RETROFITTING | 0 | 0% Physical | 0 | 19/11/2021 | 19/02/2022 | 12/06/2023 | 12/08/2020 | 0 | 0
11 | Bergram Piped Water Supply Scheme. (SM/13482) | SM/13482 | 527.4 | 1351 | NEW | 0 | 0% Physical | 6 | 02/11/2022 | 02/05/2024 | 12/06/2023 | 10/08/2023 | 32.2 | 32.2
12 | MANIKPUR PIPED WATER SUPPLY SCHEME (SM/18509) | SM/18509 | 1125.72 | 3406 | NEW | 0 | 0% Physical | 9 | 26/07/2023 | 26/07/2025 | 31/07/2023 | 10/08/2023 | 100.48 | 100.48
13 | Gokrui Piped Water Supply Scheme. (SM/13631) | SM/13631 | 426.79 | 826 | NEW | 0 | 0% Physical | 14 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 10/08/2023 | 60.12 | 60.12
14 | Majuria Piped Water Supply Scheme. (SM/13632) | SM/13632 | 998.5 | 2503 | NEW | 0 | 0% Physical | 19 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 10/08/2023 | 191.87 | 191.87
15 | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area (SM/06946) | SM/06946 | 97.74 | 1510 | RETROFITTING | 0 | 0% Physical | 39 | 03/11/2020 | 31/05/2021 | 12/06/2023 | 16/07/2021 | 38.5 | 38.5
16 | Salan Piped Water Supply Scheme. (SM/14207) | SM/14207 | 778.17 | 2622 | NEW | 0 | 0% Physical | 2 | 10/01/2023 | 10/07/2024 | 12/06/2023 | 25/08/2023 | 18 | 18
17 | Balijuri Piped Water Supply Scheme. (SM/12682) | SM/12682 | 940.28 | 2567 | NEW | 0 | 0% Physical | 14 | 21/09/2022 | 21/03/2024 | 12/06/2023 | 10/08/2023 | 134.51 | 134.51
18 | LAYEKPUR PIPED WATER SUPPLY SCHEME (SM/18361) | SM/18361 | 1217.25 | 3872 | NEW | 0 | 0% Physical | 0 | 11/07/2023 | 11/07/2025 | 14/07/2023 | 21/09/2023 | 0 | 0
19 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum (SM/08172) | SM/08172 | 95.12 | 1520 | RETROFITTING | 0 | 0% Physical | 95 | 08/02/2021 | 31/10/2021 | 12/06/2023 | 26/02/2021 | 89.98 | 89.98
20 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. (SM/12660) | SM/12660 | 21.01 | 319 | RETROFITTING | 0 | 0% Physical | 82 | 19/09/2022 | 19/12/2022 | 12/06/2023 | 19/04/2023 | 17.31 | 17.31
21 | Dhananjaypur Piped Water Supply Scheme. (SM/12688) | SM/12688 | 701.06 | 1773 | NEW | 0 | 0% Physical | 4 | 21/09/2022 | 21/03/2024 | 12/06/2023 | 10/08/2023 | 31.3 | 31.3
22 | Procurement Chemicals & Consumables, Glassware etc. Required for smooth running of the Different Laboratories under JJM under Birbhum Division PHE Dte. (SM/19268) | SM/19268 | 102.97 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
23 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/08981) | SM/08981 | 25.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 |  | 0 | 0
24 | Procurement of Computer and Peripherals for the office use in Bolpur Mechanical Division, AE-III Central Mechanical Division, Birbhum Mechanical Sub-Division (Drilling) PHE Dte. (SM/18141) | SM/18141 | 21.47 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 |  | 0 | 0
25 | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. (SM/19263) | SM/19263 | 76.18 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
26 | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. (SM/15637) | SM/15637 | 90.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 24/01/2022 | 0 | 0
27 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. (SM/06632) | SM/06632 | 71.7 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 05/07/2021 | 0 | 0
28 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratory. (SM/06628) | SM/06628 | 7.35 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 23/07/2021 | 0 | 0
29 | New Pipe Testing Laboratory for testing of UPVC and HDPE pipes at Suri, Birbhum under Birbhum Division. (SM/16483) | SM/16483 | 194.37 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 25/07/2023 | 0 | 0
30 | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM (SM/15636) | SM/15636 | 50.89 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 30/06/2023 | 0 | 0
31 | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission (SM/19083) | SM/19083 | 63.6 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
32 | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. (SM/09199) | SM/09199 | 10.32 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 29/10/2021 |  | 04/11/2021 | 31/12/2020 | 0 | 0
33 | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. (SM/18278) | SM/18278 | 12.02 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 |  | 0 | 0
34 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Birbhum District. (SM/09198) | SM/09198 | 290.12 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 04/11/2021 | 19/08/2022 | 0 | 0
35 | NARAYANPUR PIPED WATER SUPPLY SCHEME. (SM/13625) | SM/13625 | 525.66 | 1545 | NEW | 1 | Delayed | 18 | 11/11/2022 | 31/03/2024 | 27/09/2023 | 10/08/2023 | 94.03 | 94.03
36 | Demurtita Piped Water Supply Scheme. (SM/14981) | SM/14981 | 279.34 | 588 | NEW | 2 | Delayed | 10 | 04/02/2023 | 04/08/2024 | 10/05/2024 | 17/10/2023 | 27.52 | 26.59
37 | BALIARA PIPED WATER SUPPLY SCHEME (SM/14847) | SM/14847 | 709.05 | 1576 | NEW | 2 | Delayed | 4 | 03/02/2023 | 03/08/2024 | 05/12/2023 | 25/04/2023 | 27.87 | 27.87
38 | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) (SM/14851) | SM/14851 | 475.95 | 1165 | NEW | 2 | Delayed | 19 | 03/02/2023 | 03/08/2024 | 10/05/2024 | 17/10/2023 | 91.64 | 71.98
39 | Haripur Piped Water Supply Scheme (SM/14853) | SM/14853 | 934.11 | 2142 | NEW | 2 | Delayed | 34 | 03/02/2023 | 03/08/2024 | 10/05/2024 | 17/10/2023 | 319.16 | 319.16
40 | Bagahola Piped Water Supply Scheme (SM/14084) | SM/14084 | 389.21 | 514 | NEW | 2 | Delayed | 21 | 12/12/2022 | 12/06/2024 | 10/05/2024 | 17/10/2023 | 81.9 | 71.36
41 | SHEKHAMPUR PIPED WATER SUPPLY SCHEME (SM/14956) | SM/14956 | 744.62 | 1672 | NEW | 2 | Delayed | 4 | 04/02/2023 | 04/08/2024 | 13/06/2024 | 17/05/2022 | 32.26 | 32.26
42 | PARULIA PIPED WATER SUPPLY SCHEME. (SM/14538) | SM/14538 | 1104.48 | 2335 | NEW | 2 | Delayed | 44 | 30/01/2023 | 30/01/2025 | 23/11/2023 | 25/04/2023 | 480.91 | 475.94
43 | FARIDPUR PIPED WATER SUPPLY SCHEME (SM/14971) | SM/14971 | 725.24 | 1444 | NEW | 2 | Delayed | 11 | 04/02/2023 | 04/08/2024 | 13/06/2024 | 12/04/2022 | 79.93 | 79.93
44 | BHUBANESWAR PIPED WATER SUPPLY SCHEME (SM/13387) | SM/13387 | 911.71 | 2288 | NEW | 2 | Delayed | 16 | 18/10/2022 | 18/04/2024 | 14/03/2024 | 30/03/2023 | 147.41 | 147.41
45 | DULA SAHAPUR PIPED WATER SUPPLY SCHEME (SM/14746) | SM/14746 | 999.21 | 3496 | NEW | 2 | Delayed | 3 | 31/01/2023 | 29/11/2024 | 13/06/2024 | 10/08/2023 | 28.34 | 28.34
46 | Chora Piped Water Supply Scheme (SM/15523) | SM/15523 | 248.08 | 482 | NEW | 2 | Delayed | 10 | 16/02/2023 | 16/08/2024 | 10/05/2024 | 17/10/2023 | 25.17 | 25.17
47 | RANIPARA PIPED WATER SUPPLY SCHEME (SM/16276) | SM/16276 | 540.82 | 876 | NEW | 2 | Delayed | 1 | 24/02/2023 | 24/08/2024 | 13/06/2024 | 11/05/2022 | 7.92 | 7.92
48 | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) (SM/16272) | SM/16272 | 249.14 | 538 | NEW | 2 | Delayed | 39 | 24/02/2023 | 24/08/2024 | 10/05/2024 | 17/10/2023 | 95.95 | 79.93
49 | SHIRSHA PIPED WATER SUPPLY SCHEME (SM/13647) | SM/13647 | 974.04 | 2439 | NEW | 2 | Delayed | 4 | 11/11/2022 | 11/05/2024 | 14/03/2024 | 10/08/2023 | 42.22 | 42.22
50 | Sandhyajol Piped Water Supply Scheme (SM/13981) | SM/13981 | 775.21 | 2016 | NEW | 2 | Delayed | 8 | 01/12/2022 | 01/06/2024 | 08/12/2023 | 10/08/2023 | 62.74 | 62.74
51 | Bhadulia Piped Water Supply Scheme (SM/14674) | SM/14674 | 474.51 | 985 | NEW | 2 | Delayed | 16 | 31/01/2023 | 31/07/2024 | 10/05/2024 | 17/10/2023 | 77.03 | 77.03
52 | Ekura Piped Water Supply Scheme. (SM/13949) | SM/13949 | 461.93 | 667 | NEW | 2 | Delayed | 16 | 01/12/2022 | 01/06/2024 | 10/05/2024 | 17/10/2023 | 71.78 | 71.78
53 | FEUGRAM PIPED WATER SUPPLY SCHEME (SM/13477) | SM/13477 | 813.8 | 1734 | NEW | 2 | Delayed | 5 | 02/11/2022 | 02/05/2024 | 05/12/2023 | 10/03/2022 | 39.43 | 39.43
54 | MONACHITURA PIPED WATER SUPPLY SCHEME (SM/14450) | SM/14450 | 846.93 | 2499 | NEW | 2 | Delayed | 1 | 20/01/2023 | 20/07/2024 | 13/06/2024 | 15/03/2022 | 4.39 | 4.39
55 | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) (SM/14854) | SM/14854 | 582.15 | 1544 | NEW | 2 | Delayed | 22 | 03/02/2023 | 03/08/2024 | 10/05/2024 | 17/10/2023 | 127.52 | 96.27
56 | THIBA PIPEED WATER SUPPLY SCHEME (SM/14968) | SM/14968 | 538.07 | 1010 | NEW | 2 | Delayed | 4 | 04/02/2023 | 04/08/2024 | 13/06/2024 | 25/05/2022 | 20.79 | 20.79
57 | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME (SM/14534) | SM/14534 | 1071.04 | 2281 | NEW | 2 | Delayed | 4 | 30/01/2023 | 30/01/2025 | 21/05/2024 | 10/08/2023 | 46.75 | 46.75
58 | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) (SM/16270) | SM/16270 | 153.88 | 272 | NEW | 2 | Delayed | 9 | 24/02/2023 | 24/08/2024 | 10/05/2024 | 17/10/2023 | 14.36 | 3.79
59 | BHEPUR PIPED WATER SUPPLY SCHEME (SM/13759) | SM/13759 | 705.69 | 1502 | NEW | 2 | Delayed | 3 | 18/11/2022 | 18/05/2024 | 05/12/2023 | 12/04/2022 | 20.2 | 20.2
60 | Rupaspur Piped Water Supply Scheme. (SM/14081) | SM/14081 | 436.17 | 975 | NEW | 2 | Delayed | 19 | 12/12/2022 | 12/06/2024 | 10/05/2024 | 17/10/2023 | 80.85 | 70.8
61 | Bhaddi Piped Water Supply Scheme (SM/14114) | SM/14114 | 422.65 | 897 | NEW | 2 | Delayed | 22 | 02/01/2023 | 02/07/2024 | 10/05/2024 | 17/10/2023 | 94.64 | 71.55
62 | KURUMBA PIPED WATER SUPPLY SCHEME (SM/14743) | SM/14743 | 674.03 | 2184 | NEW | 2 | Delayed | 8 | 31/01/2023 | 31/07/2024 | 13/06/2024 | 22/03/2023 | 55.1 | 55.1
63 | Aliat Piped Water Supply Scheme (SM/14083) | SM/14083 | 414.62 | 804 | NEW | 2 | Delayed | 17 | 12/12/2022 | 12/06/2024 | 10/05/2024 | 17/10/2023 | 70.04 | 70.04
64 | PANCHPARA PIPED WATER SUPPLY SCHEME (SM/13951) | SM/13951 | 639.73 | 1851 | NEW | 2 | Delayed | 2 | 01/12/2022 | 01/09/2024 | 13/06/2024 | 05/05/2022 | 14.57 | 14.57
65 | BHETER PIPED WATER SUPPLY SCHEME (SM/14848) | SM/14848 | 507.47 | 1132 | NEW | 2 | Delayed | 8 | 03/02/2023 | 03/08/2024 | 05/12/2023 | 21/03/2022 | 38.44 | 38.44
66 | Parsundi Piped Water Supply Scheme (SM/14855) | SM/14855 | 506.23 | 1178 | NEW | 2 | Delayed | 22 | 03/02/2023 | 03/08/2024 | 18/04/2024 | 17/10/2023 | 111.88 | 101.74
67 | KHAYERBANI PIPED WATER SUPPLY SCHEME (SM/14677) | SM/14677 | 522.91 | 1169 | NEW | 2 | Delayed | 5 | 31/01/2023 | 31/07/2024 | 13/06/2024 | 25/04/2022 | 27.89 | 27.89
68 | GOALDIHI PIPED WATER SUPPLY SCHEME (SM/15528) | SM/15528 | 523.1 | 1042 | NEW | 2 | Delayed | 3 | 15/02/2023 | 15/08/2024 | 05/12/2023 | 22/03/2022 | 13.37 | 13.37
69 | DHANASAHA PIPED WATER SUPPLY SCHEME (SM/18352) | SM/18352 | 1202.1 | 3030 | NEW | 2 | Delayed | 22 | 11/07/2023 | 11/07/2025 | 14/03/2024 | 10/08/2023 | 262.17 | 262.17
70 | CHUNPALASHI PIPED WATER SUPPLY SCHEME (SM/13637) | SM/13637 | 740.04 | 1863 | NEW | 2 | Delayed | 4 | 11/11/2022 | 11/05/2024 | 14/03/2024 | 31/03/2022 | 31.22 | 31.22
71 | Srikantapur piped water supply scheme. (SM/13652) | SM/13652 | 774.31 | 2142 | NEW | 2 | Delayed | 7 | 11/11/2022 | 31/12/2024 | 30/09/2024 | 10/08/2023 | 53.03 | 53.03
72 | KADOA PIPED WAYER SUPPLY SCHEME (SM/14668) | SM/14668 | 594.33 | 1039 | NEW | 2 | Delayed | 6 | 31/01/2023 | 31/07/2024 | 13/06/2024 | 18/04/2022 | 37.52 | 37.52
73 | GOPINATHPUR PIPED WATER SUPPLY SCHEME (SM/15253) | SM/15253 | 649.94 | 1633 | NEW | 2 | Delayed | 8 | 06/02/2023 | 06/08/2024 | 14/03/2024 | 07/04/2022 | 50 | 50
74 | MAHESWARPUR PIPED WATER SUPPLY SCHEME (SM/15254) | SM/15254 | 471.69 | 1055 | NEW | 2 | Delayed | 26 | 06/02/2023 | 06/08/2024 | 14/03/2024 | 10/04/2023 | 124.96 | 75.48
75 | MADDA PIPED WATER SUPPLY SCHEME (SM/15255) | SM/15255 | 639.56 | 1390 | NEW | 2 | Delayed | 2 | 07/02/2023 | 07/08/2024 | 05/12/2023 | 31/03/2022 | 12.26 | 12.26
76 | Mayandal Piped Water Supply Scheme (SM/16273) | SM/16273 | 158.49 | 342 | NEW | 2 | Delayed | 7 | 23/02/2023 | 23/08/2024 | 10/05/2024 | 17/10/2023 | 11.82 | 11.82
77 | Tamra Piped Water Supply Scheme (SM/18739) | SM/18739 | 284.35 | 627 | NEW | 2 | Delayed | 12 | 17/08/2023 | 17/02/2025 | 10/05/2024 | 17/10/2023 | 34.28 | 34.28
78 | ULANDI PIPED WATER SUPPLY SCHEME (SM/13654) | SM/13654 | 626.02 | 1568 | NEW | 2 | Delayed | 21 | 11/11/2022 | 11/05/2024 | 14/03/2024 | 18/04/2022 | 128.71 | 74.91
79 | Baraban Piped Water Supply Scheme (Khoyrasole Block) (SM/14852) | SM/14852 | 585.66 | 1408 | NEW | 2 | Delayed | 21 | 03/02/2023 | 03/08/2024 | 10/05/2024 | 17/10/2023 | 124.38 | 105.21
80 | TATINAPARA PIPED WATER SUPPLY SCHEME (SM/13979) | SM/13979 | 880.48 | 2460 | NEW | 2 | Delayed | 1 | 01/12/2022 | 30/09/2024 | 28/06/2024 | 21/09/2023 | 4.59 | 4.59
81 | GOPINATHPUR PIPED WATER SUPPLY SCHEME (SM/14897) | SM/14897 | 727.26 | 1914 | NEW | 2 | Delayed | 3 | 04/02/2023 | 04/08/2024 | 13/06/2024 | 06/04/2023 | 22.41 | 22.41
82 | Hatikata Piped Water Supply Scheme (SM/16198) | SM/16198 | 290.59 | 619 | NEW | 2 | Delayed | 5 | 23/02/2023 | 23/08/2024 | 10/05/2024 | 17/10/2023 | 14.48 | 14.48
83 | ANGORA PIPED WATER SUPPLY SCHEME (SM/13971) | SM/13971 | 911.87 | 1822 | NEW | 3 | Delayed | 2 | 01/12/2022 | 01/06/2024 | 21/05/2024 | 30/03/2023 | 16.6 | 16.6
84 | Chormara Piped Water Supply Scheme. (SM/14030) | SM/14030 | 402.81 | 881 | NEW | 3 | Delayed | 8 | 05/12/2022 | 05/06/2024 | 29/03/2024 | 31/05/2023 | 30.82 | 30.82
85 | Charkalgram Piped Water Supply Scheme (SM/13481) | SM/13481 | 953.48 | 2189 | NEW | 3 | Delayed | 2 | 02/11/2022 | 30/06/2024 | 21/05/2024 | 10/08/2023 | 14.75 | 14.75
86 | Majhkanda Piped Water Supply Scheme. (SM/14896) | SM/14896 | 653.84 | 2709 | NEW | 3 | Delayed | 7 | 04/02/2023 | 31/12/2024 | 12/06/2024 | 10/08/2023 | 45.86 | 45.86
87 | Nichinta Piped Water Supply Scheme (Khoyrasole Block) (SM/16271) | SM/16271 | 145.99 | 237 | NEW | 3 | Delayed | 1 | 24/02/2023 | 24/08/2024 | 28/05/2024 | 17/10/2023 | 0.82 | 0.82
88 | Kashtagara Piped Water Supply Scheme. (SM/18733) | SM/18733 | 1262.41 | 4375 | NEW | 3 | Delayed | 1 | 14/08/2023 | 14/08/2025 | 27/09/2024 | 03/10/2023 | 17.3 | 17.3
89 | NAWADA PALANDI PIPED WATER SUPPLY SCHEME (SM/14682) | SM/14682 | 1029.06 | 2203 | NEW | 3 | Delayed | 4 | 31/01/2023 | 31/01/2025 | 21/05/2024 | 10/08/2023 | 43.16 | 43.16
90 | Penchalia Piped Water Supply Scheme (SM/16282) | SM/16282 | 389.54 | 831 | NEW | 3 | Delayed | 16 | 24/02/2023 | 24/08/2024 | 28/05/2024 | 17/10/2023 | 61.18 | 53.91
91 | KAHINAGAR PIPED WATER SUPPLY SCHME (SM/12887) | SM/12887 | 807.08 | 2309 | NEW | 3 | Delayed | 1 | 23/09/2022 | 24/09/2024 | 10/06/2024 | 25/04/2023 | 12.05 | 12.05
92 | Dakshin Chandipur Piped Water Supply Scheme. (SM/12685) | SM/12685 | 556.73 | 1416 | NEW | 3 | Delayed | 12 | 21/09/2022 | 31/12/2024 | 30/09/2024 | 20/04/2023 | 64.87 | 61.76
93 | Harinduba Piped Water Supply Scheme. (SM/12692) | SM/12692 | 739.16 | 1850 | NEW | 3 | Delayed | 9 | 20/09/2022 | 31/05/2024 | 29/11/2023 | 20/04/2023 | 69.26 | 62.55
94 | Nanubazar Piped Water Supply Scheme (SM/12673) | SM/12673 | 615.54 | 1536 | NEW | 3 | Delayed | 22 | 19/09/2022 | 31/12/2025 | 04/12/2024 | 10/08/2023 | 132.38 | 126.25
95 | Ninga Piped Water Supply Scheme (SM/14089) | SM/14089 | 844.34 | 2013 | NEW | 3 | Delayed | 7 | 12/12/2022 | 12/06/2024 | 06/03/2024 | 10/08/2023 | 62.17 | 62.17
96 | Kusumba Piped Water Supply Scheme. (SM/18362) | SM/18362 | 1173.23 | 4056 | NEW | 3 | Delayed | 5 | 11/07/2023 | 11/07/2025 | 27/09/2024 | 10/08/2023 | 56.1 | 56.1
97 | BENGA CHATRA PIPED WATER SUPPLY SCHEME (SM/13408) | SM/13408 | 716.72 | 1526 | NEW | 4 | Delayed | 5 | 02/11/2022 | 02/05/2024 | 16/10/2023 | 25/03/2022 | 35.13 | 35.13
98 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12074) | SM/12074 | 998 | 1328 | NEW | 4 | Delayed | 31 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 305.51 | 305.51
99 | Paratpur Piped Water Supply Scheme. (SM/13474) | SM/13474 | 806.88 | 2066 | NEW | 4 | Delayed | 17 | 02/11/2022 | 31/12/2024 | 10/09/2024 | 08/08/2023 | 135.53 | 135.53
100 | RANIBAZAR PIPED WATER SUPPLY SCHEME (SM/14850) | SM/14850 | 646 | 1440 | NEW | 4 | Delayed | 3 | 03/02/2023 | 03/08/2024 | 16/10/2023 | 11/05/2022 | 18.23 | 18.23
101 | Sekedda Piped Water Supply Scheme. (SM/14683) | SM/14683 | 2443.77 | 6637 | NEW | 4 | Delayed | 19 | 31/01/2023 | 31/01/2025 | 02/07/2024 | 10/08/2023 | 463.64 | 463.64
102 | Ruppur and adjoining mouzas Piped Water Supply Scheme. (SM/14686) | SM/14686 | 1387.78 | 3231 | NEW | 4 | Delayed | 23 | 31/01/2023 | 31/01/2025 | 22/03/2024 | 10/08/2023 | 316.35 | 316.35
103 | BHATRA PIPED WATER SUPPLY SCHEME (SM/14958) | SM/14958 | 785.97 | 2391 | NEW | 4 | Delayed | 10 | 04/02/2023 | 04/08/2024 | 01/08/2024 | 07/04/2022 | 75.58 | 75.58
104 | Chhora Piped Water Supply Scheme. (SM/16761) | SM/16761 | 497.37 | 1817 | NEW | 4 | Delayed | 7 | 13/03/2023 | 31/12/2024 | 05/09/2024 | 03/10/2023 | 37.15 | 37.15
105 | Bautia piped water supply scheme (SM/14536) | SM/14536 | 1467.55 | 3437 | NEW | 4 | Delayed | 29 | 30/01/2023 | 30/01/2025 | 28/02/2024 | 10/08/2023 | 421.42 | 421.42
106 | PAPURI PIPED WATER SUPPLY SCHEME (SM/14691) | SM/14691 | 889.54 | 1966 | NEW | 4 | Delayed | 6 | 31/01/2023 | 31/07/2024 | 21/05/2024 | 10/08/2023 | 52.72 | 52.72
107 | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME (SM/13950) | SM/13950 | 800.41 | 1812 | NEW | 4 | Delayed | 2 | 01/12/2022 | 01/06/2024 | 16/10/2023 | 05/05/2022 | 15.81 | 15.81
108 | SAJNOR PIPED WATER SUPPLY SCHEME (SM/14678) | SM/14678 | 872.23 | 2296 | NEW | 4 | Delayed | 4 | 31/01/2023 | 31/07/2024 | 21/05/2024 | 25/08/2023 | 30.6 | 30.6
109 | Bhabani Water Supply Scheme (SM/18351) | SM/18351 | 1451.76 | 3650 | NEW | 4 | Delayed | 10 | 11/07/2023 | 31/08/2025 | 11/06/2024 | 19/10/2023 | 147.36 | 147.36
110 | CHHATAR BANDI PIPED WATER SUPPLY SCHEME (SM/18354) | SM/18354 | 1021.7 | 2743 | NEW | 4 | Delayed | 16 | 11/07/2023 | 16/07/2025 | 25/07/2024 | 10/08/2023 | 159.23 | 159.23
111 | SANTOSHPUR PIPED WATER SUPPLY SCHEME (SM/14895) | SM/14895 | 777.41 | 1649 | NEW | 4 | Delayed | 4 | 04/02/2023 | 04/08/2024 | 16/10/2023 | 25/05/2022 | 31.8 | 31.8
112 | Ayas Piped Water Supply Scheme. (SM/18669) | SM/18669 | 2251.52 | 6861 | NEW | 4 | Delayed | 17 | 04/08/2023 | 31/08/2025 | 12/12/2023 | 10/08/2023 | 377.62 | 377.62
113 | RAYEN PIPED WATER SUPPLY SCHEME (SM/14957) | SM/14957 | 452.46 | 698 | NEW | 4 | Delayed | 5 | 04/02/2023 | 04/08/2024 | 16/10/2023 | 19/05/2022 | 20.81 | 20.81
114 | BENAGRAM PIPED WATER SUPPLY SCHEME (SM/13377) | SM/13377 | 624.74 | 1334 | NEW | 4 | Delayed | 8 | 18/10/2022 | 18/04/2024 | 16/10/2023 | 27/04/2022 | 50.24 | 50.24
115 | Daskalgram Piped Water Supply Scheme (SM/18353) | SM/18353 | 1197.31 | 2564 | NEW | 4 | Delayed | 8 | 11/07/2023 | 11/07/2025 | 21/05/2024 | 10/08/2023 | 90.53 | 90.53
116 | Metegaon and Adjoining Mouzas PWSS (SM/12700) | SM/12700 | 653.76 | 1309 | NEW | 4 | Delayed | 18 | 21/09/2022 | 31/12/2024 | 09/09/2024 | 06/04/2023 | 120.69 | 120.69
117 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR MAJURIA AND OTHER 19 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12073) | SM/12073 | 775 | 1417 | NEW | 4 | Delayed | 36 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 281.43 | 281.43
118 | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT (SM/14675) | SM/14675 | 950.21 | 2321 | NEW | 4 | Delayed | 4 | 31/01/2023 | 31/08/2024 | 28/05/2024 | 17/04/2023 | 37.72 | 37.72
119 | Dakhalbati Piped Water Supply Scheme. (SM/18363) | SM/18363 | 2553.67 | 6565 | NEW | 4 | Delayed | 6 | 11/07/2023 | 30/09/2025 | 23/03/2024 | 11/10/2023 | 158.14 | 158.14
120 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) (SM/12637) | SM/12637 | 34.45 | 530 | RETROFITTING | 5 | Delayed | 58 | 19/09/2022 | 31/07/2024 | 15/05/2024 | 13/07/2023 | 19.93 | 19.93
121 | Lakshmi Narayanpur and Adjoining Mouzas PWSS (SM/12696) | SM/12696 | 846.97 | 1874 | NEW | 5 | Delayed | 20 | 21/09/2022 | 31/12/2025 | 13/08/2024 | 10/08/2023 | 166.99 | 166.99
122 | Budhigram Piped Water Supply Scheme (SM/16762) | SM/16762 | 763.84 | 1888 | NEW | 5 | Delayed | 4 | 13/03/2023 | 30/09/2024 | 06/12/2023 | 10/08/2023 | 32.91 | 32.91
123 | Bahadurpur Piped Water Supply Scheme. (SM/12681) | SM/12681 | 749.3 | 2221 | NEW | 5 | Delayed | 28 | 21/09/2022 | 31/12/2024 | 21/03/2024 | 21/03/2023 | 209.65 | 209.65
124 | Chanchali piped water supply scheme. (SM/12683) | SM/12683 | 1034.33 | 2580 | NEW | 5 | Delayed | 42 | 21/09/2022 | 31/12/2024 | 21/03/2024 | 25/04/2023 | 433.17 | 433.17
125 | Hazaripur Piped Water Supply Scheme (SM/14679) | SM/14679 | 764.93 | 2390 | NEW | 5 | Delayed | 11 | 31/01/2023 | 31/03/2025 | 04/01/2024 | 02/08/2023 | 87.89 | 87.89
126 | Paduma Piped Water Supply Scheme. (SM/14544) | SM/14544 | 1611.92 | 3934 | NEW | 5 | Delayed | 6 | 30/01/2023 | 30/01/2025 | 23/04/2024 | 25/04/2023 | 98 | 98
127 | MATIKONA PIPED WATER SUPPLY SCHEME (SM/13643) | SM/13643 | 860.82 | 2153 | NEW | 5 | Delayed | 6 | 11/11/2022 | 31/12/2024 | 25/07/2024 | 10/08/2023 | 52.96 | 52.96
128 | Kasba Piped Water Supply Scheme. (SM/13713) | SM/13713 | 779.81 | 2304 | NEW | 5 | Delayed | 5 | 14/11/2022 | 31/12/2024 | 03/10/2024 | 10/08/2023 | 40.96 | 39.04
129 | Tilai piped water supply scheme. (SM/13127) | SM/13127 | 404.7 | 1247 | NEW | 5 | Delayed | 7 | 10/10/2022 | 31/12/2024 | 22/03/2024 | 10/08/2023 | 28.48 | 28.48
130 | Albandha Piped Water Supply Scheme. (SM/14533) | SM/14533 | 1247.73 | 2929 | NEW | 5 | Delayed | 36 | 30/01/2023 | 31/03/2025 | 06/12/2023 | 30/03/2023 | 451.42 | 451.42
131 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum (SM/18783) | SM/18783 | 99.79 | 1303 | RETROFITTING | 5 | Delayed | 60 | 29/08/2023 | 31/07/2024 | 26/07/2024 | 21/09/2023 | 60.04 | 45.97
132 | Melanpur Piped Water Supply Scheme. (SM/12699) | SM/12699 | 522.74 | 1312 | NEW | 5 | Delayed | 39 | 21/09/2022 | 30/09/2024 | 22/03/2024 | 20/04/2023 | 203.18 | 203.18
133 | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. (SM/12677) | SM/12677 | 661.51 | 10178 | RETROFITTING | 5 | Delayed | 35 | 19/09/2022 | 31/12/2024 | 11/12/2023 | 02/05/2023 | 229.82 | 124.9
134 | BIRSINGHA PIPED WATER SUPPLY SCHEME. (SM/12830) | SM/12830 | 411.72 | 1269 | NEW | 5 | Delayed | 26 | 22/09/2022 | 30/09/2024 | 28/06/2024 | 29/11/2022 | 109.08 | 109.08
135 | Ekpara Piped Water Supply Scheme. (SM/12690) | SM/12690 | 289.55 | 618 | NEW | 6 | Delayed | 9 | 20/09/2022 | 31/12/2024 | 05/08/2024 | 08/06/2023 | 27.49 | 27.49
136 | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. (SM/14960) | SM/14960 | 715.34 | 3733 | AUGMENTATION | 6 | Delayed | 30 | 04/02/2023 | 31/08/2024 | 23/03/2024 | 10/08/2023 | 214.42 | 213.11
137 | Sahapur Piped water Supply Scheme. (SM/13649) | SM/13649 | 988.96 | 1721 | NEW | 6 | Delayed | 28 | 11/11/2022 | 01/07/2025 | 29/11/2024 | 23/03/2023 | 275.7 | 275.7
138 | Kayera Water Supply Scheme (SM/13641) | SM/13641 | 488.23 | 1231 | NEW | 6 | Delayed | 22 | 11/11/2022 | 31/10/2024 | 30/05/2024 | 15/03/2022 | 107.76 | 54.73
139 | Gaganpur piped water supply scheme. (SM/12691) | SM/12691 | 913.35 | 2859 | NEW | 6 | Delayed | 27 | 20/09/2022 | 31/12/2024 | 27/03/2024 | 25/08/2023 | 243.86 | 243.86
140 | Majhara piped water supply scheme (SM/12698) | SM/12698 | 443.6 | 1109 | NEW | 6 | Delayed | 9 | 21/09/2022 | 31/12/2024 | 27/03/2024 | 19/04/2023 | 39.68 | 39.68
141 | Siur Piped Water Supply Scheme. (SM/14537) | SM/14537 | 1169.86 | 2832 | NEW | 6 | Delayed | 41 | 30/01/2023 | 30/01/2025 | 29/03/2024 | 23/03/2023 | 473.84 | 473.84
142 | Kankalitala piped water supply scheme. (SM/18518) | SM/18518 | 1174.7 | 2793 | NEW | 6 | Delayed | 38 | 26/07/2023 | 31/08/2025 | 28/11/2023 | 10/08/2023 | 452.03 | 379.79
143 | Meherpur and Adjoining Mouzas PWSS (SM/12457) | SM/12457 | 488.08 | 1520 | NEW | 6 | Delayed | 10 | 13/09/2022 | 31/07/2024 | 06/12/2023 | 10/08/2023 | 48.68 | 48.68
144 | Monai Piped Water Supply Scheme. (SM/12701) | SM/12701 | 437.26 | 1571 | NEW | 6 | Delayed | 35 | 20/09/2022 | 31/12/2024 | 23/04/2024 | 25/04/2023 | 153.42 | 153.42
145 | Math Basori Piped Water Supply Scheme. (SM/13627) | SM/13627 | 564.3 | 1616 | NEW | 6 | Delayed | 15 | 11/11/2022 | 31/12/2024 | 21/03/2024 | 14/07/2023 | 83.77 | 83.77
146 | PUNNA PIPED WATER SUPPLY SCHEME (SM/14903) | SM/14903 | 996.36 | 3136 | NEW | 6 | Delayed | 13 | 04/02/2023 | 31/12/2025 | 11/12/2024 | 30/03/2023 | 124.75 | 120
147 | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. (SM/18366) | SM/18366 | 1040.7 | 1410 | AUGMENTATION | 6 | Delayed | 33 | 11/07/2023 | 31/12/2024 | 25/06/2024 | 10/08/2023 | 340.75 | 163.24
148 | Abdullahpur Piped Water Supply Scheme. (SM/12679) | SM/12679 | 799.1 | 2283 | NEW | 6 | Delayed | 23 | 21/09/2022 | 31/03/2025 | 24/09/2024 | 20/04/2023 | 182.96 | 154.92
149 | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division (SM/13480) | SM/13480 | 534.51 | 1118 | NEW | 6 | Delayed | 30 | 02/11/2022 | 31/07/2024 | 05/12/2023 | 06/04/2023 | 161.13 | 120.2
150 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR CHANDANPUR AND OTHER 5 NOS. MOUZAS UNDER MURARAI-I & NALHATI-I BLOCKS UNDER BIRBHUM DIVISION, PHE DTE. (SM/14043) | SM/14043 | 217 | 429 | NEW | 6 | Delayed | 40 | 12/12/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 87.59 | 87.59
151 | Nohana and Adjoining Mouzas PWSS (SM/12905) | SM/12905 | 301.26 | 751 | NEW | 6 | Delayed | 41 | 22/09/2022 | 31/12/2024 | 14/06/2024 | 02/05/2023 | 122.29 | 118.55
152 | Dhalla Piped Water Supply Scheme (SM/15256) | SM/15256 | 960.39 | 2260 | NEW | 6 | Delayed | 10 | 07/02/2023 | 31/12/2024 | 23/03/2024 | 10/08/2023 | 96.96 | 96.96
153 | Sahapur Piped Water Supply Scheme. (SM/18520) | SM/18520 | 1609.49 | 4720 | NEW | 6 | Delayed | 14 | 26/07/2023 | 27/11/2025 | 06/03/2024 | 10/08/2023 | 225.5 | 225.5
154 | Kukutia piped water supply scheme. (SM/13601) | SM/13601 | 549.6 | 1341 | NEW | 7 | Delayed | 14 | 09/11/2022 | 31/12/2024 | 10/12/2024 | 10/08/2023 | 74.96 | 74.96
155 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. (SM/13375) | SM/13375 | 34.41 | 432 | RETROFITTING | 7 | WO no issued | 0 | 19/10/2022 | 31/03/2024 | 27/09/2023 |  | 0 | 0
156 | HATIKRA PIPED WATER SUPPLY SCHEME. (SM/12893) | SM/12893 | 460.73 | 1587 | NEW | 7 | Delayed | 21 | 23/09/2022 | 30/09/2024 | 06/08/2024 | 12/04/2023 | 97.4 | 97.4
157 | Dumugram piped water supply scheme. (SM/12689) | SM/12689 | 894.92 | 2559 | NEW | 7 | Delayed | 29 | 21/09/2022 | 31/12/2024 | 27/03/2024 | 25/04/2023 | 258.92 | 185.7
158 | KASHERHAT PIPED WATER SUPPLY SCHEME. (SM/12903) | SM/12903 | 578.88 | 2235 | NEW | 7 | Delayed | 36 | 22/09/2022 | 31/12/2024 | 01/10/2024 | 10/08/2023 | 209.43 | 54.86
159 | JIUI PIPED WATER SUPPLY SCHEME. (SM/12902) | SM/12902 | 599.1 | 2853 | NEW | 7 | Delayed | 33 | 22/09/2022 | 31/12/2024 | 07/11/2023 | 12/04/2023 | 195.82 | 195.82
160 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHICHUNRI AND OTHER 3 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11906) | SM/11906 | 127 | 1006 | NEW | 7 | Delayed | 79 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 100.03 | 100.03
161 | Modapa Piped Water Supply Scheme. (SM/13517) | SM/13517 | 346.07 | 922 | NEW | 7 | Delayed | 62 | 02/11/2022 | 31/12/2024 | 26/09/2024 | 19/04/2023 | 216.08 | 216.08
162 | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. (SM/13376) | SM/13376 | 794.01 | 1613 | NEW | 7 | Delayed | 25 | 18/10/2022 | 31/12/2024 | 12/08/2024 | 10/08/2023 | 195.06 | 88.76
163 | SEHANA PIPED WATER SUPPLY SCHEME. (SM/12890) | SM/12890 | 526.76 | 1860 | NEW | 7 | Delayed | 21 | 23/09/2022 | 31/12/2024 | 01/10/2024 | 10/08/2023 | 108.01 | 54.38
164 | MITRAPUR WATER SUPPLY SCHEME. (SM/12892) | SM/12892 | 1170.21 | 3936 | NEW | 7 | Delayed | 8 | 23/09/2022 | 31/12/2024 | 10/09/2024 | 10/08/2023 | 96.26 | 96.26
165 | Khanpur piped water supply scheme. (SM/13539) | SM/13539 | 875.43 | 2543 | NEW | 7 | Delayed | 39 | 04/11/2022 | 31/12/2024 | 27/09/2024 | 25/04/2023 | 343.63 | 343.63
166 | HANSAN PIPED WATER SUPPLY SCHEME (SM/14900) | SM/14900 | 900.67 | 1932 | NEW | 7 | Delayed | 5 | 04/02/2023 | 31/12/2025 | 27/09/2024 | 10/08/2023 | 44.5 | 44.5
167 | SARIHA PIPED WATER SUPPLY SCHEME (SM/12900) | SM/12900 | 807.12 | 2296 | NEW | 7 | Delayed | 21 | 22/09/2022 | 31/01/2025 | 04/01/2024 | 20/04/2023 | 169.06 | 117.84
168 | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/14141) | SM/14141 | 1206.94 | 2714 | NEW | 7 | Delayed | 23 | 02/01/2023 | 31/03/2025 | 28/05/2024 | 10/08/2023 | 272.89 | 185.67
169 | Ahmadpur Piped Water Supply Scheme (SM/14889) | SM/14889 | 896.86 | 1737 | NEW | 7 | Delayed | 58 | 03/02/2023 | 31/10/2024 | 22/03/2024 | 31/05/2023 | 518.67 | 328.67
170 | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME (SM/18514) | SM/18514 | 1186.83 | 2600 | NEW | 7 | Delayed | 12 | 26/07/2023 | 31/07/2025 | 06/03/2024 | 10/08/2023 | 142.34 | 142.34
171 | Haridaspur Piped Water Supply Scheme. (SM/14028) | SM/14028 | 977.13 | 3535 | NEW | 7 | Delayed | 24 | 05/12/2022 | 31/08/2024 | 29/03/2024 | 17/07/2023 | 233.58 | 233.58
172 | Deoash and Adjoining Mouzas PWSS (SM/12670) | SM/12670 | 643 | 2323 | NEW | 8 | Delayed | 72 | 19/09/2022 | 19/03/2024 | 28/02/2024 | 12/04/2023 | 464.11 | 455.39
173 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14015) | SM/14015 | 570 | 3626 | NEW | 8 | Delayed | 69 | 05/12/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 392.72 | 392.72
174 | Paikpara Piped Water Supply Scheme. (SM/12669) | SM/12669 | 355.1 | 806 | NEW | 8 | Delayed | 41 | 19/09/2022 | 30/11/2024 | 01/08/2024 | 03/08/2023 | 144.3 | 144.3
175 | Naoadangal and Adjoining Mouzas PWSS (SM/12904) | SM/12904 | 722.04 | 1314 | NEW | 8 | Delayed | 59 | 22/09/2022 | 31/03/2024 | 04/01/2024 | 23/03/2023 | 424.23 | 424.23
176 | Banior Piped Water Supply Scheme. (SM/14688) | SM/14688 | 2842.94 | 5908 | NEW | 8 | Delayed | 29 | 31/01/2023 | 28/02/2025 | 26/09/2024 | 10/08/2023 | 836.25 | 836.25
177 | SAMSA PIPED WATER SUPPLY SCHEME. (SM/12597) | SM/12597 | 552.71 | 1842 | NEW | 8 | Delayed | 14 | 15/09/2022 | 31/12/2024 | 26/09/2024 | 25/04/2023 | 77.27 | 73.97
178 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12069) | SM/12069 | 291 | 570 | NEW | 8 | Delayed | 30 | 02/09/2022 | 02/03/2024 | 11/12/2023 | 28/11/2022 | 88.08 | 88.08
179 | Abhirampur and Adjoining Mouzas PWSS (SM/12536) | SM/12536 | 377.57 | 973 | NEW | 8 | Delayed | 48 | 13/09/2022 | 27/12/2024 | 26/03/2024 | 25/04/2023 | 180.94 | 180.94
180 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR SABASIDANGA AND OTHER 4 NOS. MOUZAS UNDER NALHATI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11904) | SM/11904 | 189 | 221 | NEW | 8 | Delayed | 60 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 114.34 | 114.34
181 | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division (SM/13634) | SM/13634 | 336.69 | 1500 | NEW | 8 | Delayed | 66 | 11/11/2022 | 31/10/2024 | 19/12/2023 | 01/03/2023 | 223.43 | 183.82
182 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMRITAPUR AND MAJHARA MOUZAS UNDER MURARAI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11908) | SM/11908 | 85 | 182 | NEW | 8 | Delayed | 0 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 0 | 0
183 | Nabagram Piped Water Supply Scheme. (SM/13646) | SM/13646 | 628.41 | 1353 | NEW | 8 | Delayed | 12 | 11/11/2022 | 30/09/2024 | 11/01/2024 | 11/08/2023 | 74.62 | 74.62
184 | Jashoda Piped Water Supply Scheme. (SM/12891) | SM/12891 | 363.96 | 1114 | NEW | 8 | Delayed | 43 | 23/09/2022 | 30/04/2024 | 26/09/2023 | 12/04/2023 | 157.02 | 157.02
185 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALPUR AND OTHER 5 NOS. MOUZAS UNDER NALHATI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14038) | SM/14038 | 225 | 425 | NEW | 8 | Delayed | 9 | 12/12/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 20.58 | 20.58
186 | Augmentation of Margram piped water supply scheme. (SM/18372) | SM/18372 | 1979.65 | 7205 | AUGMENTATION | 8 | Delayed | 4 | 11/07/2023 | 11/04/2024 | 07/11/2023 | 28/07/2023 | 88.4 | 88.4
187 | NOHNA PIPED WATER SUPPLY SCHEME (SM/13645) | SM/13645 | 813.39 | 1848 | NEW | 8 | Delayed | 37 | 11/11/2022 | 31/08/2024 | 25/04/2024 | 10/08/2023 | 301.82 | 301.82
188 | Nawapara Piped Water Supply Scheme (SM/13479) | SM/13479 | 720.04 | 2357 | NEW | 8 | Delayed | 28 | 02/11/2022 | 31/12/2024 | 10/01/2024 | 26/07/2023 | 205.17 | 205.17
189 | PHULUR PIPED WATER SUPPLY SCHEME. (SM/12901) | SM/12901 | 653.75 | 2406 | NEW | 8 | Delayed | 18 | 22/09/2022 | 31/12/2024 | 14/06/2024 | 12/07/2023 | 118.29 | 113.93
190 | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. (SM/15236) | SM/15236 | 738.45 | 705 | AUGMENTATION | 8 | Delayed | 38 | 07/02/2023 | 30/09/2024 | 28/05/2024 | 10/08/2023 | 283.01 | 283.01
191 | DALIMA PIPED WATER SUPPLY SCHEME. (SM/12592) | SM/12592 | 662.48 | 1957 | NEW | 8 | Delayed | 11 | 15/09/2022 | 31/01/2025 | 23/09/2024 | 25/04/2023 | 71.63 | 71.63
192 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR DHEKA AND OTHER 21 NOS. MOUZAS UNDER MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11910) | SM/11910 | 840 | 1573 | NEW | 8 | Delayed | 40 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 333.91 | 333.91
193 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR NAYIT AND OTHER 3 NOS. MOUZAS UNDER MURARAI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11907) | SM/11907 | 151 | 706 | NEW | 8 | Delayed | 82 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 123.22 | 123.22
194 | BANSANKHA PIPED WATER SUPPLY SCHEME. (SM/12889) | SM/12889 | 386.07 | 1357 | NEW | 9 | Delayed | 13 | 23/09/2022 | 31/12/2024 | 06/08/2024 | 12/04/2023 | 48.41 | 48.41
195 | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/14125) | SM/14125 | 1110.9 | 2667 | NEW | 9 | Delayed | 30 | 02/01/2023 | 02/01/2025 | 28/05/2024 | 10/08/2023 | 335.83 | 335.83
196 | PAKURIA PIPED WATER SUPPLY SCHEME. (SM/12596) | SM/12596 | 578.57 | 1868 | NEW | 9 | Delayed | 28 | 15/09/2022 | 30/11/2024 | 01/08/2024 | 03/08/2023 | 163.34 | 163.34
197 | Chinpai Piped Water Supply Scheme. (SM/18462) | SM/18462 | 1443.97 | 3866 | NEW | 9 | Delayed | 34 | 20/07/2023 | 31/07/2025 | 05/12/2023 | 08/08/2023 | 486.9 | 486.9
198 | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. (SM/13626) | SM/13626 | 478.35 | 1756 | NEW | 9 | Delayed | 34 | 11/11/2022 | 31/12/2024 | 26/09/2024 | 25/04/2023 | 162.72 | 162.72
199 | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. (SM/14424) | SM/14424 | 1516.41 | 3204 | NEW | 9 | Delayed | 19 | 20/01/2023 | 31/01/2025 | 28/05/2024 | 10/08/2023 | 281.08 | 260.03
200 | Barshal piped water supply scheme. (SM/14535) | SM/14535 | 1768.83 | 4730 | NEW | 9 | Delayed | 24 | 30/01/2023 | 30/01/2025 | 09/09/2024 | 10/08/2023 | 419.19 | 419.19
201 | Bidhyadharpur Piped Water Supply Scheme. (SM/13708) | SM/13708 | 621.16 | 1761 | NEW | 9 | Delayed | 6 | 14/11/2022 | 31/12/2024 | 27/09/2024 | 10/08/2023 | 39.65 | 39.65
202 | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13653) | SM/13653 | 537.6 | 1126 | NEW | 9 | Delayed | 20 | 11/11/2022 | 31/12/2024 | 22/03/2024 | 07/11/2023 | 109.58 | 109.58
203 | Chakpara piped water supply scheme. (SM/13638) | SM/13638 | 640.93 | 1721 | NEW | 9 | Delayed | 21 | 11/11/2022 | 31/12/2024 | 11/09/2024 | 10/08/2023 | 134.35 | 134.35
204 | PURBA SIUR PIPED WATER SUPPLY SCHEME. (SM/12598) | SM/12598 | 497.79 | 1464 | NEW | 9 | Delayed | 16 | 15/09/2022 | 31/12/2024 | 14/06/2024 | 12/07/2023 | 79.2 | 79.2
205 | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. (SM/14744) | SM/14744 | 907.13 | 4098 | AUGMENTATION | 9 | Delayed | 33 | 31/01/2023 | 31/05/2024 | 27/09/2023 | 24/07/2023 | 299.65 | 299.65
206 | Loba Piped Water Supply Scheme. (SM/18511) | SM/18511 | 2382.48 | 5713 | NEW | 9 | Delayed | 24 | 26/07/2023 | 26/07/2025 | 10/09/2024 | 08/08/2023 | 563.37 | 563.37
207 | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division (SM/13982) | SM/13982 | 698.94 | 1488 | NEW | 10 | Delayed | 9 | 01/12/2022 | 31/12/2024 | 09/08/2024 | 10/08/2023 | 61.72 | 61.72
208 | MASTALI PIPED WATER SUPPLY SCHEME (SM/16275) | SM/16275 | 486.59 | 696 | NEW | 10 | Delayed | 27 | 23/02/2023 | 31/12/2025 | 13/08/2024 | 29/04/2022 | 132.1 | 67.77
209 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. (SM/12662) | SM/12662 | 42.93 | 826 | RETROFITTING | 10 | Delayed | 18 | 19/09/2022 | 31/01/2024 | 25/01/2024 | 02/05/2023 | 7.57 | 7.57
210 | NETURI PIPED WATER SUPPLY SCHEME. (SM/12656) | SM/12656 | 496.1 | 2138 | NEW | 10 | Delayed | 77 | 19/09/2022 | 30/11/2024 | 01/08/2024 | 04/11/2022 | 381.96 | 381.96
211 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. (SM/08896) | SM/08896 | 206.23 | 3305 | RETROFITTING | 10 | Delayed | 51 | 29/09/2021 | 31/12/2024 | 11/12/2023 | 03/11/2021 | 105.58 | 105.58
212 | Dakshin Kasila Piped Water Supply Scheme. (SM/12686) | SM/12686 | 909.45 | 2600 | NEW | 10 | Delayed | 5 | 21/09/2022 | 31/12/2024 | 16/05/2024 | 25/04/2023 | 43.58 | 43.58
213 | Amlachaturi Piped Water Supply Scheme (SM/16387) | SM/16387 | 904.87 | 1427 | NEW | 10 | Delayed | 26 | 28/02/2023 | 29/11/2024 | 19/07/2024 | 10/08/2023 | 237.74 | 237.74
214 | HATKALUA PIPED WATER SUPPLY SCHEME (SM/14115) | SM/14115 | 674.17 | 1845 | NEW | 10 | Delayed | 16 | 02/01/2023 | 31/12/2024 | 14/11/2024 | 06/04/2023 | 107.48 | 70.17
215 | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division (SM/09559) | SM/09559 | 416.43 | 0 | ANGANWADI | 10 | Delayed | 0 | 17/11/2021 | 12/06/2024 | 11/12/2023 | 23/08/2021 | 0 | 0
216 | Beloa Piped Water Supply Scheme (SM/18522) | SM/18522 | 1076.07 | 3051 | NEW | 10 | Delayed | 31 | 26/07/2023 | 31/10/2025 | 04/01/2024 | 02/08/2023 | 338.91 | 338.91
217 | Behira and Adjoining Mouzas PWSS (SM/12456) | SM/12456 | 313.84 | 841 | NEW | 10 | Delayed | 27 | 13/09/2022 | 31/12/2024 | 28/11/2024 | 25/04/2023 | 84.41 | 74.3
218 | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/14208) | SM/14208 | 407.65 | 851 | NEW | 11 | Delayed | 4 | 10/01/2023 | 31/12/2024 | 25/06/2024 | 10/08/2023 | 17.65 | 17.65
219 | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district (SM/18510) | SM/18510 | 1188.4 | 2733 | NEW | 11 | Delayed | 7 | 26/07/2023 | 31/08/2025 | 14/06/2024 | 10/08/2023 | 83.37 | 83.37
220 | PURBA BANKATI PIPED WATER SUPPLY SCHEME. (SM/13470) | SM/13470 | 178.79 | 358 | NEW | 11 | Delayed | 67 | 02/11/2022 | 31/12/2024 | 19/01/2024 | 01/03/2023 | 120.09 | 107.01
221 | Gulalgachi Piped Supply Scheme (SM/18419) | SM/18419 | 1267.58 | 3333 | NEW | 11 | Delayed | 54 | 18/07/2023 | 31/08/2025 | 08/04/2024 | 10/08/2023 | 688.24 | 688.24
222 | Shaspur Piped Water Supply Scheme. (SM/13651) | SM/13651 | 794.81 | 1371 | NEW | 11 | Delayed | 23 | 11/11/2022 | 30/09/2024 | 28/05/2024 | 11/08/2023 | 180.86 | 180.86
223 | Kanaipur piped water supply scheme. (SM/13640) | SM/13640 | 801.2 | 2508 | NEW | 11 | Delayed | 32 | 11/11/2022 | 31/10/2024 | 06/12/2023 | 26/07/2023 | 256.67 | 256.67
224 | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT (SM/18489) | SM/18489 | 814.18 | 2006 | NEW | 11 | Delayed | 11 | 24/07/2023 | 28/02/2025 | 30/08/2024 | 07/11/2023 | 93.5 | 73.58
225 | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division (SM/18521) | SM/18521 | 1043.88 | 2325 | NEW | 11 | Delayed | 34 | 26/07/2023 | 31/12/2025 | 28/05/2024 | 10/08/2023 | 356.61 | 356.61
226 | Chandrapur Piped Water Supply Scheme (SM/14893) | SM/14893 | 653.22 | 1003 | NEW | 12 | Delayed | 67 | 04/02/2023 | 31/12/2024 | 02/02/2024 | 06/04/2023 | 437.93 | 437.93
227 | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division (SM/14119) | SM/14119 | 399.02 | 869 | NEW | 12 | Delayed | 36 | 02/01/2023 | 31/10/2024 | 05/12/2023 | 31/05/2023 | 143.76 | 143.76
228 | KAMARDANGAL PIPED WATER SUPPLY SCHEME. (SM/12675) | SM/12675 | 238.09 | 652 | NEW | 12 | Delayed | 49 | 19/09/2022 | 31/01/2025 | 12/04/2024 | 21/03/2023 | 116.91 | 116.91
229 | DELORA PIPED WATER SUPPLY SCHEME (SM/13600) | SM/13600 | 388.22 | 863 | NEW | 12 | Delayed | 15 | 09/11/2022 | 28/02/2025 | 24/07/2024 | 12/04/2023 | 58.33 | 38.51
230 | Prasadpur Piped Water Supply Scheme (SM/13478) | SM/13478 | 833.6 | 2277 | NEW | 12 | Delayed | 29 | 02/11/2022 | 31/12/2024 | 10/01/2024 | 26/07/2023 | 244.53 | 244.53
231 | Shankarpur Piped Water Scheme (SM/14082) | SM/14082 | 717.8 | 1071 | NEW | 13 | Delayed | 32 | 12/12/2022 | 31/12/2024 | 07/02/2024 | 06/04/2023 | 227.71 | 227.71
232 | Paniara Piped Water Supply Scheme. (SM/12907) | SM/12907 | 124.83 | 497 | NEW | 13 | Delayed | 23 | 22/09/2022 | 31/12/2024 | 09/02/2024 | 10/08/2023 | 28.11 | 28.11
233 | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION (SM/18513) | SM/18513 | 1122.66 | 2393 | NEW | 13 | Delayed | 13 | 26/07/2023 | 31/10/2025 | 28/05/2024 | 10/08/2023 | 143.13 | 143.13
234 | BILASPUR PIPED WATER SUPPLY SCHEME. (SM/12594) | SM/12594 | 862.54 | 2738 | NEW | 13 | Delayed | 13 | 15/09/2022 | 31/12/2024 | 10/01/2024 | 14/07/2023 | 109.4 | 109.4
235 | Paschim Naopara and Adjoining Mouzas PWSS (SM/12458) | SM/12458 | 466.85 | 1347 | NEW | 13 | Delayed | 76 | 13/09/2022 | 31/05/2024 | 18/01/2024 | 12/07/2023 | 352.82 | 352.82
236 | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT (SM/14676) | SM/14676 | 435.64 | 665 | NEW | 13 | Delayed | 41 | 31/01/2023 | 31/12/2024 | 28/05/2024 | 08/06/2023 | 177.5 | 177.5
237 | Dadpur Piped Water Supply Scheme. (SM/12684) | SM/12684 | 593.51 | 1487 | NEW | 14 | Delayed | 41 | 21/09/2022 | 31/12/2024 | 01/02/2024 | 16/03/2023 | 246.02 | 246.02
238 | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. (SM/12591) | SM/12591 | 544.87 | 1573 | NEW | 14 | Delayed | 37 | 15/09/2022 | 31/12/2024 | 10/01/2024 | 12/04/2023 | 202.6 | 158.83
239 | Kurumsaha Piped Water Supply Scheme. (SM/13628) | SM/13628 | 301.71 | 896 | NEW | 14 | Delayed | 63 | 11/11/2022 | 30/11/2024 | 08/07/2024 | 17/04/2023 | 190.32 | 190.32
240 | BHEJENA PIPED WATER SUPPLY SCHEME. (SM/12833) | SM/12833 | 244.52 | 528 | NEW | 14 | Delayed | 53 | 22/09/2022 | 31/12/2024 | 14/06/2024 | 05/06/2023 | 130.2 | 110.3
241 | Kachujore Piped Water Supply Scheme. (SM/13016) | SM/13016 | 173.49 | 354 | NEW | 14 | Delayed | 60 | 28/09/2022 | 31/12/2024 | 25/01/2024 | 06/04/2023 | 104.18 | 104.18
242 | Mostala Piped Water Supply Scheme. (SM/18519) | SM/18519 | 1209.99 | 3889 | NEW | 14 | Delayed | 30 | 26/07/2023 | 31/08/2025 | 28/11/2023 | 10/08/2023 | 364.07 | 364.07
243 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR KATUNIA AND OTHER 2 NOS. MOUZAS UNDER MD. BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11909) | SM/11909 | 102 | 112 | NEW | 15 | Delayed | 79 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 80.27 | 80.27
244 | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. (SM/18787) | SM/18787 | 880.39 | 2363 | AUGMENTATION | 15 | Delayed | 15 | 29/08/2023 | 31/12/2024 | 19/07/2024 | 03/01/2024 | 133.92 | 133.92
245 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BABUPUR AND OTHER 5 NOS. MOUZAS UNDER SURI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11899) | SM/11899 | 222 | 314 | NEW | 15 | Delayed | 91 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 201.54 | 201.54
246 | Ikshudhara piped water supply scheme. (SM/13639) | SM/13639 | 997.9 | 2543 | NEW | 16 | Delayed | 63 | 11/11/2022 | 30/08/2024 | 06/12/2023 | 10/08/2023 | 624.22 | 546.09
247 | RAGHABPUR PIPED WATER SUPPLY SCHEME (SM/14747) | SM/14747 | 379.11 | 575 | NEW | 16 | Delayed | 16 | 31/01/2023 | 31/12/2024 | 27/09/2024 | 22/03/2023 | 60.44 | 60.44
248 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GANUTIA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11903) | SM/11903 | 849 | 2136 | NEW | 16 | Delayed | 56 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 477.44 | 477.44
249 | Khamedda Piped Water Supply Scheme (SM/13980) | SM/13980 | 737.11 | 2017 | NEW | 17 | Delayed | 6 | 01/12/2022 | 30/06/2024 | 28/05/2024 | 10/08/2023 | 42.12 | 37.55
250 | Rajpur Piped Water Supply Scheme (SM/14026) | SM/14026 | 732.55 | 1269 | NEW | 17 | Delayed | 21 | 05/12/2022 | 31/12/2024 | 09/05/2024 | 20/04/2023 | 154.34 | 154.34
251 | BHALIAN PIPED WATER SUPPLY SCHME. (SM/12834) | SM/12834 | 573.21 | 2093 | NEW | 17 | Delayed | 29 | 22/09/2022 | 31/12/2024 | 08/02/2024 | 17/04/2023 | 167.51 | 167.51
252 | Augmentation of Nagari Piped Water Supply Scheme (SM/10312) | SM/10312 | 272.8 | 969 | AUGMENTATION | 18 | Delayed | 63 | 04/03/2022 | 28/03/2024 | 11/10/2023 | 11/01/2023 | 172.28 | 166.04
253 | Monoharpur Piped Water Supply Scheme. (SM/13511) | SM/13511 | 391.63 | 835 | NEW | 18 | Delayed | 12 | 02/11/2022 | 16/07/2025 | 29/10/2024 | 10/08/2023 | 48.91 | 48.91
254 | Kamarkhul Piped Water Supply Scheme. (SM/12693) | SM/12693 | 766.32 | 2268 | NEW | 18 | Delayed | 6 | 21/09/2022 | 31/05/2024 | 11/01/2024 | 10/08/2023 | 46.98 | 46.98
255 | MAJHKALITHA PIPED WATER SUPPLY SCHEME. (SM/12838) | SM/12838 | 999.45 | 3063 | NEW | 18 | Delayed | 23 | 22/09/2022 | 30/05/2025 | 18/01/2024 | 20/04/2023 | 229.03 | 180.76
256 | JOGAI PIPED WATER SUPPLY SCHEME. (SM/12593) | SM/12593 | 514.78 | 1521 | NEW | 19 | Delayed | 39 | 15/09/2022 | 31/03/2025 | 10/01/2024 | 19/04/2023 | 202.26 | 111.74
257 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BAMUNDIHA AND OTHER 14 NOS. MOUZAS UNDER MD BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12068) | SM/12068 | 541 | 900 | NEW | 19 | Delayed | 40 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 214.04 | 214.04
258 | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/13710) | SM/13710 | 979.98 | 2004 | NEW | 19 | Delayed | 50 | 14/11/2022 | 31/12/2024 | 28/05/2024 | 14/07/2023 | 487.03 | 487.03
259 | Madhupur Water Supply Scheme (SM/13644) | SM/13644 | 676.32 | 1359 | NEW | 19 | Delayed | 11 | 11/11/2022 | 30/11/2024 | 30/05/2024 | 10/08/2023 | 74.93 | 74.93
260 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11905) | SM/11905 | 458 | 2693 | NEW | 19 | Delayed | 73 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 335.84 | 335.84
261 | Simgram Piped Water Supply Scheme. (SM/12908) | SM/12908 | 125.88 | 399 | NEW | 20 | Delayed | 52 | 22/09/2022 | 29/11/2024 | 16/05/2024 | 12/05/2023 | 65.82 | 65.82
262 | Gaytha Piped Water Supply Scheme (SM/13712) | SM/13712 | 533.16 | 1164 | NEW | 20 | Delayed | 32 | 14/11/2022 | 30/09/2024 | 28/05/2024 | 19/04/2023 | 169.77 | 49.8
263 | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME (SM/13516) | SM/13516 | 288.36 | 239 | NEW | 20 | Delayed | 29 | 02/11/2022 | 31/12/2024 | 19/09/2024 | 15/03/2022 | 84.71 | 83.16
264 | MATIARA PIPED WATER SUPPLY SCHEME. (SM/12674) | SM/12674 | 386.92 | 1248 | NEW | 21 | Delayed | 9 | 19/09/2022 | 30/09/2024 | 08/07/2024 | 17/04/2023 | 36.07 | 36.07
265 | Patalpur Piped Water Supply Scheme (SM/14955) | SM/14955 | 209.38 | 219 | NEW | 21 | Delayed | 2 | 04/02/2023 | 01/06/2025 | 29/11/2024 | 03/10/2023 | 4.68 | 0
266 | JIJIGRAM PIPED WATER SUPPLY SCHEME. (SM/12837) | SM/12837 | 900.37 | 2677 | NEW | 22 | Delayed | 56 | 22/09/2022 | 31/05/2024 | 29/11/2023 | 14/07/2023 | 503.35 | 503.35
267 | Kendangal Piped Water Supply Scheme. (SM/13642) | SM/13642 | 620.79 | 1921 | NEW | 22 | Delayed | 20 | 11/11/2022 | 16/07/2025 | 27/09/2024 | 10/08/2023 | 123.88 | 67.99
268 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMDAHARA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11902) | SM/11902 | 754 | 4302 | NEW | 23 | Delayed | 68 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 514.07 | 514.07
269 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12070) | SM/12070 | 901 | 2220 | NEW | 23 | Delayed | 69 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 623.54 | 623.54
270 | Palsa piped water supply scheme. (SM/12906) | SM/12906 | 549.14 | 1387 | NEW | 23 | Delayed | 23 | 22/09/2022 | 31/12/2024 | 01/02/2024 | 02/05/2023 | 123.86 | 92.91
271 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR TALA AND OTHER 25 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14039) | SM/14039 | 974.91 | 1554 | NEW | 23 | Delayed | 37 | 12/12/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 361.68 | 361.68
272 | Dhamara Piped Water Supply Scheme. (SM/14898) | SM/14898 | 471.2 | 1473 | NEW | 25 | Delayed | 46 | 04/02/2023 | 04/08/2024 | 03/10/2023 | 17/04/2023 | 215.32 | 177.32
273 | RAUTARA PIPED WATER SUPPLY SCHEME. (SM/12888) | SM/12888 | 247.15 | 835 | NEW | 26 | Delayed | 53 | 23/09/2022 | 23/03/2024 | 03/10/2023 | 22/03/2023 | 130.82 | 130.82
274 | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte (SM/18425) | SM/18425 | 4901.98 | 16046 | NEW | 26 | Delayed | 57 | 18/07/2023 | 30/09/2025 | 14/06/2024 | 03/10/2023 | 2793.56 | 2793.56
275 | Madhura and Adjoining mouzas PWSS (SM/12671) | SM/12671 | 780.79 | 1985 | NEW | 27 | Delayed | 53 | 19/09/2022 | 30/04/2025 | 18/01/2024 | 12/04/2023 | 410.46 | 323.14
276 | KOGRAM PIPED WATER SUPPLY SCHEME. (SM/12894) | SM/12894 | 721.43 | 2150 | NEW | 27 | Delayed | 47 | 23/09/2022 | 31/12/2024 | 10/01/2024 | 31/03/2023 | 340.01 | 340.01
277 | Atkulia Piped Water Supply Scheme (SM/18301) | SM/18301 | 1007.63 | 2807 | NEW | 27 | Delayed | 39 | 26/06/2023 | 26/06/2025 | 04/01/2024 | 25/07/2023 | 395.27 | 348.54
278 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08891) | SM/08891 | 176.25 | 2882 | RETROFITTING | 28 | Delayed | 15 | 29/09/2021 | 31/10/2023 | 04/09/2023 | 13/12/2021 | 26.35 | 26.35
279 | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13476) | SM/13476 | 754.73 | 1639 | NEW | 28 | Delayed | 22 | 02/11/2022 | 31/12/2024 | 29/05/2024 | 10/08/2023 | 164.07 | 164.07
280 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. (SM/12661) | SM/12661 | 43.64 | 700 | RETROFITTING | 30 | Delayed | 73 | 19/09/2022 | 31/03/2024 | 27/09/2023 | 08/06/2023 | 31.68 | 31.68
281 | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. (SM/13475) | SM/13475 | 445.39 | 902 | NEW | 30 | Delayed | 50 | 02/11/2022 | 31/03/2024 | 27/09/2023 | 06/04/2023 | 223.71 | 157.4
282 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. (SM/12657) | SM/12657 | 23.91 | 376 | RETROFITTING | 30 | Delayed | 70 | 19/09/2022 | 31/03/2024 | 28/05/2024 | 08/09/2022 | 16.74 | 16.74
283 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR SIMJURI AND OTHER 19 NOS. MOUZAS UNDER KHOYRASOLE BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12072) | SM/12072 | 712 | 2051 | NEW | 30 | Delayed | 49 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 348.78 | 348.78
284 | Sadanandapur piped water supply scheme. (SM/13648) | SM/13648 | 448.06 | 1233 | NEW | 31 | Delayed | 47 | 11/11/2022 | 11/05/2024 | 03/10/2023 | 06/06/2023 | 212.44 | 212.44
285 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UTTAR BHAGABATIPUR AND OTHER 8 NOS. MOUZAS UNDER MAYURESWAR-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/12071) | SM/12071 | 343 | 571 | NEW | 31 | Delayed | 69 | 02/09/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 237.69 | 237.69
286 | KUSHIPUR PIPES WATER SUPPLY SCHEME. (SM/12599) | SM/12599 | 667.02 | 2414 | NEW | 31 | Delayed | 41 | 15/09/2022 | 31/01/2025 | 08/04/2024 | 31/03/2023 | 275.92 | 275.92
287 | KANAIPUR and Adjoining Mouzas PWSS (SM/12672) | SM/12672 | 844.4 | 2303 | NEW | 31 | Delayed | 48 | 19/09/2022 | 30/04/2025 | 18/01/2024 | 20/04/2023 | 401.95 | 343.88
288 | Khanpur Piped Water Supply Scheme. (SM/14085) | SM/14085 | 846.77 | 2489 | NEW | 31 | Delayed | 25 | 12/12/2022 | 31/12/2024 | 29/02/2024 | 20/04/2023 | 208.41 | 208.3
289 | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division (SM/14088) | SM/14088 | 913.88 | 2095 | NEW | 32 | Delayed | 27 | 12/12/2022 | 31/12/2024 | 18/09/2024 | 10/08/2023 | 243.41 | 243.41
290 | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. (SM/12595) | SM/12595 | 886.16 | 3542 | NEW | 32 | Delayed | 21 | 15/09/2022 | 31/07/2024 | 10/01/2024 | 25/08/2023 | 189.37 | 189.37
291 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR PARKANDI AND OTHER 7 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11935) | SM/11935 | 313 | 483 | NEW | 33 | Delayed | 60 | 24/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 186.46 | 186.46
292 | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. (SM/13983) | SM/13983 | 447.36 | 588 | NEW | 34 | Delayed | 45 | 01/12/2022 | 31/03/2024 | 27/09/2023 | 27/02/2023 | 201.74 | 201.74
293 | Kulara Piped Water Supply Scheme. (SM/12695) | SM/12695 | 481.59 | 2968 | NEW | 34 | Delayed | 38 | 21/09/2022 | 30/09/2024 | 10/01/2024 | 06/04/2023 | 181.49 | 181.49
294 | KANIOR PIPED WATER SUPPLY SCHEME. (SM/12831) | SM/12831 | 600.79 | 1819 | NEW | 37 | Delayed | 52 | 22/09/2022 | 31/12/2024 | 04/01/2024 | 31/03/2023 | 313.1 | 313.1
295 | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division (SM/13630) | SM/13630 | 903.87 | 2008 | NEW | 37 | Delayed | 43 | 11/11/2022 | 31/12/2024 | 29/05/2024 | 10/08/2023 | 386.36 | 386.36
296 | PAIKPARA WATER SUPPLY SCHEME. (SM/12836) | SM/12836 | 924.31 | 2727 | NEW | 37 | Delayed | 39 | 22/09/2022 | 31/03/2025 | 18/01/2024 | 12/04/2023 | 362.29 | 321.61
297 | Mahurapur and Adjoining Mouzas PWSS (SM/12697) | SM/12697 | 1066.63 | 3051 | NEW | 37 | Delayed | 12 | 21/09/2022 | 30/11/2025 | 17/12/2024 | 25/04/2023 | 128.15 | 71.31
298 | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District (SM/14016) | SM/14016 | 191.26 | 656 | NEW | 38 | Delayed | 56 | 05/12/2022 | 31/03/2024 | 27/09/2023 | 06/12/2022 | 106.99 | 106.99
299 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/14037) | SM/14037 | 831.2 | 1376 | NEW | 40 | Delayed | 31 | 12/12/2022 | 31/10/2024 | 11/12/2023 | 28/11/2022 | 259.74 | 259.74
300 | Asenga Piped Water Supply Scheme. (SM/12680) | SM/12680 | 617.4 | 2144 | NEW | 40 | Delayed | 63 | 20/09/2022 | 31/08/2024 | 11/10/2023 | 20/04/2023 | 389.17 | 324.75
301 | PARKUTA PIPED WATER SUPPLY SCHEME (SM/14959) | SM/14959 | 271.5 | 8299 | NEW | 41 | Delayed | 54 | 04/02/2023 | 04/08/2024 | 28/05/2024 | 20/04/2023 | 146.82 | 146.82
302 | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division (SM/14160) | SM/14160 | 1185.64 | 2646 | NEW | 41 | Delayed | 17 | 05/01/2023 | 31/01/2025 | 28/05/2024 | 08/06/2023 | 199.43 | 181.62
303 | Banhat Piped Water Supply Scheme. (SM/14029) | SM/14029 | 484.07 | 2002 | NEW | 41 | Delayed | 58 | 05/12/2022 | 31/10/2024 | 06/12/2023 | 22/03/2023 | 281.12 | 244.58
304 | Shitalgram Piped Water Supply Scheme (SM/14087) | SM/14087 | 585.33 | 1460 | NEW | 42 | Delayed | 42 | 12/12/2022 | 31/12/2024 | 04/01/2024 | 25/07/2023 | 247.49 | 219.51
305 | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division (SM/10320) | SM/10320 | 7907.91 | 31155 | AUGMENTATION | 42 | Delayed | 45 | 07/03/2022 | 31/12/2024 | 07/03/2024 | 17/03/2022 | 3545.4 | 3211.75
306 | Kamdebnala piped water supply scheme. (SM/12694) | SM/12694 | 476.19 | 1188 | NEW | 43 | Delayed | 33 | 21/09/2022 | 31/01/2025 | 07/02/2024 | 19/04/2023 | 157.5 | 157.5
307 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Danghara (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12665) | SM/12665 | 17.6 | 272 | RETROFITTING | 45 | WO no issued | 0 | 19/09/2022 | 31/03/2024 | 04/01/2024 |  | 0 | 0
308 | Augmentation of Ahmedpur Piped Water Supply Scheme (SM/10313) | SM/10313 | 766.3 | 4884 | AUGMENTATION | 46 | Delayed | 62 | 04/03/2022 | 13/02/2024 | 30/06/2023 | 23/05/2022 | 472.95 | 472.95
309 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme (SM/12664) | SM/12664 | 58.66 | 909 | RETROFITTING | 48 | Delayed | 97 | 19/09/2022 | 30/09/2023 | 26/07/2023 | 14/12/2022 | 56.95 | 56.95
310 | Augmentation of Purandarpur Piped Water Supply Scheme (SM/09437) | SM/09437 | 679.4 | 3060 | AUGMENTATION | 50 | Delayed | 87 | 12/11/2021 | 08/02/2024 | 30/06/2023 | 24/06/2020 | 591.25 | 552.81
311 | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. (SM/16373) | SM/16373 | 751.53 | 1577 | NEW | 50 | Delayed | 41 | 28/02/2023 | 31/12/2024 | 28/05/2024 | 22/03/2023 | 305.84 | 305.84
312 | CHAUTI PIPED WATER SUPPLY SCHEME. (SM/12835) | SM/12835 | 574.46 | 1647 | NEW | 50 | Delayed | 39 | 22/09/2022 | 31/12/2024 | 27/03/2024 | 01/03/2023 | 224.35 | 224.35
313 | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. (SM/12659) | SM/12659 | 149.48 | 2304 | RETROFITTING | 50 | Delayed | 28 | 19/09/2022 | 31/03/2024 | 28/05/2024 | 03/08/2023 | 42.41 | 41.29
314 | ANDHARGRAM PIPED WATER SUPPLY SCHEME. (SM/12676) | SM/12676 | 300.02 | 2082 | NEW | 52 | Delayed | 83 | 19/09/2022 | 30/08/2024 | 06/12/2023 | 12/04/2023 | 249.99 | 249.99
315 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR NISHPARUN AND OTHER 4 NOS. MOUZAS UNDER RAMPURHAT-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11901) | SM/11901 | 206 | 1631 | NEW | 53 | Delayed | 51 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 104.19 | 104.19
316 | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT (SM/14894) | SM/14894 | 326.46 | 401 | NEW | 53 | Delayed | 58 | 04/02/2023 | 04/08/2024 | 27/09/2023 | 22/03/2023 | 189.87 | 151.07
317 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/12666) | SM/12666 | 99.4 | 1404 | RETROFITTING | 56 | Delayed | 19 | 19/09/2022 | 20/02/2024 | 10/01/2024 | 01/04/2022 | 18.79 | 18.79
318 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11936) | SM/11936 | 394 | 577 | NEW | 57 | Delayed | 80 | 24/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 316.98 | 316.98
319 | DERPUR PIPED WATER SUPPLY SCHEME. (SM/12832) | SM/12832 | 477.52 | 2033 | NEW | 58 | Delayed | 72 | 22/09/2022 | 31/12/2023 | 22/09/2023 | 29/11/2022 | 345.09 | 345.09
320 | Moubelia Piped Water Supply Scheme. (SM/14899) | SM/14899 | 409.66 | 742 | NEW | 58 | Delayed | 69 | 04/02/2023 | 31/12/2024 | 06/12/2023 | 12/04/2023 | 281.22 | 251.22
321 | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. (SM/09341) | SM/09341 | 896.76 | 13825 | RETROFITTING | 60 | Delayed | 11 | 12/11/2021 | 30/11/2024 | 04/09/2024 | 07/12/2021 | 98.34 | 88.45
322 | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. (SM/09363) | SM/09363 | 188.82 | 2910 | RETROFITTING | 60 | Delayed | 28 | 12/11/2021 | 31/12/2023 | 27/09/2023 | 02/05/2022 | 51.97 | 51.97
323 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. (SM/11900) | SM/11900 | 448 | 1209 | NEW | 61 | Delayed | 57 | 22/08/2022 | 31/12/2024 | 11/12/2023 | 28/11/2022 | 256.76 | 256.36
324 | Augmentation of Tejhati PWSS (SM/10166) | SM/10166 | 367.8 | 1953 | AUGMENTATION | 61 | Delayed | 69 | 11/02/2022 | 31/12/2024 | 04/01/2024 | 10/08/2021 | 255.52 | 243.8
325 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme (SM/10665) | SM/10665 | 58.24 | 903 | RETROFITTING | 65 | Delayed | 97 | 22/04/2022 | 28/02/2023 | 12/06/2023 | 21/09/2022 | 56.54 | 56.54
326 | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division (SM/10321) | SM/10321 | 6683.63 | 28764 | AUGMENTATION | 69 | Delayed | 64 | 07/03/2022 | 05/02/2024 | 28/05/2024 | 03/11/2021 | 4293.13 | 4276.72
327 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS (SM/07648) | SM/07648 | 99.48 | 1750 | RETROFITTING | 70 | Delayed | 76 | 07/01/2021 | 12/06/2024 | 11/12/2023 | 13/04/2022 | 75.48 | 75.48
328 | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. (SM/09369) | SM/09369 | 77.81 | 1199 | RETROFITTING | 70 | Delayed | 32 | 12/11/2021 | 13/02/2024 | 30/06/2023 | 07/12/2021 | 25.18 | 25.18
329 | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division (SM/10319) | SM/10319 | 11639.45 | 56246 | AUGMENTATION | 71 | Delayed | 91 | 07/03/2022 | 30/06/2024 | 04/01/2024 | 22/07/2021 | 10554.22 | 10447.27
330 | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09364) | SM/09364 | 234.01 | 3622 | RETROFITTING | 74 | Delayed | 63 | 12/11/2021 | 30/06/2024 | 04/01/2024 | 17/01/2022 | 148.19 | 148.19
331 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. (SM/09792) | SM/09792 | 771.82 | 12114 | RETROFITTING | 75 | Delayed | 52 | 30/11/2021 | 10/02/2024 | 04/09/2023 | 24/06/2020 | 398.74 | 393.74
332 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. (SM/08894) | SM/08894 | 148.29 | 2299 | RETROFITTING | 75 | Delayed | 75 | 29/09/2021 | 10/02/2024 | 30/06/2023 | 14/12/2021 | 111.16 | 111.16
333 | Podda Piped Water Supply Scheme (SM/13714) | SM/13714 | 424.09 | 889 | NEW | 75 | Delayed | 34 | 14/11/2022 | 31/10/2024 | 28/05/2024 | 19/04/2023 | 143.44 | 143.44
334 | Purba Anantapur Piped Water Supply Scheme (SM/13715) | SM/13715 | 586.12 | 2388 | NEW | 76 | Delayed | 46 | 14/11/2022 | 29/11/2024 | 28/05/2024 | 12/04/2023 | 269.87 | 225.14
335 | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09366) | SM/09366 | 181.79 | 2805 | RETROFITTING | 77 | Delayed | 76 | 12/11/2021 | 12/02/2024 | 23/11/2023 | 22/03/2022 | 137.64 | 137.64
336 | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07154) | SM/07154 | 99.92 | 1510 | RETROFITTING | 80 | Delayed | 84 | 01/12/2020 | 31/12/2023 | 20/07/2023 | 16/08/2021 | 83.72 | 83.72
337 | Augmentation of Panchiara Piped Water Supply Scheme (SM/10314) | SM/10314 | 921.39 | 4179 | AUGMENTATION | 80 | Delayed | 66 | 04/03/2022 | 31/03/2023 | 12/06/2023 | 24/06/2020 | 611.82 | 611.82
338 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum (SM/07530) | SM/07530 | 296.93 | 4984 | RETROFITTING | 80 | Delayed | 96 | 31/12/2020 | 01/02/2024 | 30/06/2023 | 25/01/2022 | 285.55 | 241.52
339 | Dhitora Right side and adjoining mouzas piped water supply scheme. (SM/17633) | SM/17633 | 445.95 | 1276 | NEW | 84 | On track | 43 | 22/03/2023 | 31/03/2025 | 10/01/2024 | 10/04/2023 | 193.25 | 193.25
340 | Augmentation of Mathpalsa Piped Water Supply Scheme (SM/10315) | SM/10315 | 283.04 | 1605 | AUGMENTATION | 84 | Delayed | 70 | 04/03/2022 | 12/02/2024 | 12/10/2023 | 23/05/2022 | 197.62 | 197.62
341 | Augmentation of Khoyrasole Piped Water Supply Scheme (SM/10343) | SM/10343 | 1265.98 | 783 | AUGMENTATION | 85 | Delayed | 73 | 14/03/2022 | 03/02/2024 | 30/06/2023 | 03/03/2022 | 926.83 | 926.83
342 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme (SM/13372) | SM/13372 | 20.61 | 320 | RETROFITTING | 85 | Delayed | 97 | 19/10/2022 | 30/06/2024 | 04/01/2024 | 21/03/2023 | 20.01 | 20.01
343 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) (SM/07006) | SM/07006 | 99.48 | 1393 | RETROFITTING | 85 | Delayed | 95 | 13/11/2020 | 01/02/2024 | 30/06/2023 | 16/11/2021 | 94.77 | 94.77
344 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum (SM/07532) | SM/07532 | 179.67 | 2702 | RETROFITTING | 85 | Delayed | 88 | 31/12/2020 | 30/06/2023 | 30/06/2023 | 09/02/2022 | 157.86 | 156.89
345 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sadasibpur (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (SM/13373) | SM/13373 | 13.41 | 207 | RETROFITTING | 85 | WO no issued | 0 | 19/10/2022 | 20/02/2024 | 10/01/2024 | 22/12/2022 | 0 | 0
346 | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09370) | SM/09370 | 145.06 | 2238 | RETROFITTING | 88 | Delayed | 68 | 12/11/2021 | 30/06/2024 | 04/01/2024 | 09/03/2022 | 98.55 | 98.55
347 | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. (SM/09362) | SM/09362 | 259.6 | 4002 | RETROFITTING | 90 | Delayed | 57 | 12/11/2021 | 28/02/2023 | 12/06/2023 | 10/03/2022 | 148.62 | 148.62
348 | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09367) | SM/09367 | 453.12 | 6979 | RETROFITTING | 90 | Delayed | 59 | 12/11/2021 | 03/03/2024 | 27/09/2023 | 24/06/2020 | 266.71 | 266.71
349 | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. (SM/09438) | SM/09438 | 762.27 | 3546 | AUGMENTATION | 90 | Delayed | 72 | 29/10/2021 | 31/03/2023 | 12/06/2023 | 24/06/2020 | 550.61 | 550.61
350 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) (SM/07647) | SM/07647 | 64.73 | 1050 | RETROFITTING | 90 | Delayed | 6 | 07/01/2021 | 30/03/2024 | 20/07/2023 | 28/07/2023 | 4.15 | 3.36
351 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block (SM/07651) | SM/07651 | 99.95 | 1760 | RETROFITTING | 90 | Delayed | 97 | 07/01/2021 | 30/11/2022 | 12/06/2023 | 15/06/2021 | 97.04 | 97.04
352 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) (SM/06732) | SM/06732 | 99.79 | 777 | RETROFITTING | 90 | Delayed | 93 | 18/09/2020 | 31/10/2022 | 12/06/2023 | 07/07/2021 | 92.81 | 92.81
353 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme (SM/12658) | SM/12658 | 13.68 | 211 | RETROFITTING | 90 | Delayed | 0 | 19/09/2022 | 15/02/2024 | 10/01/2024 | 20/04/2023 | 0 | 0
354 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block (SM/08286) | SM/08286 | 865 | 14748 | RETROFITTING | 90 | Delayed | 94 | 09/02/2021 | 31/03/2023 | 12/06/2023 | 28/10/2021 | 811.49 | 802.87
355 | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. (SM/09491) | SM/09491 | 149.02 | 2295 | RETROFITTING | 91 | Delayed | 72 | 19/11/2021 | 15/02/2024 | 10/01/2024 | 17/12/2021 | 107.1 | 107.1
356 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) (SM/06735) | SM/06735 | 99.99 | 1860 | RETROFITTING | 92 | Delayed | 89 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 01/10/2020 | 89.34 | 94.11
357 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum (SM/08171) | SM/08171 | 97.14 | 1525 | RETROFITTING | 95 | Delayed | 85 | 08/02/2021 | 31/12/2023 | 27/09/2023 | 04/01/2022 | 82.11 | 82.11
358 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS (SM/06736) | SM/06736 | 99.68 | 1265 | RETROFITTING | 95 | Delayed | 85 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 15/06/2021 | 85.19 | 85.19
359 | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07153) | SM/07153 | 99.72 | 1408 | RETROFITTING | 96 | Delayed | 77 | 01/12/2020 | 31/03/2024 | 27/09/2023 | 23/12/2020 | 76.43 | 76.43
360 | BANGJITA PIPED WATER SUPPLY SCHEME. (SM/12829) | SM/12829 | 489.13 | 1717 | NEW | 96 | On track | 12 | 22/09/2022 | 31/12/2024 | 15/02/2024 | 17/04/2023 | 59.38 | 53.1
361 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. (SM/08898) | SM/08898 | 147.83 | 2377 | RETROFITTING | 96 | Delayed | 58 | 29/09/2021 | 31/12/2023 | 27/09/2023 | 29/10/2021 | 85.77 | 85.77
362 | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. (SM/09368) | SM/09368 | 68.35 | 1054 | RETROFITTING | 96 | Delayed | 88 | 12/11/2021 | 30/09/2023 | 27/09/2023 | 04/01/2022 | 60.36 | 60.36
363 | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area (SM/06944) | SM/06944 | 97.37 | 1500 | RETROFITTING | 99 | Delayed | 97 | 03/11/2020 | 30/09/2023 | 10/09/2023 | 25/10/2021 | 94.53 | 41.82
364 | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area (SM/06947) | SM/06947 | 99.28 | 1520 | RETROFITTING | 99 | Delayed | 95 | 03/11/2020 | 30/09/2023 | 10/09/2023 | 13/01/2021 | 94.25 | 89.96
365 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08895) | SM/08895 | 94.58 | 1500 | RETROFITTING | 99 | Delayed | 45 | 29/09/2021 | 30/09/2023 | 10/09/2023 | 13/12/2021 | 42.31 | 42.31
366 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. (SM/08897) | SM/08897 | 109.18 | 1682 | RETROFITTING | 99 | Delayed | 83 | 29/09/2021 | 31/01/2023 | 12/06/2023 | 07/10/2021 | 91.01 | 91.01
367 | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area (SM/06951) | SM/06951 | 72.24 | 1135 | RETROFITTING | 100 | 100% Physical | 74 | 03/11/2020 | 30/06/2023 | 12/06/2023 | 18/08/2021 | 53.11 | 53.11
368 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS (SM/06744) | SM/06744 | 99.59 | 957 | RETROFITTING | 100 | 100% Physical | 95 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 08/02/2021 | 94.19 | 72.99
369 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) (SM/06733) | SM/06733 | 99.93 | 1860 | RETROFITTING | 100 | 100% Physical | 95 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 21/09/2020 | 95.17 | 95.17
370 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. (SM/08893) | SM/08893 | 293.51 | 6050 | RETROFITTING | 100 | 100% Physical | 97 | 29/09/2021 | 30/06/2023 | 12/06/2023 | 29/10/2021 | 284.96 | 284.96
371 | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07155) | SM/07155 | 94.45 | 1290 | RETROFITTING | 100 | 100% Physical | 97 | 01/12/2020 | 30/06/2022 | 12/06/2023 | 26/02/2020 | 91.7 | 91.7
372 | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area (SM/06945) | SM/06945 | 98.81 | 1510 | RETROFITTING | 100 | 100% Physical | 57 | 04/11/2020 | 31/05/2021 | 12/06/2023 | 16/07/2021 | 56.55 | 73.85
373 | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area (SM/06950) | SM/06950 | 99.83 | 1658 | RETROFITTING | 100 | 100% Physical | 97 | 03/11/2020 | 30/11/2022 | 12/06/2023 | 24/11/2021 | 96.92 | 96.92
374 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block (SM/07646) | SM/07646 | 82.04 | 1396 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 31/07/2022 | 12/06/2023 | 26/02/2021 | 79.66 | 79.66
375 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) (SM/06739) | SM/06739 | 96.06 | 1755 | RETROFITTING | 100 | 100% Physical | 93 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 21/09/2020 | 89.61 | 90.4
376 | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area (SM/06949) | SM/06949 | 99.96 | 1530 | RETROFITTING | 100 | 100% Physical | 97 | 03/11/2020 | 30/06/2022 | 12/06/2023 | 16/08/2021 | 97.05 | 97.05
377 | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area (SM/06948) | SM/06948 | 99.22 | 1520 | RETROFITTING | 100 | 100% Physical | 99 | 03/11/2020 | 31/08/2021 | 12/06/2023 | 23/12/2020 | 97.91 | 97.91
378 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) (SM/06737) | SM/06737 | 95.3 | 1752 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 16/07/2021 | 95.3 | 93.59
379 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. (SM/12667) | SM/12667 | 24.91 | 382 | RETROFITTING | 100 | 100% Physical | 78 | 19/09/2022 |  | 12/06/2023 | 17/11/2022 | 19.43 | 19.43
380 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block (SM/07649) | SM/07649 | 99.46 | 1745 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 01/12/2022 | 12/06/2023 | 06/01/2022 | 96.57 | 96.57
381 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS (SM/06734) | SM/06734 | 94.74 | 1645 | RETROFITTING | 100 | 100% Physical | 72 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 04/11/2020 | 68.47 | 68.47
382 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) (SM/06740) | SM/06740 | 99.84 | 1875 | RETROFITTING | 100 | 100% Physical | 96 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 21/09/2020 | 95.63 | 95.63
383 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte (SM/07533) | SM/07533 | 206.39 | 2864 | RETROFITTING | 100 | 100% Physical | 89 | 31/12/2020 | 30/06/2021 | 12/06/2023 | 05/02/2021 | 183.35 | 183.35
384 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme (SM/12663) | SM/12663 | 108.02 | 1465 | RETROFITTING | 100 | 100% Physical | 48 | 19/09/2022 | 31/03/2023 | 12/06/2023 | 06/01/2022 | 51.38 | 51.38
385 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. (SM/13371) | SM/13371 | 33.38 | 392 | RETROFITTING | 100 | 100% Physical | 54 | 19/10/2022 |  | 12/06/2023 | 24/11/2021 | 17.94 | 17.94
386 | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme (SM/07152) | SM/07152 | 65.97 | 851 | RETROFITTING | 100 | 100% Physical | 81 | 01/12/2020 | 30/06/2022 | 12/06/2023 | 21/09/2020 | 53.3 | 53.3
387 | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area (SM/06943) | SM/06943 | 97.5 | 1520 | RETROFITTING | 100 | 100% Physical | 97 | 03/11/2020 | 31/10/2022 | 12/06/2023 | 10/12/2021 | 94.66 | 94.66
388 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) (SM/06743) | SM/06743 | 97.37 | 1760 | RETROFITTING | 100 | 100% Physical | 53 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 16/07/2021 | 52 | 52
389 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum (SM/07531) | SM/07531 | 190.61 | 3113 | RETROFITTING | 100 | 100% Physical | 97 | 31/12/2020 | 30/04/2022 | 12/06/2023 | 11/06/2021 | 185.06 | 185.06
390 | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09371) | SM/09371 | 105.12 | 1622 | RETROFITTING | 100 | 100% Physical | 97 | 12/11/2021 | 31/03/2023 | 20/07/2023 | 07/03/2022 | 102.06 | 102.06
391 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block (SM/07645) | SM/07645 | 93.68 | 1478 | RETROFITTING | 100 | 100% Physical | 69 | 07/01/2021 | 31/10/2022 | 12/06/2023 | 11/01/2021 | 65.01 | 65.01
392 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) (SM/10543) | SM/10543 | 68.88 | 1063 | RETROFITTING | 100 | 100% Physical | 74 | 13/04/2022 | 31/03/2023 | 12/06/2023 | 01/10/2021 | 50.97 | 50.97
393 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) (SM/06741) | SM/06741 | 99.97 | 1860 | RETROFITTING | 100 | 100% Physical | 97 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 05/10/2021 | 97.06 | 93.37
394 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. (SM/08892) | SM/08892 | 96.68 | 1500 | RETROFITTING | 100 | 100% Physical | 75 | 29/09/2021 | 30/11/2022 | 12/06/2023 | 23/09/2021 | 72.23 | 65.98
395 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block (SM/07650) | SM/07650 | 53.59 | 848 | RETROFITTING | 100 | 100% Physical | 95 | 07/01/2021 | 30/04/2022 | 12/06/2023 | 02/09/2021 | 50.84 | 50.84
396 | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. (SM/09365) | SM/09365 | 120.18 | 1851 | RETROFITTING | 100 | 100% Physical | 77 | 12/11/2021 | 31/12/2023 | 27/09/2023 | 04/01/2022 | 92.33 | 92.33
397 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) (SM/06742) | SM/06742 | 98.25 | 1830 | RETROFITTING | 100 | 100% Physical | 58 | 18/09/2020 | 31/12/2021 | 12/06/2023 | 10/12/2021 | 57 | 57
398 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS (SM/06738) | SM/06738 | 99.99 | 1755 | RETROFITTING | 100 | 100% Physical | 97 | 18/09/2020 | 31/05/2021 | 12/06/2023 | 21/09/2020 | 96.79 | 96.79
399 | Preparation of DPR for Drinking Water Supply Schemes within the different blocks of Birbhum District under Birbhum Division, PHE Dte. (SM/18987) | SM/18987 | 559.97 | 0 | SUPPORT DPR & SURVEY | 100 | 100% Physical | 0 | 12/10/2023 |  | 12/10/2023 | 27/12/2021 | 0 | 0
Total |  |  | 256425.5 | 893046 | [8 empty] | 81143.49 | 77590.33