## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME (SM/15556) | SM/15556 | 216.81 | 312 | AUGMENTATION | 0 | WO no issued | 0 | 16/02/2023 | 16/08/2023 | 12/06/2023 | 07/06/2023 | 0 | 0
2 | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. (SM/11284) | SM/11284 | 551.82 | 0 | SCHOOL | 0 | WO no issued | 0 | 28/06/2022 | 31/03/2023 | 05/05/2023 | 12/07/2022 | 0 | 0
3 | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK (SM/15173) | SM/15173 | 287.77 | 0 | AUGMENTATION | 0 | WO no issued | 0 | 07/02/2023 | 07/08/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
4 | PROCUREMENT OF LAND OF TARAPOSH PIPED WATER SUPPLY SCHME KHANDAGHOSH BLOCK, DIST.- PURBA BARDHAMAN VIDE G O NO PHE/2793/IL-26/18 DATED 25/11/2021 OF THE DEPUTY SECRETARY TECHNICAL TO THE GOVERNMENT OF WEST BENGAL (SM/14185) | SM/14185 | 15.88 | 0 | NEW | 0 | WO no issued | 0 | 02/01/2023 | 02/07/2024 | 12/06/2023 |  | 0 | 0
5 | PROCUREMENT OF LAND OF PALASON RAINA-I BLOCK DIST PURBA BARDHAMAN VIDE G O NO PHE/2060/IL-72/19 DATED 01/09/2021 OF THE DEPUTY SECRETARY TECHNICAL TO THE GOVERNMENT OF WEST BENGAL. (SM/14188) | SM/14188 | 28.04 | 0 | NEW | 0 | WO no issued | 0 | 02/01/2023 | 02/07/2024 | 12/06/2023 |  | 0 | 0
6 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II (SM/16014) | SM/16014 | 979.43 | 1000 | AUGMENTATION | 0 | WO no issued | 1 | 21/02/2023 | 21/11/2023 | 12/06/2023 | 07/12/2023 | 6.16 | 0
7 | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME (SM/16193) | SM/16193 | 214.58 | 200 | AUGMENTATION | 0 | WO no issued | 0 | 23/02/2023 | 23/08/2023 | 12/06/2023 | 28/07/2023 | 0 | 0
8 | PROCUREMENT OF LAND OF NANDRA PIPED WATER SUPPLY SCHEME BURDWAN-II BLOCK DIST PURBA BARDHAMAN VIDE G O NO PHE/2061//IL/48/19 DATED 01/09/2021 OF THE DEPUTY SECRETARY TECHNICAL TO THE GOVERNMENT OF WEST BENGAL ADMIN. APPRO.NO. PHE/IV/1823/W-27/2013 DATED 2 (SM/14187) | SM/14187 | 6.98 | 0 | NEW | 0 | WO no issued | 0 | 02/01/2023 | 02/07/2024 | 12/06/2023 |  | 0 | 0
9 | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. (SM/11285) | SM/11285 | 678.43 | 0 | SCHOOL | 0 | WO no issued | 0 | 28/06/2022 | 31/03/2023 | 05/05/2023 | 12/07/2022 | 0 | 0
10 | KARAIL PIPED WATER SUPPLY SCHEME (SM/13498) | SM/13498 | 194.91 | 298 | NEW | 0 | WO no issued | 10 | 02/11/2022 | 02/05/2024 | 12/06/2023 | 29/08/2023 | 19.64 | 19.64
11 | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. (SM/11514) | SM/11514 | 472.45 | 0 | SCHOOL | 0 | WO no issued | 0 | 19/07/2022 | 31/05/2023 | 05/05/2023 | 27/12/2021 | 0 | 0
12 | BERUGRAM PIPED WATER SUPPLY SCHEME (SM/18606) | SM/18606 | 1245.1 | 3294 | NEW | 0 | WO no issued | 5 | 31/07/2023 | 31/07/2025 | 04/08/2023 | 10/08/2023 | 61.99 | 43.18
13 | PROCUREMENT OF LAND OF MADHABPUR JAMALPUR BLOCK DISTRICT PURBA BARDHAMAN VIDE G O NO PHE/2060/IL-72/19 DATED 01/09/2021 OF THE DEPUTY SECRETARY TECHNICAL TO THE GOVERNMENT OF WEST BENGAL (SM/14189) | SM/14189 | 22.22 | 0 | NEW | 0 | WO no issued | 0 | 02/01/2023 | 02/07/2024 | 12/06/2023 |  | 0 | 0
14 | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME (SM/15176) | SM/15176 | 217.82 | 1200 | AUGMENTATION | 0 | WO no issued | 0 | 08/02/2023 | 08/08/2023 | 12/06/2023 | 06/10/2023 | 0 | 0
15 | SULTANPUR PIPED WATER SUPPLY SCHEME (SM/18607) | SM/18607 | 1246.66 | 2849 | NEW | 0 | WO no issued | 0 | 31/07/2023 | 31/07/2025 | 04/08/2023 | 10/08/2023 | 3.49 | 3.49
16 | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. (SM/11993) | SM/11993 | 990 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 01/09/2022 |  | 05/09/2022 | 02/09/2022 | 0 | 0
17 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Barddhaman District. (SM/08992) | SM/08992 | 519.11 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 22/08/2022 | 0 | 0
18 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/08993) | SM/08993 | 32.45 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 07/01/2022 | 0 | 0
19 | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/11857) | SM/11857 | 246.93 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 16/08/2022 |  | 17/08/2022 | 30/06/2021 | 0 | 0
20 | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte (SM/16459) | SM/16459 | 20.77 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 03/03/2023 |  | 06/03/2023 | 04/03/2024 | 0 | 0
21 | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19071) | SM/19071 | 292.79 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 | 28/12/2023 | 0 | 0
22 | IEC Activities related to judicious & safe use of drinking water, water conservation, water quality issues under JJM support activities (SM/19094) | SM/19094 | 137.74 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | WO no issued | 0 | 06/12/2023 |  | 06/12/2023 | 27/02/2024 | 0 | 0
23 | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. (SM/08997) | SM/08997 | 31.48 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 09/11/2020 | 0 | 0
24 | Procurement of Computer and Peripherals for the office use in Central Mechanical Division, Central Mechanical Sub-Division, Bardhaman Mechanical Sub-Division(Drilling) PHE.Dte. (SM/13017) | SM/13017 | 13.58 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 29/09/2022 |  | 06/10/2022 |  | 0 | 0
25 | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT (SM/14441) | SM/14441 | 708 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 20/01/2023 |  | 29/01/2023 | 20/01/2023 | 0 | 0
26 | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission (SM/19072) | SM/19072 | 103.47 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 |  | 0 | 0
27 | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. (SM/09241) | SM/09241 | 16.96 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 03/11/2021 |  | 08/11/2021 | 17/05/2022 | 0 | 0
28 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH (SM/15179) | SM/15179 | 145.55 | 450 | AUGMENTATION | 1 | WO no issued | 0 | 08/02/2023 | 31/12/2024 | 12/07/2023 | 07/06/2023 | 0 | 0
29 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR (SM/15722) | SM/15722 | 92.86 | 0 | AUGMENTATION | 1 | WO no issued | 26 | 20/02/2023 | 31/12/2024 | 12/07/2023 | 19/05/2023 | 24.33 | 24.33
30 | BAKALSA PIPE WATER SUPPLY SCHEME (SM/16030) | SM/16030 | 268.67 | 457 | NEW | 1 | WO no issued | 5 | 21/02/2023 | 21/08/2024 | 15/01/2024 | 29/08/2023 | 12.87 | 12.87
31 | JADABGANJ PIPED WATER SUPPLY SCHEME (SM/13966) | SM/13966 | 849.7 | 1821 | NEW | 2 | WO no issued | 11 | 01/12/2022 | 31/12/2024 | 25/01/2024 | 29/08/2023 | 92.67 | 51.24
32 | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. (SM/13332) | SM/13332 | 996.22 | 3201 | NEW | 2 | WO no issued | 56 | 17/10/2022 | 31/12/2024 | 25/01/2024 | 09/08/2023 | 553.59 | 498.14
33 | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME (SM/14916) | SM/14916 | 809.85 | 1895 | NEW | 2 | WO no issued | 6 | 03/02/2023 | 31/12/2024 | 19/12/2023 | 09/08/2023 | 45.63 | 41.18
34 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL (SM/16489) | SM/16489 | 57.12 | 1075 | RETROFITTING | 2 | WO no issued | 38 | 02/03/2023 | 31/12/2024 | 04/07/2023 | 17/03/2023 | 21.93 | 21.93
35 | ANKHONA PIPED WATER SUPPLY SCHEME (SM/15157) | SM/15157 | 782.97 | 2087 | NEW | 2 | WO no issued | 26 | 08/02/2023 | 31/12/2024 | 07/08/2023 | 03/08/2023 | 201.9 | 201.9
36 | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) (SM/15166) | SM/15166 | 226.46 | 0 | AUGMENTATION | 2 | WO no issued | 20 | 08/02/2023 | 31/12/2024 | 22/08/2023 | 21/03/2023 | 45.22 | 45.22
37 | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME (SM/16017) | SM/16017 | 144.31 | 150 | AUGMENTATION | 2 | WO no issued | 36 | 21/02/2023 | 31/12/2024 | 15/07/2023 | 07/06/2023 | 52.56 | 52.56
38 | AMEGERIA PIPED WATER SUPPLY SCHEME (SM/16023) | SM/16023 | 649.63 | 1863 | NEW | 2 | WO no issued | 2 | 21/02/2023 | 31/12/2024 | 26/09/2023 | 21/08/2023 | 11.48 | 11.48
39 | SHANKRA PIPE WATER SUPPLY SCHEME (SM/16032) | SM/16032 | 470.45 | 1047 | NEW | 2 | WO no issued | 0 | 21/02/2023 | 31/12/2024 | 26/09/2023 | 07/09/2023 | 0 | 0
40 | LOHARUNDI PIPED WATER SUPPLY SCHEME (SM/16033) | SM/16033 | 256.48 | 284 | NEW | 2 | WO no issued | 11 | 21/02/2023 | 31/12/2024 | 05/01/2024 | 29/08/2023 | 27.74 | 27.74
41 | SASANGA PIPED WATER SUPPLY SCHEME (SM/18245) | SM/18245 | 1466.25 | 3700 | NEW | 2 | WO no issued | 26 | 16/06/2023 | 31/12/2024 | 15/01/2024 | 07/08/2023 | 374.2 | 374.2
42 | JIUDHARA PWSS (SM/18314) | SM/18314 | 1124.56 | 2709 | NEW | 2 | WO no issued | 4 | 26/06/2023 | 26/06/2025 | 25/01/2024 | 29/08/2023 | 45.7 | 45.7
43 | TAHERPUR PIPED WATER SUPPLY SCHEME (SM/18478) | SM/18478 | 4015.02 | 9074 | NEW | 2 | WO no issued | 8 | 24/07/2023 | 24/07/2025 | 26/09/2023 | 29/08/2023 | 305.36 | 17
44 | DIGHRA PIPED WATER SUPPLY SCHEME (SM/18482) | SM/18482 | 1127.12 | 2767 | NEW | 2 | WO no issued | 3 | 24/07/2023 | 31/12/2024 | 28/12/2023 | 10/08/2023 | 36.76 | 36.76
45 | BELSHAR PIPED WATER SUPPLY SCHEME (SM/18338) | SM/18338 | 1185.09 | 3434 | NEW | 2 | WO no issued | 36 | 04/07/2023 | 31/12/2024 | 09/01/2024 | 27/07/2023 | 424.17 | 424.17
46 | BAINCHI PIPED WATER SUPPLY SCHEME (SM/18335) | SM/18335 | 1089.2 | 2450 | NEW | 2 | WO no issued | 4 | 03/07/2023 | 31/12/2024 | 17/08/2023 | 10/08/2023 | 40.84 | 40.84
47 | AMUL PIPED WATER SUPPLY SCHEME (SM/18458) | SM/18458 | 1267.14 | 3098 | NEW | 2 | WO no issued | 32 | 20/07/2023 | 31/12/2024 | 29/01/2024 | 24/07/2023 | 401.16 | 401.16
48 | IBRAMBAD PIPED WATER SUPPLY SCHEME (SM/14444) | SM/14444 | 801.33 | 2085 | NEW | 2 | WO no issued | 25 | 20/01/2023 | 31/12/2024 | 06/12/2023 | 08/08/2023 | 197.38 | 197.38
49 | ALIGRAM PIPED WATER SUPPLY SCHEME (SM/14927) | SM/14927 | 503.42 | 1088 | NEW | 2 | WO no issued | 23 | 04/02/2023 | 31/12/2024 | 25/01/2024 | 29/08/2023 | 116.53 | 36.33
50 | LAKHURIA PIPE WATER SUPPLY SCHEME (SM/14918) | SM/14918 | 601.59 | 1344 | NEW | 2 | WO no issued | 5 | 03/02/2023 | 31/12/2024 | 22/08/2023 | 18/08/2023 | 31.28 | 31.28
51 | MALGRAM PIPED WATER SUPPLY SCHEME (SM/15150) | SM/15150 | 636.08 | 2056 | NEW | 2 | WO no issued | 22 | 08/02/2023 | 31/12/2024 | 07/08/2023 | 03/08/2023 | 137.62 | 137.62
52 | CHINISPUR PIPED WATER SUPPLY SCHEME (SM/15170) | SM/15170 | 584.6 | 1794 | NEW | 2 | WO no issued | 3 | 08/02/2023 | 31/12/2024 | 26/09/2023 | 21/08/2023 | 20.21 | 20.21
53 | BALINDAR PIPED WATER SUPPLY SCHEME (SM/16478) | SM/16478 | 996.62 | 2511 | NEW | 2 | WO no issued | 12 | 02/03/2023 | 31/12/2024 | 09/01/2024 | 10/08/2023 | 122.91 | 122.91
54 | BARASAT PIPED WATER SUPPLY SCHEME (SM/13906) | SM/13906 | 813.48 | 2198 | NEW | 2 | WO no issued | 17 | 29/11/2022 | 31/12/2024 | 15/01/2024 | 08/08/2023 | 137.55 | 118.73
55 | HALIMPUR PIPE WATER SUPPLY SCHEME (SM/18343) | SM/18343 | 1198.96 | 3829 | NEW | 2 | WO no issued | 1 | 04/07/2023 | 31/12/2024 | 10/08/2023 | 08/08/2023 | 16.69 | 16.69
56 | SHILLA PIPED WATER SUPPLY SCHEME (SM/18344) | SM/18344 | 4972.51 | 12334 | NEW | 2 | WO no issued | 8 | 04/07/2023 | 31/12/2024 | 10/08/2023 | 08/08/2023 | 402.91 | 284.99
57 | PANDUK PIPED WATER SUPPLY SCHEME (SM/18445) | SM/18445 | 1188.77 | 3269 | NEW | 2 | WO no issued | 13 | 20/07/2023 | 31/12/2024 | 17/08/2023 | 10/08/2023 | 149.53 | 59.03
58 | SIGHNALI PIPED WATER SUPPLY SCHEME. (SM/13496) | SM/13496 | 771.8 | 2101 | NEW | 2 | WO no issued | 26 | 02/11/2022 | 31/12/2024 | 08/02/2024 | 09/08/2023 | 198.66 | 198.66
59 | MERA PIPE WATER SUPPLY SCHEME (SM/15575) | SM/15575 | 559.06 | 1255 | NEW | 2 | WO no issued | 19 | 16/02/2023 | 31/12/2024 | 29/01/2024 | 15/03/2023 | 105.66 | 105.66
60 | BILLESWAR PIPED WATER SUPPLY SCHEME (SM/15241) | SM/15241 | 782.16 | 1647 | NEW | 2 | WO no issued | 24 | 07/02/2023 | 31/12/2024 | 29/01/2024 | 18/04/2023 | 190 | 190
61 | SUATA PIPED WATER SUPPLY SCHEME (SM/14974) | SM/14974 | 981.92 | 2132 | NEW | 2 | WO no issued | 39 | 04/02/2023 | 31/12/2024 | 10/11/2023 | 10/08/2023 | 379.51 | 147.88
62 | PANDUGRAM PIPED WATER SUPPLY SCHEME (SM/15160) | SM/15160 | 682.24 | 1743 | NEW | 2 | WO no issued | 27 | 08/02/2023 | 31/12/2024 | 06/12/2023 | 03/08/2023 | 184.72 | 174.32
63 | KULUTIA PIPED WATER SUPPLY SCHEME (SM/15167) | SM/15167 | 685.87 | 1631 | NEW | 2 | WO no issued | 1 | 08/02/2023 | 31/12/2024 | 31/01/2024 | 21/08/2023 | 7.21 | 7.21
64 | BIRUHA PIPED WATER SUPPLY SCHEME (SM/16287) | SM/16287 | 813.4 | 1813 | NEW | 2 | WO no issued | 11 | 23/02/2023 | 31/12/2024 | 09/01/2024 | 24/08/2023 | 87.33 | 61.23
65 | GAHAK PIPE WATER SUPPLY SCHEME (SM/16303) | SM/16303 | 414.78 | 924 | NEW | 2 | WO no issued | 2 | 23/02/2023 | 31/12/2024 | 05/02/2024 | 07/09/2023 | 9.41 | 9.41
66 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA (SM/16192) | SM/16192 | 386.1 | 1693 | AUGMENTATION | 2 | WO no issued | 16 | 23/02/2023 | 31/12/2024 | 20/02/2024 | 29/05/2023 | 62.45 | 62.45
67 | SANKARPUR PIPED WATER SUPPLY SCHEME (SM/18337) | SM/18337 | 1151.61 | 3257 | NEW | 2 | WO no issued | 16 | 04/07/2023 | 31/12/2024 | 25/01/2024 | 27/07/2023 | 178.78 | 178.78
68 | SIMULIA PIPE WATER SUPPLY SCHEME (SM/18459) | SM/18459 | 1023.66 | 2525 | NEW | 2 | WO no issued | 23 | 20/07/2023 | 20/07/2025 | 15/01/2024 | 04/10/2023 | 230.98 | 201.85
69 | PURANGAN PIPED WATER SUPPLY SCHEME (SM/18446) | SM/18446 | 2589.76 | 5643 | NEW | 2 | WO no issued | 12 | 20/07/2023 | 31/12/2024 | 10/08/2023 | 08/08/2023 | 301.3 | 41.5
70 | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block (SM/18679) | SM/18679 | 4311.81 | 7647 | NEW | 2 | WO no issued | 8 | 04/08/2023 | 04/08/2025 | 26/09/2023 | 29/08/2023 | 335.01 | 0
71 | Ichalabad Piped Water Supply Scheme (SM/18404) | SM/18404 | 1170.91 | 2647 | NEW | 2 | WO no issued | 4 | 12/07/2023 | 31/12/2024 | 07/08/2023 | 31/07/2023 | 42.36 | 14.66
72 | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME (SM/14073) | SM/14073 | 853.72 | 2189 | NEW | 2 | WO no issued | 4 | 12/12/2022 | 31/12/2024 | 27/10/2023 | 25/08/2023 | 36.9 | 36.9
73 | NANDIARA PIPED WATER SUPPLY SCHEME (SM/14019) | SM/14019 | 768.33 | 1609 | NEW | 2 | WO no issued | 21 | 05/12/2022 | 31/12/2024 | 08/02/2024 | 10/08/2023 | 161.66 | 161.66
74 | NIGAN PIPE WATER SUPPLY SCHEME (SM/14912) | SM/14912 | 722.46 | 1886 | NEW | 2 | WO no issued | 1 | 04/02/2023 | 31/12/2024 | 04/07/2023 | 23/05/2023 | 10.72 | 10.72
75 | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME (SM/15555) | SM/15555 | 380.06 | 280 | AUGMENTATION | 2 | WO no issued | 2 | 16/02/2023 | 31/12/2024 | 24/04/2024 | 07/06/2023 | 7.68 | 7.68
76 | UNIATATARPUR PIPED WATER SUPPLY SCHEME (SM/15133) | SM/15133 | 698.43 | 2232 | NEW | 2 | WO no issued | 11 | 06/02/2023 | 31/12/2024 | 17/08/2023 | 09/08/2023 | 75.81 | 65.47
77 | KASIPUR PIPED WATER SUPPLY SCHEME (SM/16019) | SM/16019 | 717.23 | 1617 | NEW | 2 | WO no issued | 7 | 21/02/2023 | 31/12/2024 | 25/01/2024 | 24/08/2023 | 50.18 | 50.18
78 | BHABANANDAPUR PIPED WATER SUPPLY SCHEME (SM/16024) | SM/16024 | 660.06 | 1470 | NEW | 2 | WO no issued | 8 | 21/02/2023 | 31/12/2024 | 05/02/2024 | 10/08/2023 | 53.3 | 47.21
79 | KHANO PIPED WATER SUPPLY SCHEME (SM/18313) | SM/18313 | 2374.1 | 4076 | NEW | 2 | WO no issued | 4 | 26/06/2023 | 26/06/2025 | 22/11/2023 | 10/08/2023 | 106.5 | 33.34
80 | BIJUR PIPED WATER SUPPLY SCHEME (SM/18605) | SM/18605 | 1119.15 | 2607 | NEW | 2 | WO no issued | 11 | 31/07/2023 | 31/12/2024 | 29/01/2024 | 09/08/2023 | 127 | 127
81 | CHANCHAL PIPED WATER SUPPLY SCHEME (SM/18609) | SM/18609 | 1327.85 | 3013 | NEW | 2 | WO no issued | 19 | 31/07/2023 | 31/07/2025 | 29/01/2024 | 05/10/2023 | 258.47 | 258.47
82 | NUDIPUR PIPED WATER SUPPLY SCHEME (SM/18834) | SM/18834 | 1111.74 | 2769 | NEW | 2 | WO no issued | 6 | 21/09/2023 | 31/12/2024 | 29/01/2024 | 05/10/2023 | 69.65 | 50.84
83 | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME (SM/18408) | SM/18408 | 1068.22 | 3278 | NEW | 2 | WO no issued | 14 | 12/07/2023 | 31/12/2024 | 14/03/2024 | 10/08/2023 | 149.43 | 42.91
84 | KHANDRA PIPED WATER SUPPLY SCHEME (SM/18505) | SM/18505 | 1127.09 | 3199 | NEW | 2 | WO no issued | 20 | 26/07/2023 | 26/07/2025 | 30/01/2024 | 05/10/2023 | 224.77 | 224.77
85 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE (SM/13291) | SM/13291 | 871.79 | 2810 | NEW | 2 | WO no issued | 11 | 17/10/2022 | 31/12/2024 | 22/02/2024 | 29/08/2023 | 92.32 | 82.25
86 | KALYANPUR PIPED WATER SUPPLY SCHEME (SM/13939) | SM/13939 | 820.46 | 2206 | NEW | 2 | WO no issued | 4 | 01/12/2022 | 31/12/2024 | 20/02/2024 | 28/06/2023 | 30.46 | 26.57
87 | KHAIDYA PIPED WATER SUPPLY SCHEME (SM/13946) | SM/13946 | 976.89 | 2342 | NEW | 2 | WO no issued | 17 | 01/12/2022 | 31/12/2024 | 15/01/2024 | 08/08/2023 | 164.22 | 164.22
88 | DIGHA PIPED WATER SUPPLY SCHEME (SM/13938) | SM/13938 | 809.82 | 1556 | NEW | 2 | WO no issued | 31 | 01/12/2022 | 31/12/2024 | 20/02/2024 | 08/08/2023 | 250.19 | 231.65
89 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE (SM/13282) | SM/13282 | 837.17 | 2248 | NEW | 2 | WO no issued | 13 | 17/10/2022 | 31/12/2024 | 29/02/2024 | 29/08/2023 | 106.16 | 106.16
90 | MAHARUTBA PIPED WATER SUPPLY SCHEME (SM/14970) | SM/14970 | 637.16 | 1569 | NEW | 2 | WO no issued | 29 | 04/02/2023 | 31/12/2024 | 04/03/2024 | 02/08/2023 | 187.9 | 168.72
91 | ANGARSON PIPED WATER SUPPLY SCHEME (SM/15587) | SM/15587 | 692.97 | 1560 | NEW | 2 | WO no issued | 9 | 16/02/2023 | 31/12/2024 | 09/01/2024 | 10/08/2023 | 59.09 | 59.09
92 | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME (SM/15152) | SM/15152 | 483.27 | 108 | AUGMENTATION | 2 | WO no issued | 34 | 07/02/2023 | 31/12/2024 | 13/03/2024 | 17/02/2023 | 162.75 | 162.75
93 | CHAKULIA PIPE WATER SUPPLY SCHEME (SM/15162) | SM/15162 | 700.93 | 2774 | NEW | 2 | WO no issued | 4 | 08/02/2023 | 31/12/2024 | 10/08/2023 | 08/08/2023 | 24.57 | 0
94 | MORGRAM PIPED WATER SUPPLY SCHEME (SM/15163) | SM/15163 | 793.5 | 1789 | NEW | 2 | WO no issued | 15 | 08/02/2023 | 31/12/2024 | 28/12/2023 | 03/08/2023 | 120.5 | 120.5
95 | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME (SM/15165) | SM/15165 | 810.54 | 2568 | NEW | 2 | WO no issued | 26 | 08/02/2023 | 31/12/2024 | 18/01/2024 | 14/07/2023 | 209.31 | 209.31
96 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR (SM/15185) | SM/15185 | 397.16 | 1500 | AUGMENTATION | 2 | WO no issued | 7 | 07/02/2023 | 31/12/2024 | 12/07/2023 | 19/05/2023 | 25.96 | 25.96
97 | PATHAR GHATA PIPED WATER SUPPLY SCHEME (SM/16029) | SM/16029 | 749.43 | 1692 | NEW | 2 | WO no issued | 8 | 21/02/2023 | 31/12/2024 | 09/01/2024 | 24/08/2023 | 59.34 | 59.34
98 | KHANPUR PIPED WATER SUPPLY SCHEME (SM/16540) | SM/16540 | 1171.58 | 3321 | NEW | 2 | WO no issued | 5 | 10/03/2023 | 10/03/2025 | 22/02/2024 | 29/08/2023 | 63.66 | 63.66
99 | AMADPUR PIPED WATER SUPPLY SCHEME (SM/18146) | SM/18146 | 571.48 | 1499 | NEW | 2 | WO no issued | 13 | 29/03/2023 | 31/12/2024 | 15/01/2024 | 14/09/2023 | 73.43 | 73.43
100 | KHAJURDIHI PIPE WATER SUPPLY SCHEME (SM/18484) | SM/18484 | 1133.66 | 3132 | NEW | 2 | WO no issued | 12 | 24/07/2023 | 31/12/2024 | 18/01/2024 | 10/08/2023 | 141.69 | 141.69
101 | REAN PIPED WATER SUPPLY SCHEME (SM/18504) | SM/18504 | 1136.79 | 2477 | NEW | 2 | WO no issued | 32 | 26/07/2023 | 31/12/2024 | 18/01/2024 | 09/08/2023 | 366.12 | 366.12
102 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE (SM/13340) | SM/13340 | 691.97 | 1861 | NEW | 2 | WO no issued | 6 | 17/10/2022 | 31/12/2024 | 13/03/2024 | 05/10/2023 | 43.2 | 43.2
103 | NIRALGACHHI PIPED WATER SUPPLY SCHEME (SM/14436) | SM/14436 | 835.48 | 2227 | NEW | 2 | WO no issued | 8 | 20/01/2023 | 31/12/2024 | 23/04/2024 | 19/04/2023 | 65.22 | 65.22
104 | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME (SM/14979) | SM/14979 | 576.58 | 1921 | NEW | 2 | WO no issued | 6 | 04/02/2023 | 31/12/2024 | 12/07/2023 | 19/05/2023 | 32.76 | 13.95
105 | KURMUN PIPED WATER SUPPLY SCHEME (SM/13943) | SM/13943 | 978.48 | 2937 | NEW | 2 | WO no issued | 15 | 01/12/2022 | 31/12/2024 | 09/11/2023 | 14/09/2023 | 143.01 | 140.34
106 | UDGARA PIPED WATER SUPPLY SCHEME (SM/14961) | SM/14961 | 609.95 | 1273 | NEW | 2 | WO no issued | 10 | 04/02/2023 | 31/12/2024 | 28/12/2023 | 29/08/2023 | 59.09 | 59.09
107 | AUSGRAM PIPED WATER SUPPLY SCHEME (SM/14905) | SM/14905 | 951.12 | 2264 | NEW | 2 | WO no issued | 22 | 04/02/2023 | 31/12/2024 | 29/12/2023 | 02/08/2023 | 205.2 | 205.2
108 | BHATPARA PIPE WATER SUPPLY SCHEME (SM/14975) | SM/14975 | 820.95 | 2183 | NEW | 2 | WO no issued | 24 | 04/02/2023 | 31/12/2024 | 10/08/2023 | 02/08/2023 | 195.77 | 195.77
109 | Narottambati Piped Water Supply Scheme (SM/15486) | SM/15486 | 1019.43 | 2297 | NEW | 2 | WO no issued | 17 | 13/02/2023 | 31/12/2024 | 05/02/2024 | 10/08/2023 | 176.41 | 176.41
110 | Pipuldaha Piped Water Supply Scheme (SM/15488) | SM/15488 | 1182.3 | 2640 | NEW | 2 | WO no issued | 10 | 13/02/2023 | 31/12/2024 | 09/01/2024 | 08/08/2023 | 116.39 | 116.39
111 | NERAGOHALIA PIPED WATER SUPPLY SCHEME (SM/16617) | SM/16617 | 998.07 | 2895 | NEW | 2 | WO no issued | 26 | 14/03/2023 | 31/12/2024 | 28/12/2023 | 09/08/2023 | 255.66 | 255.66
112 | KUSDANGA PIPED WATER SUPPLY SCHEME (SM/16036) | SM/16036 | 493.57 | 865 | NEW | 2 | WO no issued | 6 | 21/02/2023 | 31/12/2024 | 25/01/2024 | 25/08/2023 | 28.42 | 28.42
113 | BANTIR PIPED WATER SUPPLY SCHEME (SM/18300) | SM/18300 | 1286.37 | 2776 | NEW | 2 | WO no issued | 33 | 26/06/2023 | 31/12/2024 | 09/01/2024 | 27/07/2023 | 426.66 | 426.66
114 | NALA PIPED WATER SUPPLY SCHEME (SM/18256) | SM/18256 | 1246.49 | 3215 | NEW | 2 | WO no issued | 9 | 21/06/2023 | 31/12/2024 | 25/01/2024 | 02/08/2023 | 115.36 | 115.36
115 | Sanko Piped Water Supply Scheme (SM/18407) | SM/18407 | 1448.91 | 3620 | NEW | 2 | WO no issued | 17 | 12/07/2023 | 31/12/2024 | 15/01/2024 | 28/07/2023 | 250.77 | 250.77
116 | SILUT PIPED WATER SUPPLY SCHEME (SM/13903) | SM/13903 | 894.4 | 2432 | NEW | 2 | WO no issued | 25 | 29/11/2022 | 31/12/2024 | 29/12/2023 | 10/08/2023 | 225.22 | 225.22
117 | KALIGRAM PIPED WATER SUPPLY SCHEME (SM/13940) | SM/13940 | 777.44 | 1810 | NEW | 2 | WO no issued | 20 | 01/12/2022 | 31/12/2024 | 09/11/2023 | 10/08/2023 | 153.71 | 153.71
118 | SHUSHNA PIPED WATER SUPPLY SCHEME (SM/14438) | SM/14438 | 824.06 | 2000 | NEW | 2 | WO no issued | 31 | 20/01/2023 | 31/12/2024 | 25/01/2024 | 09/08/2023 | 255.99 | 255.99
119 | GOBARDHANPUR PIPED WATER SUPPLY SCHEME (SM/14445) | SM/14445 | 725.97 | 1445 | NEW | 2 | WO no issued | 2 | 20/01/2023 | 31/12/2024 | 17/08/2023 | 09/08/2023 | 11.02 | 11.02
120 | PURULIA PIPED WATER SUPPLY SCHEME (SM/15239) | SM/15239 | 459.29 | 1004 | NEW | 2 | WO no issued | 21 | 07/02/2023 | 31/12/2024 | 31/01/2024 | 18/04/2023 | 96.03 | 96.03
121 | BHEDIA PIPED WATER SUPPLY SCHEME (SM/14748) | SM/14748 | 699.32 | 1543 | NEW | 2 | WO no issued | 6 | 31/01/2023 | 31/12/2024 | 14/03/2024 | 29/08/2023 | 43.62 | 17.53
122 | SHRIGRAM PIPED WATER SUPPLY SCHEME (SM/14915) | SM/14915 | 602.71 | 1380 | NEW | 2 | WO no issued | 2 | 03/02/2023 | 31/12/2024 | 04/07/2023 | 23/05/2023 | 12.32 | 12.32
123 | SHYAMPUR PIPE WATER SUPPLY SCHEME (SM/15585) | SM/15585 | 485.78 | 813 | NEW | 2 | WO no issued | 5 | 16/02/2023 | 31/12/2024 | 26/09/2023 | 07/09/2023 | 23.9 | 23.9
124 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III (SM/15588) | SM/15588 | 793.59 | 1000 | AUGMENTATION | 2 | WO no issued | 1 | 16/02/2023 | 03/03/2024 | 29/02/2024 | 11/05/2023 | 6.16 | 6.16
125 | Chaudanga Piped Water Supply Scheme (SM/15489) | SM/15489 | 1143.73 | 2994 | NEW | 2 | WO no issued | 11 | 13/02/2023 | 31/12/2024 | 09/01/2024 | 27/07/2023 | 122.37 | 122.37
126 | MAHULA PIPED WATER SUPPLY SCHEME (SM/16025) | SM/16025 | 423.81 | 946 | NEW | 2 | WO no issued | 16 | 21/02/2023 | 31/12/2024 | 05/01/2024 | 22/08/2023 | 69.32 | 69.32
127 | BHAGABATIPUR PIPED WATER SUPPLY SCHEME (SM/14977) | SM/14977 | 841.52 | 1708 | NEW | 2 | WO no issued | 18 | 04/02/2023 | 04/08/2024 | 28/12/2023 | 05/10/2023 | 147.85 | 147.85
128 | KULSANA PIPE WATER SUPPLY SCHEME (SM/18440) | SM/18440 | 1230.88 | 3613 | NEW | 2 | WO no issued | 12 | 18/07/2023 | 31/12/2024 | 10/08/2023 | 08/08/2023 | 143.22 | 143.22
129 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. (SM/13283) | SM/13283 | 922.78 | 2296 | NEW | 2 | WO no issued | 9 | 17/10/2022 | 31/12/2024 | 22/02/2024 | 05/10/2023 | 79.87 | 79.87
130 | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. (SM/13331) | SM/13331 | 942.52 | 2827 | NEW | 2 | WO no issued | 7 | 17/10/2022 | 31/12/2024 | 22/02/2024 | 08/08/2023 | 63.03 | 63.03
131 | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. (SM/15586) | SM/15586 | 711.87 | 1614 | NEW | 2 | WO no issued | 16 | 16/02/2023 | 31/12/2024 | 25/01/2024 | 10/08/2023 | 115.63 | 115.63
132 | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) (SM/15182) | SM/15182 | 279.58 | 0 | AUGMENTATION | 2 | WO no issued | 0 | 07/02/2023 | 31/12/2024 | 22/08/2023 | 29/08/2023 | 0 | 0
133 | KARAJGRAM PIPED WATER SUPPLY SCHEME (SM/18483) | SM/18483 | 1319.23 | 2942 | NEW | 2 | WO no issued | 6 | 24/07/2023 | 31/12/2024 | 18/01/2024 | 02/08/2023 | 83.57 | 83.57
134 | LAKSHIMPUR PWSS (SM/18457) | SM/18457 | 1048.15 | 2881 | NEW | 2 | WO no issued | 19 | 20/07/2023 | 20/07/2025 | 10/05/2024 | 04/10/2023 | 201.85 | 198.71
135 | KAMALPUR PIPED WATER SUPPLY SCHEME (SM/13453) | SM/13453 | 335.66 | 695 | NEW | 3 | WO no issued | 18 | 02/11/2022 | 31/12/2024 | 15/01/2024 | 22/05/2023 | 62.08 | 62.08
136 | AMARPUR PIPED WATER SUPPLY SCHEME (SM/13967) | SM/13967 | 613.42 | 1194 | NEW | 3 | WO no issued | 7 | 01/12/2022 | 31/12/2024 | 29/02/2024 | 10/08/2023 | 45.65 | 45.65
137 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA (SM/15192) | SM/15192 | 302.82 | 1757 | AUGMENTATION | 3 | WO no issued | 55 | 08/02/2023 | 31/12/2024 | 31/07/2023 | 03/05/2023 | 166.17 | 166.17
138 | SITAHATI PIPE WATER SUPPLY SCHEME (SM/15161) | SM/15161 | 784.13 | 3022 | NEW | 3 | WO no issued | 35 | 08/02/2023 | 08/08/2024 | 04/03/2024 | 04/10/2023 | 276.28 | 276.28
139 | MASARU PIPE WATER SUPPLY SCHEME (SM/16020) | SM/16020 | 399.5 | 843 | NEW | 3 | WO no issued | 27 | 21/02/2023 | 31/12/2024 | 15/01/2024 | 10/08/2023 | 106.11 | 106.11
140 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN (SM/15723) | SM/15723 | 130.73 | 541 | AUGMENTATION | 3 | WO no issued | 60 | 20/02/2023 | 31/12/2024 | 24/11/2023 | 17/10/2022 | 79.09 | 78.15
141 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE (SM/18422) | SM/18422 | 1032.73 | 3196 | NEW | 3 | WO no issued | 46 | 18/07/2023 | 31/12/2024 | 10/05/2024 | 08/08/2023 | 478.17 | 467.49
142 | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME (SM/14906) | SM/14906 | 309.75 | 673 | NEW | 3 | WO no issued | 11 | 04/02/2023 | 31/12/2024 | 08/02/2024 | 25/08/2023 | 32.92 | 32.92
143 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR (SM/15187) | SM/15187 | 144.12 | 462 | AUGMENTATION | 3 | WO no issued | 10 | 08/02/2023 | 31/12/2024 | 24/04/2024 | 13/04/2023 | 14.39 | 14.39
144 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR (SM/15191) | SM/15191 | 226.2 | 0 | AUGMENTATION | 3 | WO no issued | 16 | 08/02/2023 | 31/12/2024 | 06/12/2023 | 31/05/2023 | 35.26 | 35.26
145 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU (SM/15203) | SM/15203 | 153.66 | 350 | AUGMENTATION | 3 | WO no issued | 29 | 07/02/2023 | 31/12/2024 | 24/04/2024 | 31/03/2023 | 45.3 | 45.3
146 | BANKAPASI PIPE WATER SUPPLY SCHEME (SM/16484) | SM/16484 | 984.37 | 2622 | NEW | 3 | WO no issued | 9 | 02/03/2023 | 31/12/2024 | 04/03/2024 | 10/08/2023 | 88.32 | 88.32
147 | DWARIATAN PIPED WATER SUPPLY SCHEME (SM/16285) | SM/16285 | 891.16 | 1996 | NEW | 3 | WO no issued | 7 | 23/02/2023 | 23/08/2024 | 09/01/2024 | 24/08/2023 | 62.8 | 62.8
148 | GUSUMBA PIPED WATER SUPPLY SCHEME (SM/18441) | SM/18441 | 1434.92 | 3423 | NEW | 3 | WO no issued | 19 | 18/07/2023 | 31/12/2024 | 24/04/2024 | 02/08/2023 | 268.57 | 268.57
149 | PALISGRAM PIPE WATER SUPPLY SCHEME (SM/18481) | SM/18481 | 1222.8 | 3319 | NEW | 3 | WO no issued | 7 | 24/07/2023 | 24/07/2025 | 03/04/2024 | 04/10/2023 | 83.71 | 83.71
150 | JAGADABAD PIPED WATER SUPPLY SCHEME (SM/13945) | SM/13945 | 872.95 | 2060 | NEW | 3 | WO no issued | 8 | 01/12/2022 | 31/12/2024 | 29/02/2024 | 08/08/2023 | 72.15 | 72.15
151 | BALIDANGA PIPE WATER SUPPLY SCHEME (SM/18315) | SM/18315 | 1116.5 | 3466 | NEW | 3 | WO no issued | 14 | 26/06/2023 | 31/12/2024 | 09/02/2024 | 08/08/2023 | 158.73 | 158.73
152 | SANUI PIPED WATER SUPPLY SCHEME (SM/18610) | SM/18610 | 1535.64 | 3764 | NEW | 3 | WO no issued | 18 | 31/07/2023 | 31/12/2024 | 15/01/2024 | 10/08/2023 | 270.37 | 270.37
153 | DAFARPUR PIPED WATER SUPPLY SCHEME (SM/16028) | SM/16028 | 417.08 | 720 | NEW | 3 | WO no issued | 16 | 21/02/2023 | 31/12/2024 | 13/03/2024 | 10/08/2023 | 64.83 | 64.83
154 | MARO PIPED WATER SUPPLY SCHEME (SM/15579) | SM/15579 | 237.76 | 238 | NEW | 3 | WO no issued | 44 | 16/02/2023 | 31/12/2024 | 13/02/2024 | 01/06/2023 | 104.94 | 104.94
155 | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME (SM/14909) | SM/14909 | 849.53 | 1666 | NEW | 3 | WO no issued | 0 | 04/02/2023 | 04/08/2024 | 20/02/2024 | 10/08/2023 | 4.15 | 4.15
156 | BHOTA PIPED WATER SUPPLY SCHEME (SM/13293) | SM/13293 | 378.17 | 799 | NEW | 3 | WO no issued | 21 | 17/10/2022 | 31/12/2024 | 29/12/2023 | 02/08/2023 | 79.77 | 79.77
157 | Amra Piped Water Supply Scheme (SM/13296) | SM/13296 | 405.32 | 896 | NEW | 3 | WO no issued | 26 | 17/10/2022 | 31/12/2024 | 29/01/2024 | 12/07/2022 | 105.29 | 105.29
158 | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME (SM/16477) | SM/16477 | 753.31 | 1812 | NEW | 3 | WO no issued | 17 | 02/03/2023 | 02/09/2024 | 04/03/2024 | 04/10/2023 | 127.94 | 127.94
159 | Balgana Piped Water Supply Scheme (SM/18326) | SM/18326 | 1124.71 | 2564 | NEW | 3 | WO no issued | 11 | 27/06/2023 | 27/06/2025 | 05/01/2024 | 24/08/2023 | 128.73 | 128.73
160 | NAYAPARA PIPED WATER SUPPLY SCHEME (SM/16026) | SM/16026 | 286.69 | 567 | NEW | 3 | WO no issued | 23 | 21/02/2023 | 31/12/2024 | 09/02/2024 | 29/08/2023 | 66.83 | 66.83
161 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN (SM/15194) | SM/15194 | 341.33 | 1684 | AUGMENTATION | 3 | WO no issued | 24 | 08/02/2023 | 31/12/2024 | 07/12/2023 | 28/03/2023 | 80.71 | 70.19
162 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR (SM/15181) | SM/15181 | 152.21 | 0 | AUGMENTATION | 3 | WO no issued | 39 | 08/02/2023 | 31/12/2024 | 15/01/2024 | 28/04/2023 | 59.53 | 49.29
163 | KHURUL PIPED WATER SUPPLY SCHEME (SM/13549) | SM/13549 | 357.08 | 738 | NEW | 4 | WO no issued | 16 | 04/11/2022 | 31/12/2024 | 29/02/2024 | 25/08/2023 | 57.64 | 28.32
164 | BAGPUR PIPED WATER SUPPLY SCHEME (SM/13323) | SM/13323 | 572.79 | 1390 | NEW | 4 | WO no issued | 6 | 17/10/2022 | 31/12/2024 | 05/02/2024 | 24/07/2023 | 34.2 | 25.05
165 | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME (SM/15159) | SM/15159 | 287.57 | 250 | AUGMENTATION | 4 | WO no issued | 1 | 07/02/2023 | 31/12/2024 | 16/08/2023 | 07/06/2023 | 2.49 | 2.49
166 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I (SM/15571) | SM/15571 | 904.68 | 1000 | AUGMENTATION | 4 | WO no issued | 26 | 16/02/2023 | 31/12/2024 | 29/02/2024 | 02/08/2023 | 236.58 | 230.42
167 | ONARI PIPED WATER SUPPLY SCHEME (SM/18246) | SM/18246 | 1194.73 | 2748 | NEW | 4 | WO no issued | 20 | 16/06/2023 | 31/12/2024 | 05/03/2024 | 07/08/2023 | 238.1 | 238.1
168 | PASHALA PIPED WATER SUPPLY SCHEME (SM/15245) | SM/15245 | 280.13 | 476 | NEW | 4 | WO no issued | 9 | 07/02/2023 | 31/12/2024 | 20/02/2024 | 29/08/2023 | 23.93 | 19.13
169 | AKALPAUSH PIPE WATER SUPPLY SCHEME (SM/16485) | SM/16485 | 921.29 | 2094 | NEW | 5 | WO no issued | 21 | 02/03/2023 | 31/12/2024 | 25/01/2024 | 24/08/2023 | 189.06 | 175.1
170 | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME (SM/16299) | SM/16299 | 205.59 | 200 | AUGMENTATION | 5 | WO no issued | 3 | 23/02/2023 | 31/12/2024 | 10/05/2024 | 01/11/2023 | 5.96 | 0
171 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR (SM/15701) | SM/15701 | 144.48 | 0 | AUGMENTATION | 5 | WO no issued | 24 | 20/02/2023 | 31/12/2024 | 13/03/2024 | 31/05/2023 | 34.51 | 23.97
172 | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME (SM/14917) | SM/14917 | 232.57 | 392 | NEW | 5 | WO no issued | 24 | 04/02/2023 | 31/12/2024 | 15/01/2024 | 23/08/2023 | 55.97 | 47.21
173 | AUGMENTATION OF RAYAN (PART-II) PWSS (SM/16486) | SM/16486 | 772.37 | 4085 | AUGMENTATION | 5 | WO no issued | 1 | 02/03/2023 | 31/03/2024 | 12/06/2023 | 07/06/2023 | 5.11 | 5.11
174 | SRIPUR PIPE WATER SUPPLY SCHEME (SM/15158) | SM/15158 | 571.6 | 1608 | NEW | 5 | WO no issued | 23 | 08/02/2023 | 31/12/2024 | 31/01/2024 | 03/08/2023 | 131.65 | 131.65
175 | GOPKHANJI PIPED WATER SUPPLY SCHEME (SM/15171) | SM/15171 | 914.1 | 2054 | NEW | 5 | WO no issued | 33 | 08/02/2023 | 31/12/2024 | 01/08/2023 | 13/03/2023 | 299.75 | 299.75
176 | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME (SM/15568) | SM/15568 | 583.85 | 444 | AUGMENTATION | 5 | WO no issued | 14 | 16/02/2023 | 01/07/2024 | 29/02/2024 | 07/06/2023 | 82.11 | 82.11
177 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH (SM/16479) | SM/16479 | 433.76 | 0 | AUGMENTATION | 5 | WO no issued | 0 | 02/03/2023 | 31/03/2024 | 04/07/2023 | 07/06/2023 | 0 | 0
178 | BAKALSA PIPED WATER SUPPLY SCHEME (SM/13944) | SM/13944 | 916.69 | 2409 | NEW | 5 | WO no issued | 3 | 01/12/2022 | 31/12/2024 | 04/01/2024 | 25/08/2023 | 29.18 | 29.18
179 | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME (SM/15557) | SM/15557 | 722.06 | 1000 | AUGMENTATION | 5 | WO no issued | 15 | 16/02/2023 | 31/12/2024 | 29/02/2024 | 07/06/2023 | 108.71 | 108.71
180 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI (SM/15565) | SM/15565 | 108.27 | 150 | AUGMENTATION | 5 | WO no issued | 5 | 16/02/2023 | 31/12/2024 | 12/07/2023 | 04/05/2023 | 5.31 | 5.31
181 | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME (SM/16301) | SM/16301 | 301.7 | 250 | AUGMENTATION | 5 | WO no issued | 2 | 23/02/2023 | 31/03/2024 | 24/08/2023 | 13/03/2023 | 4.7 | 4.7
182 | POALKURA PIPED WATER SUPPLY SCHEME (SM/14061) | SM/14061 | 384.32 | 780 | NEW | 5 | WO no issued | 11 | 12/12/2022 | 31/12/2024 | 25/01/2024 | 29/08/2023 | 40.6 | 40.6
183 | GIDHGRAM PIPED WATER SUPPLY SCHEME (SM/18485) | SM/18485 | 1409.11 | 3309 | NEW | 5 | WO no issued | 16 | 24/07/2023 | 31/12/2024 | 18/01/2024 | 07/08/2023 | 226 | 226
184 | NABASTA PIPED WATER SUPPLY SCHEME (SM/14059) | SM/14059 | 843.93 | 1515 | NEW | 5 | WO no issued | 17 | 12/12/2022 | 31/12/2024 | 25/01/2024 | 14/11/2022 | 140.08 | 113.98
185 | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME (SM/15573) | SM/15573 | 523.9 | 734 | AUGMENTATION | 5 | WO no issued | 0 | 16/02/2023 | 31/12/2024 | 29/02/2024 | 14/09/2023 | 0 | 0
186 | ARGUN PIPED WATER SUPPLY SCHEME (SM/16482) | SM/16482 | 606.69 | 1637 | NEW | 5 | WO no issued | 7 | 02/03/2023 | 31/12/2024 | 29/01/2024 | 21/08/2023 | 44.79 | 44.79
187 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV (SM/16307) | SM/16307 | 965.63 | 1000 | AUGMENTATION | 5 | WO no issued | 1 | 23/02/2023 | 31/12/2024 | 21/07/2023 | 20/07/2023 | 6.16 | 0
188 | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME (SM/16306) | SM/16306 | 246 | 150 | AUGMENTATION | 5 | WO no issued | 7 | 23/02/2023 | 31/12/2024 | 04/07/2023 | 10/05/2023 | 17.56 | 17.56
189 | MOUDANGA PIPED WATER SUPPLY SCHEME (SM/14020) | SM/14020 | 786.6 | 1630 | NEW | 5 | WO no issued | 6 | 05/12/2022 | 31/12/2024 | 16/02/2024 | 23/08/2023 | 46.43 | 46.43
190 | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman (SM/17188) | SM/17188 | 377.77 | 0 | SOLARISATION | 5 | WO no issued | 0 | 15/03/2023 | 31/03/2024 | 24/08/2023 | 23/06/2023 | 0 | 0
191 | HATSIMUL PIPED WATER SUPPLY SCHEME (SM/18409) | SM/18409 | 1338.5 | 2529 | NEW | 5 | WO no issued | 23 | 12/07/2023 | 31/12/2024 | 21/12/2023 | 31/07/2023 | 306.94 | 289.09
192 | CHARKHI PIPED WATER SUPPLY SCHEME (SM/14966) | SM/14966 | 721.47 | 1582 | NEW | 5 | WO no issued | 20 | 04/02/2023 | 31/12/2024 | 07/08/2023 | 18/04/2023 | 140.77 | 140.77
193 | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME (SM/16487) | SM/16487 | 857.85 | 2200 | AUGMENTATION | 5 | WO no issued | 2 | 02/03/2023 | 03/10/2024 | 12/03/2024 | 27/06/2022 | 16.53 | 16.53
194 | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME (SM/16293) | SM/16293 | 252.07 | 300 | AUGMENTATION | 5 | WO no issued | 0 | 23/02/2023 | 23/08/2023 | 12/06/2023 | 12/10/2023 | 0 | 0
195 | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME (SM/16298) | SM/16298 | 379.1 | 0 | AUGMENTATION | 5 | WO no issued | 5 | 23/02/2023 | 31/12/2024 | 04/07/2023 | 03/05/2023 | 20.8 | 20.8
196 | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. (SM/19113) | SM/19113 | 123.42 | 0 | AUGMENTATION | 5 | WO no issued | 2 | 22/12/2023 | 31/12/2024 | 13/03/2024 | 18/01/2024 | 1.85 | 1.85
197 | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME (SM/15487) | SM/15487 | 1236.06 | 3286 | NEW | 5 | WO no issued | 4 | 13/02/2023 | 22/04/2025 | 13/03/2024 | 24/08/2023 | 54.26 | 54.26
198 | AUGMENTATION BHALKI Z-I & Z-II PWSS (SM/15560) | SM/15560 | 466.54 | 600 | AUGMENTATION | 5 | WO no issued | 0 | 16/02/2023 | 31/12/2024 | 12/07/2023 | 18/05/2023 | 0 | 0
199 | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME (SM/16548) | SM/16548 | 312.94 | 557 | AUGMENTATION | 5 | WO no issued | 23 | 10/03/2023 | 31/12/2024 | 04/07/2023 | 19/05/2023 | 72.24 | 72.24
200 | NETRAKHANDA PIPED WATER SUPPLY SCHEME (SM/16616) | SM/16616 | 663.07 | 1424 | NEW | 5 | WO no issued | 2 | 14/03/2023 | 14/09/2024 | 28/12/2023 | 14/09/2023 | 10.56 | 10.56
201 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM (SM/15753) | SM/15753 | 126.2 | 0 | AUGMENTATION | 5 | WO no issued | 1 | 20/02/2023 | 31/12/2024 | 13/03/2024 | 25/08/2023 | 0.77 | 0.77
202 | NANAGAR PIPED WATER SUPPLY SCHEME (SM/18479) | SM/18479 | 1161.5 | 2833 | NEW | 5 | WO no issued | 4 | 24/07/2023 | 31/12/2024 | 24/04/2024 | 10/08/2023 | 49.03 | 49.03
203 | Bara Bainan Piped Water Supply Scheme (SM/18406) | SM/18406 | 1077.31 | 2814 | NEW | 5 | WO no issued | 19 | 12/07/2023 | 31/12/2024 | 06/12/2023 | 27/07/2023 | 199.82 | 199.82
204 | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN (SM/15309) | SM/15309 | 710.23 | 2344 | AUGMENTATION | 6 | WO no issued | 29 | 09/02/2023 | 31/12/2024 | 13/03/2024 | 17/02/2023 | 205.99 | 205.99
205 | GHUNI PIPE WATER SUPPLY SCHEME (SM/16034) | SM/16034 | 451.58 | 1008 | NEW | 6 | WO no issued | 17 | 21/02/2023 | 31/12/2024 | 29/02/2024 | 10/08/2023 | 76.78 | 76.78
206 | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME (SM/15725) | SM/15725 | 96.14 | 0 | AUGMENTATION | 6 | WO no issued | 1 | 20/02/2023 | 31/12/2024 | 13/03/2024 | 12/07/2023 | 0.77 | 0.77
207 | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) (SM/18112) | SM/18112 | 296.54 | 0 | AUGMENTATION | 8 | WO no issued | 5 | 27/03/2023 | 31/12/2024 | 13/03/2024 | 21/03/2023 | 14.49 | 14.49
208 | SABIDPUR PIPED WATER SUPPLY SCHEME (SM/16021) | SM/16021 | 783.85 | 1769 | NEW | 8 | WO no issued | 13 | 21/02/2023 | 31/12/2024 | 05/01/2024 | 10/08/2023 | 105.66 | 105
209 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE (SM/14132) | SM/14132 | 5905.97 | 4396 | NEW | 8 | WO no issued | 17 | 02/01/2023 | 31/03/2024 | 11/08/2023 | 20/02/2023 | 983.56 | 983.56
210 | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME (SM/14964) | SM/14964 | 835.12 | 2340 | NEW | 8 | WO no issued | 30 | 04/02/2023 | 31/12/2024 | 10/05/2024 | 18/07/2023 | 248.98 | 218.98
211 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA (SM/15205) | SM/15205 | 80.39 | 0 | AUGMENTATION | 8 | WO no issued | 1 | 07/02/2023 | 31/12/2024 | 13/03/2024 | 12/07/2023 | 0.77 | 0.77
212 | KHARGAKUR PIPED WATER SUPPLY SCHEME (SM/16035) | SM/16035 | 571.41 | 1294 | NEW | 8 | WO no issued | 23 | 21/02/2023 | 31/12/2024 | 05/01/2024 | 28/08/2023 | 133.22 | 133.22
213 | SANTOSHPUR PIPED WATER SUPPLY SCHEME (SM/18405) | SM/18405 | 1130.16 | 2995 | NEW | 8 | WO no issued | 28 | 12/07/2023 | 31/12/2024 | 06/12/2023 | 31/07/2023 | 318.73 | 318.73
214 | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME (SM/16196) | SM/16196 | 262.71 | 280 | AUGMENTATION | 8 | WO no issued | 7 | 23/02/2023 | 31/12/2024 | 19/03/2024 | 17/10/2023 | 19.21 | 19.21
215 | PALITPUR PIPED WATER SUPPLY SCHEME (SM/14076) | SM/14076 | 565.9 | 1222 | NEW | 9 | WO no issued | 6 | 12/12/2022 | 31/12/2024 | 09/11/2023 | 10/08/2023 | 33.79 | 23.37
216 | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME (SM/15562) | SM/15562 | 410.59 | 60 | AUGMENTATION | 9 | WO no issued | 1 | 16/02/2023 | 01/11/2024 | 12/03/2024 | 13/04/2023 | 2.62 | 2.62
217 | SHIBLUN PIPE WATER SUPPLY SCHEME (SM/14972) | SM/14972 | 663.56 | 1394 | NEW | 9 | WO no issued | 31 | 04/02/2023 | 31/12/2024 | 29/09/2023 | 18/04/2023 | 207.88 | 197.31
218 | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) (SM/16774) | SM/16774 | 275.12 | 0 | AUGMENTATION | 9 | WO no issued | 6 | 13/03/2023 | 31/07/2024 | 13/03/2024 | 21/03/2022 | 17.77 | 17.77
219 | KOTALGHOSH PIPED WATER SUPPLY SCHEME (SM/14062) | SM/14062 | 659.18 | 1423 | NEW | 9 | WO no issued | 35 | 12/12/2022 | 31/12/2024 | 29/09/2023 | 10/08/2023 | 229.06 | 209.87
220 | JALKANDAR PIPED WATER SUPPLY SCHEME (SM/14953) | SM/14953 | 969.12 | 2122 | NEW | 9 | WO no issued | 21 | 04/02/2023 | 31/12/2024 | 21/12/2023 | 10/08/2023 | 208.09 | 208.09
221 | CHAKDAHA PIPED WATER SUPPLY SCHEME (SM/15582) | SM/15582 | 207.53 | 293 | NEW | 9 | WO no issued | 28 | 16/02/2023 | 31/12/2024 | 19/12/2023 | 04/05/2023 | 57.5 | 57.5
222 | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME (SM/16297) | SM/16297 | 254.93 | 300 | AUGMENTATION | 9 | WO no issued | 7 | 23/02/2023 | 31/12/2024 | 09/01/2024 | 01/06/2023 | 17.63 | 17.63
223 | MACHKHARA PIPED WATER SUPPLY SCHEME (SM/14967) | SM/14967 | 878.93 | 1661 | NEW | 10 | WO no issued | 16 | 04/02/2023 | 04/08/2024 | 16/01/2024 | 29/08/2023 | 141.23 | 141.23
224 | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME (SM/15172) | SM/15172 | 739.9 | 1745 | NEW | 10 | WO no issued | 13 | 08/02/2023 | 31/12/2024 | 05/01/2024 | 10/08/2023 | 92.9 | 92.9
225 | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME (SM/14965) | SM/14965 | 446.69 | 749 | NEW | 10 | WO no issued | 14 | 04/02/2023 | 31/12/2024 | 05/03/2024 | 08/06/2023 | 64.54 | 64.54
226 | LOAPUR PIPED WATER SUPPLY SCHEME (SM/18323) | SM/18323 | 1466.39 | 3508 | NEW | 10 | WO no issued | 11 | 27/06/2023 | 31/12/2024 | 14/03/2024 | 31/07/2023 | 165.99 | 165.99
227 | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS (SM/15183) | SM/15183 | 366.86 | 0 | AUGMENTATION | 10 | WO no issued | 22 | 07/02/2023 | 31/12/2024 | 03/08/2023 | 14/03/2022 | 80.5 | 80.5
228 | AURIA PIPED WATER SUPPLY SCHEME (SM/18455) | SM/18455 | 1320.64 | 3373 | NEW | 10 | WO no issued | 37 | 20/07/2023 | 31/12/2024 | 05/10/2023 | 24/07/2023 | 483.29 | 483.29
229 | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman (SM/18991) | SM/18991 | 155.55 | 0 | SOLARISATION | 10 | WO no issued | 0 | 17/10/2023 | 10/07/2024 | 02/05/2024 | 02/11/2023 | 0 | 0
230 | TELUN PIPED WATER SUPPLY SCHEME (SM/13455) | SM/13455 | 908.7 | 2128 | NEW | 11 | WO no issued | 13 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 29/03/2023 | 122.16 | 122.16
231 | KACHUA PIPED WATER SUPPLY SCHEME (SM/13497) | SM/13497 | 520.29 | 1137 | NEW | 11 | WO no issued | 25 | 02/11/2022 | 31/12/2024 | 05/02/2024 | 22/05/2023 | 131.03 | 129.13
232 | SHIKARPUR PIPED WATER SUPPLY SCHEME (SM/14437) | SM/14437 | 947.99 | 2462 | NEW | 13 | WO no issued | 25 | 20/01/2023 | 31/12/2024 | 06/12/2023 | 01/11/2022 | 238.66 | 238.66
233 | MEJHIARI PIPED WATER SUPPLY SCHEME (SM/18456) | SM/18456 | 1088.2 | 2700 | NEW | 13 | WO no issued | 22 | 20/07/2023 | 31/12/2024 | 29/09/2023 | 31/07/2023 | 234.24 | 234.24
234 | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. (SM/15581) | SM/15581 | 500.08 | 892 | NEW | 14 | WO no issued | 20 | 16/02/2023 | 31/12/2024 | 05/01/2024 | 02/06/2023 | 99.03 | 99.03
235 | GURPARA PIPED WATER SUPPLY SCHEME (SM/14447) | SM/14447 | 773.39 | 1680 | NEW | 14 | WO no issued | 31 | 20/01/2023 | 31/12/2024 | 28/12/2023 | 18/04/2023 | 243.31 | 243.31
236 | BAMUNPUKUR PIPED WATER SUPPLY SCHEME (SM/14930) | SM/14930 | 854.64 | 2163 | NEW | 14 | WO no issued | 17 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 19/05/2023 | 147.62 | 147.62
237 | BISHNUPUR PIPED WATER SUPPLY SCHEME (SM/18608) | SM/18608 | 1610.96 | 3799 | NEW | 14 | WO no issued | 38 | 31/07/2023 | 31/12/2024 | 09/01/2024 | 07/08/2023 | 607.88 | 607.88
238 | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME (SM/14976) | SM/14976 | 685.17 | 1921 | NEW | 14 | WO no issued | 3 | 04/02/2023 | 31/12/2024 | 05/03/2024 | 19/05/2023 | 23.87 | 23.87
239 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR (SM/15195) | SM/15195 | 107.27 | 1983 | RETROFITTING | 15 | WO no issued | 52 | 08/02/2023 | 31/12/2024 | 13/03/2024 | 21/03/2023 | 56.29 | 56.29
240 | BHUYERA PIPED WATER SUPPLY SCHEME (SM/13948) | SM/13948 | 678.07 | 1330 | NEW | 17 | WO no issued | 29 | 01/12/2022 | 31/12/2024 | 21/12/2023 | 10/08/2023 | 197.28 | 172.28
241 | BARAPALASHAN PIPED WATER SUPPLY SCHEME (SM/13423) | SM/13423 | 714.32 | 1825 | NEW | 17 | WO no issued | 12 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 19/05/2023 | 86.89 | 86.89
242 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI (SM/15184) | SM/15184 | 220.43 | 544 | AUGMENTATION | 17 | WO no issued | 19 | 07/02/2023 | 31/03/2024 | 17/07/2023 | 16/05/2023 | 41.7 | 41.7
243 | DEULIA PIPED WATER SUPPLY SCHEME (SM/14973) | SM/14973 | 830.84 | 1505 | NEW | 18 | WO no issued | 5 | 04/02/2023 | 31/12/2024 | 29/09/2023 | 09/08/2023 | 44.34 | 44.34
244 | CHATKA PIPED WATER SUPPLY SCHEME (SM/15168) | SM/15168 | 771.03 | 2317 | NEW | 19 | WO no issued | 47 | 08/02/2023 | 31/12/2024 | 19/12/2023 | 17/07/2023 | 363.62 | 363.62
245 | MANGANPUR PIPED WATER SUPPLY SCHEME (SM/13327) | SM/13327 | 784.22 | 1736 | NEW | 19 | WO no issued | 15 | 17/10/2022 | 31/12/2024 | 05/01/2024 | 24/07/2023 | 113.79 | 81.53
246 | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte (SM/14425) | SM/14425 | 926.18 | 2717 | NEW | 19 | WO no issued | 35 | 20/01/2023 | 31/12/2024 | 22/02/2024 | 05/04/2023 | 328.41 | 328.41
247 | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME (SM/14448) | SM/14448 | 894.65 | 2411 | NEW | 19 | WO no issued | 20 | 20/01/2023 | 31/12/2024 | 29/09/2023 | 13/04/2023 | 179.82 | 139.36
248 | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. (SM/11283) | SM/11283 | 548.04 | 0 | SCHOOL | 20 | WO no issued | 0 | 28/06/2022 | 31/03/2024 | 09/08/2023 | 12/07/2022 | 0 | 0
249 | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) (SM/16290) | SM/16290 | 167.64 | 600 | RETROFITTING | 20 | WO no issued | 20 | 23/02/2023 | 31/03/2024 | 24/11/2023 | 01/06/2023 | 33.45 | 33.45
250 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA (SM/16488) | SM/16488 | 39.97 | 606 | RETROFITTING | 20 | WO no issued | 46 | 02/03/2023 | 31/12/2024 | 13/03/2024 | 24/03/2023 | 18.56 | 18.56
251 | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal (SM/09921) | SM/09921 | 1144.6 | 6396 | AUGMENTATION | 20 | WO no issued | 52 | 10/12/2021 | 31/12/2024 | 29/02/2024 | 27/12/2021 | 592.3 | 592.3
252 | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN (SM/10481) | SM/10481 | 749.99 | 1951 | AUGMENTATION | 20 | WO no issued | 43 | 13/04/2022 | 31/12/2024 | 13/03/2024 | 27/12/2021 | 322.02 | 298.55
253 | TAIPARA Piped Water Supply Scheme. (SM/14442) | SM/14442 | 906.99 | 2406 | NEW | 21 | WO no issued | 28 | 20/01/2023 | 31/12/2024 | 06/12/2023 | 19/04/2023 | 253.4 | 253.07
254 | BAHADURPUR PIPED WATER SUPPLY SCHEME (SM/13504) | SM/13504 | 420.97 | 936 | NEW | 22 | WO no issued | 33 | 02/11/2022 | 31/12/2024 | 09/02/2024 | 08/08/2023 | 140.61 | 140.61
255 | DEARA PIPED WATER SUPPLY SCHEME (SM/14435) | SM/14435 | 695.72 | 1692 | NEW | 23 | WO no issued | 35 | 20/01/2023 | 31/12/2024 | 24/11/2023 | 01/11/2022 | 241.96 | 220.34
256 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN (SM/14014) | SM/14014 | 848.66 | 13054 | AUGMENTATION | 24 | WO no issued | 25 | 05/12/2022 | 31/12/2024 | 13/03/2024 | 11/01/2022 | 210.23 | 210.23
257 | BAGHTONA PIPED WATER SUPPLY SCHEME (SM/18334) | SM/18334 | 1031.05 | 1867 | NEW | 24 | WO no issued | 47 | 03/07/2023 | 31/12/2024 | 24/04/2024 | 24/07/2023 | 482.28 | 482.28
258 | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME (SM/14072) | SM/14072 | 962.8 | 1821 | NEW | 24 | WO no issued | 29 | 12/12/2022 | 31/12/2024 | 29/02/2024 | 26/07/2023 | 281.76 | 269.91
259 | BANDMURA PIPED WATER SUPPLY SCHEME (SM/18480) | SM/18480 | 1451.41 | 3491 | NEW | 24 | WO no issued | 3 | 24/07/2023 | 24/07/2025 | 25/02/2024 | 29/08/2023 | 37.18 | 37.18
260 | KASIGRAM PIPE WATER SUPPLY SCHEME (SM/18367) | SM/18367 | 1354.92 | 3024 | NEW | 24 | WO no issued | 16 | 11/07/2023 | 31/12/2024 | 05/03/2024 | 24/07/2023 | 222.49 | 222.49
261 | KASHIARA PIPED WATER SUPPLY SCHEME (SM/14075) | SM/14075 | 989.54 | 2622 | NEW | 24 | WO no issued | 28 | 12/12/2022 | 31/12/2024 | 25/02/2024 | 09/08/2023 | 277.31 | 254.78
262 | GHOSHPUR PIPED WATER SUPPLY SCHEME (SM/13947) | SM/13947 | 851.51 | 1952 | NEW | 24 | WO no issued | 12 | 01/12/2022 | 31/12/2024 | 21/02/2024 | 19/05/2023 | 99.54 | 99.54
263 | GOPALBERA PIPED WATER SUPPLY SCHEME (SM/13905) | SM/13905 | 986.75 | 2144 | NEW | 24 | WO no issued | 21 | 29/11/2022 | 31/12/2024 | 21/02/2024 | 04/05/2023 | 204.02 | 204.02
264 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR (SM/15175) | SM/15175 | 174.65 | 0 | AUGMENTATION | 25 | WO no issued | 41 | 08/02/2023 | 31/12/2024 | 13/03/2024 | 13/04/2023 | 71.26 | 71.26
265 | BAJITPUR PIPED WATER SUPPLY SCHEME (SM/16619) | SM/16619 | 680.19 | 1500 | NEW | 25 | WO no issued | 9 | 14/03/2023 | 31/12/2024 | 21/02/2024 | 24/07/2023 | 60.1 | 60.1
266 | Serpur Piped Water Supply Scheme (SM/13384) | SM/13384 | 478.73 | 813 | NEW | 26 | WO no issued | 12 | 18/10/2022 | 31/12/2024 | 21/02/2024 | 18/07/2023 | 56.88 | 56.88
267 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA (SM/15718) | SM/15718 | 56.48 | 140 | AUGMENTATION | 27 | WO no issued | 18 | 20/02/2023 | 30/06/2024 | 13/03/2024 | 28/02/2023 | 10.1 | 10.1
268 | HARISHNAPUR PIPED WATER SUPPLY SCHEME (SM/15319) | SM/15319 | 714.61 | 1867 | NEW | 27 | WO no issued | 10 | 09/02/2023 | 31/12/2024 | 21/02/2024 | 24/07/2023 | 68.77 | 68.77
269 | Gangua Piped Water Supply Scheme (SM/13295) | SM/13295 | 574.91 | 1288 | NEW | 27 | WO no issued | 31 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 18/08/2023 | 180.95 | 180.95
270 | MURGRAM PIPED WATER SUPPLY SCHEME (SM/15156) | SM/15156 | 537.11 | 1763 | NEW | 27 | WO no issued | 43 | 08/02/2023 | 31/12/2024 | 28/12/2023 | 03/08/2023 | 229.58 | 229.58
271 | NRISINHAPUR PIPED WATER SUPPLY SCHEME (SM/14071) | SM/14071 | 667.05 | 1303 | NEW | 27 | WO no issued | 43 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 17/07/2023 | 285.15 | 259.05
272 | BELGRAM PIPED WATER SUPPLY SCHEME (SM/14018) | SM/14018 | 931.79 | 2093 | NEW | 28 | WO no issued | 42 | 05/12/2022 | 31/12/2024 | 21/02/2024 | 10/05/2023 | 391.68 | 387.35
273 | JAJIGRAM PIPE WATER SUPPLY SCHEME (SM/15151) | SM/15151 | 709.72 | 1588 | NEW | 28 | WO no issued | 34 | 08/02/2023 | 31/12/2024 | 26/09/2023 | 13/03/2023 | 242.61 | 229.84
274 | MOHANPUR PIPED WATER SUPPLY SCHEME (SM/18242) | SM/18242 | 1333.72 | 2788 | NEW | 28 | WO no issued | 50 | 16/06/2023 | 31/12/2024 | 21/02/2024 | 20/07/2023 | 661.16 | 641.93
275 | KHANJI PIPED WATER SUPPLY SCHEME (SM/16476) | SM/16476 | 711.62 | 2182 | NEW | 28 | WO no issued | 29 | 02/03/2023 | 31/12/2024 | 08/11/2023 | 03/08/2023 | 204.77 | 204.77
276 | MOSHRA PIPED WATER SUPPLY SCHEME (SM/14931) | SM/14931 | 556.47 | 1136 | NEW | 29 | WO no issued | 18 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 24/07/2023 | 101.01 | 101.01
277 | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL (SM/18439) | SM/18439 | 2281.19 | 9130 | AUGMENTATION | 29 | WO no issued | 31 | 18/07/2023 | 18/07/2024 | 05/01/2024 | 08/08/2023 | 712.22 | 697.92
278 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme (SM/08031) | SM/08031 | 301.39 | 5077 | RETROFITTING | 30 | WO no issued | 80 | 25/01/2021 | 31/12/2023 | 12/06/2023 | 16/03/2022 | 241.93 | 241.93
279 | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. (SM/09712) | SM/09712 | 732.87 | 4237 | AUGMENTATION | 30 | WO no issued | 39 | 26/11/2021 | 31/03/2024 | 03/08/2023 | 13/01/2022 | 283.84 | 283.84
280 | BARA KULGACHHI PIPED WATER SUPPLY SCHEME (SM/14079) | SM/14079 | 951.8 | 2461 | NEW | 30 | WO no issued | 34 | 12/12/2022 | 31/12/2024 | 29/09/2023 | 24/02/2023 | 326.25 | 326.25
281 | KARUI PIPED WATER SUPPLY SCHEME (SM/18460) | SM/18460 | 1346.35 | 3523 | NEW | 30 | WO no issued | 47 | 20/07/2023 | 31/12/2024 | 29/09/2023 | 24/07/2023 | 631.18 | 599.64
282 | JHAMATPUR PIPED WATER SUPPLY SCHEME (SM/16256) | SM/16256 | 361.18 | 655 | NEW | 31 | WO no issued | 36 | 24/02/2023 | 31/12/2024 | 29/09/2023 | 23/05/2023 | 130.9 | 130.9
283 | Baikunthapur Piped Water Supply Scheme (SM/13294) | SM/13294 | 881.8 | 1926 | NEW | 33 | WO no issued | 29 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 15/05/2023 | 253.68 | 231.14
284 | CHHATINI PIPED WATER SUPPLY SCHEME (SM/14017) | SM/14017 | 959.51 | 2137 | NEW | 33 | WO no issued | 19 | 05/12/2022 | 31/12/2024 | 21/02/2024 | 15/05/2023 | 181.39 | 181.39
285 | SHUKUR PIPED WATER SUPPLY SCHEME (SM/16255) | SM/16255 | 889.84 | 1849 | NEW | 33 | WO no issued | 13 | 24/02/2023 | 31/12/2024 | 21/02/2024 | 24/07/2023 | 115.99 | 115.99
286 | RUPSA PIPED WATER SUPPLY SCHEME (SM/13298) | SM/13298 | 947.38 | 2439 | NEW | 34 | WO no issued | 19 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 181.73 | 181.33
287 | KHATUNDI PIPED WATER SUPPLY SCHEME (SM/15154) | SM/15154 | 469.62 | 1112 | NEW | 36 | WO no issued | 31 | 08/02/2023 | 31/12/2024 | 29/02/2024 | 27/07/2023 | 147.05 | 147.05
288 | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME (SM/16016) | SM/16016 | 145.44 | 180 | AUGMENTATION | 36 | WO no issued | 41 | 21/02/2023 | 31/12/2024 | 19/12/2023 | 19/05/2023 | 60.34 | 60.34
289 | SHIBADA PIPED WATER SUPPLY SCHEME (SM/13492) | SM/13492 | 617.18 | 1282 | NEW | 36 | WO no issued | 26 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 25/07/2023 | 158.85 | 158.85
290 | DEBPUR PIPED WATER SUPPLY SCHEME (SM/13398) | SM/13398 | 792.97 | 1898 | NEW | 37 | WO no issued | 24 | 18/10/2022 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 187.72 | 187.72
291 | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME (SM/14074) | SM/14074 | 908.14 | 2233 | NEW | 37 | WO no issued | 34 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 10/05/2023 | 312.76 | 312.76
292 | KONRAPUR PIPED WATER SUPPLY SCHEME (SM/13419) | SM/13419 | 728.41 | 1636 | NEW | 38 | WO no issued | 20 | 02/11/2022 | 31/12/2024 | 22/02/2024 | 17/04/2023 | 148.02 | 148.02
293 | DEHA PIPED WATER SUPPLY SCHEME (SM/13506) | SM/13506 | 753.28 | 1516 | NEW | 38 | WO no issued | 32 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 15/05/2023 | 244.44 | 244.44
294 | AKHRA PIPED WATER SUPPLY SCHEME (SM/14057) | SM/14057 | 804.45 | 1984 | NEW | 39 | WO no issued | 28 | 12/12/2022 | 31/12/2024 | 29/09/2023 | 13/04/2023 | 227.69 | 227.69
295 | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09873) | SM/09873 | 651.8 | 3189 | AUGMENTATION | 39 | WO no issued | 30 | 06/12/2021 | 31/12/2024 | 29/02/2024 | 24/02/2022 | 195.6 | 195.6
296 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE (SM/10391) | SM/10391 | 942.3 | 4079 | AUGMENTATION | 39 | WO no issued | 74 | 24/03/2022 | 31/03/2024 | 03/10/2023 | 14/07/2021 | 700.31 | 700.31
297 | KALIKAPUR PIPED WATER SUPPLY SCHEME (SM/14053) | SM/14053 | 989.35 | 2794 | NEW | 39 | WO no issued | 30 | 12/12/2022 | 31/12/2024 | 29/09/2023 | 01/11/2022 | 295.53 | 295.53
298 | TATARPUR PIPED WATER SUPPLY SCHEME (SM/14740) | SM/14740 | 702.48 | 1639 | NEW | 40 | WO no issued | 30 | 31/01/2023 | 31/12/2024 | 21/02/2024 | 06/06/2023 | 212.9 | 202.8
299 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman (SM/08105) | SM/08105 | 311.16 | 5098 | RETROFITTING | 40 | WO no issued | 50 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 18/09/2020 | 155.35 | 155.35
300 | EORA PIPED WATER SUPPLY SCHEME (SM/13968) | SM/13968 | 247.48 | 287 | NEW | 40 | WO no issued | 34 | 01/12/2022 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 83.74 | 83.74
301 | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District (SM/09403) | SM/09403 | 651.77 | 657 | AUGMENTATION | 40 | WO no issued | 63 | 17/11/2021 | 31/12/2023 | 12/06/2023 | 23/02/2022 | 408.94 | 408.94
302 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block (SM/07870) | SM/07870 | 157.93 | 2688 | RETROFITTING | 41 | WO no issued | 28 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 10/12/2020 | 44.01 | 43.43
303 | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. (SM/18365) | SM/18365 | 1436.61 | 4783 | NEW | 41 | WO no issued | 43 | 11/07/2023 | 31/12/2024 | 21/02/2024 | 19/07/2023 | 613.31 | 601.24
304 | UCHALAN PIPED WATER SUPPLY SCHEME (SM/13329) | SM/13329 | 733.45 | 1924 | NEW | 41 | WO no issued | 22 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 18/07/2023 | 164.74 | 164.74
305 | MAHATA PIPED WATER SUPPLY SCHEME (SM/15242) | SM/15242 | 766.68 | 1751 | NEW | 41 | WO no issued | 29 | 07/02/2023 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 225.2 | 200.36
306 | DHENRIA PIPED WATER SUPPLY SCHEME (SM/15246) | SM/15246 | 703.67 | 1267 | NEW | 41 | WO no issued | 23 | 07/02/2023 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 161.29 | 161.29
307 | KAMALPUR PIPED WATER SUPPLY SCHEME (SM/13942) | SM/13942 | 869.97 | 2652 | NEW | 42 | WO no issued | 26 | 01/12/2022 | 31/12/2024 | 29/02/2024 | 04/05/2023 | 225.82 | 225.42
308 | Samanti Piped Water Supply Scheme (SM/13319) | SM/13319 | 926 | 2107 | NEW | 42 | WO no issued | 24 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 29/03/2023 | 225.47 | 225.47
309 | UKHRID PIPED WATER SUPPLY SCHEME (SM/13505) | SM/13505 | 834.72 | 2045 | NEW | 42 | WO no issued | 29 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 238.8 | 238.8
310 | BIJRA PIPED WATER SUPPLY SCHEME (SM/13426) | SM/13426 | 838.13 | 1934 | NEW | 42 | WO no issued | 22 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 15/05/2023 | 182.23 | 182.23
311 | EHIAPUR PIPED WATER SUPPLY SCHEME (SM/18342) | SM/18342 | 1201.07 | 3160 | NEW | 42 | WO no issued | 33 | 04/07/2023 | 31/12/2024 | 29/09/2023 | 08/08/2023 | 394.4 | 394.4
312 | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C (SM/16289) | SM/16289 | 94.64 | 200 | RETROFITTING | 45 | WO no issued | 25 | 23/02/2023 | 31/12/2024 | 03/10/2023 | 31/05/2023 | 23.56 | 23.56
313 | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block (SM/08030) | SM/08030 | 1902.4 | 34987 | RETROFITTING | 45 | WO no issued | 77 | 25/01/2021 | 31/12/2023 | 12/06/2023 | 02/06/2021 | 1457.37 | 1453.35
314 | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10061) | SM/10061 | 693.56 | 4019 | AUGMENTATION | 45 | WO no issued | 52 | 25/01/2022 | 31/12/2024 | 29/02/2024 | 31/01/2022 | 360.18 | 360.18
315 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10056) | SM/10056 | 726.35 | 2676 | AUGMENTATION | 45 | WO no issued | 79 | 25/01/2022 | 31/12/2024 | 29/02/2024 | 27/12/2021 | 576.16 | 576.16
316 | GOPALPUR PIPED WATER SUPPLY SCHEME (SM/15583) | SM/15583 | 379.6 | 688 | NEW | 46 | WO no issued | 31 | 16/02/2023 | 31/12/2024 | 21/02/2024 | 19/05/2023 | 117.69 | 59.65
317 | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME (SM/14926) | SM/14926 | 315.46 | 546 | NEW | 46 | WO no issued | 29 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 19/07/2023 | 93.02 | 76.53
318 | PATHARDANGA PIPED WATER SUPPLY SCHEME (SM/14440) | SM/14440 | 997.37 | 2852 | NEW | 47 | WO no issued | 36 | 20/01/2023 | 31/12/2024 | 24/11/2023 | 01/11/2022 | 354.16 | 353.83
319 | MASGARIA PIPED WATER SUPPLY SCHEME (SM/13318) | SM/13318 | 553.22 | 1233 | NEW | 47 | WO no issued | 29 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 17/04/2023 | 159.85 | 157.27
320 | CHHORA PIPED WATER SUPPLY SCHEME (SM/13328) | SM/13328 | 995.39 | 3034 | NEW | 47 | WO no issued | 55 | 17/10/2022 | 31/03/2024 | 21/02/2024 | 01/11/2022 | 542.57 | 534.69
321 | RAJUR PIPED WATER SUPPLY SCHEME (SM/15238) | SM/15238 | 955.81 | 2477 | NEW | 47 | WO no issued | 24 | 07/02/2023 | 31/12/2024 | 19/12/2023 | 12/04/2023 | 231.87 | 231.87
322 | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10058) | SM/10058 | 987.71 | 5327 | AUGMENTATION | 49 | WO no issued | 71 | 25/01/2022 | 31/12/2024 | 29/02/2024 | 23/02/2022 | 704.34 | 704.34
323 | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK (SM/13491) | SM/13491 | 789.53 | 2003 | NEW | 50 | WO no issued | 25 | 02/11/2022 | 31/12/2024 | 13/03/2024 | 01/11/2022 | 193.58 | 193.58
324 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM (SM/15602) | SM/15602 | 700.54 | 500 | AUGMENTATION | 50 | WO no issued | 34 | 16/02/2023 | 31/03/2024 | 14/07/2023 | 20/03/2023 | 235.78 | 235.78
325 | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan (SM/10378) | SM/10378 | 130.06 | 0 | SCHOOL | 50 | WO no issued | 0 | 23/03/2022 | 31/03/2024 | 10/08/2023 | 03/12/2021 | 0 | 0
326 | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10060) | SM/10060 | 489.63 | 3207 | AUGMENTATION | 50 | WO no issued | 88 | 25/01/2022 | 31/12/2024 | 29/02/2024 | 31/01/2022 | 429.4 | 429.4
327 | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. (SM/09714) | SM/09714 | 754.02 | 2485 | AUGMENTATION | 50 | WO no issued | 54 | 26/11/2021 | 30/04/2024 | 29/02/2024 | 11/02/2022 | 405.78 | 405.78
328 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR (SM/12081) | SM/12081 | 58.96 | 1250 | RETROFITTING | 50 | WO no issued | 64 | 02/09/2022 | 31/03/2024 | 29/02/2024 | 03/11/2020 | 37.97 | 37.97
329 | BARADOBA PIPED WATER SUPPLY SCHEME (SM/18230) | SM/18230 | 215.86 | 216 | NEW | 50 | WO no issued | 52 | 05/06/2023 | 31/12/2024 | 21/02/2024 | 08/06/2023 | 111.42 | 111.42
330 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block (SM/07868) | SM/07868 | 249.54 | 3050 | RETROFITTING | 50 | WO no issued | 20 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 18/02/2021 | 50.34 | 50.34
331 | CHAGRAM PIPED WATER SUPPLY SCHEME (SM/13941) | SM/13941 | 846.16 | 1984 | NEW | 51 | WO no issued | 41 | 01/12/2022 | 31/03/2024 | 21/02/2024 | 04/05/2023 | 342.98 | 324.17
332 | CHAKPUROHIT PIPED WATER SUPPLY SCHEME (SM/14978) | SM/14978 | 462.5 | 786 | NEW | 51 | WO no issued | 27 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 08/06/2023 | 126.93 | 126.93
333 | CHOTKHANDA PIPED WATER SUPPLY SCHEME (SM/13907) | SM/13907 | 995.08 | 2846 | NEW | 52 | WO no issued | 33 | 29/11/2022 | 31/12/2024 | 21/02/2024 | 19/05/2023 | 332.99 | 332.99
334 | CHAK CHANDAN PIPED WATER SUPPLY SCHEME (SM/13281) | SM/13281 | 510.5 | 1136 | NEW | 52 | WO no issued | 34 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 18/07/2023 | 175.78 | 175.78
335 | PHANRIJANGALPIPED WATER SUPPLY SCHEME (SM/14060) | SM/14060 | 551.85 | 1177 | NEW | 53 | WO no issued | 46 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 14/07/2023 | 255.28 | 233.58
336 | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block (SM/08101) | SM/08101 | 402.29 | 6182 | RETROFITTING | 55 | WO no issued | 36 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 21/03/2022 | 143.75 | 143.75
337 | BALSIDANGA PIPED WATER SUPPLY SCHEME (SM/13904) | SM/13904 | 245.44 | 319 | NEW | 55 | WO no issued | 24 | 29/11/2022 | 31/03/2024 | 21/02/2024 | 24/03/2023 | 59.45 | 59.45
338 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I (SM/08034) | SM/08034 | 1126.08 | 8364 | RETROFITTING | 55 | WO no issued | 39 | 25/01/2021 | 31/12/2023 | 12/06/2023 | 13/07/2021 | 444.08 | 443.32
339 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme (SM/07863) | SM/07863 | 125.64 | 2164 | RETROFITTING | 55 | WO no issued | 40 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 01/10/2020 | 50.26 | 50.26
340 | AMRA PIPED WATER SUPPLY SCHEME (SM/13454) | SM/13454 | 799.29 | 1602 | NEW | 55 | WO no issued | 34 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 272.24 | 272.24
341 | BALABATI PIPED WATER SUPPLY SCHEME (SM/13457) | SM/13457 | 678.2 | 1364 | NEW | 55 | WO no issued | 34 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 13/04/2023 | 230.49 | 211.67
342 | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09494) | SM/09494 | 354.12 | 2007 | AUGMENTATION | 55 | WO no issued | 85 | 19/11/2021 | 31/12/2024 | 13/03/2024 | 31/01/2022 | 300.57 | 300.57
343 | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME (SM/16022) | SM/16022 | 145.22 | 130 | AUGMENTATION | 55 | WO no issued | 43 | 21/02/2023 | 31/12/2024 | 05/10/2023 | 22/05/2023 | 62.07 | 62.07
344 | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. (SM/13280) | SM/13280 | 575.1 | 1672 | NEW | 56 | WO no issued | 51 | 17/10/2022 | 31/03/2024 | 24/11/2023 | 01/11/2022 | 292.27 | 292.27
345 | Katnabil Piped Water Supply Scheme (SM/13338) | SM/13338 | 623.44 | 1319 | NEW | 56 | WO no issued | 36 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 18/07/2023 | 224.46 | 224.46
346 | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10337) | SM/10337 | 1360.01 | 9066 | AUGMENTATION | 57 | WO no issued | 69 | 14/03/2022 | 31/12/2024 | 29/02/2024 | 15/03/2022 | 942.29 | 942.29
347 | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09566) | SM/09566 | 623.11 | 3670 | AUGMENTATION | 57 | WO no issued | 84 | 22/11/2021 | 31/12/2024 | 13/03/2024 | 31/01/2022 | 521.61 | 521.61
348 | SARANGA PIPED WATER SUPPLY SCHEME (SM/14078) | SM/14078 | 552.88 | 1147 | NEW | 57 | WO no issued | 41 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 04/05/2023 | 229.44 | 229.44
349 | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10270) | SM/10270 | 1096.06 | 6540 | AUGMENTATION | 57 | WO no issued | 67 | 25/02/2022 | 31/10/2024 | 13/03/2024 | 21/02/2022 | 739.57 | 739.57
350 | GOHAGRAM PIPED WATER SUPPLY SCHEME (SM/14910) | SM/14910 | 641.25 | 1208 | NEW | 58 | WO no issued | 32 | 04/02/2023 | 31/12/2024 | 13/02/2024 | 01/11/2022 | 204.07 | 184.89
351 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block (SM/07871) | SM/07871 | 255.84 | 3125 | RETROFITTING | 59 | WO no issued | 21 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 52.65 | 52.65
352 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block (SM/07869) | SM/07869 | 109.48 | 1976 | RETROFITTING | 60 | WO no issued | 43 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 25/01/2021 | 47 | 19.85
353 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block (SM/07777) | SM/07777 | 100.12 | 2118 | RETROFITTING | 60 | WO no issued | 76 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 26/02/2021 | 75.72 | 68.72
354 | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme (SM/08102) | SM/08102 | 489.24 | 8834 | RETROFITTING | 60 | WO no issued | 38 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 09/06/2021 | 187.96 | 187.96
355 | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME (SM/14080) | SM/14080 | 321.81 | 604 | NEW | 60 | WO no issued | 37 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 24/04/2023 | 118.9 | 118.9
356 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman (SM/08103) | SM/08103 | 331.6 | 5112 | RETROFITTING | 60 | WO no issued | 53 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 14/07/2021 | 176.65 | 173.5
357 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman (SM/08104) | SM/08104 | 365.23 | 5704 | RETROFITTING | 60 | WO no issued | 62 | 19/02/2021 | 31/12/2023 | 12/06/2023 | 13/07/2021 | 227.29 | 227.29
358 | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District (SM/09569) | SM/09569 | 527.28 | 3020 | AUGMENTATION | 60 | WO no issued | 66 | 22/11/2021 | 31/12/2024 | 29/02/2024 | 10/12/2021 | 347.13 | 347.13
359 | GOPALPUR PIPED WATER SUPPLY SCHEME (SM/15235) | SM/15235 | 743.22 | 1398 | NEW | 60 | WO no issued | 30 | 07/02/2023 | 31/12/2024 | 21/02/2024 | 12/04/2023 | 225.83 | 225.83
360 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10057) | SM/10057 | 972.04 | 3593 | AUGMENTATION | 60 | WO no issued | 53 | 25/01/2022 | 31/12/2024 | 13/03/2024 | 31/01/2022 | 511.75 | 511.75
361 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. (SM/09104) | SM/09104 | 245.18 | 4335 | RETROFITTING | 60 | WO no issued | 30 | 28/10/2021 | 31/12/2023 | 12/06/2023 | 25/06/2021 | 72.49 | 72.49
362 | HARIGRAM PIPED WATER SUPPLY SCHEME (SM/13292) | SM/13292 | 526.13 | 1217 | NEW | 61 | WO no issued | 44 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 231.76 | 220.3
363 | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK (SM/13450) | SM/13450 | 450.26 | 800 | NEW | 61 | WO no issued | 43 | 02/11/2022 | 31/03/2024 | 21/02/2024 | 01/11/2022 | 194.69 | 194.69
364 | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME (SM/14962) | SM/14962 | 939.99 | 2126 | NEW | 61 | WO no issued | 44 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 29/03/2023 | 417.25 | 417.25
365 | JABAGRAM PIPED WATER SUPPLY SCHEME (SM/14980) | SM/14980 | 879.79 | 2196 | NEW | 61 | WO no issued | 39 | 04/02/2023 | 31/12/2024 | 29/09/2023 | 01/11/2022 | 342.25 | 342.16
366 | SADHPUKHARIA PIPED WATER SUPPLY SCHEME (SM/16308) | SM/16308 | 179.63 | 401 | NEW | 61 | WO no issued | 67 | 23/02/2023 | 31/12/2024 | 24/11/2023 | 24/04/2023 | 121.07 | 120.7
367 | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09488) | SM/09488 | 344.93 | 1789 | AUGMENTATION | 62 | WO no issued | 72 | 19/11/2021 | 31/12/2024 | 13/03/2024 | 31/01/2022 | 248.72 | 248.72
368 | BHANDARITURI PIPED WATER SUPPLY SCHEME (SM/14925) | SM/14925 | 190.41 | 457 | NEW | 63 | WO no issued | 28 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 20/03/2023 | 52.99 | 52.99
369 | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman (SM/09408) | SM/09408 | 495.29 | 2829 | AUGMENTATION | 65 | WO no issued | 99 | 17/11/2021 | 30/09/2024 | 13/03/2024 | 31/01/2022 | 491.66 | 491.66
370 | KUNDA PIPED WATER SUPPLY SCHEME (SM/14913) | SM/14913 | 385.14 | 481 | NEW | 65 | WO no issued | 23 | 04/02/2023 | 31/12/2024 | 29/09/2023 | 22/03/2023 | 87.57 | 87.57
371 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block (SM/07776) | SM/07776 | 123.62 | 2615 | RETROFITTING | 65 | WO no issued | 43 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 05/01/2022 | 53.09 | 53.09
372 | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME (SM/13495) | SM/13495 | 213.85 | 320 | NEW | 65 | WO no issued | 40 | 02/11/2022 | 30/06/2024 | 13/03/2024 | 10/05/2023 | 85.28 | 85.28
373 | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10085) | SM/10085 | 3231.45 | 15363 | AUGMENTATION | 65 | WO no issued | 54 | 31/01/2022 | 31/12/2024 | 29/02/2024 | 18/01/2021 | 1745.68 | 1745.68
374 | Augmentation of Ganganandapur PWSS for providing FHTC. (SM/09411) | SM/09411 | 808.85 | 2940 | AUGMENTATION | 65 | WO no issued | 71 | 17/11/2021 | 31/10/2024 | 13/03/2024 | 21/01/2022 | 573.52 | 573.52
375 | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10123) | SM/10123 | 1083.3 | 4801 | AUGMENTATION | 65 | WO no issued | 48 | 08/02/2022 | 31/12/2024 | 29/02/2024 | 27/01/2022 | 516.88 | 516.76
376 | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME (SM/14054) | SM/14054 | 991.42 | 2763 | NEW | 66 | WO no issued | 35 | 12/12/2022 | 31/12/2024 | 29/09/2023 | 01/11/2022 | 343.49 | 343.49
377 | MULGRAM PIPED WATER SUPPLY SCHEME (SM/14058) | SM/14058 | 824.61 | 2199 | NEW | 66 | WO no issued | 52 | 12/12/2022 | 31/12/2024 | 19/12/2023 | 08/02/2023 | 429.03 | 429.03
378 | KARJJANA PIPED WATER SUPPLY SCHEME (SM/15244) | SM/15244 | 235.19 | 309 | NEW | 66 | WO no issued | 32 | 07/02/2023 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 74.8 | 74.8
379 | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME (SM/13417) | SM/13417 | 234.83 | 354 | NEW | 67 | WO no issued | 42 | 02/11/2022 | 31/12/2024 | 21/02/2024 | 12/04/2023 | 97.75 | 97.75
380 | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/09489) | SM/09489 | 599.17 | 4192 | AUGMENTATION | 67 | WO no issued | 93 | 19/11/2021 | 31/12/2024 | 13/03/2024 | 10/09/2021 | 556.28 | 556.28
381 | KHEJURHATI PIPED WATER SUPPLY SCHEME (SM/14952) | SM/14952 | 408.16 | 687 | NEW | 67 | WO no issued | 51 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 04/05/2023 | 207.72 | 207.72
382 | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/10130) | SM/10130 | 1023.72 | 5728 | AUGMENTATION | 69 | WO no issued | 88 | 08/02/2022 | 31/12/2024 | 29/02/2024 | 31/01/2022 | 899.39 | 899.39
383 | SAR PIPED WATER SUPPLY SCHEME (SM/14929) | SM/14929 | 395.09 | 1131 | NEW | 69 | WO no issued | 46 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 16/05/2023 | 179.88 | 179.88
384 | LAKSHAMPUR PIPED WATER SUPPLY SCHEME (SM/13493) | SM/13493 | 146.5 | 182 | NEW | 69 | WO no issued | 42 | 02/11/2022 | 30/04/2024 | 13/03/2024 | 28/03/2023 | 62.11 | 62.11
385 | SAHAPUR PIPED WATER SUPPLY SCHEME (SM/14969) | SM/14969 | 475.62 | 885 | NEW | 69 | WO no issued | 25 | 04/02/2023 | 31/12/2024 | 04/01/2024 | 30/05/2023 | 119.69 | 119.69
386 | Karatia Piped Water Supply Scheme (SM/13397) | SM/13397 | 839.41 | 2002 | NEW | 69 | WO no issued | 44 | 18/10/2022 | 31/12/2024 | 21/02/2024 | 18/07/2023 | 366.94 | 366.94
387 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block (SM/07780) | SM/07780 | 297.21 | 5098 | RETROFITTING | 70 | WO no issued | 44 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 15/01/2021 | 129.39 | 129.39
388 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (SM/08701) | SM/08701 | 505.33 | 5237 | RETROFITTING | 70 | WO no issued | 17 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 09/03/2022 | 87.52 | 87.52
389 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar (SM/08033) | SM/08033 | 1100.67 | 6269 | RETROFITTING | 70 | WO no issued | 36 | 25/01/2021 | 30/09/2024 | 18/04/2024 | 15/06/2021 | 401.42 | 393.79
390 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block (SM/07814) | SM/07814 | 191.46 | 4050 | RETROFITTING | 70 | WO no issued | 44 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 85 | 83.3
391 | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME (SM/16254) | SM/16254 | 254.97 | 446 | NEW | 70 | WO no issued | 37 | 24/02/2023 | 31/12/2024 | 13/03/2024 | 24/03/2023 | 94.65 | 94.65
392 | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL (SM/09415) | SM/09415 | 443 | 1667 | AUGMENTATION | 70 | WO no issued | 58 | 17/11/2021 | 31/12/2024 | 13/03/2024 | 31/03/2022 | 257.15 | 257.15
393 | SRIBATI PIPED WATER SUPPLY SCHEME (SM/14055) | SM/14055 | 998.02 | 2799 | NEW | 70 | WO no issued | 49 | 12/12/2022 | 31/12/2024 | 29/02/2024 | 01/11/2022 | 488.48 | 488.48
394 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block (SM/07828) | SM/07828 | 261 | 3257 | RETROFITTING | 70 | WO no issued | 51 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 133.26 | 133.26
395 | KHANDARI PIPED WATER SUPPLY SCHEME (SM/13396) | SM/13396 | 977.81 | 2173 | NEW | 70 | WO no issued | 67 | 18/10/2022 | 31/05/2024 | 14/03/2024 | 01/11/2022 | 652.38 | 652.38
396 | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK (SM/13424) | SM/13424 | 997.78 | 2435 | NEW | 71 | WO no issued | 44 | 02/11/2022 | 31/03/2024 | 21/02/2024 | 13/04/2023 | 436.6 | 436.6
397 | HARIPUR PIPED WATER SUPPLY SCHEME (SM/13315) | SM/13315 | 342.07 | 543 | NEW | 71 | WO no issued | 26 | 17/10/2022 | 31/05/2024 | 13/03/2024 | 22/03/2023 | 90.55 | 90.55
398 | Kusha Piped Water Supply Scheme (SM/13279) | SM/13279 | 548.58 | 1059 | NEW | 71 | WO no issued | 45 | 17/10/2022 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 244.91 | 244.91
399 | MAKHALTOR PIPED WATER SUPPLY SCHEME (SM/15153) | SM/15153 | 390.21 | 1069 | NEW | 72 | WO no issued | 61 | 07/02/2023 | 31/12/2024 | 17/10/2023 | 01/11/2022 | 238.28 | 238.28
400 | PICHKURI PIPED WATER SUPPLY SCHEME (SM/13330) | SM/13330 | 703.65 | 1793 | NEW | 73 | WO no issued | 28 | 17/10/2022 | 31/03/2024 | 14/03/2024 | 27/04/2023 | 198.59 | 198.36
401 | NOAHATI PIPED WATER SUPPLY SCHEME (SM/13452) | SM/13452 | 921.11 | 1938 | NEW | 74 | WO no issued | 41 | 02/11/2022 | 31/07/2024 | 13/03/2024 | 01/11/2022 | 379.87 | 361.06
402 | KALAIJHUTI PIPED WATER SUPPLY SCHEME (SM/14954) | SM/14954 | 294.41 | 491 | NEW | 74 | WO no issued | 49 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 30/03/2023 | 144.52 | 144.52
403 | KHUNDKURI PIPED WATER SUPPLY SCHEME (SM/13465) | SM/13465 | 992.74 | 2692 | NEW | 74 | WO no issued | 40 | 02/11/2022 | 30/07/2024 | 13/03/2024 | 01/11/2022 | 392.59 | 392.19
404 | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme (SM/07549) | SM/07549 | 82.44 | 1744 | RETROFITTING | 75 | WO no issued | 32 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 25/01/2021 | 25.99 | 20.72
405 | KHERUA PIPED WATER SUPPLY SCHEME (SM/15240) | SM/15240 | 692.15 | 1521 | NEW | 75 | WO no issued | 49 | 07/02/2023 | 31/12/2024 | 29/09/2023 | 01/11/2022 | 341.45 | 341.45
406 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (SM/08703) | SM/08703 | 196.29 | 3098 | RETROFITTING | 75 | WO no issued | 33 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 12/02/2021 | 65.35 | 63.8
407 | NASIGRAM PIPED WATER SUPPLY SCHEME (SM/14443) | SM/14443 | 993.43 | 2924 | NEW | 75 | WO no issued | 44 | 20/01/2023 | 31/12/2024 | 21/02/2024 | 19/04/2023 | 435.06 | 435.06
408 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block (SM/07829) | SM/07829 | 239.55 | 4100 | RETROFITTING | 75 | WO no issued | 43 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 25/01/2021 | 102.84 | 102.84
409 | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. (SM/08704) | SM/08704 | 267.25 | 4909 | RETROFITTING | 75 | WO no issued | 43 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 25/01/2021 | 115.98 | 114.25
410 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme (SM/07823) | SM/07823 | 151.83 | 2579 | RETROFITTING | 75 | WO no issued | 40 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 12/02/2021 | 60.18 | 60.18
411 | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block (SM/07775) | SM/07775 | 120.55 | 2550 | RETROFITTING | 75 | WO no issued | 57 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 02/02/2021 | 68.5 | 68.48
412 | MANDARDIHI PIPED WATER SUPPLY SCHEME (SM/14052) | SM/14052 | 251.9 | 317 | NEW | 75 | WO no issued | 44 | 12/12/2022 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 111.63 | 79.14
413 | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme (SM/07557) | SM/07557 | 74.73 | 1153 | RETROFITTING | 75 | WO no issued | 54 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 09/02/2021 | 40.03 | 40.03
414 | SONAIAIMA Purba Piped Water Supply Scheme (SM/13326) | SM/13326 | 633.06 | 1416 | NEW | 76 | WO no issued | 45 | 17/10/2022 | 31/05/2024 | 14/03/2024 | 01/11/2022 | 286.74 | 286.74
415 | UTRA PIPED WATER SUPPLY SCHEME (SM/14077) | SM/14077 | 752 | 2024 | NEW | 76 | WO no issued | 54 | 12/12/2022 | 31/12/2024 | 24/11/2023 | 12/04/2023 | 403.4 | 399.47
416 | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN (SM/11492) | SM/11492 | 666.43 | 2015 | NEW | 77 | WO no issued | 53 | 19/07/2022 | 31/03/2024 | 21/02/2024 | 27/12/2021 | 350.13 | 350.13
417 | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) (SM/15178) | SM/15178 | 273.13 | 0 | AUGMENTATION | 77 | WO no issued | 2 | 07/02/2023 | 31/10/2024 | 13/03/2024 | 08/06/2023 | 5.58 | 5.58
418 | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) (SM/10032) | SM/10032 | 1069.93 | 5865 | AUGMENTATION | 77 | WO no issued | 71 | 19/01/2022 | 30/09/2024 | 13/03/2024 | 23/02/2022 | 756.77 | 756.77
419 | ARJUNPUKUR PIPED WATER SUPPLY SCHEME (SM/13413) | SM/13413 | 653.36 | 1316 | NEW | 77 | WO no issued | 43 | 02/11/2022 | 30/06/2024 | 13/03/2024 | 05/04/2023 | 281.23 | 281.23
420 | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME (SM/13466) | SM/13466 | 313.2 | 503 | NEW | 78 | WO no issued | 55 | 02/11/2022 | 31/03/2024 | 14/03/2024 | 01/11/2022 | 172.29 | 172.29
421 | BICHKHARA PIPED WATER SUPPLY SCHEME (SM/13422) | SM/13422 | 287.39 | 382 | NEW | 78 | WO no issued | 58 | 02/11/2022 | 31/03/2024 | 27/09/2023 | 01/11/2022 | 166.88 | 155.92
422 | AMILIA PIPED WATER SUPPLY SCHEME (SM/14963) | SM/14963 | 415.83 | 894 | NEW | 78 | WO no issued | 55 | 04/02/2023 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 229.31 | 229.31
423 | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District (SM/09414) | SM/09414 | 487.81 | 2613 | AUGMENTATION | 78 | WO no issued | 79 | 17/11/2021 | 31/12/2024 | 29/02/2024 | 11/04/2022 | 387.42 | 387.42
424 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme (SM/07819) | SM/07819 | 257.15 | 3993 | RETROFITTING | 80 | WO no issued | 7 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 11/01/2022 | 18.82 | 18.82
425 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme (SM/07820) | SM/07820 | 141.29 | 2176 | RETROFITTING | 80 | WO no issued | 91 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 04/12/2020 | 128.19 | 128.16
426 | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/09493) | SM/09493 | 371.84 | 2087 | AUGMENTATION | 80 | WO no issued | 95 | 19/11/2021 | 31/08/2024 | 13/03/2024 | 31/01/2022 | 353.99 | 353.99
427 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme (SM/07860) | SM/07860 | 115.29 | 1853 | RETROFITTING | 80 | WO no issued | 13 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 15/02/2022 | 14.63 | 14.63
428 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block (SM/07813) | SM/07813 | 139.08 | 2942 | RETROFITTING | 80 | WO no issued | 54 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 24/02/2021 | 75.74 | 75.3
429 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. (SM/12080) | SM/12080 | 26.74 | 414 | RETROFITTING | 80 | WO no issued | 64 | 02/09/2022 | 02/12/2022 | 12/06/2023 | 20/09/2021 | 17.18 | 17.18
430 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. (SM/08710) | SM/08710 | 268.29 | 4223 | RETROFITTING | 80 | WO no issued | 66 | 03/09/2021 | 31/03/2024 | 29/02/2024 | 24/06/2021 | 176.28 | 175.79
431 | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME (SM/16349) | SM/16349 | 126.77 | 500 | RETROFITTING | 80 | WO no issued | 47 | 23/02/2023 | 31/12/2024 | 03/10/2023 | 30/05/2023 | 59.54 | 59.54
432 | SIPTA PIPED WATER SUPPLY SCHEME (SM/16618) | SM/16618 | 441.18 | 708 | NEW | 80 | WO no issued | 46 | 14/03/2023 | 31/12/2024 | 21/02/2024 | 24/03/2023 | 202.38 | 202.38
433 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block (SM/07856) | SM/07856 | 129.06 | 2730 | RETROFITTING | 80 | WO no issued | 75 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 19/01/2021 | 97.25 | 95.71
434 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block (SM/07817) | SM/07817 | 132.65 | 2806 | RETROFITTING | 80 | WO no issued | 58 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 27/07/2021 | 76.66 | 75.52
435 | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. (SM/09718) | SM/09718 | 802.22 | 3845 | AUGMENTATION | 80 | WO no issued | 64 | 26/11/2021 | 31/12/2024 | 29/02/2024 | 27/12/2021 | 514.97 | 514.97
436 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme (SM/07800) | SM/07800 | 90.29 | 1910 | RETROFITTING | 80 | WO no issued | 23 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 05/01/2021 | 20.41 | 20.41
437 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block (SM/07816) | SM/07816 | 109.06 | 2307 | RETROFITTING | 80 | WO no issued | 83 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 25/01/2021 | 90.65 | 86.04
438 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block (SM/07781) | SM/07781 | 103.35 | 1810 | RETROFITTING | 80 | WO no issued | 58 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 29/01/2021 | 60.13 | 58.47
439 | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL (SM/09409) | SM/09409 | 532.8 | 3783 | AUGMENTATION | 80 | WO no issued | 79 | 17/11/2021 | 30/06/2024 | 13/03/2024 | 24/02/2022 | 421.18 | 421.18
440 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08705) | SM/08705 | 119.29 | 2137 | RETROFITTING | 80 | WO no issued | 25 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 11/02/2022 | 29.25 | 25
441 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme (SM/07864) | SM/07864 | 148.07 | 2535 | RETROFITTING | 80 | WO no issued | 85 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 29/06/2021 | 125.63 | 125.62
442 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. (SM/08714) | SM/08714 | 177.72 | 2879 | RETROFITTING | 80 | WO no issued | 46 | 03/09/2021 | 30/04/2024 | 29/02/2024 | 07/10/2021 | 82.4 | 82.4
443 | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme (SM/07545) | SM/07545 | 73.51 | 1555 | RETROFITTING | 80 | WO no issued | 32 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 01/12/2020 | 23.66 | 23.6
444 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block (SM/07861) | SM/07861 | 253.82 | 3926 | RETROFITTING | 80 | WO no issued | 66 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 07/10/2020 | 166.4 | 166.4
445 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme (SM/07862) | SM/07862 | 136.5 | 2107 | RETROFITTING | 80 | WO no issued | 73 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 08/12/2020 | 100.12 | 100.12
446 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme (SM/07821) | SM/07821 | 105.81 | 1654 | RETROFITTING | 80 | WO no issued | 55 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 24/02/2021 | 57.85 | 57.85
447 | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District (SM/09410) | SM/09410 | 697.69 | 3077 | AUGMENTATION | 80 | WO no issued | 53 | 17/11/2021 | 31/12/2024 | 29/02/2024 | 11/04/2022 | 372.48 | 372.48
448 | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. (SM/10016) | SM/10016 | 471.57 | 0 | ANGANWADI | 80 | WO no issued | 0 | 30/12/2021 | 31/03/2024 | 29/02/2024 | 21/06/2021 | 0 | 0
449 | DHARALA PIPED WATER SUPPLY SCHEME (SM/14056) | SM/14056 | 347.99 | 713 | NEW | 84 | WO no issued | 31 | 12/12/2022 | 31/03/2024 | 14/03/2024 | 15/03/2023 | 106.7 | 106.7
450 | RAJAPUR PIPED WATER SUPPLY SCHEME (SM/14021) | SM/14021 | 270.24 | 576 | NEW | 84 | WO no issued | 47 | 05/12/2022 | 31/12/2024 | 21/02/2024 | 01/11/2022 | 127.22 | 127.22
451 | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District (SM/09416) | SM/09416 | 563.41 | 1935 | AUGMENTATION | 85 | WO no issued | 68 | 17/11/2021 | 31/05/2024 | 13/03/2024 | 15/02/2022 | 383.59 | 383.59
452 | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME (SM/16304) | SM/16304 | 286.45 | 200 | AUGMENTATION | 86 | WO no issued | 12 | 23/02/2023 | 31/12/2024 | 03/10/2023 | 03/05/2023 | 35.67 | 35.67
453 | SAHAPUR PIPED WATER SUPPLY SCHEME (SM/13425) | SM/13425 | 572.23 | 1188 | NEW | 88 | WO no issued | 45 | 02/11/2022 | 31/03/2024 | 13/03/2024 | 01/11/2022 | 259.4 | 259.4
454 | KUCHUT PIPED WATER SUPPLY SCHEME (SM/13464) | SM/13464 | 910.64 | 2306 | NEW | 88 | WO no issued | 41 | 02/11/2022 | 30/04/2024 | 13/03/2024 | 01/11/2022 | 376.96 | 376.96
455 | SATINANDI PIPED WATER SUPPLY SCHEME (SM/13494) | SM/13494 | 642.77 | 1630 | NEW | 89 | WO no issued | 49 | 02/11/2022 | 31/03/2024 | 14/03/2024 | 01/11/2022 | 316.63 | 316.63
456 | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN (SM/11491) | SM/11491 | 457.23 | 1442 | NEW | 90 | WO no issued | 72 | 19/07/2022 | 31/03/2024 | 21/02/2024 | 27/12/2021 | 327.12 | 327.12
457 | GROUND WATER BASED KANDARSONA PWSS (SM/13339) | SM/13339 | 497.29 | 1011 | NEW | 90 | WO no issued | 47 | 17/10/2022 | 31/07/2024 | 13/03/2024 | 01/11/2022 | 232.3 | 232.3
458 | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) (SM/09717) | SM/09717 | 530.67 | 1762 | AUGMENTATION | 90 | WO no issued | 60 | 26/11/2021 | 31/05/2024 | 13/03/2024 | 02/02/2022 | 319.01 | 319.01
459 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN (SM/10055) | SM/10055 | 114.87 | 1771 | RETROFITTING | 90 | WO no issued | 43 | 25/01/2022 | 31/03/2024 | 29/02/2024 | 07/04/2022 | 49.18 | 49.18
460 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block (SM/07827) | SM/07827 | 126.36 | 1969 | RETROFITTING | 90 | WO no issued | 67 | 08/01/2021 | 31/12/2023 | 03/10/2023 | 13/07/2021 | 84.28 | 62.9
461 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio (SM/08712) | SM/08712 | 147.7 | 2643 | RETROFITTING | 90 | WO no issued | 80 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 02/12/2020 | 117.49 | 112.77
462 | RASUIKHANDA PIPED WATER SUPPLY SCHEME (SM/16253) | SM/16253 | 996.62 | 2353 | NEW | 90 | WO no issued | 58 | 24/02/2023 | 31/12/2024 | 21/02/2024 | 12/04/2023 | 575.27 | 575.27
463 | KANKURHATI PIPED WATER SUPPLY SCHEME (SM/16031) | SM/16031 | 251.87 | 466 | NEW | 91 | WO no issued | 35 | 21/02/2023 | 31/03/2024 | 12/03/2024 | 24/03/2023 | 89.41 | 89.41
464 | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District (SM/09412) | SM/09412 | 537.66 | 4088 | AUGMENTATION | 92 | WO no issued | 75 | 17/11/2021 | 31/12/2024 | 29/02/2024 | 25/01/2022 | 405.18 | 405.18
465 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block (SM/07799) | SM/07799 | 67.65 | 1431 | RETROFITTING | 95 | WO no issued | 25 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 03/08/2022 | 16.66 | 16.66
466 | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09492) | SM/09492 | 586.55 | 3020 | AUGMENTATION | 95 | WO no issued | 98 | 19/11/2021 | 30/06/2024 | 13/03/2024 | 31/01/2022 | 575.81 | 575.81
467 | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) (SM/09719) | SM/09719 | 677.83 | 2213 | AUGMENTATION | 95 | WO no issued | 72 | 26/11/2021 | 31/12/2024 | 29/02/2024 | 02/02/2022 | 487.11 | 487.11
468 | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. (SM/09716) | SM/09716 | 652.1 | 2772 | AUGMENTATION | 98 | WO no issued | 22 | 26/11/2021 | 31/03/2024 | 13/03/2024 | 01/02/2022 | 143.34 | 143.34
469 | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09568) | SM/09568 | 455.89 | 2804 | AUGMENTATION | 98 | WO no issued | 96 | 22/11/2021 | 31/12/2024 | 29/02/2024 | 24/01/2022 | 437.08 | 437.08
470 | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/09404) | SM/09404 | 851.6 | 4677 | AUGMENTATION | 99 | WO no issued | 90 | 17/11/2021 | 31/12/2024 | 29/02/2024 | 31/01/2022 | 767.76 | 767.76
471 | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District (SM/09406) | SM/09406 | 316.97 | 2045 | AUGMENTATION | 99 | WO no issued | 97 | 17/11/2021 | 31/12/2024 | 29/02/2024 | 24/01/2022 | 307.73 | 307.73
472 | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT (SM/08998) | SM/08998 | 497.47 | 2744 | AUGMENTATION | 99 | WO no issued | 96 | 29/10/2021 | 30/04/2024 | 13/03/2024 | 31/01/2022 | 477.05 | 477.05
473 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme (SM/06968) | SM/06968 | 99.96 | 1895 | RETROFITTING | 100 | WO no issued | 100 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 04/12/2020 | 99.96 | 99.96
474 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS (SM/06749) | SM/06749 | 93.49 | 1484 | RETROFITTING | 100 | WO no issued | 53 | 18/09/2020 | 31/12/2023 | 12/06/2023 | 12/10/2020 | 49.68 | 49.68
475 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme (SM/07205) | SM/07205 | 39.16 | 576 | RETROFITTING | 100 | WO no issued | 60 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 10/08/2020 | 23.45 | 23.45
476 | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme (SM/07548) | SM/07548 | 89.96 | 1903 | RETROFITTING | 100 | WO no issued | 78 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 70.03 | 70.03
477 | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme (SM/07555) | SM/07555 | 16.96 | 264 | RETROFITTING | 100 | WO no issued | 81 | 31/12/2020 | 30/04/2022 | 12/06/2023 | 16/10/2020 | 13.75 | 13.75
478 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block (SM/07858) | SM/07858 | 205.59 | 4349 | RETROFITTING | 100 | WO no issued | 89 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 12/02/2021 | 182.93 | 182.92
479 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block (SM/07797) | SM/07797 | 39.14 | 828 | RETROFITTING | 100 | WO no issued | 29 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 15/01/2021 | 11.22 | 11.22
480 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block (SM/07779) | SM/07779 | 142.32 | 2517 | RETROFITTING | 100 | WO no issued | 55 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 78.95 | 76.09
481 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block (SM/07808) | SM/07808 | 89.76 | 1383 | RETROFITTING | 100 | WO no issued | 53 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 16/11/2021 | 47.9 | 47.9
482 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block (SM/07810) | SM/07810 | 83.84 | 1398 | RETROFITTING | 100 | WO no issued | 57 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 08/02/2021 | 48.09 | 48.09
483 | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/09413) | SM/09413 | 564.13 | 2817 | AUGMENTATION | 100 | WO no issued | 85 | 17/11/2021 | 31/12/2023 | 16/08/2023 | 25/01/2022 | 479.51 | 479.42
484 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08702) | SM/08702 | 60.29 | 759 | RETROFITTING | 100 | WO no issued | 100 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 03/06/2021 | 60 | 50.24
485 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. (SM/08713) | SM/08713 | 52.2 | 806 | RETROFITTING | 100 | WO no issued | 53 | 03/09/2021 | 30/04/2022 | 12/06/2023 | 15/01/2021 | 27.42 | 17.36
486 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08716) | SM/08716 | 80.58 | 1113 | RETROFITTING | 100 | WO no issued | 100 | 03/09/2021 | 30/04/2022 | 12/06/2023 | 27/06/2022 | 80.5 | 68.88
487 | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme (SM/07547) | SM/07547 | 41.6 | 880 | RETROFITTING | 100 | WO no issued | 100 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 09/06/2021 | 41.6 | 41.6
488 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme (SM/07822) | SM/07822 | 205.82 | 3222 | RETROFITTING | 100 | WO no issued | 84 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 27/07/2021 | 171.93 | 171.93
489 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block (SM/07778) | SM/07778 | 113.22 | 2395 | RETROFITTING | 100 | WO no issued | 79 | 08/01/2021 | 30/04/2022 | 12/06/2023 | 29/06/2021 | 89.64 | 89.64
490 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme (SM/06962) | SM/06962 | 99.94 | 1829 | RETROFITTING | 100 | WO no issued | 87 | 09/11/2020 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 86.73 | 86.73
491 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme (SM/06964) | SM/06964 | 99.26 | 1798 | RETROFITTING | 100 | WO no issued | 100 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 10/12/2020 | 99.26 | 94.16
492 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme (SM/06966) | SM/06966 | 98.36 | 1871 | RETROFITTING | 100 | WO no issued | 100 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 04/08/2020 | 98.36 | 98.36
493 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme (SM/07825) | SM/07825 | 121.31 | 1867 | RETROFITTING | 100 | WO no issued | 95 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 16/10/2020 | 114.89 | 112.89
494 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block (SM/07830) | SM/07830 | 121.39 | 1922 | RETROFITTING | 100 | WO no issued | 25 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 11/01/2022 | 30.51 | 30.51
495 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block (SM/07809) | SM/07809 | 69.73 | 1133 | RETROFITTING | 100 | WO no issued | 99 | 07/01/2021 | 30/04/2022 | 12/06/2023 | 22/11/2021 | 69.21 | 68.16
496 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block (SM/07812) | SM/07812 | 116.95 | 2474 | RETROFITTING | 100 | WO no issued | 50 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 05/01/2021 | 58.56 | 58.29
497 | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/09495) | SM/09495 | 531.47 | 2747 | AUGMENTATION | 100 | WO no issued | 97 | 19/11/2021 | 31/03/2024 | 16/08/2023 | 31/01/2022 | 513.45 | 513.45
498 | Rejuvenation of Bhalki Water Supply Scheme. (SM/09103) | SM/09103 | 293.35 | 1000 | AUGMENTATION | 100 | WO no issued | 95 | 29/10/2021 | 31/12/2023 | 12/06/2023 | 27/07/2021 | 280.08 | 280.08
499 | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. (SM/09699) | SM/09699 | 323.86 | 1185 | AUGMENTATION | 100 | WO no issued | 91 | 26/11/2021 | 31/03/2024 | 12/06/2023 | 22/12/2021 | 295.46 | 295.46
500 | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. (SM/09700) | SM/09700 | 625.09 | 2498 | AUGMENTATION | 100 | WO no issued | 86 | 26/11/2021 | 31/12/2023 | 16/08/2023 | 27/01/2022 | 534.5 | 534.5
501 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B (SM/13043) | SM/13043 | 109.18 | 1775 | RETROFITTING | 100 | WO no issued | 37 | 29/09/2022 | 31/03/2024 | 12/06/2023 | 08/10/2021 | 40.76 | 40.76
502 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme (SM/06971) | SM/06971 | 99.89 | 1937 | RETROFITTING | 100 | WO no issued | 81 | 09/11/2020 | 31/07/2022 | 12/06/2023 | 10/08/2020 | 80.46 | 79.28
503 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (SM/08708) | SM/08708 | 112.85 | 1804 | RETROFITTING | 100 | WO no issued | 76 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 02/05/2022 | 85.3 | 85.3
504 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS (SM/06753) | SM/06753 | 53.37 | 917 | RETROFITTING | 100 | WO no issued | 28 | 18/09/2020 | 31/12/2023 | 12/06/2023 | 04/08/2020 | 15 | 15
505 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block (SM/07857) | SM/07857 | 110.71 | 2342 | RETROFITTING | 100 | WO no issued | 100 | 14/01/2021 | 30/04/2022 | 12/06/2023 | 26/02/2021 | 110.71 | 110.71
506 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block (SM/07873) | SM/07873 | 47.08 | 996 | RETROFITTING | 100 | WO no issued | 75 | 19/01/2021 | 30/04/2022 | 12/06/2023 | 16/08/2021 | 35.45 | 35.45
507 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS (SM/06769) | SM/06769 | 89.62 | 1732 | RETROFITTING | 100 | WO no issued | 100 | 22/09/2020 | 30/04/2022 | 12/06/2023 | 12/02/2021 | 89.62 | 89.62
508 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block (SM/07824) | SM/07824 | 117.09 | 1830 | RETROFITTING | 100 | WO no issued | 79 | 08/01/2021 | 30/04/2022 | 12/06/2023 | 10/12/2020 | 92.5 | 92.5
509 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block (SM/07811) | SM/07811 | 65.25 | 1041 | RETROFITTING | 100 | WO no issued | 100 | 07/01/2021 | 30/04/2022 | 12/06/2023 | 22/09/2020 | 65.25 | 65.25
510 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. (SM/08709) | SM/08709 | 327.79 | 5528 | RETROFITTING | 100 | WO no issued | 100 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 09/11/2021 | 327.61 | 327.61
511 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block (SM/07818) | SM/07818 | 122.01 | 2581 | RETROFITTING | 100 | WO no issued | 99 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 120.25 | 120.25
512 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS (SM/06746) | SM/06746 | 72.6 | 1075 | RETROFITTING | 100 | WO no issued | 97 | 18/09/2020 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 70.34 | 70.29
513 | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme (SM/07550) | SM/07550 | 94.55 | 2000 | RETROFITTING | 100 | WO no issued | 99 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 18/02/2021 | 93.95 | 93.95
514 | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme (SM/07556) | SM/07556 | 52.23 | 816 | RETROFITTING | 100 | WO no issued | 49 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 16/10/2020 | 25.42 | 25.32
515 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block (SM/07798) | SM/07798 | 88.92 | 1881 | RETROFITTING | 100 | WO no issued | 100 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 15/02/2021 | 88.84 | 88.84
516 | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme (SM/07544) | SM/07544 | 73.32 | 1551 | RETROFITTING | 100 | WO no issued | 100 | 31/12/2020 | 30/04/2022 | 12/06/2023 | 25/09/2020 | 73.17 | 73.12
517 | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio (SM/12116) | SM/12116 | 73.22 | 900 | AUGMENTATION | 100 | WO no issued | 73 | 07/09/2022 |  | 12/06/2023 | 18/04/2022 | 53.15 | 53.15
518 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block (SM/07806) | SM/07806 | 26.44 | 410 | RETROFITTING | 100 | WO no issued | 68 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 05/01/2021 | 17.88 | 17.88
519 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme (SM/06963) | SM/06963 | 99.85 | 1751 | RETROFITTING | 100 | WO no issued | 100 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 25/09/2020 | 99.85 | 96.46
520 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme (SM/06965) | SM/06965 | 91.43 | 1691 | RETROFITTING | 100 | WO no issued | 51 | 09/11/2020 | 31/12/2023 | 12/06/2023 | 02/02/2021 | 46.39 | 44.78
521 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme (SM/06969) | SM/06969 | 83.79 | 1429 | RETROFITTING | 100 | WO no issued | 100 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 10/08/2020 | 83.79 | 83.72
522 | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme (SM/07546) | SM/07546 | 95.87 | 2028 | RETROFITTING | 100 | WO no issued | 70 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 02/02/2021 | 67.22 | 67.22
523 | Providing Functional Household Tap Connection (FHTC) under the command area of Chandutia Piped Water Supply Scheme (SM/07554) | SM/07554 | 26.82 | 413 | RETROFITTING | 100 | WO no issued | 19 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 04/01/2022 | 5 | 5
524 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block (SM/07859) | SM/07859 | 134.62 | 2550 | RETROFITTING | 100 | WO no issued | 96 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 13/07/2021 | 128.92 | 128.92
525 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme (SM/07801) | SM/07801 | 96.93 | 1538 | RETROFITTING | 100 | WO no issued | 67 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 16/10/2020 | 64.78 | 64.75
526 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block (SM/07867) | SM/07867 | 168.95 | 2784 | RETROFITTING | 100 | WO no issued | 66 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 18/09/2020 | 110.9 | 110.9
527 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS (SM/06771) | SM/06771 | 91.38 | 1583 | RETROFITTING | 100 | WO no issued | 99 | 22/09/2020 | 30/04/2022 | 12/06/2023 | 07/12/2020 | 90.84 | 90.84
528 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block (SM/07815) | SM/07815 | 162.76 | 3443 | RETROFITTING | 100 | WO no issued | 79 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 22/02/2021 | 127.92 | 127.92
529 | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District (SM/09405) | SM/09405 | 262.41 | 1240 | AUGMENTATION | 100 | WO no issued | 100 | 17/11/2021 | 31/03/2024 | 16/08/2023 | 31/01/2022 | 262.41 | 262.41
530 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. (SM/08711) | SM/08711 | 211.86 | 3285 | RETROFITTING | 100 | WO no issued | 90 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 06/09/2021 | 189.68 | 189.68
531 | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. (SM/09713) | SM/09713 | 594.6 | 2306 | AUGMENTATION | 100 | WO no issued | 85 | 26/11/2021 | 31/12/2023 | 16/08/2023 | 25/10/2021 | 504.25 | 504.25
532 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS (SM/06745) | SM/06745 | 78.36 | 1563 | RETROFITTING | 100 | WO no issued | 100 | 18/09/2020 | 30/04/2022 | 12/06/2023 | 08/10/2021 | 78.36 | 64
533 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme (SM/06970) | SM/06970 | 70.91 | 1184 | RETROFITTING | 100 | WO no issued | 86 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 11/11/2020 | 60.95 | 60.95
534 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme (SM/06972) | SM/06972 | 99.97 | 1996 | RETROFITTING | 100 | WO no issued | 85 | 09/11/2020 | 30/04/2022 | 12/06/2023 | 21/09/2020 | 84.84 | 84.84
535 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS (SM/06750) | SM/06750 | 58.89 | 1006 | RETROFITTING | 100 | WO no issued | 100 | 18/09/2020 | 30/04/2022 | 12/06/2023 | 05/02/2021 | 58.89 | 49.8
536 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS (SM/06751) | SM/06751 | 99.03 | 1898 | RETROFITTING | 100 | WO no issued | 99 | 18/09/2020 | 30/04/2022 | 12/06/2023 | 02/12/2020 | 98.04 | 98.04
537 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block (SM/07855) | SM/07855 | 184.84 | 3912 | RETROFITTING | 100 | WO no issued | 100 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 24/02/2021 | 184.75 | 184.75
538 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block (SM/07804) | SM/07804 | 79.59 | 1262 | RETROFITTING | 100 | WO no issued | 64 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 16/10/2020 | 51.33 | 51.33
539 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme (SM/07865) | SM/07865 | 106.28 | 1651 | RETROFITTING | 100 | WO no issued | 46 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 10/12/2020 | 48.72 | 48.72
540 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block (SM/07782) | SM/07782 | 117.85 | 2001 | RETROFITTING | 100 | WO no issued | 100 | 08/01/2021 | 30/04/2022 | 12/06/2023 | 06/09/2021 | 117.85 | 117.85
541 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08715) | SM/08715 | 143.24 | 2156 | RETROFITTING | 100 | WO no issued | 43 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 17/12/2021 | 61.21 | 61.21
542 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08700) | SM/08700 | 63.32 | 858 | RETROFITTING | 100 | WO no issued | 60 | 01/09/2021 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 37.92 | 37.92
543 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme (SM/07201) | SM/07201 | 47.47 | 515 | RETROFITTING | 100 | WO no issued | 34 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 04/08/2020 | 15.97 | 14.79
544 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme (SM/07202) | SM/07202 | 46.9 | 503 | RETROFITTING | 100 | WO no issued | 50 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 01/10/2020 | 23.34 | 23.34
545 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme (SM/07203) | SM/07203 | 47.76 | 521 | RETROFITTING | 100 | WO no issued | 50 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 30/09/2020 | 23.99 | 22.44
546 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme (SM/07204) | SM/07204 | 99.8 | 1976 | RETROFITTING | 100 | WO no issued | 63 | 08/12/2020 | 31/12/2023 | 12/06/2023 | 10/08/2020 | 62.87 | 62.87
547 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS (SM/06747) | SM/06747 | 39.12 | 567 | RETROFITTING | 100 | WO no issued | 25 | 18/09/2020 | 31/12/2023 | 12/06/2023 | 25/09/2020 | 9.84 | 9.84
548 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS (SM/06748) | SM/06748 | 99.68 | 1827 | RETROFITTING | 100 | WO no issued | 100 | 18/09/2020 | 30/04/2022 | 12/06/2023 | 07/12/2020 | 99.68 | 99.68
549 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block (SM/07802) | SM/07802 | 28.42 | 446 | RETROFITTING | 100 | WO no issued | 90 | 07/01/2021 | 30/04/2022 | 12/06/2023 | 18/02/2021 | 25.53 | 25.53
550 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block (SM/07803) | SM/07803 | 71.15 | 1103 | RETROFITTING | 100 | WO no issued | 53 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 18/02/2021 | 38 | 38
551 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block (SM/07805) | SM/07805 | 46.03 | 713 | RETROFITTING | 100 | WO no issued | 39 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 16/10/2020 | 18.08 | 18.08
552 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block (SM/07807) | SM/07807 | 62.17 | 1017 | RETROFITTING | 100 | WO no issued | 69 | 07/01/2021 | 31/12/2023 | 12/06/2023 | 05/01/2021 | 42.7 | 42.7
553 | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) (SM/09407) | SM/09407 | 159.5 | 1813 | AUGMENTATION | 100 | WO no issued | 71 | 17/11/2021 | 31/12/2023 | 03/10/2023 | 23/02/2022 | 113.99 | 112.32
554 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS (SM/06772) | SM/06772 | 74.63 | 1157 | RETROFITTING | 100 | WO no issued | 75 | 22/09/2020 | 31/12/2023 | 12/06/2023 | 18/02/2021 | 55.92 | 55.92
555 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08707) | SM/08707 | 181.66 | 3140 | RETROFITTING | 100 | WO no issued | 31 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 17/01/2022 | 56.58 | 56.58
556 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme (SM/06967) | SM/06967 | 81.42 | 1490 | RETROFITTING | 100 | WO no issued | 52 | 09/11/2020 | 31/12/2023 | 12/06/2023 | 14/10/2020 | 42.26 | 42.26
557 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS (SM/06752) | SM/06752 | 81.95 | 1308 | RETROFITTING | 100 | WO no issued | 100 | 18/09/2020 | 30/04/2022 | 12/06/2023 | 07/08/2020 | 81.95 | 81.63
558 | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme (SM/07551) | SM/07551 | 57.39 | 1214 | RETROFITTING | 100 | WO no issued | 84 | 31/12/2020 | 30/04/2022 | 12/06/2023 | 21/06/2021 | 48.31 | 48.31
559 | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme (SM/07552) | SM/07552 | 92.04 | 1610 | RETROFITTING | 100 | WO no issued | 77 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 16/11/2021 | 70.62 | 70.62
560 | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme (SM/07553) | SM/07553 | 99.79 | 1536 | RETROFITTING | 100 | WO no issued | 98 | 31/12/2020 | 31/12/2023 | 12/06/2023 | 01/12/2020 | 97.35 | 97.35
561 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block (SM/07866) | SM/07866 | 283.41 | 4796 | RETROFITTING | 100 | WO no issued | 98 | 14/01/2021 | 31/12/2023 | 12/06/2023 | 12/02/2021 | 278.17 | 278.17
562 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS (SM/06768) | SM/06768 | 37.98 | 583 | RETROFITTING | 100 | WO no issued | 65 | 22/09/2020 | 31/12/2023 | 12/06/2023 | 09/07/2020 | 24.65 | 24.65
563 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS (SM/06770) | SM/06770 | 46.11 | 607 | RETROFITTING | 100 | WO no issued | 83 | 22/09/2020 | 31/12/2023 | 12/06/2023 | 07/10/2020 | 38.3 | 38.3
564 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS (SM/06773) | SM/06773 | 60.25 | 1113 | RETROFITTING | 100 | WO no issued | 100 | 22/09/2020 | 31/12/2023 | 12/06/2023 | 07/12/2020 | 60.25 | 60.22
565 | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. (SM/08706) | SM/08706 | 99.81 | 1552 | RETROFITTING | 100 | WO no issued | 37 | 03/09/2021 | 31/12/2023 | 12/06/2023 | 11/01/2022 | 36.56 | 36.56
566 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) (SM/08717) | SM/08717 | 46.27 | 671 | RETROFITTING | 100 | WO no issued | 99 | 03/09/2021 | 30/04/2022 | 12/06/2023 | 06/09/2021 | 46 | 40.97
567 | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. (SM/09715) | SM/09715 | 523.43 | 1708 | AUGMENTATION | 100 | WO no issued | 69 | 26/11/2021 | 31/03/2024 | 03/10/2023 | 14/01/2022 | 362.58 | 358.82
568 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (SM/10059) | SM/10059 | 79.18 | 559 | AUGMENTATION | 100 | WO no issued | 77 | 25/01/2022 | 31/12/2023 | 16/08/2023 | 31/01/2022 | 61.07 | 61.07
569 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B (SM/08699) | SM/08699 | 198.59 | 3292 | RETROFITTING | 100 | WO no issued | 51 | 01/09/2021 | 30/04/2022 | 12/06/2023 | 14/01/2022 | 102.1 | 102.1
570 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block (SM/07826) | SM/07826 | 104.89 | 1637 | RETROFITTING | 100 | WO no issued | 34 | 08/01/2021 | 31/12/2023 | 12/06/2023 | 09/02/2021 | 35.72 | 35.72
571 | Annual Procurement of Chemicals, Consumables and Glassware for water testing Laboratories. (SM/06624) | SM/06624 | 60.16 | 0 | SUPPORT-WQMSP | 100 | WO no issued | 0 | 05/02/2020 | 28/02/2021 | 31/08/2020 | 21/09/2020 | 0 | 0
Total |  |  | 329887.48 | 1147059 | [8 empty] | 93852.86 | 90839.22