## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. (SM/08994) | SM/08994 | 294.27 | 0 | DISASTER | 0 | 0% Physical | 0 | 29/10/2021 | 31/03/2024 | 14/08/2025 | 21/05/2021 | 0 | 0
2 | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) (SM/10757) | SM/10757 | 40.92 | 0 | DISASTER | 0 | 0% Physical | 0 | 23/05/2022 | 31/03/2026 | 14/08/2025 | 08/06/2020 | 0 | 0
3 | SULANGGARI Piped Water Supply Scheme (SM/14634) | SM/14634 | 1224.19 | 3786 | NEW | 0 | 0% Physical | 3 | 31/01/2023 | 31/12/2025 | 14/08/2025 | 20/04/2023 | 33 | 33
4 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Deganga Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15770) | SM/15770 | 117.36 | 0 | SOLARISATION | 0 | WO no issued | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 |  | 0 | 0
5 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Habra - I and Sandeshkhali - I & II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15760) | SM/15760 | 917.53 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
6 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bongaon Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15765) | SM/15765 | 565.45 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
7 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Baduria Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15766) | SM/15766 | 266.72 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
8 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bagda Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15769) | SM/15769 | 437.43 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 02/11/2023 | 0 | 0
9 | SURFACE BASED PWSS FOR BARASAT-II BLOCK (SM/19040) | SM/19040 | 9483.34 | 0 | AUGMENTATION | 0 | 0% Physical | 28 | 17/11/2023 | 31/12/2025 | 14/08/2025 | 25/01/2024 | 2675.15 | 2675.15
10 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Minakhan, Hingalganj and Amdanga Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15764) | SM/15764 | 714.82 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 02/11/2023 | 0 | 0
11 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Basirhat- II Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15761) | SM/15761 | 426.76 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
12 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13543) | SM/13543 | 720.77 | 11904 | RETROFITTING | 0 | 0% Physical | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/09/2023 | 0 | 0
13 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13545) | SM/13545 | 652.34 | 10384 | RETROFITTING | 0 | 0% Physical | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/09/2023 | 0 | 0
14 | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. (SM/15559) | SM/15559 | 308.06 | 750 | AUGMENTATION | 0 | 0% Physical | 13 | 16/02/2023 | 31/12/2025 | 14/08/2025 | 26/05/2023 | 39.04 | 39.04
15 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Basirhat- I Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15767) | SM/15767 | 341.41 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
16 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Barrackpur-II and Sandeshkhali-I Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/17172) | SM/17172 | 117.36 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/03/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
17 | TARULIA Piped Water Supply Scheme (SM/18598) | SM/18598 | 1481.95 | 4266 | NEW | 0 | 0% Physical | 1 | 31/07/2023 | 02/08/2025 | 14/08/2025 | 11/08/2023 | 19.7 | 19.7
18 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13546) | SM/13546 | 870.02 | 14980 | RETROFITTING | 0 | 0% Physical | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/09/2023 | 0 | 0
19 | TEGHARIA Piped Water Supply Scheme (SM/16457) | SM/16457 | 806.96 | 1445 | NEW | 0 | 0% Physical | 2 | 03/03/2023 | 31/12/2025 | 14/08/2025 | 20/04/2023 | 14.91 | 14.91
20 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Barasat- I & II And Habra-II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15762) | SM/15762 | 608.13 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 16/10/2023 | 0 | 0
21 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Gaighata & Swarupnagar Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15768) | SM/15768 | 629.47 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 02/11/2023 | 0 | 0
22 | JATRAGACHHI Piped Water Supply Scheme (SM/16625) | SM/16625 | 940.04 | 2053 | NEW | 0 | 0% Physical | 2 | 14/03/2023 | 31/12/2025 | 14/08/2025 | 20/04/2023 | 19.7 | 19.7
23 | BARDASIA Piped Water Supply Scheme (SM/16626) | SM/16626 | 961.59 | 1968 | NEW | 0 | 0% Physical | 2 | 14/03/2023 | 31/12/2025 | 14/08/2025 | 20/04/2023 | 19.29 | 19.29
24 | KOLA Piped Water Supply Scheme (SM/18591) | SM/18591 | 1532.91 | 3283 | NEW | 0 | 0% Physical | 4 | 31/07/2023 | 02/08/2025 | 14/08/2025 | 14/08/2023 | 66.69 | 66.69
25 | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Hasnabad Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. (SM/15763) | SM/15763 | 384.08 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 31/10/2023 | 0 | 0
26 | GHUNI Piped Water Supply Scheme (SM/18537) | SM/18537 | 1721.16 | 5806 | NEW | 0 | 0% Physical | 1 | 26/07/2023 | 02/08/2025 | 14/08/2025 | 31/07/2023 | 12.92 | 12.92
27 | Expenditure Audit for Division under Programme Fund & Support Fund related to NRDWP (Presently JJM) (SM/08583) | SM/08583 | 12.98 | 0 | SUPPORT-ADMIN / ESTABLISHMENT | 0 | WO no issued | 0 | 26/02/2021 |  | 31/03/2022 |  | 0 | 0
28 | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for the office premises of North 24 Parganas W/S Division-I, Public Health Engineering Directorate, Govt. of West Be (SM/11648) | SM/11648 | 55.66 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 27/07/2022 |  | 29/07/2022 | 06/02/2023 | 0 | 0
29 | Development of custom Document Archival System (DAS) software and selection of Service Provider for scanning / digitalization of documents for the Office of The Superintending Engineer, Eastern Circle, P.H.E. Dte. at Janasswasthya Karigari Bhawan, Public (SM/16510) | SM/16510 | 62.9 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 03/03/2023 |  | 06/03/2023 | 28/03/2023 | 0 | 0
30 | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. (SM/18144) | SM/18144 | 196.41 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 | 24/04/2023 | 0 | 0
31 | Procurement of Computer and peripherals for the office use in Eastern Mechanical Division, There Sub-Divisions and office of the Superintending Engineer, Mechanical Circle-III, PHE Dte. (SM/19116) | SM/19116 | 37.55 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 22/12/2023 |  | 22/12/2023 | 27/08/2024 | 0 | 0
32 | Survey of Drinking water & Sanitary. Arrangement of Schools, AWC within the District of North 24 paraganas (SM/09035) | SM/09035 | 13.89 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 30/10/2021 |  | 02/11/2021 | 27/11/2020 | 0 | 0
33 | Drinking water sample collection and testing through Field Test Kit FTKs by ASHAs and uploading test result to WQMIS for three months related to Water Quality Monitoring and Surveillance programme under Jal Jeevan Mission (SM/13736) | SM/13736 | 28.82 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/11/2022 |  | 18/11/2022 | 13/02/2023 | 0 | 0
34 | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/12048) | SM/12048 | 13.73 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 01/09/2022 |  | 05/09/2022 | 29/03/2022 | 0 | 0
35 | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. (SM/19088) | SM/19088 | 42.89 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 29/08/2023 | 0 | 0
36 | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. (SM/06629) | SM/06629 | 136.49 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 30/04/2021 | 26/11/2021 | 0 | 0
37 | Renovation of District Laboratory for NABL set-up under Barasat Division. (SM/08691) | SM/08691 | 17.08 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/08/2021 |  | 31/08/2021 | 24/12/2021 | 0 | 0
38 | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 (SM/10759) | SM/10759 | 25 | 0 | SUPPORT-R&D | 0 | 0% Physical | 0 | 23/05/2022 |  | 23/05/2022 | 12/07/2022 | 0 | 0
39 | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 (SM/10740) | SM/10740 | 17.79 | 0 | SUPPORT-R&D | 0 | 0% Physical | 0 | 19/05/2022 |  | 20/05/2022 | 12/07/2022 | 0 | 0
40 | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. (SM/13735) | SM/13735 | 21.42 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 17/11/2022 |  | 18/11/2022 |  | 0 | 0
41 | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) (SM/18143) | SM/18143 | 108.45 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/03/2023 |  | 31/03/2023 | 12/02/2024 | 0 | 0
42 | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. (SM/13407) | SM/13407 | 19.05 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 02/11/2022 |  | 04/11/2022 |  | 0 | 0
43 | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. (SM/19259) | SM/19259 | 186 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 29/09/2023 | 0 | 0
44 | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. (SM/13849) | SM/13849 | 18.63 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 25/11/2022 |  | 26/11/2022 | 12/11/2021 | 0 | 0
45 | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. (SM/19323) | SM/19323 | 49.45 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 26/12/2024 |  | 27/12/2024 |  | 0 | 0
46 | Drinking water sample collection & testing through field test kits (FTKs) & uploading charges for the same related to Water Quality monitoring & Surveillance Programme Under JJM (SM/09243) | SM/09243 | 25.34 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 03/11/2021 |  | 08/11/2021 |  | 0 | 0
47 | Engagement of Laboratory personnel to operate Atomic Absorption Spectrophotometer, Chemist for testing of bottling plant samples (PRANDHARA) & Data entry operator for BIS Documentation works as per IS 14543-2016 protocol including supply, delivery, instal (SM/10734) | SM/10734 | 13.16 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/05/2022 |  | 19/05/2022 | 29/06/2022 | 0 | 0
48 | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. (SM/11625) | SM/11625 | 104.68 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/07/2022 |  | 28/07/2022 | 31/12/2021 | 0 | 0
49 | DPR for Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission under Barasat Division, P.H.E. Dte. (SM/12896) | SM/12896 | 78.13 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 23/09/2022 |  | 26/09/2022 | 09/08/2024 | 0 | 0
50 | Improvement of IT Infrastructure by providing Desktop computers, printers, copiers and its peripherals for Barasat Arsenic Division & Barasat Arsenic Sub Division Offices, PHE Dte. (SM/17634) | SM/17634 | 15.34 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 22/03/2023 |  | 24/03/2023 |  | 0 | 0
51 | Supply, Installation, Commissioning & Monitoring of INTELLIGENT Disinfection Systems for the complete, desired. Continuous, constant & external power free disinfection of drinking water (via the national JJM approved green technology) supplied through (PW (SM/14516) | SM/14516 | 12.59 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 20/01/2023 |  | 29/01/2023 | 27/01/2023 | 0 | 0
52 | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. (SM/06633) | SM/06633 | 10.88 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 30/04/2021 | 19/01/2021 | 0 | 0
53 | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. (SM/08690) | SM/08690 | 17.47 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/08/2021 |  | 31/08/2021 | 24/12/2021 | 0 | 0
54 | Engagement of implementation support agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support activities at North 24 Parganas District (SM/08991) | SM/08991 | 490.66 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 20/05/2022 | 0 | 0
55 | Project Management Services and Engineering Consultancy Job for 1. Integrated Surface Water Based Piped Water Supply Scheme for arsenic affected block of Baduria, Basirhat-I & II, Deganga & Swarupnagar in North 24 Parganas District & 2. Surface Water Bas (SM/18477) | SM/18477 | 1688.7 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 24/07/2023 |  | 26/07/2023 |  | 0 | 0
56 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18264) | SM/18264 | 1347.55 | 2796 | AUGMENTATION | 1 | Delayed | 0 | 21/06/2023 | 31/03/2027 | 14/08/2025 | 12/07/2023 | 4.29 | 4.29
57 | Kaugachhi Zone-III Piped Water Supply Scheme (SM/14502) | SM/14502 | 696.59 | 1061 | NEW | 1 | Delayed | 1 | 20/01/2023 | 31/12/2026 | 14/08/2025 | 02/02/2023 | 4.95 | 4.95
58 | Kaugachhi Zone-I Piped Water Supply Scheme (SM/14499) | SM/14499 | 697.72 | 1061 | NEW | 1 | Delayed | 1 | 20/01/2023 | 31/12/2026 | 14/08/2025 | 02/02/2023 | 4.96 | 4.96
59 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18258) | SM/18258 | 1544.28 | 6162 | AUGMENTATION | 1 | Delayed | 0 | 21/06/2023 | 11/07/2025 | 14/08/2025 | 26/07/2023 | 4.88 | 4.88
60 | Kaugachhi Zone-II Piped Water Supply Scheme (SM/14500) | SM/14500 | 924.3 | 1582 | NEW | 1 | Delayed | 6 | 20/01/2023 | 31/12/2026 | 14/08/2025 | 02/02/2023 | 52.21 | 52.21
61 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07604) | SM/07604 | 56.87 | 889 | RETROFITTING | 2 | Delayed | 97 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 01/02/2021 | 55.28 | 55.28
62 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) (SM/07605) | SM/07605 | 73.51 | 1477 | RETROFITTING | 2 | Delayed | 98 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 71.79 | 71.79
63 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07607) | SM/07607 | 65.75 | 962 | RETROFITTING | 2 | Delayed | 97 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 01/02/2021 | 63.46 | 63.46
64 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18265) | SM/18265 | 1145.89 | 2703 | AUGMENTATION | 5 | Delayed | 5 | 21/06/2023 | 31/12/2026 | 14/08/2025 | 12/07/2023 | 52.2 | 52.2
65 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15817) | SM/15817 | 1177.21 | 1169 | AUGMENTATION | 5 | Delayed | 1 | 20/02/2023 | 31/12/2026 | 14/08/2025 | 26/07/2022 | 11.23 | 11.23
66 | Gar Shyamnagar Piped Water Supply Scheme (SM/14504) | SM/14504 | 920.61 | 1723 | NEW | 5 | Delayed | 2 | 20/01/2023 | 31/12/2026 | 14/08/2025 | 02/02/2023 | 18.11 | 18.11
67 | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. (SM/14501) | SM/14501 | 121.26 | 129 | NEW | 5 | Delayed | 25 | 20/01/2023 | 31/10/2025 | 14/08/2025 | 11/01/2023 | 30.01 | 30.01
68 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07606) | SM/07606 | 40.1 | 467 | RETROFITTING | 6 | Delayed | 93 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 37.28 | 37.28
69 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18263) | SM/18263 | 1271.37 | 2648 | AUGMENTATION | 7 | Delayed | 2 | 21/06/2023 | 31/12/2026 | 14/08/2025 | 12/07/2023 | 27.7 | 27.7
70 | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC (SM/11600) | SM/11600 | 822.65 | 1849 | AUGMENTATION | 10 | Delayed | 57 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 20/12/2022 | 470.34 | 470.34
71 | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. (SM/10758) | SM/10758 | 1349.65 | 3750 | AUGMENTATION | 10 | Delayed | 8 | 23/05/2022 | 31/12/2026 | 14/08/2025 | 18/01/2021 | 106.85 | 106.85
72 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC (SM/11525) | SM/11525 | 815.39 | 2881 | AUGMENTATION | 10 | Delayed | 58 | 19/07/2022 | 31/07/2026 | 14/08/2025 | 09/12/2022 | 470.3 | 470.3
73 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. (SM/11664) | SM/11664 | 1010.56 | 1711 | AUGMENTATION | 10 | Delayed | 64 | 27/07/2022 | 30/04/2025 | 14/08/2025 | 01/11/2022 | 646.43 | 646.43
74 | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC (SM/11665) | SM/11665 | 449.33 | 1413 | AUGMENTATION | 10 | Delayed | 41 | 27/07/2022 | 30/09/2025 | 14/08/2025 | 07/03/2022 | 184.13 | 184.13
75 | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte (SM/11661) | SM/11661 | 486.98 | 1024 | AUGMENTATION | 11 | Delayed | 37 | 28/07/2022 | 31/08/2025 | 14/08/2025 | 19/09/2022 | 180.99 | 180.99
76 | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. (SM/19110) | SM/19110 | 874.94 | 0 | AUGMENTATION | 12 | Delayed | 9 | 18/12/2023 | 31/03/2026 | 14/08/2025 | 02/02/2024 | 82.75 | 82.75
77 | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. (SM/11555) | SM/11555 | 679.03 | 2114 | AUGMENTATION | 12 | Delayed | 10 | 22/07/2022 | 31/12/2026 | 14/08/2025 | 18/01/2021 | 64.71 | 50.73
78 | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/13420) | SM/13420 | 448.62 | 567 | AUGMENTATION | 13 | Delayed | 47 | 02/11/2022 | 31/08/2025 | 14/08/2025 | 18/01/2023 | 211.34 | 209.44
79 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13537) | SM/13537 | 660.09 | 12085 | RETROFITTING | 15 | Delayed | 12 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/10/2023 | 78.14 | 78.14
80 | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. (SM/18712) | SM/18712 | 1055.5 | 1753 | AUGMENTATION | 15 | Delayed | 19 | 04/08/2023 | 02/08/2025 | 14/08/2025 | 28/08/2023 | 205.53 | 185.07
81 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/14539) | SM/14539 | 1034.29 | 17377 | RETROFITTING | 15 | Delayed | 0 | 30/01/2023 | 02/08/2025 | 14/08/2025 | 18/10/2023 | 0 | 0
82 | RAIGACHHI Piped Water Supply Scheme. (SM/18599) | SM/18599 | 1046.62 | 2070 | NEW | 15 | Delayed | 2 | 31/07/2023 | 02/08/2025 | 14/08/2025 | 11/08/2023 | 20.6 | 20.6
83 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12730) | SM/12730 | 1212.9 | 4443 | AUGMENTATION | 16 | Delayed | 12 | 21/09/2022 | 31/12/2026 | 14/08/2025 | 01/04/2022 | 145.36 | 145.36
84 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12728) | SM/12728 | 1428.95 | 5189 | AUGMENTATION | 19 | Delayed | 13 | 21/09/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 192.5 | 192.5
85 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13521) | SM/13521 | 961.66 | 16930 | RETROFITTING | 20 | Delayed | 41 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 16/10/2023 | 390.88 | 0
86 | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC (SM/14162) | SM/14162 | 2047.08 | 3166 | AUGMENTATION | 20 | Delayed | 18 | 05/01/2023 | 02/08/2025 | 14/08/2025 | 10/12/2021 | 364.87 | 364.87
87 | Augmentation of Hingalganj Piped water supply scheme Zone-II (SM/14513) | SM/14513 | 1151.69 | 0 | AUGMENTATION | 20 | Delayed | 36 | 20/01/2023 | 31/03/2026 | 14/08/2025 | 08/04/2022 | 409.3 | 409.3
88 | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC (SM/13405) | SM/13405 | 3013.93 | 10427 | AUGMENTATION | 20 | Delayed | 43 | 21/10/2022 | 31/05/2026 | 14/08/2025 | 26/04/2023 | 1302.49 | 1302.49
89 | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/13761) | SM/13761 | 353.38 | 279 | AUGMENTATION | 20 | Delayed | 52 | 18/11/2022 | 31/08/2025 | 14/08/2025 | 01/11/2022 | 185.46 | 185.46
90 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18259) | SM/18259 | 1062.34 | 2438 | AUGMENTATION | 20 | Delayed | 10 | 21/06/2023 | 31/12/2026 | 14/08/2025 | 12/07/2023 | 102.19 | 100.91
91 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/14541) | SM/14541 | 1061.62 | 32281 | RETROFITTING | 22 | Delayed | 12 | 30/01/2023 | 31/12/2025 | 14/08/2025 | 08/08/2023 | 126.15 | 126.15
92 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12564) | SM/12564 | 1554.33 | 4883 | AUGMENTATION | 25 | Delayed | 20 | 14/09/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 312.64 | 312.64
93 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18262) | SM/18262 | 1313.24 | 2191 | AUGMENTATION | 25 | Delayed | 7 | 21/06/2023 | 31/12/2026 | 14/08/2025 | 12/07/2023 | 93.75 | 93.22
94 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12372) | SM/12372 | 1325.35 | 4012 | AUGMENTATION | 26 | Delayed | 19 | 13/09/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 246.37 | 246.37
95 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11708) | SM/11708 | 593.08 | 1360 | AUGMENTATION | 26 | Delayed | 57 | 29/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 338.82 | 338.82
96 | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11706) | SM/11706 | 328.48 | 174 | AUGMENTATION | 26 | Delayed | 28 | 29/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 93.05 | 93.05
97 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13544) | SM/13544 | 580.6 | 9800 | RETROFITTING | 26 | Delayed | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/09/2023 | 0 | 0
98 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18261) | SM/18261 | 1392.6 | 3740 | AUGMENTATION | 27 | Delayed | 23 | 21/06/2023 | 31/12/2026 | 14/08/2025 | 12/07/2023 | 320.55 | 316.03
99 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. (SM/13434) | SM/13434 | 892.16 | 2481 | AUGMENTATION | 27 | Delayed | 23 | 02/11/2022 | 30/06/2026 | 14/08/2025 | 08/09/2023 | 203.03 | 203.03
100 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11826) | SM/11826 | 914.47 | 2983 | AUGMENTATION | 27 | Delayed | 22 | 16/08/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 198.91 | 198.91
101 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11922) | SM/11922 | 737.22 | 2477 | AUGMENTATION | 28 | Delayed | 25 | 22/08/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 181.08 | 181.08
102 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11827) | SM/11827 | 805.42 | 3690 | AUGMENTATION | 28 | Delayed | 19 | 16/08/2022 | 31/12/2026 | 14/08/2025 | 24/03/2022 | 153.39 | 153.39
103 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12565) | SM/12565 | 1267.76 | 3621 | AUGMENTATION | 29 | Delayed | 22 | 14/09/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 273.36 | 273.36
104 | Khariat Abad Piped Water Supply Scheme (SM/15829) | SM/15829 | 1521.01 | 1936 | NEW | 30 | Delayed | 12 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 21/02/2022 | 178.08 | 135.76
105 | Ketarchak Piped Water Supply Scheme (SM/15833) | SM/15833 | 1333.54 | 1519 | NEW | 30 | Delayed | 10 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 02/02/2022 | 129.74 | 129.74
106 | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. (SM/13469) | SM/13469 | 1151.34 | 6478 | AUGMENTATION | 30 | Delayed | 19 | 02/11/2022 | 02/08/2025 | 14/08/2025 | 10/08/2023 | 224.47 | 224.47
107 | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme (SM/15323) | SM/15323 | 1710.38 | 4190 | AUGMENTATION | 30 | Delayed | 30 | 09/02/2023 | 31/03/2026 | 14/08/2025 | 29/08/2022 | 511.51 | 508.98
108 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/15824) | SM/15824 | 1037.4 | 16712 | RETROFITTING | 30 | Delayed | 0 | 20/02/2023 | 02/08/2025 | 14/08/2025 | 16/10/2023 | 0 | 0
109 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas D (SM/13534) | SM/13534 | 621.18 | 11231 | RETROFITTING | 30 | Delayed | 18 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 113.88 | 113.88
110 | Kusangra Piped Water Supply Scheme (SM/15832) | SM/15832 | 1105.8 | 1977 | NEW | 30 | Delayed | 20 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 09/02/2022 | 217.05 | 217.05
111 | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme (SM/13892) | SM/13892 | 1174.01 | 3220 | AUGMENTATION | 30 | Delayed | 27 | 25/11/2022 | 31/03/2026 | 14/08/2025 | 31/08/2022 | 321.69 | 321.69
112 | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme (SM/14490) | SM/14490 | 1562.27 | 3595 | AUGMENTATION | 30 | Delayed | 28 | 20/01/2023 | 31/03/2026 | 14/08/2025 | 18/08/2022 | 438.99 | 437.28
113 | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di (SM/15816) | SM/15816 | 8915.09 | 0 | AUGMENTATION | 30 | Delayed | 28 | 20/02/2023 | 30/06/2026 | 14/08/2025 | 29/09/2022 | 2461.21 | 2460.99
114 | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC (SM/17679) | SM/17679 | 968.81 | 2600 | AUGMENTATION | 30 | Delayed | 23 | 17/03/2023 | 02/08/2025 | 14/08/2025 | 10/08/2023 | 222.24 | 222.24
115 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11941) | SM/11941 | 898.63 | 2055 | AUGMENTATION | 30 | Delayed | 23 | 24/08/2022 | 31/12/2026 | 14/08/2025 | 01/04/2022 | 203.61 | 203.61
116 | Mallik Gheri Piped Water Supply Scheme. (SM/13813) | SM/13813 | 1020.87 | 1847 | NEW | 30 | Delayed | 37 | 23/11/2022 | 30/06/2025 | 14/08/2025 | 10/02/2022 | 378.43 | 378.43
117 | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11659) | SM/11659 | 564.26 | 1405 | AUGMENTATION | 30 | Delayed | 40 | 28/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 224.8 | 224.8
118 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proj (SM/13536) | SM/13536 | 735.64 | 13491 | RETROFITTING | 30 | Delayed | 61 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 451.1 | 451.1
119 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15818) | SM/15818 | 1477.06 | 3626 | AUGMENTATION | 30 | Delayed | 25 | 20/02/2023 | 31/12/2026 | 14/08/2025 | 10/03/2023 | 367.84 | 367.84
120 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11864) | SM/11864 | 806.01 | 1808 | AUGMENTATION | 31 | Delayed | 23 | 17/08/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 187.16 | 187.16
121 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11921) | SM/11921 | 767.04 | 3112 | AUGMENTATION | 31 | Delayed | 25 | 22/08/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 191.61 | 191.61
122 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13527) | SM/13527 | 646.01 | 11462 | RETROFITTING | 32 | Delayed | 18 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 05/10/2023 | 117.84 | 0
123 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/11971) | SM/11971 | 909.24 | 2421 | AUGMENTATION | 34 | Delayed | 29 | 29/08/2022 | 31/12/2026 | 14/08/2025 | 01/04/2022 | 261.76 | 261.76
124 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/13435) | SM/13435 | 1010.75 | 2177 | AUGMENTATION | 34 | Delayed | 33 | 02/11/2022 | 31/12/2026 | 14/08/2025 | 07/11/2022 | 338.3 | 338.3
125 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12563) | SM/12563 | 1134.55 | 5075 | AUGMENTATION | 35 | Delayed | 29 | 14/09/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 328.35 | 328.35
126 | Augmentation of Mathurabil Zone-I in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. (SM/19108) | SM/19108 | 985.92 | 0 | AUGMENTATION | 35 | Delayed | 83 | 18/12/2023 | 31/03/2026 | 14/08/2025 | 02/02/2024 | 814.6 | 814.6
127 | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. (SM/11940) | SM/11940 | 200.23 | 200 | AUGMENTATION | 35 | Delayed | 30 | 24/08/2022 | 31/12/2026 | 14/08/2025 | 08/05/2023 | 59.45 | 59.45
128 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13530) | SM/13530 | 864.01 | 15467 | RETROFITTING | 35 | Delayed | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 0 | 0
129 | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. (SM/18410) | SM/18410 | 1210.72 | 1391 | AUGMENTATION | 36 | Delayed | 25 | 12/07/2023 | 10/08/2025 | 14/08/2025 | 10/08/2023 | 305.21 | 286.62
130 | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC (SM/14161) | SM/14161 | 2784.85 | 8477 | AUGMENTATION | 36 | Delayed | 30 | 05/01/2023 | 02/08/2025 | 14/08/2025 | 07/08/2023 | 847.46 | 747.46
131 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. (SM/12625) | SM/12625 | 1285.8 | 5414 | AUGMENTATION | 36 | Delayed | 30 | 19/09/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 391.88 | 392.63
132 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12383) | SM/12383 | 1036.82 | 2150 | AUGMENTATION | 36 | Delayed | 27 | 13/09/2022 | 31/12/2026 | 14/08/2025 | 05/09/2022 | 282.76 | 282.12
133 | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC (SM/15324) | SM/15324 | 1184.15 | 3785 | AUGMENTATION | 38 | Delayed | 32 | 10/02/2023 | 02/08/2025 | 14/08/2025 | 07/08/2023 | 375.58 | 372.38
134 | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. (SM/14127) | SM/14127 | 494.62 | 1047 | AUGMENTATION | 38 | Delayed | 28 | 02/01/2023 | 31/03/2026 | 14/08/2025 | 20/02/2023 | 138.98 | 138.98
135 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/13902) | SM/13902 | 1111.41 | 7593 | AUGMENTATION | 38 | Delayed | 30 | 28/11/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 328.63 | 328.63
136 | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC (SM/18416) | SM/18416 | 2716.04 | 3561 | AUGMENTATION | 38 | Delayed | 28 | 13/07/2023 | 02/08/2025 | 14/08/2025 | 07/08/2023 | 768.68 | 768.68
137 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13531) | SM/13531 | 678.06 | 12180 | RETROFITTING | 39 | Delayed | 28 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 190.93 | 0
138 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12566) | SM/12566 | 1197.72 | 2636 | AUGMENTATION | 39 | Delayed | 31 | 14/09/2022 | 30/06/2026 | 14/08/2025 | 24/03/2022 | 375.32 | 375.32
139 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/14540) | SM/14540 | 1050.88 | 18376 | RETROFITTING | 40 | Delayed | 25 | 30/01/2023 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 260.09 | 86.1
140 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13532) | SM/13532 | 683.5 | 13185 | RETROFITTING | 40 | Delayed | 22 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 151.25 | 118.25
141 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/13794) | SM/13794 | 932.42 | 2731 | AUGMENTATION | 40 | Delayed | 33 | 22/11/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 310.76 | 310.76
142 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13547) | SM/13547 | 860.32 | 15096 | RETROFITTING | 40 | Delayed | 44 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 13/10/2023 | 375 | 68.48
143 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/14543) | SM/14543 | 1059.55 | 19274 | RETROFITTING | 40 | Delayed | 41 | 30/01/2023 | 02/08/2025 | 14/08/2025 | 16/10/2023 | 437.82 | 437.82
144 | Balibhara Piped Water Supply Scheme (SM/14498) | SM/14498 | 990.89 | 1942 | NEW | 40 | Delayed | 20 | 20/01/2023 | 31/12/2026 | 14/08/2025 | 02/02/2023 | 194.94 | 189.2
145 | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. (SM/13446) | SM/13446 | 867.07 | 4384 | AUGMENTATION | 41 | Delayed | 37 | 02/11/2022 | 31/03/2026 | 14/08/2025 | 16/12/2021 | 322.36 | 322.36
146 | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11707) | SM/11707 | 613.96 | 703 | AUGMENTATION | 41 | Delayed | 54 | 29/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 333.26 | 333.26
147 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje (SM/13533) | SM/13533 | 653.74 | 11911 | RETROFITTING | 42 | Delayed | 40 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 16/10/2023 | 262.06 | 262.06
148 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje (SM/13535) | SM/13535 | 960.53 | 17629 | RETROFITTING | 42 | Delayed | 74 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 16/10/2023 | 713.16 | 713.16
149 | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. (SM/10582) | SM/10582 | 601.04 | 1205 | AUGMENTATION | 42 | Delayed | 32 | 18/04/2022 | 31/12/2026 | 14/08/2025 | 21/03/2022 | 189.53 | 189.53
150 | Atpukur Zone-I Piped Water Supply Scheme (SM/15828) | SM/15828 | 1127.24 | 2029 | NEW | 42 | Delayed | 23 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 02/02/2022 | 255.54 | 240.26
151 | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11662) | SM/11662 | 547.66 | 391 | AUGMENTATION | 44 | Delayed | 53 | 28/07/2022 | 31/08/2025 | 14/08/2025 | 30/12/2021 | 289.48 | 287.13
152 | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) (SM/10559) | SM/10559 | 74.08 | 180 | AUGMENTATION | 44 | Delayed | 49 | 18/04/2022 | 31/08/2025 | 14/08/2025 | 17/06/2022 | 36.19 | 36.19
153 | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. (SM/10607) | SM/10607 | 1098.59 | 3671 | AUGMENTATION | 45 | Delayed | 43 | 19/04/2022 | 31/12/2026 | 14/08/2025 | 18/01/2021 | 468.83 | 468.83
154 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12729) | SM/12729 | 1320.45 | 3297 | AUGMENTATION | 45 | Delayed | 36 | 21/09/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 479.48 | 479.48
155 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13528) | SM/13528 | 764.12 | 13840 | RETROFITTING | 45 | Delayed | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 10/01/2024 | 0 | 0
156 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa (SM/13529) | SM/13529 | 798.89 | 14011 | RETROFITTING | 45 | Delayed | 0 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 10/01/2024 | 0 | 0
157 | Augmentation of Mathurabil Zone-II in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. (SM/19109) | SM/19109 | 940.91 | 0 | AUGMENTATION | 45 | Delayed | 42 | 18/12/2023 | 31/03/2026 | 14/08/2025 | 02/02/2024 | 394.57 | 394.57
158 | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. (SM/10579) | SM/10579 | 1074.06 | 5789 | AUGMENTATION | 46 | Delayed | 41 | 18/04/2022 | 30/06/2026 | 14/08/2025 | 31/12/2021 | 445.21 | 445.21
159 | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. (SM/11556) | SM/11556 | 544.26 | 705 | AUGMENTATION | 46 | Delayed | 33 | 22/07/2022 | 30/06/2026 | 14/08/2025 | 01/04/2022 | 181.22 | 180.66
160 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/13538) | SM/13538 | 863.74 | 16062 | RETROFITTING | 47 | Delayed | 45 | 04/11/2022 | 02/08/2025 | 14/08/2025 | 29/09/2023 | 388.77 | 388.77
161 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/10551) | SM/10551 | 977.41 | 2191 | AUGMENTATION | 47 | Delayed | 63 | 18/04/2022 | 31/08/2025 | 14/08/2025 | 18/08/2022 | 619.52 | 619.52
162 | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte (SM/09039) | SM/09039 | 67.97 | 0 | ANGANWADI | 48 | Delayed | 0 | 30/10/2021 | 31/12/2024 | 14/08/2025 | 18/11/2021 | 0 | 0
163 | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11544) | SM/11544 | 634.45 | 1790 | AUGMENTATION | 48 | Delayed | 54 | 22/07/2022 | 31/08/2025 | 14/08/2025 | 26/09/2022 | 341.74 | 341.74
164 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11663) | SM/11663 | 461.93 | 150 | AUGMENTATION | 48 | Delayed | 50 | 28/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 228.97 | 228.97
165 | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. (SM/11558) | SM/11558 | 694.76 | 2875 | AUGMENTATION | 49 | Delayed | 59 | 22/07/2022 | 31/08/2025 | 14/08/2025 | 05/09/2022 | 411.11 | 411.11
166 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. (SM/13313) | SM/13313 | 1562.48 | 4240 | AUGMENTATION | 50 | Delayed | 54 | 17/10/2022 | 31/03/2026 | 14/08/2025 | 09/02/2023 | 843.61 | 843.61
167 | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme (SM/13893) | SM/13893 | 1058.92 | 2697 | AUGMENTATION | 50 | Delayed | 38 | 25/11/2022 | 31/12/2025 | 14/08/2025 | 18/08/2022 | 403.05 | 403.05
168 | NITYABARIA PIPED WATER SUPPLY SCHEME (SM/10182) | SM/10182 | 1219.24 | 2277 | NEW | 50 | Delayed | 26 | 17/02/2022 | 31/03/2025 | 14/08/2025 | 04/01/2022 | 315.72 | 315.72
169 | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11559) | SM/11559 | 253.86 | 128 | AUGMENTATION | 50 | Delayed | 67 | 22/07/2022 | 31/08/2025 | 14/08/2025 | 25/05/2022 | 169.11 | 169.11
170 | Kachurhula Zone-I Piped Water Supply Scheme (SM/13522) | SM/13522 | 602.01 | 564 | NEW | 50 | Delayed | 22 | 04/11/2022 | 30/06/2025 | 14/08/2025 | 09/02/2022 | 134.43 | 134.43
171 | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC (SM/12124) | SM/12124 | 1238.73 | 3158 | AUGMENTATION | 50 | Delayed | 43 | 06/09/2022 | 31/03/2026 | 14/08/2025 | 07/06/2023 | 531.61 | 531.61
172 | Bhandarkhali Piped Water Supply Scheme (SM/15827) | SM/15827 | 1348.25 | 1690 | NEW | 50 | Delayed | 24 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 322.53 | 322.53
173 | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC (SM/12126) | SM/12126 | 2516.15 | 7089 | AUGMENTATION | 50 | Delayed | 44 | 06/09/2022 | 02/08/2025 | 14/08/2025 | 13/07/2023 | 1102.39 | 1102.39
174 | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11705) | SM/11705 | 525.59 | 573 | AUGMENTATION | 51 | Delayed | 56 | 29/07/2022 | 31/08/2025 | 14/08/2025 | 06/05/2022 | 292.62 | 292.62
175 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas (SM/10102) | SM/10102 | 620.68 | 4118 | AUGMENTATION | 52 | Delayed | 45 | 02/02/2022 | 31/03/2027 | 14/08/2025 | 24/02/2022 | 281.12 | 281.12
176 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/14542) | SM/14542 | 1138.26 | 19110 | RETROFITTING | 52 | Delayed | 11 | 30/01/2023 | 02/08/2025 | 14/08/2025 | 05/10/2023 | 123.26 | 123.26
177 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block (SM/08244) | SM/08244 | 92.41 | 1464 | RETROFITTING | 53 | Delayed | 74 | 22/02/2021 | 30/06/2025 | 14/08/2025 | 22/12/2021 | 68 | 68
178 | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. (SM/13472) | SM/13472 | 875.39 | 2268 | AUGMENTATION | 54 | Delayed | 31 | 02/11/2022 | 08/06/2025 | 14/08/2025 | 08/06/2023 | 275.51 | 275.51
179 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block (SM/08243) | SM/08243 | 99.94 | 1919 | RETROFITTING | 55 | Delayed | 76 | 22/02/2021 | 30/04/2025 | 14/08/2025 | 14/08/2020 | 75.99 | 75.99
180 | Purana Bongaon Piped water supply scheme (SM/13896) | SM/13896 | 934.47 | 2307 | NEW | 55 | Delayed | 28 | 25/11/2022 | 31/03/2026 | 14/08/2025 | 07/07/2022 | 265.44 | 265.44
181 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District (SM/15823) | SM/15823 | 1006.41 | 28138 | RETROFITTING | 55 | WO no issued | 0 | 20/02/2023 | 31/03/2026 | 14/08/2025 |  | 0 | 0
182 | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC (SM/11528) | SM/11528 | 957.1 | 3792 | AUGMENTATION | 55 | Delayed | 47 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 14/03/2022 | 447.32 | 447.32
183 | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. (SM/13471) | SM/13471 | 538.28 | 2187 | AUGMENTATION | 55 | Delayed | 57 | 02/11/2022 | 08/06/2025 | 14/08/2025 | 08/06/2023 | 304.75 | 304.75
184 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/10549) | SM/10549 | 863.01 | 1845 | AUGMENTATION | 57 | Delayed | 64 | 18/04/2022 | 31/08/2025 | 14/08/2025 | 23/12/2021 | 554.31 | 554.31
185 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15821) | SM/15821 | 1115.04 | 2537 | AUGMENTATION | 57 | On track | 47 | 20/02/2023 | 31/12/2026 | 14/08/2025 | 05/09/2022 | 521.35 | 521.35
186 | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. (SM/09004) | SM/09004 | 298.76 | 0 | DISASTER | 59 | Delayed | 0 | 29/10/2021 | 31/03/2025 | 14/08/2025 | 29/06/2021 | 0 | 0
187 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) (SM/07842) | SM/07842 | 92.43 | 1417 | RETROFITTING | 59 | Delayed | 55 | 14/01/2021 | 31/12/2025 | 14/08/2025 | 18/01/2021 | 50.44 | 50.44
188 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bangangram (Zone-I) Water Supply Scheme at Bongaon Block (Phase-II) (SM/08044) | SM/08044 | 39.06 | 611 | RETROFITTING | 59 | Delayed | 96 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 27/05/2021 | 37.4 | 37.4
189 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chandpur Water Supply Scheme at Bagdah Block under (Phase-I) (SM/08042) | SM/08042 | 75.47 | 1125 | RETROFITTING | 60 | Delayed | 94 | 01/02/2021 | 31/12/2026 | 14/08/2025 | 29/06/2021 | 70.66 | 70.66
190 | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC (SM/11753) | SM/11753 | 505.51 | 938 | AUGMENTATION | 60 | Delayed | 43 | 03/08/2022 | 31/03/2026 | 14/08/2025 | 20/02/2023 | 218.46 | 218.46
191 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC (SM/11756) | SM/11756 | 1005.08 | 2394 | AUGMENTATION | 60 | Delayed | 35 | 02/08/2022 | 31/03/2025 | 14/08/2025 | 11/04/2023 | 348.82 | 348.82
192 | Augmentation of ground water based piped water supply scheme for Sandeshkhali (SM/14152) | SM/14152 | 1139.85 | 2919 | AUGMENTATION | 60 | Delayed | 18 | 05/01/2023 | 31/03/2026 | 14/08/2025 | 26/04/2023 | 202.9 | 202.9
193 | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC (SM/11626) | SM/11626 | 1207.61 | 2582 | AUGMENTATION | 60 | Delayed | 26 | 26/07/2022 | 31/03/2026 | 14/08/2025 | 13/02/2023 | 315.87 | 315.87
194 | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC (SM/13737) | SM/13737 | 1459.08 | 7093 | AUGMENTATION | 60 | Delayed | 39 | 17/11/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 564.13 | 564.13
195 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. (SM/10299) | SM/10299 | 429.81 | 2699 | AUGMENTATION | 60 | Delayed | 54 | 02/03/2022 | 31/12/2026 | 14/08/2025 | 10/08/2021 | 230.08 | 230.08
196 | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC (SM/12274) | SM/12274 | 1647.37 | 7610 | AUGMENTATION | 60 | Delayed | 42 | 09/09/2022 | 31/03/2026 | 14/08/2025 | 16/11/2022 | 695.89 | 695.36
197 | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC (SM/11586) | SM/11586 | 487.39 | 824 | AUGMENTATION | 60 | Delayed | 44 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 01/12/2022 | 216.27 | 216.27
198 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12413) | SM/12413 | 1032.42 | 1543 | AUGMENTATION | 60 | Delayed | 42 | 13/09/2022 | 31/12/2025 | 14/08/2025 | 05/09/2022 | 437.64 | 437.64
199 | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. (SM/11545) | SM/11545 | 285.37 | 248 | AUGMENTATION | 60 | Delayed | 72 | 22/07/2022 | 31/08/2025 | 14/08/2025 | 24/08/2022 | 206.08 | 205.44
200 | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC (SM/17408) | SM/17408 | 649.79 | 3543 | AUGMENTATION | 60 | Delayed | 44 | 15/03/2023 | 31/03/2026 | 14/08/2025 | 14/03/2022 | 288.48 | 288.48
201 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC (SM/12123) | SM/12123 | 1539.73 | 4944 | AUGMENTATION | 60 | Delayed | 57 | 06/09/2022 | 02/08/2025 | 14/08/2025 | 04/08/2023 | 882.12 | 882.12
202 | Augmentation of ground water based piped water supply scheme for Mohanpur (SM/14151) | SM/14151 | 1333.28 | 3339 | AUGMENTATION | 60 | Delayed | 48 | 05/01/2023 | 30/09/2025 | 14/08/2025 | 09/02/2023 | 642.97 | 642.97
203 | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC (SM/10555) | SM/10555 | 997.1 | 2638 | AUGMENTATION | 60 | Delayed | 60 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 31/03/2023 | 598.76 | 598.76
204 | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC (SM/12895) | SM/12895 | 837.52 | 3422 | AUGMENTATION | 60 | Delayed | 51 | 23/09/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 429.7 | 429.7
205 | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC (SM/12569) | SM/12569 | 1498.08 | 6270 | AUGMENTATION | 60 | Delayed | 41 | 14/09/2022 | 31/03/2026 | 14/08/2025 | 16/03/2022 | 608.74 | 608.74
206 | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC (SM/11541) | SM/11541 | 248.17 | 743 | AUGMENTATION | 60 | Delayed | 23 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 28/02/2022 | 55.84 | 55.84
207 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC (SM/12125) | SM/12125 | 1168.29 | 2007 | AUGMENTATION | 60 | Delayed | 54 | 06/09/2022 | 31/03/2026 | 14/08/2025 | 03/08/2022 | 625.18 | 625.18
208 | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC (SM/13350) | SM/13350 | 1412.09 | 5843 | AUGMENTATION | 60 | Delayed | 50 | 19/10/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 702.55 | 702.55
209 | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC (SM/13040) | SM/13040 | 1430.19 | 6262 | AUGMENTATION | 60 | Delayed | 55 | 29/09/2022 | 31/03/2026 | 14/08/2025 | 14/03/2022 | 781.19 | 781.19
210 | Petua Dhanihati Piped Water Supply Scheme (SM/15830) | SM/15830 | 1122.5 | 1144 | NEW | 60 | Delayed | 27 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 21/02/2022 | 305.25 | 300.43
211 | Dakshin Akhratala Piped Water Supply Scheme (SM/18617) | SM/18617 | 2028.44 | 3261 | NEW | 60 | Delayed | 33 | 31/07/2023 | 02/08/2025 | 14/08/2025 | 10/08/2023 | 667.42 | 667.42
212 | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC (SM/18618) | SM/18618 | 1018.08 | 2811 | AUGMENTATION | 60 | Delayed | 54 | 31/07/2023 | 22/08/2025 | 14/08/2025 | 22/03/2022 | 546.57 | 546.57
213 | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. (SM/10583) | SM/10583 | 1053.27 | 2829 | AUGMENTATION | 61 | Delayed | 51 | 18/04/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 533.52 | 533.52
214 | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme (SM/13894) | SM/13894 | 1170 | 4283 | AUGMENTATION | 62 | Delayed | 46 | 25/11/2022 | 31/12/2025 | 14/08/2025 | 25/08/2022 | 542.73 | 542.73
215 | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC (SM/14733) | SM/14733 | 732.09 | 1484 | AUGMENTATION | 62 | Delayed | 53 | 31/01/2023 | 08/06/2025 | 14/08/2025 | 08/06/2023 | 388.31 | 388.31
216 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07599) | SM/07599 | 70.98 | 1096 | RETROFITTING | 65 | Delayed | 97 | 05/01/2021 | 30/06/2025 | 14/08/2025 | 08/01/2021 | 68.51 | 68.51
217 | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC (SM/11764) | SM/11764 | 983.58 | 1419 | AUGMENTATION | 65 | Delayed | 39 | 02/08/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 382.18 | 382.18
218 | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC (SM/12273) | SM/12273 | 1683.01 | 4583 | AUGMENTATION | 65 | On track | 40 | 09/09/2022 | 31/10/2026 | 14/08/2025 | 28/02/2022 | 675.33 | 675.33
219 | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC (SM/11604) | SM/11604 | 706.65 | 1674 | AUGMENTATION | 65 | Delayed | 54 | 22/07/2022 | 31/03/2025 | 14/08/2025 | 28/02/2022 | 380.63 | 380.63
220 | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC (SM/11757) | SM/11757 | 566.66 | 2015 | AUGMENTATION | 65 | Delayed | 49 | 03/08/2022 | 31/05/2026 | 14/08/2025 | 22/03/2022 | 276.81 | 276.81
221 | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC (SM/11758) | SM/11758 | 342.34 | 898 | AUGMENTATION | 65 | Delayed | 41 | 02/08/2022 | 31/01/2026 | 14/08/2025 | 22/03/2022 | 139.85 | 139.85
222 | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC (SM/11655) | SM/11655 | 1153.55 | 1939 | AUGMENTATION | 65 | Delayed | 40 | 27/07/2022 | 31/03/2026 | 14/08/2025 | 16/11/2022 | 465.28 | 465.28
223 | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC (SM/10782) | SM/10782 | 1093.14 | 3202 | AUGMENTATION | 65 | Delayed | 64 | 25/05/2022 | 31/03/2025 | 14/08/2025 | 23/08/2022 | 699.93 | 698.15
224 | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC (SM/11702) | SM/11702 | 551.46 | 1402 | AUGMENTATION | 65 | Delayed | 62 | 29/07/2022 | 31/03/2026 | 14/08/2025 | 01/12/2022 | 341.62 | 341.62
225 | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC (SM/11653) | SM/11653 | 955.4 | 2311 | AUGMENTATION | 65 | Delayed | 51 | 27/07/2022 | 31/03/2026 | 14/08/2025 | 15/02/2022 | 487.74 | 487.74
226 | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC (SM/11634) | SM/11634 | 511.35 | 1019 | AUGMENTATION | 65 | Delayed | 58 | 26/07/2022 | 30/09/2025 | 14/08/2025 | 16/11/2022 | 294.8 | 294.8
227 | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC (SM/11524) | SM/11524 | 266.67 | 720 | AUGMENTATION | 65 | Delayed | 42 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 02/12/2022 | 111.83 | 111.83
228 | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC (SM/11974) | SM/11974 | 583.85 | 1109 | AUGMENTATION | 65 | Delayed | 56 | 29/08/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 326.89 | 325.41
229 | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC (SM/11754) | SM/11754 | 166.16 | 122 | AUGMENTATION | 65 | Delayed | 36 | 02/08/2022 | 31/12/2025 | 14/08/2025 | 29/08/2022 | 60.63 | 60.63
230 | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC (SM/11654) | SM/11654 | 403.69 | 687 | AUGMENTATION | 65 | Delayed | 40 | 27/07/2022 | 31/12/2025 | 14/08/2025 | 02/12/2022 | 160.93 | 160.93
231 | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC (SM/11633) | SM/11633 | 1027.09 | 2889 | AUGMENTATION | 65 | On track | 55 | 26/07/2022 | 31/07/2026 | 14/08/2025 | 06/12/2022 | 562.52 | 562.52
232 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15822) | SM/15822 | 1340.98 | 3593 | AUGMENTATION | 66 | On track | 56 | 20/02/2023 | 30/06/2026 | 14/08/2025 | 23/02/2023 | 752.23 | 752.23
233 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. (SM/10104) | SM/10104 | 630.72 | 2759 | AUGMENTATION | 66 | On track | 60 | 02/02/2022 | 31/03/2027 | 14/08/2025 | 31/12/2021 | 380.43 | 380.43
234 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15820) | SM/15820 | 1399.45 | 3667 | AUGMENTATION | 68 | Delayed | 55 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 10/03/2023 | 769.43 | 769.43
235 | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC (SM/13314) | SM/13314 | 1702.13 | 3979 | AUGMENTATION | 69 | Delayed | 63 | 17/10/2022 | 31/12/2025 | 14/08/2025 | 13/07/2022 | 1079.26 | 1079.26
236 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/15819) | SM/15819 | 1316.36 | 2939 | AUGMENTATION | 69 | On track | 54 | 20/02/2023 | 31/03/2026 | 14/08/2025 | 28/02/2023 | 707.28 | 707.28
237 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N (SM/08045) | SM/08045 | 93.98 | 1452 | RETROFITTING | 70 | Delayed | 75 | 01/02/2021 | 30/04/2025 | 14/08/2025 | 27/05/2021 | 70.23 | 70.23
238 | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC (SM/10584) | SM/10584 | 576.54 | 192 | AUGMENTATION | 70 | Delayed | 33 | 18/04/2022 | 31/03/2026 | 14/08/2025 | 17/08/2022 | 192.53 | 192.53
239 | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC (SM/11656) | SM/11656 | 718.56 | 1127 | AUGMENTATION | 70 | Delayed | 41 | 27/07/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 297.5 | 297.5
240 | Augmentation of Ground water based piped water supply scheme for Durgamandap (SM/10370) | SM/10370 | 867.35 | 624 | AUGMENTATION | 70 | Delayed | 55 | 16/03/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 480.35 | 480.35
241 | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC (SM/11703) | SM/11703 | 455.33 | 1568 | AUGMENTATION | 70 | Delayed | 48 | 29/07/2022 | 31/03/2026 | 14/08/2025 | 17/03/2022 | 218.56 | 218.56
242 | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC (SM/11628) | SM/11628 | 365.06 | 965 | AUGMENTATION | 70 | Delayed | 52 | 26/07/2022 | 31/12/2025 | 14/08/2025 | 16/11/2022 | 188.37 | 188.37
243 | Phulbari Abad Piped Water Supply Scheme. (SM/12717) | SM/12717 | 647.71 | 958 | NEW | 70 | Delayed | 44 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 15/02/2022 | 287.34 | 287.34
244 | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC (SM/11606) | SM/11606 | 884.98 | 3004 | AUGMENTATION | 70 | Delayed | 57 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 01/11/2022 | 505.1 | 505.1
245 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC (SM/11666) | SM/11666 | 990.11 | 2291 | AUGMENTATION | 70 | Delayed | 49 | 27/07/2022 | 31/12/2025 | 14/08/2025 | 18/02/2022 | 486.29 | 486.29
246 | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC (SM/10574) | SM/10574 | 1020.62 | 3309 | AUGMENTATION | 70 | Delayed | 43 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 434.11 | 434.11
247 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate (SM/10533) | SM/10533 | 852.36 | 3344 | AUGMENTATION | 70 | Delayed | 58 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 23/08/2022 | 494.11 | 494.11
248 | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC (SM/11704) | SM/11704 | 852.45 | 3161 | AUGMENTATION | 70 | On track | 60 | 29/07/2022 | 31/03/2026 | 14/08/2025 | 08/06/2023 | 513.49 | 513.49
249 | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC (SM/11585) | SM/11585 | 802.4 | 2199 | AUGMENTATION | 70 | Delayed | 61 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 01/11/2022 | 491.58 | 491.58
250 | Niruli Abad Piped Water Supply Scheme. (SM/12716) | SM/12716 | 491.85 | 581 | NEW | 70 | Delayed | 30 | 21/09/2022 | 31/03/2025 | 14/08/2025 | 10/02/2022 | 146.32 | 146.32
251 | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC (SM/13468) | SM/13468 | 1056.2 | 1841 | AUGMENTATION | 70 | Delayed | 68 | 02/11/2022 | 02/08/2025 | 14/08/2025 | 10/08/2023 | 714.25 | 714.25
252 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC (SM/11535) | SM/11535 | 470.6 | 1243 | AUGMENTATION | 70 | Delayed | 62 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 23/08/2022 | 292.93 | 292.93
253 | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. (SM/10374) | SM/10374 | 1137.13 | 1398 | AUGMENTATION | 70 | Delayed | 54 | 16/03/2022 | 31/12/2025 | 14/08/2025 | 28/06/2022 | 617.79 | 617.79
254 | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah (SM/10298) | SM/10298 | 724.36 | 5384 | AUGMENTATION | 70 | Delayed | 54 | 02/03/2022 | 31/03/2026 | 14/08/2025 | 26/04/2022 | 389.01 | 389.01
255 | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC (SM/10310) | SM/10310 | 705.5 | 3788 | AUGMENTATION | 70 | Delayed | 58 | 04/03/2022 | 31/12/2025 | 14/08/2025 | 04/04/2022 | 412.33 | 412.33
256 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC (SM/12568) | SM/12568 | 1677.27 | 7163 | AUGMENTATION | 70 | Delayed | 60 | 14/09/2022 | 31/03/2026 | 14/08/2025 | 14/03/2022 | 1009.6 | 1009.6
257 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC (SM/12275) | SM/12275 | 1553.55 | 2879 | AUGMENTATION | 70 | Delayed | 6 | 09/09/2022 | 31/03/2026 | 14/08/2025 | 10/08/2023 | 96.34 | 96.34
258 | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. (SM/10153) | SM/10153 | 1043.42 | 7823 | AUGMENTATION | 70 | Delayed | 60 | 11/02/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 627.43 | 627.43
259 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC (SM/12111) | SM/12111 | 932.15 | 2009 | AUGMENTATION | 70 | Delayed | 64 | 02/09/2022 | 31/03/2026 | 14/08/2025 | 20/04/2023 | 598.43 | 598.43
260 | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC (SM/11755) | SM/11755 | 279.25 | 249 | AUGMENTATION | 70 | Delayed | 27 | 02/08/2022 | 31/03/2026 | 14/08/2025 | 08/12/2022 | 75.04 | 75.04
261 | Hatbhanga Piped Water Supply Scheme (SM/13525) | SM/13525 | 752.17 | 789 | NEW | 70 | Delayed | 18 | 04/11/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 138.88 | 138.88
262 | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC (SM/12278) | SM/12278 | 2002.67 | 3854 | AUGMENTATION | 70 | Delayed | 60 | 09/09/2022 | 31/03/2026 | 14/08/2025 | 11/01/2023 | 1202.71 | 1202.71
263 | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate (SM/10577) | SM/10577 | 176.85 | 205 | AUGMENTATION | 70 | Delayed | 30 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 02/12/2021 | 52.88 | 52.88
264 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC (SM/11593) | SM/11593 | 954.12 | 2958 | AUGMENTATION | 70 | Delayed | 59 | 22/07/2022 | 30/09/2025 | 14/08/2025 | 12/07/2022 | 560.33 | 560.33
265 | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC (SM/11669) | SM/11669 | 1068.23 | 1270 | AUGMENTATION | 70 | Delayed | 60 | 27/07/2022 | 31/12/2025 | 14/08/2025 | 20/02/2023 | 636.05 | 636.05
266 | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC (SM/11762) | SM/11762 | 845.97 | 902 | AUGMENTATION | 70 | Delayed | 41 | 02/08/2022 | 31/05/2025 | 14/08/2025 | 18/02/2022 | 348.17 | 348.17
267 | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC (SM/11763) | SM/11763 | 492.23 | 1021 | AUGMENTATION | 70 | Delayed | 43 | 03/08/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 213.5 | 213.5
268 | Pipuldaha Piped Water Supply Scheme. (SM/12721) | SM/12721 | 570.24 | 584 | NEW | 70 | Delayed | 56 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 15/02/2022 | 321.27 | 321.27
269 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC (SM/11701) | SM/11701 | 606.99 | 1389 | AUGMENTATION | 70 | On track | 52 | 29/07/2022 | 31/03/2026 | 14/08/2025 | 19/04/2023 | 316.82 | 316.82
270 | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC (SM/11760) | SM/11760 | 479.08 | 1178 | AUGMENTATION | 70 | Delayed | 55 | 02/08/2022 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 265.64 | 265.64
271 | Niruli Piped Water Supply Scheme (SM/12714) | SM/12714 | 786.23 | 1435 | NEW | 70 | Delayed | 44 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 10/02/2022 | 344.92 | 344.92
272 | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. (SM/11595) | SM/11595 | 537.62 | 499 | AUGMENTATION | 70 | Delayed | 50 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 17/08/2022 | 271.42 | 271.42
273 | Bachhra piped Water supply scheme (SM/12712) | SM/12712 | 642.14 | 634 | NEW | 70 | Delayed | 42 | 21/09/2022 | 30/06/2025 | 14/08/2025 | 03/02/2022 | 272.4 | 272.4
274 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC (SM/12277) | SM/12277 | 2018.38 | 4188 | AUGMENTATION | 70 | Delayed | 65 | 09/09/2022 | 02/08/2025 | 14/08/2025 | 10/08/2023 | 1320.78 | 1320.78
275 | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC (SM/11700) | SM/11700 | 1121.08 | 2424 | AUGMENTATION | 70 | On track | 51 | 29/07/2022 | 31/03/2026 | 14/08/2025 | 20/04/2023 | 575.33 | 575.33
276 | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC (SM/11533) | SM/11533 | 436.8 | 847 | AUGMENTATION | 70 | On track | 36 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 18/11/2022 | 158.79 | 158.79
277 | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC (SM/11629) | SM/11629 | 697.7 | 1998 | AUGMENTATION | 70 | Delayed | 52 | 26/07/2022 | 31/03/2025 | 14/08/2025 | 09/12/2022 | 364.2 | 364.2
278 | Augmentation of Ground water based piped water supply scheme for Kumarjole (SM/10302) | SM/10302 | 1052.3 | 921 | AUGMENTATION | 70 | Delayed | 45 | 02/03/2022 | 31/03/2026 | 14/08/2025 | 20/07/2022 | 469.4 | 469.4
279 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC (SM/11657) | SM/11657 | 999.42 | 2138 | AUGMENTATION | 70 | On track | 61 | 27/07/2022 | 31/03/2026 | 14/08/2025 | 03/08/2022 | 604.83 | 604.83
280 | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC (SM/11660) | SM/11660 | 693.56 | 1931 | AUGMENTATION | 70 | Delayed | 45 | 27/07/2022 | 31/03/2026 | 14/08/2025 | 23/06/2022 | 309.57 | 309.57
281 | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC (SM/11527) | SM/11527 | 720.88 | 1674 | AUGMENTATION | 70 | Delayed | 51 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 01/11/2022 | 367.44 | 367.44
282 | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC (SM/11635) | SM/11635 | 622.98 | 1912 | AUGMENTATION | 70 | Delayed | 56 | 26/07/2022 | 31/03/2026 | 14/08/2025 | 12/12/2022 | 351.76 | 351.76
283 | Tapla Kusangra Piped Water Supply Scheme. (SM/12720) | SM/12720 | 807.9 | 1247 | NEW | 70 | Delayed | 31 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 15/02/2022 | 252.84 | 252.84
284 | Kharibaria Piped Water Supply Scheme. (SM/13519) | SM/13519 | 978.77 | 1485 | NEW | 70 | Delayed | 32 | 02/11/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 311.15 | 311.15
285 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. (SM/11214) | SM/11214 | 1374.55 | 4258 | AUGMENTATION | 71 | On track | 61 | 13/06/2022 | 31/12/2026 | 14/08/2025 | 10/08/2021 | 842.35 | 842.35
286 | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. (SM/11536) | SM/11536 | 1064.01 | 578 | AUGMENTATION | 73 | On track | 68 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 17/08/2022 | 722.62 | 722.62
287 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block (SM/08241) | SM/08241 | 249.86 | 2780 | RETROFITTING | 73 | Delayed | 88 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 24/11/2021 | 219.86 | 219
288 | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC (SM/11699) | SM/11699 | 774.86 | 1182 | AUGMENTATION | 74 | Delayed | 72 | 29/07/2022 | 31/12/2025 | 14/08/2025 | 14/09/2022 | 558.36 | 549.8
289 | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC (SM/10587) | SM/10587 | 1031.13 | 4689 | AUGMENTATION | 75 | Delayed | 53 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 29/08/2022 | 549.66 | 549.66
290 | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC (SM/11530) | SM/11530 | 592.93 | 1741 | AUGMENTATION | 75 | On track | 59 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 02/12/2022 | 347.87 | 347.87
291 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/18260) | SM/18260 | 1279.46 | 2566 | AUGMENTATION | 75 | On track | 50 | 21/06/2023 | 31/12/2025 | 14/08/2025 | 12/07/2023 | 643.79 | 641.26
292 | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC (SM/10706) | SM/10706 | 482.57 | 163 | AUGMENTATION | 75 | Delayed | 58 | 12/05/2022 | 31/12/2025 | 14/08/2025 | 03/08/2022 | 280.62 | 280.62
293 | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC (SM/11759) | SM/11759 | 806.28 | 3060 | AUGMENTATION | 75 | Delayed | 51 | 02/08/2022 | 31/01/2026 | 14/08/2025 | 23/03/2022 | 414.86 | 414.86
294 | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME (SM/17680) | SM/17680 | 294.29 | 440 | AUGMENTATION | 75 | Delayed | 18 | 17/03/2023 | 31/12/2025 | 14/08/2025 | 28/02/2022 | 52.32 | 52.32
295 | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC (SM/11538) | SM/11538 | 761.95 | 1731 | AUGMENTATION | 75 | Delayed | 56 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 31/08/2022 | 425.33 | 425.33
296 | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC (SM/11529) | SM/11529 | 190.44 | 200 | AUGMENTATION | 75 | Delayed | 40 | 19/07/2022 | 31/03/2025 | 14/08/2025 | 08/12/2022 | 77.08 | 77.08
297 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. (SM/12735) | SM/12735 | 1501.39 | 2598 | AUGMENTATION | 75 | On track | 48 | 21/09/2022 | 31/03/2026 | 14/08/2025 | 01/11/2022 | 727.65 | 736.2
298 | Garibpur Piped water supply scheme (SM/13897) | SM/13897 | 594.36 | 755 | NEW | 75 | Delayed | 26 | 25/11/2022 | 30/06/2025 | 14/08/2025 | 07/07/2022 | 152.39 | 152.39
299 | Katakhali Piped Water Supply Scheme (SM/15826) | SM/15826 | 1183.01 | 1341 | NEW | 75 | Delayed | 47 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 561.18 | 561.18
300 | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. (SM/10608) | SM/10608 | 329.25 | 662 | AUGMENTATION | 75 | On track | 63 | 19/04/2022 | 31/03/2026 | 14/08/2025 | 18/01/2021 | 206.84 | 206.84
301 | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. (SM/11212) | SM/11212 | 1269.72 | 3611 | AUGMENTATION | 75 | On track | 63 | 09/06/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 804.22 | 804.22
302 | Paschim Huda Piped water supply scheme (SM/13895) | SM/13895 | 697.08 | 1209 | NEW | 75 | Delayed | 42 | 25/11/2022 | 31/12/2025 | 14/08/2025 | 07/07/2022 | 294.1 | 294.1
303 | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC (SM/10690) | SM/10690 | 869.9 | 2285 | AUGMENTATION | 75 | Delayed | 68 | 12/05/2022 | 31/12/2025 | 14/08/2025 | 29/08/2022 | 594.28 | 594.28
304 | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC (SM/11630) | SM/11630 | 198.28 | 557 | AUGMENTATION | 75 | On track | 37 | 26/07/2022 | 31/03/2026 | 14/08/2025 | 28/02/2022 | 74.06 | 74.06
305 | Uchildaha Piped water supply scheme (SM/13815) | SM/13815 | 1165.33 | 2107 | NEW | 75 | Delayed | 38 | 23/11/2022 | 31/12/2025 | 14/08/2025 | 15/02/2022 | 437.84 | 437.84
306 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC (SM/11523) | SM/11523 | 506.98 | 948 | AUGMENTATION | 75 | On track | 38 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 01/11/2022 | 194.11 | 194.11
307 | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. (SM/12122) | SM/12122 | 1503.75 | 1563 | AUGMENTATION | 75 | Delayed | 75 | 06/09/2022 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 1121.03 | 1121.03
308 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). (SM/08043) | SM/08043 | 99.82 | 1242 | RETROFITTING | 75 | Delayed | 81 | 01/02/2021 | 30/04/2025 | 14/08/2025 | 31/05/2021 | 80.66 | 80.66
309 | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC (SM/11627) | SM/11627 | 439.49 | 783 | AUGMENTATION | 75 | On track | 59 | 26/07/2022 | 31/03/2026 | 14/08/2025 | 31/08/2022 | 259.96 | 258.55
310 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC (SM/11658) | SM/11658 | 718.93 | 2804 | AUGMENTATION | 75 | On track | 59 | 27/07/2022 | 31/05/2026 | 14/08/2025 | 22/03/2022 | 427.7 | 427.7
311 | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC (SM/11602) | SM/11602 | 508.4 | 873 | AUGMENTATION | 75 | Delayed | 42 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 12/12/2022 | 212.35 | 212.35
312 | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC (SM/11540) | SM/11540 | 956.46 | 2748 | AUGMENTATION | 75 | Delayed | 60 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 31/08/2022 | 574.89 | 574.89
313 | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC (SM/11603) | SM/11603 | 402.14 | 1196 | AUGMENTATION | 75 | Delayed | 71 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 18/02/2022 | 286.39 | 286.39
314 | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC (SM/11607) | SM/11607 | 938.51 | 2915 | AUGMENTATION | 75 | On track | 51 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 09/12/2022 | 480.77 | 480.77
315 | Debitala Piped Water Supply Scheme (SM/13523) | SM/13523 | 978.01 | 1458 | NEW | 75 | Delayed | 38 | 04/11/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 371.31 | 371.31
316 | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC (SM/17409) | SM/17409 | 375.47 | 711 | AUGMENTATION | 75 | On track | 61 | 15/03/2023 | 31/03/2026 | 14/08/2025 | 22/03/2022 | 229.7 | 229.7
317 | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC (SM/11532) | SM/11532 | 754.87 | 4199 | AUGMENTATION | 75 | On track | 60 | 20/07/2022 | 31/03/2026 | 14/08/2025 | 28/02/2022 | 455.72 | 455.72
318 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (SM/12414) | SM/12414 | 1064.62 | 1500 | AUGMENTATION | 75 | Delayed | 68 | 13/09/2022 | 31/12/2025 | 14/08/2025 | 16/09/2022 | 722.62 | 705.77
319 | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC (SM/11591) | SM/11591 | 793.5 | 2566 | AUGMENTATION | 75 | On track | 64 | 22/07/2022 | 31/03/2026 | 14/08/2025 | 06/12/2022 | 510.72 | 495.05
320 | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC (SM/11601) | SM/11601 | 531.68 | 975 | AUGMENTATION | 75 | Delayed | 42 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 28/10/2021 | 225.61 | 225.61
321 | Ghipukuria Piped Water Supply Scheme. (SM/12718) | SM/12718 | 756.27 | 955 | NEW | 75 | Delayed | 21 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 158.68 | 158.68
322 | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC (SM/12127) | SM/12127 | 1547.01 | 3057 | AUGMENTATION | 75 | Delayed | 58 | 06/09/2022 | 31/12/2025 | 14/08/2025 | 23/08/2022 | 897.36 | 895.47
323 | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate (SM/10693) | SM/10693 | 467.39 | 1154 | AUGMENTATION | 78 | Delayed | 57 | 12/05/2022 | 31/03/2025 | 14/08/2025 | 03/08/2022 | 266.89 | 266.89
324 | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. (SM/10415) | SM/10415 | 611 | 1799 | AUGMENTATION | 78 | On track | 65 | 08/04/2022 | 31/03/2026 | 14/08/2025 | 21/07/2022 | 398.74 | 398.74
325 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- (SM/08076) | SM/08076 | 144.46 | 2274 | RETROFITTING | 78 | Delayed | 96 | 04/02/2021 | 31/12/2025 | 14/08/2025 | 18/02/2021 | 138.93 | 138.93
326 | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. (SM/10100) | SM/10100 | 1063.69 | 8990 | AUGMENTATION | 79 | Delayed | 73 | 02/02/2022 | 31/12/2025 | 14/08/2025 | 31/12/2021 | 772.96 | 772.96
327 | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC (SM/10565) | SM/10565 | 776.91 | 1929 | AUGMENTATION | 80 | On track | 70 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 03/11/2021 | 542.04 | 542.04
328 | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC (SM/10392) | SM/10392 | 899.31 | 910 | AUGMENTATION | 80 | On track | 52 | 24/03/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 463.63 | 463.63
329 | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC (SM/11605) | SM/11605 | 1108.82 | 5725 | AUGMENTATION | 80 | On track | 74 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 820.77 | 820.77
330 | Sankardaha Piped water supply scheme (SM/13518) | SM/13518 | 920.98 | 1217 | NEW | 80 | On track | 37 | 02/11/2022 | 31/12/2025 | 14/08/2025 | 15/02/2022 | 336.56 | 336.56
331 | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC (SM/18582) | SM/18582 | 1303.27 | 5552 | AUGMENTATION | 80 | Delayed | 72 | 31/07/2023 | 16/08/2025 | 14/08/2025 | 11/08/2023 | 939.46 | 939.46
332 | Kachurhula Zone-II Piped Water Supply Scheme (SM/13445) | SM/13445 | 413.72 | 411 | NEW | 80 | On track | 35 | 02/11/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 144.67 | 144.67
333 | Augmentation of Sultanpur Piped water supply scheme (SM/14510) | SM/14510 | 454.99 | 0 | AUGMENTATION | 80 | On track | 61 | 20/01/2023 | 31/12/2025 | 14/08/2025 | 08/04/2022 | 279.77 | 279.77
334 | Ambaria Piped Water Supply Scheme (SM/15831) | SM/15831 | 1121.04 | 1376 | NEW | 80 | On track | 39 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 432.09 | 382.98
335 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su (SM/08773) | SM/08773 | 296.54 | 4050 | RETROFITTING | 80 | Delayed | 80 | 13/09/2021 | 31/12/2025 | 14/08/2025 | 12/11/2021 | 238.07 | 238.02
336 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Korakati Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) (SM/08761) | SM/08761 | 98.6 | 660 | RETROFITTING | 80 | Delayed | 80 | 13/09/2021 | 31/12/2025 | 14/08/2025 | 14/09/2021 | 78.54 | 78.54
337 | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC (SM/12377) | SM/12377 | 2265.92 | 10639 | AUGMENTATION | 80 | On track | 70 | 13/09/2022 | 31/03/2026 | 14/08/2025 | 23/03/2022 | 1588.57 | 1588.57
338 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10501) | SM/10501 | 570.78 | 4243 | RETROFITTING | 80 | Delayed | 39 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 20/06/2022 | 220.28 | 220.28
339 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC (SM/11594) | SM/11594 | 754.2 | 2140 | AUGMENTATION | 80 | Delayed | 67 | 22/07/2022 | 30/09/2025 | 14/08/2025 | 31/08/2022 | 502.57 | 502.57
340 | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. (SM/11596) | SM/11596 | 1096.37 | 2785 | AUGMENTATION | 80 | On track | 67 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 19/04/2023 | 734.19 | 734.19
341 | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. (SM/11987) | SM/11987 | 1816.81 | 5300 | AUGMENTATION | 80 | On track | 68 | 01/09/2022 | 31/12/2025 | 14/08/2025 | 11/01/2023 | 1242.53 | 1242.5
342 | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC (SM/10727) | SM/10727 | 385.63 | 1097 | AUGMENTATION | 80 | Delayed | 65 | 18/05/2022 | 31/03/2025 | 14/08/2025 | 23/08/2022 | 250.99 | 250.99
343 | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC (SM/11667) | SM/11667 | 508.35 | 225 | AUGMENTATION | 80 | On track | 33 | 27/07/2022 | 31/12/2025 | 14/08/2025 | 16/03/2022 | 169.22 | 169.22
344 | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC (SM/11668) | SM/11668 | 880.6 | 2162 | AUGMENTATION | 80 | On track | 67 | 27/07/2022 | 31/12/2025 | 14/08/2025 | 31/08/2022 | 591.67 | 591.67
345 | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC (SM/11761) | SM/11761 | 705.21 | 2253 | AUGMENTATION | 80 | On track | 55 | 02/08/2022 | 31/12/2025 | 14/08/2025 | 03/11/2021 | 389.01 | 389.01
346 | Augmentation of Bermajur Piped water supply scheme (SM/14511) | SM/14511 | 1000.57 | 0 | AUGMENTATION | 80 | On track | 39 | 20/01/2023 | 31/12/2025 | 14/08/2025 | 08/04/2022 | 388.21 | 388.21
347 | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC (SM/10300) | SM/10300 | 699.49 | 2629 | AUGMENTATION | 80 | On track | 66 | 02/03/2022 | 31/12/2025 | 14/08/2025 | 21/04/2022 | 461.05 | 461.05
348 | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC (SM/10558) | SM/10558 | 901.97 | 1313 | AUGMENTATION | 80 | On track | 35 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 17/08/2022 | 314.21 | 314.21
349 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC (SM/12276) | SM/12276 | 1476.58 | 4712 | AUGMENTATION | 80 | Delayed | 63 | 09/09/2022 | 31/05/2025 | 14/08/2025 | 18/02/2022 | 927.84 | 927.84
350 | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC (SM/11531) | SM/11531 | 355.01 | 564 | AUGMENTATION | 80 | On track | 53 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 02/12/2022 | 189.76 | 189.76
351 | Augmentation of Chhota Sehara Piped water supply scheme (SM/14514) | SM/14514 | 791.27 | 0 | AUGMENTATION | 80 | On track | 34 | 20/01/2023 | 31/12/2025 | 14/08/2025 | 08/04/2022 | 268.72 | 268.72
352 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block (SM/08073) | SM/08073 | 216.27 | 1834 | RETROFITTING | 80 | On track | 98 | 04/02/2021 | 31/12/2025 | 14/08/2025 | 26/07/2021 | 212.17 | 200.87
353 | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. (SM/10376) | SM/10376 | 671.07 | 728 | AUGMENTATION | 80 | On track | 74 | 16/03/2022 | 31/12/2025 | 14/08/2025 | 20/07/2022 | 498.92 | 498.92
354 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC (SM/11592) | SM/11592 | 743.79 | 2223 | AUGMENTATION | 80 | On track | 66 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 06/12/2022 | 490.59 | 490.59
355 | Jhikra Piped Water Supply Scheme. (SM/12719) | SM/12719 | 841.62 | 1421 | NEW | 80 | On track | 49 | 21/09/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 411.59 | 416.12
356 | Bamanpukuria Piped Water Supply Scheme. (SM/13814) | SM/13814 | 1179.1 | 1777 | NEW | 80 | On track | 29 | 23/11/2022 | 31/12/2025 | 14/08/2025 | 03/02/2022 | 342.58 | 342.58
357 | Bargan Gopalpur Piped Water Supply Scheme (SM/15902) | SM/15902 | 1073.62 | 789 | NEW | 80 | On track | 36 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 03/02/2022 | 391.6 | 386.93
358 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate (SM/10531) | SM/10531 | 821.44 | 3457 | AUGMENTATION | 80 | On track | 73 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 14/09/2022 | 600.94 | 600.94
359 | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC (SM/10371) | SM/10371 | 1151.54 | 1338 | AUGMENTATION | 80 | On track | 46 | 16/03/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 530.68 | 530.68
360 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC (SM/11631) | SM/11631 | 1164.88 | 3153 | AUGMENTATION | 80 | On track | 52 | 26/07/2022 | 31/12/2025 | 14/08/2025 | 18/02/2022 | 609.91 | 609.91
361 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC (SM/11597) | SM/11597 | 357.1 | 194 | AUGMENTATION | 80 | On track | 51 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 06/12/2022 | 183.7 | 183.7
362 | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC (SM/11526) | SM/11526 | 691.03 | 1126 | AUGMENTATION | 80 | On track | 64 | 19/07/2022 | 31/03/2026 | 14/08/2025 | 16/09/2021 | 444.11 | 444.11
363 | Matbari Abad Piped Water Supply Scheme (SM/15825) | SM/15825 | 1326.01 | 1601 | NEW | 80 | On track | 29 | 20/02/2023 | 31/12/2025 | 14/08/2025 | 21/02/2022 | 390.49 | 372.49
364 | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. (SM/10580) | SM/10580 | 690.43 | 1297 | AUGMENTATION | 81 | On track | 67 | 18/04/2022 | 30/06/2026 | 14/08/2025 | 18/01/2021 | 462.95 | 462.95
365 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. (SM/10101) | SM/10101 | 592.32 | 1810 | AUGMENTATION | 81 | On track | 70 | 02/02/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 417.03 | 414.41
366 | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. (SM/11557) | SM/11557 | 634.07 | 2441 | AUGMENTATION | 82 | Delayed | 80 | 22/07/2022 | 31/08/2025 | 14/08/2025 | 05/07/2022 | 504.93 | 504.93
367 | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. (SM/10638) | SM/10638 | 929.85 | 3051 | AUGMENTATION | 82 | On track | 74 | 21/04/2022 | 31/03/2026 | 14/08/2025 | 18/01/2021 | 686.46 | 686.46
368 | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC (SM/10514) | SM/10514 | 983.88 | 2590 | AUGMENTATION | 82 | On track | 75 | 13/04/2022 | 31/03/2026 | 14/08/2025 | 25/05/2022 | 737.04 | 737.04
369 | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah (SM/10786) | SM/10786 | 537.38 | 2004 | AUGMENTATION | 82 | On track | 78 | 25/05/2022 | 31/12/2025 | 14/08/2025 | 09/06/2022 | 417.43 | 417.43
370 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. (SM/10110) | SM/10110 | 673.06 | 3893 | AUGMENTATION | 83 | On track | 75 | 02/02/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 507.88 | 507.88
371 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. (SM/10098) | SM/10098 | 906.75 | 5274 | AUGMENTATION | 84 | On track | 80 | 02/02/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 724.09 | 724.09
372 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase (SM/10506) | SM/10506 | 603.79 | 3737 | RETROFITTING | 85 | On track | 75 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 01/06/2022 | 455.52 | 455.52
373 | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon (SM/10308) | SM/10308 | 660.87 | 3185 | AUGMENTATION | 85 | Delayed | 72 | 04/03/2022 | 31/08/2025 | 14/08/2025 | 19/04/2022 | 474.82 | 474.82
374 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10556) | SM/10556 | 430.12 | 3056 | RETROFITTING | 85 | On track | 84 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 11/01/2023 | 361.84 | 361.84
375 | Atpukur Zone-II Piped Water Supply Scheme (SM/13510) | SM/13510 | 619.01 | 623 | NEW | 85 | On track | 47 | 02/11/2022 | 31/12/2025 | 14/08/2025 | 02/02/2022 | 291.72 | 291.72
376 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P (SM/10504) | SM/10504 | 324.12 | 1423 | RETROFITTING | 85 | On track | 89 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 07/06/2022 | 287.67 | 287.67
377 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10502) | SM/10502 | 329.73 | 766 | RETROFITTING | 85 | On track | 60 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 10/06/2022 | 198.17 | 198.17
378 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. (SM/10111) | SM/10111 | 938.03 | 3767 | AUGMENTATION | 85 | On track | 78 | 02/02/2022 | 31/12/2026 | 14/08/2025 | 31/12/2021 | 732.28 | 732.28
379 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC (SM/11598) | SM/11598 | 1165.1 | 6031 | AUGMENTATION | 85 | On track | 76 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 31/08/2022 | 887.11 | 887.11
380 | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas (SM/14153) | SM/14153 | 2402.37 | 4554 | AUGMENTATION | 85 | On track | 82 | 05/01/2023 | 31/12/2025 | 14/08/2025 | 28/02/2023 | 1960.67 | 1960.67
381 | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC (SM/10309) | SM/10309 | 565.58 | 3130 | AUGMENTATION | 85 | On track | 82 | 04/03/2022 | 31/12/2025 | 14/08/2025 | 04/04/2022 | 465.15 | 465.15
382 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC (SM/11534) | SM/11534 | 422.75 | 1129 | AUGMENTATION | 85 | On track | 52 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 218.57 | 218.57
383 | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. (SM/10781) | SM/10781 | 519.69 | 145 | AUGMENTATION | 85 | On track | 78 | 25/05/2022 | 31/12/2025 | 14/08/2025 | 28/07/2022 | 405.96 | 405.96
384 | Chutkia Radhanagar Piped Water Supply Scheme (SM/13524) | SM/13524 | 759.76 | 976 | NEW | 85 | On track | 38 | 04/11/2022 | 31/12/2025 | 14/08/2025 | 09/02/2022 | 290.16 | 290.16
385 | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota (SM/13984) | SM/13984 | 273.98 | 2061 | AUGMENTATION | 85 | On track | 76 | 01/12/2022 | 30/10/2025 | 14/08/2025 | 13/07/2023 | 208.12 | 208.12
386 | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC (SM/10375) | SM/10375 | 509.48 | 2479 | AUGMENTATION | 85 | On track | 81 | 16/03/2022 | 31/10/2025 | 14/08/2025 | 18/01/2021 | 413.76 | 413.76
387 | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate (SM/10530) | SM/10530 | 648.71 | 1399 | AUGMENTATION | 85 | On track | 62 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 25/05/2022 | 399.69 | 399.69
388 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North (SM/08040) | SM/08040 | 84.03 | 1337 | RETROFITTING | 85 | On track | 87 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 31/05/2021 | 73.38 | 73.38
389 | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC (SM/11539) | SM/11539 | 452.26 | 290 | AUGMENTATION | 85 | On track | 60 | 19/07/2022 | 31/12/2025 | 14/08/2025 | 31/08/2022 | 270.04 | 270.04
390 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10503) | SM/10503 | 393.8 | 1101 | RETROFITTING | 85 | On track | 46 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 25/05/2022 | 180.98 | 180.98
391 | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC (SM/10301) | SM/10301 | 592.89 | 2979 | AUGMENTATION | 85 | On track | 74 | 02/03/2022 | 31/12/2025 | 14/08/2025 | 31/03/2022 | 439.93 | 439.93
392 | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC (SM/11599) | SM/11599 | 631.14 | 450 | AUGMENTATION | 85 | On track | 79 | 22/07/2022 | 31/12/2025 | 14/08/2025 | 15/12/2021 | 499.52 | 499.52
393 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m (SM/08653) | SM/08653 | 297.03 | 1395 | RETROFITTING | 86 | On track | 83 | 18/06/2021 | 31/03/2026 | 14/08/2025 | 26/10/2021 | 246.54 | 230.87
394 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase (SM/10508) | SM/10508 | 455.09 | 2839 | RETROFITTING | 87 | On track | 88 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 26/05/2022 | 401.27 | 401.27
395 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) (SM/08762) | SM/08762 | 98.91 | 1150 | RETROFITTING | 87 | On track | 81 | 13/09/2021 | 31/12/2025 | 14/08/2025 | 14/09/2021 | 80.33 | 80.33
396 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme for Arsenic affected areas at Deganga Block of North 24 Parganas (SM/08049) | SM/08049 | 99.22 | 1004 | RETROFITTING | 87 | On track | 87 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 26/02/2021 | 86.14 | 86.14
397 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I (SM/10507) | SM/10507 | 619.21 | 4230 | RETROFITTING | 87 | On track | 74 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 01/06/2022 | 461.04 | 461.04
398 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10505) | SM/10505 | 404.01 | 1713 | RETROFITTING | 90 | Delayed | 91 | 13/04/2022 | 31/03/2025 | 14/08/2025 | 07/06/2022 | 367.2 | 367.2
399 | Augmentation of Hingalganj Piped water supply scheme Zone-I (SM/14512) | SM/14512 | 944.47 | 0 | AUGMENTATION | 90 | On track | 54 | 20/01/2023 | 31/12/2025 | 14/08/2025 | 08/04/2022 | 505.54 | 505.54
400 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-I WaterSupply Scheme at Bongaon Block (Phase-II). (SM/08236) | SM/08236 | 77.55 | 1303 | RETROFITTING | 90 | On track | 91 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 07/10/2021 | 70.56 | 70.56
401 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10510) | SM/10510 | 371.96 | 1074 | RETROFITTING | 90 | On track | 87 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 13/06/2022 | 322.46 | 322.46
402 | Augmentation of Rajbari Piped water supply scheme (SM/14515) | SM/14515 | 732.31 | 0 | AUGMENTATION | 90 | On track | 45 | 20/01/2023 | 31/12/2025 | 14/08/2025 | 08/04/2022 | 330.42 | 330.42
403 | Electrocoagulation based package Surface water based water supply scheme (Solar Power) in Minakhan Block (SM/14625) | SM/14625 | 46.97 | 50 | NEW | 90 | On track | 76 | 31/01/2023 | 31/12/2025 | 14/08/2025 | 09/02/2023 | 35.83 | 35.83
404 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10550) | SM/10550 | 448.57 | 1699 | RETROFITTING | 90 | On track | 42 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 07/06/2022 | 189.41 | 189.41
405 | Augmentation of ground water based piped water supply scheme for Chhaimalpur (SM/13767) | SM/13767 | 389.4 | 1050 | AUGMENTATION | 90 | On track | 67 | 18/11/2022 | 31/12/2025 | 14/08/2025 | 20/04/2023 | 262.37 | 262.37
406 | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC (SM/10519) | SM/10519 | 827.36 | 2082 | AUGMENTATION | 90 | On track | 78 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 23/03/2022 | 645.49 | 645.49
407 | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate (SM/10529) | SM/10529 | 438.64 | 1216 | AUGMENTATION | 90 | On track | 52 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 25/05/2022 | 226.99 | 226.99
408 | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC (SM/11632) | SM/11632 | 758.33 | 2060 | AUGMENTATION | 90 | On track | 63 | 26/07/2022 | 31/12/2025 | 14/08/2025 | 23/08/2022 | 479.16 | 479.16
409 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 (SM/08046) | SM/08046 | 94.8 | 1351 | RETROFITTING | 90 | On track | 83 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 27/05/2021 | 78.29 | 78.29
410 | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC (SM/10570) | SM/10570 | 628.03 | 1788 | AUGMENTATION | 90 | On track | 62 | 18/04/2022 | 31/12/2025 | 14/08/2025 | 23/03/2022 | 386.54 | 386.54
411 | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. (SM/10581) | SM/10581 | 702.18 | 2628 | AUGMENTATION | 91 | On track | 80 | 18/04/2022 | 30/06/2026 | 14/08/2025 | 31/12/2021 | 562.32 | 562.32
412 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Jadavpur, Khanpur, Odhanpur, Kumarpur, Fazilpur, Rampur & Sohai mouzas (Part) within Sohai Swetpur Zone-II Piped Water Sup (SM/08652) | SM/08652 | 276.49 | 1987 | RETROFITTING | 92 | On track | 82 | 18/06/2021 | 31/03/2026 | 14/08/2025 | 30/09/2021 | 225.94 | 225.09
413 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10509) | SM/10509 | 749.52 | 4766 | RETROFITTING | 92 | On track | 97 | 13/04/2022 | 31/12/2025 | 14/08/2025 | 13/06/2022 | 727.69 | 727.69
414 | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. (SM/10639) | SM/10639 | 933.78 | 1886 | AUGMENTATION | 93 | On track | 84 | 21/04/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 780.27 | 780.27
415 | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. (SM/10412) | SM/10412 | 731.42 | 1449 | AUGMENTATION | 93 | On track | 78 | 08/04/2022 | 31/03/2026 | 14/08/2025 | 21/03/2022 | 571.93 | 571.93
416 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08640) | SM/08640 | 260.99 | 4000 | RETROFITTING | 94 | On track | 90 | 18/06/2021 | 31/12/2025 | 14/08/2025 | 25/08/2021 | 234.48 | 234.48
417 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, (SM/07852) | SM/07852 | 57.27 | 698 | RETROFITTING | 94 | Delayed | 96 | 14/01/2021 | 31/03/2025 | 14/08/2025 | 02/04/2018 | 55.15 | 55.15
418 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block (SM/09225) | SM/09225 | 419.92 | 1624 | RETROFITTING | 95 | On track | 96 | 01/11/2021 | 31/12/2025 | 14/08/2025 | 13/01/2021 | 403.9 | 400.45
419 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. (SM/10109) | SM/10109 | 843.1 | 5976 | AUGMENTATION | 95 | On track | 87 | 02/02/2022 | 31/12/2026 | 14/08/2025 | 31/12/2021 | 730.1 | 730.1
420 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) (SM/08074) | SM/08074 | 226.61 | 1100 | RETROFITTING | 95 | On track | 92 | 04/02/2021 | 31/12/2025 | 14/08/2025 | 12/02/2021 | 208.91 | 208.91
421 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block (SM/09224) | SM/09224 | 589.31 | 3453 | RETROFITTING | 95 | On track | 95 | 01/11/2021 | 31/12/2025 | 14/08/2025 | 13/08/2021 | 562.09 | 562.09
422 | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District (SM/10777) | SM/10777 | 1054.95 | 4201 | AUGMENTATION | 95 | On track | 85 | 25/05/2022 | 31/03/2026 | 14/08/2025 | 18/01/2021 | 892.55 | 892.55
423 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC (SM/11537) | SM/11537 | 704.44 | 1237 | AUGMENTATION | 95 | Delayed | 46 | 19/07/2022 | 30/06/2025 | 14/08/2025 | 19/04/2023 | 323.47 | 323.47
424 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) (SM/08039) | SM/08039 | 252.36 | 4288 | RETROFITTING | 96 | On track | 93 | 01/02/2021 | 31/08/2025 | 14/08/2025 | 12/05/2021 | 234.23 | 232.72
425 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. (SM/10105) | SM/10105 | 918.69 | 8163 | AUGMENTATION | 97 | On track | 90 | 02/02/2022 | 31/03/2026 | 14/08/2025 | 31/12/2021 | 826.55 | 826.55
426 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07600) | SM/07600 | 92.84 | 1761 | RETROFITTING | 97 | On track | 98 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 08/01/2021 | 91.12 | 91.12
427 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07603) | SM/07603 | 69.29 | 1068 | RETROFITTING | 97 | On track | 93 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 64.5 | 64.5
428 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Nabatkati W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). (SM/09729) | SM/09729 | 200.79 | 1700 | RETROFITTING | 98 | On track | 97 | 26/11/2021 | 31/03/2026 | 14/08/2025 | 18/01/2021 | 194.73 | 194.73
429 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10511) | SM/10511 | 464.15 | 2195 | RETROFITTING | 98 | On track | 94 | 13/04/2022 | 31/03/2025 | 14/08/2025 | 29/09/2021 | 437.85 | 437.85
430 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. (SM/07611) | SM/07611 | 198.98 | 1085 | RETROFITTING | 98 | On track | 49 | 05/01/2021 | 31/12/2025 | 14/08/2025 | 12/04/2022 | 97.51 | 97.51
431 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). (SM/10554) | SM/10554 | 150.09 | 863 | RETROFITTING | 99 | Delayed | 97 | 18/04/2022 | 31/03/2025 | 14/08/2025 | 12/04/2022 | 145.72 | 145.72
432 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). (SM/08041) | SM/08041 | 89.3 | 185 | RETROFITTING | 100 | 100% Physical | 99 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 31/05/2021 | 88.6 | 88.41
433 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Water Supply Scheme at Swarupnagar Block (Phase-I) (SM/07854) | SM/07854 | 24.84 | 105 | RETROFITTING | 100 | 100% Physical | 91 | 14/01/2021 | 30/05/2025 | 14/08/2025 | 18/01/2021 | 22.53 | 22.53
434 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) (SM/07616) | SM/07616 | 64.05 | 987 | RETROFITTING | 100 | 100% Physical | 100 | 05/01/2021 | 30/05/2025 | 14/08/2025 | 21/07/2022 | 64.03 | 61.5
435 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-II) (SM/07620) | SM/07620 | 133.68 | 98 | RETROFITTING | 100 | WO no issued | 0 | 05/01/2021 | 29/05/2025 | 14/08/2025 |  | 0 | 0
436 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Water Supply Scheme at Baduria Block, Dist.-North 24 Parganas (Phase-I) (SM/07843) | SM/07843 | 47.8 | 700 | RETROFITTING | 100 | 100% Physical | 88 | 14/01/2021 | 26/05/2025 | 14/08/2025 | 18/01/2021 | 42.22 | 42.22
437 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) (SM/08269) | SM/08269 | 230.73 | 3550 | RETROFITTING | 100 | 100% Physical | 93 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 18/02/2022 | 214.11 | 214.02
438 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). (SM/08234) | SM/08234 | 57.5 | 1431 | RETROFITTING | 100 | 100% Physical | 91 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 08/10/2021 | 52.03 | 52.03
439 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur mouza (rest part after Phase-I) & Bakpukhuria mouza of Akipur Piped Water Supply Scheme, Basirhat-II Block under B (SM/08771) | SM/08771 | 60.85 | 550 | RETROFITTING | 100 | 100% Physical | 88 | 13/09/2021 | 31/05/2025 | 14/08/2025 | 08/10/2021 | 53.25 | 53.25
440 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). (SM/08789) | SM/08789 | 80.66 | 1200 | RETROFITTING | 100 | 100% Physical | 98 | 13/09/2021 | 31/05/2025 | 14/08/2025 | 24/01/2022 | 79.03 | 78.89
441 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) (SM/08264) | SM/08264 | 177.55 | 2407 | RETROFITTING | 100 | 100% Physical | 96 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 18/11/2021 | 170.7 | 170.7
442 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Bermajur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). (SM/10616) | SM/10616 | 158.22 | 396 | RETROFITTING | 100 | WO no issued | 0 | 20/04/2022 | 31/03/2025 | 14/08/2025 |  | 0 | 0
443 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) (SM/08265) | SM/08265 | 144.14 | 1880 | RETROFITTING | 100 | 100% Physical | 80 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 31/01/2022 | 116.03 | 116.03
444 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) (SM/08259) | SM/08259 | 98.93 | 1400 | RETROFITTING | 100 | 100% Physical | 85 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 08/09/2021 | 84.1 | 84.1
445 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kola Water Supply Scheme at Bagdah Block (Phase-I) (SM/08069) | SM/08069 | 34.3 | 528 | RETROFITTING | 100 | 100% Physical | 100 | 04/02/2021 | 31/05/2025 | 14/08/2025 | 21/07/2022 | 34.14 | 34.14
446 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-I) (SM/07849) | SM/07849 | 55.2 | 635 | RETROFITTING | 100 | 100% Physical | 92 | 14/01/2021 | 29/05/2025 | 14/08/2025 | 18/01/2021 | 50.83 | 50.83
447 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) (SM/08072) | SM/08072 | 68.38 | 618 | RETROFITTING | 100 | 100% Physical | 76 | 04/02/2021 | 31/03/2025 | 14/08/2025 | 08/09/2021 | 51.98 | 51.98
448 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Water Supply Scheme at Basirhat-II Block (Phase-I) (SM/07853) | SM/07853 | 50.97 | 420 | RETROFITTING | 100 | 100% Physical | 96 | 14/01/2021 | 19/05/2025 | 14/08/2025 | 18/01/2021 | 49.14 | 49.14
449 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-II) (SM/07618) | SM/07618 | 22.12 | 346 | RETROFITTING | 100 | 100% Physical | 96 | 05/01/2021 | 31/05/2025 | 14/08/2025 | 16/03/2022 | 21.23 | 21.23
450 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-I) (SM/07846) | SM/07846 | 44.61 | 506 | RETROFITTING | 100 | 100% Physical | 99 | 14/01/2021 | 31/05/2025 | 14/08/2025 | 18/01/2021 | 44.33 | 44.33
451 | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08728) | SM/08728 | 143.69 | 1365 | RETROFITTING | 100 | 100% Physical | 72 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 02/12/2021 | 103.35 | 103.35
452 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). (SM/08238) | SM/08238 | 76.1 | 1202 | RETROFITTING | 100 | 100% Physical | 81 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 07/10/2021 | 61.73 | 61.73
453 | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . (SM/08245) | SM/08245 | 104.38 | 1215 | RETROFITTING | 100 | 100% Physical | 94 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 07/06/2021 | 97.85 | 97.85
454 | Retrofitting of Jashaikati Zone II & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . (SM/08246) | SM/08246 | 100.27 | 1352 | RETROFITTING | 100 | 100% Physical | 89 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 07/06/2021 | 89.56 | 89.56
455 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) (SM/08769) | SM/08769 | 17.35 | 214 | RETROFITTING | 100 | 100% Physical | 81 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 08/10/2021 | 14 | 13.84
456 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) (SM/08772) | SM/08772 | 25.42 | 329 | RETROFITTING | 100 | 100% Physical | 87 | 13/09/2021 | 31/05/2025 | 14/08/2025 | 08/10/2021 | 22 | 22
457 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08638) | SM/08638 | 61.11 | 900 | RETROFITTING | 100 | 100% Physical | 92 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/09/2021 | 56.27 | 56.27
458 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) (SM/08639) | SM/08639 | 100.22 | 1500 | RETROFITTING | 100 | 100% Physical | 87 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/09/2021 | 87.19 | 87.19
459 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) (SM/08660) | SM/08660 | 100.06 | 1500 | RETROFITTING | 100 | 100% Physical | 90 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/03/2022 | 89.71 | 89.71
460 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/09735) | SM/09735 | 180.22 | 1200 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2021 | 28/05/2025 | 14/08/2025 | 18/01/2021 | 172.83 | 172.83
461 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) (SM/08780) | SM/08780 | 91.28 | 1394 | RETROFITTING | 100 | 100% Physical | 95 | 13/09/2021 | 30/05/2025 | 14/08/2025 | 09/12/2021 | 87.13 | 80.15
462 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) (SM/08785) | SM/08785 | 253.71 | 2134 | RETROFITTING | 100 | 100% Physical | 83 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 13/12/2021 | 210.09 | 210.09
463 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) (SM/08786) | SM/08786 | 197.7 | 3000 | RETROFITTING | 100 | 100% Physical | 86 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 27/12/2021 | 169.43 | 169.43
464 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/08787) | SM/08787 | 230.14 | 4500 | RETROFITTING | 100 | 100% Physical | 90 | 13/09/2021 | 29/05/2025 | 14/08/2025 | 13/12/2021 | 207.13 | 207.13
465 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) (SM/07615) | SM/07615 | 67.21 | 1036 | RETROFITTING | 100 | 100% Physical | 54 | 05/01/2021 | 30/05/2025 | 14/08/2025 | 05/02/2021 | 36.39 | 36.39
466 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Diara Water Supply Scheme at Bagdah Block (Phase-I) (SM/08070) | SM/08070 | 26.81 | 412 | RETROFITTING | 100 | 100% Physical | 84 | 04/02/2021 | 30/05/2025 | 14/08/2025 | 18/02/2022 | 22.46 | 22.46
467 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dighari Water Supply Scheme at Bongaon Block (Phase-II). (SM/08048) | SM/08048 | 62.67 | 1164 | RETROFITTING | 100 | 100% Physical | 96 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 31/05/2021 | 60 | 60
468 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) (SM/07617) | SM/07617 | 99.98 | 1260 | RETROFITTING | 100 | 100% Physical | 91 | 05/01/2021 | 31/03/2025 | 14/08/2025 | 14/08/2020 | 90.67 | 90.29
469 | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection (SM/07021) | SM/07021 | 61.28 | 500 | RETROFITTING | 100 | 100% Physical | 69 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 42.54 | 42.54
470 | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection (SM/07024) | SM/07024 | 104.68 | 1509 | RETROFITTING | 100 | 100% Physical | 74 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 77.81 | 77.81
471 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) (SM/08763) | SM/08763 | 98.97 | 1000 | RETROFITTING | 100 | 100% Physical | 97 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 95.81 | 95.81
472 | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. (SM/09152) | SM/09152 | 204.21 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 14/08/2025 | 14/06/2021 | 0 | 0
473 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) (SM/08766) | SM/08766 | 98.79 | 912 | RETROFITTING | 100 | 100% Physical | 83 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 14/09/2021 | 82.24 | 82.24
474 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). (SM/09730) | SM/09730 | 197.1 | 2300 | RETROFITTING | 100 | 100% Physical | 88 | 26/11/2021 | 31/03/2025 | 14/08/2025 | 19/04/2022 | 172.97 | 172.97
475 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08656) | SM/08656 | 100.07 | 1500 | RETROFITTING | 100 | 100% Physical | 87 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/09/2021 | 87.1 | 87.1
476 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) (SM/08256) | SM/08256 | 97.57 | 842 | RETROFITTING | 100 | 100% Physical | 78 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 75.76 | 75.76
477 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) (SM/08644) | SM/08644 | 291.24 | 2731 | RETROFITTING | 100 | 100% Physical | 63 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 18/01/2022 | 184.73 | 184.73
478 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/08788) | SM/08788 | 89.79 | 1350 | RETROFITTING | 100 | 100% Physical | 97 | 13/09/2021 | 27/05/2025 | 14/08/2025 | 10/02/2022 | 87 | 87
479 | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08729) | SM/08729 | 116.53 | 1131 | RETROFITTING | 100 | 100% Physical | 85 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 01/10/2021 | 99.01 | 99.01
480 | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) (SM/08178) | SM/08178 | 102.85 | 1352 | RETROFITTING | 100 | 100% Physical | 88 | 08/02/2021 | 31/03/2025 | 14/08/2025 | 19/02/2021 | 90.25 | 90.25
481 | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) (SM/08176) | SM/08176 | 80.2 | 1229 | RETROFITTING | 100 | 100% Physical | 87 | 08/02/2021 | 31/03/2025 | 14/08/2025 | 19/02/2021 | 70 | 70
482 | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) (SM/08179) | SM/08179 | 99.61 | 1622 | RETROFITTING | 100 | 100% Physical | 87 | 08/02/2021 | 31/03/2025 | 14/08/2025 | 19/02/2021 | 87.14 | 87.14
483 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07602) | SM/07602 | 94.17 | 1615 | RETROFITTING | 100 | 100% Physical | 99 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 93.02 | 93.02
484 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07609) | SM/07609 | 53.91 | 1443 | RETROFITTING | 100 | 100% Physical | 96 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 52.01 | 52.01
485 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. (SM/07610) | SM/07610 | 223.92 | 2979 | RETROFITTING | 100 | 100% Physical | 100 | 05/01/2021 | 31/03/2025 | 14/08/2025 | 14/01/2021 | 223.82 | 221
486 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) (SM/07613) | SM/07613 | 60.66 | 639 | RETROFITTING | 100 | 100% Physical | 90 | 05/01/2021 | 31/03/2025 | 14/08/2025 | 18/01/2021 | 54.77 | 54.77
487 | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07712) | SM/07712 | 89.51 | 1097 | RETROFITTING | 100 | 100% Physical | 87 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 26/02/2021 | 77.97 | 77.97
488 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-I) (SM/07844) | SM/07844 | 50.79 | 730 | RETROFITTING | 100 | 100% Physical | 92 | 14/01/2021 | 31/03/2025 | 14/08/2025 | 31/05/2021 | 46.68 | 46.68
489 | Retrofitting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08726) | SM/08726 | 78.61 | 2322 | RETROFITTING | 100 | 100% Physical | 71 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 01/10/2021 | 55.58 | 55.58
490 | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm (SM/09154) | SM/09154 | 249.78 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 14/08/2025 | 30/06/2021 | 0 | 0
491 | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha (SM/09030) | SM/09030 | 176.14 | 0 | DISASTER | 100 | 100% Physical | 0 | 30/10/2021 | 03/07/2024 | 14/08/2025 | 23/03/2022 | 0 | 0
492 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) (SM/07851) | SM/07851 | 84.15 | 867 | RETROFITTING | 100 | 100% Physical | 97 | 14/01/2021 | 31/03/2025 | 14/08/2025 | 18/01/2021 | 81.55 | 81.55
493 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Piped Water Supply Scheme, Basirhat-I Block under Barasat Division, P.H.E.Dte. (Phase-II) (SM/08768) | SM/08768 | 17 | 202 | RETROFITTING | 100 | 100% Physical | 94 | 13/09/2021 | 22/05/2025 | 14/08/2025 | 08/10/2021 | 16 | 14.77
494 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Piped Water Supply Scheme, Baduria Block under Barasat Division, P.H.E.Dte. (Phase-II) (SM/08770) | SM/08770 | 22.44 | 273 | RETROFITTING | 100 | 100% Physical | 95 | 13/09/2021 | 19/05/2025 | 14/08/2025 | 08/10/2021 | 21.3 | 21.27
495 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa Piped Water Supply Scheme at Habra-II Block (Phase-I) (SM/08776) | SM/08776 | 91.53 | 1328 | RETROFITTING | 100 | 100% Physical | 76 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 20/01/2022 | 69.88 | 69.88
496 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-II) Piped Water Supply Scheme at Baduria Block (Phase-I) (SM/08654) | SM/08654 | 154.44 | 1997 | RETROFITTING | 100 | 100% Physical | 76 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 14/03/2022 | 118.07 | 118.07
497 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Raghunathpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) (SM/08657) | SM/08657 | 61.11 | 900 | RETROFITTING | 100 | 100% Physical | 84 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 08/09/2021 | 51.21 | 51.21
498 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) (SM/08784) | SM/08784 | 134.94 | 2085 | RETROFITTING | 100 | 100% Physical | 76 | 13/09/2021 | 30/05/2025 | 14/08/2025 | 28/12/2021 | 101.91 | 100.33
499 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08650) | SM/08650 | 54.59 | 800 | RETROFITTING | 100 | 100% Physical | 94 | 18/06/2021 | 28/05/2025 | 14/08/2025 | 31/12/2021 | 51.55 | 51.55
500 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-II) (SM/07624) | SM/07624 | 67.83 | 1043 | RETROFITTING | 100 | 100% Physical | 98 | 05/01/2021 | 31/05/2025 | 14/08/2025 | 01/11/2022 | 66.23 | 66.23
501 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) (SM/08260) | SM/08260 | 99.12 | 1113 | RETROFITTING | 100 | 100% Physical | 100 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 08/09/2021 | 99.09 | 99.09
502 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh (SM/08767) | SM/08767 | 60.31 | 900 | RETROFITTING | 100 | 100% Physical | 96 | 13/09/2021 | 28/05/2025 | 14/08/2025 | 08/10/2021 | 57.61 | 57.61
503 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-II) (SM/08066) | SM/08066 | 6.6 | 100 | RETROFITTING | 100 | 100% Physical | 96 | 04/02/2021 | 30/05/2025 | 14/08/2025 | 31/01/2022 | 6.31 | 6.31
504 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Palla Water Supply Scheme at Bongaon Block (Phase-I) (SM/08047) | SM/08047 | 73.37 | 1048 | RETROFITTING | 100 | 100% Physical | 95 | 01/02/2021 | 31/03/2026 | 14/08/2025 | 10/06/2021 | 69.5 | 69.5
505 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07601) | SM/07601 | 85.45 | 1371 | RETROFITTING | 100 | 100% Physical | 96 | 05/01/2021 | 30/04/2025 | 14/08/2025 | 20/01/2021 | 82.23 | 82.23
506 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) (SM/07621) | SM/07621 | 54.83 | 848 | RETROFITTING | 100 | 100% Physical | 94 | 05/01/2021 | 30/05/2025 | 14/08/2025 | 11/02/2021 | 51.58 | 51.58
507 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) (SM/07622) | SM/07622 | 32.21 | 467 | RETROFITTING | 100 | 100% Physical | 95 | 05/01/2021 | 29/05/2025 | 14/08/2025 | 29/06/2021 | 30.7 | 30.7
508 | Retrofitting of Chaumuha Water Supply scheme under Barasat - II Block for providing Functional House Tap Connection (SM/07023) | SM/07023 | 100.03 | 981 | RETROFITTING | 100 | 100% Physical | 83 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 83.1 | 83.1
509 | Retrofiting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection (SM/07025) | SM/07025 | 105.21 | 2322 | RETROFITTING | 100 | 100% Physical | 91 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 95.72 | 95.72
510 | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection (SM/07027) | SM/07027 | 89.31 | 1143 | RETROFITTING | 100 | 100% Physical | 95 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 84.69 | 84.69
511 | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07713) | SM/07713 | 84.21 | 1006 | RETROFITTING | 100 | 100% Physical | 95 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 26/02/2021 | 79.93 | 79.93
512 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) (SM/07845) | SM/07845 | 22.88 | 300 | RETROFITTING | 100 | 100% Physical | 93 | 14/01/2021 | 28/05/2025 | 14/08/2025 | 28/02/2022 | 21.16 | 21.16
513 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). (SM/08731) | SM/08731 | 99.33 | 802 | RETROFITTING | 100 | 100% Physical | 95 | 09/09/2021 | 31/12/2025 | 14/08/2025 | 16/11/2021 | 94.07 | 94.02
514 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) (SM/08270) | SM/08270 | 145.34 | 1481 | RETROFITTING | 100 | 100% Physical | 97 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 01/02/2022 | 140.36 | 140.36
515 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Bangangram (Zone-II) Water SupplyScheme at Bongaon Block (Phase-II). (SM/08237) | SM/08237 | 61.96 | 1085 | RETROFITTING | 100 | 100% Physical | 84 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 12/11/2021 | 52.35 | 50.74
516 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Taranipur W/S Scheme (Zone-II) at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). (SM/09728) | SM/09728 | 148.48 | 1100 | RETROFITTING | 100 | 100% Physical | 95 | 26/11/2021 | 31/03/2025 | 14/08/2025 | 18/01/2021 | 141.1 | 141.1
517 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08642) | SM/08642 | 99.01 | 1500 | RETROFITTING | 100 | 100% Physical | 98 | 18/06/2021 | 26/05/2025 | 14/08/2025 | 08/09/2021 | 96.82 | 96.82
518 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08659) | SM/08659 | 225.64 | 3500 | RETROFITTING | 100 | 100% Physical | 95 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 26/10/2021 | 214.44 | 214.44
519 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08646) | SM/08646 | 67.63 | 1000 | RETROFITTING | 100 | 100% Physical | 92 | 18/06/2021 | 29/05/2025 | 14/08/2025 | 08/09/2021 | 62.47 | 62.47
520 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08647) | SM/08647 | 262.67 | 4000 | RETROFITTING | 100 | 100% Physical | 98 | 18/06/2021 | 30/05/2025 | 14/08/2025 | 01/02/2022 | 257.49 | 257.49
521 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). (SM/10553) | SM/10553 | 89.4 | 144 | RETROFITTING | 100 | 100% Physical | 97 | 18/04/2022 | 30/05/2025 | 14/08/2025 | 05/07/2022 | 86.79 | 86.79
522 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-II) (SM/08071) | SM/08071 | 14.47 | 222 | RETROFITTING | 100 | WO no issued | 97 | 04/02/2021 | 31/05/2025 | 14/08/2025 | 19/02/2021 | 14 | 14
523 | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07709) | SM/07709 | 93.79 | 1280 | RETROFITTING | 100 | 100% Physical | 91 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 20/01/2021 | 84.93 | 84.93
524 | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) (SM/07706) | SM/07706 | 78.7 | 1262 | RETROFITTING | 100 | 100% Physical | 84 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 21/01/2021 | 66.31 | 66.31
525 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-I) (SM/08067) | SM/08067 | 135.21 | 2110 | RETROFITTING | 100 | 100% Physical | 91 | 04/02/2021 | 31/03/2025 | 14/08/2025 | 03/08/2021 | 123.31 | 123.31
526 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) (SM/08068) | SM/08068 | 87.78 | 983 | RETROFITTING | 100 | 100% Physical | 96 | 04/02/2021 | 30/05/2025 | 14/08/2025 | 19/02/2021 | 84.25 | 84.25
527 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-I) (SM/07848) | SM/07848 | 59.57 | 711 | RETROFITTING | 100 | 100% Physical | 95 | 14/01/2021 | 30/05/2025 | 14/08/2025 | 18/01/2021 | 56.38 | 56.38
528 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) (SM/07612) | SM/07612 | 87.47 | 1036 | RETROFITTING | 100 | 100% Physical | 90 | 05/01/2021 | 31/03/2025 | 14/08/2025 | 18/02/2021 | 78.39 | 78.39
529 | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07707) | SM/07707 | 102.91 | 1390 | RETROFITTING | 100 | 100% Physical | 82 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 20/01/2021 | 84.74 | 84.74
530 | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08723) | SM/08723 | 100.71 | 1485 | RETROFITTING | 100 | 100% Physical | 86 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 30/09/2021 | 86.5 | 86.5
531 | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) (SM/08724) | SM/08724 | 137 | 1807 | RETROFITTING | 100 | 100% Physical | 84 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 16/03/2022 | 114.74 | 114.74
532 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) (SM/08266) | SM/08266 | 93.01 | 2338 | RETROFITTING | 100 | 100% Physical | 92 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 85.22 | 85.22
533 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) (SM/08267) | SM/08267 | 44.13 | 679 | RETROFITTING | 100 | 100% Physical | 95 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 19/01/2022 | 41.99 | 41.99
534 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) (SM/08777) | SM/08777 | 164.51 | 2393 | RETROFITTING | 100 | 100% Physical | 86 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 141.79 | 140.88
535 | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) (SM/08247) | SM/08247 | 103.23 | 1397 | RETROFITTING | 100 | 100% Physical | 95 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 07/06/2021 | 97.64 | 97.6
536 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) (SM/08778) | SM/08778 | 139.9 | 2027 | RETROFITTING | 100 | 100% Physical | 81 | 13/09/2021 | 30/05/2025 | 14/08/2025 | 31/12/2021 | 112.88 | 112.72
537 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) (SM/08263) | SM/08263 | 193.64 | 2046 | RETROFITTING | 100 | 100% Physical | 97 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 08/07/2021 | 187.05 | 187.05
538 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/10557) | SM/10557 | 309.66 | 1727 | RETROFITTING | 100 | 100% Physical | 96 | 18/04/2022 | 31/03/2026 | 14/08/2025 | 11/01/2023 | 297.71 | 297.71
539 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). (SM/08239) | SM/08239 | 92.02 | 1496 | RETROFITTING | 100 | 100% Physical | 91 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 08/10/2021 | 83.57 | 83.57
540 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). (SM/08732) | SM/08732 | 91.82 | 1768 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/03/2026 | 14/08/2025 | 07/10/2021 | 89.14 | 89.14
541 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) (SM/08645) | SM/08645 | 100.07 | 1500 | RETROFITTING | 100 | 100% Physical | 86 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 15/12/2021 | 85.66 | 85.66
542 | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection (SM/07022) | SM/07022 | 105.02 | 1694 | RETROFITTING | 100 | 100% Physical | 86 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 89.84 | 89.84
543 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of CHAMPAPUKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08658) | SM/08658 | 80.66 | 1200 | RETROFITTING | 100 | 100% Physical | 91 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/09/2021 | 73.65 | 73.65
544 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-I) (SM/07850) | SM/07850 | 97.77 | 1596 | RETROFITTING | 100 | 100% Physical | 95 | 14/01/2021 | 30/05/2025 | 14/08/2025 | 18/01/2021 | 93.32 | 93.32
545 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) (SM/07608) | SM/07608 | 74.49 | 1927 | RETROFITTING | 100 | 100% Physical | 94 | 05/01/2021 | 31/03/2026 | 14/08/2025 | 20/01/2021 | 69.88 | 69.88
546 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme (Phase-I) (SM/07623) | SM/07623 | 50.43 | 790 | RETROFITTING | 100 | 100% Physical | 100 | 05/01/2021 | 31/05/2025 | 14/08/2025 | 16/03/2022 | 50.39 | 50.39
547 | Retrofitting of Dwarir Jangle water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection (SM/07026) | SM/07026 | 104.87 | 2746 | RETROFITTING | 100 | 100% Physical | 86 | 18/11/2020 | 31/03/2025 | 14/08/2025 | 18/12/2020 | 90.35 | 90.35
548 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). (SM/09226) | SM/09226 | 67.73 | 1000 | RETROFITTING | 100 | 100% Physical | 94 | 01/11/2021 | 31/03/2025 | 14/08/2025 | 18/01/2021 | 63.54 | 63.53
549 | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08727) | SM/08727 | 104.96 | 906 | RETROFITTING | 100 | 100% Physical | 81 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 01/10/2021 | 85.03 | 85.03
550 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gainpur Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (SM/08730) | SM/08730 | 53.55 | 464 | RETROFITTING | 100 | 100% Physical | 90 | 09/09/2021 | 31/03/2026 | 14/08/2025 | 07/10/2021 | 48.08 | 48.08
551 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ghatpatila (Zone-I) Piped Water Supply Scheme, Bagdah Block (Phase-I) (SM/08268) | SM/08268 | 132.23 | 1763 | RETROFITTING | 100 | 100% Physical | 88 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 01/02/2022 | 116.57 | 116.57
552 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-II WaterSupply Scheme at Bongaon Block (Phase-I). (SM/08235) | SM/08235 | 66.16 | 1040 | RETROFITTING | 100 | 100% Physical | 89 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 07/10/2021 | 58.92 | 58.92
553 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08655) | SM/08655 | 97.8 | 1500 | RETROFITTING | 100 | 100% Physical | 97 | 18/06/2021 | 20/05/2025 | 14/08/2025 | 10/02/2022 | 95.32 | 95.32
554 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08649) | SM/08649 | 93.7 | 1400 | RETROFITTING | 100 | 100% Physical | 97 | 18/06/2021 | 24/05/2025 | 14/08/2025 | 18/01/2021 | 90.57 | 90.57
555 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) (SM/08258) | SM/08258 | 98.58 | 1450 | RETROFITTING | 100 | 100% Physical | 100 | 22/02/2021 | 31/05/2025 | 14/08/2025 | 22/02/2021 | 98.55 | 98.55
556 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) (SM/08782) | SM/08782 | 238.36 | 3674 | RETROFITTING | 100 | 100% Physical | 67 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 27/12/2021 | 159.85 | 159.85
557 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) (SM/08783) | SM/08783 | 108.98 | 1585 | RETROFITTING | 100 | 100% Physical | 73 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 79.16 | 79.16
558 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) (SM/08262) | SM/08262 | 79.42 | 1051 | RETROFITTING | 100 | 100% Physical | 93 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 08/08/2023 | 73.69 | 73.69
559 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) (SM/08075) | SM/08075 | 163.43 | 1031 | RETROFITTING | 100 | 100% Physical | 83 | 04/02/2021 | 31/03/2025 | 14/08/2025 | 14/08/2020 | 136.22 | 136.22
560 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) (SM/07614) | SM/07614 | 99.79 | 1153 | RETROFITTING | 100 | 100% Physical | 99 | 05/01/2021 | 31/03/2025 | 14/08/2025 | 18/01/2021 | 99.29 | 98.69
561 | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07708) | SM/07708 | 94.8 | 1247 | RETROFITTING | 100 | 100% Physical | 89 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 21/01/2021 | 84.13 | 84.13
562 | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . (SM/08177) | SM/08177 | 103.74 | 1773 | RETROFITTING | 100 | 100% Physical | 88 | 08/02/2021 | 31/03/2025 | 14/08/2025 | 19/02/2021 | 91.72 | 91.72
563 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) (SM/07619) | SM/07619 | 25.19 | 349 | RETROFITTING | 100 | 100% Physical | 79 | 05/01/2021 | 30/05/2025 | 14/08/2025 | 01/11/2022 | 19.78 | 19.78
564 | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07710) | SM/07710 | 105.05 | 1352 | RETROFITTING | 100 | 100% Physical | 86 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 21/01/2021 | 90.28 | 90.28
565 | Retrofitting of Paltadanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) (SM/07711) | SM/07711 | 94.25 | 1228 | RETROFITTING | 100 | 100% Physical | 92 | 07/01/2021 | 31/03/2025 | 14/08/2025 | 20/01/2021 | 86.53 | 86.53
566 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-I) (SM/07847) | SM/07847 | 37.68 | 413 | RETROFITTING | 100 | 100% Physical | 94 | 14/01/2021 | 28/05/2025 | 14/08/2025 | 18/01/2021 | 35.25 | 35.25
567 | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) (SM/08725) | SM/08725 | 73.87 | 2746 | RETROFITTING | 100 | 100% Physical | 91 | 07/09/2021 | 31/03/2025 | 14/08/2025 | 01/10/2021 | 67.41 | 67.41
568 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) (SM/08764) | SM/08764 | 99.01 | 1200 | RETROFITTING | 100 | 100% Physical | 79 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 14/09/2021 | 78.57 | 78.57
569 | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm (SM/09153) | SM/09153 | 282.59 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 14/08/2025 | 14/06/2021 | 0 | 0
570 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at Bongaon Block (Phase-II). (SM/08240) | SM/08240 | 56.45 | 1040 | RETROFITTING | 100 | 100% Physical | 89 | 22/02/2021 | 31/03/2026 | 14/08/2025 | 25/10/2021 | 49.97 | 49.95
571 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) (SM/08774) | SM/08774 | 79.82 | 1161 | RETROFITTING | 100 | 100% Physical | 74 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 28/12/2021 | 59.46 | 59.46
572 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) (SM/08775) | SM/08775 | 210.37 | 3230 | RETROFITTING | 100 | 100% Physical | 76 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 17/12/2021 | 160.7 | 144.05
573 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08651) | SM/08651 | 78.68 | 1200 | RETROFITTING | 100 | 100% Physical | 95 | 18/06/2021 | 31/03/2026 | 14/08/2025 | 15/12/2021 | 75 | 74.9
574 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08641) | SM/08641 | 253.69 | 4000 | RETROFITTING | 100 | 100% Physical | 100 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 31/12/2021 | 253.64 | 253.64
575 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). (SM/08643) | SM/08643 | 100.22 | 1500 | RETROFITTING | 100 | 100% Physical | 100 | 18/06/2021 | 22/05/2025 | 14/08/2025 | 24/01/2022 | 100.22 | 100.22
576 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) (SM/08257) | SM/08257 | 98.87 | 800 | RETROFITTING | 100 | 100% Physical | 100 | 22/02/2021 | 31/03/2025 | 14/08/2025 | 17/01/2022 | 98.87 | 98
577 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) (SM/08261) | SM/08261 | 97.54 | 1495 | RETROFITTING | 100 | 100% Physical | 100 | 22/02/2021 | 31/05/2025 | 14/08/2025 | 27/05/2021 | 97.54 | 97.54
578 | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte (SM/08996) | SM/08996 | 148.09 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 03/07/2024 | 14/08/2025 | 28/05/2021 | 0 | 0
579 | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. (SM/10546) | SM/10546 | 738.46 | 3466 | AUGMENTATION | 100 | 100% Physical | 22 | 18/04/2022 | 31/12/2026 | 14/08/2025 | 31/12/2021 | 162.45 | 161.7
580 | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) (SM/09934) | SM/09934 | 168.33 | 1435 | RETROFITTING | 100 | 100% Physical | 33 | 13/12/2021 | 31/03/2025 | 14/08/2025 | 17/02/2022 | 55.62 | 55.62
581 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) (SM/08779) | SM/08779 | 187.55 | 2765 | RETROFITTING | 100 | 100% Physical | 76 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 03/01/2022 | 142.71 | 142.59
582 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block (SM/08242) | SM/08242 | 88.07 | 1179 | RETROFITTING | 100 | 100% Physical | 94 | 22/02/2021 | 30/04/2025 | 14/08/2025 | 08/10/2021 | 83.13 | 83.13
583 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) (SM/08781) | SM/08781 | 80.33 | 1200 | RETROFITTING | 100 | 100% Physical | 47 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 05/09/2022 | 37.9 | 37.9
584 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) (SM/08765) | SM/08765 | 99.39 | 1300 | RETROFITTING | 100 | 100% Physical | 83 | 13/09/2021 | 31/03/2025 | 14/08/2025 | 20/01/2022 | 82.49 | 82.49
585 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). (SM/08648) | SM/08648 | 67.63 | 1000 | RETROFITTING | 100 | 100% Physical | 93 | 18/06/2021 | 31/03/2025 | 14/08/2025 | 07/09/2021 | 62.87 | 62.87
586 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) (SM/10552) | SM/10552 | 122.05 | 874 | RETROFITTING | 100 | 100% Physical | 91 | 18/04/2022 | 31/03/2025 | 14/08/2025 | 23/02/2022 | 111.65 | 111.65
Total |  |  | 363675.36 | 1426426 | [8 empty] | 156604.66 | 154967.22