## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. (SM/09025) | SM/09025 | 157.43 | 0 | DISASTER | 0 | WO no issued | 0 | 30/10/2021 |  | 02/11/2021 | 15/02/2021 | 0 | 0
2 | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. (SM/15216) | SM/15216 | 222.22 | 0 | SOLARISATION | 0 | WO no issued | 0 | 07/02/2023 | 31/03/2024 | 12/06/2023 | 17/07/2023 | 0 | 0
3 | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. (SM/11989) | SM/11989 | 55 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 01/09/2022 |  | 05/09/2022 | 28/03/2022 | 0 | 0
4 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/08967) | SM/08967 | 29.51 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 28/10/2021 |  | 29/10/2021 | 30/12/2022 | 0 | 0
5 | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte (SM/18130) | SM/18130 | 21 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 29/03/2023 |  | 31/03/2023 | 05/05/2023 | 0 | 0
6 | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. (SM/06617) | SM/06617 | 44.02 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/02/2020 |  | 31/05/2021 | 15/09/2021 | 0 | 0
7 | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte (SM/19085) | SM/19085 | 84.55 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/12/2023 |  | 05/12/2023 | 01/06/2023 | 0 | 0
8 | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. (SM/11504) | SM/11504 | 687.92 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 04/07/2022 |  | 21/07/2022 | 18/04/2022 | 0 | 0
9 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Hooghly District. (SM/08974) | SM/08974 | 406.09 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 19/08/2022 | 0 | 0
10 | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities (SM/18131) | SM/18131 | 131.68 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | WO no issued | 0 | 29/03/2023 |  | 31/03/2023 | 11/10/2023 | 0 | 0
11 | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR (SM/11996) | SM/11996 | 38.59 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 01/09/2022 |  | 05/09/2022 | 29/06/2022 | 0 | 0
12 | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme (SM/18931) | SM/18931 | 83.25 | 0 | AUGMENTATION | 1 | WO no issued | 33 | 09/10/2023 | 09/04/2024 | 03/11/2023 | 01/02/2022 | 27.26 | 27.26
13 | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] (SM/19161) | SM/19161 | 51.21 | 1522 | AUGMENTATION | 1 | WO no issued | 2 | 18/01/2024 | 30/09/2024 | 26/04/2024 | 15/01/2024 | 0.93 | 0
14 | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. (SM/18930) | SM/18930 | 55.3 | 0 | AUGMENTATION | 1 | WO no issued | 66 | 09/10/2023 | 09/04/2024 | 29/11/2023 | 01/02/2022 | 36.53 | 36.26
15 | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block (SM/18953) | SM/18953 | 67.84 | 0 | AUGMENTATION | 7 | WO no issued | 21 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 14.33 | 0
16 | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block (SM/18955) | SM/18955 | 67.84 | 0 | AUGMENTATION | 7 | WO no issued | 1 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 31/08/2023 | 0.96 | 0.96
17 | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block (SM/18956) | SM/18956 | 67.84 | 0 | AUGMENTATION | 7 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
18 | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block (SM/18951) | SM/18951 | 153.27 | 0 | AUGMENTATION | 8 | WO no issued | 12 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 18.67 | 14.46
19 | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block (SM/18952) | SM/18952 | 153.27 | 0 | AUGMENTATION | 8 | WO no issued | 25 | 10/10/2023 | 31/03/2025 | 14/05/2024 | 06/11/2023 | 37.66 | 28.08
20 | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block (SM/18948) | SM/18948 | 153.27 | 0 | AUGMENTATION | 8 | WO no issued | 12 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 18.64 | 0
21 | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. (SM/18949) | SM/18949 | 144.76 | 0 | AUGMENTATION | 8 | WO no issued | 1 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0.95 | 0.95
22 | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block (SM/18963) | SM/18963 | 63.33 | 0 | AUGMENTATION | 8 | WO no issued | 43 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 01/12/2022 | 27.46 | 27.46
23 | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18939) | SM/18939 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
24 | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/18943) | SM/18943 | 85.43 | 0 | AUGMENTATION | 9 | WO no issued | 15 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 21/11/2023 | 12.44 | 4.98
25 | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18969) | SM/18969 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 4 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 8.41 | 3.65
26 | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18976) | SM/18976 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
27 | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/18978) | SM/18978 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
28 | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18938) | SM/18938 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
29 | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block (SM/18958) | SM/18958 | 155.79 | 0 | AUGMENTATION | 9 | WO no issued | 6 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 22/03/2022 | 9.55 | 9.55
30 | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I (SM/18928) | SM/18928 | 162.48 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 08/11/2023 | 0 | 0
31 | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/18975) | SM/18975 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 23 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 43.62 | 43.62
32 | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18977) | SM/18977 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
33 | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18932) | SM/18932 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
34 | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18935) | SM/18935 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 1 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0.95 | 0.95
35 | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18940) | SM/18940 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
36 | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block (SM/18954) | SM/18954 | 153.27 | 0 | AUGMENTATION | 9 | WO no issued | 9 | 10/10/2023 | 31/03/2025 | 14/05/2024 | 06/11/2023 | 14.31 | 14.31
37 | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18945) | SM/18945 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 1 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 1.91 | 1.91
38 | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block (SM/18947) | SM/18947 | 140.91 | 0 | AUGMENTATION | 9 | WO no issued | 13 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 23/11/2023 | 18.97 | 0
39 | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18973) | SM/18973 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 22/11/2023 | 0 | 0
40 | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18941) | SM/18941 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 9 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 21/11/2023 | 17.08 | 17.08
41 | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18946) | SM/18946 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
42 | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18933) | SM/18933 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 1 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0.95 | 0
43 | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] (SM/18791) | SM/18791 | 72.46 | 3233 | AUGMENTATION | 9 | WO no issued | 14 | 07/09/2023 | 30/04/2024 | 26/04/2024 | 26/09/2023 | 10.35 | 10.35
44 | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18971) | SM/18971 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
45 | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18972) | SM/18972 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
46 | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/18974) | SM/18974 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 22/11/2023 | 0 | 0
47 | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18936) | SM/18936 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
48 | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/18937) | SM/18937 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
49 | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block (SM/18959) | SM/18959 | 75.93 | 0 | AUGMENTATION | 9 | WO no issued | 12 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 17/03/2022 | 8.76 | 8.76
50 | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly (SM/15793) | SM/15793 | 52.29 | 610 | AUGMENTATION | 9 | WO no issued | 12 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 6.12 | 0
51 | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18934) | SM/18934 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
52 | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18970) | SM/18970 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
53 | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block (SM/18957) | SM/18957 | 146.07 | 0 | AUGMENTATION | 9 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 08/11/2023 | 0 | 0
54 | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/18944) | SM/18944 | 188.47 | 0 | AUGMENTATION | 9 | WO no issued | 1 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 1.91 | 1.91
55 | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly (SM/19014) | SM/19014 | 211.71 | 335 | NEW | 10 | WO no issued | 0 | 27/10/2023 | 30/04/2024 | 26/04/2024 | 30/10/2023 | 0 | 0
56 | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/18981) | SM/18981 | 103.03 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
57 | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block (SM/18965) | SM/18965 | 174.68 | 0 | AUGMENTATION | 10 | WO no issued | 7 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 12.28 | 12.28
58 | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block (SM/18960) | SM/18960 | 172.88 | 0 | AUGMENTATION | 10 | WO no issued | 12 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/03/2022 | 20.9 | 20.9
59 | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I (SM/18929) | SM/18929 | 194.31 | 0 | AUGMENTATION | 10 | WO no issued | 21 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 40.95 | 40.95
60 | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block (SM/18961) | SM/18961 | 174.48 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 0 | 0
61 | Improvement of BHANDARHATI Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block-Arambagh (SM/18927) | SM/18927 | 92.25 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 09/10/2023 | 30/04/2024 | 26/04/2024 |  | 0 | 0
62 | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK (SM/18979) | SM/18979 | 103.03 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0 | 0
63 | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block (SM/18964) | SM/18964 | 194.51 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 0 | 0
64 | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK (SM/18942) | SM/18942 | 103.03 | 1766 | AUGMENTATION | 10 | WO no issued | 4 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 21/11/2023 | 4.29 | 4.29
65 | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' (SM/19015) | SM/19015 | 170.87 | 296 | NEW | 10 | WO no issued | 8 | 27/10/2023 | 31/03/2025 | 30/04/2024 | 30/10/2023 | 14.42 | 1.82
66 | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block (SM/18962) | SM/18962 | 192.68 | 0 | AUGMENTATION | 10 | WO no issued | 0 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 0 | 0
67 | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK (SM/18980) | SM/18980 | 103.03 | 0 | AUGMENTATION | 10 | WO no issued | 1 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 06/11/2023 | 0.86 | 0.86
68 | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block (SM/18950) | SM/18950 | 153.27 | 0 | AUGMENTATION | 10 | WO no issued | 10 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 21/11/2022 | 15.66 | 15.66
69 | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local (SM/18967) | SM/18967 | 124.38 | 0 | AUGMENTATION | 11 | WO no issued | 11 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 14.02 | 14.02
70 | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly (SM/18310) | SM/18310 | 1372.02 | 3156 | NEW | 12 | WO no issued | 6 | 26/06/2023 | 30/04/2024 | 26/04/2024 | 27/07/2023 | 80.36 | 80.36
71 | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/12235) | SM/12235 | 981.16 | 3207 | NEW | 13 | WO no issued | 14 | 07/09/2022 | 31/12/2024 | 26/04/2024 | 30/12/2022 | 138.27 | 138.27
72 | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY (SM/14118) | SM/14118 | 958.51 | 2117 | NEW | 13 | WO no issued | 13 | 02/01/2023 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 124.35 | 124.35
73 | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly (SM/13333) | SM/13333 | 928.84 | 2064 | NEW | 13 | WO no issued | 8 | 17/10/2022 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 70.38 | 70.38
74 | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly (SM/13762) | SM/13762 | 977.91 | 2092 | NEW | 13 | WO no issued | 9 | 18/11/2022 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 86.42 | 76.34
75 | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/13324) | SM/13324 | 962.17 | 2319 | NEW | 13 | WO no issued | 10 | 17/10/2022 | 17/04/2025 | 10/05/2024 | 09/02/2023 | 95.08 | 81.64
76 | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY (SM/14116) | SM/14116 | 920.66 | 2013 | NEW | 13 | WO no issued | 12 | 02/01/2023 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 114.32 | 114.32
77 | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/12233) | SM/12233 | 964.48 | 2578 | NEW | 13 | WO no issued | 25 | 07/09/2022 | 31/12/2024 | 26/04/2024 | 30/12/2022 | 237.64 | 237.64
78 | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. (SM/18345) | SM/18345 | 1177.52 | 3124 | NEW | 13 | WO no issued | 7 | 04/07/2023 | 31/12/2024 | 26/04/2024 | 27/07/2023 | 80.76 | 80.76
79 | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric (SM/15898) | SM/15898 | 71.13 | 200 | AUGMENTATION | 13 | WO no issued | 60 | 20/02/2023 | 30/04/2024 | 26/04/2024 | 11/04/2023 | 42.78 | 42.78
80 | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly (SM/18309) | SM/18309 | 1026.73 | 2455 | NEW | 13 | WO no issued | 2 | 26/06/2023 | 31/10/2024 | 26/04/2024 | 27/07/2023 | 15.45 | 12.07
81 | Source Augmentation of Bamonjol PWSS (SM/15794) | SM/15794 | 55.16 | 1233 | AUGMENTATION | 13 | WO no issued | 42 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 22.96 | 22.96
82 | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY (SM/17176) | SM/17176 | 277.86 | 793 | NEW | 14 | WO no issued | 24 | 15/03/2023 | 30/04/2024 | 26/04/2024 | 10/04/2023 | 67.41 | 54.12
83 | Saibana Mini Piped Water Supply Scheme (SM/13556) | SM/13556 | 41.7 | 84 | NEW | 14 | WO no issued | 0 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
84 | Bhabapur mini pipe water supply scheme (SM/13673) | SM/13673 | 39.84 | 78 | NEW | 15 | WO no issued | 1 | 09/11/2022 | 30/04/2024 | 26/04/2024 |  | 0.48 | 0.48
85 | Jasapur mini pipe water supply scheme (SM/13664) | SM/13664 | 41.46 | 96 | NEW | 15 | WO no issued | 1 | 09/11/2022 | 30/04/2024 | 26/04/2024 |  | 0.59 | 0.59
86 | Charkona Mini Piped Water Supply Scheme (SM/13415) | SM/13415 | 34.85 | 25 | NEW | 15 | WO no issued | 0 | 02/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
87 | Chetua Mini Piped Water Supply Scheme (SM/13558) | SM/13558 | 38.93 | 58 | NEW | 15 | WO no issued | 0 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
88 | Sibpur Mini Piped Water Supply Scheme (SM/13668) | SM/13668 | 37.24 | 42 | NEW | 15 | WO no issued | 0 | 09/11/2022 | 30/04/2024 | 26/04/2024 |  | 0 | 0
89 | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. (SM/18373) | SM/18373 | 1258.73 | 4229 | NEW | 15 | WO no issued | 14 | 11/07/2023 | 30/04/2024 | 26/04/2024 | 04/08/2023 | 177.89 | 7.26
90 | Chak Behala mini pipe water supply scheme (SM/13656) | SM/13656 | 35.41 | 37 | NEW | 15 | WO no issued | 1 | 09/11/2022 | 30/04/2024 | 26/04/2024 |  | 0.23 | 0.23
91 | Kaipukuria Mini Piped Water Supply Scheme (SM/13557) | SM/13557 | 41.09 | 82 | NEW | 15 | WO no issued | 0 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
92 | Par adra mini pipe water supply scheme (SM/13559) | SM/13559 | 41.27 | 94 | NEW | 15 | WO no issued | 1 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 0.58 | 0.58
93 | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/17626) | SM/17626 | 663.19 | 1341 | NEW | 15 | WO no issued | 8 | 21/03/2023 | 30/11/2024 | 26/04/2024 | 19/04/2023 | 54.51 | 50.38
94 | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. (SM/18624) | SM/18624 | 1061.79 | 3725 | NEW | 15 | WO no issued | 34 | 31/07/2023 | 30/04/2024 | 26/04/2024 | 07/08/2023 | 359.64 | 321.1
95 | Jot ram mini pipe water supply scheme (SM/13672) | SM/13672 | 39.59 | 76 | NEW | 15 | WO no issued | 1 | 09/11/2022 | 30/04/2024 | 26/04/2024 |  | 0.47 | 0.47
96 | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY (SM/15790) | SM/15790 | 432.75 | 993 | NEW | 16 | WO no issued | 11 | 20/02/2023 | 31/12/2024 | 26/04/2024 | 18/04/2023 | 45.57 | 45.57
97 | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/17290) | SM/17290 | 400.4 | 706 | NEW | 16 | WO no issued | 25 | 15/03/2023 | 31/12/2024 | 26/04/2024 | 24/03/2023 | 99.47 | 51.54
98 | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. (SM/18623) | SM/18623 | 1061.62 | 4209 | NEW | 16 | WO no issued | 16 | 31/07/2023 | 30/04/2024 | 26/04/2024 | 10/08/2023 | 171.41 | 166.01
99 | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. (SM/18666) | SM/18666 | 1136.8 | 3725 | NEW | 16 | WO no issued | 44 | 04/08/2023 | 30/04/2024 | 26/04/2024 | 07/08/2023 | 505.01 | 505.01
100 | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. (SM/12245) | SM/12245 | 688.42 | 2741 | NEW | 16 | WO no issued | 15 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 101.15 | 95.85
101 | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY (SM/12239) | SM/12239 | 649.37 | 2266 | NEW | 16 | WO no issued | 10 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 66.05 | 61.95
102 | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. (SM/12248) | SM/12248 | 671.18 | 2935 | NEW | 16 | WO no issued | 48 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 325.4 | 304.57
103 | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK (SM/15801) | SM/15801 | 178.69 | 613 | AUGMENTATION | 16 | WO no issued | 37 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 18/04/2023 | 65.95 | 65.95
104 | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/14684) | SM/14684 | 494.21 | 806 | NEW | 16 | WO no issued | 7 | 31/01/2023 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 34.97 | 17.74
105 | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) (SM/17719) | SM/17719 | 398.66 | 907 | NEW | 16 | WO no issued | 19 | 17/03/2023 | 31/12/2024 | 26/04/2024 | 15/05/2023 | 74.76 | 74.76
106 | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. (SM/12250) | SM/12250 | 637.12 | 2029 | NEW | 16 | WO no issued | 12 | 06/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 75.76 | 61.73
107 | KALACHHARA PIPED WATER SUPPLY SCHEME (SM/18100) | SM/18100 | 190.75 | 292 | NEW | 16 | WO no issued | 13 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 25.24 | 24.28
108 | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. (SM/17632) | SM/17632 | 637.99 | 2018 | NEW | 16 | WO no issued | 7 | 22/03/2023 | 30/04/2024 | 26/04/2024 | 24/04/2023 | 47.4 | 47.4
109 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR (SM/18397) | SM/18397 | 4047.1 | 12225 | AUGMENTATION | 16 | WO no issued | 15 | 12/07/2023 | 30/04/2024 | 26/04/2024 | 20/07/2023 | 612.06 | 612.06
110 | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY (SM/18320) | SM/18320 | 1374.35 | 4389 | NEW | 17 | WO no issued | 11 | 27/06/2023 | 30/04/2024 | 26/04/2024 | 28/07/2023 | 157 | 94.85
111 | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18592) | SM/18592 | 1147.47 | 2086 | NEW | 17 | WO no issued | 5 | 31/07/2023 | 31/03/2025 | 30/04/2024 | 28/08/2023 | 56.02 | 34.49
112 | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) (SM/14685) | SM/14685 | 690.25 | 2176 | NEW | 17 | WO no issued | 6 | 31/01/2023 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 42.39 | 42.39
113 | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK (SM/18644) | SM/18644 | 2099.59 | 5011 | AUGMENTATION | 17 | WO no issued | 2 | 31/07/2023 | 31/03/2025 | 26/04/2024 | 28/08/2023 | 51.68 | 0
114 | Augmentation Of Piped Water Supply Scheme For KHANAKUL (SM/18645) | SM/18645 | 1200.12 | 3930 | AUGMENTATION | 17 | WO no issued | 2 | 31/07/2023 | 30/04/2024 | 26/04/2024 | 08/08/2023 | 20.78 | 20.78
115 | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. (SM/18667) | SM/18667 | 1548.7 | 5093 | NEW | 17 | WO no issued | 18 | 04/08/2023 | 30/04/2024 | 26/04/2024 | 04/08/2023 | 272.81 | 272.81
116 | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) (SM/15252) | SM/15252 | 726.99 | 2352 | NEW | 17 | WO no issued | 7 | 07/02/2023 | 31/12/2024 | 26/04/2024 | 22/02/2023 | 54.3 | 50.36
117 | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT (SM/18594) | SM/18594 | 1120.56 | 2500 | NEW | 17 | WO no issued | 8 | 31/07/2023 | 31/03/2025 | 14/05/2024 | 28/08/2023 | 88.39 | 69.28
118 | Mayapur Piped Water Supply Scheme. (SM/18833) | SM/18833 | 1143.23 | 2505 | NEW | 17 | WO no issued | 2 | 21/09/2023 | 31/05/2025 | 10/05/2024 | 22/09/2023 | 18.9 | 14.58
119 | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY (SM/18642) | SM/18642 | 1974.34 | 4990 | NEW | 17 | WO no issued | 1 | 31/07/2023 | 31/12/2024 | 26/04/2024 | 07/08/2023 | 12.79 | 12.79
120 | GROUND BASED PWSS FOR NASIBPUR (SM/17627) | SM/17627 | 900.19 | 2463 | NEW | 17 | WO no issued | 25 | 21/03/2023 | 30/04/2024 | 26/04/2024 | 19/04/2023 | 228.89 | 218.92
121 | Baligari Piped Water Supply Scheme. (SM/18671) | SM/18671 | 2067.16 | 3994 | NEW | 17 | WO no issued | 22 | 04/08/2023 | 30/04/2024 | 26/04/2024 | 07/08/2023 | 460.19 | 440.39
122 | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME (SM/18657) | SM/18657 | 1453.6 | 3347 | NEW | 17 | WO no issued | 18 | 04/08/2023 | 30/04/2024 | 26/04/2024 | 07/08/2023 | 259.62 | 259.62
123 | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18772) | SM/18772 | 1654.55 | 3575 | NEW | 17 | WO no issued | 6 | 25/08/2023 | 30/04/2024 | 26/04/2024 | 29/08/2023 | 103.47 | 103.47
124 | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12251) | SM/12251 | 605.31 | 2417 | NEW | 17 | WO no issued | 40 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 243.39 | 243.39
125 | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18595) | SM/18595 | 1140.41 | 2659 | NEW | 17 | WO no issued | 18 | 31/07/2023 | 30/04/2024 | 26/04/2024 | 28/08/2023 | 207.24 | 207.24
126 | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly (SM/18771) | SM/18771 | 1074.94 | 2347 | NEW | 17 | WO no issued | 4 | 25/08/2023 | 30/04/2024 | 26/04/2024 | 29/08/2023 | 40.3 | 40.3
127 | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/17625) | SM/17625 | 685.43 | 1354 | NEW | 17 | WO no issued | 4 | 21/03/2023 | 31/12/2024 | 26/04/2024 | 19/04/2023 | 29.74 | 29.74
128 | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR (SM/18643) | SM/18643 | 1148.41 | 5168 | AUGMENTATION | 17 | WO no issued | 8 | 31/07/2023 | 31/12/2024 | 26/04/2024 | 07/08/2023 | 92.01 | 92.01
129 | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/12232) | SM/12232 | 762.35 | 1752 | NEW | 17 | WO no issued | 5 | 07/09/2022 | 30/11/2024 | 26/04/2024 | 30/12/2022 | 36.17 | 36.17
130 | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. (SM/12249) | SM/12249 | 659.51 | 2152 | NEW | 17 | WO no issued | 8 | 06/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 51.33 | 51.33
131 | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. (SM/18101) | SM/18101 | 224.39 | 328 | NEW | 17 | WO no issued | 43 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 95.72 | 84.71
132 | SINHAL PATAN PIPED WATER SUPPLY SCHEME (SM/18103) | SM/18103 | 183.43 | 230 | NEW | 17 | WO no issued | 3 | 27/03/2023 | 30/04/2024 | 26/04/2024 | 15/05/2023 | 4.71 | 4.71
133 | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) (SM/17721) | SM/17721 | 861.33 | 2838 | NEW | 17 | WO no issued | 14 | 17/03/2023 | 31/12/2024 | 26/04/2024 | 24/04/2023 | 123.05 | 123.05
134 | BENGAI WATER SUPPLY SCHEME (SM/18597) | SM/18597 | 1076.77 | 3263 | NEW | 17 | WO no issued | 7 | 31/07/2023 | 31/12/2024 | 26/04/2024 | 28/08/2023 | 73.92 | 73.92
135 | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly (SM/13334) | SM/13334 | 942.99 | 2537 | NEW | 17 | WO no issued | 47 | 17/10/2022 | 30/04/2024 | 26/04/2024 | 09/02/2023 | 447.77 | 447.77
136 | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/13322) | SM/13322 | 862.94 | 1951 | NEW | 17 | WO no issued | 5 | 17/10/2022 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 46.49 | 46.49
137 | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY (SM/15792) | SM/15792 | 916.78 | 1899 | NEW | 17 | WO no issued | 3 | 20/02/2023 | 31/12/2024 | 26/04/2024 | 28/03/2023 | 24.49 | 24.49
138 | BHANDARDAHA PIPED WATER SUPPLY SCHEME (SM/18096) | SM/18096 | 214.91 | 368 | NEW | 17 | WO no issued | 42 | 27/03/2023 | 30/04/2024 | 26/04/2024 | 15/05/2023 | 89.8 | 89.8
139 | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18308) | SM/18308 | 1433.95 | 3198 | NEW | 17 | WO no issued | 5 | 26/06/2023 | 31/12/2024 | 26/04/2024 | 27/07/2023 | 78.73 | 78.73
140 | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly (SM/18646) | SM/18646 | 1321.9 | 3142 | NEW | 17 | WO no issued | 1 | 31/07/2023 | 31/12/2024 | 26/04/2024 | 07/08/2023 | 19.35 | 19.35
141 | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12253) | SM/12253 | 576.69 | 1882 | NEW | 17 | WO no issued | 88 | 08/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 507.65 | 507.65
142 | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12256) | SM/12256 | 908.93 | 3235 | NEW | 18 | WO no issued | 39 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 351.18 | 351.18
143 | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12246) | SM/12246 | 700.75 | 3344 | NEW | 18 | WO no issued | 33 | 06/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 232.47 | 232.47
144 | Source Augmentation of Paschim Joykrishnapur PWSS (SM/15795) | SM/15795 | 110.32 | 4230 | AUGMENTATION | 18 | WO no issued | 79 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 87.11 | 87.11
145 | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12257) | SM/12257 | 811.45 | 3762 | NEW | 18 | WO no issued | 31 | 06/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 252.04 | 252.04
146 | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12243) | SM/12243 | 538.93 | 1963 | NEW | 18 | WO no issued | 36 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 195.25 | 195.25
147 | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/13325) | SM/13325 | 647.04 | 1356 | NEW | 18 | WO no issued | 1 | 17/10/2022 | 31/12/2024 | 26/04/2024 | 09/02/2023 | 8.33 | 8.33
148 | Ground Water Based Bighati (Zone -II) PWSS (SM/15249) | SM/15249 | 711.52 | 1579 | NEW | 18 | WO no issued | 42 | 07/02/2023 | 30/04/2024 | 26/04/2024 | 06/03/2023 | 300.46 | 300.46
149 | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE (SM/13354) | SM/13354 | 295.6 | 4709 | RETROFITTING | 18 | WO no issued | 0 | 19/10/2022 | 31/08/2024 | 26/04/2024 | 19/07/2023 | 0 | 0
150 | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS (SM/17628) | SM/17628 | 764.21 | 2306 | NEW | 18 | WO no issued | 28 | 21/03/2023 | 30/04/2024 | 26/04/2024 | 19/04/2023 | 216.48 | 216.48
151 | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12252) | SM/12252 | 523.15 | 1695 | NEW | 18 | WO no issued | 28 | 06/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 147.07 | 147.07
152 | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block (SM/15788) | SM/15788 | 308.8 | 50 | AUGMENTATION | 18 | WO no issued | 0 | 20/02/2023 | 30/11/2024 | 26/04/2024 | 28/03/2023 | 0.31 | 0.31
153 | Alasin Mini Piped Water Supply Scheme (SM/13671) | SM/13671 | 42.45 | 92 | NEW | 18 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
154 | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca (SM/18966) | SM/18966 | 408.03 | 0 | AUGMENTATION | 19 | WO no issued | 6 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 10/11/2023 | 25.68 | 14.26
155 | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME (SM/16136) | SM/16136 | 231.55 | 540 | NEW | 19 | WO no issued | 31 | 22/02/2023 | 30/04/2024 | 26/04/2024 | 18/04/2023 | 72.43 | 72.43
156 | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. (SM/18926) | SM/18926 | 164.41 | 500 | AUGMENTATION | 19 | WO no issued | 1 | 09/10/2023 | 30/04/2024 | 26/04/2024 | 14/03/2024 | 0.95 | 0
157 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME (SM/15891) | SM/15891 | 151.75 | 2353 | AUGMENTATION | 19 | WO no issued | 78 | 20/02/2023 | 30/04/2024 | 26/04/2024 | 11/05/2023 | 117.91 | 99.88
158 | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME (SM/18097) | SM/18097 | 362.38 | 934 | NEW | 19 | WO no issued | 11 | 27/03/2023 | 30/04/2024 | 26/04/2024 | 15/05/2023 | 39.02 | 39.02
159 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block (SM/18109) | SM/18109 | 41.33 | 1874 | RETROFITTING | 19 | WO no issued | 0 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 20/02/2024 | 0 | 0
160 | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' (SM/19013) | SM/19013 | 312.74 | 534 | NEW | 19 | WO no issued | 11 | 27/10/2023 | 30/06/2024 | 26/04/2024 | 30/10/2023 | 35.47 | 35.47
161 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block (SM/18106) | SM/18106 | 21.11 | 170 | RETROFITTING | 19 | WO no issued | 0 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 29/02/2024 | 0 | 0
162 | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. (SM/15890) | SM/15890 | 995.46 | 2876 | NEW | 20 | WO no issued | 48 | 20/02/2023 | 30/04/2024 | 26/04/2024 | 11/04/2023 | 473.99 | 455.33
163 | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/16237) | SM/16237 | 55.7 | 124 | NEW | 20 | WO no issued | 40 | 24/02/2023 | 31/05/2024 | 26/04/2024 | 17/04/2023 | 22.36 | 22.36
164 | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly (SM/17629) | SM/17629 | 406.5 | 933 | NEW | 20 | WO no issued | 21 | 21/03/2023 | 30/04/2024 | 26/04/2024 | 19/04/2023 | 84.39 | 84.39
165 | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK (SM/18099) | SM/18099 | 241.67 | 522 | NEW | 20 | WO no issued | 12 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 28.77 | 28.77
166 | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan (SM/10248) | SM/10248 | 666.15 | 0 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 20 | WO no issued | 0 | 24/02/2022 | 31/03/2024 | 14/10/2023 | 19/04/2022 | 0 | 0
167 | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, (SM/10273) | SM/10273 | 659.42 | 0 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 20 | WO no issued | 0 | 25/02/2022 | 31/03/2024 | 14/10/2023 | 24/06/2020 | 0 | 0
168 | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME (SM/11582) | SM/11582 | 681.54 | 1724 | NEW | 21 | WO no issued | 38 | 22/07/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 256.61 | 158.67
169 | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME (SM/11581) | SM/11581 | 695.99 | 1489 | NEW | 21 | WO no issued | 36 | 22/07/2022 | 30/04/2024 | 26/04/2024 | 01/11/2022 | 253.44 | 219.07
170 | Bhupatipur Mini Piped Water Supply Scheme (SM/13587) | SM/13587 | 33.76 | 16 | NEW | 21 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
171 | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/15899) | SM/15899 | 114.3 | 300 | AUGMENTATION | 21 | WO no issued | 31 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 35.45 | 35.45
172 | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly (SM/18104) | SM/18104 | 554.56 | 891 | NEW | 21 | WO no issued | 15 | 27/03/2023 | 30/04/2024 | 26/04/2024 | 15/05/2023 | 80.72 | 71.04
173 | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. (SM/18778) | SM/18778 | 1107.03 | 0 | NEW | 21 | WO no issued | 9 | 28/08/2023 | 31/03/2025 | 26/04/2024 | 29/08/2023 | 96.65 | 0
174 | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/15900) | SM/15900 | 114.3 | 300 | AUGMENTATION | 21 | WO no issued | 33 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 38.16 | 37.88
175 | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly (SM/18105) | SM/18105 | 673.9 | 1287 | NEW | 21 | WO no issued | 25 | 27/03/2023 | 30/04/2024 | 26/04/2024 | 15/05/2023 | 168.76 | 54.65
176 | SAMANTA KHANDA WATER SUPPLY SCHEME (SM/16127) | SM/16127 | 810.49 | 2089 | NEW | 21 | WO no issued | 8 | 22/02/2023 | 30/06/2024 | 26/04/2024 | 06/03/2023 | 65.91 | 65.91
177 | SIRAZPUR PIPED WATER SUPPLY SCHEME (SM/11580) | SM/11580 | 811.72 | 2119 | NEW | 21 | WO no issued | 41 | 22/07/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 330.15 | 319.49
178 | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/13337) | SM/13337 | 769.29 | 2648 | NEW | 21 | WO no issued | 21 | 17/10/2022 | 30/04/2024 | 26/04/2024 | 30/05/2023 | 163.04 | 126.66
179 | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY (SM/18346) | SM/18346 | 1006.17 | 2882 | NEW | 21 | WO no issued | 23 | 04/07/2023 | 30/04/2024 | 26/04/2024 | 28/07/2023 | 228.9 | 118.38
180 | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18429) | SM/18429 | 1139.61 | 3194 | NEW | 21 | WO no issued | 2 | 18/07/2023 | 31/12/2024 | 26/04/2024 | 26/07/2023 | 19.68 | 19.68
181 | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT (SM/15913) | SM/15913 | 907.78 | 2200 | NEW | 22 | WO no issued | 22 | 22/02/2023 | 30/11/2024 | 26/04/2024 | 06/03/2023 | 197.68 | 164.27
182 | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly (SM/16138) | SM/16138 | 271.36 | 611 | NEW | 22 | WO no issued | 60 | 22/02/2023 | 30/04/2024 | 26/04/2024 | 18/04/2023 | 161.92 | 116.24
183 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block (SM/18111) | SM/18111 | 20.53 | 160 | RETROFITTING | 22 | WO no issued | 0 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 28/10/2022 | 0 | 0
184 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR (SM/12369) | SM/12369 | 3756.01 | 12977 | AUGMENTATION | 22 | WO no issued | 20 | 13/09/2022 | 30/04/2024 | 26/04/2024 | 31/08/2022 | 743.56 | 740.75
185 | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12263) | SM/12263 | 831.48 | 3116 | NEW | 22 | WO no issued | 25 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 209.15 | 173.74
186 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block (SM/18107) | SM/18107 | 21.7 | 180 | RETROFITTING | 22 | WO no issued | 0 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/06/2023 | 0 | 0
187 | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS (SM/17289) | SM/17289 | 787.21 | 1715 | NEW | 22 | WO no issued | 41 | 15/03/2023 | 30/04/2024 | 26/04/2024 | 10/04/2023 | 320.82 | 319.62
188 | Sultangachha Mini Piped Water Supply Scheme (SM/13593) | SM/13593 | 40.81 | 72 | NEW | 22 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
189 | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly (SM/15889) | SM/15889 | 884.94 | 2516 | NEW | 22 | WO no issued | 9 | 20/02/2023 | 30/04/2024 | 26/04/2024 | 03/08/2023 | 78.61 | 78.61
190 | Nesraguri Mini Piped Water Supply Scheme (SM/13588) | SM/13588 | 35.58 | 26 | NEW | 22 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
191 | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12265) | SM/12265 | 948.04 | 4371 | NEW | 22 | WO no issued | 39 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 366.76 | 366.37
192 | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme (SM/18110) | SM/18110 | 142.51 | 1776 | RETROFITTING | 23 | WO no issued | 72 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 26/09/2022 | 101.92 | 101.92
193 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME (SM/12014) | SM/12014 | 197.98 | 3119 | RETROFITTING | 23 | WO no issued | 0 | 01/09/2022 | 31/07/2024 | 26/04/2024 | 19/07/2023 | 0 | 0
194 | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly (SM/18670) | SM/18670 | 1132.16 | 4182 | AUGMENTATION | 23 | WO no issued | 10 | 04/08/2023 | 31/12/2024 | 26/04/2024 | 07/08/2023 | 113.96 | 0
195 | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/16119) | SM/16119 | 558.04 | 200 | AUGMENTATION | 23 | WO no issued | 26 | 22/02/2023 | 30/04/2024 | 26/04/2024 | 19/05/2023 | 146.09 | 146.09
196 | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/15887) | SM/15887 | 920.25 | 2293 | NEW | 24 | WO no issued | 17 | 20/02/2023 | 30/11/2024 | 26/04/2024 | 18/04/2023 | 155.59 | 134.81
197 | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT (SM/18288) | SM/18288 | 1182.64 | 2787 | NEW | 24 | WO no issued | 22 | 26/06/2023 | 30/11/2024 | 26/04/2024 | 27/07/2023 | 257.52 | 207.02
198 | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/15800) | SM/15800 | 178.69 | 50 | AUGMENTATION | 24 | WO no issued | 24 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 42.28 | 42.28
199 | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly (SM/16979) | SM/16979 | 371.55 | 827 | NEW | 24 | WO no issued | 45 | 16/03/2023 | 30/04/2024 | 26/04/2024 | 19/04/2023 | 167.29 | 167.29
200 | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly (SM/15789) | SM/15789 | 962.24 | 2185 | NEW | 24 | WO no issued | 17 | 20/02/2023 | 31/12/2024 | 26/04/2024 | 11/04/2023 | 166.34 | 145.02
201 | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12229) | SM/12229 | 823.3 | 3651 | NEW | 25 | WO no issued | 43 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 355.68 | 355.68
202 | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12262) | SM/12262 | 749.81 | 2542 | NEW | 25 | WO no issued | 35 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 260.05 | 260.05
203 | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK (SM/12258) | SM/12258 | 390.37 | 837 | NEW | 25 | WO no issued | 8 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 31.75 | 31.75
204 | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK (SM/18098) | SM/18098 | 237.95 | 740 | NEW | 25 | WO no issued | 32 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 76.24 | 76.24
205 | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12260) | SM/12260 | 653.17 | 2969 | NEW | 25 | WO no issued | 36 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 233.31 | 233.31
206 | BADE DIGARIA PIPED WATER SUPPLY SCHEME (SM/13336) | SM/13336 | 657.34 | 1666 | NEW | 26 | WO no issued | 44 | 17/10/2022 | 30/04/2024 | 26/04/2024 | 09/02/2023 | 291.24 | 192.7
207 | BASUBATI PIPED WATER SUPPLY SCHEME (SM/12365) | SM/12365 | 1115.75 | 3236 | NEW | 26 | WO no issued | 29 | 13/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 324.1 | 211.22
208 | BHANJIPUR PIPED WATER SUPPLY SCHEME (SM/11288) | SM/11288 | 759.23 | 2533 | NEW | 26 | WO no issued | 36 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 29/09/2022 | 274.98 | 274.98
209 | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/12238) | SM/12238 | 533.98 | 2145 | NEW | 26 | WO no issued | 34 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 183.91 | 183.49
210 | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/15797) | SM/15797 | 114.3 | 300 | AUGMENTATION | 26 | WO no issued | 56 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 18/04/2023 | 63.65 | 53.19
211 | NANDA PIPED WATER SUPPLY SCHEME (SM/12567) | SM/12567 | 1120.63 | 2460 | NEW | 26 | WO no issued | 39 | 14/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 433.07 | 353.49
212 | PARJANA PIPED WATER SUPPLY SCHEME (SM/13335) | SM/13335 | 950 | 2350 | NEW | 26 | WO no issued | 36 | 17/10/2022 | 30/04/2024 | 26/04/2024 | 09/02/2023 | 340.3 | 149.75
213 | HARAT PIPED WATER SUPPLY SCHEME (SM/11290) | SM/11290 | 668.44 | 1913 | NEW | 26 | WO no issued | 45 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 29/09/2022 | 302.14 | 282.53
214 | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/15798) | SM/15798 | 114.3 | 300 | AUGMENTATION | 26 | WO no issued | 44 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 50.17 | 50.17
215 | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK (SM/18095) | SM/18095 | 274.98 | 477 | NEW | 26 | WO no issued | 38 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 104.61 | 93.35
216 | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME (SM/16651) | SM/16651 | 550.37 | 1407 | NEW | 26 | WO no issued | 41 | 14/03/2023 | 30/04/2024 | 26/04/2024 | 19/04/2023 | 226.96 | 226.96
217 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block (SM/18108) | SM/18108 | 20.53 | 160 | RETROFITTING | 27 | WO no issued | 0 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 28/04/2023 | 0 | 0
218 | BINAGRAM PIPED WATER SUPPLY SCHEME (SM/13568) | SM/13568 | 1145.89 | 2669 | NEW | 27 | WO no issued | 24 | 09/11/2022 | 30/04/2024 | 26/04/2024 | 09/02/2023 | 269.88 | 256.84
219 | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/13321) | SM/13321 | 883.11 | 3505 | NEW | 27 | WO no issued | 62 | 17/10/2022 | 30/04/2024 | 26/04/2024 | 09/02/2023 | 548.52 | 548.52
220 | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block (SM/15806) | SM/15806 | 65.81 | 25 | AUGMENTATION | 28 | WO no issued | 0 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 0 | 0
221 | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block (SM/15807) | SM/15807 | 128.96 | 50 | AUGMENTATION | 28 | WO no issued | 21 | 17/02/2023 | 31/08/2024 | 26/04/2024 | 18/04/2023 | 27.33 | 27.33
222 | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/17716) | SM/17716 | 728.51 | 1985 | NEW | 28 | WO no issued | 19 | 17/03/2023 | 31/12/2024 | 26/04/2024 | 24/04/2023 | 135.17 | 135.17
223 | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly (SM/14982) | SM/14982 | 886.42 | 1829 | NEW | 28 | WO no issued | 39 | 04/02/2023 | 30/11/2024 | 26/04/2024 | 09/02/2023 | 343.98 | 343.98
224 | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block (SM/15802) | SM/15802 | 66.42 | 50 | AUGMENTATION | 28 | WO no issued | 38 | 20/02/2023 | 31/07/2024 | 26/04/2024 | 11/04/2023 | 25.09 | 25.09
225 | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block (SM/15787) | SM/15787 | 441.46 | 50 | AUGMENTATION | 28 | WO no issued | 50 | 20/02/2023 | 30/11/2024 | 26/04/2024 | 17/04/2023 | 222.61 | 211.29
226 | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK (SM/18668) | SM/18668 | 1392.22 | 3101 | NEW | 28 | WO no issued | 23 | 04/08/2023 | 31/03/2025 | 26/04/2024 | 07/08/2023 | 320.46 | 313.6
227 | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block (SM/15814) | SM/15814 | 129.51 | 25 | AUGMENTATION | 28 | WO no issued | 0 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 28/03/2023 | 0 | 0
228 | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/15799) | SM/15799 | 201.57 | 2683 | AUGMENTATION | 28 | WO no issued | 32 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 30/12/2022 | 64.49 | 64.49
229 | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE (SM/13355) | SM/13355 | 139.24 | 2150 | RETROFITTING | 29 | WO no issued | 1 | 19/10/2022 | 30/06/2024 | 26/04/2024 | 11/08/2023 | 0.7 | 0.7
230 | GAURIBATI PIPED WATER SUPPLY SCHEME (SM/11289) | SM/11289 | 464.35 | 1387 | NEW | 29 | WO no issued | 48 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 29/09/2022 | 222.76 | 222.76
231 | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block (SM/15811) | SM/15811 | 65.58 | 25 | AUGMENTATION | 29 | WO no issued | 0 | 17/02/2023 | 31/10/2024 | 26/04/2024 | 28/03/2023 | 0 | 0
232 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR (SM/13349) | SM/13349 | 1335.08 | 3300 | AUGMENTATION | 30 | WO no issued | 41 | 19/10/2022 | 30/04/2024 | 26/04/2024 | 31/05/2022 | 545.87 | 545.87
233 | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME (SM/13348) | SM/13348 | 1091.61 | 4545 | AUGMENTATION | 31 | WO no issued | 54 | 19/10/2022 | 30/04/2024 | 26/04/2024 | 31/08/2022 | 587.27 | 587.27
234 | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/13320) | SM/13320 | 999.62 | 2300 | NEW | 31 | WO no issued | 25 | 17/10/2022 | 31/10/2024 | 26/04/2024 | 09/02/2023 | 248.58 | 127.38
235 | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block (SM/15808) | SM/15808 | 77.79 | 25 | AUGMENTATION | 31 | WO no issued | 19 | 17/02/2023 | 31/08/2024 | 26/04/2024 | 28/03/2023 | 14.53 | 3.95
236 | NAWPARA PIPED WATER SUPPLY SCHEME (SM/18241) | SM/18241 | 1152.24 | 2929 | NEW | 31 | WO no issued | 45 | 16/06/2023 | 30/06/2024 | 26/04/2024 | 22/06/2023 | 518.81 | 372.77
237 | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. (SM/18347) | SM/18347 | 1047.32 | 4186 | AUGMENTATION | 31 | WO no issued | 24 | 04/07/2023 | 31/10/2024 | 26/04/2024 | 28/07/2023 | 247.41 | 247.41
238 | BAHIRKHANDA PIPED WATER SUPPLY SCHEME (SM/13404) | SM/13404 | 1616.96 | 3610 | NEW | 32 | WO no issued | 49 | 21/10/2022 | 30/06/2024 | 26/04/2024 | 30/12/2022 | 795.69 | 781.05
239 | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY (SM/14117) | SM/14117 | 753.82 | 1616 | NEW | 32 | WO no issued | 36 | 02/01/2023 | 31/10/2024 | 26/04/2024 | 09/02/2023 | 269.96 | 180.47
240 | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block (SM/15812) | SM/15812 | 75.87 | 50 | AUGMENTATION | 33 | WO no issued | 13 | 17/02/2023 | 31/10/2024 | 26/04/2024 | 28/03/2023 | 9.76 | 9.76
241 | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block (SM/15809) | SM/15809 | 153.03 | 50 | AUGMENTATION | 33 | WO no issued | 19 | 20/02/2023 | 31/08/2024 | 26/04/2024 | 09/03/2023 | 28.52 | 28.52
242 | Source Augmentation of Malia PWSS (SM/15796) | SM/15796 | 55.16 | 1301 | AUGMENTATION | 33 | WO no issued | 79 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 13/05/2021 | 43.55 | 43.27
243 | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/12247) | SM/12247 | 553.34 | 1847 | NEW | 33 | WO no issued | 44 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 245.77 | 245.77
244 | BHAGABATIPUR PIPED WATER SUPPLY SCHEME (SM/11287) | SM/11287 | 99.57 | 180 | NEW | 33 | WO no issued | 37 | 28/06/2022 | 30/06/2024 | 26/04/2024 | 19/10/2022 | 36.48 | 36.2
245 | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18596) | SM/18596 | 1182.91 | 2863 | NEW | 33 | WO no issued | 25 | 31/07/2023 | 30/11/2024 | 26/04/2024 | 28/08/2023 | 292.57 | 204.6
246 | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/15250) | SM/15250 | 345.51 | 1095 | NEW | 34 | WO no issued | 55 | 07/02/2023 | 30/04/2024 | 26/04/2024 | 14/02/2023 | 190.28 | 190.28
247 | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK (SM/12259) | SM/12259 | 563.79 | 2185 | NEW | 34 | WO no issued | 47 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 264.58 | 264.58
248 | ASTARA PIPED WATER SUPPLY SCHEME (SM/11286) | SM/11286 | 646.77 | 1992 | NEW | 34 | WO no issued | 69 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 31/08/2022 | 445.81 | 425.13
249 | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/14467) | SM/14467 | 812.88 | 2454 | NEW | 34 | WO no issued | 37 | 20/01/2023 | 30/04/2024 | 26/04/2024 | 22/02/2023 | 299.99 | 299.99
250 | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/14121) | SM/14121 | 511.47 | 1852 | NEW | 34 | WO no issued | 44 | 02/01/2023 | 30/04/2024 | 26/04/2024 | 22/02/2023 | 222.69 | 222.69
251 | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block (SM/16130) | SM/16130 | 178.48 | 25 | AUGMENTATION | 36 | WO no issued | 19 | 22/02/2023 | 30/06/2024 | 26/04/2024 | 27/10/2021 | 34.19 | 33.93
252 | Digra Mini Piped Water Supply Scheme (SM/13670) | SM/13670 | 38.05 | 53 | NEW | 36 | WO no issued | 75 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 28.45 | 28.45
253 | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/14531) | SM/14531 | 1227.07 | 5064 | NEW | 36 | WO no issued | 47 | 30/01/2023 | 30/04/2024 | 26/04/2024 | 22/02/2023 | 580.15 | 577.67
254 | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/15251) | SM/15251 | 336.9 | 1570 | NEW | 36 | WO no issued | 45 | 07/02/2023 | 30/06/2024 | 26/04/2024 | 14/02/2023 | 153.12 | 153.12
255 | Muragari Mini Piped Water Supply Scheme (SM/13564) | SM/13564 | 38.17 | 55 | NEW | 36 | WO no issued | 74 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 28.23 | 28.23
256 | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. (SM/09516) | SM/09516 | 43.94 | 0 | AUGMENTATION | 36 | WO no issued | 55 | 19/11/2021 | 30/04/2024 | 02/04/2024 | 20/12/2021 | 23.95 | 23.95
257 | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. (SM/09517) | SM/09517 | 43.94 | 0 | AUGMENTATION | 36 | WO no issued | 75 | 19/11/2021 | 30/06/2024 | 24/01/2024 | 20/12/2021 | 33.05 | 33.05
258 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District (SM/19036) | SM/19036 | 25800.8 | 103628 | AUGMENTATION | 37 | WO no issued | 0 | 08/11/2023 | 31/12/2024 | 26/04/2024 | 10/11/2023 | 0 | 0
259 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI (SM/11293) | SM/11293 | 385.02 | 881 | NEW | 37 | WO no issued | 49 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 25/11/2022 | 189.48 | 189.48
260 | Char Sundalpur Mini Piped Water Supply Scheme (SM/13657) | SM/13657 | 39.14 | 65 | NEW | 37 | WO no issued | 74 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 29.11 | 29.11
261 | Rampur Mini Piped Water Supply Scheme (SM/13563) | SM/13563 | 42.21 | 94 | NEW | 37 | WO no issued | 76 | 04/11/2022 | 30/06/2024 | 26/04/2024 | 29/02/2024 | 31.91 | 31.91
262 | Mamudpur Mini Piped Water Supply Scheme (SM/13658) | SM/13658 | 38.7 | 60 | NEW | 37 | WO no issued | 74 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 28.71 | 28.71
263 | Gopalbati Piped Water Supply Scheme. (SM/16756) | SM/16756 | 421.19 | 1059 | NEW | 37 | WO no issued | 24 | 13/03/2023 | 31/10/2024 | 26/04/2024 | 22/05/2023 | 102.2 | 102.2
264 | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block (SM/15803) | SM/15803 | 63.2 | 25 | AUGMENTATION | 37 | WO no issued | 0 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 28/03/2023 | 0 | 0
265 | Basantapur Mini Piped Water Supply Scheme (SM/13560) | SM/13560 | 42.06 | 93 | NEW | 38 | WO no issued | 1 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 0.57 | 0.57
266 | Jangalpur Mini Piped Water Supply Scheme (SM/13598) | SM/13598 | 42.73 | 95 | NEW | 38 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
267 | Chautpur Mini Piped Water Supply Scheme (SM/13596) | SM/13596 | 43.04 | 98 | NEW | 38 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
268 | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly (SM/18593) | SM/18593 | 1071.3 | 2432 | NEW | 38 | WO no issued | 18 | 31/07/2023 | 31/10/2024 | 26/04/2024 | 08/08/2023 | 188.44 | 188.44
269 | Durlabhpur Mini Piped Water Supply Scheme (SM/13561) | SM/13561 | 39.95 | 74 | NEW | 38 | WO no issued | 75 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 29.83 | 29.83
270 | Naopara Mini Piped Water Supply Scheme (SM/13562) | SM/13562 | 40.56 | 77 | NEW | 38 | WO no issued | 75 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 30.41 | 30.41
271 | Dhanijpur Mini Piped Water Supply Scheme (SM/13597) | SM/13597 | 40.53 | 69 | NEW | 38 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
272 | Telinipara Mini Piped Water Supply Scheme (SM/13599) | SM/13599 | 39.39 | 68 | NEW | 38 | WO no issued | 74 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 29.33 | 29.33
273 | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (SM/18968) | SM/18968 | 45.23 | 0 | AUGMENTATION | 40 | WO no issued | 46 | 10/10/2023 | 30/04/2024 | 26/04/2024 | 20/02/2024 | 20.83 | 4.77
274 | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK (SM/15886) | SM/15886 | 679.29 | 1519 | NEW | 41 | WO no issued | 40 | 20/02/2023 | 30/09/2024 | 26/04/2024 | 18/04/2023 | 274.17 | 274.17
275 | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY (SM/12242) | SM/12242 | 286.66 | 472 | NEW | 42 | WO no issued | 53 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 151.98 | 151.98
276 | ATISARA PIPED WATER SUPPLY SCHEME (SM/12727) | SM/12727 | 1322.35 | 3260 | NEW | 42 | WO no issued | 59 | 21/09/2022 | 30/04/2024 | 26/04/2024 | 13/02/2023 | 786.3 | 655.16
277 | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY (SM/15791) | SM/15791 | 742.77 | 1671 | NEW | 43 | WO no issued | 29 | 20/02/2023 | 30/11/2024 | 26/04/2024 | 18/04/2023 | 214.91 | 214.91
278 | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under (SM/16448) | SM/16448 | 63.58 | 100 | AUGMENTATION | 43 | WO no issued | 52 | 28/02/2023 | 30/06/2024 | 26/04/2024 | 28/03/2023 | 32.79 | 32.79
279 | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK (SM/18339) | SM/18339 | 1052.22 | 4199 | AUGMENTATION | 43 | WO no issued | 48 | 04/07/2023 | 31/10/2024 | 26/04/2024 | 13/07/2023 | 505.4 | 297.03
280 | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK (SM/12255) | SM/12255 | 689.12 | 3145 | NEW | 43 | WO no issued | 53 | 07/09/2022 | 30/04/2024 | 26/04/2024 | 30/12/2022 | 365.18 | 365.18
281 | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly (SM/18348) | SM/18348 | 1091.61 | 2581 | NEW | 43 | WO no issued | 35 | 04/07/2023 | 31/10/2024 | 26/04/2024 | 13/07/2023 | 377.77 | 235.51
282 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI (SM/14040) | SM/14040 | 1265.48 | 4472 | AUGMENTATION | 44 | WO no issued | 42 | 12/12/2022 | 30/06/2024 | 26/04/2024 | 29/06/2021 | 534.54 | 521.77
283 | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly (SM/16236) | SM/16236 | 851.51 | 1850 | NEW | 45 | WO no issued | 59 | 24/02/2023 | 30/04/2024 | 26/04/2024 | 06/03/2023 | 501.79 | 501.79
284 | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block (SM/15813) | SM/15813 | 72.23 | 25 | AUGMENTATION | 45 | WO no issued | 27 | 20/02/2023 | 30/06/2024 | 26/04/2024 | 28/03/2023 | 19.26 | 7.9
285 | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly (SM/15888) | SM/15888 | 515.59 | 1260 | NEW | 46 | WO no issued | 39 | 20/02/2023 | 30/04/2024 | 26/04/2024 | 18/04/2023 | 201.87 | 191.36
286 | Augmentation of Balipur Water Supply Scheme (SM/18770) | SM/18770 | 1152.8 | 4804 | AUGMENTATION | 46 | WO no issued | 28 | 25/08/2023 | 30/04/2024 | 26/04/2024 | 29/08/2023 | 325.53 | 325.53
287 | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se (SM/16449) | SM/16449 | 128.7 | 50 | AUGMENTATION | 47 | WO no issued | 36 | 28/02/2023 | 30/06/2024 | 12/04/2024 | 11/04/2023 | 45.76 | 45.76
288 | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/18307) | SM/18307 | 1089.72 | 2440 | NEW | 47 | WO no issued | 38 | 26/06/2023 | 30/09/2024 | 26/04/2024 | 27/07/2023 | 409.76 | 409.76
289 | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. (SM/09208) | SM/09208 | 35.42 | 0 | AUGMENTATION | 48 | WO no issued | 17 | 30/10/2021 | 30/06/2024 | 26/04/2024 | 27/07/2023 | 6.15 | 6.15
290 | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT (SM/14983) | SM/14983 | 605.65 | 1322 | NEW | 48 | WO no issued | 26 | 04/02/2023 | 30/11/2024 | 26/04/2024 | 09/02/2023 | 157.32 | 157.32
291 | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und (SM/16447) | SM/16447 | 109.03 | 1450 | AUGMENTATION | 49 | WO no issued | 84 | 28/02/2023 | 30/06/2024 | 26/04/2024 | 08/02/2023 | 91.18 | 87.76
292 | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/13343) | SM/13343 | 222.7 | 879 | AUGMENTATION | 49 | WO no issued | 40 | 29/09/2022 | 30/06/2024 | 26/04/2024 | 14/02/2023 | 88.48 | 77.74
293 | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block (SM/15805) | SM/15805 | 64.09 | 25 | AUGMENTATION | 49 | WO no issued | 49 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 31.68 | 31.4
294 | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S (SM/16450) | SM/16450 | 136.17 | 100 | AUGMENTATION | 49 | WO no issued | 68 | 28/02/2023 | 30/06/2024 | 26/04/2024 | 02/01/2023 | 92.18 | 84.93
295 | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block (SM/15804) | SM/15804 | 115.21 | 50 | AUGMENTATION | 50 | WO no issued | 17 | 17/02/2023 | 30/06/2024 | 26/04/2024 | 11/04/2023 | 19.52 | 19.52
296 | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY (SM/16120) | SM/16120 | 417.91 | 435 | AUGMENTATION | 51 | WO no issued | 23 | 22/02/2023 | 31/08/2024 | 26/04/2024 | 10/05/2023 | 97.91 | 97.91
297 | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block (SM/16124) | SM/16124 | 190.76 | 50 | AUGMENTATION | 51 | WO no issued | 0 | 22/02/2023 | 31/07/2024 | 26/04/2024 | 18/05/2023 | 0 | 0
298 | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/13410) | SM/13410 | 248.89 | 22 | AUGMENTATION | 52 | WO no issued | 30 | 02/11/2022 | 30/06/2024 | 26/04/2024 | 23/08/2022 | 75.47 | 75.47
299 | Augmentation of Kulteghori Piped Water Supply Scheme (SM/16564) | SM/16564 | 59.1 | 2963 | AUGMENTATION | 52 | WO no issued | 0 | 10/03/2023 | 30/06/2024 | 26/04/2024 | 15/05/2023 | 0 | 0
300 | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. (SM/11466) | SM/11466 | 590.5 | 2923 | AUGMENTATION | 52 | WO no issued | 50 | 12/07/2022 | 30/06/2024 | 26/04/2024 | 14/07/2022 | 293.37 | 269.22
301 | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block (SM/16121) | SM/16121 | 163.66 | 25 | AUGMENTATION | 52 | WO no issued | 32 | 22/02/2023 | 30/06/2024 | 26/04/2024 | 18/05/2023 | 52.26 | 51.71
302 | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block (SM/15810) | SM/15810 | 64.36 | 50 | AUGMENTATION | 52 | WO no issued | 59 | 17/02/2023 | 31/05/2024 | 26/04/2024 | 11/04/2023 | 37.87 | 37.6
303 | Shripala Mini Piped Water Supply Scheme (SM/13669) | SM/13669 | 42.07 | 88 | NEW | 53 | WO no issued | 0 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
304 | Raghubati Piped Water Supply Scheme. (SM/18672) | SM/18672 | 1129.16 | 5842 | NEW | 53 | WO no issued | 25 | 04/08/2023 | 31/10/2024 | 26/04/2024 | 08/08/2023 | 287.92 | 287.92
305 | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/13345) | SM/13345 | 225.59 | 511 | AUGMENTATION | 54 | WO no issued | 73 | 29/09/2022 | 30/06/2024 | 26/04/2024 | 30/12/2022 | 164.03 | 145.19
306 | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block (SM/16122) | SM/16122 | 198.87 | 50 | AUGMENTATION | 54 | WO no issued | 28 | 22/02/2023 | 31/07/2024 | 26/04/2024 | 18/04/2023 | 56.65 | 37.81
307 | Shyamsundarpur Mini Piped Water Supply Scheme (SM/13412) | SM/13412 | 42.66 | 94 | NEW | 54 | WO no issued | 0 | 02/11/2022 | 30/06/2024 | 26/04/2024 |  | 0 | 0
308 | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block (SM/15815) | SM/15815 | 67.86 | 25 | AUGMENTATION | 56 | WO no issued | 0 | 20/02/2023 | 30/04/2024 | 19/03/2024 | 06/04/2023 | 0 | 0
309 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI (SM/11866) | SM/11866 | 689.8 | 2063 | AUGMENTATION | 57 | WO no issued | 61 | 17/08/2022 | 30/06/2024 | 26/04/2024 | 24/06/2020 | 422.19 | 422.19
310 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE (SM/11463) | SM/11463 | 974.92 | 3369 | AUGMENTATION | 57 | WO no issued | 64 | 12/07/2022 | 30/11/2024 | 26/04/2024 | 22/04/2022 | 620.4 | 620.4
311 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT (SM/11621) | SM/11621 | 996.92 | 1850 | NEW | 58 | WO no issued | 51 | 26/07/2022 | 30/04/2024 | 26/04/2024 | 01/11/2022 | 509.25 | 509.25
312 | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/13409) | SM/13409 | 201.57 | 2689 | AUGMENTATION | 58 | WO no issued | 19 | 02/11/2022 | 30/06/2024 | 26/04/2024 | 02/03/2023 | 38.11 | 28.68
313 | Palpukur Mini Piped Water Supply Scheme (SM/13659) | SM/13659 | 36.56 | 29 | NEW | 59 | WO no issued | 74 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 27 | 27
314 | Arazi Krittibaspur Mini Piped Water Supply Scheme (SM/13660) | SM/13660 | 34.7 | 19 | NEW | 59 | WO no issued | 73 | 09/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 25.19 | 25.19
315 | Dewanchak Mini Piped Water Supply Scheme (SM/13586) | SM/13586 | 36.22 | 25 | NEW | 59 | WO no issued | 73 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 26.52 | 26.52
316 | Kapsit Mini Piped Water Supply Scheme (SM/13554) | SM/13554 | 38.3 | 53 | NEW | 60 | WO no issued | 75 | 04/11/2022 | 30/06/2024 | 26/04/2024 | 17/03/2022 | 28.69 | 28.69
317 | Dwaripara Mini Piped Water Supply Scheme (SM/13665) | SM/13665 | 42.75 | 98 | NEW | 61 | WO no issued | 77 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 33.01 | 33.01
318 | Chak Netara Mini Piped Water Supply Scheme (SM/13551) | SM/13551 | 40.48 | 67 | NEW | 61 | WO no issued | 76 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 30.8 | 30.8
319 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT (SM/11583) | SM/11583 | 997.69 | 1656 | NEW | 61 | WO no issued | 47 | 22/07/2022 | 30/04/2024 | 26/04/2024 | 17/04/2023 | 469.14 | 469.14
320 | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/13411) | SM/13411 | 197.18 | 754 | AUGMENTATION | 61 | WO no issued | 45 | 02/11/2022 | 30/06/2024 | 26/04/2024 | 23/08/2022 | 88.24 | 83.34
321 | Jot Mahabhat Mini Piped Water Supply Scheme (SM/13555) | SM/13555 | 39.7 | 59 | NEW | 61 | WO no issued | 76 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 30.05 | 30.05
322 | Uttar Hazipur Mini Piped Water Supply Scheme (SM/13663) | SM/13663 | 39.26 | 68 | NEW | 61 | WO no issued | 75 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 29.62 | 29.62
323 | Dumurpara Mini Piped water Supply Scheme (SM/13591) | SM/13591 | 40.73 | 70 | NEW | 61 | WO no issued | 76 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 31.05 | 31.05
324 | Naraharbati Mini Piped water Supply Scheme (SM/13662) | SM/13662 | 38.96 | 60 | NEW | 61 | WO no issued | 75 | 09/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 29.33 | 29.33
325 | Dwariapur Mini Piped Water Supply Scheme (SM/13553) | SM/13553 | 40.17 | 73 | NEW | 61 | WO no issued | 76 | 04/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 30.51 | 30.51
326 | Sikil Beldiha Mini Piped Water Supply Scheme (SM/13661) | SM/13661 | 39.43 | 65 | NEW | 61 | WO no issued | 76 | 09/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 29.78 | 29.78
327 | Bara Kumursa mini pipe water supply scheme (SM/13592) | SM/13592 | 40.14 | 63 | NEW | 61 | WO no issued | 76 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 30.47 | 30.47
328 | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK (SM/13344) | SM/13344 | 235.69 | 511 | AUGMENTATION | 61 | WO no issued | 37 | 29/09/2022 | 30/06/2024 | 26/04/2024 | 14/02/2023 | 87.42 | 66.49
329 | Purba Chakla Mini Piped Water Supply Scheme (SM/13666) | SM/13666 | 40.33 | 75 | NEW | 61 | WO no issued | 76 | 09/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 30.66 | 30.66
330 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT (SM/11584) | SM/11584 | 940.95 | 1692 | NEW | 62 | WO no issued | 77 | 22/07/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 728.6 | 728.6
331 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE (SM/11468) | SM/11468 | 709.16 | 2800 | AUGMENTATION | 62 | WO no issued | 56 | 12/07/2022 | 31/05/2024 | 26/04/2024 | 19/05/2022 | 395.53 | 395.53
332 | Chak mamrej mini pipe water supply scheme (SM/13590) | SM/13590 | 42.75 | 88 | NEW | 62 | WO no issued | 76 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 32.46 | 32.46
333 | Rautara Mini Piped Water Supply Scheme (SM/13667) | SM/13667 | 43.31 | 94 | NEW | 62 | WO no issued | 66 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 28.41 | 28.41
334 | Barul mini pipe water supply scheme (SM/13548) | SM/13548 | 41.13 | 74 | NEW | 62 | WO no issued | 75 | 04/11/2022 | 30/06/2024 | 26/04/2024 |  | 30.98 | 30.98
335 | Shyampur Mini Piped Water Supply Scheme (SM/13421) | SM/13421 | 42.22 | 92 | NEW | 62 | WO no issued | 77 | 02/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 32.5 | 32.5
336 | Belun Mini Piped Water Supply Scheme (SM/13552) | SM/13552 | 41.57 | 85 | NEW | 62 | WO no issued | 77 | 04/11/2022 | 30/06/2024 | 26/04/2024 | 01/11/2022 | 31.86 | 31.86
337 | Adra mini pipe water supply scheme (SM/13589) | SM/13589 | 43.03 | 91 | NEW | 62 | WO no issued | 77 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 33.28 | 33.28
338 | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly (SM/18102) | SM/18102 | 45.54 | 96 | NEW | 62 | WO no issued | 78 | 27/03/2023 | 30/06/2024 | 26/04/2024 | 12/05/2023 | 35.37 | 34.41
339 | Surjyapur Mini Piped Water Supply Scheme (SM/13594) | SM/13594 | 41.97 | 79 | NEW | 62 | WO no issued | 77 | 09/11/2022 | 30/06/2024 | 26/04/2024 |  | 32.25 | 32.25
340 | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/16763) | SM/16763 | 240.53 | 541 | NEW | 64 | WO no issued | 43 | 13/03/2023 | 30/04/2024 | 26/04/2024 | 23/03/2023 | 103.5 | 91.41
341 | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK (SM/13346) | SM/13346 | 214.65 | 1868 | AUGMENTATION | 66 | WO no issued | 62 | 29/09/2022 | 30/06/2024 | 12/04/2024 | 23/08/2022 | 132.43 | 132.43
342 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE (SM/11462) | SM/11462 | 765.32 | 2600 | AUGMENTATION | 67 | WO no issued | 55 | 12/07/2022 | 30/09/2024 | 26/04/2024 | 22/08/2022 | 419.03 | 376.47
343 | PANRRA PIPED WATER SUPPLY SCHEME (SM/11292) | SM/11292 | 987.53 | 2998 | NEW | 67 | WO no issued | 28 | 28/06/2022 | 30/04/2024 | 26/04/2024 | 29/09/2022 | 272.25 | 272.25
344 | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/14122) | SM/14122 | 329.66 | 983 | NEW | 72 | WO no issued | 63 | 02/01/2023 | 30/04/2024 | 26/04/2024 | 08/02/2023 | 206.3 | 201.59
345 | RETROFITTING FOR BANDIPUR WS SCHEME (SM/16648) | SM/16648 | 99.14 | 1550 | RETROFITTING | 73 | WO no issued | 32 | 14/03/2023 | 30/06/2024 | 26/04/2024 | 20/04/2023 | 31.61 | 31.61
346 | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly (SM/15247) | SM/15247 | 797.78 | 1796 | NEW | 74 | WO no issued | 38 | 07/02/2023 | 31/07/2024 | 26/04/2024 | 22/02/2023 | 306.49 | 243.51
347 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME (SM/11924) | SM/11924 | 748.82 | 2217 | AUGMENTATION | 74 | WO no issued | 55 | 22/08/2022 | 30/06/2024 | 26/04/2024 | 21/02/2022 | 415.49 | 404.81
348 | Ghosha Mini Piped Water Supply Scheme (SM/13595) | SM/13595 | 41.94 | 92 | NEW | 75 | WO no issued | 1 | 09/11/2022 | 30/06/2024 | 19/02/2024 | 01/11/2022 | 0.57 | 0.57
349 | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT (SM/13414) | SM/13414 | 737.21 | 1759 | NEW | 78 | WO no issued | 55 | 02/11/2022 | 31/05/2024 | 26/04/2024 | 09/02/2023 | 407.37 | 387.34
350 | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly (SM/13501) | SM/13501 | 377.67 | 606 | NEW | 78 | WO no issued | 77 | 02/11/2022 | 31/05/2024 | 26/04/2024 | 14/02/2023 | 290.59 | 290.59
351 | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. (SM/11465) | SM/11465 | 307.35 | 1770 | AUGMENTATION | 79 | WO no issued | 63 | 12/07/2022 | 30/06/2024 | 26/04/2024 | 14/07/2022 | 192.16 | 188.31
352 | Ramnagar Piped Water Supply Scheme. (SM/16757) | SM/16757 | 755.39 | 2549 | NEW | 80 | WO no issued | 65 | 13/03/2023 | 30/06/2024 | 12/04/2024 | 22/05/2023 | 487.4 | 466.06
353 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE (SM/11461) | SM/11461 | 329.51 | 883 | AUGMENTATION | 80 | WO no issued | 73 | 12/07/2022 | 30/06/2024 | 24/01/2024 | 12/11/2021 | 239.22 | 239.22
354 | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI (SM/09984) | SM/09984 | 1334.97 | 4914 | AUGMENTATION | 82 | WO no issued | 83 | 16/12/2021 | 30/06/2024 | 12/04/2024 | 07/07/2022 | 1106.33 | 1102.19
355 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. (SM/09690) | SM/09690 | 350.38 | 1615 | AUGMENTATION | 83 | WO no issued | 80 | 25/11/2021 | 30/06/2024 | 26/04/2024 | 18/02/2022 | 281.62 | 281.62
356 | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/15243) | SM/15243 | 482.37 | 1459 | AUGMENTATION | 83 | WO no issued | 48 | 07/02/2023 | 30/06/2024 | 19/03/2024 | 14/02/2023 | 231.79 | 231.79
357 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE (SM/11464) | SM/11464 | 369.78 | 1500 | AUGMENTATION | 83 | WO no issued | 41 | 12/07/2022 | 31/08/2024 | 05/03/2024 | 31/08/2022 | 152.9 | 152.9
358 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN (SM/11867) | SM/11867 | 446.85 | 1870 | AUGMENTATION | 84 | WO no issued | 74 | 17/08/2022 | 30/06/2024 | 19/02/2024 | 12/07/2022 | 331.8 | 331.8
359 | NAITA PIPED WATER SUPPLY SCHEME (SM/11291) | SM/11291 | 817.35 | 2196 | NEW | 85 | WO no issued | 48 | 28/06/2022 | 30/04/2024 | 12/04/2024 | 29/09/2022 | 394.91 | 394.91
360 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. (SM/10341) | SM/10341 | 1037.36 | 0 | AUGMENTATION | 85 | WO no issued | 65 | 14/03/2022 | 30/09/2024 | 26/04/2024 | 19/05/2022 | 678.97 | 678.43
361 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE (SM/11467) | SM/11467 | 552.74 | 2350 | AUGMENTATION | 86 | WO no issued | 67 | 12/07/2022 | 30/06/2024 | 26/04/2024 | 30/08/2022 | 372.64 | 357.62
362 | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME (SM/11969) | SM/11969 | 1096.03 | 4827 | AUGMENTATION | 86 | WO no issued | 52 | 29/08/2022 | 30/06/2024 | 19/02/2024 | 24/06/2020 | 574.85 | 574.27
363 | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur (SM/11167) | SM/11167 | 494.57 | 1843 | AUGMENTATION | 88 | WO no issued | 41 | 02/06/2022 | 30/06/2024 | 12/04/2024 | 17/02/2022 | 204.21 | 199.51
364 | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK (SM/12254) | SM/12254 | 608.75 | 2763 | NEW | 89 | WO no issued | 6 | 07/09/2022 | 30/04/2024 | 02/04/2024 | 30/12/2022 | 33.5 | 20.27
365 | Augmentation of Chanparai Water Supply Scheme (SM/10467) | SM/10467 | 414.46 | 1711 | AUGMENTATION | 89 | WO no issued | 48 | 13/04/2022 | 30/06/2024 | 19/02/2024 | 17/02/2022 | 198.91 | 198.91
366 | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR (SM/09791) | SM/09791 | 885.42 | 2698 | AUGMENTATION | 89 | WO no issued | 67 | 30/11/2021 | 30/06/2024 | 19/02/2024 | 01/11/2021 | 595.12 | 594.85
367 | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK (SM/15901) | SM/15901 | 219.96 | 0 | AUGMENTATION | 89 | WO no issued | 35 | 25/02/2023 | 30/06/2024 | 26/04/2024 | 20/04/2023 | 76.91 | 76.91
368 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. (SM/10338) | SM/10338 | 1306.66 | 10123 | AUGMENTATION | 90 | WO no issued | 42 | 14/03/2022 | 30/04/2024 | 02/04/2024 | 17/03/2022 | 545.83 | 499.57
369 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II (SM/09695) | SM/09695 | 854.05 | 3469 | AUGMENTATION | 90 | WO no issued | 72 | 25/11/2021 | 30/06/2024 | 26/04/2024 | 21/02/2022 | 614.58 | 609.45
370 | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL (SM/09982) | SM/09982 | 1481.84 | 5180 | AUGMENTATION | 90 | WO no issued | 72 | 16/12/2021 | 30/06/2024 | 12/04/2024 | 31/08/2022 | 1068.55 | 1068.55
371 | Augmentation of Salepur-Duttapur Water Supply Scheme (SM/10023) | SM/10023 | 1460.01 | 4593 | AUGMENTATION | 91 | WO no issued | 72 | 05/01/2022 | 30/06/2024 | 05/03/2024 | 13/04/2022 | 1047.64 | 1047.64
372 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. (SM/09698) | SM/09698 | 620.51 | 2088 | AUGMENTATION | 91 | WO no issued | 42 | 25/11/2021 | 31/07/2024 | 19/03/2024 | 31/12/2021 | 258.63 | 258.63
373 | Augmentation of Polba Water Supply Scheme (SM/10468) | SM/10468 | 963.64 | 4025 | AUGMENTATION | 91 | WO no issued | 80 | 13/04/2022 | 30/04/2024 | 02/04/2024 | 24/08/2022 | 773.08 | 755.07
374 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. (SM/10339) | SM/10339 | 1352.9 | 5839 | AUGMENTATION | 91 | WO no issued | 34 | 14/03/2022 | 30/06/2024 | 19/02/2024 | 24/06/2020 | 466.05 | 466.05
375 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. (SM/09694) | SM/09694 | 772.01 | 4298 | AUGMENTATION | 92 | WO no issued | 71 | 25/11/2021 | 30/04/2024 | 02/04/2024 | 18/02/2022 | 546.96 | 526.04
376 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR (SM/11868) | SM/11868 | 837.42 | 2962 | AUGMENTATION | 92 | WO no issued | 52 | 17/08/2022 | 30/04/2024 | 02/04/2024 | 16/12/2022 | 431.62 | 431.62
377 | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR (SM/10022) | SM/10022 | 2250.51 | 7976 | AUGMENTATION | 92 | WO no issued | 70 | 05/01/2022 | 30/04/2024 | 02/04/2024 | 31/08/2022 | 1576.99 | 1576.99
378 | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA (SM/09983) | SM/09983 | 1263.17 | 4500 | AUGMENTATION | 93 | WO no issued | 69 | 16/12/2021 | 30/04/2024 | 02/04/2024 | 24/03/2022 | 872.02 | 872.02
379 | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME (SM/10451) | SM/10451 | 989.36 | 3308 | AUGMENTATION | 93 | WO no issued | 42 | 12/04/2022 | 30/06/2024 | 24/01/2024 | 27/01/2022 | 411.2 | 381.52
380 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali (SM/11166) | SM/11166 | 895.83 | 3961 | AUGMENTATION | 94 | WO no issued | 67 | 02/06/2022 | 30/04/2024 | 02/04/2024 | 31/03/2022 | 598.33 | 592.25
381 | Augmentation of Champadanga Water Supply Scheme (SM/10005) | SM/10005 | 1532.55 | 6374 | AUGMENTATION | 94 | WO no issued | 64 | 20/12/2021 | 30/04/2024 | 02/04/2024 | 20/04/2022 | 980.73 | 975.69
382 | Bilaspur Piped Water Supply Scheme. (SM/09825) | SM/09825 | 2255.49 | 8919 | NEW | 94 | WO no issued | 47 | 02/12/2021 | 30/04/2024 | 02/04/2024 | 06/09/2021 | 1058.21 | 1054.59
383 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. (SM/09691) | SM/09691 | 541.55 | 2605 | AUGMENTATION | 95 | WO no issued | 57 | 25/11/2021 | 30/09/2024 | 16/04/2024 | 31/12/2021 | 309.84 | 309.84
384 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme (SM/07149) | SM/07149 | 77.24 | 1107 | RETROFITTING | 95 | WO no issued | 78 | 01/12/2020 | 31/05/2024 | 02/04/2024 | 07/04/2022 | 60 | 60
385 | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. (SM/09423) | SM/09423 | 43.82 | 3352 | AUGMENTATION | 95 | WO no issued | 73 | 17/11/2021 | 30/06/2024 | 19/02/2024 | 22/03/2022 | 32.02 | 26.65
386 | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte (SM/10357) | SM/10357 | 777.8 | 2878 | NEW | 95 | WO no issued | 38 | 16/03/2022 | 31/07/2024 | 16/04/2024 | 13/09/2022 | 299.37 | 299.37
387 | Chandanpur Piped Water Supply Scheme. (SM/08995) | SM/08995 | 486.65 | 1105 | NEW | 95 | WO no issued | 75 | 29/10/2021 | 30/06/2024 | 19/02/2024 | 13/04/2022 | 365.36 | 366.92
388 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. (SM/09790) | SM/09790 | 508.53 | 2619 | AUGMENTATION | 95 | WO no issued | 47 | 30/11/2021 | 31/07/2024 | 05/03/2024 | 30/11/2021 | 240.69 | 240.69
389 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. (SM/10340) | SM/10340 | 1822.88 | 9147 | AUGMENTATION | 95 | WO no issued | 59 | 14/03/2022 | 30/09/2024 | 02/04/2024 | 25/11/2021 | 1077.87 | 1056.96
390 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II (SM/09688) | SM/09688 | 278.45 | 1324 | AUGMENTATION | 95 | WO no issued | 90 | 25/11/2021 | 30/06/2024 | 19/02/2024 | 31/12/2021 | 250.68 | 250.68
391 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. (SM/09693) | SM/09693 | 615.63 | 3192 | AUGMENTATION | 95 | WO no issued | 80 | 25/11/2021 | 31/07/2024 | 16/04/2024 | 31/12/2021 | 493.38 | 492.16
392 | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR (SM/10004) | SM/10004 | 1553.96 | 5595 | AUGMENTATION | 95 | WO no issued | 50 | 20/12/2021 | 30/04/2024 | 02/04/2024 | 14/12/2021 | 781.03 | 647.38
393 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME (SM/11990) | SM/11990 | 376.63 | 5823 | RETROFITTING | 95 | WO no issued | 49 | 01/09/2022 | 31/07/2024 | 05/03/2024 | 16/12/2022 | 182.84 | 182.84
394 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME (SM/12001) | SM/12001 | 88.46 | 1365 | RETROFITTING | 95 | WO no issued | 67 | 01/09/2022 | 30/06/2024 | 19/03/2024 | 16/01/2023 | 59.53 | 59.53
395 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME (SM/12015) | SM/12015 | 163.75 | 2620 | RETROFITTING | 97 | WO no issued | 72 | 01/09/2022 | 31/08/2024 | 05/03/2024 | 29/04/2022 | 117.86 | 117.86
396 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. (SM/09692) | SM/09692 | 444.24 | 2553 | AUGMENTATION | 97 | WO no issued | 67 | 25/11/2021 | 30/09/2024 | 16/04/2024 | 31/12/2021 | 296.77 | 296.77
397 | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE (SM/13353) | SM/13353 | 186.31 | 2936 | RETROFITTING | 98 | WO no issued | 53 | 19/10/2022 | 30/04/2024 | 02/04/2024 | 16/12/2022 | 99.35 | 99.35
398 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. (SM/09689) | SM/09689 | 333.93 | 1738 | AUGMENTATION | 98 | WO no issued | 62 | 25/11/2021 | 30/04/2024 | 02/04/2024 | 27/10/2021 | 205.48 | 205.45
399 | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) (SM/06763) | SM/06763 | 99.47 | 1342 | RETROFITTING | 98 | WO no issued | 61 | 18/09/2020 | 30/04/2024 | 02/04/2024 | 26/04/2023 | 60.55 | 60.55
400 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme (SM/06993) | SM/06993 | 79.51 | 1259 | RETROFITTING | 98 | WO no issued | 35 | 11/11/2020 | 30/04/2024 | 02/04/2024 | 17/12/2020 | 27.88 | 27.88
401 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09776) | SM/09776 | 130.24 | 2181 | RETROFITTING | 98 | WO no issued | 54 | 30/11/2021 | 30/04/2024 | 02/04/2024 | 21/09/2022 | 70.61 | 70.61
402 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme (SM/06759) | SM/06759 | 40.46 | 511 | RETROFITTING | 99 | WO no issued | 96 | 18/09/2020 | 31/05/2024 | 05/03/2024 | 24/11/2020 | 39 | 39
403 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio (SM/06994) | SM/06994 | 68.52 | 2096 | RETROFITTING | 99 | WO no issued | 99 | 11/11/2020 | 31/05/2024 | 05/03/2024 | 15/02/2022 | 68 | 68
404 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme (SM/06990) | SM/06990 | 80.57 | 2215 | RETROFITTING | 99 | WO no issued | 99 | 11/11/2020 | 31/05/2024 | 05/03/2024 | 17/12/2020 | 80.02 | 80.02
405 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme (SM/07460) | SM/07460 | 145.28 | 2391 | RETROFITTING | 100 | WO no issued | 84 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 121.56 | 113.76
406 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. (SM/07956) | SM/07956 | 203.01 | 3727 | RETROFITTING | 100 | WO no issued | 83 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 167.94 | 165.92
407 | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme (SM/06767) | SM/06767 | 99.51 | 1190 | RETROFITTING | 100 | WO no issued | 95 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 24/11/2020 | 94.22 | 63.65
408 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. (SM/07536) | SM/07536 | 81.79 | 1270 | RETROFITTING | 100 | WO no issued | 92 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 75.25 | 74.43
409 | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. (SM/09207) | SM/09207 | 35.42 | 0 | AUGMENTATION | 100 | WO no issued | 88 | 30/10/2021 | 30/06/2023 | 12/06/2023 | 03/02/2022 | 31 | 31
410 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME (SM/09067) | SM/09067 | 131.23 | 2144 | RETROFITTING | 100 | WO no issued | 40 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 27/10/2021 | 52.39 | 52.39
411 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme (SM/06989) | SM/06989 | 57.3 | 2215 | RETROFITTING | 100 | WO no issued | 36 | 11/11/2020 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 20.6 | 20.6
412 | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. (SM/11001) | SM/11001 | 128.04 | 2289 | RETROFITTING | 100 | WO no issued | 47 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 07/07/2022 | 59.87 | 59.87
413 | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. (SM/11006) | SM/11006 | 77.49 | 1224 | RETROFITTING | 100 | WO no issued | 6 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 13/04/2022 | 4.69 | 4.69
414 | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK (SM/13677) | SM/13677 | 295.58 | 222 | AUGMENTATION | 100 | WO no issued | 44 | 29/09/2022 | 31/03/2024 | 12/06/2023 | 10/03/2022 | 129.21 | 129.21
415 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME (SM/11999) | SM/11999 | 218.68 | 3492 | RETROFITTING | 100 | WO no issued | 34 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 29/04/2022 | 73.68 | 73.68
416 | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. (SM/13356) | SM/13356 | 103.91 | 1600 | RETROFITTING | 100 | WO no issued | 48 | 19/10/2022 | 30/06/2023 | 12/06/2023 | 23/08/2022 | 50.28 | 50.28
417 | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) (SM/06755) | SM/06755 | 99.95 | 1522 | RETROFITTING | 100 | WO no issued | 100 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 24/11/2020 | 99.95 | 99.95
418 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. (SM/07945) | SM/07945 | 74.37 | 1203 | RETROFITTING | 100 | WO no issued | 96 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 07/04/2022 | 71.05 | 71.05
419 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. (SM/07951) | SM/07951 | 99.86 | 4320 | RETROFITTING | 100 | WO no issued | 97 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 96.94 | 96.94
420 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) (SM/06760) | SM/06760 | 43.92 | 1263 | RETROFITTING | 100 | WO no issued | 31 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 27/04/2022 | 13.77 | 13.77
421 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme (SM/06762) | SM/06762 | 87.72 | 1187 | RETROFITTING | 100 | WO no issued | 67 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 04/01/2022 | 58.51 | 58.51
422 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. (SM/07537) | SM/07537 | 95.57 | 1515 | RETROFITTING | 100 | WO no issued | 90 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 85.55 | 85.55
423 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. (SM/07538) | SM/07538 | 32.62 | 502 | RETROFITTING | 100 | WO no issued | 67 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 21.83 | 21.83
424 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. (SM/08743) | SM/08743 | 147.07 | 2754 | RETROFITTING | 100 | WO no issued | 49 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 71.63 | 57.8
425 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. (SM/08737) | SM/08737 | 163.87 | 2836 | RETROFITTING | 100 | WO no issued | 41 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 03/06/2022 | 66.97 | 66.97
426 | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme (SM/09066) | SM/09066 | 97.91 | 1625 | RETROFITTING | 100 | WO no issued | 75 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 16/10/2020 | 73.21 | 64.39
427 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME (SM/10131) | SM/10131 | 83.52 | 1061 | RETROFITTING | 100 | WO no issued | 62 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 52.06 | 52.06
428 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09775) | SM/09775 | 234.97 | 4182 | RETROFITTING | 100 | WO no issued | 64 | 30/11/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 150.43 | 150.43
429 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME (SM/11005) | SM/11005 | 270.62 | 4206 | RETROFITTING | 100 | WO no issued | 85 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 23/06/2022 | 231.07 | 231.07
430 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME (SM/11997) | SM/11997 | 213.94 | 3456 | RETROFITTING | 100 | WO no issued | 34 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 04/01/2022 | 73.26 | 73.26
431 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. (SM/07952) | SM/07952 | 212.07 | 3320 | RETROFITTING | 100 | WO no issued | 97 | 21/01/2021 |  | 12/06/2023 | 29/06/2021 | 205.83 | 205.83
432 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. (SM/07438) | SM/07438 | 272.67 | 2082 | RETROFITTING | 100 | WO no issued | 0 | 30/12/2020 | 31/12/2023 | 12/06/2023 | 14/12/2021 | 0.08 | 0.08
433 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09772) | SM/09772 | 337.05 | 5146 | RETROFITTING | 100 | WO no issued | 85 | 30/11/2021 | 30/06/2023 | 12/06/2023 | 13/09/2021 | 285.98 | 285.06
434 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. (SM/07443) | SM/07443 | 115.31 | 1951 | RETROFITTING | 100 | WO no issued | 87 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 25/08/2022 | 99.89 | 99.89
435 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme (SM/06988) | SM/06988 | 75.19 | 1189 | RETROFITTING | 100 | WO no issued | 0 | 11/11/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 0 | 0
436 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme (SM/06991) | SM/06991 | 83.37 | 1287 | RETROFITTING | 100 | WO no issued | 97 | 11/11/2020 | 30/06/2023 | 12/06/2023 | 02/02/2021 | 80.94 | 80.94
437 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme (SM/07461) | SM/07461 | 111.14 | 1814 | RETROFITTING | 100 | WO no issued | 86 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 02/11/2021 | 95.18 | 90.79
438 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. (SM/07949) | SM/07949 | 99.58 | 2534 | RETROFITTING | 100 | WO no issued | 92 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 19/01/2022 | 91.39 | 91.38
439 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. (SM/07953) | SM/07953 | 78.24 | 2299 | RETROFITTING | 100 | WO no issued | 85 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 05/01/2022 | 66.19 | 66.04
440 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. (SM/07957) | SM/07957 | 163.57 | 2936 | RETROFITTING | 100 | WO no issued | 59 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 95.91 | 84.06
441 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. (SM/07542) | SM/07542 | 95.57 | 1488 | RETROFITTING | 100 | WO no issued | 76 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 72.98 | 69.44
442 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09774) | SM/09774 | 166.04 | 2826 | RETROFITTING | 100 | WO no issued | 3 | 30/11/2021 | 30/06/2023 | 12/06/2023 | 23/08/2022 | 5.29 | 5.29
443 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME (SM/11002) | SM/11002 | 371.11 | 4068 | RETROFITTING | 100 | WO no issued | 39 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 07/04/2022 | 145.59 | 145.59
444 | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION (SM/11004) | SM/11004 | 244.08 | 4123 | RETROFITTING | 100 | WO no issued | 49 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 16/12/2022 | 119.71 | 119.71
445 | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly (SM/12228) | SM/12228 | 741.99 | 3126 | AUGMENTATION | 100 | WO no issued | 28 | 07/09/2022 | 31/03/2024 | 12/06/2023 | 31/05/2022 | 207.83 | 137.27
446 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) (SM/12002) | SM/12002 | 217.2 | 3383 | RETROFITTING | 100 | WO no issued | 45 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 29/04/2022 | 97.18 | 97.18
447 | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. (SM/13347) | SM/13347 | 517.76 | 1798 | NEW | 100 | WO no issued | 16 | 29/09/2022 | 31/03/2024 | 12/06/2023 | 18/02/2022 | 85.19 | 85.19
448 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. (SM/08740) | SM/08740 | 230.84 | 4056 | RETROFITTING | 100 | WO no issued | 94 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 29/06/2021 | 218.11 | 200.4
449 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. (SM/07958) | SM/07958 | 119.68 | 2122 | RETROFITTING | 100 | WO no issued | 91 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 109.14 | 109.14
450 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME (SM/11998) | SM/11998 | 140.93 | 2241 | RETROFITTING | 100 | WO no issued | 18 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 04/01/2022 | 25.49 | 25.49
451 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. (SM/09072) | SM/09072 | 42.14 | 3956 | RETROFITTING | 100 | WO no issued | 76 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 13/09/2021 | 31.91 | 31.91
452 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme (SM/07463) | SM/07463 | 130.74 | 2123 | RETROFITTING | 100 | WO no issued | 97 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 27/10/2021 | 126.93 | 126.93
453 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. (SM/07436) | SM/07436 | 288.46 | 5421 | RETROFITTING | 100 | WO no issued | 93 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 25/02/2021 | 267.57 | 266.59
454 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme (SM/07462) | SM/07462 | 184.15 | 3233 | RETROFITTING | 100 | WO no issued | 42 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 20/12/2021 | 76.79 | 76.69
455 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. (SM/07944) | SM/07944 | 48.29 | 745 | RETROFITTING | 100 | WO no issued | 69 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 26/02/2021 | 33.53 | 33.53
456 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. (SM/08744) | SM/08744 | 80.9 | 1135 | RETROFITTING | 100 | WO no issued | 75 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 15/12/2021 | 60.95 | 48.27
457 | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. (SM/09604) | SM/09604 | 43.94 | 0 | AUGMENTATION | 100 | WO no issued | 33 | 23/11/2021 | 31/03/2024 | 12/06/2023 | 15/07/2022 | 14.42 | 14.42
458 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte (SM/10132) | SM/10132 | 126.17 | 2111 | RETROFITTING | 100 | WO no issued | 64 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 80.4 | 80.4
459 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. (SM/10133) | SM/10133 | 99.96 | 1702 | RETROFITTING | 100 | WO no issued | 97 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 97.04 | 97.04
460 | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. (SM/11003) | SM/11003 | 51.92 | 800 | RETROFITTING | 100 | WO no issued | 28 | 01/06/2022 | 31/03/2024 | 12/06/2023 | 11/07/2022 | 14.75 | 14.75
461 | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR (SM/12370) | SM/12370 | 1268.51 | 4599 | AUGMENTATION | 100 | WO no issued | 63 | 13/09/2022 | 31/03/2024 | 12/06/2023 | 31/05/2022 | 797.76 | 766.36
462 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME (SM/07541) | SM/07541 | 56.68 | 893 | RETROFITTING | 100 | WO no issued | 92 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 01/12/2021 | 52.12 | 52.12
463 | Augmentation of Gobindapur Water Supply Scheme (SM/16351) | SM/16351 | 331.19 | 225 | AUGMENTATION | 100 | WO no issued | 36 | 28/02/2023 | 31/03/2024 | 12/06/2023 | 04/01/2022 | 120.6 | 120.6
464 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. (SM/07437) | SM/07437 | 278.22 | 4968 | RETROFITTING | 100 | WO no issued | 61 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 168.52 | 167.12
465 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. (SM/07442) | SM/07442 | 123.87 | 1961 | RETROFITTING | 100 | WO no issued | 92 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 23/12/2021 | 114.13 | 114.13
466 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. (SM/07946) | SM/07946 | 97.35 | 3076 | RETROFITTING | 100 | WO no issued | 97 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 94.29 | 94.06
467 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. (SM/07948) | SM/07948 | 98.47 | 4046 | RETROFITTING | 100 | WO no issued | 97 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 26/02/2021 | 95.26 | 95.07
468 | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) (SM/06766) | SM/06766 | 93.4 | 3814 | RETROFITTING | 100 | WO no issued | 97 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 90.67 | 90.67
469 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte (SM/10134) | SM/10134 | 88.95 | 1386 | RETROFITTING | 100 | WO no issued | 65 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 57.55 | 57.55
470 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) (SM/06757) | SM/06757 | 99.73 | 3925 | RETROFITTING | 100 | WO no issued | 8 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 7.58 | 7.58
471 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME (SM/12000) | SM/12000 | 148.75 | 2300 | RETROFITTING | 100 | WO no issued | 4 | 01/09/2022 | 31/10/2022 | 12/06/2023 | 26/02/2021 | 6.46 | 6.46
472 | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE (SM/12882) | SM/12882 | 409.9 | 6938 | RETROFITTING | 100 | WO no issued | 20 | 23/09/2022 | 30/06/2023 | 12/06/2023 | 07/11/2022 | 80 | 71.65
473 | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. (SM/13357) | SM/13357 | 38.98 | 600 | RETROFITTING | 100 | WO no issued | 81 | 19/10/2022 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 31.74 | 31.74
474 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. (SM/08741) | SM/08741 | 214.13 | 3700 | RETROFITTING | 100 | WO no issued | 70 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 149.19 | 128.74
475 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. (SM/07947) | SM/07947 | 83.61 | 2555 | RETROFITTING | 100 | WO no issued | 69 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 01/12/2021 | 57.4 | 57.4
476 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS (SM/06758) | SM/06758 | 74.68 | 984 | RETROFITTING | 100 | WO no issued | 39 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 19/01/2022 | 29.43 | 29.43
477 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. (SM/07441) | SM/07441 | 128.62 | 2048 | RETROFITTING | 100 | WO no issued | 98 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 126.21 | 106.45
478 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under (SM/07150) | SM/07150 | 56.16 | 803 | RETROFITTING | 100 | WO no issued | 18 | 01/12/2020 | 30/06/2023 | 12/06/2023 | 02/02/2021 | 10.01 | 10.01
479 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. (SM/07950) | SM/07950 | 99.37 | 2559 | RETROFITTING | 100 | WO no issued | 100 | 21/01/2021 |  | 12/06/2023 | 03/02/2021 | 99.34 | 99.34
480 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY (SM/07954) | SM/07954 | 247.47 | 4296 | RETROFITTING | 100 | WO no issued | 65 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 161.75 | 161.15
481 | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem (SM/06765) | SM/06765 | 89.54 | 1089 | RETROFITTING | 100 | WO no issued | 82 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 24/11/2020 | 73.35 | 61.38
482 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. (SM/07543) | SM/07543 | 86.15 | 1348 | RETROFITTING | 100 | WO no issued | 54 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 03/06/2022 | 46.56 | 46.56
483 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. (SM/08739) | SM/08739 | 197.26 | 2939 | RETROFITTING | 100 | WO no issued | 52 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 101.84 | 101.84
484 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. (SM/07535) | SM/07535 | 57.39 | 883 | RETROFITTING | 100 | WO no issued | 97 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 55.68 | 55.68
485 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09777) | SM/09777 | 131.1 | 2123 | RETROFITTING | 100 | WO no issued | 68 | 30/11/2021 | 30/06/2023 | 12/06/2023 | 01/12/2021 | 89.15 | 89.15
486 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) (SM/12012) | SM/12012 | 47.77 | 735 | RETROFITTING | 100 | WO no issued | 95 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 21/09/2022 | 45.38 | 45.38
487 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. (SM/07955) | SM/07955 | 166.55 | 2860 | RETROFITTING | 100 | WO no issued | 85 | 21/01/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 141.44 | 141.43
488 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. (SM/07540) | SM/07540 | 66.84 | 1068 | RETROFITTING | 100 | WO no issued | 90 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 60.48 | 55.44
489 | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS (SM/06754) | SM/06754 | 73.81 | 1236 | RETROFITTING | 100 | WO no issued | 93 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 68.4 | 68.4
490 | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) (SM/06761) | SM/06761 | 83.39 | 1065 | RETROFITTING | 100 | WO no issued | 98 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 17/12/2020 | 82 | 82
491 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme (SM/06764) | SM/06764 | 70.7 | 976 | RETROFITTING | 100 | WO no issued | 89 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 24/11/2020 | 62.91 | 62.91
492 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. (SM/09068) | SM/09068 | 80.21 | 1287 | RETROFITTING | 100 | WO no issued | 19 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 14.88 | 14.88
493 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. (SM/09069) | SM/09069 | 95.2 | 1553 | RETROFITTING | 100 | WO no issued | 28 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 03/02/2021 | 26.71 | 26.71
494 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. (SM/09071) | SM/09071 | 50.04 | 800 | RETROFITTING | 100 | WO no issued | 51 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 13/09/2021 | 25.3 | 23.45
495 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. (SM/09773) | SM/09773 | 95.96 | 1577 | RETROFITTING | 100 | WO no issued | 50 | 30/11/2021 | 30/06/2023 | 12/06/2023 | 26/02/2021 | 48.21 | 46.28
496 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. (SM/07440) | SM/07440 | 230.1 | 3860 | RETROFITTING | 100 | WO no issued | 83 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 15/02/2021 | 190.94 | 190.94
497 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. (SM/08742) | SM/08742 | 176.84 | 3011 | RETROFITTING | 100 | WO no issued | 93 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 164.46 | 164.46
498 | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) (SM/06756) | SM/06756 | 99.92 | 1286 | RETROFITTING | 100 | WO no issued | 97 | 18/09/2020 | 30/06/2023 | 12/06/2023 | 03/02/2021 | 97 | 97
499 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. (SM/07439) | SM/07439 | 157.36 | 2472 | RETROFITTING | 100 | WO no issued | 93 | 30/12/2020 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 146.44 | 146.44
500 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme (SM/06992) | SM/06992 | 98.98 | 1695 | RETROFITTING | 100 | WO no issued | 76 | 11/11/2020 | 30/06/2023 | 12/06/2023 | 26/02/2021 | 75.4 | 75.4
501 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik (SM/07151) | SM/07151 | 69.81 | 2096 | RETROFITTING | 100 | WO no issued | 81 | 01/12/2020 | 30/06/2023 | 12/06/2023 | 12/11/2021 | 56.87 | 53.95
502 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. (SM/07534) | SM/07534 | 72.23 | 1112 | RETROFITTING | 100 | WO no issued | 94 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 30/11/2021 | 67.59 | 67.59
503 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. (SM/08738) | SM/08738 | 134.58 | 2305 | RETROFITTING | 100 | WO no issued | 93 | 09/09/2021 | 30/06/2023 | 12/06/2023 | 06/05/2021 | 125.65 | 120.65
504 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. (SM/09070) | SM/09070 | 136.85 | 3870 | RETROFITTING | 100 | WO no issued | 97 | 28/10/2021 | 30/06/2023 | 12/06/2023 | 13/09/2021 | 132.86 | 89.14
505 | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme (SM/10136) | SM/10136 | 104.32 | 1694 | RETROFITTING | 100 | WO no issued | 47 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 48.85 | 48.85
506 | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. (SM/11225) | SM/11225 | 271.91 | 4588 | RETROFITTING | 100 | WO no issued | 16 | 16/06/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 44.6 | 44.6
507 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME (SM/12013) | SM/12013 | 199.03 | 3502 | RETROFITTING | 100 | WO no issued | 15 | 01/09/2022 | 30/06/2023 | 12/06/2023 | 14/12/2021 | 30.15 | 30.15
508 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. (SM/07539) | SM/07539 | 35.08 | 540 | RETROFITTING | 100 | WO no issued | 100 | 31/12/2020 | 30/06/2023 | 12/06/2023 | 10/05/2021 | 35.08 | 35.08
509 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme (SM/06987) | SM/06987 | 92.65 | 1435 | RETROFITTING | 100 | WO no issued | 63 | 11/11/2020 | 30/06/2023 | 12/06/2023 | 03/02/2021 | 58.57 | 58.57
510 | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte (SM/10135) | SM/10135 | 137.19 | 2163 | RETROFITTING | 100 | WO no issued | 62 | 08/02/2022 | 30/06/2023 | 12/06/2023 | 10/03/2022 | 84.42 | 84.42
511 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME (SM/11165) | SM/11165 | 264.04 | 5831 | RETROFITTING | 100 | WO no issued | 53 | 02/06/2022 | 31/03/2024 | 12/06/2023 | 07/04/2022 | 140.04 | 132.01
Total |  |  | 246018.47 | 980490 | [8 empty] | 74069.24 | 69950.4