## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | () |  | 0 | 2610 |  | 0 | 0% Physical | INF |  |  |  | 01/02/2022 | 179.15 | 179.15
2 | () |  | 0 | 2273 |  | 0 | 0% Physical | INF |  |  |  | 30/12/2021 | 202.38 | 206.84
3 | () |  | 0 | 813 |  | 0 | 0% Physical | INF |  |  |  | 23/09/2021 | 67.46 | 67.46
4 | () |  | 0 | 2721 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 224.67 | 224.67
5 | () |  | 0 | 2274 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 191.11 | 191.11
6 | () |  | 0 | 3143 |  | 0 | 0% Physical | INF |  |  |  | 03/03/2022 | 181.52 | 181.52
7 | () |  | 0 | 2017 |  | 0 | 0% Physical | INF |  |  |  | 22/02/2022 | 110.87 | 110.87
8 | () |  | 0 | 569 |  | 0 | 0% Physical | INF |  |  |  | 28/02/2022 | 37.2 | 37.2
9 | () |  | 0 | 2435 |  | 0 | 0% Physical | INF |  |  |  | 30/12/2021 | 110.55 | 109.28
10 | () |  | 0 | 7078 |  | 0 | 0% Physical | INF |  |  |  | 09/02/2022 | 232.46 | 232.46
11 | () |  | 0 | 59 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.69 | 23.69
12 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.06
13 | () |  | 0 | 82 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.23 | 32.23
14 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.94 | 31.94
15 | () |  | 0 | 65 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.93 | 0.93
16 | () |  | 0 | 591 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.21 | 31.21
17 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.34 | 32.34
18 | () |  | 0 | 56 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
19 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.08 | 27.08
20 | () |  | 0 | 54 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.81 | 21.81
21 | () |  | 0 | 42 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
22 | () |  | 0 | 35 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 18.55 | 18.55
23 | () |  | 0 | 26 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 17.08 | 17.08
24 | () |  | 0 | 24 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 14.62 | 14.62
25 | () |  | 0 | 48 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
26 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
27 | () |  | 0 | 53 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 18.02 | 18.02
28 | () |  | 0 | 88 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
29 | () |  | 0 | 57 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
30 | () |  | 0 | 88 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.12 | 10
31 | () |  | 0 | 68 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
32 | () |  | 0 | 90 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
33 | () |  | 0 | 347 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.43 | 28.43
34 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.81 | 28.81
35 | () |  | 0 | 29 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.84 | 31.84
36 | () |  | 0 | 20 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.92 | 25.92
37 | () |  | 0 | 77 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.72 | 29.72
38 | () |  | 0 | 46 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
39 | () |  | 0 | 175 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.12 | 29.12
40 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.58 | 26.58
41 | () |  | 0 | 607 |  | 0 | 0% Physical | INF |  |  |  | 28/01/2022 | 157.15 | 157.15
42 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.34 | 24.34
43 | () |  | 0 | 35 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.23 | 22.23
44 | () |  | 0 | 407 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.66 | 31.66
45 | () |  | 0 | 717 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
46 | () |  | 0 | 2525 |  | 0 | 0% Physical | INF |  |  |  | 23/09/2021 | 440.62 | 445.61
47 | () |  | 0 | 46 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
48 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.02 | 28.02
49 | () |  | 0 | 399 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.29 | 28.29
50 | () |  | 0 | 265 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.08 | 27.08
51 | () |  | 0 | 259 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.33 | 26.33
52 | () |  | 0 | 496 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.58 | 26.58
53 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.66 | 10.66
54 | () |  | 0 | 658 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.51 | 19.51
55 | () |  | 0 | 950 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 222.6 | 222.6
56 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
57 | () |  | 0 | 22 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.44 | 28.44
58 | () |  | 0 | 313 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
59 | () |  | 0 | 345 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.93 | 15.93
60 | () |  | 0 | 812 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 93.86 | 93.86
61 | () |  | 0 | 1325 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 252.74 | 252.74
62 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.84 | 25.84
63 | () |  | 0 | 517 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
64 | () |  | 0 | 29 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
65 | () |  | 0 | 1004 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 63.64 | 63.64
66 | () |  | 0 | 1297 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 248.92 | 248.92
67 | () |  | 0 | 1528 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 295.01 | 295.01
68 | () |  | 0 | 3789 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 205.99 | 205.99
69 | () |  | 0 | 2744 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 645.02 | 645.02
70 | () |  | 0 | 1575 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 238.73 | 238.73
71 | () |  | 0 | 3768 |  | 0 | 0% Physical | INF |  |  |  | 22/05/2023 | 185.49 | 188
72 | () |  | 0 | 434 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 19.23 | 15.79
73 | () |  | 0 | 2234 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 368.98 | 368.98
74 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
75 | () |  | 0 | 900 |  | 0 | 0% Physical | INF |  |  |  | 02/06/2023 | 46.9 | 46.9
76 | () |  | 0 | 2145 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 215.66 | 215.66
77 | () |  | 0 | 290 |  | 0 | 0% Physical | INF |  |  |  | 19/05/2023 | 209.19 | 209.19
78 | () |  | 0 | 710 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 81.05 | 81.05
79 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 30.86 | 30.86
80 | () |  | 0 | 340 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 134.36 | 141.02
81 | () |  | 0 | 320 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 53.89 | 53.89
82 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 24/08/2023 | 47.98 | 47.98
83 | () |  | 0 | 165 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 93.16 | 97.17
84 | () |  | 0 | 653 |  | 0 | 0% Physical | INF |  |  |  | 06/11/2023 | 121.31 | 121.31
85 | () |  | 0 | 1025 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 88.68 | 88.68
86 | () |  | 0 | 250 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 76.36 | 76.36
87 | () |  | 0 | 9820 |  | 0 | 0% Physical | INF |  |  |  | 11/11/2022 | 663.03 | 663.03
88 | () |  | 0 | 2315 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 370.19 | 370.19
89 | () |  | 0 | 100 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 71.37 | 75.37
90 | () |  | 0 | 172 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 70.56 | 68.98
91 | () |  | 0 | 77 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 100.03 | 100.03
92 | () |  | 0 | 225 |  | 0 | 0% Physical | INF |  |  |  | 25/05/2023 | 72.96 | 72.96
93 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 01/09/2023 | 17.21 | 17.21
94 | () |  | 0 | 6421 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 805.12 | 805.12
95 | () |  | 0 | 3211 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 359.85 | 359.85
96 | () |  | 0 | 290 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
97 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.41 | 24.23
98 | () |  | 0 | 68 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.65 | 10.65
99 | () |  | 0 | 2052 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 275.49 | 275.49
100 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.12 | 29.12
101 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
102 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.08 | 29.08
103 | () |  | 0 | 3357 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 135.34 | 135.34
104 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 11.12 | 11
105 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
106 | () |  | 0 | 216 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
107 | () |  | 0 | 590 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 175.91 | 175.91
108 | () |  | 0 | 1030 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 49.07 | 48.88
109 | () |  | 0 | 1663 |  | 0 | 0% Physical | INF |  |  |  | 22/02/2022 | 73.22 | 73.22
110 | () |  | 0 | 2280 |  | 0 | 0% Physical | INF |  |  |  | 25/03/2022 | 188.16 | 188.16
111 | () |  | 0 | 2872 |  | 0 | 0% Physical | INF |  |  |  | 24/06/2020 | 136.13 | 136.13
112 | () |  | 0 | 1047 |  | 0 | 0% Physical | INF |  |  |  | 18/02/2022 | 42.97 | 42.97
113 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2021 | 236.93 | 236.93
114 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 10/08/2021 | 1554.8 | 1554.8
115 | () |  | 0 | 41 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
116 | () |  | 0 | 70 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
117 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
118 | () |  | 0 | 56 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.07 | 24.07
119 | () |  | 0 | 198 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.65 | 10.65
120 | () |  | 0 | 404 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.39 | 25.39
121 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.83 | 31.83
122 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.18 | 29.18
123 | () |  | 0 | 48 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
124 | () |  | 0 | 38 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
125 | () |  | 0 | 31 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 16.12 | 16.12
126 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
127 | () |  | 0 | 49 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
128 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
129 | () |  | 0 | 64 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.12 | 10
130 | () |  | 0 | 51 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.5 | 25.5
131 | () |  | 0 | 90 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.72 | 29.72
132 | () |  | 0 | 157 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.37 | 0.37
133 | () |  | 0 | 52 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
134 | () |  | 0 | 53 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.77 | 20.77
135 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.12 | 24.12
136 | () |  | 0 | 42 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.15 | 28.15
137 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.15 | 28.15
138 | () |  | 0 | 8274 |  | 0 | 0% Physical | NAN |  |  |  | 24/07/2023 | 0 | 0
139 | () |  | 0 | 39 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.71 | 21.71
140 | () |  | 0 | 1224 |  | 0 | 0% Physical | INF |  |  |  | 12/05/2022 | 238.38 | 241.23
141 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
142 | () |  | 0 | 29 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.41 | 25.41
143 | () |  | 0 | 183 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.44 | 20.44
144 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
145 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
146 | () |  | 0 | 383 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.66 | 10.66
147 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.66 | 10.66
148 | () |  | 0 | 74 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.71 | 32.71
149 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
150 | () |  | 0 | 1199 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 461.46 | 461.46
151 | () |  | 0 | 271 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.01 | 20.01
152 | () |  | 0 | 33 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.82 | 31.82
153 | () |  | 0 | 90 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30.66 | 30.66
154 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.25 | 22.25
155 | () |  | 0 | 77 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.57 | 28.57
156 | () |  | 0 | 136 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
157 | () |  | 0 | 43 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.33 | 24.33
158 | () |  | 0 | 2578 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 216.58 | 216.58
159 | () |  | 0 | 1428 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 130.71 | 130.71
160 | () |  | 0 | 896 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 196.81 | 196.81
161 | () |  | 0 | 2116 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 243.93 | 243.93
162 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
163 | () |  | 0 | 2771 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 420.03 | 420.03
164 | () |  | 0 | 1381 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 125.03 | 125.03
165 | () |  | 0 | 431 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 205.09 | 205.09
166 | () |  | 0 | 770 |  | 0 | 0% Physical | INF |  |  |  | 22/05/2023 | 118.89 | 118.89
167 | () |  | 0 | 820 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 216.32 | 216.32
168 | () |  | 0 | 1086 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 36.98 | 36.98
169 | () |  | 0 | 470 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 101.81 | 101.81
170 | () |  | 0 | 230 |  | 0 | 0% Physical | INF |  |  |  | 25/05/2023 | 48.98 | 48.98
171 | () |  | 0 | 780 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 188.39 | 188.39
172 | () |  | 0 | 4059 |  | 0 | 0% Physical | INF |  |  |  | 28/08/2023 | 494.79 | 494.79
173 | () |  | 0 | 120 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 31.92 | 31.92
174 | () |  | 0 | 250 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 64.52 | 66.12
175 | () |  | 0 | 210 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 13.63 | 16.91
176 | () |  | 0 | 603 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 267.94 | 267.94
177 | () |  | 0 | 1400 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 91.8 | 91.8
178 | () |  | 0 | 2847 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 597.13 | 597.13
179 | () |  | 0 | 410 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 98.13 | 98.13
180 | () |  | 0 | 1508 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 153.84 | 153.84
181 | () |  | 0 | 480 |  | 0 | 0% Physical | INF |  |  |  | 01/09/2023 | 24.64 | 24.64
182 | () |  | 0 | 340 |  | 0 | 0% Physical | INF |  |  |  | 18/04/2023 | 109.65 | 109.65
183 | () |  | 0 | 210 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 120.82 | 120.82
184 | () |  | 0 | 300 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 147.73 | 147.73
185 | () |  | 0 | 190 |  | 0 | 0% Physical | INF |  |  |  | 12/09/2023 | 102.95 | 104.76
186 | () |  | 0 | 325 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 135.04 | 135.04
187 | () |  | 0 | 310 |  | 0 | 0% Physical | INF |  |  |  | 09/10/2023 | 61.41 | 63.52
188 | () |  | 0 | 1645 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 339.66 | 339.66
189 | () |  | 0 | 2764 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 282.51 | 282.51
190 | () |  | 0 | 35 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
191 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.3 | 13.3
192 | () |  | 0 | 1984 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 130.51 | 130.51
193 | () |  | 0 | 3575 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 397.9 | 397.9
194 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.15 | 28.15
195 | () |  | 0 | 63 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
196 | () |  | 0 | 88 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
197 | () |  | 0 | 21 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
198 | () |  | 0 | 867 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 34.66 | 34.66
199 | () |  | 0 | 54 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.23 | 27.23
200 | () |  | 0 | 3761 |  | 0 | 0% Physical | INF |  |  |  | 31/08/2022 | 117.82 | 117.82
201 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 17/12/2021 | 167.89 | 167.89
202 | () |  | 0 | 977 |  | 0 | 0% Physical | INF |  |  |  | 01/12/2021 | 71.21 | 71.21
203 | () |  | 0 | 2080 |  | 0 | 0% Physical | INF |  |  |  | 21/04/2022 | 111.61 | 111.61
204 | () |  | 0 | 2822 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 208.52 | 208.52
205 | () |  | 0 | 2522 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 152.22 | 152.22
206 | () |  | 0 | 1796 |  | 0 | 0% Physical | INF |  |  |  | 12/02/2021 | 285.63 | 285.63
207 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 28/02/2022 | 42.98 | 42.98
208 | () |  | 0 | 2304 |  | 0 | 0% Physical | INF |  |  |  | 24/02/2022 | 166.58 | 166.58
209 | () |  | 0 | 2000 |  | 0 | 0% Physical | INF |  |  |  | 04/03/2022 | 131.54 | 131.54
210 | () |  | 0 | 3005 |  | 0 | 0% Physical | INF |  |  |  | 04/03/2022 | 247.54 | 247.54
211 | () |  | 0 | 15728 |  | 0 | 0% Physical | INF |  |  |  | 24/06/2020 | 1144.6 | 1144.6
212 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.25 | 29.25
213 | () |  | 0 | 86 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.23 | 22.23
214 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.93 | 26.93
215 | () |  | 0 | 804 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.18 | 33.18
216 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.53 | 10.53
217 | () |  | 0 | 300 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22 | 22
218 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
219 | () |  | 0 | 44 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
220 | () |  | 0 | 55 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
221 | () |  | 0 | 27 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.92 | 23.92
222 | () |  | 0 | 79 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
223 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
224 | () |  | 0 | 52 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
225 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.69 | 21.69
226 | () |  | 0 | 223 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.08 | 31.08
227 | () |  | 0 | 48 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 16.54 | 16.54
228 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
229 | () |  | 0 | 215 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
230 | () |  | 0 | 167 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.12 | 28.12
231 | () |  | 0 | 35 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.62 | 29.62
232 | () |  | 0 | 400 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
233 | () |  | 0 | 59 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
234 | () |  | 0 | 1434 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 429.8 | 429.8
235 | () |  | 0 | 410 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 122.26 | 122.26
236 | () |  | 0 | 217 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
237 | () |  | 0 | 299 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.59 | 19.59
238 | () |  | 0 | 67 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
239 | () |  | 0 | 698 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 97.72 | 97.72
240 | () |  | 0 | 418 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.13 | 0.13
241 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
242 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.66 | 32.66
243 | () |  | 0 | 150 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.71 | 31.71
244 | () |  | 0 | 39 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
245 | () |  | 0 | 249 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 16.85 | 16.85
246 | () |  | 0 | 82 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
247 | () |  | 0 | 604 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
248 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
249 | () |  | 0 | 54 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.92 | 23.92
250 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.08 | 27.08
251 | () |  | 0 | 1025 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 90.47 | 90.47
252 | () |  | 0 | 1905 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 208.89 | 208.89
253 | () |  | 0 | 2105 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 332.23 | 332.23
254 | () |  | 0 | 3405 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 425.61 | 425.61
255 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
256 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
257 | () |  | 0 | 3339 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 318.01 | 318.01
258 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
259 | () |  | 0 | 743 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 119.32 | 117.99
260 | () |  | 0 | 4478 |  | 0 | 0% Physical | INF |  |  |  | 10/02/2022 | 357.45 | 358
261 | () |  | 0 | 3815 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2023 | 172.41 | 172.41
262 | () |  | 0 | 416 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 71.27 | 71.27
263 | () |  | 0 | 230 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 97.42 | 97.42
264 | () |  | 0 | 480 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 128.29 | 129.2
265 | () |  | 0 | 245 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 106.12 | 106.12
266 | () |  | 0 | 420 |  | 0 | 0% Physical | INF |  |  |  | 23/03/2023 | 143.4 | 143.4
267 | () |  | 0 | 630 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 120.14 | 120.14
268 | () |  | 0 | 1968 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 436.96 | 436.96
269 | () |  | 0 | 2517 |  | 0 | 0% Physical | INF |  |  |  | 12/09/2023 | 185.58 | 185.58
270 | () |  | 0 | 945 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 257.37 | 257.37
271 | () |  | 0 | 318 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 142.4 | 142.4
272 | () |  | 0 | 804 |  | 0 | 0% Physical | INF |  |  |  | 01/09/2023 | 181.6 | 181.6
273 | () |  | 0 | 480 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 131.65 | 131.65
274 | () |  | 0 | 215 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 89.35 | 89.35
275 | () |  | 0 | 850 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 248.73 | 248.73
276 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 21/09/2023 | 102.8 | 104.52
277 | () |  | 0 | 3614 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 356.88 | 356.88
278 | () |  | 0 | 2413 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 277.93 | 277.93
279 | () |  | 0 | 3297 |  | 0 | 0% Physical | INF |  |  |  | 01/06/2023 | 175.23 | 175.23
280 | () |  | 0 | 104 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
281 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 01/03/2024 | 0 | 0
282 | () |  | 0 | 350 |  | 0 | 0% Physical | INF |  |  |  | 31/10/2023 | 11.02 | 11.02
283 | () |  | 0 | 21 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.15 | 28.15
284 | () |  | 0 | 49 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.38 | 13.38
285 | () |  | 0 | 3303 |  | 0 | 0% Physical | INF |  |  |  | 11/09/2023 | 475.57 | 475.57
286 | () |  | 0 | 312 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.44 | 28.44
287 | () |  | 0 | 740 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30 | 30
288 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.28 | 20.28
289 | () |  | 0 | 71 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
290 | () |  | 0 | 20 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
291 | () |  | 0 | 2976 |  | 0 | 0% Physical | INF |  |  |  | 03/10/2023 | 90.43 | 90.43
292 | () |  | 0 | 3377 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 16.3 | 16.3
293 | () |  | 0 | 3000 |  | 0 | 0% Physical | INF |  |  |  | 25/07/2023 | 637.67 | 627.16
294 | () |  | 0 | 888 |  | 0 | 0% Physical | INF |  |  |  | 23/09/2021 | 72.23 | 72.23
295 | () |  | 0 | 2480 |  | 0 | 0% Physical | INF |  |  |  | 25/03/2022 | 172.84 | 172.84
296 | () |  | 0 | 89 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
297 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.78 | 32.78
298 | () |  | 0 | 225 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 34.24 | 34.24
299 | () |  | 0 | 161 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.24 | 32.24
300 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.96 | 32.96
301 | () |  | 0 | 92 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27 | 27
302 | () |  | 0 | 63 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.07 | 25.07
303 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.08 | 27.08
304 | () |  | 0 | 47 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
305 | () |  | 0 | 67 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
306 | () |  | 0 | 384 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.59 | 31.59
307 | () |  | 0 | 651 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
308 | () |  | 0 | 68 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.62 | 33.62
309 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
310 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.02 | 28.02
311 | () |  | 0 | 61 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
312 | () |  | 0 | 89 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
313 | () |  | 0 | 80 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
314 | () |  | 0 | 67 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.62 | 29.62
315 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
316 | () |  | 0 | 451 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.01 | 27.01
317 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
318 | () |  | 0 | 86 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
319 | () |  | 0 | 68 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.62 | 29.62
320 | () |  | 0 | 244 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28 | 28
321 | () |  | 0 | 157 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.12 | 27.12
322 | () |  | 0 | 317 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.13 | 28.13
323 | () |  | 0 | 285 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
324 | () |  | 0 | 28 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.99 | 26.99
325 | () |  | 0 | 39 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
326 | () |  | 0 | 81 |  | 0 | 0% Physical | INF |  |  |  | 06/04/2023 | 27.19 | 27.19
327 | () |  | 0 | 3612 |  | 0 | 0% Physical | INF |  |  |  | 01/02/2022 | 375.97 | 388.94
328 | () |  | 0 | 730 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.5 | 25.5
329 | () |  | 0 | 33 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
330 | () |  | 0 | 24 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.34 | 24.34
331 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
332 | () |  | 0 | 658 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 207.54 | 207.54
333 | () |  | 0 | 74 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.55 | 28.55
334 | () |  | 0 | 21 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
335 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0.12
336 | () |  | 0 | 358 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.66 | 10.66
337 | () |  | 0 | 33 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
338 | () |  | 0 | 336 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.9 | 21.9
339 | () |  | 0 | 182 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.08 | 27.08
340 | () |  | 0 | 1946 |  | 0 | 0% Physical | INF |  |  |  | 23/02/2023 | 122.09 | 122.09
341 | () |  | 0 | 188 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
342 | () |  | 0 | 633 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.01 | 20.01
343 | () |  | 0 | 80 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.66 | 32.66
344 | () |  | 0 | 24 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
345 | () |  | 0 | 73 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
346 | () |  | 0 | 74 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
347 | () |  | 0 | 52 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
348 | () |  | 0 | 2127 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 258.41 | 258.41
349 | () |  | 0 | 130 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30 | 30
350 | () |  | 0 | 181 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
351 | () |  | 0 | 79 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
352 | () |  | 0 | 1800 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 180.51 | 180.51
353 | () |  | 0 | 654 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 154.05 | 154.05
354 | () |  | 0 | 2927 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 703.85 | 703.85
355 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
356 | () |  | 0 | 1851 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 277.79 | 277.79
357 | () |  | 0 | 4060 |  | 0 | 0% Physical | INF |  |  |  | 10/05/2022 | 491.19 | 499.14
358 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
359 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
360 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/08/2023 | 0 | 0
361 | () |  | 0 | 1080 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 227.02 | 227.02
362 | () |  | 0 | 110 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 38.02 | 38.02
363 | () |  | 0 | 80 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 84.39 | 86.99
364 | () |  | 0 | 2156 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 180.65 | 180.65
365 | () |  | 0 | 302 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 77.43 | 77.43
366 | () |  | 0 | 245 |  | 0 | 0% Physical | INF |  |  |  | 11/05/2023 | 62.6 | 62.6
367 | () |  | 0 | 251 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 90.06 | 90.06
368 | () |  | 0 | 985 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 147.31 | 139.32
369 | () |  | 0 | 586 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 93.54 | 93.54
370 | () |  | 0 | 780 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 189.41 | 189.41
371 | () |  | 0 | 312 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2023 | 147.19 | 146.61
372 | () |  | 0 | 222 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 42.15 | 44.6
373 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 88.45 | 90.93
374 | () |  | 0 | 3576 |  | 0 | 0% Physical | INF |  |  |  | 23/02/2023 | 262.11 | 262.11
375 | () |  | 0 | 65 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
376 | () |  | 0 | 282 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.71 | 19.71
377 | () |  | 0 | 62 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
378 | () |  | 0 | 32 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.92 | 27.92
379 | () |  | 0 | 51 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.05 | 27.05
380 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 36.71 | 36.71
381 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.92 | 15.92
382 | () |  | 0 | 89 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.69 | 23.69
383 | () |  | 0 | 91 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.3 | 21.3
384 | () |  | 0 | 299 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
385 | () |  | 0 | 31 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.77 | 20.77
386 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
387 | () |  | 0 | 66 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
388 | () |  | 0 | 2682 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 165.19 | 165.19
389 | () |  | 0 | 2933 |  | 0 | 0% Physical | INF |  |  |  | 01/02/2022 | 108.25 | 108.25
390 | () |  | 0 | 1015 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 58.63 | 58.63
391 | () |  | 0 | 943 |  | 0 | 0% Physical | NAN |  |  |  | 22/11/2021 | 0 | 0
392 | () |  | 0 | 793 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 60.62 | 60.62
393 | () |  | 0 | 2933 |  | 0 | 0% Physical | INF |  |  |  | 03/01/2022 | 261.53 | 259.7
394 | () |  | 0 | 2356 |  | 0 | 0% Physical | INF |  |  |  | 29/10/2021 | 116.6 | 116.38
395 | () |  | 0 | 703 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 70.93 | 70.93
396 | () |  | 0 | 882 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 70.24 | 70.24
397 | () |  | 0 | 2270 |  | 0 | 0% Physical | INF |  |  |  | 21/04/2022 | 37.92 | 37.92
398 | () |  | 0 | 2653 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 184.48 | 184.48
399 | () |  | 0 | 714 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 87.4 | 87.4
400 | () |  | 0 | 81 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 18.95 | 18.95
401 | () |  | 0 | 28 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
402 | () |  | 0 | 82 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
403 | () |  | 0 | 52 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
404 | () |  | 0 | 194 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.97 | 26.97
405 | () |  | 0 | 51 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.93 | 26.93
406 | () |  | 0 | 123 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.12 | 25.12
407 | () |  | 0 | 197 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.5 | 25.5
408 | () |  | 0 | 65 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.07 | 26.07
409 | () |  | 0 | 156 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.53 | 10.53
410 | () |  | 0 | 55 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.16 | 13.16
411 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.33 | 26.33
412 | () |  | 0 | 49 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.8 | 15.8
413 | () |  | 0 | 41 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
414 | () |  | 0 | 21 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.28 | 13.28
415 | () |  | 0 | 46 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
416 | () |  | 0 | 33 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
417 | () |  | 0 | 73 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
418 | () |  | 0 | 33 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
419 | () |  | 0 | 72 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
420 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.88 | 25.88
421 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
422 | () |  | 0 | 83 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
423 | () |  | 0 | 94 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.78 | 32.78
424 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
425 | () |  | 0 | 151 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.53 | 10.53
426 | () |  | 0 | 72 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
427 | () |  | 0 | 25 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.71 | 21.71
428 | () |  | 0 | 69 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.4 | 13.4
429 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
430 | () |  | 0 | 42 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.02 | 28.02
431 | () |  | 0 | 35 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.23 | 22.23
432 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31 | 31
433 | () |  | 0 | 474 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.13 | 28.13
434 | () |  | 0 | 48 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.36 | 24.36
435 | () |  | 0 | 214 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30.52 | 30.52
436 | () |  | 0 | 49 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
437 | () |  | 0 | 661 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.94 | 29.94
438 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
439 | () |  | 0 | 1001 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 89.35 | 89.35
440 | () |  | 0 | 2353 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 409.76 | 409.76
441 | () |  | 0 | 272 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.12 | 28.12
442 | () |  | 0 | 21 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.23 | 22.23
443 | () |  | 0 | 3930 |  | 0 | 0% Physical | INF |  |  |  | 06/01/2022 | 784.38 | 784.38
444 | () |  | 0 | 53 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
445 | () |  | 0 | 332 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.13 | 0.13
446 | () |  | 0 | 52 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.31 | 31.31
447 | () |  | 0 | 90 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
448 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.54 | 32.54
449 | () |  | 0 | 71 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.44 | 28.44
450 | () |  | 0 | 158 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.24 | 19.12
451 | () |  | 0 | 262 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.96 | 21.96
452 | () |  | 0 | 91 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.13 | 20.13
453 | () |  | 0 | 1133 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 129.55 | 129.55
454 | () |  | 0 | 227 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
455 | () |  | 0 | 45 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.14 | 19.14
456 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
457 | () |  | 0 | 184 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 18.93 | 18.93
458 | () |  | 0 | 608 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 76.2 | 76.2
459 | () |  | 0 | 1936 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 168.44 | 168.44
460 | () |  | 0 | 2974 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 412.03 | 412.03
461 | () |  | 0 | 3461 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 422.43 | 422.43
462 | () |  | 0 | 1922 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 293.02 | 293.02
463 | () |  | 0 | 765 |  | 0 | 0% Physical | INF |  |  |  | 20/03/2023 | 89.09 | 89.09
464 | () |  | 0 | 540 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 159.68 | 159.68
465 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
466 | () |  | 0 | 176 |  | 0 | 0% Physical | INF |  |  |  | 09/10/2023 | 43.28 | 43.28
467 | () |  | 0 | 1106 |  | 0 | 0% Physical | INF |  |  |  | 22/05/2023 | 89.32 | 89.32
468 | () |  | 0 | 319 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 27.01 | 27.01
469 | () |  | 0 | 968 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 280.83 | 280.83
470 | () |  | 0 | 2105 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 316.28 | 316.28
471 | () |  | 0 | 1258 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 160.85 | 160.85
472 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 115.5 | 117.18
473 | () |  | 0 | 430 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 180.65 | 180.65
474 | () |  | 0 | 1295 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 226.92 | 226.92
475 | () |  | 0 | 757 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 33.85 | 33.85
476 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 23/03/2023 | 108.14 | 108.14
477 | () |  | 0 | 1539 |  | 0 | 0% Physical | INF |  |  |  | 24/04/2023 | 381.59 | 381.59
478 | () |  | 0 | 310 |  | 0 | 0% Physical | INF |  |  |  | 11/04/2023 | 101.03 | 101.03
479 | () |  | 0 | 275 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 63.33 | 63.33
480 | () |  | 0 | 950 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 231.45 | 231.45
481 | () |  | 0 | 520 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 134.24 | 134.24
482 | () |  | 0 | 143 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 138.31 | 139.87
483 | () |  | 0 | 1120 |  | 0 | 0% Physical | INF |  |  |  | 01/06/2023 | 331.93 | 331.93
484 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 49.07 | 50.16
485 | () |  | 0 | 1118 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 232.51 | 232.51
486 | () |  | 0 | 2785 |  | 0 | 0% Physical | INF |  |  |  | 01/02/2022 | 259.66 | 265.24
487 | () |  | 0 | 350 |  | 0 | 0% Physical | INF |  |  |  | 07/09/2022 | 45.23 | 45.23
488 | () |  | 0 | 390 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 184.95 | 184.95
489 | () |  | 0 | 245 |  | 0 | 0% Physical | INF |  |  |  | 01/09/2023 | 159.23 | 159.23
490 | () |  | 0 | 850 |  | 0 | 0% Physical | INF |  |  |  | 11/09/2023 | 27.32 | 27.32
491 | () |  | 0 | 141 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.12 | 27.12
492 | () |  | 0 | 94 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
493 | () |  | 0 | 2586 |  | 0 | 0% Physical | INF |  |  |  | 11/09/2023 | 442.83 | 442.83
494 | () |  | 0 | 55 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.45 | 25.45
495 | () |  | 0 | 67 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
496 | () |  | 0 | 99 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.65 | 10.65
497 | () |  | 0 | 61 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
498 | () |  | 0 | 3401 |  | 0 | 0% Physical | INF |  |  |  | 21/08/2023 | 599.18 | 599.18
499 | () |  | 0 | 500 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 109.45 | 109.45
500 | () |  | 0 | 3319 |  | 0 | 0% Physical | INF |  |  |  | 03/01/2022 | 171.75 | 171.75
501 | () |  | 0 | 3109 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 106.88 | 106.88
502 | () |  | 0 | 1257 |  | 0 | 0% Physical | INF |  |  |  | 13/12/2021 | 68.17 | 68.17
503 | () |  | 0 | 1657 |  | 0 | 0% Physical | INF |  |  |  | 10/05/2022 | 184.79 | 184.79
504 | () |  | 0 | 1650 |  | 0 | 0% Physical | INF |  |  |  | 10/05/2022 | 179.8 | 179.8
505 | () |  | 0 | 1927 |  | 0 | 0% Physical | INF |  |  |  | 09/02/2022 | 151.87 | 151.87
506 | () |  | 0 | 1564 |  | 0 | 0% Physical | INF |  |  |  | 11/03/2022 | 445.85 | 448.48
507 | () |  | 0 | 1759 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 36.18 | 36.18
508 | () |  | 0 | 25 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
509 | () |  | 0 | 91 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.16 | 13.16
510 | () |  | 0 | 53 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
511 | () |  | 0 | 358 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26 | 26
512 | () |  | 0 | 246 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.12 | 26.12
513 | () |  | 0 | 324 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24 | 24
514 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
515 | () |  | 0 | 92 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.71 | 31.71
516 | () |  | 0 | 86 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.81 | 21.81
517 | () |  | 0 | 28 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
518 | () |  | 0 | 28 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
519 | () |  | 0 | 355 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.7 | 33.7
520 | () |  | 0 | 91 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
521 | () |  | 0 | 77 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
522 | () |  | 0 | 310 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.47 | 29.47
523 | () |  | 0 | 66 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.91 | 15.91
524 | () |  | 0 | 84 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 18.95 | 18.95
525 | () |  | 0 | 65 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
526 | () |  | 0 | 451 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.18 | 29.18
527 | () |  | 0 | 62 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.12 | 29.12
528 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0.12
529 | () |  | 0 | 56 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.16 | 13.16
530 | () |  | 0 | 725 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.01 | 28.01
531 | () |  | 0 | 90 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.15 | 28.15
532 | () |  | 0 | 194 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.33 | 26.33
533 | () |  | 0 | 193 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.11 | 28.11
534 | () |  | 0 | 23 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.23 | 20.23
535 | () |  | 0 | 134 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.53 | 20.53
536 | () |  | 0 | 34 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.27 | 21.27
537 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.75 | 29.75
538 | () |  | 0 | 887 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.8 | 15.8
539 | () |  | 0 | 87 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.66 | 33.66
540 | () |  | 0 | 501 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
541 | () |  | 0 | 276 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
542 | () |  | 0 | 30 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
543 | () |  | 0 | 262 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.16 | 13.16
544 | () |  | 0 | 59 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.65 | 10.65
545 | () |  | 0 | 61 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
546 | () |  | 0 | 1259 |  | 0 | 0% Physical | INF |  |  |  | 06/01/2022 | 299.68 | 299.68
547 | () |  | 0 | 126 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.01 | 22.01
548 | () |  | 0 | 51 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
549 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.71 | 32.59
550 | () |  | 0 | 82 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.53 | 10.53
551 | () |  | 0 | 213 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
552 | () |  | 0 | 721 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 91.55 | 91.55
553 | () |  | 0 | 7983 |  | 0 | 0% Physical | INF |  |  |  | 25/04/2023 | 157.19 | 157.19
554 | () |  | 0 | 2331 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 242.41 | 242.41
555 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
556 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
557 | () |  | 0 | 2019 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 116.98 | 113.82
558 | () |  | 0 | 1828 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 157.89 | 157.89
559 | () |  | 0 | 100 |  | 0 | 0% Physical | INF |  |  |  | 11/04/2023 | 134.03 | 134.03
560 | () |  | 0 | 748 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 184.4 | 184.4
561 | () |  | 0 | 180 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 35.74 | 35.74
562 | () |  | 0 | 1459 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 85.63 | 85.63
563 | () |  | 0 | 1277 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 80.65 | 80.65
564 | () |  | 0 | 1153 |  | 0 | 0% Physical | INF |  |  |  | 26/10/2023 | 203.79 | 203.79
565 | () |  | 0 | 404 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 208.19 | 208.19
566 | () |  | 0 | 100 |  | 0 | 0% Physical | INF |  |  |  | 08/06/2023 | 94.63 | 89.55
567 | () |  | 0 | 265 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 112 | 112
568 | () |  | 0 | 270 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 178.64 | 178.64
569 | () |  | 0 | 474 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2023 | 87.4 | 87.4
570 | () |  | 0 | 448 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 90.96 | 90.96
571 | () |  | 0 | 564 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 152.99 | 152.99
572 | () |  | 0 | 305 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 668.36 | 669.16
573 | () |  | 0 | 520 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 151.22 | 151.22
574 | () |  | 0 | 367 |  | 0 | 0% Physical | INF |  |  |  | 08/02/2024 | 20.61 | 20.61
575 | () |  | 0 | 505 |  | 0 | 0% Physical | INF |  |  |  | 23/02/2023 | 272.29 | 272.29
576 | () |  | 0 | 3100 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 438.34 | 438.34
577 | () |  | 0 | 797 |  | 0 | 0% Physical | INF |  |  |  | 23/02/2023 | 218.44 | 218.44
578 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 04/10/2023 | 1257.7 | 1257.7
579 | () |  | 0 | 25 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.44 | 23.44
580 | () |  | 0 | 62 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.12 | 22.12
581 | () |  | 0 | 163 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22 | 22
582 | () |  | 0 | 565 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.62 | 26.62
583 | () |  | 0 | 96 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.71 | 31.71
584 | () |  | 0 | 32 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.99 | 26.99
585 | () |  | 0 | 46 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.99 | 24.99
586 | () |  | 0 | 80 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0.12
587 | () |  | 0 | 86 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.35 | 22.35
588 | () |  | 0 | 37 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
589 | () |  | 0 | 3991 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 48.23 | 48.23
590 | () |  | 0 | 2309 |  | 0 | 0% Physical | INF |  |  |  | 24/06/2020 | 140.7 | 140.7
591 | () |  | 0 | 589 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 65.01 | 64.99
592 | () |  | 0 | 2627 |  | 0 | 0% Physical | INF |  |  |  | 15/12/2021 | 169.21 | 169.21
593 | () |  | 0 | 2267 |  | 0 | 0% Physical | INF |  |  |  | 22/02/2022 | 140.24 | 140.24
594 | () |  | 0 | 1510 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 43.6 | 43.6
595 | () |  | 0 | 1422 |  | 0 | 0% Physical | INF |  |  |  | 03/03/2022 | 50.36 | 50.36
596 | () |  | 0 | 663 |  | 0 | 0% Physical | INF |  |  |  | 02/06/2023 | 80.67 | 80.67
597 | () |  | 0 | 5831 |  | 0 | 0% Physical | INF |  |  |  | 10/08/2021 | 1259.71 | 1259.71
598 | () |  | 0 | 3489 |  | 0 | 0% Physical | INF |  |  |  | 24/09/2021 | 706.98 | 706.98
599 | () |  | 0 | 67 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
600 | () |  | 0 | 40 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.44 | 28.44
601 | () |  | 0 | 315 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.62 | 27.62
602 | () |  | 0 | 620 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.55 | 28.55
603 | () |  | 0 | 135 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.25 | 32.25
604 | () |  | 0 | 156 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
605 | () |  | 0 | 1128 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22 | 22
606 | () |  | 0 | 441 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.09 | 28.09
607 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.16 | 13.16
608 | () |  | 0 | 64 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 18.95 | 18.95
609 | () |  | 0 | 44 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.03 | 22.03
610 | () |  | 0 | 628 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.71 | 21.71
611 | () |  | 0 | 46 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 16.96 | 16.96
612 | () |  | 0 | 225 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.14 | 32.14
613 | () |  | 0 | 85 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
614 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
615 | () |  | 0 | 77 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
616 | () |  | 0 | 59 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
617 | () |  | 0 | 70 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.12 | 0
618 | () |  | 0 | 925 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
619 | () |  | 0 | 44 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 17.08 | 17.08
620 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.23 | 27.23
621 | () |  | 0 | 88 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
622 | () |  | 0 | 92 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
623 | () |  | 0 | 128 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
624 | () |  | 0 | 63 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
625 | () |  | 0 | 238 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.12 | 28.12
626 | () |  | 0 | 242 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.12 | 28.12
627 | () |  | 0 | 159 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.12 | 27.12
628 | () |  | 0 | 293 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30 | 30
629 | () |  | 0 | 74 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.28 | 13.28
630 | () |  | 0 | 508 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.93 | 33.93
631 | () |  | 0 | 65 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
632 | () |  | 0 | 1109 |  | 0 | 0% Physical | INF |  |  |  | 14/11/2022 | 324.51 | 350.94
633 | () |  | 0 | 3690 |  | 0 | 0% Physical | INF |  |  |  | 13/04/2022 | 263.41 | 263.41
634 | () |  | 0 | 1358 |  | 0 | 0% Physical | INF |  |  |  | 27/09/2022 | 93.04 | 93.04
635 | () |  | 0 | 700 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.62 | 25.62
636 | () |  | 0 | 36 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
637 | () |  | 0 | 24 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.97 | 26.97
638 | () |  | 0 | 47 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
639 | () |  | 0 | 64 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
640 | () |  | 0 | 1423 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 331.02 | 331.02
641 | () |  | 0 | 746 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30.12 | 30.12
642 | () |  | 0 | 37 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
643 | () |  | 0 | 59 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.77 | 26.77
644 | () |  | 0 | 157 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.71 | 19.71
645 | () |  | 0 | 649 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.13 | 0.13
646 | () |  | 0 | 25 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.6 | 32.6
647 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.6 | 29.6
648 | () |  | 0 | 583 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 20.01 | 20.01
649 | () |  | 0 | 1479 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.17 | 23.17
650 | () |  | 0 | 446 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.11 | 0.11
651 | () |  | 0 | 157 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30 | 30
652 | () |  | 0 | 42 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.33 | 26.33
653 | () |  | 0 | 122 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 73.15 | 73.15
654 | () |  | 0 | 2305 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 56.36 | 56.36
655 | () |  | 0 | 713 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 194.76 | 194.76
656 | () |  | 0 | 1052 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 187.34 | 187.34
657 | () |  | 0 | 1670 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 284.14 | 284.14
658 | () |  | 0 | 2546 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 217.32 | 217.32
659 | () |  | 0 | 1981 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 147.01 | 147.01
660 | () |  | 0 | 475 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 96.79 | 96.79
661 | () |  | 0 | 350 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 33.05 | 33.05
662 | () |  | 0 | 730 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 77.18 | 77.18
663 | () |  | 0 | 478 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 197.41 | 197.41
664 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 172.06 | 172.06
665 | () |  | 0 | 403 |  | 0 | 0% Physical | INF |  |  |  | 22/05/2023 | 121.15 | 121.15
666 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 105.28 | 107.33
667 | () |  | 0 | 966 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 201.02 | 201.02
668 | () |  | 0 | 6 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 22.91 | 25.97
669 | () |  | 0 | 920 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 110.48 | 110.48
670 | () |  | 0 | 344 |  | 0 | 0% Physical | INF |  |  |  | 17/08/2023 | 112.48 | 112.48
671 | () |  | 0 | 150 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 94.8 | 94.8
672 | () |  | 0 | 128 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 187.24 | 187.24
673 | () |  | 0 | 480 |  | 0 | 0% Physical | INF |  |  |  | 20/03/2023 | 14.02 | 14.02
674 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 114.35 | 114.35
675 | () |  | 0 | 600 |  | 0 | 0% Physical | INF |  |  |  | 02/06/2023 | 106.05 | 106.05
676 | () |  | 0 | 1443 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 257.73 | 257.73
677 | () |  | 0 | 280 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 123.84 | 123.84
678 | () |  | 0 | 34 |  | 0 | 0% Physical | INF |  |  |  | 27/07/2023 | 98.33 | 101.29
679 | () |  | 0 | 281 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 105.98 | 105.98
680 | () |  | 0 | 360 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 168.64 | 166.09
681 | () |  | 0 | 840 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 192.17 | 192.17
682 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 81.74 | 83.91
683 | () |  | 0 | 680 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 174.4 | 174.4
684 | () |  | 0 | 254 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 110.74 | 110.74
685 | () |  | 0 | 490 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 108.18 | 108.18
686 | () |  | 0 | 205 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 148.91 | 148.91
687 | () |  | 0 | 180 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 35.6 | 35.6
688 | () |  | 0 | 350 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 69.2 | 69.2
689 | () |  | 0 | 62 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
690 | () |  | 0 | 100 |  | 0 | 0% Physical | INF |  |  |  | 31/10/2023 | 97.33 | 97.33
691 | () |  | 0 | 60 |  | 0 | 0% Physical | INF |  |  |  | 09/02/2024 | 2.47 | 2.47
692 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 09/02/2024 | 122.41 | 122.41
693 | () |  | 0 | 291 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30 | 30
694 | () |  | 0 | 0 |  | 0 | WO no issued | NAN |  |  |  |  | 0 | 0
695 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.23 | 27.23
696 | () |  | 0 | 25 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
697 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
698 | () |  | 0 | 1960 |  | 0 | 0% Physical | INF |  |  |  | 31/12/2021 | 94.67 | 94.67
699 | () |  | 0 | 3315 |  | 0 | 0% Physical | INF |  |  |  | 19/04/2022 | 289.24 | 279.97
700 | () |  | 0 | 949 |  | 0 | 0% Physical | INF |  |  |  | 29/11/2021 | 84.36 | 84.36
701 | () |  | 0 | 2442 |  | 0 | 0% Physical | INF |  |  |  | 13/11/2020 | 89.5 | 89.5
702 | () |  | 0 | 1926 |  | 0 | 0% Physical | INF |  |  |  | 03/03/2022 | 108.26 | 108.26
703 | () |  | 0 | 1119 |  | 0 | 0% Physical | INF |  |  |  | 23/09/2021 | 87.36 | 87.36
704 | () |  | 0 | 1461 |  | 0 | 0% Physical | INF |  |  |  | 03/03/2022 | 67.34 | 71.63
705 | () |  | 0 | 1806 |  | 0 | 0% Physical | INF |  |  |  | 19/04/2022 | 170.7 | 170.7
706 | () |  | 0 | 2536 |  | 0 | 0% Physical | INF |  |  |  | 22/02/2022 | 206.29 | 206.29
707 | () |  | 0 | 2339 |  | 0 | 0% Physical | INF |  |  |  | 10/05/2022 | 130.13 | 130.13
708 | () |  | 0 | 1713 |  | 0 | 0% Physical | INF |  |  |  | 03/03/2022 | 44.94 | 44.94
709 | () |  | 0 | 98 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.06 | 21.06
710 | () |  | 0 | 72 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.81 | 23.81
711 | () |  | 0 | 4030 |  | 0 | 0% Physical | INF |  |  |  | 05/01/2023 | 458.61 | 458.61
712 | () |  | 0 | 76 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.03 | 27.03
713 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 23.94 | 23.94
714 | () |  | 0 | 283 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 37.47 | 37.47
715 | () |  | 0 | 143 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 25.2 | 25.2
716 | () |  | 0 | 51 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
717 | () |  | 0 | 70 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
718 | () |  | 0 | 96 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
719 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.18 | 21.18
720 | () |  | 0 | 50 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.5 | 27.5
721 | () |  | 0 | 82 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 19.07 | 19.07
722 | () |  | 0 | 244 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.55 | 32.55
723 | () |  | 0 | 325 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 34.71 | 34.71
724 | () |  | 0 | 81 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
725 | () |  | 0 | 0 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 15.92 | 15.92
726 | () |  | 0 | 55 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
727 | () |  | 0 | 121 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.4 | 21.4
728 | () |  | 0 | 94 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
729 | () |  | 0 | 63 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
730 | () |  | 0 | 78 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.12 | 24.12
731 | () |  | 0 | 96 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 24.88 | 24.88
732 | () |  | 0 | 93 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.52 | 27.52
733 | () |  | 0 | 87 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.36 | 32.36
734 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.62 | 29.62
735 | () |  | 0 | 22 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.46 | 26.46
736 | () |  | 0 | 1107 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 247.12 | 247.12
737 | () |  | 0 | 1287 |  | 0 | 0% Physical | INF |  |  |  | 23/03/2022 | 225.72 | 225.72
738 | () |  | 0 | 748 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31 | 31
739 | () |  | 0 | 36 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.85 | 26.85
740 | () |  | 0 | 29 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.32 | 21.32
741 | () |  | 0 | 33 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.35 | 22.35
742 | () |  | 0 | 75 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 29.94 | 29.94
743 | () |  | 0 | 2340 |  | 0 | 0% Physical | INF |  |  |  | 04/05/2023 | 477.14 | 477.14
744 | () |  | 0 | 1742 |  | 0 | 0% Physical | INF |  |  |  | 21/02/2023 | 311.39 | 311.39
745 | () |  | 0 | 700 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 0.13 | 0.13
746 | () |  | 0 | 236 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 10.66 | 10.66
747 | () |  | 0 | 71 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.76 | 26.76
748 | () |  | 0 | 208 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.32 | 33.32
749 | () |  | 0 | 53 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 33.33 | 33.33
750 | () |  | 0 | 92 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 30.66 | 30.66
751 | () |  | 0 | 79 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.71 | 31.71
752 | () |  | 0 | 571 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 22.63 | 22.63
753 | () |  | 0 | 97 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 13.27 | 13.27
754 | () |  | 0 | 159 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 27.47 | 27.47
755 | () |  | 0 | 565 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 101.03 | 103.62
756 | () |  | 0 | 957 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 142.03 | 142.03
757 | () |  | 0 | 1951 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 107.85 | 107.85
758 | () |  | 0 | 1049 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 135.1 | 135.1
759 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 23/03/2023 | 0 | 0
760 | () |  | 0 | 1415 |  | 0 | 0% Physical | INF |  |  |  | 24/05/2022 | 115.12 | 115.12
761 | () |  | 0 | 3132 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 349.17 | 349.17
762 | () |  | 0 | 290 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 123.01 | 123.01
763 | () |  | 0 | 900 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 222.52 | 222.52
764 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
765 | () |  | 0 | 80 |  | 0 | 0% Physical | INF |  |  |  | 11/04/2023 | 79.8 | 79.8
766 | () |  | 0 | 718 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 87.14 | 87.14
767 | () |  | 0 | 180 |  | 0 | 0% Physical | INF |  |  |  | 01/08/2023 | 78.48 | 78.48
768 | () |  | 0 | 120 |  | 0 | 0% Physical | INF |  |  |  | 19/04/2023 | 80.86 | 83.8
769 | () |  | 0 | 544 |  | 0 | 0% Physical | INF |  |  |  | 14/08/2023 | 67.19 | 67.19
770 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
771 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 17/04/2023 | 0 | 0
772 | () |  | 0 | 400 |  | 0 | 0% Physical | INF |  |  |  | 30/03/2023 | 77.91 | 77.91
773 | () |  | 0 | 55 |  | 0 | 0% Physical | INF |  |  |  | 28/07/2023 | 89 | 89
774 | () |  | 0 | 700 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 34.49 | 34.49
775 | () |  | 0 | 3247 |  | 0 | 0% Physical | INF |  |  |  | 24/07/2023 | 141.42 | 141.42
776 | () |  | 0 | 538 |  | 0 | 0% Physical | INF |  |  |  | 19/07/2023 | 217.69 | 217.69
777 | () |  | 0 | 545 |  | 0 | 0% Physical | INF |  |  |  | 18/07/2023 | 153.05 | 153.05
778 | () |  | 0 | 260 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 76.64 | 76.64
779 | () |  | 0 | 320 |  | 0 | 0% Physical | INF |  |  |  | 28/03/2023 | 46.29 | 46.29
780 | () |  | 0 | 230 |  | 0 | 0% Physical | INF |  |  |  | 13/07/2023 | 251.91 | 254.45
781 | () |  | 0 | 310 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 53.87 | 53.87
782 | () |  | 0 | 2522 |  | 0 | 0% Physical | INF |  |  |  | 17/04/2023 | 736.71 | 736.71
783 | () |  | 0 | 310 |  | 0 | 0% Physical | INF |  |  |  | 17/03/2023 | 21.23 | 21.23
784 | () |  | 0 | 95 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 32.76 | 32.76
785 | () |  | 0 | 89 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 21.24 | 21.12
786 | () |  | 0 | 201 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.44 | 26.44
787 | () |  | 0 | 330 |  | 0 | 0% Physical | INF |  |  |  | 24/08/2023 | 78.42 | 78.42
788 | () |  | 0 | 72 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.57 | 26.57
789 | () |  | 0 | 20 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 31.59 | 31.59
790 | () |  | 0 | 377 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 26.33 | 26.33
791 | () |  | 0 | 89 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 28.05 | 28.05
792 | () |  | 0 | 186 |  | 0 | 0% Physical | NAN |  |  |  | 03/08/2022 | 0 | 0
793 | () |  | 0 | 46 |  | 0 | 0% Physical | INF |  |  |  | 03/08/2022 | 34.5 | 34.5
794 | () |  | 0 | 3432 |  | 0 | 0% Physical | INF |  |  |  | 13/04/2022 | 291.57 | 291.57
795 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 18/04/2022 | 0 | 0
796 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 26/09/2024 | 0 | 0
797 | () |  | 0 | 0 |  | 0 | WO no issued | NAN |  |  |  |  | 0 | 0
798 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 10/08/2020 | 0 | 0
799 | () |  | 0 | 0 |  | 0 | WO no issued | NAN |  |  |  |  | 0 | 0
800 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 10/01/2022 | 0 | 0
801 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 06/02/2024 | 0 | 0
802 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 21/12/2023 | 0 | 0
803 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 10/09/2024 | 0 | 0
804 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 08/06/2023 | 0 | 0
805 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 04/04/2023 | 0 | 0
806 | () |  | 0 | 0 |  | 0 | 0% Physical | NAN |  |  |  | 03/05/2023 | 0 | 0
807 | () |  | 0 | 0 |  | 0 | WO no issued | NAN |  |  |  | 04/04/2023 | 0 | 0
808 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. (SM/08977) | SM/08977 | 481.61 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 20/05/2022 | 0 | 0
809 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) (Part-A) (SM/07352) | SM/07352 | 99.63 | 121 | RETROFITTING | 6 | Delayed | 84 | 11/12/2020 | 31/05/2025 | 15/12/2025 | 18/09/2020 | 83.47 | 83.47
810 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan (SM/06798) | SM/06798 | 91.53 | 336 | RETROFITTING | 40 | Delayed | 80 | 23/09/2020 | 30/06/2025 | 15/12/2025 | 09/10/2020 | 73.38 | 73.38
811 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-II) (Part-B) (SM/07369) | SM/07369 | 94.58 | 994 | RETROFITTING | 45 | Delayed | 72 | 11/12/2020 | 30/06/2025 | 15/12/2025 | 25/08/2021 | 68 | 67.56
812 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) (SM/07371) | SM/07371 | 78.33 | 1094 | RETROFITTING | 45 | Delayed | 97 | 11/12/2020 | 30/06/2025 | 15/12/2025 | 01/12/2021 | 76.05 | 76.05
813 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) (SM/07272) | SM/07272 | 88.11 | 1275 | RETROFITTING | 45 | Delayed | 97 | 08/12/2020 | 31/07/2025 | 15/12/2025 | 10/02/2021 | 85.54 | 85.54
814 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg (SM/09315) | SM/09315 | 230.75 | 3480 | RETROFITTING | 50 | Delayed | 98 | 08/11/2021 | 30/06/2025 | 15/12/2025 | 11/11/2021 | 226.77 | 226.77
815 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r (SM/06797) | SM/06797 | 77.86 | 343 | RETROFITTING | 52 | Delayed | 0 | 23/09/2020 | 30/06/2025 | 15/12/2025 | 09/12/2020 | 0 | 0
816 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas (SM/06801) | SM/06801 | 48.55 | 580 | RETROFITTING | 52 | Delayed | 97 | 23/09/2020 | 31/05/2025 | 15/12/2025 | 09/12/2020 | 46.92 | 46.92
817 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota (SM/06790) | SM/06790 | 86.99 | 1015 | RETROFITTING | 52 | Delayed | 74 | 23/09/2020 | 30/06/2025 | 15/12/2025 | 09/10/2020 | 64.66 | 64.66
818 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41) , Baurisol (42) and Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its (SM/06795) | SM/06795 | 88.07 | 1090 | RETROFITTING | 52 | Delayed | 97 | 23/09/2020 | 31/05/2025 | 15/12/2025 | 09/12/2020 | 85.5 | 80.88
819 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Ekteswar (Part, 70%) & Sankarhati) of pipe water supply scheme for E (SM/09310) | SM/09310 | 32.92 | 452 | RETROFITTING | 55 | Delayed | 97 | 08/11/2021 | 31/07/2025 | 15/12/2025 | 12/11/2021 | 31.96 | 31.54
820 | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I) (Part-B) (SM/07368) | SM/07368 | 86.28 | 945 | RETROFITTING | 55 | Delayed | 84 | 11/12/2020 | 30/06/2025 | 15/12/2025 | 25/08/2021 | 72.06 | 69.64
821 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) (SM/07271) | SM/07271 | 96.39 | 1029 | RETROFITTING | 55 | Delayed | 94 | 08/12/2020 | 31/07/2025 | 15/12/2025 | 20/01/2021 | 90.54 | 93.11
822 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06796) | SM/06796 | 99.94 | 384 | RETROFITTING | 55 | Delayed | 100 | 23/09/2020 | 30/06/2025 | 15/12/2025 | 09/10/2020 | 99.94 | 99.94
823 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dulaparar (231), Asarda (232), Chandpara (233), Luapara (269), Kemduadangri (273), Benasuli (275), Phulberia (278), Danara (279) mouzas by retrofitting of Piped Water Supply (SM/06791) | SM/06791 | 85.04 | 580 | RETROFITTING | 57 | Delayed | 90 | 23/09/2020 | 30/06/2025 | 15/12/2025 | 09/10/2020 | 76.25 | 76.25
824 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme (SM/06799) | SM/06799 | 91.99 | 1532 | RETROFITTING | 62 | Delayed | 85 | 23/09/2020 | 31/05/2025 | 15/12/2025 | 09/10/2020 | 78.13 | 78.13
825 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sinyajora (32), Bhelaidiha (36), Korkhi (37) , Shyampur (44), Jugidangra (47), Rasikpur (48) and Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for L (SM/06793) | SM/06793 | 67.66 | 675 | RETROFITTING | 65 | Delayed | 67 | 23/09/2020 | 31/07/2025 | 15/12/2025 | 09/12/2020 | 45.48 | 45.48
826 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) (SM/07330) | SM/07330 | 67.6 | 241 | RETROFITTING | 65 | Delayed | 57 | 10/12/2020 | 30/11/2025 | 15/12/2025 | 10/02/2021 | 38.42 | 45.04
827 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) (SM/07350) | SM/07350 | 58.68 | 816 | RETROFITTING | 65 | Delayed | 100 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 25/08/2021 | 58.68 | 62.46
828 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06792) | SM/06792 | 74.89 | 981 | RETROFITTING | 65 | Delayed | 69 | 23/09/2020 | 31/07/2025 | 15/12/2025 | 09/10/2020 | 51.31 | 25.22
829 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gotkanali (45), Bankhola (54), Jarisa (89) & Harinyaguri (90) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06794) | SM/06794 | 86.48 | 1100 | RETROFITTING | 75 | Delayed | 34 | 23/09/2020 | 31/07/2025 | 15/12/2025 | 09/10/2020 | 28.99 | 28.83
830 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, (SM/09314) | SM/09314 | 169.28 | 1633 | RETROFITTING | 75 | Delayed | 82 | 08/11/2021 | 31/05/2025 | 15/12/2025 | 16/11/2021 | 139.05 | 127.84
831 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply s (SM/09309) | SM/09309 | 36.21 | 245 | RETROFITTING | 75 | Delayed | 97 | 08/11/2021 | 31/05/2025 | 15/12/2025 | 12/11/2021 | 35.14 | 35.14
832 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) (SM/07370) | SM/07370 | 98.13 | 1419 | RETROFITTING | 80 | Delayed | 97 | 11/12/2020 | 31/05/2025 | 15/12/2025 | 31/08/2022 | 95.27 | 95.27
833 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas (SM/06800) | SM/06800 | 60.74 | 697 | RETROFITTING | 82 | Delayed | 89 | 23/09/2020 | 30/09/2025 | 15/12/2025 | 09/12/2020 | 54.16 | 54.16
834 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 nos. Mouzas (Kastara, Rangamati, Kendana, Sat-deuli) of pipe water supply sc (SM/09311) | SM/09311 | 55.5 | 38 | RETROFITTING | 85 | Delayed | 97 | 08/11/2021 | 31/05/2025 | 15/12/2025 | 12/11/2021 | 53.88 | 53.88
835 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, (SM/09316) | SM/09316 | 272.68 | 3242 | RETROFITTING | 85 | Delayed | 97 | 08/11/2021 | 31/05/2025 | 15/12/2025 | 11/11/2021 | 264.73 | 267.42
836 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) (SM/08983) | SM/08983 | 672.25 | 2939 | AUGMENTATION | 85 | Delayed | 64 | 29/10/2021 | 30/07/2025 | 15/12/2025 | 25/05/2022 | 433.41 | 433.41
837 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-B) (SM/07351) | SM/07351 | 61.18 | 869 | RETROFITTING | 89 | Delayed | 97 | 11/12/2020 | 30/11/2025 | 15/12/2025 | 18/09/2020 | 59.4 | 59.4
838 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. (SM/06634) | SM/06634 | 104.55 | 0 | SUPPORT-WQMSP | 90 |  | 0 | 05/02/2020 |  | 05/04/2024 | 22/11/2021 | 0 | 0
839 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dhaldanga, Chak dhaldanga, (SM/07242) | SM/07242 | 79.81 | 1138 | RETROFITTING | 95 | On track | 85 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 31/12/2020 | 68.17 | 68.17
840 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supp (SM/07365) | SM/07365 | 65.48 | 757 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 63.57 | 63.57
841 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) (SM/07372) | SM/07372 | 75.12 | 921 | RETROFITTING | 95 | On track | 86 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 64.78 | 64.78
842 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Anchuri, Dhulkumari, Patha (SM/07249) | SM/07249 | 85.75 | 920 | RETROFITTING | 95 | On track | 52 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 44.68 | 44.68
843 | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR and Direct Zone- 1)und (SM/07765) | SM/07765 | 1524.36 | 17874 | RETROFITTING | 95 | On track | 92 | 11/01/2021 | 31/10/2025 | 15/12/2025 | 12/02/2021 | 1395.56 | 1395.42
844 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo (SM/07259) | SM/07259 | 86.91 | 955 | RETROFITTING | 95 | On track | 100 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 86.91 | 86.91
845 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bara Gajra (103), Asberya (104), Kaliahuta (105), Jadurbankata (106), Nischintapur (107), Kankata (127), Dharra Muli (128) & Bagaldhara (129) mouzas by retrofitting Zone-F (M (SM/07269) | SM/07269 | 89.36 | 1043 | RETROFITTING | 95 | On track | 29 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 25.9 | 25.9
846 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kundurka (43), Paira (44), Simlabandh (45), Bhedua (46) & Lutia (47) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at (SM/07337) | SM/07337 | 56.54 | 721 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 54.9 | 54.87
847 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kendboni, Kantaboni, Mamur (SM/06815) | SM/06815 | 86.39 | 1213 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 83.88 | 83.84
848 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 Nos. Mouzas (Malpara, Harokabedy, Mangalda, Palsora, Kalai, Amdiha, Parasi (SM/07324) | SM/07324 | 96.55 | 1058 | RETROFITTING | 95 | On track | 73 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 70.14 | 70.14
849 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh W (SM/07357) | SM/07357 | 88.45 | 561 | RETROFITTING | 95 | On track | 87 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 76.89 | 76.89
850 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (SM/07358) | SM/07358 | 79.04 | 937 | RETROFITTING | 95 | On track | 94 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 74.32 | 73.76
851 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas ( Baraleddya, Dhagoria, Ban (SM/07329) | SM/07329 | 96.08 | 811 | RETROFITTING | 95 | On track | 64 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 04/02/2021 | 61.96 | 61.96
852 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Birasimul-70, Shakrul-71, Suripuskarini-72 & D (SM/09318) | SM/09318 | 99.95 | 1343 | RETROFITTING | 95 | On track | 79 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 16/11/2021 | 79.13 | 79.07
853 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa (SM/09320) | SM/09320 | 146.29 | 2035 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 17/12/2021 | 142.03 | 138.96
854 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Layak Bandh - 13 & Chua Masina - 17) of (SM/09321) | SM/09321 | 210.06 | 2202 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 31/12/2021 | 203.94 | 203.41
855 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR (SM/08293) | SM/08293 | 73.3 | 886 | RETROFITTING | 95 | On track | 97 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 11/11/2021 | 71.17 | 72.43
856 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 (SM/08299) | SM/08299 | 87.68 | 1112 | RETROFITTING | 95 | On track | 97 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 85.12 | 85.12
857 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Basuda, Rajprasadpur, Saldanga, Managram, Dewangrya, Numuigary (SM/07248) | SM/07248 | 83.6 | 946 | RETROFITTING | 95 | On track | 85 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 71.35 | 71.35
858 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kulpat Bonkati, Gourangadi (SM/06810) | SM/06810 | 90.12 | 1186 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 87.5 | 87.5
859 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mouzas (Bagapatal, Parasia bad, Ba (SM/06813) | SM/06813 | 60.4 | 829 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 18/02/2021 | 58.64 | 58.64
860 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 02 Nos. Mouzas (Pinguri & Tentulpoha) of MALIARA (Zone - A) under Bankura - I, (SM/07308) | SM/07308 | 85.15 | 999 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 25/02/2021 | 82.67 | 82.67
861 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - I) of MALIARA (Zone - A) under Bankura - I, II (SM/07309) | SM/07309 | 84.49 | 954 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 25/02/2021 | 82.03 | 82.03
862 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Bara (SM/07265) | SM/07265 | 75.82 | 874 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 15/01/2021 | 73.61 | 72.7
863 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kasipur (230), Indkucha (231), Dhanara (234), Nekra Sonda (246), Sabudad (253), Dumuria (254), Dhargram (255), Sial Pahari (256) & Dhabani (257) mouzas by retrofitting Zone-H (SM/07361) | SM/07361 | 99.88 | 1117 | RETROFITTING | 95 | On track | 35 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 35.03 | 35.03
864 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R (SM/07363) | SM/07363 | 97.85 | 1178 | RETROFITTING | 95 | On track | 77 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 74.97 | 74.92
865 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (6 (SM/07364) | SM/07364 | 69.9 | 788 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 67.86 | 67.86
866 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) (SM/07374) | SM/07374 | 97.77 | 1298 | RETROFITTING | 95 | On track | 69 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 02/06/2023 | 67.23 | 67.23
867 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Z (SM/07360) | SM/07360 | 99.9 | 1103 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 96.99 | 96.99
868 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Shitla, Manjumara, Monoharbati & Pabaya) of Kanchanpur (Zone - (SM/07258) | SM/07258 | 86.63 | 952 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 84.1 | 84.1
869 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo (SM/07270) | SM/07270 | 100 | 1265 | RETROFITTING | 95 | On track | 90 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 89.61 | 82.25
870 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bamdhantur, Nabada, Sibara (SM/07316) | SM/07316 | 99.71 | 931 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 96.8 | 96.8
871 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under (SM/07319) | SM/07319 | 77.62 | 992 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 19/01/2021 | 75.35 | 75.35
872 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pita Dungri (275) & Kuchiar Mahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh (SM/07354) | SM/07354 | 67.76 | 833 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 65.79 | 65.79
873 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas ( Bhalukbasa, Hrtyasol, Kus (SM/07344) | SM/07344 | 95.35 | 819 | RETROFITTING | 95 | On track | 49 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 19/01/2021 | 46.94 | 46.94
874 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Wa (SM/07331) | SM/07331 | 99.99 | 1207 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 09/02/2021 | 97.08 | 97.08
875 | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Sup (SM/09312) | SM/09312 | 206.86 | 1949 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 17/12/2021 | 200.84 | 200.63
876 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Hariramp (SM/09313) | SM/09313 | 262.33 | 938 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 01/02/2022 | 254.69 | 254.69
877 | Construction & commissioning d of FHTC by Retrofitting of completeand commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Kunjapur-112 & Bahalalpur-114) of Betanal (SM/09317) | SM/09317 | 97.49 | 852 | RETROFITTING | 95 | On track | 53 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 26/11/2021 | 52.08 | 52.08
878 | & commissiConstruction oning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Dighalgram-126) of Betanal (Zone - B) under (SM/09322) | SM/09322 | 98.43 | 751 | RETROFITTING | 95 | On track | 58 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 16/11/2021 | 57.57 | 57.57
879 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi (SM/09324) | SM/09324 | 187.99 | 2264 | RETROFITTING | 95 | On track | 92 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 30/12/2021 | 172.89 | 172.89
880 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Ajodhya (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Sancha - 6,Patalpur -8, Loharara - 9, Ajodhya -10 (SM/09326) | SM/09326 | 291.93 | 3096 | RETROFITTING | 95 | On track | 58 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 12/05/2022 | 168.44 | 168.44
881 | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan (SM/09327) | SM/09327 | 254.63 | 2355 | RETROFITTING | 95 | On track | 90 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 11/11/2021 | 230.08 | 229.86
882 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it (SM/09233) | SM/09233 | 99.93 | 1000 | RETROFITTING | 95 | On track | 65 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 65.04 | 65.04
883 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) (SM/09236) | SM/09236 | 271.55 | 2199 | RETROFITTING | 95 | On track | 97 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 263.64 | 261.86
884 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Abantika- 88 , Belthya- 89 & Deuli- 91) of BENDA u (SM/09240) | SM/09240 | 73.17 | 733 | RETROFITTING | 95 | On track | 61 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 11/11/2021 | 44.79 | 44.79
885 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Narasole, Radhaballavpur, Gopinathdihi, Taljhoria, Namabad, K (SM/07239) | SM/07239 | 96.29 | 924 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 93.48 | 93.48
886 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh (SM/09319) | SM/09319 | 254.76 | 2881 | RETROFITTING | 95 | On track | 69 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 31/12/2021 | 175.3 | 175.3
887 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Nangalbhanga-18, Chwak Chuamosina-19, B (SM/09308) | SM/09308 | 67.34 | 807 | RETROFITTING | 95 | On track | 83 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 16/11/2021 | 55.84 | 55.43
888 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Purunia, sangrampur, Laxminarayanpur, Baharkhulia & Gangadarpu (SM/07256) | SM/07256 | 98.92 | 700 | RETROFITTING | 95 | On track | 94 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 93.33 | 93.33
889 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 nos. Mouzas (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, P (SM/09328) | SM/09328 | 236.78 | 1891 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 16/11/2021 | 229.89 | 229.89
890 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra (SM/07257) | SM/07257 | 94.9 | 931 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 92.13 | 92.13
891 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o (SM/07251) | SM/07251 | 99.13 | 958 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/10/2021 | 96.25 | 96.25
892 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Guniada (1), Chalka (2), Chatanibaid (3), Bangopalpur (4) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph (SM/07266) | SM/07266 | 71.22 | 845 | RETROFITTING | 95 | On track | 50 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 35.73 | 35.73
893 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mouzas (Bhangaria, Magra and Sonad (SM/06812) | SM/06812 | 60.55 | 831 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/12/2020 | 60.55 | 60.55
894 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, (SM/06807) | SM/06807 | 99.9 | 1008 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 99.9 | 99.9
895 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su (SM/07359) | SM/07359 | 99.99 | 1147 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 97.08 | 97.08
896 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Ramchandrapur, Paschim Brindabanpur, Palsana & Saluka) of Jo (SM/07328) | SM/07328 | 95.32 | 923 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 92.54 | 92.54
897 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Raniban (SM/07332) | SM/07332 | 86.55 | 957 | RETROFITTING | 95 | On track | 78 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 67.56 | 67.56
898 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Srikara-31, Padua-11, Adpara Kumrul-12, Srip (SM/09323) | SM/09323 | 206.18 | 2465 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 200.17 | 203.03
899 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, (SM/09238) | SM/09238 | 80.74 | 495 | RETROFITTING | 95 | On track | 82 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 01/12/2021 | 66.05 | 66.05
900 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, (SM/08290) | SM/08290 | 78.52 | 692 | RETROFITTING | 95 | On track | 97 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 22/09/2021 | 76.23 | 76.23
901 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Tentulara-20, Saluka-21, Dharampur-22, (SM/08291) | SM/08291 | 78.23 | 867 | RETROFITTING | 95 | On track | 75 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 22/09/2021 | 58.35 | 58.35
902 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 (SM/09239) | SM/09239 | 76.06 | 735 | RETROFITTING | 95 | On track | 40 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 26/10/2021 | 30.72 | 32.32
903 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368), Deuli (369) & Majura (372) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF (SM/09230) | SM/09230 | 89 | 1179 | RETROFITTING | 95 | On track | 86 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 08/11/2021 | 76.31 | 76.31
904 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo (SM/09305) | SM/09305 | 95.96 | 917 | RETROFITTING | 95 | On track | 66 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 26/02/2021 | 63.55 | 63.55
905 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam (SM/07264) | SM/07264 | 83.94 | 1086 | RETROFITTING | 95 | On track | 10 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 12/07/2022 | 8.78 | 8.78
906 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan (SM/07306) | SM/07306 | 96.39 | 1304 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 93.58 | 93.58
907 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Talgaria (93), Itamara (94), Uganpathar (95), Benagaria (96), Pathardihi (97), Jambedya (98), Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangam (SM/07267) | SM/07267 | 96.51 | 1056 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 93.7 | 93.7
908 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar (SM/07255) | SM/07255 | 98.39 | 665 | RETROFITTING | 95 | On track | 90 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 88.39 | 88.39
909 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Mouladanga, Mithila, Jagan (SM/07238) | SM/07238 | 76.09 | 1035 | RETROFITTING | 95 | On track | 98 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 74.38 | 74.38
910 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed (SM/07246) | SM/07246 | 96.56 | 797 | RETROFITTING | 95 | On track | 75 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 31/12/2020 | 72.68 | 72.68
911 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa (SM/07766) | SM/07766 | 1310.43 | 14433 | RETROFITTING | 95 | On track | 98 | 11/01/2021 | 31/10/2025 | 15/12/2025 | 12/02/2021 | 1287.86 | 1287.67
912 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorshal, Dhenga kend, Kushma, Golhati & Bonomadhavpur) of J (SM/07339) | SM/07339 | 81.28 | 841 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 78.79 | 78.79
913 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gourangadihi, Ledadihi, Ra (SM/06818) | SM/06818 | 78.36 | 872 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 18/02/2021 | 76.08 | 76.08
914 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chakadoba (73), Balarampur (138), Kubasol (139), Ban Pukhuria (140), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas (SM/07335) | SM/07335 | 99.02 | 1201 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 96.13 | 139.11
915 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Kenjera-129, Chattrakhanda-130 & Nagatentu (SM/09332) | SM/09332 | 85.14 | 613 | RETROFITTING | 95 | On track | 55 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 22/11/2021 | 46.71 | 41.71
916 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur (SM/09237) | SM/09237 | 299.8 | 3263 | RETROFITTING | 95 | On track | 68 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 29/10/2021 | 202.51 | 202.51
917 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde (SM/08297) | SM/08297 | 84.54 | 1421 | RETROFITTING | 95 | On track | 97 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 82.07 | 82.07
918 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District (SM/08310) | SM/08310 | 295.5 | 7200 | RETROFITTING | 95 | On track | 30 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 04/06/2021 | 87.99 | 87.99
919 | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Kumirdoha, Gairabad, Fulberia, Dhaban, Bhabanipur, Upargara) o (SM/09306) | SM/09306 | 97.18 | 914 | RETROFITTING | 95 | On track | 80 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 18/02/2021 | 77.29 | 75.04
920 | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE (SM/07310) | SM/07310 | 90.97 | 1185 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 09/07/2021 | 88.32 | 87.98
921 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5), Elora (7), Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirba (SM/07268) | SM/07268 | 77.68 | 919 | RETROFITTING | 95 | On track | 95 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 73.58 | 73.58
922 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hare Krishnapur , Dadimukha , Gopbandh , Bankuradanga, Belut , (SM/07305) | SM/07305 | 96.08 | 1303 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 93.29 | 93.29
923 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa (SM/07250) | SM/07250 | 88.19 | 918 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 85.63 | 85.63
924 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (1 (SM/07366) | SM/07366 | 79.75 | 945 | RETROFITTING | 95 | On track | 72 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 09/07/2021 | 57.74 | 57.64
925 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyalda (SM/07240) | SM/07240 | 83.76 | 1131 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 09/07/2021 | 81.32 | 81.32
926 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kusum Goria, Tajpur Rampur, Rajmadhavtir, Kotalpukur & Mahidar (SM/07243) | SM/07243 | 77.66 | 963 | RETROFITTING | 95 | On track | 96 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 24/02/2021 | 74.71 | 74.71
927 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dadhimukha, Jamboni,Jagdal (SM/07245) | SM/07245 | 81.76 | 1185 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 19/01/2021 | 79.37 | 79.37
928 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas (Dhaboagram, Tantkanali, Ni (SM/07247) | SM/07247 | 85.75 | 920 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 31/12/2020 | 83.25 | 83.25
929 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouza (Bandarkoda, Bhairabdanga, Barkura, Radhakantapur, Kantabesa, Ni (SM/07263) | SM/07263 | 99.4 | 1052 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 96.51 | 96.51
930 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bara Bendya, Joytunga, Kostia & Khemua) of Joytunga (Zone - (SM/07313) | SM/07313 | 97.22 | 819 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 94.39 | 93.55
931 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Bandarkhola, Ramharipur, Katapesia, Kolaberia & Maitha Gopinat (SM/07314) | SM/07314 | 91.63 | 853 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 88.96 | 88.96
932 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF (SM/07338) | SM/07338 | 89.1 | 955 | RETROFITTING | 95 | On track | 72 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 63.73 | 113.73
933 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh (SM/07353) | SM/07353 | 66.76 | 828 | RETROFITTING | 95 | On track | 89 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 59.29 | 42.54
934 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mouzas (Junbedia) of HARIALGORA (Z (SM/06817) | SM/06817 | 78.79 | 881 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 78.79 | 78.79
935 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas (SM/06808) | SM/06808 | 88 | 1013 | RETROFITTING | 95 | On track | 99 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 86.73 | 86.73
936 | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme (SM/09330) | SM/09330 | 211.32 | 2161 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 17/12/2021 | 205.16 | 204.63
937 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Mathurabihari-28, Ramchandrapur-30, Matukp (SM/08292) | SM/08292 | 70.88 | 828 | RETROFITTING | 95 | On track | 90 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 64.06 | 63.72
938 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du (SM/08298) | SM/08298 | 75.69 | 1240 | RETROFITTING | 95 | On track | 71 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 26/10/2021 | 53.48 | 53.48
939 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjo (SM/09231) | SM/09231 | 99.3 | 375 | RETROFITTING | 95 | On track | 72 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 71.91 | 71.91
940 | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura (SM/09304) | SM/09304 | 85.58 | 974 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 25/02/2021 | 83.08 | 81.12
941 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala) of Nabagr (SM/07342) | SM/07342 | 98.67 | 806 | RETROFITTING | 95 | On track | 0 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 25/08/2021 | 0 | 0
942 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku (SM/07336) | SM/07336 | 63.54 | 617 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 61.69 | 61.69
943 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) & Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under (SM/07356) | SM/07356 | 64.72 | 735 | RETROFITTING | 95 | On track | 84 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 54.05 | 54.05
944 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Bamania-113) of Betanal (Zone - B) under In (SM/09331) | SM/09331 | 92.06 | 753 | RETROFITTING | 95 | On track | 43 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 40 | 39.78
945 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap (SM/07261) | SM/07261 | 83.44 | 1033 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 81.01 | 81.01
946 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo (SM/07327) | SM/07327 | 66.26 | 926 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 64.33 | 64.29
947 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Ladna, Mathana, Kodalia) of Joytunga (Zone - H) under Banku (SM/07312) | SM/07312 | 85.93 | 859 | RETROFITTING | 95 | On track | 100 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 85.93 | 85.93
948 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Nangla, Agaya, Gidhuria, Pachasimul, Mechabaid, Banjurya, Har (SM/07253) | SM/07253 | 90.95 | 872 | RETROFITTING | 95 | On track | 77 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 27/07/2021 | 69.75 | 69.75
949 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Dakaisini, Khandari, Bansol, Dhwajmonipur & Damodarpur) of (SM/07260) | SM/07260 | 89.89 | 959 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 87.27 | 87.27
950 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z (SM/07320) | SM/07320 | 77.52 | 990 | RETROFITTING | 95 | On track | 69 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 25/08/2021 | 53.16 | 53.16
951 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Khejurbedia, Upardihi, Rad (SM/06809) | SM/06809 | 99.97 | 1008 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 97.06 | 97.06
952 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-H (SM/07355) | SM/07355 | 61.82 | 716 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 15/01/2021 | 60.02 | 60.02
953 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa (SM/07340) | SM/07340 | 88.31 | 1104 | RETROFITTING | 95 | On track | 70 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 23/02/2021 | 62.17 | 62.17
954 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad (SM/06816) | SM/06816 | 80.94 | 870 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 78.58 | 78.58
955 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Mobarakpur, Chaptara, Send (SM/06803) | SM/06803 | 94.04 | 49304 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 94.04 | 94.04
956 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Taldanga, Upar Narrah, Khe (SM/06806) | SM/06806 | 78.26 | 1057 | RETROFITTING | 95 | On track | 96 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 75.41 | 75.41
957 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na (SM/07347) | SM/07347 | 93.49 | 1055 | RETROFITTING | 95 | On track | 85 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 79.81 | 79.81
958 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha (SM/07349) | SM/07349 | 95.93 | 1050 | RETROFITTING | 95 | On track | 11 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 04/02/2021 | 10.72 | 10.72
959 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Sc (SM/07333) | SM/07333 | 61.29 | 664 | RETROFITTING | 95 | On track | 82 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 50.17 | 50.17
960 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under (SM/09227) | SM/09227 | 51.96 | 327 | RETROFITTING | 95 | On track | 97 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 11/02/2021 | 50.44 | 48.32
961 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur (SM/09228) | SM/09228 | 255.23 | 2415 | RETROFITTING | 95 | On track | 65 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 12/05/2022 | 166.74 | 166.74
962 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Nabagram, Vidyadharpur, Ai (SM/06804) | SM/06804 | 92.61 | 1209 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 92.61 | 92.61
963 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) (SM/07373) | SM/07373 | 96.11 | 1284 | RETROFITTING | 95 | On track | 65 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 25/02/2021 | 62.94 | 62.94
964 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Rangametya, Kuladabar, Burat, Deulberia, Murgathol, Ampahari, (SM/07311) | SM/07311 | 88.11 | 1181 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 85.2 | 85.2
965 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kalipur, Housibad, Parulia, Biskodar, Joljolia Banshal) of K (SM/07254) | SM/07254 | 74.43 | 873 | RETROFITTING | 95 | On track | 83 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 61.71 | 61.71
966 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70), Jamdahara (71), Tilabani (72), Dhanga Dungri (74), Mirgi (75), Basudebpur (79), Jhat Pukhuria (80) & Patasimul (1 (SM/07367) | SM/07367 | 99.39 | 1201 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 96.49 | 146.48
967 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu (SM/07237) | SM/07237 | 75.94 | 1033 | RETROFITTING | 95 | On track | 100 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 75.94 | 75.94
968 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap (SM/07244) | SM/07244 | 77.31 | 806 | RETROFITTING | 95 | On track | 31 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 23/02/2023 | 24.25 | 24.25
969 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, (SM/07315) | SM/07315 | 98.56 | 932 | RETROFITTING | 95 | On track | 98 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 96.63 | 96.63
970 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahirdya, Fulkusma, Jambede, Nabagram)of Nabagram (Zon - K) unde (SM/07321) | SM/07321 | 97.45 | 802 | RETROFITTING | 95 | On track | 46 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 25/08/2021 | 45 | 45
971 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouza (Talanda, Cahndanpur, Swargabati, Harishpur, Gopinathpur, Brinda (SM/07345) | SM/07345 | 85.97 | 1056 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 29/12/2020 | 83.47 | 83.47
972 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math (SM/07346) | SM/07346 | 99.61 | 1056 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 19/02/2021 | 96.71 | 96.71
973 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal (SM/06814) | SM/06814 | 86.25 | 1212 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 83.74 | 83.74
974 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und (SM/07323) | SM/07323 | 89.87 | 751 | RETROFITTING | 95 | On track | 78 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 69.76 | 69.76
975 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Brindajam, Kaminbedia, Sihikapahari, Hatjore, Simulbedia, Moy (SM/07325) | SM/07325 | 88.06 | 1108 | RETROFITTING | 95 | On track | 87 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 09/07/2021 | 76.94 | 76.94
976 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Chhendua, Chamkara, Fengab (SM/07343) | SM/07343 | 99.07 | 994 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 19/01/2021 | 96.18 | 96.17
977 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, (SM/06802) | SM/06802 | 94.88 | 1209 | RETROFITTING | 95 | On track | 97 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 92.44 | 92.44
978 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Patna Joykrishnapur, Kunja (SM/06805) | SM/06805 | 78.14 | 1056 | RETROFITTING | 95 | On track | 100 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 09/12/2020 | 78.14 | 78.14
979 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos mousas (Helna, Fagua kanali, Dumur (SM/07348) | SM/07348 | 93.87 | 1018 | RETROFITTING | 95 | On track | 62 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 18/08/2021 | 58.16 | 58.16
980 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Banki-85, Chotogobindapur-86, Adilpur-87 & (SM/09325) | SM/09325 | 226.6 | 2639 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 30/12/2021 | 220 | 226.8
981 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B a (SM/09232) | SM/09232 | 82.52 | 930 | RETROFITTING | 95 | On track | 91 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 08/11/2021 | 75.27 | 75.27
982 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari (SM/07322) | SM/07322 | 78.19 | 995 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 75.91 | 75.91
983 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Mamudpur-124, Barabaikunthapur-125, Habish (SM/08294) | SM/08294 | 80.95 | 549 | RETROFITTING | 95 | On track | 52 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 42.21 | 42.21
984 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya (SM/09229) | SM/09229 | 89.49 | 1188 | RETROFITTING | 95 | On track | 72 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 08/11/2021 | 64.84 | 64.43
985 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Barsi, Malbedya, Narasinghapur, Arrah, Barabanagram, Khudra b (SM/07241) | SM/07241 | 96.76 | 1062 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 27/07/2021 | 93.87 | 93.87
986 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - II) of MALIARA (Zone - A) under Bankura - I,II & (SM/07307) | SM/07307 | 84.49 | 954 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 25/02/2021 | 82.03 | 82.03
987 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Raniban (SM/07362) | SM/07362 | 77.85 | 939 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 75.59 | 75.59
988 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jhunka, Shushunia parasibana, Paharbedia, Bharatpur, Kendua) (SM/07252) | SM/07252 | 90.97 | 874 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 88.32 | 88.32
989 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 12 Nos. Mouzas (Enayetpur, Kaleberia, Namoghansara, Kururia Balarampur, Malkuru (SM/07262) | SM/07262 | 80.43 | 1032 | RETROFITTING | 95 | On track | 97 | 08/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 78.09 | 78.08
990 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou (SM/07317) | SM/07317 | 85.51 | 972 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 24/02/2021 | 83.02 | 83.02
991 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola (SM/07318) | SM/07318 | 80.74 | 1164 | RETROFITTING | 95 | On track | 86 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 04/02/2021 | 69.14 | 69.11
992 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria (SM/06811) | SM/06811 | 90.1 | 1186 | RETROFITTING | 95 | On track | 81 | 23/09/2020 | 31/10/2025 | 15/12/2025 | 08/10/2020 | 73.15 | 73.15
993 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam (SM/07326) | SM/07326 | 72.12 | 998 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 10/02/2021 | 70.02 | 70.02
994 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis (SM/07334) | SM/07334 | 99.12 | 1254 | RETROFITTING | 95 | On track | 97 | 10/12/2020 | 31/10/2025 | 15/12/2025 | 18/01/2021 | 96.24 | 96.24
995 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District (SM/08311) | SM/08311 | 298.3 | 7093 | RETROFITTING | 95 | On track | 62 | 26/02/2021 | 31/10/2025 | 15/12/2025 | 12/05/2022 | 186.33 | 174.53
996 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S (SM/09329) | SM/09329 | 160.36 | 1144 | RETROFITTING | 95 | On track | 96 | 08/11/2021 | 31/10/2025 | 15/12/2025 | 11/11/2021 | 153.17 | 153.17
997 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by (SM/09235) | SM/09235 | 79.85 | 885 | RETROFITTING | 95 | On track | 78 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 08/11/2021 | 62.57 | 62.57
998 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S (SM/09234) | SM/09234 | 82.8 | 967 | RETROFITTING | 95 | On track | 92 | 25/05/2021 | 31/10/2025 | 15/12/2025 | 23/09/2021 | 76.31 | 76.31
999 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo (SM/07341) | SM/07341 | 85.33 | 1066 | RETROFITTING | 95 | On track | 97 | 11/12/2020 | 31/10/2025 | 15/12/2025 | 05/02/2021 | 82.51 | 82.51
Total |  |  | 23060.84 | 858679 | [8 empty] | 93478.39 | 93626.67