## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | MINI PIPED WATER SUPPLY SCHEME FOR MAHISHAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11083) | SM/11083 | 32.56 | 28 | NEW | 0 | 0% Physical | 0 | 30/05/2022 | 31/03/2023 | 12/06/2023 | 03/08/2022 | 0 | 0
2 | MINI PIPED WATER SUPPLY SCHEME FOR BERUABAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11131) | SM/11131 | 43.25 | 90 | NEW | 0 | 0% Physical | 0 | 30/05/2022 | 31/03/2023 | 12/06/2023 | 03/08/2022 | 0 | 0
3 | Construction of Grid-connected Solar Photo-Voltaic system for Joypur pump house-I of Joypur PWSS scheme,Dist: Bankura (SM/16932) | SM/16932 | 9.77 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 17/04/2023 | 0 | 0
4 | Water supply scheme for ASRAMSALA OF Ramkrishna Mission Sarada Vidyapith under Bishnupur Sub-Division of Bankura Division P.H.E. Dte. (SM/18851) | SM/18851 | 67.55 | 0 | SCHOOL | 0 | WO no issued | 0 | 29/09/2023 |  | 29/09/2023 |  | 0 | 0
5 | Construction of Grid-Connected solar photo -voltaic system for Pump House I of Moynapur PWS scheme Dist Bankura (SM/15328) | SM/15328 | 14.34 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/02/2023 | 09/08/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
6 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA GOALDANGRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11133) | SM/11133 | 41.89 | 83 | NEW | 0 | 0% Physical | 0 | 30/05/2022 | 31/03/2023 | 12/06/2023 | 03/08/2022 | 0 | 0
7 | Construction of Grid-connected Solar Photo-Voltaic system for Katulpur pump house-I(OHR site) of Kotulpur PWSS scheme,Dist: Bankura (SM/16963) | SM/16963 | 11.12 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 17/04/2023 | 0 | 0
8 | MINI PIPED WATER SUPPLY SCHEME FOR AULIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11073) | SM/11073 | 34.46 | 37 | NEW | 0 | 0% Physical | 0 | 30/05/2022 | 31/03/2023 | 12/06/2023 | 03/08/2022 | 0 | 0
9 | MINI PIPED WATER SUPPLY SCHEME FOR MAHADEBSINAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11033) | SM/11033 | 36.46 | 45 | NEW | 0 | 0% Physical | 0 | 30/05/2022 | 31/03/2023 | 12/06/2023 | 03/08/2022 | 0.11 | 0.11
10 | Arrangement for double tank Chlorine dosing system at different PWSS under different Blocks of Bankura District (SM/19296) | SM/19296 | 47.11 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
11 | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission (SM/19084) | SM/19084 | 85.6 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 06/02/2024 | 0 | 0
12 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. (SM/08977) | SM/08977 | 481.61 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 20/05/2022 | 0 | 0
13 | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE (SM/18829) | SM/18829 | 55.09 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 12/09/2023 |  | 18/09/2023 | 21/12/2023 | 0 | 0
14 | Infrastructure development for Taldangra Sub-District water Testing Laboratory regarding NABL accreditation under Bankura Division, PHE Dte. related to support activities under JJM (SM/17416) | SM/17416 | 17.29 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 18/03/2023 |  | 23/03/2023 | 04/04/2023 | 0 | 0
15 | Operational charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19264) | SM/19264 | 134.66 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 26/09/2024 | 0 | 0
16 | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. (SM/19269) | SM/19269 | 168.45 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 10/09/2024 | 0 | 0
17 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11077) | SM/11077 | 36.71 | 46 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
18 | MINI PIPED WATER SUPPLY SCHEME FOR PUNESA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11049) | SM/11049 | 42.86 | 88 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
19 | MINI PIPED WATER SUPPLY SCHEME FOR JAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11200) | SM/11200 | 40.91 | 78 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
20 | MINI PIPED WATER SUPPLY SCHEME FOR ASNASUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11074) | SM/11074 | 35.46 | 41 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
21 | MINI PIPED WATER SUPPLY SCHEME FOR BANKTOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11076) | SM/11076 | 36.21 | 44 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
22 | MINI PIPED WATER SUPPLY SCHEME FOR DHUAKAKI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11039) | SM/11039 | 41.3 | 80 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0.12
23 | MINI PIPED WATER SUPPLY SCHEME FOR KUKUTIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11202) | SM/11202 | 39.52 | 61 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
24 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11042) | SM/11042 | 39.29 | 60 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
25 | MINI PIPED WATER SUPPLY SCHEME FOR BRAHMANDHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11055) | SM/11055 | 41.6 | 70 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
26 | MINI PIPED WATER SUPPLY SCHEME FOR CHAKJAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11058) | SM/11058 | 41.14 | 68 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
27 | MINI PIPED WATER SUPPLY SCHEME FOR TELANBANDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11204) | SM/11204 | 37.66 | 53 | NEW | 1 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 0.12 | 0
28 | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18893) | SM/18893 | 464 | 60 | AUGMENTATION | 3 | Delayed | 0 | 05/10/2023 | 31/03/2025 | 28/11/2024 | 09/02/2024 | 1.21 | 1.21
29 | Biur Piped Water Supply Scheme (SM/18754) | SM/18754 | 1334.45 | 2976 | NEW | 6 | Delayed | 6 | 21/08/2023 | 25/10/2025 | 14/11/2024 | 03/10/2023 | 80.28 | 80.28
30 | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18894) | SM/18894 | 770.48 | 350 | AUGMENTATION | 6 | Delayed | 1 | 05/10/2023 | 31/03/2025 | 28/11/2024 | 31/10/2023 | 5.35 | 5.35
31 | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh (SM/18612) | SM/18612 | 5127.01 | 0 | AUGMENTATION | 7 | Delayed | 25 | 31/07/2023 | 31/12/2025 | 20/12/2024 | 04/10/2023 | 1257.7 | 1257.7
32 | Nandur Piped Water Supply Scheme (SM/18252) | SM/18252 | 1462.49 | 3247 | NEW | 9 | Delayed | 10 | 16/06/2023 | 30/09/2025 | 16/12/2024 | 24/07/2023 | 141.42 | 141.42
33 | MINI PIPED WATER SUPPLY SCHEME FOR KORKHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11064) | SM/11064 | 37.43 | 52 | NEW | 10 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0 | 0
34 | MINI PIPED WATER SUPPLY SCHEME FOR RENGURBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11071) | SM/11071 | 39.98 | 128 | NEW | 10 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0 | 0
35 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARBERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11126) | SM/11126 | 44.04 | 925 | NEW | 10 | Delayed | 48 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.18 | 21.18
36 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Khanabari, House Hold No.: 53) (SM/11676) | SM/11676 | 39.88 | 700 | NEW | 11 | Delayed | 0 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 0.13 | 0.13
37 | Patrabandh Piped Water Supply Scheme (SM/14012) | SM/14012 | 978.71 | 1936 | NEW | 12 | Delayed | 6 | 05/12/2022 | 31/03/2025 | 25/09/2024 | 24/07/2023 | 59.31 | 59.31
38 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhandarya, House Hold No.: 72) (SM/11679) | SM/11679 | 39.88 | 332 | NEW | 13 | Delayed | 0 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 0.13 | 0.13
39 | MINI PIPED WATER SUPPLY SCHEME FOR SONAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11067) | SM/11067 | 42.86 | 88 | NEW | 15 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0 | 0
40 | Augmentation of Prakash Zone-B Water Supply Scheme (SM/16945) | SM/16945 | 188.68 | 210 | AUGMENTATION | 15 | Delayed | 7 | 16/03/2023 | 31/01/2025 | 16/12/2024 | 19/07/2023 | 13.63 | 13.63
41 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Pirragara, House Hold No.: 75) (SM/11673) | SM/11673 | 39.88 | 76 | NEW | 16 | Delayed | 27 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 10.66 | 10.66
42 | Laugram Piped Water Supply Scheme (SM/18438) | SM/18438 | 1392.19 | 2764 | NEW | 17 | Delayed | 14 | 18/07/2023 | 31/03/2025 | 14/11/2024 | 24/07/2023 | 198.18 | 198.18
43 | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18895) | SM/18895 | 882.2 | 50 | AUGMENTATION | 17 | Delayed | 13 | 05/10/2023 | 31/03/2025 | 28/11/2024 | 09/02/2024 | 118.35 | 118.35
44 | Rautara Piped Water Supply Scheme (SM/14521) | SM/14521 | 1022.54 | 2019 | NEW | 18 | Delayed | 10 | 30/01/2023 | 31/08/2025 | 11/12/2024 | 24/07/2023 | 100.73 | 82.6
45 | Nanda Mohanpur Piped Water Supply Scheme (SM/19178) | SM/19178 | 1443.13 | 3377 | NEW | 18 | Delayed | 1 | 16/02/2024 | 31/08/2025 | 16/12/2024 | 24/07/2023 | 16.3 | 2.19
46 | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18892) | SM/18892 | 799.62 | 100 | AUGMENTATION | 18 | Delayed | 12 | 05/10/2023 | 31/03/2025 | 28/11/2024 | 31/10/2023 | 92.76 | 92.76
47 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza (SM/09535) | SM/09535 | 152.7 | 1713 | RETROFITTING | 18 | Delayed | 29 | 19/11/2021 | 31/12/2024 | 12/02/2024 | 03/03/2022 | 44.94 | 44.94
48 | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. (SM/16696) | SM/16696 | 621.66 | 1459 | NEW | 19 | Delayed | 14 | 14/03/2023 | 31/05/2025 | 30/11/2024 | 17/03/2023 | 85.63 | 85.63
49 | MINI PIPED WATER SUPPLY SCHEME FOR SUKNABAD VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11068) | SM/11068 | 37.71 | 50 | NEW | 20 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0.12 | 0.12
50 | MINI PIPED WATER SUPPLY SCHEME FOR BAGDUBI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11110) | SM/11110 | 37.71 | 50 | NEW | 20 | Delayed | 28 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 10.53 | 10.53
51 | Augmentation for Gouripur Water Supply Scheme. (SM/17120) | SM/17120 | 116.24 | 120 | AUGMENTATION | 20 | Delayed | 70 | 16/03/2023 | 31/12/2024 | 31/08/2024 | 19/04/2023 | 80.86 | 80.86
52 | MINI PIPED WATER SUPPLY SCHEME FOR TAPUBAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11069) | SM/11069 | 43.65 | 92 | NEW | 20 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0 | 0
53 | MINI PIPED WATER SUPPLY SCHEME FOR DUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11072) | SM/11072 | 40.44 | 65 | NEW | 20 | Delayed | 0 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0 | 0
54 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 (SM/09533) | SM/09533 | 198.8 | 2270 | RETROFITTING | 20 | Delayed | 19 | 19/11/2021 | 31/12/2024 | 12/02/2024 | 21/04/2022 | 37.92 | 37.92
55 | MINI PIPED WATER SUPPLY SCHEME FOR NAMADUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11063) | SM/11063 | 31.49 | 157 | NEW | 20 | Delayed | 1 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 0.37 | 0.37
56 | Lego Piped Water Supply Scheme (SM/14177) | SM/14177 | 1049.01 | 1951 | NEW | 20 | Delayed | 4 | 09/01/2023 | 31/05/2025 | 20/12/2024 | 24/07/2023 | 45.09 | 45.07
57 | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16971) | SM/16971 | 607.96 | 176 | AUGMENTATION | 21 | Delayed | 6 | 16/03/2023 | 31/12/2024 | 20/12/2024 | 09/10/2023 | 38.04 | 38.04
58 | Augmentation of Betanal Zone-A Water Supply Scheme (SM/17692) | SM/17692 | 267.76 | 251 | AUGMENTATION | 21 | Delayed | 34 | 17/03/2023 | 28/02/2025 | 02/12/2024 | 14/08/2023 | 90.06 | 90.06
59 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Purba Nischintapur, House Hold No.: 81) (SM/11674) | SM/11674 | 39.88 | 649 | NEW | 21 | Delayed | 0 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 0.13 | 0.13
60 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dumohani, House Hold No.: 51) (SM/11677) | SM/11677 | 39.88 | 358 | NEW | 21 | Delayed | 27 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 10.66 | 10.66
61 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Kushtara , House Hold No.: 21 ) (SM/11680) | SM/11680 | 39.88 | 418 | NEW | 23 | Delayed | 0 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 0.13 | 0.13
62 | Karajbani Piped Water Supply Scheme (SM/16702) | SM/16702 | 505.78 | 1086 | NEW | 23 | Delayed | 6 | 14/03/2023 | 25/10/2025 | 11/12/2024 | 27/07/2023 | 28.49 | 24.82
63 | Narayanpur Piped Water Supply Scheme (SM/14178) | SM/14178 | 1043.85 | 1981 | NEW | 24 | Delayed | 8 | 09/01/2023 | 31/03/2025 | 13/11/2024 | 24/07/2023 | 83.29 | 83.29
64 | MINI PIPED WATER SUPPLY SCHEME FOR SUKNI BASA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11028) | SM/11028 | 37.21 | 48 | NEW | 25 | Delayed | 36 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 13.27 | 13.27
65 | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17242) | SM/17242 | 503.31 | 100 | AUGMENTATION | 25 | Delayed | 18 | 15/03/2023 | 31/01/2025 | 25/07/2024 | 08/06/2023 | 89.15 | 89.15
66 | MINI PIPED WATER SUPPLY SCHEME FOR NACHNA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11043) | SM/11043 | 41.14 | 68 | NEW | 25 | Delayed | 26 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 10.65 | 10.65
67 | MINI PIPED WATER SUPPLY SCHEME FOR KAWA TANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11109) | SM/11109 | 37.46 | 49 | NEW | 25 | Delayed | 36 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 13.38 | 13.38
68 | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10920) | SM/10920 | 41.6 | 70 | NEW | 25 | Delayed | 32 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.27 | 13.27
69 | MINI PIPED WATER SUPPLY SCHEME FOR GUMKIHATA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11011) | SM/11011 | 40.91 | 78 | NEW | 25 | Delayed | 32 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 13.16 | 13.16
70 | MINI PIPED WATER SUPPLY SCHEME FOR MARASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11051) | SM/11051 | 40.21 | 64 | NEW | 25 | Delayed | 25 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 10.12 | 10
71 | MINI PIPED WATER SUPPLY SCHEME FOR SALUKDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10981) | SM/10981 | 38.36 | 56 | NEW | 25 | Delayed | 34 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.16 | 13.16
72 | MINI PIPED WATER SUPPLY SCHEME FOR DHOBAGERE VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10880) | SM/10880 | 36.46 | 262 | NEW | 25 | Delayed | 36 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.16 | 13.16
73 | MINI PIPED WATER SUPPLY SCHEME FOR NEKRAKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10946) | SM/10946 | 41.5 | 81 | NEW | 25 | Delayed | 46 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 18.95 | 18.95
74 | MINI PIPED WATER SUPPLY SCHEME FOR SIROMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10991) | SM/10991 | 43.45 | 91 | NEW | 25 | Delayed | 30 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.16 | 13.16
75 | MINI PIPED WATER SUPPLY SCHEME FOR BUCHI BURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11026) | SM/11026 | 37.46 | 49 | NEW | 25 | Delayed | 42 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 15.8 | 15.8
76 | MINI PIPED WATER SUPPLY SCHEME FOR SURBHAGAB BAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11057) | SM/11057 | 42.86 | 88 | NEW | 25 | Delayed | 24 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 10.12 | 10
77 | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13252) | SM/13252 | 44.62 | 97 | NEW | 25 | Delayed | 30 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.27 | 13.27
78 | MINI PIPED WATER SUPPLY SCHEME FOR KOLSULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11082) | SM/11082 | 36.46 | 45 | NEW | 25 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 0.12 | 0
79 | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18403) | SM/18403 | 2747.96 | 3000 | AUGMENTATION | 25 | Delayed | 22 | 12/07/2023 | 31/05/2025 | 20/12/2024 | 25/07/2023 | 617.97 | 616.78
80 | MINI PIPED WATER SUPPLY SCHEME FOR BALI BANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11080) | SM/11080 | 32.56 | 28 | NEW | 25 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 0.12 | 0
81 | MINI PIPED WATER SUPPLY SCHEME FOR KENDUT VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10967) | SM/10967 | 44.43 | 151 | NEW | 25 | Delayed | 24 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 10.53 | 10.53
82 | MINI PIPED WATER SUPPLY SCHEME FOR BANAGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10915) | SM/10915 | 41.37 | 69 | NEW | 25 | Delayed | 32 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.3 | 13.28
83 | MINI PIPED WATER SUPPLY SCHEME FOR GORADIHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11124) | SM/11124 | 31.22 | 156 | NEW | 25 | Delayed | 34 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 10.53 | 10.53
84 | MINI PIPED WATER SUPPLY SCHEME FOR PURBATOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10960) | SM/10960 | 33.91 | 33 | NEW | 25 | Delayed | 39 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.27 | 13.27
85 | MINI PIPED WATER SUPPLY SCHEME FOR BAMNISHALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11127) | SM/11127 | 40.68 | 66 | NEW | 25 | Delayed | 39 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 15.91 | 15.91
86 | MINI PIPED WATER SUPPLY SCHEME FOR UTTAR KENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10982) | SM/10982 | 42.53 | 74 | NEW | 25 | Delayed | 31 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 13.28 | 13.28
87 | MINI PIPED WATER SUPPLY SCHEME FOR JALJURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11012) | SM/11012 | 38.13 | 55 | NEW | 25 | Delayed | 35 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 13.16 | 13.16
88 | MINI PIPED WATER SUPPLY SCHEME FOR JIAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11078) | SM/11078 | 33.91 | 33 | NEW | 25 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 0 | 0
89 | MINI PIPED WATER SUPPLY SCHEME FOR CHINGRAGOALASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10910) | SM/10910 | 32.83 | 84 | NEW | 25 | Delayed | 58 | 30/05/2022 | 31/12/2024 | 30/08/2024 | 03/08/2022 | 18.95 | 18.95
90 | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11203) | SM/11203 | 39.29 | 60 | NEW | 25 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 0.12 | 0.12
91 | MINI PIPED WATER SUPPLY SCHEME FOR BARAMASIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10911) | SM/10911 | 42.28 | 85 | NEW | 25 | Delayed | 61 | 30/05/2022 | 31/07/2024 | 01/07/2024 | 03/08/2022 | 25.88 | 25.88
92 | MINI PIPED WATER SUPPLY SCHEME FOR BAGNADA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11059) | SM/11059 | 34.46 | 48 | NEW | 25 | Delayed | 46 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 15.8 | 15.8
93 | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11066) | SM/11066 | 41.37 | 69 | NEW | 25 | Delayed | 32 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 13.4 | 13.4
94 | MINI PIPED WATER SUPPLY SCHEME FOR TIKARPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13273) | SM/13273 | 34.21 | 82 | NEW | 25 | Delayed | 31 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 10.53 | 10.53
95 | MINI PIPED WATER SUPPLY SCHEME FOR PEDDAA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11056) | SM/11056 | 44.23 | 95 | NEW | 25 | Delayed | 25 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 11.12 | 11
96 | MINI PIPED WATER SUPPLY SCHEME FOR KHALPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11015) | SM/11015 | 40.21 | 64 | NEW | 25 | Delayed | 47 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 18.95 | 18.95
97 | MINI PIPED WATER SUPPLY SCHEME FOR THANA DUMAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11125) | SM/11125 | 37.46 | 0 | NEW | 25 | Delayed | 42 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 15.91 | 15.91
98 | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11130) | SM/11130 | 43.06 | 0 | NEW | 26 | Delayed | 37 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 15.92 | 15.92
99 | Augmentation of Jayrambati Piped Water Supply Scheme. (SM/09880) | SM/09880 | 388.87 | 1287 | AUGMENTATION | 26 | Delayed | 58 | 08/12/2021 | 31/03/2025 | 02/12/2024 | 23/03/2022 | 225.72 | 225.72
100 | Khiri Piped Water Supply Scheme (SM/18436) | SM/18436 | 1118.52 | 1645 | NEW | 26 | Delayed | 19 | 18/07/2023 | 31/03/2025 | 05/10/2024 | 24/07/2023 | 208.1 | 208.1
101 | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11115) | SM/11115 | 41.6 | 70 | NEW | 26 | Delayed | 32 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 13.27 | 13.27
102 | Karak Berya Piped Water Supply Scheme (SM/14247) | SM/14247 | 1009.33 | 1922 | NEW | 27 | Delayed | 18 | 16/01/2023 | 31/03/2025 | 13/09/2024 | 24/07/2023 | 184.1 | 184.1
103 | Hirapur Piped Water Supply Scheme (SM/12418) | SM/12418 | 902.58 | 1423 | NEW | 28 | Delayed | 23 | 13/09/2022 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 210.23 | 210.23
104 | Pratappur Piped Water Supply Scheme. (SM/15019) | SM/15019 | 963.17 | 1828 | NEW | 28 | Delayed | 16 | 04/02/2023 | 31/03/2025 | 13/11/2024 | 24/07/2023 | 157.89 | 157.89
105 | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17241) | SM/17241 | 499.85 | 150 | AUGMENTATION | 28 | Delayed | 16 | 15/03/2023 | 31/12/2025 | 31/08/2024 | 18/07/2023 | 81.16 | 81.16
106 | Dhula Danga Piped Water Supply Scheme (SM/14176) | SM/14176 | 1163.2 | 2331 | NEW | 28 | Delayed | 14 | 09/01/2023 | 31/08/2025 | 05/12/2024 | 24/07/2023 | 166.82 | 166.82
107 | Nandagram Piped Water Supply Scheme (SM/14248) | SM/14248 | 1465.27 | 3132 | NEW | 28 | Delayed | 24 | 16/01/2023 | 31/03/2025 | 16/12/2024 | 24/07/2023 | 348.03 | 348.03
108 | Basantapur Piped Water Supply Scheme (SM/12424) | SM/12424 | 882.95 | 2052 | NEW | 28 | Delayed | 20 | 13/09/2022 | 31/03/2025 | 14/11/2024 | 21/02/2023 | 176.33 | 176.33
109 | Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura. (SM/18043) | SM/18043 | 672.83 | 1508 | NEW | 29 | Delayed | 20 | 17/03/2023 | 31/03/2025 | 19/11/2024 | 01/08/2023 | 132.79 | 132.79
110 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME (SM/15001) | SM/15001 | 395.06 | 1025 | AUGMENTATION | 29 | Delayed | 23 | 04/02/2023 | 31/12/2025 | 24/07/2024 | 24/05/2022 | 90.47 | 90.47
111 | Augmentation of Kotulpur Piped Water Supply Scheme. (SM/09981) | SM/09981 | 842.25 | 4060 | AUGMENTATION | 29 | Delayed | 58 | 16/12/2021 | 28/02/2025 | 02/12/2024 | 10/05/2022 | 487.35 | 487.35
112 | MINI PIPED WATER SUPPLY SCHEME FOR NATSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10969) | SM/10969 | 40.52 | 76 | NEW | 30 | Delayed | 54 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.69 | 21.69
113 | Nabasan Piped Water Supply Scheme (SM/13874) | SM/13874 | 925.26 | 1528 | NEW | 30 | Delayed | 20 | 25/11/2022 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 185.15 | 185.15
114 | MINI PIPED WATER SUPPLY SCHEME FOR BHULUI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10959) | SM/10959 | 36.71 | 628 | NEW | 30 | Delayed | 59 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.59 | 21.59
115 | MINI PIPED WATER SUPPLY SCHEME FOR KANAIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11201) | SM/11201 | 39.05 | 59 | NEW | 30 | Delayed | 27 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 10.65 | 10.65
116 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/B WATER SUPPLY SCHEME (SM/15002) | SM/15002 | 447.46 | 1004 | AUGMENTATION | 30 | Delayed | 14 | 04/02/2023 | 31/12/2025 | 04/12/2024 | 24/05/2022 | 63.64 | 63.64
117 | Rautkhanda Piped Water Supply Scheme (SM/14524) | SM/14524 | 1442.11 | 3461 | NEW | 30 | Delayed | 14 | 30/01/2023 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 206.39 | 197.66
118 | MINI PIPED WATER SUPPLY SCHEME FOR SIAKULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11128) | SM/11128 | 40.44 | 65 | NEW | 30 | Delayed | 52 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.18 | 21.18
119 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11122) | SM/11122 | 36.96 | 198 | NEW | 30 | Delayed | 29 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 10.65 | 10.65
120 | MINI PIPED WATER SUPPLY SCHEME FOR BENAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10958) | SM/10958 | 36.21 | 44 | NEW | 30 | Delayed | 60 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.69 | 21.69
121 | MINI PIPED WATER SUPPLY SCHEME FOR NABASHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10962) | SM/10962 | 37.46 | 49 | NEW | 30 | Delayed | 35 | 30/05/2022 | 31/07/2024 | 16/02/2024 | 03/08/2022 | 13.27 | 13.27
122 | MINI PIPED WATER SUPPLY SCHEME FOR BANKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13274) | SM/13274 | 41.69 | 52 | NEW | 30 | Delayed | 38 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 15.91 | 15.91
123 | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. (SM/17297) | SM/17297 | 869.82 | 350 | AUGMENTATION | 31 | Delayed | 5 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 07/09/2022 | 39.72 | 39.72
124 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) (SM/11678) | SM/11678 | 39.88 | 236 | NEW | 31 | Delayed | 27 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 10.66 | 10.66
125 | Deshra Piped Water Supply Scheme (SM/14246) | SM/14246 | 1591.82 | 3339 | NEW | 31 | Delayed | 18 | 16/01/2023 | 30/06/2025 | 20/12/2024 | 24/07/2023 | 287 | 287
126 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chakchuamasina, House Hold No.: 75) (SM/11675) | SM/11675 | 39.88 | 75 | NEW | 31 | Delayed | 27 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 10.66 | 10.66
127 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha (SM/07349) | SM/07349 | 95.93 | 1050 | RETROFITTING | 31 | Delayed | 11 | 11/12/2020 | 31/03/2025 | 12/02/2024 | 04/02/2021 | 10.72 | 10.72
128 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. (SM/10292) | SM/10292 | 3658.45 | 5831 | AUGMENTATION | 32 | Delayed | 34 | 28/02/2022 | 31/12/2025 | 12/11/2024 | 10/08/2021 | 1252.23 | 1252.23
129 | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17695) | SM/17695 | 681.6 | 653 | AUGMENTATION | 32 | Delayed | 9 | 17/03/2023 | 30/04/2025 | 30/11/2024 | 06/11/2023 | 60.77 | 60.77
130 | Salkhara Piped Water Supply Scheme (SM/14003) | SM/14003 | 462.35 | 812 | NEW | 32 | Delayed | 20 | 05/12/2022 | 31/08/2025 | 05/12/2024 | 17/04/2023 | 93.86 | 93.86
131 | Pankhai Piped Water Supply Scheme (SM/12427) | SM/12427 | 825.44 | 1742 | NEW | 32 | Delayed | 34 | 13/09/2022 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 282.01 | 282.01
132 | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme (SM/18424) | SM/18424 | 1092.92 | 330 | AUGMENTATION | 32 | Delayed | 7 | 18/07/2023 | 31/03/2025 | 04/12/2024 | 24/08/2023 | 78.42 | 78.42
133 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Ramnagar, House Hold No.: 88) (SM/11671) | SM/11671 | 39.88 | 383 | NEW | 33 | Delayed | 27 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 10.66 | 10.66
134 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 53) (SM/11672) | SM/11672 | 39.88 | 496 | NEW | 33 | Delayed | 67 | 30/05/2022 | 15/12/2024 | 19/04/2024 | 03/08/2022 | 26.58 | 26.58
135 | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16970) | SM/16970 | 488.77 | 500 | AUGMENTATION | 33 | Delayed | 21 | 16/03/2023 | 31/08/2025 | 20/12/2024 | 13/07/2023 | 103.77 | 103.77
136 | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. (SM/17577) | SM/17577 | 468.23 | 254 | NEW | 35 | Delayed | 24 | 18/03/2023 | 31/10/2025 | 02/12/2024 | 13/07/2023 | 110.74 | 110.74
137 | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17249) | SM/17249 | 220.71 | 757 | AUGMENTATION | 35 | Delayed | 12 | 15/03/2023 | 31/03/2025 | 30/08/2024 | 30/03/2023 | 26.63 | 26.63
138 | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA (SM/18040) | SM/18040 | 357.67 | 804 | NEW | 35 | Delayed | 47 | 17/03/2023 | 31/03/2025 | 20/12/2024 | 01/09/2023 | 168.35 | 168.35
139 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su (SM/09524) | SM/09524 | 142.09 | 1759 | RETROFITTING | 36 | Delayed | 25 | 19/11/2021 | 31/12/2024 | 20/07/2024 | 31/12/2021 | 36.18 | 36.18
140 | Augmentation of Betanal Zone-B Water Supply Scheme (SM/17418) | SM/17418 | 386.52 | 222 | AUGMENTATION | 36 | Delayed | 11 | 18/03/2023 | 31/03/2025 | 02/12/2024 | 13/07/2023 | 42.15 | 42.15
141 | Lankajol Piped Water Supply Scheme. (SM/15022) | SM/15022 | 999.38 | 2546 | NEW | 36 | Delayed | 12 | 04/02/2023 | 31/08/2025 | 16/12/2024 | 24/07/2023 | 122.73 | 117.17
142 | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17711) | SM/17711 | 464.57 | 245 | AUGMENTATION | 37 | Delayed | 13 | 17/03/2023 | 28/02/2025 | 04/12/2024 | 11/05/2023 | 62.6 | 62.6
143 | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16972) | SM/16972 | 601.7 | 100 | AUGMENTATION | 37 | Delayed | 21 | 16/03/2023 | 31/12/2025 | 31/08/2024 | 11/04/2023 | 128.59 | 128.59
144 | Augmentation of Akui Zone-A Water Supply Scheme (SM/16943) | SM/16943 | 228.16 | 250 | AUGMENTATION | 37 | Delayed | 28 | 16/03/2023 | 15/01/2025 | 28/11/2024 | 13/07/2023 | 64.52 | 64.52
145 | Basudebpur Piped Water Supply Scheme. (SM/16944) | SM/16944 | 880.89 | 2156 | NEW | 37 | Delayed | 21 | 16/03/2023 | 31/03/2025 | 03/12/2024 | 17/04/2023 | 180.65 | 171.66
146 | Patsol Piped Water Supply Scheme (SM/14011) | SM/14011 | 251.67 | 122 | NEW | 37 | Delayed | 21 | 05/12/2022 | 31/03/2025 | 03/12/2024 | 24/07/2023 | 52.24 | 52.24
147 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 (SM/09522) | SM/09522 | 101.77 | 1047 | RETROFITTING | 38 | Delayed | 42 | 19/11/2021 | 31/12/2024 | 12/02/2024 | 18/02/2022 | 42.97 | 42.97
148 | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/16984) | SM/16984 | 500.19 | 470 | AUGMENTATION | 38 | Delayed | 19 | 16/03/2023 | 31/03/2025 | 04/12/2024 | 13/07/2023 | 97.37 | 97.37
149 | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. (SM/12380) | SM/12380 | 664.39 | 1259 | AUGMENTATION | 38 | Delayed | 45 | 13/09/2022 | 31/03/2025 | 20/12/2024 | 06/01/2022 | 297.16 | 297.16
150 | Ranpur Piped Water Supply Scheme (SM/14519) | SM/14519 | 1534.45 | 3789 | NEW | 39 | Delayed | 13 | 30/01/2023 | 31/03/2025 | 03/12/2024 | 24/07/2023 | 205.99 | 196.14
151 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME (SM/15003) | SM/15003 | 656.7 | 1800 | AUGMENTATION | 39 | Delayed | 27 | 04/02/2023 | 31/12/2025 | 25/09/2024 | 24/05/2022 | 175.4 | 175.4
152 | MINI PIPED WATER SUPPLY SCHEME FOR KELERA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10894) | SM/10894 | 42.76 | 75 | NEW | 40 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.6 | 29.6
153 | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10978) | SM/10978 | 39.98 | 63 | NEW | 40 | Delayed | 82 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.76 | 32.76
154 | Jamkuri Piped Water Supply Scheme (SM/14007) | SM/14007 | 950.14 | 1905 | NEW | 40 | Delayed | 20 | 05/12/2022 | 31/08/2025 | 30/11/2024 | 24/07/2023 | 189.62 | 189.62
155 | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA (SM/18039) | SM/18039 | 624.98 | 1400 | NEW | 40 | Delayed | 15 | 17/03/2023 | 31/03/2025 | 20/12/2024 | 24/07/2023 | 91.8 | 91.8
156 | Binod Nagar Piped Water Supply Scheme (SM/18340) | SM/18340 | 1113.09 | 2682 | NEW | 40 | Delayed | 14 | 04/07/2023 | 31/08/2025 | 16/12/2024 | 24/07/2023 | 155.28 | 155.28
157 | MINI PIPED WATER SUPPLY SCHEME FOR BIRBHANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11111) | SM/11111 | 37.66 | 53 | NEW | 40 | Delayed | 70 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 26.44 | 26.44
158 | MINI PIPED WATER SUPPLY SCHEME FOR GHOLKURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11031) | SM/11031 | 36.71 | 46 | NEW | 40 | Delayed | 46 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 16.96 | 16.96
159 | Construction of Grid-Connected solar photo -voltaic system for Chhoto Birbhanpur PWSS scheme Dist Bankura (SM/17239) | SM/17239 | 11.26 | 0 | SOLARISATION | 40 | Delayed | 0 | 15/03/2023 | 31/12/2024 | 17/05/2024 | 17/04/2023 | 0 | 0
160 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10988) | SM/10988 | 41.37 | 69 | NEW | 40 | Delayed | 51 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.18 | 21.06
161 | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11113) | SM/11113 | 42.08 | 84 | NEW | 40 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 19.07 | 19.07
162 | MINI PIPED WATER SUPPLY SCHEME FOR NISCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10972) | SM/10972 | 43.25 | 90 | NEW | 40 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.72 | 29.72
163 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Chhota Narayanpur, Household-24) (SM/11407) | SM/11407 | 39.11 | 24 | NEW | 40 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
164 | MINI PIPED WATER SUPPLY SCHEME FOR KUSUM KHUNDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11114) | SM/11114 | 42.08 | 84 | NEW | 40 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 19.07 | 19.07
165 | Ramnagar Piped Water Supply Scheme (SM/14005) | SM/14005 | 991.65 | 2116 | NEW | 40 | Delayed | 23 | 05/12/2022 | 31/08/2025 | 30/11/2024 | 24/04/2023 | 230.65 | 230.65
166 | MINI PIPED WATER SUPPLY SCHEME FOR BENAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13251) | SM/13251 | 37.89 | 54 | NEW | 40 | Delayed | 63 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.8 | 23.8
167 | MINI PIPED WATER SUPPLY SCHEME FOR PHULJHOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11027) | SM/11027 | 35.46 | 41 | NEW | 40 | Delayed | 54 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 19.07 | 19.07
168 | MINI PIPED WATER SUPPLY SCHEME FOR RADHANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10980) | SM/10980 | 40.72 | 77 | NEW | 40 | Delayed | 73 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.72 | 29.72
169 | Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura (SM/15330) | SM/15330 | 366.53 | 0 | SOLARISATION | 40 | Delayed | 0 | 09/02/2023 | 31/12/2024 | 14/06/2024 | 17/08/2023 | 0 | 0
170 | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17705) | SM/17705 | 271.86 | 630 | AUGMENTATION | 40 | Delayed | 44 | 17/03/2023 | 31/12/2025 | 30/08/2024 | 27/07/2023 | 120.14 | 120.14
171 | MINI PIPED WATER SUPPLY SCHEME FOR KHATA-AM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11119) | SM/11119 | 40.72 | 290 | NEW | 40 | Delayed | 65 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 26.44 | 26.44
172 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goppdanga, House Hold:36) (SM/11429) | SM/11429 | 38.91 | 36 | NEW | 40 | Delayed | 41 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 15.91 | 15.91
173 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10868) | SM/10868 | 32.83 | 29 | NEW | 40 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.32 | 21.3
174 | MINI PIPED WATER SUPPLY SCHEME FOR KHATANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13270) | SM/13270 | 32.83 | 43 | NEW | 40 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 24.33 | 24.33
175 | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. (SM/16697) | SM/16697 | 598.58 | 1277 | NEW | 40 | Delayed | 8 | 14/03/2023 | 31/08/2025 | 11/12/2024 | 01/08/2023 | 46.52 | 46.52
176 | Kaktia Piped Water Supply Scheme. (SM/16701) | SM/16701 | 964.45 | 2145 | NEW | 41 | Delayed | 21 | 14/03/2023 | 31/03/2025 | 28/11/2024 | 24/07/2023 | 200.02 | 195.22
177 | Augmentation of Akui Zone-B Water Supply Scheme (SM/17228) | SM/17228 | 332.35 | 143 | AUGMENTATION | 41 | Delayed | 42 | 15/03/2023 | 15/02/2025 | 28/11/2024 | 28/07/2023 | 138.31 | 138.31
178 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. (SM/10295) | SM/10295 | 1828.18 | 2522 | AUGMENTATION | 41 | Delayed | 40 | 28/02/2022 | 31/12/2025 | 24/07/2024 | 17/04/2023 | 736.71 | 736.71
179 | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) (SM/17432) | SM/17432 | 436.2 | 180 | AUGMENTATION | 41 | Delayed | 8 | 18/03/2023 | 31/03/2025 | 04/12/2024 | 30/03/2023 | 35.6 | 35.6
180 | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17730) | SM/17730 | 449.24 | 260 | AUGMENTATION | 41 | Delayed | 11 | 17/03/2023 | 31/03/2025 | 04/12/2024 | 24/08/2023 | 47.98 | 47.98
181 | Augmentation of Dhengasole Water Supply Scheme (SM/17699) | SM/17699 | 323.64 | 448 | AUGMENTATION | 42 | Delayed | 28 | 17/03/2023 | 31/01/2025 | 29/11/2024 | 24/07/2023 | 90.96 | 90.96
182 | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) (SM/17430) | SM/17430 | 457.56 | 310 | AUGMENTATION | 42 | Delayed | 11 | 18/03/2023 | 31/03/2025 | 04/12/2024 | 17/03/2023 | 51.22 | 51.22
183 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME (SM/16936) | SM/16936 | 466.25 | 1106 | AUGMENTATION | 42 | Delayed | 19 | 16/03/2023 | 31/12/2025 | 20/12/2024 | 22/05/2023 | 89.32 | 89.32
184 | Augmentation of Chuamasina Zone-A Water Supply Scheme (SM/17696) | SM/17696 | 390.83 | 410 | AUGMENTATION | 42 | Delayed | 25 | 17/03/2023 | 31/03/2025 | 02/12/2024 | 24/07/2023 | 98.13 | 98.13
185 | MINI PIPED WATER SUPPLY SCHEME FOR SIMCHAKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10952) | SM/10952 | 41.69 | 82 | NEW | 42 | Delayed | 46 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
186 | MINI PIPED WATER SUPPLY SCHEME FOR JAVI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11121) | SM/11121 | 43.65 | 0 | NEW | 42 | Delayed | 61 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 26.44 | 26.44
187 | Construction of Grid-Connected solar photo -voltaic system for Nabakishor PWSS scheme Dist Bankura (SM/15316) | SM/15316 | 11.26 | 0 | SOLARISATION | 42 | Delayed | 0 | 09/02/2023 | 31/03/2024 | 27/02/2024 | 23/03/2023 | 0 | 0
188 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME (SM/16261) | SM/16261 | 509.65 | 1415 | AUGMENTATION | 42 | Delayed | 23 | 24/02/2023 | 31/12/2025 | 27/08/2024 | 24/05/2022 | 115.12 | 115.12
189 | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17434) | SM/17434 | 632.28 | 215 | AUGMENTATION | 42 | Delayed | 14 | 18/03/2023 | 30/04/2025 | 20/12/2024 | 27/07/2023 | 85.94 | 42.26
190 | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. (SM/17578) | SM/17578 | 490.58 | 586 | NEW | 43 | Delayed | 19 | 18/03/2023 | 30/04/2025 | 30/11/2024 | 14/08/2023 | 93.54 | 93.54
191 | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17731) | SM/17731 | 484.18 | 280 | AUGMENTATION | 44 | Delayed | 26 | 17/03/2023 | 28/02/2025 | 20/12/2024 | 17/03/2023 | 123.84 | 87.41
192 | Construction of Grid-Connected solar photo -voltaic system for Patrasayer PWSS scheme Dist Bankura (SM/15313) | SM/15313 | 8.35 | 0 | SOLARISATION | 44 | Delayed | 0 | 09/02/2023 | 31/10/2024 | 10/05/2024 | 23/03/2023 | 0 | 0
193 | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) (SM/17254) | SM/17254 | 571.7 | 400 | AUGMENTATION | 44 | Delayed | 13 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 30/03/2023 | 74.08 | 74.08
194 | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17304) | SM/17304 | 485.66 | 260 | AUGMENTATION | 44 | Delayed | 16 | 15/03/2023 | 31/03/2025 | 20/12/2024 | 17/03/2023 | 76.64 | 76.64
195 | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas (SM/09879) | SM/09879 | 416.45 | 1358 | AUGMENTATION | 44 | Delayed | 22 | 08/12/2021 | 31/12/2024 | 30/08/2024 | 27/09/2022 | 93.04 | 93.04
196 | Augmentation of Benda water supply scheme (SM/17244) | SM/17244 | 273.28 | 80 | AUGMENTATION | 44 | Delayed | 28 | 15/03/2023 | 31/01/2025 | 29/11/2024 | 19/07/2023 | 76.37 | 73.69
197 | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17729) | SM/17729 | 459.25 | 600 | AUGMENTATION | 44 | Delayed | 22 | 17/03/2023 | 31/03/2025 | 20/12/2024 | 02/06/2023 | 101.51 | 101.51
198 | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17292) | SM/17292 | 752.47 | 210 | AUGMENTATION | 45 | Delayed | 15 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 18/07/2023 | 116.49 | 116.49
199 | Mathurabati Piped Water Supply Scheme (SM/12417) | SM/12417 | 691.64 | 1001 | NEW | 45 | Delayed | 13 | 13/09/2022 | 31/03/2025 | 16/12/2024 | 04/05/2023 | 89.35 | 89.35
200 | Construction of Grid-Connected solar photo -voltaic system for Sarenga PWSS scheme Dist Bankura (SM/15317) | SM/15317 | 42.2 | 0 | SOLARISATION | 45 | Delayed | 0 | 09/02/2023 | 31/01/2025 | 21/06/2024 | 17/04/2023 | 0 | 0
201 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME (SM/18495) | SM/18495 | 1126 | 3991 | AUGMENTATION | 45 | Delayed | 4 | 26/07/2023 | 31/12/2025 | 20/12/2024 | 14/08/2023 | 48.23 | 48.23
202 | MINI PIPED WATER SUPPLY SCHEME FOR CHHATRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10984) | SM/10984 | 40.91 | 67 | NEW | 45 | Delayed | 58 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.81 | 23.81
203 | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10916) | SM/10916 | 43.84 | 93 | NEW | 45 | Delayed | 55 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.92 | 23.92
204 | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11018) | SM/11018 | 40.52 | 76 | NEW | 45 | Delayed | 65 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.33 | 26.33
205 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME (SM/16935) | SM/16935 | 999.97 | 3815 | AUGMENTATION | 45 | Delayed | 17 | 16/03/2023 | 31/12/2025 | 20/12/2024 | 24/05/2023 | 172.41 | 172.41
206 | Ghora Danga Piped Water Supply Scheme (SM/18611) | SM/18611 | 1085.31 | 2413 | NEW | 45 | Delayed | 25 | 31/07/2023 | 30/06/2025 | 20/12/2024 | 14/08/2023 | 269.21 | 269.21
207 | Ground water based Diga pipe water supply scheme, under Bankura Division, Block -Onda, Dist - Bankura. (SM/11923) | SM/11923 | 541.12 | 1133 | NEW | 45 | Delayed | 24 | 22/08/2022 | 31/10/2025 | 02/12/2024 | 17/03/2023 | 129.55 | 129.55
208 | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. (SM/15260) | SM/15260 | 168.45 | 0 | SUPPORT-WQMSP | 45 | Delayed | 0 | 06/02/2023 | 30/09/2024 | 16/02/2024 | 18/04/2022 | 0 | 0
209 | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17260) | SM/17260 | 436.62 | 120 | AUGMENTATION | 46 | Delayed | 7 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 17/03/2023 | 31.92 | 31.92
210 | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA (SM/17227) | SM/17227 | 766.66 | 2517 | NEW | 47 | Delayed | 24 | 15/03/2023 | 31/03/2025 | 20/12/2024 | 12/09/2023 | 185.58 | 185.58
211 | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). (SM/17262) | SM/17262 | 348.2 | 260 | AUGMENTATION | 47 | Delayed | 7 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 14/08/2023 | 24.28 | 24.28
212 | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. (SM/17231) | SM/17231 | 654.57 | 966 | NEW | 47 | Delayed | 31 | 15/03/2023 | 31/05/2025 | 28/11/2024 | 01/08/2023 | 200.08 | 200.08
213 | Telrui Piped Water Supply Scheme (SM/13711) | SM/13711 | 674.44 | 950 | NEW | 47 | Delayed | 26 | 14/11/2022 | 30/07/2025 | 04/12/2024 | 24/07/2023 | 173.57 | 173.57
214 | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17123) | SM/17123 | 230.53 | 544 | AUGMENTATION | 48 | Delayed | 29 | 16/03/2023 | 31/03/2025 | 25/11/2024 | 14/08/2023 | 67.19 | 42.49
215 | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17694) | SM/17694 | 473.96 | 680 | AUGMENTATION | 48 | Delayed | 37 | 17/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 174.4 | 174.4
216 | Banna Piped Water Supply Scheme (SM/14525) | SM/14525 | 1424.34 | 3405 | NEW | 48 | Delayed | 22 | 30/01/2023 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 316.82 | 316.82
217 | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17295) | SM/17295 | 790.33 | 325 | AUGMENTATION | 48 | Delayed | 17 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 27/07/2023 | 131.1 | 52.54
218 | Makarandapur Piped Water Supply Scheme (SM/14520) | SM/14520 | 1153.54 | 2105 | NEW | 48 | Delayed | 18 | 30/01/2023 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 201.98 | 201.98
219 | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17702) | SM/17702 | 709.58 | 603 | AUGMENTATION | 48 | Delayed | 38 | 17/03/2023 | 31/03/2025 | 30/08/2024 | 18/07/2023 | 267.94 | 267.94
220 | Augmentation of Rol Zone-B Water Supply Scheme (SM/17683) | SM/17683 | 341.82 | 77 | AUGMENTATION | 48 | Delayed | 27 | 17/03/2023 | 31/01/2025 | 05/12/2024 | 19/07/2023 | 91.82 | 91.82
221 | Augmentation of Kushmuri Zone-B Water Supply Scheme (SM/17682) | SM/17682 | 309.8 | 190 | AUGMENTATION | 49 | Delayed | 28 | 17/03/2023 | 28/02/2025 | 02/12/2024 | 12/09/2023 | 87.83 | 87.83
222 | Hetia Piped Water Supply Scheme (SM/12425) | SM/12425 | 815.5 | 2353 | NEW | 49 | Delayed | 31 | 13/09/2022 | 31/03/2025 | 29/11/2024 | 21/02/2023 | 250.21 | 250.21
223 | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16961) | SM/16961 | 456.92 | 540 | AUGMENTATION | 49 | Delayed | 33 | 16/03/2023 | 31/03/2025 | 24/09/2024 | 27/07/2023 | 150.49 | 150.49
224 | Pathara Piped Water Supply Scheme (SM/14009) | SM/14009 | 510.54 | 721 | NEW | 49 | Delayed | 18 | 05/12/2022 | 31/03/2025 | 03/12/2024 | 04/05/2023 | 91.55 | 91.55
225 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Abantika- 88 , Belthya- 89 & Deuli- 91) of BENDA u (SM/09240) | SM/09240 | 73.17 | 733 | RETROFITTING | 50 | Delayed | 61 | 25/05/2021 | 19/12/2024 | 20/02/2024 | 11/11/2021 | 44.79 | 44.79
226 | MINI PIPED WATER SUPPLY SCHEME FOR JARKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11021) | SM/11021 | 37.89 | 54 | NEW | 50 | Delayed | 58 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 21.81 | 21.81
227 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13250) | SM/13250 | 39.05 | 188 | NEW | 50 | Delayed | 49 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 18.95 | 18.95
228 | Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura (SM/15329) | SM/15329 | 366.53 | 0 | SOLARISATION | 50 | Delayed | 0 | 09/02/2023 | 31/10/2024 | 10/05/2024 | 17/04/2023 | 0 | 0
229 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I) (Part-B) (SM/07368) | SM/07368 | 86.28 | 945 | RETROFITTING | 50 | Delayed | 84 | 11/12/2020 | 30/12/2024 | 20/02/2024 | 25/08/2021 | 72.06 | 69.64
230 | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11199) | SM/11199 | 43.06 | 89 | NEW | 50 | Delayed | 49 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 21.24 | 21.12
231 | MINI PIPED WATER SUPPLY SCHEME FOR BANSHKETYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10885) | SM/10885 | 44.23 | 95 | NEW | 50 | Delayed | 30 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 13.28 | 13.28
232 | MINI PIPED WATER SUPPLY SCHEME FOR INDARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10966) | SM/10966 | 37.89 | 54 | NEW | 50 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 26.33 | 26.33
233 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Baramara-149 & Kulaijuri-134) of CHAK (SM/09638) | SM/09638 | 78.32 | 793 | RETROFITTING | 50 | Delayed | 77 | 24/11/2021 | 17/12/2024 | 20/02/2024 | 29/11/2021 | 60.62 | 60.62
234 | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10951) | SM/10951 | 42.07 | 72 | NEW | 50 | Delayed | 57 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 23.81 | 23.81
235 | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10953) | SM/10953 | 41.69 | 82 | NEW | 50 | Delayed | 46 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
236 | MINI PIPED WATER SUPPLY SCHEME FOR BHEDUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11041) | SM/11041 | 41.11 | 79 | NEW | 50 | Delayed | 52 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 21.18 | 21.18
237 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNABATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11060) | SM/11060 | 31.76 | 25 | NEW | 50 | Delayed | 68 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 21.71 | 21.71
238 | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11062) | SM/11062 | 37.21 | 121 | NEW | 50 | Delayed | 55 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 20.53 | 20.53
239 | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10977) | SM/10977 | 44.04 | 94 | NEW | 50 | Delayed | 74 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.76 | 32.76
240 | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura (SM/18036) | SM/18036 | 799.22 | 1120 | AUGMENTATION | 50 | Delayed | 40 | 17/03/2023 | 31/05/2025 | 30/11/2024 | 01/06/2023 | 320.41 | 320.41
241 | MINI PIPED WATER SUPPLY SCHEME FOR SABUDAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10954) | SM/10954 | 42.86 | 88 | NEW | 50 | Delayed | 56 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 23.81 | 23.81
242 | MINI PIPED WATER SUPPLY SCHEME FOR MEMOULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11061) | SM/11061 | 33.37 | 31 | NEW | 50 | Delayed | 62 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 20.77 | 20.77
243 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Tentulara-20, Saluka-21, Dharampur-22, (SM/08291) | SM/08291 | 78.23 | 867 | RETROFITTING | 50 | Delayed | 75 | 26/02/2021 | 31/01/2025 | 29/11/2024 | 22/09/2021 | 58.35 | 58.35
244 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Dhabani-136, Chitrang-137, Baliguma-1 (SM/09637) | SM/09637 | 86.89 | 949 | RETROFITTING | 50 | Delayed | 97 | 24/11/2021 | 15/12/2024 | 20/02/2024 | 29/11/2021 | 84.36 | 84.36
245 | MINI PIPED WATER SUPPLY SCHEME FOR BANKATI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10955) | SM/10955 | 40.91 | 78 | NEW | 50 | Delayed | 47 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
246 | MINI PIPED WATER SUPPLY SCHEME FOR CHENCHURYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11046) | SM/11046 | 37.66 | 53 | NEW | 50 | Delayed | 48 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 18.02 | 18.02
247 | MINI PIPED WATER SUPPLY SCHEME FOR NABAGRAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11052) | SM/11052 | 40.72 | 77 | NEW | 50 | Delayed | 65 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 26.44 | 26.44
248 | MINI PIPED WATER SUPPLY SCHEME FOR RADHASHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10849) | SM/10849 | 41.14 | 717 | NEW | 50 | Delayed | 51 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.18 | 21.18
249 | MINI PIPED WATER SUPPLY SCHEME FOR DANGARSAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11025) | SM/11025 | 44.43 | 96 | NEW | 50 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 31.71 | 31.71
250 | MINI PIPED WATER SUPPLY SCHEME FOR JASHODANANDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11047) | SM/11047 | 45.01 | 99 | NEW | 50 | Delayed | 24 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 10.65 | 10.65
251 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 (SM/09239) | SM/09239 | 76.06 | 735 | RETROFITTING | 50 | Delayed | 40 | 25/05/2021 | 19/12/2024 | 20/02/2024 | 26/10/2021 | 30.72 | 30.72
252 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District (SM/08310) | SM/08310 | 295.5 | 7200 | RETROFITTING | 50 | Delayed | 30 | 26/02/2021 | 31/12/2024 | 20/02/2024 | 04/06/2021 | 87.99 | 87.99
253 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10947) | SM/10947 | 44.82 | 98 | NEW | 50 | Delayed | 47 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.06 | 21.06
254 | MINI PIPED WATER SUPPLY SCHEME FOR GOALKPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11040) | SM/11040 | 40.91 | 67 | NEW | 50 | Delayed | 47 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 19.07 | 19.07
255 | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16960) | SM/16960 | 678.24 | 730 | AUGMENTATION | 50 | Delayed | 11 | 16/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 77.18 | 77.18
256 | Brindabanpur Piped Water Supply Scheme (SM/18437) | SM/18437 | 1649.04 | 3614 | NEW | 50 | Delayed | 19 | 18/07/2023 | 31/08/2025 | 16/12/2024 | 24/07/2023 | 320.14 | 316.63
257 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11132) | SM/11132 | 43.84 | 93 | NEW | 50 | Delayed | 36 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 15.92 | 15.92
258 | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10968) | SM/10968 | 38.13 | 55 | NEW | 50 | Delayed | 62 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.8 | 23.8
259 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du (SM/08298) | SM/08298 | 75.69 | 1240 | RETROFITTING | 50 | Delayed | 71 | 26/02/2021 | 31/12/2024 | 20/02/2024 | 26/10/2021 | 53.48 | 53.48
260 | MINI PIPED WATER SUPPLY SCHEME FOR SAHARGHATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11079) | SM/11079 | 34.71 | 38 | NEW | 50 | Delayed | 0 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 0 | 0
261 | MINI PIPED WATER SUPPLY SCHEME FOR BHADULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11065) | SM/11065 | 37.66 | 53 | NEW | 50 | Delayed | 55 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 20.77 | 20.77
262 | MINI PIPED WATER SUPPLY SCHEME FOR BIRUDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13267) | SM/13267 | 36.46 | 45 | NEW | 50 | Delayed | 52 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 19.14 | 19.14
263 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Kenjera-129, Chattrakhanda-130 & Nagatentu (SM/09332) | SM/09332 | 85.14 | 613 | RETROFITTING | 50 | Delayed | 55 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 22/11/2021 | 46.71 | 41.71
264 | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11081) | SM/11081 | 33.37 | 31 | NEW | 50 | Delayed | 48 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 16.12 | 0.12
265 | MINI PIPED WATER SUPPLY SCHEME FOR DHANDORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10961) | SM/10961 | 32.3 | 27 | NEW | 50 | Delayed | 74 | 30/05/2022 | 31/07/2024 | 12/02/2024 | 03/08/2022 | 23.8 | 23.8
266 | MINI PIPED WATER SUPPLY SCHEME FOR TALTALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11044) | SM/11044 | 42.07 | 72 | NEW | 50 | Delayed | 63 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 26.44 | 26.44
267 | MINI PIPED WATER SUPPLY SCHEME FOR SUSHUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11034) | SM/11034 | 31.76 | 25 | NEW | 50 | Delayed | 74 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 23.44 | 23.44
268 | MINI PIPED WATER SUPPLY SCHEME FOR BHALAIDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10948) | SM/10948 | 31.76 | 25 | NEW | 50 | Delayed | 60 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
269 | MINI PIPED WATER SUPPLY SCHEME FOR BHADLI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11024) | SM/11024 | 42.47 | 86 | NEW | 50 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 21.81 | 21.81
270 | MINI PIPED WATER SUPPLY SCHEME FOR BAHARAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11075) | SM/11075 | 31.49 | 24 | NEW | 50 | Delayed | 46 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 14.62 | 12.12
271 | MINI PIPED WATER SUPPLY SCHEME FOR MURRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13253) | SM/13253 | 39.29 | 60 | NEW | 50 | Delayed | 61 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.8 | 23.8
272 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Bamania-113) of Betanal (Zone - B) under In (SM/09331) | SM/09331 | 92.06 | 753 | RETROFITTING | 50 | Delayed | 43 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 08/10/2020 | 40 | 39.78
273 | MINI PIPED WATER SUPPLY SCHEME FOR BHABANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10965) | SM/10965 | 41.37 | 651 | NEW | 50 | Delayed | 48 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 20.01 | 20.01
274 | MINI PIPED WATER SUPPLY SCHEME FOR BAMUN PATHRI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11070) | SM/11070 | 42.47 | 86 | NEW | 50 | Delayed | 53 | 30/05/2022 | 31/08/2024 | 23/07/2024 | 03/08/2022 | 22.35 | 22.35
275 | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. (SM/15258) | SM/15258 | 60.18 | 0 | SUPPORT-WQMSP | 50 | Delayed | 0 | 06/02/2023 | 31/08/2024 | 16/02/2024 | 08/06/2023 | 0 | 0
276 | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11129) | SM/11129 | 36.21 | 44 | NEW | 51 | Delayed | 47 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 17.08 | 17.08
277 | Augmentation of Sashpur Zone-A Water Supply Scheme (SM/18114) | SM/18114 | 361.86 | 340 | AUGMENTATION | 51 | Delayed | 36 | 18/03/2023 | 15/01/2025 | 28/11/2024 | 13/07/2023 | 130.7 | 130.7
278 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. (SM/09477) | SM/09477 | 197.45 | 2435 | RETROFITTING | 51 | Delayed | 56 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 30/12/2021 | 110.55 | 109.28
279 | Danna Piped Water Supply Scheme. (SM/18302) | SM/18302 | 1305.29 | 3100 | NEW | 51 | Delayed | 33 | 26/06/2023 | 31/08/2025 | 16/12/2024 | 04/05/2023 | 431.03 | 431.03
280 | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17251) | SM/17251 | 455.28 | 230 | AUGMENTATION | 51 | Delayed | 8 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 25/05/2023 | 37.08 | 37.08
281 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde (SM/08297) | SM/08297 | 84.54 | 1421 | RETROFITTING | 51 | Delayed | 97 | 26/02/2021 | 31/12/2024 | 20/02/2024 | 23/09/2021 | 82.07 | 82.07
282 | Dhagaria Piped Water Supply Scheme (SM/15023) | SM/15023 | 908 | 1851 | NEW | 51 | Delayed | 28 | 04/02/2023 | 31/08/2025 | 30/11/2024 | 24/04/2023 | 256.11 | 256.11
283 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Anchuri, Dhulkumari, Patha (SM/07249) | SM/07249 | 85.75 | 920 | RETROFITTING | 51 | Delayed | 52 | 08/12/2020 | 31/03/2025 | 11/02/2024 | 19/02/2021 | 44.68 | 44.68
284 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Nangalbhanga-18, Chwak Chuamosina-19, B (SM/09308) | SM/09308 | 67.34 | 807 | RETROFITTING | 51 | Delayed | 83 | 08/11/2021 | 05/12/2024 | 22/02/2024 | 16/11/2021 | 55.84 | 55.43
285 | MINI PIPED WATER SUPPLY SCHEME FOR TILABAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11035) | SM/11035 | 30.68 | 21 | NEW | 52 | Delayed | 43 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 13.28 | 13.28
286 | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme (SM/17707) | SM/17707 | 675.82 | 320 | AUGMENTATION | 52 | Delayed | 8 | 17/03/2023 | 31/03/2025 | 20/12/2024 | 28/03/2023 | 53.89 | 53.89
287 | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. (SM/18044) | SM/18044 | 379.09 | 564 | NEW | 52 | Delayed | 40 | 17/03/2023 | 31/03/2025 | 20/12/2024 | 27/07/2023 | 151.42 | 151.42
288 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) (SM/07371) | SM/07371 | 78.33 | 1094 | RETROFITTING | 52 | Delayed | 97 | 11/12/2020 | 31/12/2024 | 20/02/2024 | 01/12/2021 | 76.05 | 76.05
289 | Augmentation of Amrul Zone-B Water Supply Scheme (SM/17230) | SM/17230 | 314.92 | 50 | AUGMENTATION | 52 | Delayed | 32 | 15/03/2023 | 31/01/2025 | 29/11/2024 | 13/07/2023 | 101.93 | 101.93
290 | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u (SM/18390) | SM/18390 | 2538.24 | 6421 | AUGMENTATION | 52 | Delayed | 31 | 11/07/2023 | 31/03/2025 | 04/12/2024 | 14/08/2023 | 774.62 | 774.62
291 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME (SM/14091) | SM/14091 | 816.64 | 2305 | AUGMENTATION | 52 | On track | 3 | 12/12/2022 | 31/12/2025 | 04/12/2024 | 24/05/2022 | 20.86 | 20.86
292 | Augmentation works for Lakshmanpur (Zone L) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17313) | SM/17313 | 347.79 | 1025 | AUGMENTATION | 52 | On track | 25 | 15/03/2023 | 31/12/2025 | 30/08/2024 | 18/07/2023 | 88.68 | 88.68
293 | Augmentation of Chakuparsole Zone-B Water Supply Scheme (SM/17426) | SM/17426 | 357.24 | 172 | AUGMENTATION | 52 | Delayed | 16 | 18/03/2023 | 31/03/2025 | 29/11/2024 | 28/07/2023 | 55.38 | 55.38
294 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Mamudpur-124, Barabaikunthapur-125, Habish (SM/08294) | SM/08294 | 80.95 | 549 | RETROFITTING | 52 | Delayed | 52 | 26/02/2021 | 31/12/2024 | 02/12/2024 | 23/09/2021 | 42.21 | 42.21
295 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). (SM/17441) | SM/17441 | 226.63 | 367 | AUGMENTATION | 52 | Delayed | 9 | 18/03/2023 | 25/02/2025 | 30/11/2024 | 08/02/2024 | 20.61 | 20.61
296 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Ajodhya (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Sancha - 6,Patalpur -8, Loharara - 9, Ajodhya -10 (SM/09326) | SM/09326 | 291.93 | 3096 | RETROFITTING | 52 | Delayed | 58 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 12/05/2022 | 168.44 | 168.44
297 | MINI PIPED WATER SUPPLY SCHEME FOR BANSNALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10957) | SM/10957 | 42.3 | 73 | NEW | 52 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
298 | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). (SM/16950) | SM/16950 | 246.4 | 80 | AUGMENTATION | 52 | Delayed | 32 | 16/03/2023 | 31/03/2025 | 31/08/2024 | 11/04/2023 | 79.8 | 79.8
299 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) (Part-A) (SM/07352) | SM/07352 | 99.63 | 121 | RETROFITTING | 53 | Delayed | 84 | 11/12/2020 | 28/12/2024 | 20/02/2024 | 18/09/2020 | 83.47 | 83.47
300 | Madhab Bati Piped Water Supply Scheme (SM/14522) | SM/14522 | 1157.88 | 2974 | NEW | 53 | Delayed | 13 | 30/01/2023 | 31/03/2025 | 29/11/2024 | 21/02/2023 | 150.25 | 150.25
301 | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' (SM/17700) | SM/17700 | 262.44 | 310 | AUGMENTATION | 53 | Delayed | 35 | 17/03/2023 | 31/03/2025 | 30/11/2024 | 11/04/2023 | 91.46 | 91.46
302 | Augmentation of Kushmuri Zone-A Water Supply Scheme (SM/17420) | SM/17420 | 288.97 | 55 | AUGMENTATION | 53 | Delayed | 27 | 18/03/2023 | 31/03/2025 | 02/12/2024 | 28/07/2023 | 77.18 | 77.18
303 | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). (SM/17303) | SM/17303 | 285.68 | 480 | AUGMENTATION | 53 | Delayed | 9 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 01/09/2023 | 24.64 | 24.64
304 | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas (SM/09924) | SM/09924 | 874.28 | 3432 | AUGMENTATION | 53 | Delayed | 33 | 10/12/2021 | 30/06/2025 | 20/12/2024 | 13/04/2022 | 288.03 | 288.03
305 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Layak Bandh - 13 & Chua Masina - 17) of (SM/09321) | SM/09321 | 210.06 | 2202 | RETROFITTING | 53 | Delayed | 97 | 08/11/2021 | 05/12/2024 | 22/02/2024 | 31/12/2021 | 203.94 | 203.41
306 | MINI PIPED WATER SUPPLY SCHEME FOR PAINADA MODARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11036) | SM/11036 | 34.45 | 35 | NEW | 53 | Delayed | 54 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 18.55 | 18.55
307 | Augmentation of Rol Zone-A Water Supply Scheme (SM/17693) | SM/17693 | 165.71 | 50 | AUGMENTATION | 53 | Delayed | 49 | 17/03/2023 | 31/01/2025 | 16/12/2024 | 28/07/2023 | 81.74 | 81.74
308 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME (SM/15007) | SM/15007 | 362.07 | 565 | AUGMENTATION | 54 | On track | 27 | 04/02/2023 | 31/12/2025 | 20/12/2024 | 24/05/2022 | 96.69 | 96.69
309 | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. (SM/16694) | SM/16694 | 370.23 | 718 | NEW | 54 | Delayed | 19 | 14/03/2023 | 28/02/2025 | 30/11/2024 | 17/03/2023 | 71.64 | 71.64
310 | Augmentation of Sashpur Zone-B Water Supply Scheme (SM/17421) | SM/17421 | 344.8 | 318 | AUGMENTATION | 54 | Delayed | 41 | 18/03/2023 | 15/02/2025 | 28/11/2024 | 13/07/2023 | 142.4 | 142.4
311 | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17433) | SM/17433 | 489.22 | 350 | AUGMENTATION | 54 | Delayed | 14 | 18/03/2023 | 31/05/2025 | 20/12/2024 | 30/03/2023 | 66.44 | 66.44
312 | Construction & commissioning d of FHTC by Retrofitting of completeand commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Kunjapur-112 & Bahalalpur-114) of Betanal (SM/09317) | SM/09317 | 97.49 | 852 | RETROFITTING | 54 | Delayed | 53 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 26/11/2021 | 52.08 | 52.08
313 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) (SM/07271) | SM/07271 | 96.39 | 1029 | RETROFITTING | 54 | Delayed | 94 | 08/12/2020 | 28/12/2024 | 20/02/2024 | 20/01/2021 | 90.54 | 90.54
314 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). (SM/17245) | SM/17245 | 639.01 | 430 | AUGMENTATION | 54 | Delayed | 20 | 15/03/2023 | 31/07/2025 | 11/12/2024 | 18/07/2023 | 127.23 | 127.23
315 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, (SM/09624) | SM/09624 | 139.57 | 1461 | RETROFITTING | 55 | Delayed | 48 | 24/11/2021 | 27/12/2024 | 22/02/2024 | 03/03/2022 | 67.34 | 67.34
316 | MINI PIPED WATER SUPPLY SCHEME FOR BARUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11030) | SM/11030 | 35.71 | 42 | NEW | 55 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 15.91 | 15.91
317 | Kataban Piped Water Supply Scheme (SM/14526) | SM/14526 | 1021.84 | 2234 | NEW | 55 | Delayed | 29 | 30/01/2023 | 31/03/2025 | 16/12/2024 | 21/02/2023 | 296.9 | 296.9
318 | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17252) | SM/17252 | 250.9 | 480 | AUGMENTATION | 55 | Delayed | 6 | 15/03/2023 | 31/03/2025 | 12/11/2024 | 20/03/2023 | 14.02 | 14.02
319 | MINI PIPED WATER SUPPLY SCHEME FOR MALIN DASI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10912) | SM/10912 | 41.37 | 69 | NEW | 55 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 30/08/2024 | 03/08/2022 | 31.71 | 31.71
320 | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17706) | SM/17706 | 255.52 | 275 | AUGMENTATION | 55 | Delayed | 25 | 17/03/2023 | 31/03/2025 | 30/08/2024 | 18/07/2023 | 63.33 | 63.33
321 | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17703) | SM/17703 | 248.23 | 850 | AUGMENTATION | 55 | Delayed | 11 | 17/03/2023 | 31/03/2025 | 30/08/2024 | 11/09/2023 | 27.32 | 27.32
322 | & commissiConstruction oning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Dighalgram-126) of Betanal (Zone - B) under (SM/09322) | SM/09322 | 98.43 | 751 | RETROFITTING | 55 | Delayed | 58 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 16/11/2021 | 57.57 | 57.57
323 | MINI PIPED WATER SUPPLY SCHEME FOR BANPUKHURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11029) | SM/11029 | 34.45 | 35 | NEW | 55 | Delayed | 55 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
324 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-II) (Part-B) (SM/07369) | SM/07369 | 94.58 | 994 | RETROFITTING | 55 | Delayed | 72 | 11/12/2020 | 28/12/2024 | 20/02/2024 | 25/08/2021 | 68 | 67.56
325 | MINI PIPED WATER SUPPLY SCHEME FOR KHAPKATA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10869) | SM/10869 | 36.46 | 887 | NEW | 55 | Delayed | 43 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 15.8 | 15.8
326 | MINI PIPED WATER SUPPLY SCHEME FOR KUMIR PATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10875) | SM/10875 | 36.96 | 47 | NEW | 55 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.81 | 23.81
327 | Bhat Pushkarini Piped Water Supply Scheme (SM/12416) | SM/12416 | 948.65 | 1434 | NEW | 55 | Delayed | 45 | 13/09/2022 | 31/03/2025 | 29/11/2024 | 24/04/2023 | 429.8 | 429.8
328 | Kubir Bandh Piped Water Supply Scheme (SM/14008) | SM/14008 | 724.55 | 1052 | NEW | 55 | Delayed | 26 | 05/12/2022 | 31/03/2025 | 29/11/2024 | 17/04/2023 | 187.34 | 182.64
329 | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11112) | SM/11112 | 37.2 | 51 | NEW | 55 | Delayed | 71 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 26.44 | 26.44
330 | MINI PIPED WATER SUPPLY SCHEME FOR KATAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10950) | SM/10950 | 42.08 | 84 | NEW | 55 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 19.07 | 19.07
331 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) (SM/07374) | SM/07374 | 97.77 | 1298 | RETROFITTING | 55 | Delayed | 69 | 11/12/2020 | 31/12/2024 | 22/02/2024 | 02/06/2023 | 67.23 | 67.23
332 | MINI PIPED WATER SUPPLY SCHEME FOR KALACHANDPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10863) | SM/10863 | 34.18 | 34 | NEW | 55 | Delayed | 62 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.27 | 21.27
333 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina (SM/09521) | SM/09521 | 135.75 | 1510 | RETROFITTING | 56 | Delayed | 32 | 19/11/2021 | 31/12/2024 | 20/07/2024 | 31/12/2021 | 43.6 | 43.6
334 | Naruala Piped Water Supply Scheme (SM/13789) | SM/13789 | 633.32 | 1049 | NEW | 56 | Delayed | 18 | 18/11/2022 | 31/03/2025 | 16/12/2024 | 24/07/2023 | 115.01 | 115.01
335 | Manik Bazar Piped Water Supply Scheme. (SM/16705) | SM/16705 | 565.3 | 1258 | NEW | 56 | Delayed | 13 | 14/03/2023 | 31/03/2025 | 03/12/2024 | 04/05/2023 | 72.15 | 72.15
336 | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA (SM/18038) | SM/18038 | 224.65 | 474 | NEW | 56 | Delayed | 36 | 17/03/2023 | 28/02/2025 | 20/12/2024 | 03/08/2023 | 81.04 | 81.04
337 | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17429) | SM/17429 | 464.58 | 225 | AUGMENTATION | 56 | Delayed | 14 | 18/03/2023 | 31/03/2025 | 20/12/2024 | 25/05/2023 | 64.81 | 64.81
338 | MINI PIPED WATER SUPPLY SCHEME FOR PANCHPUKHURIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10917) | SM/10917 | 42.28 | 85 | NEW | 56 | Delayed | 78 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 32.94 | 32.94
339 | Khundanga Piped Water Supply Scheme (SM/14482) | SM/14482 | 764.18 | 1575 | NEW | 56 | Delayed | 30 | 20/01/2023 | 28/02/2025 | 16/12/2024 | 04/05/2023 | 229.84 | 229.84
340 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of (SM/09619) | SM/09619 | 73.06 | 703 | RETROFITTING | 56 | Delayed | 97 | 24/11/2021 | 15/12/2024 | 20/02/2024 | 29/11/2021 | 70.93 | 70.93
341 | Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. (SM/16695) | SM/16695 | 196.01 | 319 | NEW | 56 | Delayed | 14 | 14/03/2023 | 14/09/2024 | 20/07/2024 | 01/08/2023 | 27.01 | 27.01
342 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) (SM/07372) | SM/07372 | 75.12 | 921 | RETROFITTING | 56 | Delayed | 86 | 11/12/2020 | 29/12/2024 | 22/02/2024 | 10/02/2021 | 64.78 | 64.78
343 | Ghagara Piped Water Supply Scheme (SM/12426) | SM/12426 | 457.53 | 658 | NEW | 56 | Delayed | 35 | 13/09/2022 | 31/03/2025 | 29/11/2024 | 21/02/2023 | 159.8 | 159.8
344 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D (SM/09473) | SM/09473 | 189.75 | 1806 | RETROFITTING | 56 | Delayed | 90 | 19/11/2021 | 01/12/2024 | 20/02/2024 | 19/04/2022 | 170.7 | 170.7
345 | Augmentation of Somsar (BRGF) Water Supply Scheme (SM/17579) | SM/17579 | 104.34 | 320 | AUGMENTATION | 56 | Delayed | 37 | 18/03/2023 | 31/01/2025 | 05/12/2024 | 28/03/2023 | 38.81 | 38.81
346 | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10918) | SM/10918 | 43.65 | 283 | NEW | 56 | Delayed | 74 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 32.23 | 32.23
347 | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17697) | SM/17697 | 579.05 | 538 | AUGMENTATION | 56 | Delayed | 37 | 17/03/2023 | 31/03/2025 | 11/12/2024 | 19/07/2023 | 213.82 | 213.82
348 | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17714) | SM/17714 | 863.2 | 310 | AUGMENTATION | 56 | Delayed | 5 | 17/03/2023 | 28/02/2025 | 20/12/2024 | 09/10/2023 | 40.7 | 40.7
349 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na (SM/09478) | SM/09478 | 212.48 | 2536 | RETROFITTING | 57 | Delayed | 97 | 19/11/2021 | 31/12/2024 | 12/02/2024 | 22/02/2022 | 206.29 | 206.29
350 | MINI PIPED WATER SUPPLY SCHEME FOR KARRASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10913) | SM/10913 | 32.3 | 194 | NEW | 57 | Delayed | 84 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 26.97 | 26.97
351 | MINI PIPED WATER SUPPLY SCHEME FOR TENTUL BERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10914) | SM/10914 | 35.96 | 51 | NEW | 57 | Delayed | 60 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 21.7 | 21.7
352 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME (SM/15005) | SM/15005 | 648.32 | 2578 | AUGMENTATION | 57 | Delayed | 33 | 04/02/2023 | 31/12/2024 | 20/12/2024 | 24/05/2022 | 216.58 | 216.58
353 | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/16980) | SM/16980 | 433.81 | 110 | AUGMENTATION | 57 | Delayed | 9 | 16/03/2023 | 31/03/2025 | 04/12/2024 | 30/03/2023 | 38.02 | 38.02
354 | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17713) | SM/17713 | 743.39 | 230 | AUGMENTATION | 57 | Delayed | 34 | 17/03/2023 | 31/03/2025 | 04/12/2024 | 13/07/2023 | 251.91 | 251.91
355 | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17435) | SM/17435 | 861.68 | 312 | AUGMENTATION | 57 | Delayed | 17 | 18/03/2023 | 28/02/2025 | 04/12/2024 | 24/05/2023 | 147.19 | 146.61
356 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17712) | SM/17712 | 347.13 | 520 | AUGMENTATION | 57 | Delayed | 36 | 17/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 125.29 | 125.29
357 | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16959) | SM/16959 | 376.93 | 290 | AUGMENTATION | 57 | Delayed | 22 | 16/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 83.71 | 83.71
358 | Augmentation of Chuamasina Zone-B Water Supply Scheme (SM/17427) | SM/17427 | 243.49 | 260 | AUGMENTATION | 57 | Delayed | 36 | 18/03/2023 | 28/02/2025 | 02/12/2024 | 24/07/2023 | 88.45 | 88.45
359 | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17240) | SM/17240 | 547.7 | 344 | AUGMENTATION | 57 | Delayed | 19 | 15/03/2023 | 30/04/2025 | 11/12/2024 | 17/08/2023 | 103.46 | 103.46
360 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). (SM/17428) | SM/17428 | 688.26 | 840 | AUGMENTATION | 57 | Delayed | 26 | 18/03/2023 | 28/08/2025 | 11/12/2024 | 18/07/2023 | 181.38 | 181.38
361 | Karachmani Khayarsol Piped Water Supply Scheme (SM/12420) | SM/12420 | 417.62 | 410 | NEW | 58 | Delayed | 27 | 13/09/2022 | 31/03/2025 | 29/11/2024 | 17/04/2023 | 113.11 | 109.78
362 | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA (SM/18042) | SM/18042 | 438.88 | 985 | NEW | 58 | Delayed | 30 | 17/03/2023 | 30/04/2025 | 20/12/2024 | 14/08/2023 | 133.72 | 133.72
363 | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone (SM/09504) | SM/09504 | 80.23 | 977 | RETROFITTING | 58 | Delayed | 89 | 19/11/2021 | 31/12/2024 | 20/02/2024 | 01/12/2021 | 71.21 | 71.21
364 | Augmentation of Amrul Zone-A Water Supply Scheme (SM/17229) | SM/17229 | 297.35 | 75 | AUGMENTATION | 58 | Delayed | 38 | 15/03/2023 | 31/01/2025 | 29/11/2024 | 18/07/2023 | 113.15 | 113.15
365 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. (SM/09852) | SM/09852 | 580.47 | 0 | AUGMENTATION | 58 | Delayed | 41 | 03/12/2021 | 31/03/2025 | 20/12/2024 | 27/07/2021 | 236.93 | 236.93
366 | Augmentation of Chakuparsole Zone-A Water Supply Scheme (SM/17425) | SM/17425 | 423.84 | 360 | AUGMENTATION | 58 | On track | 39 | 18/03/2023 | 31/03/2026 | 29/11/2024 | 24/07/2023 | 166.09 | 153.15
367 | Panahar Piped Water Supply Scheme (SM/18790) | SM/18790 | 1324.42 | 2586 | NEW | 58 | Delayed | 33 | 07/09/2023 | 31/03/2025 | 16/12/2024 | 11/09/2023 | 436.53 | 159.03
368 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) (SM/07373) | SM/07373 | 96.11 | 1284 | RETROFITTING | 58 | Delayed | 65 | 11/12/2020 | 29/12/2024 | 22/02/2024 | 25/02/2021 | 62.94 | 62.94
369 | Chakai Piped Water Supply Scheme (SM/14245) | SM/14245 | 1142.89 | 2771 | NEW | 59 | Delayed | 37 | 16/01/2023 | 31/03/2025 | 29/11/2024 | 24/04/2023 | 420.03 | 404.29
370 | Augmentation of Karisunda Water Supply Scheme (SM/17419) | SM/17419 | 311.6 | 100 | AUGMENTATION | 59 | Delayed | 23 | 18/03/2023 | 31/03/2025 | 05/12/2024 | 28/07/2023 | 71.37 | 71.37
371 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed (SM/07246) | SM/07246 | 96.56 | 797 | RETROFITTING | 59 | Delayed | 75 | 08/12/2020 | 31/03/2025 | 11/02/2024 | 31/12/2020 | 72.68 | 72.68
372 | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. (SM/17301) | SM/17301 | 995.79 | 9820 | AUGMENTATION | 59 | Delayed | 67 | 15/03/2023 | 31/12/2024 | 01/07/2024 | 11/11/2022 | 663.03 | 663.03
373 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, (SM/08290) | SM/08290 | 78.52 | 692 | RETROFITTING | 59 | Delayed | 97 | 26/02/2021 | 31/12/2024 | 22/02/2024 | 22/09/2021 | 76.23 | 76.23
374 | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17424) | SM/17424 | 392.78 | 281 | AUGMENTATION | 59 | Delayed | 25 | 18/03/2023 | 31/12/2024 | 30/08/2024 | 01/08/2023 | 96.66 | 96.66
375 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) (SM/07370) | SM/07370 | 98.13 | 1419 | RETROFITTING | 59 | Delayed | 97 | 11/12/2020 | 31/12/2024 | 20/02/2024 | 31/08/2022 | 95.27 | 95.27
376 | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10909) | SM/10909 | 42.28 | 310 | NEW | 60 | Delayed | 57 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 24.23 | 20.23
377 | Construction of Grid-Connected solar photo -voltaic system for Laxmisagar PWSS scheme Dist Bankura (SM/15315) | SM/15315 | 6.8 | 0 | SOLARISATION | 60 | Delayed | 0 | 09/02/2023 | 31/12/2024 | 16/07/2024 | 23/03/2023 | 0 | 0
378 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) (SM/09549) | SM/09549 | 286.81 | 2480 | RETROFITTING | 60 | Delayed | 60 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 25/03/2022 | 172.84 | 172.84
379 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Mach Doba, Household-67) (SM/11419) | SM/11419 | 39.11 | 67 | NEW | 60 | Delayed | 54 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 21.18 | 21.18
380 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Dakshinsol, Household-36) (SM/11405) | SM/11405 | 39.11 | 36 | NEW | 60 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.13 | 20.13
381 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rupuisar, Household-85) (SM/11411) | SM/11411 | 39.11 | 85 | NEW | 60 | Delayed | 57 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 22.25 | 22.25
382 | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17235) | SM/17235 | 231.27 | 230 | AUGMENTATION | 60 | Delayed | 42 | 15/03/2023 | 31/03/2025 | 29/10/2024 | 13/07/2023 | 97.42 | 97.42
383 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Majuria-135) of CHAKUPARSOLE (Zone - A) (SM/09636) | SM/09636 | 86.9 | 943 | RETROFITTING | 60 | Delayed | 0 | 24/11/2021 | 15/12/2024 | 20/02/2024 | 22/11/2021 | 0 | 0
384 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Hurhrjangar, House Hold:45) (SM/11431) | SM/11431 | 38.91 | 45 | NEW | 60 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
385 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Tiura, Household-95) (SM/11420) | SM/11420 | 39.11 | 604 | NEW | 60 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 28/05/2024 | 03/08/2022 | 20.13 | 20.13
386 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Kubir Bandh, Household-43) (SM/11403) | SM/11403 | 39.11 | 633 | NEW | 60 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.01 | 20.01
387 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Sapuradihi, household-25) (SM/11408) | SM/11408 | 39.11 | 25 | NEW | 60 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
388 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), (SM/09550) | SM/09550 | 234.05 | 2280 | RETROFITTING | 60 | Delayed | 79 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 25/03/2022 | 184.62 | 184.62
389 | MINI PIPED WATER SUPPLY SCHEME FOR SHIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10871) | SM/10871 | 36.46 | 45 | NEW | 60 | Delayed | 67 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 24.34 | 24.34
390 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Jaypur, Household-22) (SM/11404) | SM/11404 | 39.11 | 583 | NEW | 60 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.01 | 20.01
391 | Adwaitabati Piped Water Supply Scheme (SM/16942) | SM/16942 | 999.06 | 1539 | NEW | 60 | Delayed | 38 | 16/03/2023 | 31/07/2025 | 16/12/2024 | 24/04/2023 | 381.59 | 381.59
392 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, (SM/09238) | SM/09238 | 80.74 | 495 | RETROFITTING | 60 | Delayed | 82 | 25/05/2021 | 31/12/2024 | 20/02/2024 | 01/12/2021 | 66.05 | 66.05
393 | MINI PIPED WATER SUPPLY SCHEME FOR ASNASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11045) | SM/11045 | 43.45 | 91 | NEW | 60 | Delayed | 49 | 30/05/2022 | 31/05/2024 | 12/04/2024 | 03/08/2022 | 21.18 | 21.18
394 | MINI PIPED WATER SUPPLY SCHEME FOR BHANDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11054) | SM/11054 | 40.52 | 76 | NEW | 60 | Delayed | 52 | 30/05/2022 | 31/05/2024 | 12/04/2024 | 03/08/2022 | 21.18 | 21.18
395 | MINI PIPED WATER SUPPLY SCHEME FOR SALGERYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10870) | SM/10870 | 31.49 | 24 | NEW | 60 | Delayed | 77 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 24.34 | 24.34
396 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Radhakrishnapur, House Hold:22) (SM/11432) | SM/11432 | 38.91 | 271 | NEW | 60 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.01 | 20.01
397 | Augmentation of Morar Zone-A Water Supply Scheme (SM/17237) | SM/17237 | 420.31 | 404 | AUGMENTATION | 60 | Delayed | 50 | 15/03/2023 | 31/01/2025 | 16/12/2024 | 24/07/2023 | 208.19 | 208.19
398 | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/17128) | SM/17128 | 78.45 | 0 | SUPPORT-WQMSP | 60 | Delayed | 0 | 16/03/2023 | 30/04/2024 | 16/02/2024 | 03/05/2023 | 0 | 0
399 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17287) | SM/17287 | 260.78 | 490 | AUGMENTATION | 61 | Delayed | 39 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 102.74 | 102.74
400 | MINI PIPED WATER SUPPLY SCHEME FOR HARIDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10919) | SM/10919 | 39.29 | 135 | NEW | 61 | Delayed | 82 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 32.25 | 32.25
401 | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16966) | SM/16966 | 478.54 | 743 | AUGMENTATION | 61 | Delayed | 25 | 16/03/2023 | 20/02/2025 | 10/12/2024 | 18/07/2023 | 119.32 | 104.82
402 | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). (SM/18423) | SM/18423 | 1215.26 | 3575 | AUGMENTATION | 61 | Delayed | 33 | 18/07/2023 | 31/05/2025 | 28/11/2024 | 18/07/2023 | 395.06 | 395.06
403 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17288) | SM/17288 | 976.27 | 780 | AUGMENTATION | 61 | Delayed | 17 | 15/03/2023 | 31/01/2025 | 20/12/2024 | 24/07/2023 | 165.56 | 165.56
404 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17280) | SM/17280 | 327.8 | 390 | AUGMENTATION | 61 | Delayed | 56 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 27/07/2023 | 184.95 | 177.85
405 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). (SM/17710) | SM/17710 | 631.55 | 950 | AUGMENTATION | 62 | Delayed | 35 | 17/03/2023 | 31/03/2025 | 30/11/2024 | 14/08/2023 | 219.41 | 219.41
406 | MINI PIPED WATER SUPPLY SCHEME FOR GHAGAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11050) | SM/11050 | 40.72 | 77 | NEW | 62 | Delayed | 65 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 26.44 | 26.44
407 | Mukundapur Piped Water Supply Scheme (SM/14006) | SM/14006 | 696.82 | 1297 | NEW | 62 | On track | 25 | 05/12/2022 | 31/08/2025 | 30/11/2024 | 24/07/2023 | 172.38 | 165.17
408 | Rampur Piped Water Supply Scheme (SM/18349) | SM/18349 | 1338.73 | 3297 | NEW | 62 | On track | 10 | 06/07/2023 | 31/08/2025 | 16/12/2024 | 01/06/2023 | 133.91 | 133.91
409 | Atra Piped Water Supply Scheme (SM/14000) | SM/14000 | 913.15 | 2127 | NEW | 62 | On track | 27 | 05/12/2022 | 31/07/2025 | 16/12/2024 | 04/05/2023 | 248.56 | 248.56
410 | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). (SM/17291) | SM/17291 | 244.22 | 340 | AUGMENTATION | 62 | Delayed | 45 | 15/03/2023 | 31/03/2025 | 29/10/2024 | 18/04/2023 | 109.65 | 109.65
411 | Gopalpur Piped Water Supply Scheme. (SM/16698) | SM/16698 | 945.93 | 2105 | NEW | 62 | On track | 33 | 14/03/2023 | 31/07/2025 | 16/12/2024 | 04/05/2023 | 316.28 | 312.58
412 | MINI PIPED WATER SUPPLY SCHEME FOR BALARAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11053) | SM/11053 | 39.05 | 59 | NEW | 62 | Delayed | 68 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 26.44 | 26.44
413 | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17234) | SM/17234 | 480.48 | 920 | AUGMENTATION | 62 | Delayed | 22 | 15/03/2023 | 31/03/2025 | 30/11/2024 | 18/07/2023 | 108.08 | 108.08
414 | Augmentation of Somsar Water Supply Scheme (SM/17422) | SM/17422 | 152.16 | 85 | AUGMENTATION | 62 | Delayed | 26 | 18/03/2023 | 31/01/2025 | 05/12/2024 | 28/03/2023 | 39.04 | 39.04
415 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17440) | SM/17440 | 985.52 | 850 | AUGMENTATION | 63 | Delayed | 25 | 18/03/2023 | 31/03/2025 | 20/12/2024 | 13/07/2023 | 248.73 | 248.73
416 | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16967) | SM/16967 | 749.13 | 900 | AUGMENTATION | 63 | Delayed | 30 | 16/03/2023 | 30/04/2025 | 30/11/2024 | 24/07/2023 | 222.52 | 222.52
417 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). (SM/17259) | SM/17259 | 999.07 | 4059 | AUGMENTATION | 63 | Delayed | 47 | 15/03/2023 | 31/03/2025 | 30/11/2024 | 28/08/2023 | 467.65 | 467.65
418 | Mahaldanga Piped Water Supply Scheme (SM/18318) | SM/18318 | 1541.49 | 2847 | NEW | 63 | Delayed | 39 | 26/06/2023 | 31/03/2025 | 16/12/2024 | 04/05/2023 | 597.13 | 593.16
419 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME (SM/15009) | SM/15009 | 450.15 | 1428 | AUGMENTATION | 63 | On track | 28 | 04/02/2023 | 31/12/2025 | 20/12/2024 | 24/05/2022 | 124.47 | 124.47
420 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME (SM/15008) | SM/15008 | 454.11 | 957 | AUGMENTATION | 63 | On track | 31 | 04/02/2023 | 31/12/2025 | 20/12/2024 | 24/05/2022 | 142.03 | 137.41
421 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). (SM/17285) | SM/17285 | 622.12 | 3576 | AUGMENTATION | 64 | Delayed | 42 | 15/03/2023 | 31/03/2025 | 11/12/2024 | 23/02/2023 | 262.11 | 262.11
422 | Baragaria Piped Water Supply Scheme (SM/18789) | SM/18789 | 1529 | 3303 | NEW | 64 | Delayed | 31 | 07/09/2023 | 30/04/2025 | 16/12/2024 | 11/09/2023 | 475.57 | 475.57
423 | Kushadwip Piped Water Supply Scheme (SM/15266) | SM/15266 | 753.15 | 1670 | NEW | 64 | Delayed | 33 | 07/02/2023 | 31/03/2025 | 30/11/2024 | 24/07/2023 | 245.43 | 245.43
424 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Tulardihi, House Hold:21) (SM/11430) | SM/11430 | 38.91 | 158 | NEW | 65 | Delayed | 49 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 19.24 | 19.12
425 | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. (SM/18041) | SM/18041 | 497.65 | 1118 | NEW | 65 | Delayed | 46 | 17/03/2023 | 28/02/2025 | 30/11/2024 | 01/08/2023 | 226.66 | 226.66
426 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) (SM/07330) | SM/07330 | 67.6 | 241 | RETROFITTING | 65 | Delayed | 57 | 10/12/2020 | 29/12/2024 | 20/02/2024 | 10/02/2021 | 38.42 | 38.42
427 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) (SM/07350) | SM/07350 | 58.68 | 816 | RETROFITTING | 65 | Delayed | 100 | 11/12/2020 | 25/12/2024 | 15/05/2024 | 25/08/2021 | 58.68 | 58.68
428 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Jhiknara-119 & Kharsi-121, Narra-120, Ratra-1 (SM/09622) | SM/09622 | 193.98 | 2522 | RETROFITTING | 65 | Delayed | 78 | 24/11/2021 | 31/12/2024 | 08/04/2024 | 15/12/2021 | 152.22 | 152.22
429 | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17704) | SM/17704 | 235.52 | 302 | AUGMENTATION | 65 | Delayed | 33 | 17/03/2023 | 31/03/2025 | 30/08/2024 | 14/08/2023 | 77.43 | 77.43
430 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Mathurabati, Household-54) (SM/11421) | SM/11421 | 39.11 | 262 | NEW | 65 | Delayed | 56 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 21.96 | 21.96
431 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) (SM/11424) | SM/11424 | 39.11 | 571 | NEW | 65 | Delayed | 58 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 22.63 | 22.63
432 | Bagdoba Piped Water Supply Scheme (SM/18305) | SM/18305 | 1189.17 | 2315 | NEW | 65 | Delayed | 31 | 26/06/2023 | 31/03/2025 | 16/12/2024 | 04/05/2023 | 370.19 | 370.19
433 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR (SM/08293) | SM/08293 | 73.3 | 886 | RETROFITTING | 65 | Delayed | 97 | 26/02/2021 | 25/12/2024 | 22/02/2024 | 11/11/2021 | 71.17 | 70
434 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara (SM/09644) | SM/09644 | 92.7 | 589 | RETROFITTING | 65 | Delayed | 70 | 24/11/2021 | 21/12/2024 | 20/02/2024 | 29/11/2021 | 65.01 | 64.99
435 | MINI PIPED WATER SUPPLY SCHEME FOR TUNAMARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10861) | SM/10861 | 34.96 | 39 | NEW | 65 | Delayed | 62 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 21.71 | 21.71
436 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. (SM/14126) | SM/14126 | 551.14 | 7983 | RETROFITTING | 65 | Delayed | 27 | 02/01/2023 | 31/03/2025 | 23/10/2024 | 25/04/2023 | 149.91 | 149.91
437 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, (SM/09631) | SM/09631 | 427.7 | 3315 | RETROFITTING | 65 | Delayed | 66 | 24/11/2021 | 31/12/2024 | 20/02/2024 | 19/04/2022 | 283.28 | 273.48
438 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINASANBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10862) | SM/10862 | 34.46 | 134 | NEW | 65 | Delayed | 60 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 20.53 | 20.53
439 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Bara Naryanpur, Household-73) (SM/11422) | SM/11422 | 39.11 | 73 | NEW | 65 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 28/05/2024 | 03/08/2022 | 26.44 | 26.44
440 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name: Indkata, House Hold- 93) (SM/11427) | SM/11427 | 39.11 | 313 | NEW | 65 | Delayed | 41 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 15.91 | 15.91
441 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) (SM/11414) | SM/11414 | 39.11 | 201 | NEW | 65 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
442 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Samanta Bandi, Household-39) (SM/11406) | SM/11406 | 39.11 | 39 | NEW | 65 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.13 | 20.13
443 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Siltya(P), House Hold:22) (SM/11428) | SM/11428 | 38.91 | 345 | NEW | 65 | Delayed | 41 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 15.93 | 15.93
444 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. (SM/14491) | SM/14491 | 483.88 | 3768 | RETROFITTING | 65 | Delayed | 38 | 20/01/2023 | 31/01/2025 | 28/11/2024 | 22/05/2023 | 185.49 | 185.49
445 | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/16977) | SM/16977 | 234.93 | 350 | AUGMENTATION | 65 | Delayed | 14 | 16/03/2023 | 31/03/2025 | 30/08/2024 | 28/03/2023 | 33.05 | 33.05
446 | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16964) | SM/16964 | 694.01 | 748 | AUGMENTATION | 65 | Delayed | 20 | 16/03/2023 | 28/02/2025 | 30/11/2024 | 01/08/2023 | 140.44 | 140.44
447 | MINI PIPED WATER SUPPLY SCHEME FOR SHALUKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10860) | SM/10860 | 37.46 | 299 | NEW | 65 | Delayed | 57 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.18 | 21.18
448 | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. (SM/16973) | SM/16973 | 417.13 | 590 | AUGMENTATION | 65 | Delayed | 41 | 16/03/2023 | 31/03/2025 | 29/10/2024 | 24/07/2023 | 172.81 | 172.81
449 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nischintapur, Household-81) (SM/11413) | SM/11413 | 39.11 | 249 | NEW | 65 | Delayed | 43 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 16.85 | 16.85
450 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D (SM/09472) | SM/09472 | 278.21 | 2785 | RETROFITTING | 65 | Delayed | 93 | 19/11/2021 | 01/12/2024 | 20/02/2024 | 01/02/2022 | 259.66 | 259.66
451 | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme (SM/17281) | SM/17281 | 929.93 | 280 | AUGMENTATION | 66 | Delayed | 2 | 15/03/2023 | 28/02/2025 | 04/12/2024 | 01/09/2023 | 17.21 | 17.21
452 | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16957) | SM/16957 | 293.59 | 416 | AUGMENTATION | 66 | Delayed | 24 | 16/03/2023 | 31/03/2025 | 30/11/2024 | 19/07/2023 | 71.27 | 71.27
453 | Dhulai Piped Water Supply Scheme. (SM/18753) | SM/18753 | 1452.39 | 3401 | NEW | 66 | Delayed | 41 | 21/08/2023 | 31/03/2025 | 29/11/2024 | 21/08/2023 | 599.18 | 588.88
454 | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17261) | SM/17261 | 439.33 | 710 | AUGMENTATION | 66 | Delayed | 16 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 14/08/2023 | 68.79 | 62.85
455 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VI WATER SUPPLY SCHEME (SM/16260) | SM/16260 | 383.62 | 1381 | AUGMENTATION | 66 | On track | 27 | 24/02/2023 | 31/12/2025 | 20/12/2024 | 24/05/2022 | 103.21 | 103.21
456 | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18231) | SM/18231 | 153.99 | 310 | AUGMENTATION | 66 | Delayed | 14 | 05/06/2023 | 31/03/2025 | 12/12/2024 | 17/03/2023 | 21.23 | 21.23
457 | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16968) | SM/16968 | 447.32 | 431 | AUGMENTATION | 66 | Delayed | 45 | 16/03/2023 | 31/03/2025 | 30/11/2024 | 19/07/2023 | 202.02 | 78.29
458 | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17283) | SM/17283 | 759.85 | 250 | AUGMENTATION | 67 | Delayed | 10 | 15/03/2023 | 28/02/2025 | 04/12/2024 | 13/07/2023 | 76.36 | 76.36
459 | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17236) | SM/17236 | 486.42 | 290 | AUGMENTATION | 67 | Delayed | 39 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 19/05/2023 | 188.53 | 188.53
460 | Kalyanpur Piped Water Supply Scheme (SM/14010) | SM/14010 | 594.62 | 654 | NEW | 67 | Delayed | 26 | 05/12/2022 | 31/03/2025 | 16/12/2024 | 04/05/2023 | 154.05 | 149.34
461 | Bhubut Piped Water Supply Scheme (SM/16700) | SM/16700 | 518.29 | 1153 | NEW | 67 | Delayed | 38 | 14/03/2023 | 31/03/2025 | 14/11/2024 | 26/10/2023 | 197.77 | 188.79
462 | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17698) | SM/17698 | 443.04 | 545 | AUGMENTATION | 68 | Delayed | 33 | 17/03/2023 | 20/03/2025 | 11/12/2024 | 18/07/2023 | 148.3 | 148.3
463 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME (SM/14650) | SM/14650 | 89 | 184 | AUGMENTATION | 68 | On track | 21 | 31/01/2023 | 31/12/2025 | 04/12/2024 | 24/05/2022 | 18.93 | 18.93
464 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr (SM/09523) | SM/09523 | 137.57 | 1422 | RETROFITTING | 68 | Delayed | 37 | 19/11/2021 | 31/12/2024 | 20/07/2024 | 03/03/2022 | 50.36 | 50.36
465 | Augmentation of Panchal Zone-II Water Supply Scheme (SM/17423) | SM/17423 | 236.43 | 34 | AUGMENTATION | 68 | Delayed | 42 | 18/03/2023 | 31/01/2025 | 16/12/2024 | 27/07/2023 | 98.33 | 98.33
466 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17282) | SM/17282 | 551.35 | 797 | AUGMENTATION | 68 | Delayed | 39 | 15/03/2023 | 25/02/2025 | 30/11/2024 | 23/02/2023 | 213.81 | 213.81
467 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Banki-85, Chotogobindapur-86, Adilpur-87 & (SM/09325) | SM/09325 | 226.6 | 2639 | RETROFITTING | 68 | Delayed | 97 | 08/11/2021 | 31/12/2024 | 08/04/2024 | 30/12/2021 | 220 | 220
468 | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). (SM/18119) | SM/18119 | 387.1 | 520 | AUGMENTATION | 68 | Delayed | 39 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 27/07/2023 | 150.33 | 150.33
469 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Srikara-31, Padua-11, Adpara Kumrul-12, Srip (SM/09323) | SM/09323 | 206.18 | 2465 | RETROFITTING | 69 | Delayed | 97 | 08/11/2021 | 31/12/2024 | 20/02/2024 | 08/10/2020 | 200.17 | 200.17
470 | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17253) | SM/17253 | 441.03 | 780 | AUGMENTATION | 69 | Delayed | 42 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 24/07/2023 | 184.32 | 184.32
471 | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16956) | SM/16956 | 632.16 | 968 | AUGMENTATION | 69 | Delayed | 44 | 16/03/2023 | 31/01/2025 | 30/08/2024 | 24/07/2023 | 280.83 | 280.83
472 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). (SM/17701) | SM/17701 | 339.34 | 260 | AUGMENTATION | 69 | Delayed | 34 | 17/03/2023 | 28/02/2025 | 30/11/2024 | 30/03/2023 | 114.35 | 114.35
473 | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16969) | SM/16969 | 640.4 | 478 | AUGMENTATION | 69 | Delayed | 31 | 16/03/2023 | 28/02/2025 | 30/11/2024 | 24/07/2023 | 197.41 | 197.41
474 | Rani Bandh Piped Water Supply Scheme (SM/12415) | SM/12415 | 924.1 | 1199 | NEW | 69 | Delayed | 50 | 13/09/2022 | 31/03/2025 | 29/11/2024 | 04/05/2023 | 461.46 | 461.46
475 | Jibta Piped Water Supply Scheme (SM/15018) | SM/15018 | 670.46 | 896 | NEW | 69 | On track | 29 | 04/02/2023 | 31/07/2025 | 05/12/2024 | 24/04/2023 | 196.81 | 196.81
476 | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17438) | SM/17438 | 824.28 | 245 | AUGMENTATION | 69 | Delayed | 16 | 18/03/2023 | 28/02/2025 | 20/12/2024 | 01/09/2023 | 130.76 | 130.76
477 | MINI PIPED WATER SUPPLY SCHEME FOR CHANDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10993) | SM/10993 | 43.84 | 93 | NEW | 70 | Delayed | 75 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.78 | 32.76
478 | MINI PIPED WATER SUPPLY SCHEME FOR KAMLABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10893) | SM/10893 | 44.62 | 97 | NEW | 70 | Delayed | 53 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.81 | 23.81
479 | MINI PIPED WATER SUPPLY SCHEME FOR KURUSTHALIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10971) | SM/10971 | 42.28 | 85 | NEW | 70 | Delayed | 56 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.81 | 23.81
480 | MINI PIPED WATER SUPPLY SCHEME FOR KALIAPATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10976) | SM/10976 | 41.14 | 68 | NEW | 70 | Delayed | 72 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.62 | 29.6
481 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benjtabani (51), Benrebati (52), Tilbari (53), Sarasbakra (55), Pukhuria (56), Birsingpur (57), Bikrampur (58), Krishnapur (59), Kathjuria (60), Nuniabad (61), Harintuli (62) (SM/09551) | SM/09551 | 264.94 | 3109 | RETROFITTING | 70 | Delayed | 40 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 15/12/2021 | 106.88 | 106.88
482 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jhumka (156) Nutangram (157), Ghaghrakhulia (169), Ekaria Jambani (170), Krishnabati (171), Chandpur (172), Putiadaha (173), Pithabakra (174), Bagnada (175) & Nekratapal (176 (SM/09554) | SM/09554 | 112.59 | 1257 | RETROFITTING | 70 | Delayed | 61 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 13/12/2021 | 68.17 | 68.17
483 | MINI PIPED WATER SUPPLY SCHEME FOR GANDLUGARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10892) | SM/10892 | 44.04 | 94 | NEW | 70 | Delayed | 74 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.78 | 32.76
484 | MINI PIPED WATER SUPPLY SCHEME FOR SHALTORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10970) | SM/10970 | 41.14 | 451 | NEW | 70 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 26.33 | 26.33
485 | MINI PIPED WATER SUPPLY SCHEME FOR PATIJANARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10973) | SM/10973 | 42.07 | 72 | NEW | 70 | Delayed | 78 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.76 | 32.76
486 | MINI PIPED WATER SUPPLY SCHEME FOR BINODPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10865) | SM/10865 | 31.49 | 24 | NEW | 70 | Delayed | 86 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 26.97 | 26.97
487 | MINI PIPED WATER SUPPLY SCHEME FOR AMDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10878) | SM/10878 | 34.46 | 37 | NEW | 70 | Delayed | 80 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 27.5 | 27.5
488 | MINI PIPED WATER SUPPLY SCHEME FOR BAJORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10983) | SM/10983 | 43.06 | 89 | NEW | 70 | Delayed | 55 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.69 | 23.69
489 | MINI PIPED WATER SUPPLY SCHEME FOR BELARUMA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10992) | SM/10992 | 44.62 | 97 | NEW | 70 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.08 | 29.08
490 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Gangabati-32, Maurui-33, Bhagabanbati-34, Nu (SM/09628) | SM/09628 | 241.81 | 2627 | RETROFITTING | 70 | Delayed | 70 | 24/11/2021 | 28/12/2024 | 20/02/2024 | 15/12/2021 | 169.21 | 169.21
491 | Augmentation of Prakash Zone-A Water Supply Scheme (SM/17222) | SM/17222 | 185.96 | 700 | AUGMENTATION | 70 | Delayed | 19 | 15/03/2023 | 31/01/2025 | 29/11/2024 | 18/07/2023 | 34.49 | 34.49
492 | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11120) | SM/11120 | 42.07 | 72 | NEW | 70 | Delayed | 45 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
493 | MINI PIPED WATER SUPPLY SCHEME FOR DEUL BHIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10986) | SM/10986 | 43.06 | 89 | NEW | 70 | Delayed | 76 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.76 | 32.76
494 | MINI PIPED WATER SUPPLY SCHEME FOR LEDAPAKUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11116) | SM/11116 | 40.44 | 65 | NEW | 70 | Delayed | 47 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
495 | MINI PIPED WATER SUPPLY SCHEME FOR BURISAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11117) | SM/11117 | 39.98 | 63 | NEW | 70 | Delayed | 48 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
496 | MINI PIPED WATER SUPPLY SCHEME FOR PARESNATH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11032) | SM/11032 | 37.21 | 48 | NEW | 70 | Delayed | 51 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
497 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10856) | SM/10856 | 31.22 | 23 | NEW | 70 | Delayed | 65 | 30/05/2022 | 31/03/2024 | 24/01/2024 | 03/08/2022 | 20.23 | 17.23
498 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Shibdanga, Household-82) (SM/11415) | SM/11415 | 39.11 | 82 | NEW | 70 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
499 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). (SM/17247) | SM/17247 | 586.37 | 1295 | AUGMENTATION | 70 | Delayed | 39 | 15/03/2023 | 27/02/2025 | 30/11/2024 | 14/08/2023 | 226.92 | 226.92
500 | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme (SM/17725) | SM/17725 | 592.88 | 300 | AUGMENTATION | 70 | Delayed | 25 | 17/03/2023 | 28/02/2025 | 04/12/2024 | 13/07/2023 | 147.73 | 147.73
501 | MINI PIPED WATER SUPPLY SCHEME FOR KENDBANADHAGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10864) | SM/10864 | 33.64 | 32 | NEW | 70 | Delayed | 80 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 26.99 | 26.97
502 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTAKEEHANDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10866) | SM/10866 | 37.46 | 49 | NEW | 70 | Delayed | 79 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.6 | 29.6
503 | MINI PIPED WATER SUPPLY SCHEME FOR CHHELEBAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10882) | SM/10882 | 34.21 | 36 | NEW | 70 | Delayed | 82 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 28.02 | 28.02
504 | MINI PIPED WATER SUPPLY SCHEME FOR BANDARKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10949) | SM/10949 | 32.56 | 28 | NEW | 70 | Delayed | 65 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 21.18 | 21.18
505 | MINI PIPED WATER SUPPLY SCHEME FOR BOTKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10895) | SM/10895 | 42.47 | 86 | NEW | 70 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.6 | 29.6
506 | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10889) | SM/10889 | 44.23 | 95 | NEW | 70 | Delayed | 74 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 32.76 | 32.76
507 | MINI PIPED WATER SUPPLY SCHEME FOR BANGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10872) | SM/10872 | 34.45 | 35 | NEW | 70 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
508 | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10987) | SM/10987 | 39.05 | 59 | NEW | 70 | Delayed | 61 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.69 | 23.69
509 | MINI PIPED WATER SUPPLY SCHEME FOR GOALMURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11118) | SM/11118 | 38.36 | 56 | NEW | 70 | Delayed | 50 | 30/05/2022 | 31/05/2024 | 26/04/2024 | 03/08/2022 | 19.07 | 19.07
510 | MINI PIPED WATER SUPPLY SCHEME FOR JAGATDEULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10887) | SM/10887 | 41.3 | 80 | NEW | 70 | Delayed | 72 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 29.6 | 29.6
511 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKBASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10891) | SM/10891 | 37.43 | 52 | NEW | 70 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 23.81 | 23.81
512 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10897) | SM/10897 | 36.46 | 223 | NEW | 70 | Delayed | 80 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 29.08 | 29.08
513 | Goala Danga Piped Water Supply Scheme. (SM/14001) | SM/14001 | 478.88 | 713 | NEW | 71 | On track | 34 | 05/12/2022 | 30/04/2025 | 05/12/2024 | 24/07/2023 | 163.21 | 163.21
514 | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17302) | SM/17302 | 966.49 | 305 | AUGMENTATION | 71 | Delayed | 69 | 15/03/2023 | 31/03/2025 | 04/12/2024 | 14/08/2023 | 663.79 | 663.79
515 | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna (SM/10296) | SM/10296 | 2502.19 | 0 | AUGMENTATION | 71 | Delayed | 54 | 28/02/2022 | 31/03/2025 | 20/12/2024 | 10/08/2021 | 1344.77 | 1344.77
516 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 (SM/08299) | SM/08299 | 87.68 | 1112 | RETROFITTING | 72 | Delayed | 97 | 26/02/2021 | 31/12/2024 | 20/02/2024 | 23/09/2021 | 85.12 | 85.12
517 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). (SM/16974) | SM/16974 | 738.82 | 1080 | AUGMENTATION | 72 | Delayed | 31 | 16/03/2023 | 31/03/2025 | 30/11/2024 | 18/07/2023 | 227.02 | 227.02
518 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Shyampur, House Hold:42) (SM/11138) | SM/11138 | 39.69 | 42 | NEW | 72 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.15 | 28.13
519 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Akargarya, House Hold No.: 94) (SM/11158) | SM/11158 | 39.69 | 94 | NEW | 72 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
520 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dharapat, House Hold No.: 65) (SM/11087) | SM/11087 | 38.5 | 65 | NEW | 72 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
521 | Construction of Grid-connected Solar Photo-Voltaic system for Rampur pump house-I of Rampur PWSS scheme,Dist: Bankura (SM/16965) | SM/16965 | 6.92 | 0 | SOLARISATION | 72 | Delayed | 0 | 16/03/2023 | 31/03/2024 | 25/01/2024 | 17/04/2023 | 0 | 0
522 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhalukgere, House Hold No.: 48) (SM/11195) | SM/11195 | 38.64 | 48 | NEW | 72 | Delayed | 63 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 24.36 | 24.34
523 | Chak Patrasaer Piped Water Supply Scheme (SM/18401) | SM/18401 | 1280.02 | 3211 | NEW | 73 | On track | 27 | 12/07/2023 | 12/07/2025 | 16/12/2024 | 04/05/2023 | 344.4 | 344.4
524 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Barakura, House Hold No.: 61) (SM/11687) | SM/11687 | 39.88 | 61 | NEW | 73 | Delayed | 66 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 26.44 | 26.44
525 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Danga Makarandapur, House Hold No.: 90) (SM/11685) | SM/11685 | 39.88 | 90 | NEW | 73 | Delayed | 66 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 26.44 | 26.44
526 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Adhakata, House Hold No.: 51) (SM/11688) | SM/11688 | 39.88 | 51 | NEW | 73 | Delayed | 66 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 26.44 | 26.44
527 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Piritchak, House Hold No.: 39) (SM/11194) | SM/11194 | 38.64 | 39 | NEW | 73 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
528 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17286) | SM/17286 | 262.47 | 480 | AUGMENTATION | 73 | Delayed | 49 | 15/03/2023 | 31/12/2024 | 30/08/2024 | 18/07/2023 | 127.45 | 127.45
529 | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. (SM/11980) | SM/11980 | 1043.82 | 3930 | AUGMENTATION | 73 | Delayed | 75 | 31/08/2022 | 28/02/2025 | 04/12/2024 | 06/01/2022 | 781.86 | 689.33
530 | Augmentation of Indas Water Supply Scheme (SM/17684) | SM/17684 | 178.2 | 280 | AUGMENTATION | 73 | Delayed | 54 | 17/03/2023 | 31/03/2025 | 05/12/2024 | 21/09/2023 | 96.25 | 91.82
531 | Chandal Bandi Piped Water Supply Scheme (SM/13999) | SM/13999 | 603.03 | 1325 | NEW | 73 | On track | 42 | 05/12/2022 | 30/04/2025 | 05/12/2024 | 04/05/2023 | 252.74 | 214.99
532 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dehuabani, House Hold No.: 61) (SM/11088) | SM/11088 | 38.5 | 61 | NEW | 73 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
533 | Construction of Grid-Connected solar photo -voltaic system for Beliatore PWSS scheme, Dist- Bankura (SM/15311) | SM/15311 | 21.98 | 0 | SOLARISATION | 73 | Delayed | 0 | 09/02/2023 | 31/12/2024 | 21/05/2024 | 23/03/2023 | 0 | 0
534 | Augmentation of Radhanagar Zone-II Water Supply Scheme (SM/17691) | SM/17691 | 219.61 | 165 | AUGMENTATION | 73 | Delayed | 42 | 17/03/2023 | 31/03/2025 | 05/12/2024 | 28/07/2023 | 93.16 | 93.16
535 | Dhan Simla Piped Water Supply Scheme. (SM/16706) | SM/16706 | 231.21 | 403 | NEW | 73 | Delayed | 52 | 14/03/2023 | 31/01/2025 | 05/12/2024 | 22/05/2023 | 121.15 | 121.15
536 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sri Rampur, House Hold:46) (SM/11139) | SM/11139 | 39.69 | 46 | NEW | 74 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
537 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Rampur, House Hold No.:65) (SM/11100) | SM/11100 | 38.5 | 65 | NEW | 74 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
538 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Siringa, House Hold No.: 21) (SM/11106) | SM/11106 | 38.5 | 21 | NEW | 74 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.15 | 28.13
539 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Haldar Chak, House Hold No.: 40) (SM/11107) | SM/11107 | 38.5 | 156 | NEW | 74 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
540 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Mohanchak, House Hold No.: 96) (SM/11135) | SM/11135 | 39.69 | 347 | NEW | 74 | Delayed | 72 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.43 | 28.43
541 | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC (SM/12379) | SM/12379 | 590.96 | 1107 | AUGMENTATION | 74 | Delayed | 42 | 13/09/2022 | 31/03/2025 | 04/12/2024 | 24/05/2022 | 247.12 | 247.12
542 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) (SM/11157) | SM/11157 | 39.69 | 81 | NEW | 74 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
543 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Jemo, House Hold No.: 54) (SM/11137) | SM/11137 | 39.69 | 215 | NEW | 74 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
544 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Adwaitabati, House Hold No.: 50) (SM/11099) | SM/11099 | 38.5 | 50 | NEW | 74 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.15 | 28.13
545 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ramchandrapur, House Hold No.: 45) (SM/11191) | SM/11191 | 38.64 | 45 | NEW | 74 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.58 | 26.56
546 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Tentulia, House Hold No.: 23) (SM/11187) | SM/11187 | 38.64 | 265 | NEW | 74 | Delayed | 70 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.08 | 27.08
547 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Jhero, House Hold No.: 21) (SM/11188) | SM/11188 | 38.64 | 21 | NEW | 74 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
548 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) (SM/11136) | SM/11136 | 39.69 | 96 | NEW | 74 | Delayed | 37 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 14.88 | 14.86
549 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) (SM/11105) | SM/11105 | 38.5 | 22 | NEW | 74 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
550 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Parbatipur, House Hold No.: 50) (SM/11186) | SM/11186 | 38.64 | 50 | NEW | 74 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
551 | Augmentation of Morar Zone-B Water Supply Scheme. (SM/17243) | SM/17243 | 439.27 | 128 | AUGMENTATION | 74 | Delayed | 41 | 15/03/2023 | 15/01/2025 | 29/11/2024 | 28/07/2023 | 178.52 | 178.52
552 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Durgabati, House Hold No.: 20) (SM/11192) | SM/11192 | 38.64 | 565 | NEW | 74 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.62 | 26.62
553 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Fatepur, House Hold:88) (SM/11134) | SM/11134 | 39.69 | 451 | NEW | 74 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 29.18 | 29.18
554 | Birsingpur Piped Water Supply Scheme. (SM/17223) | SM/17223 | 898.01 | 1968 | NEW | 74 | Delayed | 47 | 15/03/2023 | 31/03/2025 | 16/12/2024 | 17/04/2023 | 424.94 | 414.63
555 | MINI PIPED WATER SUPPLY SCHEME FOR NARAYANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10924) | SM/10924 | 32.3 | 1128 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 22 | 18
556 | MINI PIPED WATER SUPPLY SCHEME FOR MANHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11019) | SM/11019 | 37.71 | 50 | NEW | 75 | Delayed | 72 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 27.08 | 27.08
557 | MINI PIPED WATER SUPPLY SCHEME FOR BENATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME+B20:B21 (SM/10964) | SM/10964 | 43.45 | 355 | NEW | 75 | Delayed | 78 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 33.7 | 33.7
558 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kachara , House Hold No.: 25) (SM/11104) | SM/11104 | 38.5 | 285 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
559 | MINI PIPED WATER SUPPLY SCHEME FOR JAMSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10854) | SM/10854 | 41.6 | 193 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28.11 | 18.11
560 | MINI PIPED WATER SUPPLY SCHEME FOR KALLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13255) | SM/13255 | 32.57 | 181 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0 | 0
561 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA KUMIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10944) | SM/10944 | 44.23 | 291 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30 | 18
562 | MINI PIPED WATER SUPPLY SCHEME FOR SANKARARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10851) | SM/10851 | 43.45 | 740 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30 | 18
563 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rautara (41), Kawabasa (42), Panbaraj (43), Kiabati (44), Bhulanpur (45), Palash Bani (46), Gengari (47), Pratappur (48), Gopalpur (49), Dhabani (50), Metyala (51), Jamjuri ( (SM/09520) | SM/09520 | 266.81 | 3005 | RETROFITTING | 75 | Delayed | 93 | 19/11/2021 | 31/12/2024 | 12/02/2024 | 04/03/2022 | 247.54 | 247.54
564 | MINI PIPED WATER SUPPLY SCHEME FOR GOBINDAPURBAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10922) | SM/10922 | 31.49 | 300 | NEW | 75 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 22 | 18
565 | MINI PIPED WATER SUPPLY SCHEME FOR LACHHIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11017) | SM/11017 | 43.65 | 92 | NEW | 75 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 31.71 | 31.71
566 | MINI PIPED WATER SUPPLY SCHEME FOR MACHLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11048) | SM/11048 | 44.23 | 95 | NEW | 75 | Delayed | 48 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 21.18 | 21.18
567 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kankara, House Hold No.: 69) (SM/11090) | SM/11090 | 38.5 | 69 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
568 | MINI PIPED WATER SUPPLY SCHEME FOR KALIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10937) | SM/10937 | 44.62 | 242 | NEW | 75 | Delayed | 63 | 30/05/2022 | 31/07/2024 | 12/02/2024 | 03/08/2022 | 28.12 | 18.12
569 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10886) | SM/10886 | 44.62 | 97 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 31 | 27
570 | MINI PIPED WATER SUPPLY SCHEME FOR BENAGERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10879) | SM/10879 | 33.1 | 30 | NEW | 75 | Delayed | 58 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 19.07 | 19.07
571 | MINI PIPED WATER SUPPLY SCHEME FOR INDRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13275) | SM/13275 | 37.43 | 130 | NEW | 75 | Delayed | 80 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30 | 27
572 | MINI PIPED WATER SUPPLY SCHEME FOR CHAK KRISHNASINGHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13258) | SM/13258 | 42.51 | 213 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0 | 0
573 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj (SM/09553) | SM/09553 | 279 | 3357 | RETROFITTING | 75 | Delayed | 49 | 19/11/2021 | 31/01/2025 | 23/10/2024 | 15/12/2021 | 135.34 | 135.34
574 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Mukha, House Hold No.: 93) (SM/11094) | SM/11094 | 38.5 | 93 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
575 | MINI PIPED WATER SUPPLY SCHEME FOR RAUTKHANA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13271) | SM/13271 | 35.96 | 20 | NEW | 75 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.44 | 26.44
576 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi (SM/09324) | SM/09324 | 187.99 | 2264 | RETROFITTING | 75 | Delayed | 92 | 08/11/2021 | 31/12/2024 | 08/04/2024 | 30/12/2021 | 172.89 | 172.89
577 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D (SM/09474) | SM/09474 | 208.88 | 1927 | RETROFITTING | 75 | Delayed | 73 | 19/11/2021 | 28/12/2024 | 20/02/2024 | 09/02/2022 | 151.87 | 151.87
578 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHIN KAMALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10994) | SM/10994 | 37.43 | 52 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 26.46 | 26.44
579 | MINI PIPED WATER SUPPLY SCHEME FOR KHEJURBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11016) | SM/11016 | 38.36 | 56 | NEW | 75 | Delayed | 62 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 23.81 | 23.81
580 | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11023) | SM/11023 | 44.23 | 95 | NEW | 75 | Delayed | 48 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 21.18 | 21.18
581 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Jaljala, House Hold No.: 84) (SM/11086) | SM/11086 | 38.5 | 84 | NEW | 75 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.02 | 28.02
582 | MINI PIPED WATER SUPPLY SCHEME FOR CHANDIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10934) | SM/10934 | 34.46 | 97 | NEW | 75 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 24.12 | 18.12
583 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Lalgara, House Hold No.: 34) (SM/11103) | SM/11103 | 38.5 | 194 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.33 | 26.33
584 | MINI PIPED WATER SUPPLY SCHEME FOR HARISHCHANDRAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10867) | SM/10867 | 33.91 | 33 | NEW | 75 | Delayed | 62 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.18 | 21.18
585 | MINI PIPED WATER SUPPLY SCHEME FOR KOT MADAN MOHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10848) | SM/10848 | 44.62 | 746 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30.12 | 18.12
586 | MINI PIPED WATER SUPPLY SCHEME FOR JAMRA MADHABPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13264) | SM/13264 | 43.19 | 159 | NEW | 75 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 27.47 | 25
587 | MINI PIPED WATER SUPPLY SCHEME FOR KALYANSAER VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13269) | SM/13269 | 35.71 | 29 | NEW | 75 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.44 | 26.44
588 | MINI PIPED WATER SUPPLY SCHEME FOR TURUBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13272) | SM/13272 | 30.41 | 36 | NEW | 75 | Delayed | 87 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.44 | 26.44
589 | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17250) | SM/17250 | 177.09 | 245 | AUGMENTATION | 75 | On track | 60 | 15/03/2023 | 31/03/2025 | 30/08/2024 | 18/07/2023 | 106.12 | 106.12
590 | MINI PIPED WATER SUPPLY SCHEME FOR CHAK RANGA METYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10921) | SM/10921 | 32.03 | 62 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 22.12 | 18.12
591 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13262) | SM/13262 | 40.19 | 216 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0.11 | 0.11
592 | MINI PIPED WATER SUPPLY SCHEME FOR AMALA DIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10926) | SM/10926 | 33.64 | 246 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.12 | 18.12
593 | MINI PIPED WATER SUPPLY SCHEME FOR ATARYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10929) | SM/10929 | 35.21 | 324 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 24 | 18
594 | MINI PIPED WATER SUPPLY SCHEME FOR KHARAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10888) | SM/10888 | 37.2 | 51 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 25.5 | 23
595 | MINI PIPED WATER SUPPLY SCHEME FOR DAMRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10936) | SM/10936 | 43.84 | 238 | NEW | 75 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28.12 | 18.12
596 | MINI PIPED WATER SUPPLY SCHEME FOR LAKHYARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10942) | SM/10942 | 42.86 | 175 | NEW | 75 | Delayed | 68 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 29.12 | 18.12
597 | MINI PIPED WATER SUPPLY SCHEME FOR MALLIKDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10943) | SM/10943 | 44.62 | 293 | NEW | 75 | Delayed | 67 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30 | 18
598 | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10850) | SM/10850 | 37.2 | 700 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 19/03/2024 | 03/08/2022 | 25.62 | 18.12
599 | MINI PIPED WATER SUPPLY SCHEME FOR CHARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10847) | SM/10847 | 41.3 | 276 | NEW | 75 | Delayed | 67 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 27.5 | 18
600 | MINI PIPED WATER SUPPLY SCHEME FOR PATRA HATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13265) | SM/13265 | 39.95 | 157 | NEW | 75 | Delayed | 75 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30 | 27
601 | MINI PIPED WATER SUPPLY SCHEME FOR BARAKHARANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11009) | SM/11009 | 43.45 | 91 | NEW | 75 | Delayed | 49 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 21.3 | 21.3
602 | MINI PIPED WATER SUPPLY SCHEME FOR RAJPURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11123) | SM/11123 | 33.64 | 404 | NEW | 75 | Delayed | 75 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 25.39 | 25.39
603 | MINI PIPED WATER SUPPLY SCHEME FOR CHATURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11010) | SM/11010 | 43.84 | 93 | NEW | 75 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 31.83 | 31.83
604 | MINI PIPED WATER SUPPLY SCHEME FOR MANJURA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10908) | SM/10908 | 41.14 | 68 | NEW | 75 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28.62 | 25.12
605 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Ram Bakhra, House Hold No.: 63) (SM/11098) | SM/11098 | 38.5 | 63 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
606 | MINI PIPED WATER SUPPLY SCHEME FOR ITA DANGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10941) | SM/10941 | 42.07 | 159 | NEW | 75 | Delayed | 64 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 27.12 | 18.12
607 | MINI PIPED WATER SUPPLY SCHEME FOR BALIKHUN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10852) | SM/10852 | 45.01 | 748 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 31 | 18
608 | MINI PIPED WATER SUPPLY SCHEME FOR TOL CHANDRAKONA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13261) | SM/13261 | 40.42 | 136 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0 | 0
609 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply s (SM/09309) | SM/09309 | 36.21 | 245 | RETROFITTING | 75 | Delayed | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 12/11/2021 | 35.14 | 35.14
610 | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. (SM/10294) | SM/10294 | 1011.34 | 3489 | AUGMENTATION | 75 | Delayed | 69 | 28/02/2022 | 31/03/2025 | 25/11/2024 | 24/09/2021 | 694.97 | 694.97
611 | MINI PIPED WATER SUPPLY SCHEME FOR BELARMARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10927) | SM/10927 | 33.64 | 123 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 23.12 | 18.12
612 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOLA BAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10932) | SM/10932 | 34.46 | 143 | NEW | 75 | Delayed | 73 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 25.2 | 19.2
613 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMSUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11038) | SM/11038 | 36.96 | 47 | NEW | 75 | Delayed | 52 | 30/05/2022 | 31/05/2024 | 13/02/2024 | 03/08/2022 | 19.07 | 19.07
614 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Shimdal, House Hold No.: 50) (SM/11093) | SM/11093 | 38.5 | 50 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
615 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10935) | SM/10935 | 41.84 | 167 | NEW | 75 | Delayed | 67 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28 | 18
616 | MINI PIPED WATER SUPPLY SCHEME FOR KENTHALYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10939) | SM/10939 | 41.6 | 157 | NEW | 75 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 27.12 | 18.12
617 | MINI PIPED WATER SUPPLY SCHEME FOR KHAJURI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10855) | SM/10855 | 43.45 | 214 | NEW | 75 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 30.52 | 13.52
618 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Birampur, House Hold No.: 57) (SM/11694) | SM/11694 | 39.88 | 1479 | NEW | 75 | Delayed | 58 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 23.17 | 23.17
619 | MINI PIPED WATER SUPPLY SCHEME FOR TELLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13260) | SM/13260 | 43.39 | 446 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0.11 | 0.11
620 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13263) | SM/13263 | 40.26 | 227 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0.11 | 0.11
621 | MINI PIPED WATER SUPPLY SCHEME FOR DALI MAHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13257) | SM/13257 | 36.7 | 104 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0.11 | 0.11
622 | MINI PIPED WATER SUPPLY SCHEME FOR HATIBAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13254) | SM/13254 | 33.92 | 186 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0 | 0
623 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa (SM/07340) | SM/07340 | 88.31 | 1104 | RETROFITTING | 75 | Delayed | 70 | 11/12/2020 | 31/12/2024 | 20/09/2024 | 23/02/2021 | 62.17 | 62.17
624 | MINI PIPED WATER SUPPLY SCHEME FOR KUDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10923) | SM/10923 | 37.46 | 358 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 26 | 18
625 | MINI PIPED WATER SUPPLY SCHEME FOR PARAMANIK KUNRI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10925) | SM/10925 | 33.37 | 92 | NEW | 75 | Delayed | 66 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 22 | 18
626 | MINI PIPED WATER SUPPLY SCHEME FOR PANKUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10931) | SM/10931 | 34.96 | 441 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 24.12 | 18.12
627 | MINI PIPED WATER SUPPLY SCHEME FOR JAGANNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11020) | SM/11020 | 37.71 | 50 | NEW | 75 | Delayed | 72 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 27.08 | 27.08
628 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) (SM/11091) | SM/11091 | 38.5 | 55 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
629 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) (SM/11095) | SM/11095 | 38.5 | 93 | NEW | 75 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.52 | 27.5
630 | MINI PIPED WATER SUPPLY SCHEME FOR BAMUNDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10853) | SM/10853 | 41.5 | 730 | NEW | 75 | Delayed | 61 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 25.5 | 18
631 | MINI PIPED WATER SUPPLY SCHEME FOR CHAITANDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10857) | SM/10857 | 33.64 | 400 | NEW | 75 | Delayed | 63 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 21.18 | 21.18
632 | MINI PIPED WATER SUPPLY SCHEME FOR BHIRINGI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10846) | SM/10846 | 40.52 | 272 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28.12 | 18.12
633 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chaknayan, House Hold No.: 29) (SM/11189) | SM/11189 | 38.64 | 29 | NEW | 75 | Delayed | 66 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 25.41 | 25.39
634 | Construction of Grid-Connected solar photo -voltaic system for Radhanagar PWSS scheme Dist Bankura (SM/15314) | SM/15314 | 31.01 | 0 | SOLARISATION | 75 | Delayed | 0 | 09/02/2023 | 31/10/2023 | 23/08/2023 | 23/03/2023 | 0 | 0
635 | MINI PIPED WATER SUPPLY SCHEME FOR BRINDABANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10930) | SM/10930 | 32.83 | 163 | NEW | 75 | Delayed | 67 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 22 | 18
636 | MINI PIPED WATER SUPPLY SCHEME FOR SUDARSHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10940) | SM/10940 | 41.89 | 141 | NEW | 75 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 27.12 | 18.12
637 | MINI PIPED WATER SUPPLY SCHEME FOR ASAN CHUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10945) | SM/10945 | 42.08 | 280 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 29.12 | 18.12
638 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) (SM/11085) | SM/11085 | 38.5 | 89 | NEW | 75 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.05 | 28.03
639 | MINI PIPED WATER SUPPLY SCHEME FOR MANDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10928) | SM/10928 | 36.71 | 197 | NEW | 75 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 25.5 | 18
640 | MINI PIPED WATER SUPPLY SCHEME FOR KELAI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10938) | SM/10938 | 45.01 | 244 | NEW | 75 | Delayed | 62 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 28 | 18
641 | MINI PIPED WATER SUPPLY SCHEME FOR GHUTIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10883) | SM/10883 | 34.45 | 35 | NEW | 75 | Delayed | 65 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 22.23 | 22.23
642 | MINI PIPED WATER SUPPLY SCHEME FOR MOULESWAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13256) | SM/13256 | 30.69 | 79 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0 | 0
643 | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13259) | SM/13259 | 40.88 | 517 | NEW | 75 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 0.11 | 0.11
644 | MINI PIPED WATER SUPPLY SCHEME FOR BERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13266) | SM/13266 | 43.58 | 45 | NEW | 75 | Delayed | 62 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 27.08 | 27.08
645 | MINI PIPED WATER SUPPLY SCHEME FOR CHATURIKALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/13268) | SM/13268 | 36.46 | 42 | NEW | 75 | Delayed | 72 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.33 | 26.33
646 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10963) | SM/10963 | 37.46 | 377 | NEW | 75 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 11/02/2024 | 03/08/2022 | 26.33 | 26.33
647 | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. (SM/15259) | SM/15259 | 141.68 | 0 | SUPPORT-WQMSP | 75 | Delayed | 0 | 06/02/2023 | 31/01/2025 | 25/07/2024 | 04/04/2023 | 0 | 0
648 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17257) | SM/17257 | 492.36 | 420 | AUGMENTATION | 76 | Delayed | 29 | 15/03/2023 | 28/02/2025 | 30/11/2024 | 23/03/2023 | 143.4 | 143.4
649 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). (SM/17258) | SM/17258 | 367.1 | 260 | AUGMENTATION | 76 | On track | 25 | 15/03/2023 | 31/03/2025 | 30/08/2024 | 23/03/2023 | 91.86 | 91.86
650 | Augmentation of Joypur Piped Water Supply Scheme. (SM/09878) | SM/09878 | 822.71 | 3612 | AUGMENTATION | 76 | Delayed | 46 | 08/12/2021 | 31/01/2025 | 29/11/2024 | 01/02/2022 | 375.97 | 375.97
651 | MINI PIPED WATER SUPPLY SCHEME FOR RESIAGARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11037) | SM/11037 | 32.03 | 26 | NEW | 76 | Delayed | 53 | 30/05/2022 | 31/05/2024 | 15/04/2024 | 03/08/2022 | 17.08 | 17.08
652 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Gaighata, House Hold No.: 84) (SM/11185) | SM/11185 | 38.64 | 84 | NEW | 76 | Delayed | 63 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 24.41 | 24.23
653 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10933) | SM/10933 | 34.96 | 78 | NEW | 77 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 24.12 | 18.12
654 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10956) | SM/10956 | 38.13 | 55 | NEW | 77 | Delayed | 69 | 30/05/2022 | 31/05/2024 | 16/02/2024 | 03/08/2022 | 26.44 | 26.44
655 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chandipur, House Hold No.: 97) (SM/11142) | SM/11142 | 39.69 | 725 | NEW | 77 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.01 | 28.01
656 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Napukur, House Hold No.: 89) (SM/11089) | SM/11089 | 38.5 | 89 | NEW | 78 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
657 | MINI PIPED WATER SUPPLY SCHEME FOR GANGPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10975) | SM/10975 | 37.71 | 50 | NEW | 78 | Delayed | 70 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 26.46 | 26.44
658 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Angazrasol, House Hold:42) (SM/11141) | SM/11141 | 39.69 | 42 | NEW | 78 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.02 | 28.02
659 | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10884) | SM/10884 | 32.56 | 28 | NEW | 78 | Delayed | 83 | 30/05/2022 | 31/07/2024 | 02/02/2024 | 03/08/2022 | 26.99 | 26.97
660 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhelaighata, House Hold No.: 32) (SM/11193) | SM/11193 | 38.64 | 474 | NEW | 78 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.13 | 28.13
661 | Augmentation of Ajodhya Water Supply Scheme (SM/17246) | SM/17246 | 320.23 | 480 | AUGMENTATION | 78 | Delayed | 40 | 15/03/2023 | 31/01/2025 | 16/12/2024 | 24/07/2023 | 128.29 | 128.29
662 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Pal Puskarini, House Hold No.: 79) (SM/11150) | SM/11150 | 39.69 | 620 | NEW | 78 | Delayed | 72 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.55 | 28.55
663 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) (SM/11108) | SM/11108 | 38.5 | 804 | NEW | 78 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 26.68 | 26.68
664 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Enayet Chak, House Hold No.: 85) (SM/11155) | SM/11155 | 39.69 | 85 | NEW | 78 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.46 | 26.44
665 | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16958) | SM/16958 | 289.59 | 280 | AUGMENTATION | 78 | On track | 59 | 16/03/2023 | 31/03/2025 | 30/11/2024 | 13/07/2023 | 172.06 | 172.06
666 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dashere, House Hold No.: 75) (SM/11096) | SM/11096 | 38.5 | 75 | NEW | 78 | Delayed | 73 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.15 | 28.13
667 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) (SM/11084) | SM/11084 | 38.5 | 50 | NEW | 78 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
668 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Baragopinathpur, House Hold No.: 90) (SM/11146) | SM/11146 | 39.69 | 90 | NEW | 78 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 28.15 | 28.13
669 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17284) | SM/17284 | 555.78 | 505 | AUGMENTATION | 79 | On track | 49 | 15/03/2023 | 25/02/2025 | 30/11/2024 | 23/02/2023 | 272.29 | 272.29
670 | Augmentation of Radhanagar Zone-I Water Supply Scheme (SM/17690) | SM/17690 | 389.87 | 205 | AUGMENTATION | 79 | Delayed | 38 | 17/03/2023 | 15/01/2025 | 29/11/2024 | 28/07/2023 | 148.91 | 148.91
671 | Danga Makarandapur Piped Water Supply Scheme (SM/14523) | SM/14523 | 1199.48 | 2744 | NEW | 79 | Delayed | 54 | 30/01/2023 | 31/01/2025 | 29/11/2024 | 21/02/2023 | 645.02 | 645.02
672 | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16955) | SM/16955 | 478.49 | 820 | AUGMENTATION | 79 | Delayed | 45 | 16/03/2023 | 14/02/2025 | 30/11/2024 | 27/07/2023 | 216.32 | 209.82
673 | MINI PIPED WATER SUPPLY SCHEME FOR UPARGERYAKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10974) | SM/10974 | 39.75 | 62 | NEW | 80 | Delayed | 73 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 29.12 | 27.12
674 | Harinashuli Piped Water Supply Scheme (SM/12422) | SM/12422 | 946.83 | 2340 | NEW | 80 | On track | 50 | 13/09/2022 | 03/03/2025 | 29/11/2024 | 04/05/2023 | 477.14 | 477.14
675 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Paschim Nabasan, House Hold:33) (SM/11433) | SM/11433 | 38.91 | 33 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
676 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) (SM/11416) | SM/11416 | 39.11 | 92 | NEW | 80 | Delayed | 78 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 30.66 | 30.66
677 | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11022) | SM/11022 | 44.43 | 96 | NEW | 80 | Delayed | 60 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 26.44 | 26.44
678 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name -Aligang, House Hold-91) (SM/11426) | SM/11426 | 39.11 | 91 | NEW | 80 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.13 | 20.13
679 | MINI PIPED WATER SUPPLY SCHEME FOR KALUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10905) | SM/10905 | 39.52 | 161 | NEW | 80 | Delayed | 82 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 32.24 | 32.24
680 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Amghata, Household-22) (SM/11410) | SM/11410 | 39.11 | 22 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 28/05/2024 | 03/08/2022 | 26.44 | 26.44
681 | MINI PIPED WATER SUPPLY SCHEME FOR NIYASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10876) | SM/10876 | 36.71 | 46 | NEW | 80 | Delayed | 61 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
682 | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10874) | SM/10874 | 33.91 | 33 | NEW | 80 | Delayed | 66 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.35 | 22.35
683 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Chaulya, Household-71) (SM/11417) | SM/11417 | 39.11 | 71 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
684 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nachanhati, Household-84) (SM/11425) | SM/11425 | 39.11 | 84 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
685 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Birasimul-70, Shakrul-71, Suripuskarini-72 & D (SM/09318) | SM/09318 | 99.95 | 1343 | RETROFITTING | 80 | Delayed | 79 | 08/11/2021 | 22/12/2024 | 20/02/2024 | 16/11/2021 | 79.13 | 79.07
686 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Mathurabihari-28, Ramchandrapur-30, Matukp (SM/08292) | SM/08292 | 70.88 | 828 | RETROFITTING | 80 | Delayed | 90 | 26/02/2021 | 25/12/2024 | 22/02/2024 | 23/09/2021 | 64.06 | 63.72
687 | MINI PIPED WATER SUPPLY SCHEME FOR NISHCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10859) | SM/10859 | 34.21 | 36 | NEW | 80 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 0 | 0
688 | MINI PIPED WATER SUPPLY SCHEME FOR TARKAJOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10881) | SM/10881 | 36.71 | 46 | NEW | 80 | Delayed | 0 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 0 | 0
689 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) (SM/11418) | SM/11418 | 39.11 | 79 | NEW | 80 | Delayed | 81 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 31.71 | 31.71
690 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjo (SM/09231) | SM/09231 | 99.3 | 375 | RETROFITTING | 80 | Delayed | 72 | 25/05/2021 | 31/01/2025 | 28/11/2024 | 23/09/2021 | 71.91 | 71.91
691 | MINI PIPED WATER SUPPLY SCHEME FOR GHUGUJAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10903) | SM/10903 | 37.43 | 0 | NEW | 80 | Delayed | 58 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 21.7 | 21.7
692 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10877) | SM/10877 | 30.68 | 21 | NEW | 80 | Delayed | 72 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
693 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Salda, Household-77) (SM/11412) | SM/11412 | 39.11 | 77 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.57 | 26.57
694 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINKENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10873) | SM/10873 | 30.68 | 21 | NEW | 80 | Delayed | 69 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 21.18 | 21.18
695 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District (SM/08311) | SM/08311 | 298.3 | 7093 | RETROFITTING | 80 | Delayed | 62 | 26/02/2021 | 31/12/2024 | 01/07/2024 | 12/05/2022 | 186.33 | 174.53
696 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10985) | SM/10985 | 40.52 | 76 | NEW | 80 | Delayed | 55 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.25 | 22.23
697 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10990) | SM/10990 | 42.47 | 86 | NEW | 80 | Delayed | 52 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
698 | MINI PIPED WATER SUPPLY SCHEME FOR NADUSENARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10890) | SM/10890 | 37.71 | 50 | NEW | 80 | Delayed | 59 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
699 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village name-Chakdhoyakure, household-36) (SM/11409) | SM/11409 | 39.11 | 36 | NEW | 80 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
700 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Maitya, Household-74) (SM/11423) | SM/11423 | 39.11 | 74 | NEW | 80 | Delayed | 54 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 21.18 | 21.18
701 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). (SM/16952) | SM/16952 | 172.5 | 180 | AUGMENTATION | 80 | On track | 45 | 16/03/2023 | 31/03/2025 | 31/08/2024 | 01/08/2023 | 78.48 | 78.48
702 | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. (SM/17238) | SM/17238 | 140.97 | 0 | SOLARISATION | 80 | Delayed | 0 | 15/03/2023 | 31/03/2024 | 31/01/2024 | 17/04/2023 | 0 | 0
703 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Mahishabandi, House Hold No.: 93) (SM/11183) | SM/11183 | 38.64 | 399 | NEW | 81 | Delayed | 60 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 23.29 | 23.29
704 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Shibdanga, House Hold No.: 74) (SM/11184) | SM/11184 | 38.64 | 74 | NEW | 81 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 28.55 | 28.55
705 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME (SM/15006) | SM/15006 | 246.43 | 608 | AUGMENTATION | 81 | On track | 31 | 04/02/2023 | 31/12/2025 | 24/07/2024 | 24/05/2022 | 76.2 | 76.2
706 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09927) | SM/09927 | 308.91 | 1224 | AUGMENTATION | 81 | Delayed | 77 | 09/12/2021 | 31/01/2025 | 29/11/2024 | 12/05/2022 | 238.38 | 238.38
707 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. (SM/10293) | SM/10293 | 1980.57 | 15728 | AUGMENTATION | 81 | On track | 58 | 28/02/2022 | 31/03/2025 | 31/08/2024 | 24/06/2020 | 1144.6 | 1144.6
708 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Sanpura-57, Jagaldwip-58, Dasarathbati-61 (SM/09623) | SM/09623 | 190.01 | 2653 | RETROFITTING | 81 | Delayed | 97 | 24/11/2021 | 31/12/2024 | 20/02/2024 | 15/12/2021 | 184.48 | 184.48
709 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram, House Hold No.: 81) (SM/11182) | SM/11182 | 38.64 | 501 | NEW | 81 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 26.44 | 26.44
710 | Dwarika Pipe Water Supply Scheme (SM/17224) | SM/17224 | 733.57 | 1443 | NEW | 81 | Delayed | 34 | 15/03/2023 | 31/01/2025 | 29/11/2024 | 14/08/2023 | 247.22 | 247.22
711 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17708) | SM/17708 | 408.45 | 270 | AUGMENTATION | 81 | On track | 44 | 17/03/2023 | 25/02/2025 | 30/11/2024 | 13/07/2023 | 178.64 | 178.64
712 | Jamuna Band Pipe Water Supply Scheme (SM/18037) | SM/18037 | 563.85 | 945 | NEW | 81 | Delayed | 35 | 17/03/2023 | 15/01/2025 | 29/11/2024 | 01/08/2023 | 199.1 | 199.1
713 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Jamsala, House Hold:60) (SM/11143) | SM/11143 | 39.69 | 317 | NEW | 82 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 28.13 | 28.13
714 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (SM/09877) | SM/09877 | 656.27 | 3690 | AUGMENTATION | 82 | Delayed | 39 | 08/12/2021 | 14/02/2025 | 30/11/2024 | 13/04/2022 | 256.99 | 256.99
715 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Rohimchak, House Hold No.: 78) (SM/11148) | SM/11148 | 39.69 | 315 | NEW | 82 | Delayed | 70 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.62 | 27.62
716 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) (SM/11101) | SM/11101 | 38.5 | 75 | NEW | 82 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 29.62 | 29.6
717 | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16954) | SM/16954 | 127.61 | 900 | AUGMENTATION | 82 | Delayed | 37 | 16/03/2023 | 31/01/2025 | 30/11/2024 | 02/06/2023 | 46.9 | 46.9
718 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bramhanairi, House Hold No.: 67) (SM/11092) | SM/11092 | 38.5 | 67 | NEW | 82 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 29.62 | 29.6
719 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Mahammad, House Hold No.: 83) (SM/11144) | SM/11144 | 39.69 | 312 | NEW | 82 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.44 | 26.44
720 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Dhanjoga, House Hold No.: 56) (SM/11140) | SM/11140 | 39.69 | 280 | NEW | 82 | Delayed | 67 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 26.44 | 26.44
721 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) (SM/11097) | SM/11097 | 38.5 | 87 | NEW | 82 | Delayed | 84 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 32.36 | 32.34
722 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Asude, House Hold No.: 35) (SM/11102) | SM/11102 | 38.5 | 35 | NEW | 82 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 29.62 | 29.6
723 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) (SM/11145) | SM/11145 | 39.69 | 46 | NEW | 82 | Delayed | 69 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 27.5 | 27.5
724 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dharisyer, House Hold No.: 25) (SM/11684) | SM/11684 | 39.88 | 62 | NEW | 83 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 29.6 | 29.6
725 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) (SM/08983) | SM/08983 | 672.25 | 2939 | AUGMENTATION | 83 | Delayed | 64 | 29/10/2021 | 31/01/2025 | 30/11/2024 | 25/05/2022 | 433.41 | 433.41
726 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chandabil, House Hold No.: 93) (SM/11686) | SM/11686 | 39.88 | 93 | NEW | 83 | Delayed | 74 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 29.6 | 29.6
727 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhabanipur, House Hold No.: 60) (SM/11695) | SM/11695 | 39.88 | 150 | NEW | 83 | Delayed | 80 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 31.71 | 31.71
728 | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) (SM/10290) | SM/10290 | 1004.54 | 4030 | AUGMENTATION | 84 | On track | 45 | 28/02/2022 | 31/01/2025 | 05/12/2024 | 05/01/2023 | 454.79 | 454.79
729 | Jadabnagar Piped Water Supply Scheme (SM/14527) | SM/14527 | 1225.04 | 2927 | NEW | 84 | On track | 49 | 30/01/2023 | 31/01/2025 | 29/11/2024 | 04/05/2023 | 602.15 | 602.15
730 | MINI PIPED WATER SUPPLY SCHEME FOR MAKARKENDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10900) | SM/10900 | 35.21 | 40 | NEW | 85 | Delayed | 75 | 30/05/2022 | 30/06/2024 | 20/04/2024 | 03/08/2022 | 26.44 | 26.44
731 | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10906) | SM/10906 | 40.52 | 76 | NEW | 85 | Delayed | 67 | 30/05/2022 | 24/07/2024 | 20/04/2024 | 03/08/2022 | 27.03 | 27.03
732 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) (SM/11175) | SM/11175 | 38.64 | 75 | NEW | 85 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 26.44 | 26.44
733 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Brindabanpur, House Hold:60 (SM/11445) | SM/11445 | 38.91 | 183 | NEW | 85 | Delayed | 53 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 20.44 | 20.44
734 | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/16976) | SM/16976 | 306.48 | 765 | AUGMENTATION | 85 | On track | 29 | 16/03/2023 | 31/03/2025 | 30/08/2024 | 20/03/2023 | 89.09 | 89.09
735 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). (SM/16951) | SM/16951 | 110.96 | 180 | AUGMENTATION | 85 | Delayed | 32 | 16/03/2023 | 31/10/2024 | 20/07/2024 | 24/07/2023 | 35.74 | 35.74
736 | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10902) | SM/10902 | 33.64 | 51 | NEW | 85 | Delayed | 65 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 21.82 | 21.82
737 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 (SM/09627) | SM/09627 | 280.67 | 3761 | RETROFITTING | 85 | Delayed | 42 | 24/11/2021 | 31/12/2024 | 10/08/2024 | 31/08/2022 | 117.82 | 117.82
738 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Radhanagar, House Hold No.: 97) (SM/11171) | SM/11171 | 38.64 | 97 | NEW | 85 | Delayed | 58 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 22.25 | 22.23
739 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, (SM/09314) | SM/09314 | 169.28 | 1633 | RETROFITTING | 85 | Delayed | 82 | 08/11/2021 | 31/12/2024 | 28/11/2024 | 16/11/2021 | 139.05 | 127.84
740 | MINI PIPED WATER SUPPLY SCHEME FOR SUPURDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10899) | SM/10899 | 30.41 | 20 | NEW | 85 | Delayed | 79 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 23.92 | 23.92
741 | MINI PIPED WATER SUPPLY SCHEME FOR SIARBADA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10898) | SM/10898 | 33.64 | 32 | NEW | 85 | Delayed | 71 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 23.92 | 23.92
742 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10907) | SM/10907 | 38.59 | 57 | NEW | 85 | Delayed | 77 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 29.6 | 29.6
743 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram Radhamohanpur, House Hold No.: 88) (SM/11174) | SM/11174 | 38.64 | 661 | NEW | 85 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 26.44 | 26.44
744 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Dihilapur, House Hold:52) (SM/11439) | SM/11439 | 38.91 | 182 | NEW | 85 | Delayed | 70 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 27.08 | 27.08
745 | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. (SM/16975) | SM/16975 | 282.39 | 475 | AUGMENTATION | 85 | On track | 34 | 16/03/2023 | 31/03/2025 | 30/08/2024 | 24/07/2023 | 96.79 | 96.79
746 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. (SM/16940) | SM/16940 | 659.22 | 4478 | RETROFITTING | 85 | On track | 52 | 16/03/2023 | 31/01/2025 | 23/10/2024 | 10/02/2022 | 340.3 | 306.05
747 | MINI PIPED WATER SUPPLY SCHEME FOR JAMARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10904) | SM/10904 | 43.06 | 0 | NEW | 85 | Delayed | 74 | 30/05/2022 | 30/07/2024 | 20/04/2024 | 03/08/2022 | 31.71 | 31.71
748 | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. (SM/17248) | SM/17248 | 394.85 | 265 | AUGMENTATION | 85 | On track | 28 | 15/03/2023 | 31/03/2025 | 30/08/2024 | 24/07/2023 | 112 | 112
749 | MINI PIPED WATER SUPPLY SCHEME FOR NUNIABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10989) | SM/10989 | 41.69 | 82 | NEW | 85 | Delayed | 53 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
750 | MINI PIPED WATER SUPPLY SCHEME FOR SIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10901) | SM/10901 | 36.96 | 225 | NEW | 85 | Delayed | 87 | 30/05/2022 | 29/07/2024 | 20/04/2024 | 03/08/2022 | 32.24 | 32.24
751 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nachur, House Hold No.: 59) (SM/11172) | SM/11172 | 38.64 | 59 | NEW | 85 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 29.6 | 29.6
752 | MINI PIPED WATER SUPPLY SCHEME FOR JIRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10896) | SM/10896 | 32.83 | 29 | NEW | 85 | Delayed | 97 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 31.84 | 31.84
753 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Akharashal, House Hold No.: 35) (SM/11190) | SM/11190 | 38.64 | 259 | NEW | 85 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 26.33 | 26.33
754 | MINI PIPED WATER SUPPLY SCHEME FOR KALIPAHARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10979) | SM/10979 | 37.71 | 50 | NEW | 85 | Delayed | 59 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 22.23 | 22.23
755 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Metelsair, House Hold No.: 93) (SM/11153) | SM/11153 | 39.69 | 384 | NEW | 86 | Delayed | 80 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 31.59 | 31.59
756 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chanpatala, House Hold No.: 63) (SM/11179) | SM/11179 | 38.64 | 63 | NEW | 86 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 26.44 | 26.44
757 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Haira bandh, House Hold:54 (SM/11450) | SM/11450 | 38.91 | 157 | NEW | 86 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 19.71 | 19.71
758 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Dumni, House Hold:67 (SM/11447) | SM/11447 | 38.91 | 67 | NEW | 86 | Delayed | 71 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 27.5 | 27.5
759 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) (SM/07272) | SM/07272 | 88.11 | 1275 | RETROFITTING | 86 | Delayed | 97 | 08/12/2020 | 31/12/2024 | 20/02/2024 | 10/02/2021 | 85.54 | 85.54
760 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goala Danga, House Hold:96) (SM/11438) | SM/11438 | 38.91 | 282 | NEW | 86 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 19.71 | 19.71
761 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name : Radha Damodarpur, House Hold:79 (SM/11446) | SM/11446 | 38.91 | 299 | NEW | 86 | Delayed | 50 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 19.59 | 19.59
762 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 (SM/11442) | SM/11442 | 38.91 | 53 | NEW | 86 | Delayed | 68 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 26.33 | 26.33
763 | Water Supply arrangement at Eklavya Model Residential school (EMRS) at Mukutmanipur, Khatra Sub- Division by creating source, Laying Rising Main & Distribution pipeline and Constructing CWR & Pump House (SM/18862) | SM/18862 | 56.72 | 0 | SCHOOL | 86 | Delayed | 0 | 04/10/2023 | 31/12/2024 | 08/08/2024 | 01/03/2024 | 0 | 0
764 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balaramp[ur, House Hold:49) (SM/11149) | SM/11149 | 39.69 | 591 | NEW | 87 | Delayed | 79 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 31.21 | 31.21
765 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Bhetia, House Hold:78 (SM/11449) | SM/11449 | 38.91 | 78 | NEW | 87 | Delayed | 52 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 20.13 | 20.13
766 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) (SM/11435) | SM/11435 | 38.91 | 208 | NEW | 87 | Delayed | 57 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 22.32 | 22.32
767 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) (SM/11154) | SM/11154 | 39.69 | 325 | NEW | 87 | Delayed | 80 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 31.71 | 31.71
768 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Maheshpur , House Hold No.: 84) (SM/11682) | SM/11682 | 39.88 | 867 | NEW | 87 | Delayed | 77 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 30.66 | 30.66
769 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kendgara, House Hold:27) (SM/11152) | SM/11152 | 39.69 | 225 | NEW | 87 | Delayed | 81 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 32.14 | 32.14
770 | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. (SM/12382) | SM/12382 | 600.05 | 1109 | AUGMENTATION | 87 | On track | 54 | 13/09/2022 | 31/03/2025 | 28/11/2024 | 14/11/2022 | 324.51 | 324.51
771 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:66) (SM/11440) | SM/11440 | 38.91 | 66 | NEW | 87 | Delayed | 0 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 0 | 0
772 | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. (SM/16953) | SM/16953 | 183.46 | 770 | AUGMENTATION | 87 | On track | 65 | 16/03/2023 | 31/01/2025 | 30/11/2024 | 22/05/2023 | 118.89 | 118.89
773 | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura (SM/15312) | SM/15312 | 34.74 | 0 | SOLARISATION | 88 | Delayed | 0 | 09/02/2023 | 31/10/2024 | 10/05/2024 | 23/03/2023 | 0 | 0
774 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) (SM/11156) | SM/11156 | 39.69 | 20 | NEW | 88 | Delayed | 80 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 31.59 | 31.59
775 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balananda, House Hold:42) (SM/11147) | SM/11147 | 39.69 | 508 | NEW | 88 | Delayed | 85 | 30/05/2022 | 31/12/2024 | 19/04/2024 | 03/08/2022 | 33.93 | 33.93
776 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shankarpur, House Hold:52) (SM/11436) | SM/11436 | 38.91 | 52 | NEW | 88 | Delayed | 56 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 21.81 | 21.81
777 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shalkota, House Hold:75) (SM/11441) | SM/11441 | 38.91 | 126 | NEW | 88 | Delayed | 56 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 21.69 | 21.69
778 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Thakurhati , House Hold: 74 (SM/11451) | SM/11451 | 38.91 | 74 | NEW | 88 | Delayed | 51 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 19.71 | 19.71
779 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Borajpota, House Hold No.: 33) (SM/11681) | SM/11681 | 39.88 | 33 | NEW | 88 | Delayed | 80 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 31.82 | 31.82
780 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Khamardihi, House Hold:92 (SM/11444) | SM/11444 | 38.91 | 217 | NEW | 88 | Delayed | 52 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 20.13 | 20.13
781 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) (SM/11151) | SM/11151 | 39.69 | 244 | NEW | 89 | On track | 72 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 28.55 | 28.55
782 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-B) (SM/07351) | SM/07351 | 61.18 | 869 | RETROFITTING | 89 | Delayed | 97 | 11/12/2020 | 28/12/2024 | 20/02/2024 | 18/09/2020 | 59.4 | 59.4
783 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Gosai Gram, House Hold:59 (SM/11448) | SM/11448 | 38.91 | 59 | NEW | 89 | On track | 69 | 30/05/2022 | 31/12/2024 | 22/02/2024 | 03/08/2022 | 26.77 | 26.77
784 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Kamar Bera, House Hold:81) (SM/11437) | SM/11437 | 38.91 | 336 | NEW | 89 | On track | 56 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 21.9 | 21.9
785 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap (SM/07244) | SM/07244 | 77.31 | 806 | RETROFITTING | 90 | On track | 31 | 08/12/2020 | 31/12/2024 | 31/08/2024 | 23/02/2023 | 24.25 | 24.25
786 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Hariramp (SM/09313) | SM/09313 | 262.33 | 938 | RETROFITTING | 90 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 01/02/2022 | 254.69 | 254.69
787 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), (SM/09503) | SM/09503 | 239.83 | 2356 | RETROFITTING | 90 | Delayed | 49 | 19/11/2021 |  | 05/04/2024 | 29/10/2021 | 116.6 | 116.38
788 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) (SM/11434) | SM/11434 | 38.91 | 71 | NEW | 90 | On track | 53 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 20.76 | 20.76
789 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Parashia, House Hold:71 (SM/11443) | SM/11443 | 38.91 | 71 | NEW | 90 | On track | 54 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 21.18 | 21.18
790 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg (SM/09315) | SM/09315 | 230.75 | 3480 | RETROFITTING | 90 | On track | 98 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 11/11/2021 | 226.77 | 226.77
791 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishn (SM/09327) | SM/09327 | 254.63 | 2355 | RETROFITTING | 90 | On track | 90 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 11/11/2021 | 230.08 | 229.86
792 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith (SM/09498) | SM/09498 | 247.99 | 2933 | RETROFITTING | 90 | On track | 44 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 01/02/2022 | 108.25 | 108.25
793 | New pipe line with Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas (SM/09632) | SM/09632 | 294.2 | 1796 | RETROFITTING | 90 | On track | 97 | 24/11/2021 | 31/12/2024 | 20/09/2024 | 12/02/2021 | 285.63 | 285.63
794 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma (SM/09534) | SM/09534 | 197.45 | 2339 | RETROFITTING | 90 | On track | 66 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 10/05/2022 | 130.13 | 130.13
795 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. (SM/11823) | SM/11823 | 513.85 | 8274 | RETROFITTING | 90 | On track | 0 | 16/08/2022 | 31/12/2024 | 20/09/2024 | 24/07/2023 | 0 | 0
796 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Ekteswar (Part, 70%) & Sankarhati) of pipe water supply scheme for E (SM/09310) | SM/09310 | 32.92 | 452 | RETROFITTING | 90 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 12/11/2021 | 31.96 | 31.54
797 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 nos. Mouzas (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, P (SM/09328) | SM/09328 | 236.78 | 1891 | RETROFITTING | 90 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 16/11/2021 | 229.89 | 229.89
798 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur (SM/09529) | SM/09529 | 228.15 | 2872 | RETROFITTING | 90 | On track | 60 | 19/11/2021 | 31/12/2024 | 01/07/2024 | 24/06/2020 | 136.13 | 136.13
799 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B (SM/09536) | SM/09536 | 34.65 | 434 | RETROFITTING | 90 | On track | 56 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 31/12/2021 | 19.23 | 15.79
800 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Schem (SM/09330) | SM/09330 | 211.32 | 2161 | RETROFITTING | 90 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 17/12/2021 | 205.16 | 204.63
801 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its (SM/09639) | SM/09639 | 74.39 | 888 | RETROFITTING | 90 | Delayed | 97 | 24/11/2021 |  | 05/04/2024 | 23/09/2021 | 72.23 | 72.23
802 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting (SM/09531) | SM/09531 | 170.99 | 2017 | RETROFITTING | 90 | On track | 65 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 22/02/2022 | 110.87 | 110.87
803 | MINI PIPED WATER SUPPLY SCHEME FOR KALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11013) | SM/11013 | 44.23 | 95 | NEW | 90 | On track | 73 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 32.34 | 32.34
804 | MINI PIPED WATER SUPPLY SCHEME FOR KARAMARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. (SM/11014) | SM/11014 | 39.29 | 60 | NEW | 90 | On track | 74 | 30/05/2022 | 31/12/2024 | 28/11/2024 | 03/08/2022 | 29.18 | 29.18
805 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gamidya (192), Amla Tara (196), Angaria (197), Madan Mohanpur (198), Kheruashol (199), Betajora (200), Bhaluk Khulya (201), Brindabanpur (202), Shirsha (203), Siara (204), Ku (SM/09528) | SM/09528 | 148.3 | 1663 | RETROFITTING | 90 | On track | 49 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 22/02/2022 | 73.22 | 73.22
806 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Amlasol, House Hold No.: 69) (SM/11173) | SM/11173 | 38.64 | 69 | NEW | 90 | On track | 71 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 27.5 | 27.5
807 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa (SM/07766) | SM/07766 | 1310.43 | 14433 | RETROFITTING | 90 | On track | 98 | 11/01/2021 | 31/12/2024 | 02/09/2024 | 12/02/2021 | 1287.86 | 1287.67
808 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S (SM/09329) | SM/09329 | 160.36 | 1144 | RETROFITTING | 90 | On track | 96 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 11/11/2021 | 153.17 | 153.17
809 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui (SM/09621) | SM/09621 | 211.82 | 2822 | RETROFITTING | 90 | On track | 98 | 24/11/2021 | 31/12/2024 | 22/02/2024 | 15/12/2021 | 208.52 | 208.52
810 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Karajbani , House Hold:74 (SM/11452) | SM/11452 | 38.91 | 658 | NEW | 90 | On track | 50 | 30/05/2022 | 31/12/2024 | 08/04/2024 | 03/08/2022 | 19.51 | 19.51
811 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam (SM/07264) | SM/07264 | 83.94 | 1086 | RETROFITTING | 90 | On track | 10 | 08/12/2020 | 31/12/2024 | 31/08/2024 | 12/07/2022 | 8.78 | 8.78
812 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} (SM/09501) | SM/09501 | 92.18 | 2442 | RETROFITTING | 90 | On track | 97 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 13/11/2020 | 89.5 | 89.5
813 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjo (SM/09532) | SM/09532 | 177.6 | 2080 | RETROFITTING | 90 | On track | 63 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 21/04/2022 | 111.61 | 111.61
814 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhanga Bandh (91), Bheduasol (92), Kamalpur (93), Sayer Bankra (99), Kotalpur (100), Ramnagar (101), Dhabani (102), Manipur (105), Guinandi (106), Itapanchira (107), Paharpur (SM/09480) | SM/09480 | 207.69 | 2309 | RETROFITTING | 90 | On track | 68 | 19/11/2021 | 31/12/2024 | 01/07/2024 | 24/06/2020 | 140.7 | 140.7
815 | Survey & collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in primary, upper primary schools anganwadi centers within Bankura District for the financial year 2020-2021 (SM/09928) | SM/09928 | 11.7 | 0 | SUPPORT-WQMSP | 90 | Delayed | 0 | 10/12/2021 |  | 05/04/2024 | 10/01/2022 | 0 | 0
816 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. (SM/06634) | SM/06634 | 104.55 | 0 | SUPPORT-WQMSP | 90 |  | 0 | 05/02/2020 |  | 05/04/2024 | 22/11/2021 | 0 | 0
817 | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/10858) | SM/10858 | 34.21 | 36 | NEW | 92 | Delayed | 79 | 30/05/2022 | 31/07/2024 | 20/04/2024 | 03/08/2022 | 26.85 | 26.85
818 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bagsara, House Hold No.: 25) (SM/11683) | SM/11683 | 39.88 | 25 | NEW | 92 | On track | 74 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 29.6 | 29.6
819 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha , Napra, Bagulia) of MALIARA (Zone - A) under Bankur (SM/09304) | SM/09304 | 85.58 | 974 | RETROFITTING | 92 | On track | 97 | 08/11/2021 | 31/12/2024 | 01/07/2024 | 25/02/2021 | 83.08 | 81.12
820 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Parashe, House Hold No.: 90) (SM/11689) | SM/11689 | 39.88 | 90 | NEW | 92 | On track | 77 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 30.66 | 30.66
821 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09926) | SM/09926 | 532.09 | 2525 | AUGMENTATION | 92 | On track | 83 | 09/12/2021 | 31/01/2025 | 16/12/2024 | 23/09/2021 | 440.62 | 440.62
822 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chhatina, House Hold No.: 80) (SM/11693) | SM/11693 | 39.88 | 80 | NEW | 92 | On track | 77 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 30.66 | 30.66
823 | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl (SM/09633) | SM/09633 | 295.14 | 1657 | RETROFITTING | 92 | On track | 63 | 24/11/2021 | 31/12/2024 | 01/07/2024 | 10/05/2022 | 184.79 | 184.79
824 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09454) | SM/09454 | 510.5 | 1564 | AUGMENTATION | 93 | On track | 87 | 19/11/2021 | 31/01/2025 | 16/12/2024 | 11/03/2022 | 445.85 | 445.85
825 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Basantapur, House Hold No.: 62) (SM/11181) | SM/11181 | 38.64 | 62 | NEW | 93 | On track | 85 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 32.76 | 32.76
826 | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora B (SM/09634) | SM/09634 | 294.27 | 1650 | RETROFITTING | 93 | On track | 61 | 24/11/2021 | 31/12/2024 | 01/07/2024 | 10/05/2022 | 179.8 | 179.8
827 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 60) (SM/11690) | SM/11690 | 39.88 | 60 | NEW | 93 | On track | 77 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 30.54 | 30.54
828 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi (SM/09626) | SM/09626 | 202.38 | 2273 | RETROFITTING | 93 | On track | 100 | 24/11/2021 | 22/12/2024 | 22/02/2024 | 30/12/2021 | 202.38 | 202.38
829 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Mohishkhoar, House Hold No.: 78) (SM/11691) | SM/11691 | 39.88 | 78 | NEW | 93 | On track | 80 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 31.71 | 31.59
830 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Digrya, House Hold No.: 64) (SM/11178) | SM/11178 | 38.64 | 64 | NEW | 93 | On track | 85 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 32.76 | 32.76
831 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Madhurpur, House Hold No.: 93) (SM/11692) | SM/11692 | 39.88 | 93 | NEW | 94 | On track | 77 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 30.66 | 30.66
832 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Brindabanpur, House Hold No.: 95) (SM/11180) | SM/11180 | 38.64 | 407 | NEW | 94 | On track | 79 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 30.66 | 30.66
833 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Hajipur, House Hold No.: 87) (SM/11177) | SM/11177 | 38.64 | 87 | NEW | 95 | On track | 79 | 30/05/2022 | 31/12/2024 | 04/10/2024 | 03/08/2022 | 30.66 | 30.66
834 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Su (SM/09312) | SM/09312 | 206.86 | 1949 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 17/12/2021 | 200.84 | 200.63
835 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa (SM/09320) | SM/09320 | 146.29 | 2035 | RETROFITTING | 95 | On track | 97 | 08/11/2021 | 31/12/2024 | 20/09/2024 | 17/12/2021 | 142.03 | 138.96
836 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, (SM/09625) | SM/09625 | 184.53 | 2610 | RETROFITTING | 95 | On track | 97 | 24/11/2021 | 31/12/2024 | 20/02/2024 | 01/02/2022 | 179.15 | 179.15
837 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band (SM/09479) | SM/09479 | 181.27 | 2267 | RETROFITTING | 95 | On track | 77 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 22/02/2022 | 140.24 | 140.24
838 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under Jal Jeevan Mission (JJM) for 04 nos, Kharigara (302), Dhonara (303), Chingragoalaso (SM/12839) | SM/12839 | 115.16 | 698 | RETROFITTING | 95 | On track | 85 | 22/09/2022 | 31/12/2024 | 20/09/2024 | 28/03/2023 | 97.72 | 97.72
839 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Kumardubi, House Hold No.: 50) (SM/11176) | SM/11176 | 38.64 | 50 | NEW | 96 | On track | 85 | 30/05/2022 | 31/12/2024 | 25/06/2024 | 03/08/2022 | 32.76 | 32.76
840 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1)under S (SM/07765) | SM/07765 | 1524.36 | 17874 | RETROFITTING | 96 | On track | 92 | 11/01/2021 | 31/12/2024 | 20/09/2024 | 12/02/2021 | 1395.56 | 1395.42
841 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI (SM/11822) | SM/11822 | 33.27 | 81 | RETROFITTING | 96 | On track | 82 | 16/08/2022 | 31/12/2024 | 20/09/2024 | 06/04/2023 | 27.19 | 27.19
842 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by (SM/09530) | SM/09530 | 251.99 | 3143 | RETROFITTING | 97 | On track | 72 | 19/11/2021 | 31/12/2024 | 20/09/2024 | 03/03/2022 | 181.52 | 181.52
843 | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura (SM/15318) | SM/15318 | 34.74 | 0 | SOLARISATION | 98 | Delayed | 0 | 09/02/2023 | 31/10/2024 | 10/05/2024 | 17/04/2023 | 0 | 0
844 | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t (SM/09853) | SM/09853 | 293.12 | 7078 | AUGMENTATION | 99 | On track | 79 | 03/12/2021 | 31/12/2024 | 20/09/2024 | 09/02/2022 | 232.46 | 232.46
845 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (6 (SM/07364) | SM/07364 | 69.9 | 788 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 67.86 | 67.86
846 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Dakaisini, Khandari, Bansol, Dhwajmonipur & Damodarpur) of (SM/07260) | SM/07260 | 89.89 | 959 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 87.27 | 87.27
847 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo (SM/07270) | SM/07270 | 100 | 1265 | RETROFITTING | 100 | 100% Physical | 90 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 89.61 | 82.25
848 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mouzas (Junbedia) of HARIALGORA (Z (SM/06817) | SM/06817 | 78.79 | 881 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 78.79 | 78.79
849 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Taldanga, Upar Narrah, Khe (SM/06806) | SM/06806 | 78.26 | 1057 | RETROFITTING | 100 | 100% Physical | 96 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 75.41 | 75.41
850 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Ramchandrapur, Paschim Brindabanpur, Palsana & Saluka) of Jo (SM/07328) | SM/07328 | 95.32 | 923 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 92.54 | 92.54
851 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Wa (SM/07331) | SM/07331 | 99.99 | 1207 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 09/02/2021 | 97.08 | 97.08
852 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 nos. Mouzas (Kastara, Rangamati, Kendana, Sat-deuli) of pipe water supply sc (SM/09311) | SM/09311 | 55.5 | 38 | RETROFITTING | 100 | 100% Physical | 97 | 08/11/2021 | 31/12/2024 | 28/11/2024 | 12/11/2021 | 53.88 | 53.88
853 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an (SM/09643) | SM/09643 | 79.61 | 1015 | RETROFITTING | 100 | 100% Physical | 74 | 24/11/2021 |  | 09/04/2024 | 29/11/2021 | 58.63 | 58.63
854 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and (SM/09618) | SM/09618 | 99.94 | 1119 | RETROFITTING | 100 | 100% Physical | 87 | 24/11/2021 | 30/06/2024 | 01/07/2024 | 23/09/2021 | 87.36 | 87.36
855 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap (SM/09475) | SM/09475 | 57.03 | 0 | RETROFITTING | 100 | 100% Physical | 75 | 19/11/2021 |  | 09/04/2024 | 28/02/2022 | 42.98 | 42.98
856 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo (SM/09305) | SM/09305 | 95.96 | 917 | RETROFITTING | 100 | 100% Physical | 66 | 08/11/2021 | 29/03/2024 | 09/08/2023 | 26/02/2021 | 63.55 | 63.55
857 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari (SM/07322) | SM/07322 | 78.19 | 995 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 75.91 | 75.91
858 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) & Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under (SM/07356) | SM/07356 | 64.72 | 735 | RETROFITTING | 100 | 100% Physical | 84 | 11/12/2020 | 31/08/2024 | 02/09/2024 | 05/02/2021 | 54.05 | 54.05
859 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S (SM/09234) | SM/09234 | 82.8 | 967 | RETROFITTING | 100 | 100% Physical | 92 | 25/05/2021 |  | 09/04/2024 | 23/09/2021 | 76.31 | 76.31
860 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Purunia, sangrampur, Laxminarayanpur, Baharkhulia & Gangadarpu (SM/07256) | SM/07256 | 98.92 | 700 | RETROFITTING | 100 | 100% Physical | 94 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 93.33 | 93.33
861 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan (SM/07306) | SM/07306 | 96.39 | 1304 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 93.58 | 93.58
862 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - II) of MALIARA (Zone - A) under Bankura - I,II & (SM/07307) | SM/07307 | 84.49 | 954 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 31/03/2022 | 12/06/2023 | 25/02/2021 | 82.03 | 82.03
863 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa (SM/07250) | SM/07250 | 88.19 | 918 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 85.63 | 85.63
864 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (1 (SM/07366) | SM/07366 | 79.75 | 945 | RETROFITTING | 100 | 100% Physical | 72 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 09/07/2021 | 57.04 | 56.93
865 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Z (SM/07360) | SM/07360 | 99.9 | 1103 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 30/10/2024 | 02/09/2024 | 05/02/2021 | 96.99 | 96.99
866 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF (SM/07338) | SM/07338 | 89.1 | 955 | RETROFITTING | 100 | 100% Physical | 72 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 63.73 | 113.73
867 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math (SM/07346) | SM/07346 | 99.61 | 1056 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 96.71 | 96.71
868 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas (SM/06801) | SM/06801 | 48.55 | 580 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 46.92 | 46.92
869 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh (SM/07353) | SM/07353 | 66.76 | 828 | RETROFITTING | 100 | 100% Physical | 89 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 23/09/2021 | 59.29 | 42.54
870 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 Nos. Mouzas (Malpara, Harokabedy, Mangalda, Palsora, Kalai, Amdiha, Parasi (SM/07324) | SM/07324 | 96.55 | 1058 | RETROFITTING | 100 | 100% Physical | 73 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 70.14 | 70.14
871 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme ( (SM/09635) | SM/09635 | 69.48 | 813 | RETROFITTING | 100 | 100% Physical | 97 | 24/11/2021 |  | 09/04/2024 | 23/09/2021 | 67.46 | 67.46
872 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm (SM/09496) | SM/09496 | 234.6 | 0 | RETROFITTING | 100 | 100% Physical | 72 | 19/11/2021 |  | 09/04/2024 | 17/12/2021 | 167.89 | 167.89
873 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas by retrofitting of Water Supply Scheme for Pa (SM/09476) | SM/09476 | 56.84 | 569 | RETROFITTING | 100 | 100% Physical | 65 | 19/11/2021 |  | 09/04/2024 | 28/02/2022 | 37.2 | 37.2
874 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u (SM/09641) | SM/09641 | 237.71 | 2304 | RETROFITTING | 100 | 100% Physical | 70 | 24/11/2021 |  | 09/04/2024 | 24/02/2022 | 166.58 | 166.58
875 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Kumirdoha, Gairabad, Fulberia, Dhaban, Bhabanipur, Upargara) (SM/09306) | SM/09306 | 97.18 | 914 | RETROFITTING | 100 | 100% Physical | 80 | 08/11/2021 | 31/12/2024 | 28/11/2024 | 18/02/2021 | 77.29 | 75.04
876 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41) , Baurisol (42) and Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its (SM/06795) | SM/06795 | 88.07 | 1090 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 21/07/2023 | 09/12/2020 | 85.5 | 80.88
877 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo (SM/07341) | SM/07341 | 85.33 | 1066 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 31/12/2024 | 28/11/2024 | 05/02/2021 | 82.51 | 82.51
878 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Bara (SM/07265) | SM/07265 | 75.82 | 874 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 |  | 09/04/2024 | 15/01/2021 | 73.61 | 72.7
879 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar (SM/07255) | SM/07255 | 98.39 | 665 | RETROFITTING | 100 | 100% Physical | 90 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 88.39 | 88.39
880 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Raniban (SM/07362) | SM/07362 | 77.85 | 939 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 75.59 | 75.59
881 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyalda (SM/07240) | SM/07240 | 83.76 | 1131 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 09/07/2021 | 81.32 | 81.32
882 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dadhimukha, Jamboni,Jagdal (SM/07245) | SM/07245 | 81.76 | 1185 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 19/01/2021 | 79.37 | 79.37
883 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, (SM/07315) | SM/07315 | 98.56 | 932 | RETROFITTING | 100 | 100% Physical | 98 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 96.63 | 96.63
884 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola (SM/07318) | SM/07318 | 80.74 | 1164 | RETROFITTING | 100 | 100% Physical | 86 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 04/02/2021 | 69.14 | 69.11
885 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06792) | SM/06792 | 74.89 | 981 | RETROFITTING | 100 | 100% Physical | 69 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 51.31 | 25.22
886 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos mousas (Helna, Fagua kanali, Dumur (SM/07348) | SM/07348 | 93.87 | 1018 | RETROFITTING | 100 | 100% Physical | 62 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/08/2021 | 58.16 | 58.16
887 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis (SM/07334) | SM/07334 | 99.12 | 1254 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 96.24 | 96.24
888 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it (SM/09233) | SM/09233 | 99.93 | 1000 | RETROFITTING | 100 | 100% Physical | 65 | 25/05/2021 | 30/06/2024 | 01/07/2024 | 23/09/2021 | 65.04 | 65.04
889 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by (SM/09235) | SM/09235 | 79.85 | 885 | RETROFITTING | 100 | 100% Physical | 78 | 25/05/2021 |  | 09/04/2024 | 08/11/2021 | 62.57 | 62.57
890 | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A (SM/09502) | SM/09502 | 198.36 | 2274 | RETROFITTING | 100 | 100% Physical | 96 | 19/11/2021 | 31/12/2024 | 28/11/2024 | 31/12/2021 | 191.11 | 191.11
891 | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. (SM/12381) | SM/12381 | 206.2 | 607 | AUGMENTATION | 100 | 100% Physical | 76 | 13/09/2022 |  | 09/04/2024 | 28/01/2022 | 157.15 | 157.15
892 | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas (SM/12840) | SM/12840 | 997.56 | 1946 | AUGMENTATION | 100 | 100% Physical | 12 | 22/09/2022 | 31/05/2023 | 12/06/2023 | 23/02/2023 | 122.09 | 122.09
893 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - I) of MALIARA (Zone - A) under Bankura - I, II (SM/07309) | SM/07309 | 84.49 | 954 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 25/02/2021 | 82.03 | 82.03
894 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dhaldanga, Chak dhaldanga, (SM/07242) | SM/07242 | 79.81 | 1138 | RETROFITTING | 100 | 100% Physical | 85 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 31/12/2020 | 68.17 | 68.17
895 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Nangla, Agaya, Gidhuria, Pachasimul, Mechabaid, Banjurya, Har (SM/07253) | SM/07253 | 90.95 | 872 | RETROFITTING | 100 | 100% Physical | 77 | 08/12/2020 | 31/12/2024 | 28/11/2024 | 27/07/2021 | 69.75 | 69.75
896 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu (SM/07237) | SM/07237 | 75.94 | 1033 | RETROFITTING | 100 | 100% Physical | 100 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 75.94 | 75.94
897 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Shitla, Manjumara, Monoharbati & Pabaya) of Kanchanpur (Zone - (SM/07258) | SM/07258 | 86.63 | 952 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 84.1 | 84.1
898 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou (SM/07317) | SM/07317 | 85.51 | 972 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 24/02/2021 | 83.02 | 83.02
899 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z (SM/07320) | SM/07320 | 77.52 | 990 | RETROFITTING | 100 | 100% Physical | 69 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 25/08/2021 | 53.16 | 53.16
900 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mouzas (Bhangaria, Magra and Sonad (SM/06812) | SM/06812 | 60.55 | 831 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/12/2020 | 60.55 | 60.55
901 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pita Dungri (275) & Kuchiar Mahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh (SM/07354) | SM/07354 | 67.76 | 833 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 65.79 | 65.79
902 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorshal, Dhenga kend, Kushma, Golhati & Bonomadhavpur) of J (SM/07339) | SM/07339 | 81.28 | 841 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 78.79 | 78.79
903 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme (SM/06799) | SM/06799 | 91.99 | 1532 | RETROFITTING | 100 | 100% Physical | 85 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 78.13 | 78.13
904 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, (SM/06802) | SM/06802 | 94.88 | 1209 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 92.44 | 92.44
905 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Patna Joykrishnapur, Kunja (SM/06805) | SM/06805 | 78.14 | 1056 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 78.14 | 78.14
906 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam (SM/07326) | SM/07326 | 72.12 | 998 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 70.02 | 70.02
907 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) (SM/09236) | SM/09236 | 271.55 | 2199 | RETROFITTING | 100 | 100% Physical | 97 | 25/05/2021 |  | 09/04/2024 | 08/10/2020 | 263.64 | 261.86
908 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 (SM/09552) | SM/09552 | 161.82 | 1926 | RETROFITTING | 100 | 100% Physical | 67 | 19/11/2021 |  | 09/04/2024 | 03/03/2022 | 108.26 | 108.26
909 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone (SM/09620) | SM/09620 | 75.16 | 882 | RETROFITTING | 100 | 100% Physical | 93 | 24/11/2021 |  | 09/04/2024 | 29/11/2021 | 70.24 | 70.24
910 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JOR (SM/07310) | SM/07310 | 90.97 | 1185 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 09/07/2021 | 88.32 | 87.98
911 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of (SM/10041) | SM/10041 | 83.4 | 663 | RETROFITTING | 100 | 100% Physical | 86 | 19/01/2022 | 19/12/2024 | 23/07/2024 | 02/06/2023 | 71.72 | 71.72
912 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kulpat Bonkati, Gourangadi (SM/06810) | SM/06810 | 90.12 | 1186 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 87.5 | 87.5
913 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya (SM/09229) | SM/09229 | 89.49 | 1188 | RETROFITTING | 100 | 100% Physical | 72 | 25/05/2021 |  | 09/04/2024 | 08/11/2021 | 64.84 | 64.43
914 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Barsi, Malbedya, Narasinghapur, Arrah, Barabanagram, Khudra b (SM/07241) | SM/07241 | 96.76 | 1062 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 27/07/2021 | 93.87 | 93.87
915 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hare Krishnapur , Dadimukha , Gopbandh , Bankuradanga, Belut , (SM/07305) | SM/07305 | 96.08 | 1303 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 93.29 | 93.29
916 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kalipur, Housibad, Parulia, Biskodar, Joljolia Banshal) of K (SM/07254) | SM/07254 | 74.43 | 873 | RETROFITTING | 100 | 100% Physical | 83 | 08/12/2020 | 31/12/2024 | 28/11/2024 | 05/02/2021 | 61.71 | 61.71
917 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Mouladanga, Mithila, Jagan (SM/07238) | SM/07238 | 76.09 | 1035 | RETROFITTING | 100 | 100% Physical | 98 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 74.38 | 74.38
918 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o (SM/07251) | SM/07251 | 99.13 | 958 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/10/2021 | 96.25 | 96.25
919 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kundurka (43), Paira (44), Simlabandh (45), Bhedua (46) & Lutia (47) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at (SM/07337) | SM/07337 | 56.54 | 721 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 54.9 | 54.87
920 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouza (Talanda, Cahndanpur, Swargabati, Harishpur, Gopinathpur, Brinda (SM/07345) | SM/07345 | 85.97 | 1056 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 83.47 | 83.47
921 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Khejurbedia, Upardihi, Rad (SM/06809) | SM/06809 | 99.97 | 1008 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 97.06 | 97.06
922 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dulaparar (231), Asarda (232), Chandpara (233), Luapara (269), Kemduadangri (273), Benasuli (275), Phulberia (278), Danara (279) mouzas by retrofitting of Piped Water Supply (SM/06791) | SM/06791 | 85.04 | 580 | RETROFITTING | 100 | 100% Physical | 90 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 76.25 | 76.25
923 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sinyajora (32), Bhelaidiha (36), Korkhi (37) , Shyampur (44), Jugidangra (47), Rasikpur (48) and Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for L (SM/06793) | SM/06793 | 67.66 | 675 | RETROFITTING | 100 | 100% Physical | 67 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 45.48 | 45.48
924 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und (SM/07323) | SM/07323 | 89.87 | 751 | RETROFITTING | 100 | 100% Physical | 78 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 69.76 | 69.76
925 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Brindajam, Kaminbedia, Sihikapahari, Hatjore, Simulbedia, Moy (SM/07325) | SM/07325 | 88.06 | 1108 | RETROFITTING | 100 | 100% Physical | 87 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 09/07/2021 | 76.94 | 76.94
926 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Mobarakpur, Chaptara, Send (SM/06803) | SM/06803 | 94.04 | 49304 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 94.04 | 94.04
927 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas (SM/06808) | SM/06808 | 88 | 1013 | RETROFITTING | 100 | 100% Physical | 99 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 86.73 | 86.73
928 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (SM/07358) | SM/07358 | 79.04 | 937 | RETROFITTING | 100 | 100% Physical | 94 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 74.32 | 73.76
929 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chakadoba (73), Balarampur (138), Kubasol (139), Ban Pukhuria (140), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas (SM/07335) | SM/07335 | 99.02 | 1201 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 96.13 | 139.11
930 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur (SM/09237) | SM/09237 | 299.8 | 3263 | RETROFITTING | 100 | 100% Physical | 68 | 25/05/2021 |  | 09/04/2024 | 29/10/2021 | 202.51 | 170.95
931 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) (SM/09630) | SM/09630 | 184.06 | 1960 | RETROFITTING | 100 | 100% Physical | 51 | 24/11/2021 | 31/12/2024 | 28/11/2024 | 31/12/2021 | 94.67 | 94.67
932 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadamara (9), Pukhuria (10), Baranimdiha (13), Rengurbandh (14) & Rajabandh (15) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas un (SM/09640) | SM/09640 | 90.02 | 714 | RETROFITTING | 100 | 100% Physical | 97 | 24/11/2021 |  | 09/04/2024 | 29/11/2021 | 87.4 | 87.4
933 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala) of Nabagr (SM/07342) | SM/07342 | 98.67 | 806 | RETROFITTING | 100 | 100% Physical | 0 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 25/08/2021 | 0 | 0
934 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Basuda, Rajprasadpur, Saldanga, Managram, Dewangrya, Numuigary (SM/07248) | SM/07248 | 83.6 | 946 | RETROFITTING | 100 | 100% Physical | 85 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 71.35 | 71.35
935 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mouzas (Bagapatal, Parasia bad, Ba (SM/06813) | SM/06813 | 60.4 | 829 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 18/02/2021 | 58.64 | 58.64
936 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap (SM/07261) | SM/07261 | 83.44 | 1033 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 81.01 | 81.01
937 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & J (SM/07327) | SM/07327 | 66.26 | 926 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 64.33 | 64.29
938 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas (SM/06800) | SM/06800 | 60.74 | 697 | RETROFITTING | 100 | 100% Physical | 89 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 54.16 | 54.16
939 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Rangametya, Kuladabar, Burat, Deulberia, Murgathol, Ampahari, (SM/07311) | SM/07311 | 88.11 | 1181 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 85.2 | 85.2
940 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jhunka, Shushunia parasibana, Paharbedia, Bharatpur, Kendua) (SM/07252) | SM/07252 | 90.97 | 874 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 31/12/2024 | 28/11/2024 | 23/09/2021 | 88.32 | 88.32
941 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 12 Nos. Mouzas (Enayetpur, Kaleberia, Namoghansara, Kururia Balarampur, Malkur (SM/07262) | SM/07262 | 80.43 | 1032 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 78.09 | 78.08
942 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Bandarkhola, Ramharipur, Katapesia, Kolaberia & Maitha Gopinat (SM/07314) | SM/07314 | 91.63 | 853 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 88.96 | 88.96
943 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahirdya, Fulkusma, Jambede, Nabagram)of Nabagram (Zon - K) unde (SM/07321) | SM/07321 | 97.45 | 802 | RETROFITTING | 100 | 100% Physical | 46 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 25/08/2021 | 45 | 45
944 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gotkanali (45), Bankhola (54), Jarisa (89) & Harinyaguri (90) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06794) | SM/06794 | 86.48 | 1100 | RETROFITTING | 100 | 100% Physical | 34 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 28.99 | 28.83
945 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad (SM/06816) | SM/06816 | 80.94 | 870 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 78.58 | 78.58
946 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas ( Bhalukbasa, Hrtyasol, Kus (SM/07344) | SM/07344 | 95.35 | 819 | RETROFITTING | 100 | 100% Physical | 49 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 19/01/2021 | 46.94 | 46.94
947 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na (SM/07347) | SM/07347 | 93.49 | 1055 | RETROFITTING | 100 | 100% Physical | 85 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 10/02/2021 | 79.81 | 79.81
948 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur (SM/09228) | SM/09228 | 255.23 | 2415 | RETROFITTING | 100 | 100% Physical | 65 | 25/05/2021 |  | 09/04/2024 | 12/05/2022 | 166.74 | 166.74
949 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B a (SM/09232) | SM/09232 | 82.52 | 930 | RETROFITTING | 100 | 100% Physical | 91 | 25/05/2021 |  | 09/04/2024 | 08/11/2021 | 75.27 | 75.27
950 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib (SM/09499) | SM/09499 | 231.41 | 2721 | RETROFITTING | 100 | 100% Physical | 97 | 19/11/2021 | 31/12/2024 | 28/11/2024 | 31/12/2021 | 224.67 | 224.67
951 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jaba Balarampur (68), Bagjata (78), Debagram (79), Baidyanathpur (80), Mankhamar (81), Bhatgram (82), Banamalipur (83), Mukundabati (84), Lodna (89) & Madanpur (90) mouzas by (SM/09481) | SM/09481 | 164.78 | 2000 | RETROFITTING | 100 | 100% Physical | 80 | 19/11/2021 | 29/03/2024 | 11/08/2023 | 04/03/2022 | 131.54 | 131.54
952 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 02 Nos. Mouzas (Pinguri & Tentulpoha) of MALIARA (Zone - A) under Bankura - I, (SM/07308) | SM/07308 | 85.15 | 999 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 25/02/2021 | 82.67 | 82.67
953 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Ladna, Mathana, Kodalia) of Joytunga (Zone - H) under Banku (SM/07312) | SM/07312 | 85.93 | 859 | RETROFITTING | 100 | 100% Physical | 100 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 85.93 | 85.93
954 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Talgaria (93), Itamara (94), Uganpathar (95), Benagaria (96), Pathardihi (97), Jambedya (98), Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangam (SM/07267) | SM/07267 | 96.51 | 1056 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 93.7 | 93.7
955 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra (SM/07257) | SM/07257 | 94.9 | 931 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 92.13 | 92.13
956 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R (SM/07363) | SM/07363 | 97.85 | 1178 | RETROFITTING | 100 | 100% Physical | 77 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 74.97 | 74.92
957 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supp (SM/07365) | SM/07365 | 65.48 | 757 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 63.57 | 63.57
958 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70), Jamdahara (71), Tilabani (72), Dhanga Dungri (74), Mirgi (75), Basudebpur (79), Jhat Pukhuria (80) & Patasimul (1 (SM/07367) | SM/07367 | 99.39 | 1201 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 96.49 | 146.48
959 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo (SM/07259) | SM/07259 | 86.91 | 955 | RETROFITTING | 100 | 100% Physical | 100 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 86.91 | 86.91
960 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouza (Bandarkoda, Bhairabdanga, Barkura, Radhakantapur, Kantabesa, Ni (SM/07263) | SM/07263 | 99.4 | 1052 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 29/12/2020 | 96.51 | 96.51
961 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bamdhantur, Nabada, Sibara (SM/07316) | SM/07316 | 99.71 | 931 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 96.8 | 96.8
962 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (SM/06796) | SM/06796 | 99.94 | 384 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 99.94 | 99.94
963 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r (SM/06797) | SM/06797 | 77.86 | 343 | RETROFITTING | 100 | 100% Physical | 0 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/12/2020 | 0 | 0
964 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-H (SM/07355) | SM/07355 | 61.82 | 716 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 15/01/2021 | 60.02 | 60.02
965 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gourangadihi, Ledadihi, Ra (SM/06818) | SM/06818 | 78.36 | 872 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 18/02/2021 | 76.08 | 76.08
966 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, (SM/06807) | SM/06807 | 99.9 | 1008 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 99.9 | 99.9
967 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh W (SM/07357) | SM/07357 | 88.45 | 561 | RETROFITTING | 100 | 100% Physical | 87 | 11/12/2020 | 31/08/2024 | 02/09/2024 | 18/01/2021 | 76.89 | 76.89
968 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas ( Baraleddya, Dhagoria, Ban (SM/07329) | SM/07329 | 96.08 | 811 | RETROFITTING | 100 | 100% Physical | 64 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 04/02/2021 | 61.96 | 61.96
969 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Raniban (SM/07332) | SM/07332 | 86.55 | 957 | RETROFITTING | 100 | 100% Physical | 78 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 67.56 | 67.56
970 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Sc (SM/07333) | SM/07333 | 61.29 | 664 | RETROFITTING | 100 | 100% Physical | 82 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 50.17 | 50.17
971 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Narasole, Radhaballavpur, Gopinathdihi, Taljhoria, Namabad, K (SM/07239) | SM/07239 | 96.29 | 924 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 93.48 | 93.48
972 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Nabagram, Vidyadharpur, Ai (SM/06804) | SM/06804 | 92.61 | 1209 | RETROFITTING | 100 | 100% Physical | 100 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 92.61 | 92.61
973 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku (SM/07336) | SM/07336 | 63.54 | 617 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 61.69 | 61.69
974 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh (SM/09319) | SM/09319 | 254.76 | 2881 | RETROFITTING | 100 | 100% Physical | 69 | 08/11/2021 | 31/12/2024 | 28/11/2024 | 31/12/2021 | 175.3 | 175.3
975 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan (SM/09629) | SM/09629 | 159.63 | 1984 | RETROFITTING | 100 | 100% Physical | 82 | 24/11/2021 | 31/12/2024 | 28/11/2024 | 31/12/2021 | 130.51 | 130.51
976 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kasipur (230), Indkucha (231), Dhanara (234), Nekra Sonda (246), Sabudad (253), Dumuria (254), Dhargram (255), Sial Pahari (256) & Dhabani (257) mouzas by retrofitting Zone-H (SM/07361) | SM/07361 | 99.88 | 1117 | RETROFITTING | 100 | 100% Physical | 35 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 35.03 | 35.03
977 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kusum Goria, Tajpur Rampur, Rajmadhavtir, Kotalpukur & Mahidar (SM/07243) | SM/07243 | 77.66 | 963 | RETROFITTING | 100 | 100% Physical | 96 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 24/02/2021 | 74.71 | 74.71
978 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas (Dhaboagram, Tantkanali, Ni (SM/07247) | SM/07247 | 85.75 | 920 | RETROFITTING | 100 | 100% Physical | 97 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 31/12/2020 | 83.25 | 83.25
979 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Guniada (1), Chalka (2), Chatanibaid (3), Bangopalpur (4) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph (SM/07266) | SM/07266 | 71.22 | 845 | RETROFITTING | 100 | 100% Physical | 50 | 08/12/2020 | 31/08/2024 | 02/09/2024 | 18/01/2021 | 35.73 | 35.73
980 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bara Gajra (103), Asberya (104), Kaliahuta (105), Jadurbankata (106), Nischintapur (107), Kankata (127), Dharra Muli (128) & Bagaldhara (129) mouzas by retrofitting Zone-F (M (SM/07269) | SM/07269 | 89.36 | 1043 | RETROFITTING | 100 | 100% Physical | 29 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 25.9 | 25.9
981 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bara Bendya, Joytunga, Kostia & Khemua) of Joytunga (Zone - (SM/07313) | SM/07313 | 97.22 | 819 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 28/02/2022 | 12/06/2023 | 19/02/2021 | 94.39 | 93.55
982 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under (SM/07319) | SM/07319 | 77.62 | 992 | RETROFITTING | 100 | 100% Physical | 97 | 10/12/2020 | 31/12/2024 | 28/11/2024 | 19/01/2021 | 75.35 | 75.35
983 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan (SM/06798) | SM/06798 | 91.53 | 336 | RETROFITTING | 100 | 100% Physical | 80 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 73.38 | 73.38
984 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria (SM/06811) | SM/06811 | 90.1 | 1186 | RETROFITTING | 100 | 100% Physical | 81 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 73.15 | 73.15
985 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal (SM/06814) | SM/06814 | 86.25 | 1212 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 83.74 | 83.74
986 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kendboni, Kantaboni, Mamur (SM/06815) | SM/06815 | 86.39 | 1213 | RETROFITTING | 100 | 100% Physical | 97 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 08/10/2020 | 83.88 | 83.84
987 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Chhendua, Chamkara, Fengab (SM/07343) | SM/07343 | 99.07 | 994 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 19/01/2021 | 96.18 | 96.17
988 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su (SM/07359) | SM/07359 | 99.99 | 1147 | RETROFITTING | 100 | 100% Physical | 97 | 11/12/2020 | 28/02/2022 | 12/06/2023 | 18/01/2021 | 97.08 | 97.08
989 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, (SM/09316) | SM/09316 | 272.68 | 3242 | RETROFITTING | 100 | 100% Physical | 97 | 08/11/2021 | 31/12/2024 | 28/11/2024 | 11/11/2021 | 264.73 | 264.73
990 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under (SM/09227) | SM/09227 | 51.96 | 327 | RETROFITTING | 100 | 100% Physical | 97 | 25/05/2021 |  | 09/04/2024 | 11/02/2021 | 50.44 | 48.32
991 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368), Deuli (369) & Majura (372) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF (SM/09230) | SM/09230 | 89 | 1179 | RETROFITTING | 100 | 100% Physical | 86 | 25/05/2021 | 30/11/2024 | 25/09/2024 | 08/11/2021 | 76.31 | 76.31
992 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme (SM/09497) | SM/09497 | 272.39 | 3319 | RETROFITTING | 100 | 100% Physical | 63 | 19/11/2021 |  | 09/04/2024 | 03/01/2022 | 171.75 | 171.75
993 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Jamrepara (295), Debgram (296), Agaya (350), Ampata (351) & Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjo (SM/09642) | SM/09642 | 84.2 | 1030 | RETROFITTING | 100 | 100% Physical | 58 | 24/11/2021 |  | 09/04/2024 | 29/11/2021 | 49.07 | 48.88
994 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) (SM/09500) | SM/09500 | 297.84 | 2933 | RETROFITTING | 100 | 100% Physical | 88 | 19/11/2021 |  | 09/04/2024 | 03/01/2022 | 261.53 | 259.7
995 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5), Elora (7), Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirba (SM/07268) | SM/07268 | 77.68 | 919 | RETROFITTING | 100 | 100% Physical | 95 | 08/12/2020 | 28/02/2022 | 12/06/2023 | 05/02/2021 | 73.58 | 73.58
996 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota (SM/06790) | SM/06790 | 86.99 | 1015 | RETROFITTING | 100 | 100% Physical | 74 | 23/09/2020 | 28/02/2022 | 12/06/2023 | 09/10/2020 | 64.66 | 64.66
997 | Augmentation of Panchal Zone-I Water Supply Scheme (SM/17233) | SM/17233 | 23.84 | 6 | AUGMENTATION | 100 | 100% Physical | 72 | 15/03/2023 | 31/12/2024 | 30/11/2024 | 28/03/2023 | 17.15 | 17.15
998 | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura (SM/10348) | SM/10348 | 11.44 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 100 | 100% Physical | 0 | 16/03/2022 |  | 11/11/2022 | 10/08/2020 | 0 | 0
Total |  |  | 242322.25 | 858679 | [8 empty] | 89095.28 | 87788.95