## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16969) | SM/16969 | 640.4 | 478 | AUGMENTATION | 0 | 0% Physical | 31 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 24/07/2023 | 197.41 | 197.41
2 | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16958) | SM/16958 | 289.59 | 280 | AUGMENTATION | 0 | 0% Physical | 59 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 172.06 | 172.06
3 | Augmentation of Morar Zone-A Water Supply Scheme (SM/17237) | SM/17237 | 420.31 | 404 | AUGMENTATION | 0 | 0% Physical | 50 | 15/03/2023 | 30/09/2025 | 16/05/2025 | 24/07/2023 | 208.19 | 208.19
4 | Augmentation of Benda water supply scheme (SM/17244) | SM/17244 | 273.28 | 80 | AUGMENTATION | 0 | 0% Physical | 31 | 15/03/2023 | 31/10/2025 | 16/05/2025 | 19/07/2023 | 84.39 | 84.39
5 | Augmentation of Radhanagar Zone-II Water Supply Scheme (SM/17691) | SM/17691 | 219.61 | 165 | AUGMENTATION | 0 | 0% Physical | 42 | 17/03/2023 | 31/10/2025 | 16/05/2025 | 28/07/2023 | 93.16 | 93.16
6 | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. (SM/16973) | SM/16973 | 417.13 | 590 | AUGMENTATION | 0 | 0% Physical | 42 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 24/07/2023 | 175.91 | 172.81
7 | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16968) | SM/16968 | 447.32 | 431 | AUGMENTATION | 0 | 0% Physical | 46 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 19/07/2023 | 205.09 | 205.09
8 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17280) | SM/17280 | 327.8 | 390 | AUGMENTATION | 0 | 0% Physical | 56 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 27/07/2023 | 184.95 | 184.95
9 | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme (SM/18424) | SM/18424 | 1092.92 | 330 | AUGMENTATION | 0 | 0% Physical | 7 | 18/07/2023 | 08/02/2025 | 16/05/2025 | 24/08/2023 | 78.42 | 78.42
10 | Augmentation of Kushmuri Zone-A Water Supply Scheme (SM/17420) | SM/17420 | 288.97 | 55 | AUGMENTATION | 0 | 0% Physical | 31 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 28/07/2023 | 89 | 89
11 | Augmentation of Radhanagar Zone-I Water Supply Scheme (SM/17690) | SM/17690 | 389.87 | 205 | AUGMENTATION | 0 | 0% Physical | 38 | 17/03/2023 | 31/10/2025 | 16/05/2025 | 28/07/2023 | 148.91 | 148.91
12 | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh (SM/18612) | SM/18612 | 5127.01 | 0 | AUGMENTATION | 0 | 0% Physical | 25 | 31/07/2023 | 08/02/2025 | 16/05/2025 | 04/10/2023 | 1257.7 | 1257.7
13 | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) (SM/10290) | SM/10290 | 1004.54 | 4030 | AUGMENTATION | 0 | 0% Physical | 46 | 28/02/2022 | 31/05/2025 | 16/05/2025 | 05/01/2023 | 458.61 | 458.61
14 | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16954) | SM/16954 | 127.61 | 900 | AUGMENTATION | 0 | 0% Physical | 37 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 02/06/2023 | 46.9 | 46.9
15 | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17236) | SM/17236 | 486.42 | 290 | AUGMENTATION | 0 | 0% Physical | 43 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 19/05/2023 | 209.19 | 209.19
16 | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17697) | SM/17697 | 579.05 | 538 | AUGMENTATION | 0 | 0% Physical | 38 | 17/03/2023 | 31/12/2025 | 16/05/2025 | 19/07/2023 | 217.69 | 213.82
17 | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u (SM/18390) | SM/18390 | 2538.24 | 6421 | AUGMENTATION | 0 | 0% Physical | 32 | 11/07/2023 | 31/12/2025 | 16/05/2025 | 14/08/2023 | 805.12 | 781.26
18 | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18894) | SM/18894 | 770.48 | 350 | AUGMENTATION | 0 | 0% Physical | 1 | 05/10/2023 | 05/08/2025 | 16/05/2025 | 31/10/2023 | 11.02 | 11.02
19 | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18895) | SM/18895 | 882.2 | 50 | AUGMENTATION | 0 | 0% Physical | 14 | 05/10/2023 | 05/12/2025 | 16/05/2025 | 09/02/2024 | 122.41 | 122.41
20 | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. (SM/11980) | SM/11980 | 1043.82 | 3930 | AUGMENTATION | 0 | 0% Physical | 75 | 31/08/2022 | 30/06/2025 | 16/05/2025 | 06/01/2022 | 784.38 | 784.38
21 | Augmentation of Ajodhya Water Supply Scheme (SM/17246) | SM/17246 | 320.23 | 480 | AUGMENTATION | 0 | 0% Physical | 40 | 15/03/2023 | 30/09/2025 | 16/05/2025 | 24/07/2023 | 128.29 | 128.29
22 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09454) | SM/09454 | 510.5 | 1564 | AUGMENTATION | 0 | 0% Physical | 87 | 19/11/2021 | 31/10/2025 | 16/05/2025 | 11/03/2022 | 445.85 | 445.85
23 | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18231) | SM/18231 | 153.99 | 310 | AUGMENTATION | 0 | 0% Physical | 14 | 05/06/2023 | 08/02/2025 | 16/05/2025 | 17/03/2023 | 21.23 | 21.23
24 | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/16980) | SM/16980 | 433.81 | 110 | AUGMENTATION | 0 | 0% Physical | 9 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 38.02 | 38.02
25 | Augmentation of Kushmuri Zone-B Water Supply Scheme (SM/17682) | SM/17682 | 309.8 | 190 | AUGMENTATION | 0 | 0% Physical | 33 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 12/09/2023 | 102.95 | 102.95
26 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME (SM/18495) | SM/18495 | 1126 | 3991 | AUGMENTATION | 0 | 0% Physical | 4 | 26/07/2023 | 08/02/2025 | 16/05/2025 | 14/08/2023 | 48.23 | 48.23
27 | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16971) | SM/16971 | 607.96 | 176 | AUGMENTATION | 18 | Delayed | 7 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 09/10/2023 | 43.28 | 43.28
28 | Augmentation for Gouripur Water Supply Scheme. (SM/17120) | SM/17120 | 116.24 | 120 | AUGMENTATION | 20 | Delayed | 70 | 16/03/2023 | 31/10/2025 | 16/05/2025 | 19/04/2023 | 80.86 | 80.86
29 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME (SM/14650) | SM/14650 | 89 | 184 | AUGMENTATION | 20 | Delayed | 21 | 31/01/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 18.93 | 18.93
30 | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16966) | SM/16966 | 478.54 | 743 | AUGMENTATION | 20 | Delayed | 25 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 18/07/2023 | 119.32 | 106.24
31 | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). (SM/17291) | SM/17291 | 244.22 | 340 | AUGMENTATION | 20 | Delayed | 45 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 18/04/2023 | 109.65 | 109.65
32 | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17242) | SM/17242 | 503.31 | 100 | AUGMENTATION | 25 | Delayed | 18 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 08/06/2023 | 89.55 | 89.55
33 | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17304) | SM/17304 | 485.66 | 260 | AUGMENTATION | 25 | Delayed | 16 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 17/03/2023 | 76.64 | 76.64
34 | Augmentation of Betanal Zone-B Water Supply Scheme (SM/17418) | SM/17418 | 386.52 | 222 | AUGMENTATION | 27 | Delayed | 11 | 18/03/2023 | 30/06/2025 | 16/05/2025 | 13/07/2023 | 42.15 | 42.15
35 | Augmentation of Betanal Zone-A Water Supply Scheme (SM/17692) | SM/17692 | 267.76 | 251 | AUGMENTATION | 27 | Delayed | 34 | 17/03/2023 | 30/06/2025 | 16/05/2025 | 14/08/2023 | 90.06 | 90.06
36 | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. (SM/17297) | SM/17297 | 869.82 | 350 | AUGMENTATION | 27 | Delayed | 5 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 07/09/2022 | 45.23 | 45.23
37 | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17123) | SM/17123 | 230.53 | 544 | AUGMENTATION | 29 | Delayed | 29 | 16/03/2023 | 30/04/2025 | 17/01/2025 | 14/08/2023 | 67.19 | 67.19
38 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME (SM/15001) | SM/15001 | 395.06 | 1025 | AUGMENTATION | 30 | Delayed | 23 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 90.47 | 90.47
39 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/B WATER SUPPLY SCHEME (SM/15002) | SM/15002 | 447.46 | 1004 | AUGMENTATION | 31 | Delayed | 14 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 63.64 | 63.64
40 | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16972) | SM/16972 | 601.7 | 100 | AUGMENTATION | 32 | Delayed | 22 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 11/04/2023 | 134.03 | 134.03
41 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. (SM/10292) | SM/10292 | 3658.45 | 5831 | AUGMENTATION | 32 | Delayed | 34 | 28/02/2022 | 30/06/2026 | 16/05/2025 | 10/08/2021 | 1258.75 | 1258.75
42 | Augmentation of Prakash Zone-B Water Supply Scheme (SM/16945) | SM/16945 | 188.68 | 210 | AUGMENTATION | 35 | Delayed | 7 | 16/03/2023 | 31/10/2025 | 16/05/2025 | 19/07/2023 | 13.63 | 13.63
43 | Augmentation of Kotulpur Piped Water Supply Scheme. (SM/09981) | SM/09981 | 842.25 | 4060 | AUGMENTATION | 35 | Delayed | 58 | 16/12/2021 | 30/06/2025 | 16/05/2025 | 10/05/2022 | 491.19 | 491.19
44 | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17249) | SM/17249 | 220.71 | 757 | AUGMENTATION | 38 | Delayed | 14 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 30.88 | 30.88
45 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME (SM/15003) | SM/15003 | 656.7 | 1800 | AUGMENTATION | 40 | Delayed | 27 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 180.51 | 180.51
46 | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/18403) | SM/18403 | 2747.96 | 3000 | AUGMENTATION | 44 | Delayed | 23 | 12/07/2023 | 31/12/2025 | 16/05/2025 | 25/07/2023 | 627.16 | 625.97
47 | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas (SM/09879) | SM/09879 | 416.45 | 1358 | AUGMENTATION | 44 | Delayed | 22 | 08/12/2021 | 31/12/2025 | 16/05/2025 | 27/09/2022 | 93.04 | 93.04
48 | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17702) | SM/17702 | 709.58 | 603 | AUGMENTATION | 45 | Delayed | 38 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 18/07/2023 | 267.94 | 267.94
49 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME (SM/16936) | SM/16936 | 466.25 | 1106 | AUGMENTATION | 45 | Delayed | 19 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 22/05/2023 | 89.32 | 89.32
50 | Augmentation of Chuamasina Zone-A Water Supply Scheme (SM/17696) | SM/17696 | 390.83 | 410 | AUGMENTATION | 45 | Delayed | 25 | 17/03/2023 | 31/12/2025 | 16/05/2025 | 24/07/2023 | 98.13 | 98.13
51 | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). (SM/18423) | SM/18423 | 1215.26 | 3575 | AUGMENTATION | 45 | Delayed | 33 | 18/07/2023 | 08/02/2025 | 16/05/2025 | 18/07/2023 | 397.9 | 397.9
52 | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17292) | SM/17292 | 752.47 | 210 | AUGMENTATION | 45 | Delayed | 16 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 18/07/2023 | 120.82 | 119.64
53 | Augmentation of Akui Zone-B Water Supply Scheme (SM/17228) | SM/17228 | 332.35 | 143 | AUGMENTATION | 45 | Delayed | 42 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 28/07/2023 | 138.31 | 138.31
54 | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17705) | SM/17705 | 271.86 | 630 | AUGMENTATION | 46 | Delayed | 44 | 17/03/2023 | 31/10/2025 | 16/05/2025 | 27/07/2023 | 120.14 | 120.14
55 | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17434) | SM/17434 | 632.28 | 215 | AUGMENTATION | 47 | Delayed | 14 | 18/03/2023 | 31/05/2025 | 16/05/2025 | 27/07/2023 | 89.35 | 89.35
56 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME (SM/16935) | SM/16935 | 999.97 | 3815 | AUGMENTATION | 48 | Delayed | 17 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 24/05/2023 | 172.41 | 172.41
57 | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17694) | SM/17694 | 473.96 | 680 | AUGMENTATION | 48 | Delayed | 37 | 17/03/2023 | 31/12/2025 | 16/05/2025 | 18/07/2023 | 174.4 | 174.4
58 | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16961) | SM/16961 | 456.92 | 540 | AUGMENTATION | 49 | Delayed | 35 | 16/03/2023 | 30/09/2025 | 16/05/2025 | 27/07/2023 | 159.68 | 159.68
59 | Augmentation of Karisunda Water Supply Scheme (SM/17419) | SM/17419 | 311.6 | 100 | AUGMENTATION | 50 | Delayed | 23 | 18/03/2023 | 30/09/2025 | 16/05/2025 | 28/07/2023 | 71.37 | 71.37
60 | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16960) | SM/16960 | 678.24 | 730 | AUGMENTATION | 50 | Delayed | 11 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 18/07/2023 | 77.18 | 77.18
61 | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). (SM/16950) | SM/16950 | 246.4 | 80 | AUGMENTATION | 52 | Delayed | 32 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 11/04/2023 | 79.8 | 79.8
62 | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' (SM/17700) | SM/17700 | 262.44 | 310 | AUGMENTATION | 52 | Delayed | 38 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 11/04/2023 | 101.03 | 101.03
63 | Augmentation works for Lakshmanpur (Zone L) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17313) | SM/17313 | 347.79 | 1025 | AUGMENTATION | 52 | Delayed | 25 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 18/07/2023 | 88.68 | 88.68
64 | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas (SM/09924) | SM/09924 | 874.28 | 3432 | AUGMENTATION | 53 | Delayed | 33 | 10/12/2021 | 31/12/2025 | 16/05/2025 | 13/04/2022 | 291.57 | 291.57
65 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME (SM/16261) | SM/16261 | 509.65 | 1415 | AUGMENTATION | 55 | Delayed | 23 | 24/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 115.12 | 115.12
66 | Augmentation of Rol Zone-A Water Supply Scheme (SM/17693) | SM/17693 | 165.71 | 50 | AUGMENTATION | 55 | Delayed | 49 | 17/03/2023 | 31/08/2025 | 16/05/2025 | 28/07/2023 | 81.74 | 81.74
67 | Augmentation of Rol Zone-B Water Supply Scheme (SM/17683) | SM/17683 | 341.82 | 77 | AUGMENTATION | 55 | Delayed | 29 | 17/03/2023 | 31/08/2025 | 16/05/2025 | 19/07/2023 | 100.03 | 100.03
68 | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17295) | SM/17295 | 790.33 | 325 | AUGMENTATION | 55 | Delayed | 17 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 27/07/2023 | 135.04 | 135.04
69 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME (SM/14091) | SM/14091 | 816.64 | 2305 | AUGMENTATION | 55 | Delayed | 7 | 12/12/2022 | 31/07/2025 | 16/05/2025 | 24/05/2022 | 56.36 | 56.36
70 | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18893) | SM/18893 | 464 | 60 | AUGMENTATION | 55 | Delayed | 1 | 05/10/2023 | 05/05/2025 | 16/05/2025 | 09/02/2024 | 2.47 | 2.47
71 | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17252) | SM/17252 | 250.9 | 480 | AUGMENTATION | 55 | Delayed | 6 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 20/03/2023 | 14.02 | 14.02
72 | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/17703) | SM/17703 | 248.23 | 850 | AUGMENTATION | 55 | Delayed | 11 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 11/09/2023 | 27.32 | 27.32
73 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17712) | SM/17712 | 347.13 | 520 | AUGMENTATION | 57 | Delayed | 39 | 17/03/2023 | 30/09/2025 | 16/05/2025 | 18/07/2023 | 134.24 | 125.29
74 | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16959) | SM/16959 | 376.93 | 290 | AUGMENTATION | 57 | Delayed | 33 | 16/03/2023 | 30/09/2025 | 16/05/2025 | 18/07/2023 | 123.01 | 123.01
75 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). (SM/17428) | SM/17428 | 688.26 | 840 | AUGMENTATION | 57 | Delayed | 28 | 18/03/2023 | 30/06/2025 | 16/05/2025 | 18/07/2023 | 192.17 | 187.14
76 | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17424) | SM/17424 | 392.78 | 281 | AUGMENTATION | 59 | Delayed | 27 | 18/03/2023 | 30/09/2025 | 16/05/2025 | 01/08/2023 | 105.98 | 96.66
77 | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. (SM/17301) | SM/17301 | 995.79 | 9820 | AUGMENTATION | 59 | Delayed | 67 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 11/11/2022 | 663.03 | 663.03
78 | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17235) | SM/17235 | 231.27 | 230 | AUGMENTATION | 60 | Delayed | 42 | 15/03/2023 | 31/10/2025 | 16/05/2025 | 13/07/2023 | 97.42 | 97.42
79 | Augmentation of Chuamasina Zone-B Water Supply Scheme (SM/17427) | SM/17427 | 243.49 | 260 | AUGMENTATION | 60 | Delayed | 36 | 18/03/2023 | 31/05/2025 | 16/05/2025 | 24/07/2023 | 88.45 | 88.45
80 | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme (SM/17707) | SM/17707 | 675.82 | 320 | AUGMENTATION | 60 | Delayed | 8 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 28/03/2023 | 53.89 | 53.89
81 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). (SM/17245) | SM/17245 | 639.01 | 430 | AUGMENTATION | 62 | Delayed | 28 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 18/07/2023 | 180.65 | 180.65
82 | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17714) | SM/17714 | 863.2 | 310 | AUGMENTATION | 62 | Delayed | 7 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 09/10/2023 | 61.41 | 61.41
83 | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17234) | SM/17234 | 480.48 | 920 | AUGMENTATION | 62 | Delayed | 22 | 15/03/2023 | 31/10/2025 | 16/05/2025 | 18/07/2023 | 108.08 | 108.08
84 | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17429) | SM/17429 | 464.58 | 225 | AUGMENTATION | 63 | Delayed | 16 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 25/05/2023 | 72.96 | 72.96
85 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). (SM/17259) | SM/17259 | 999.07 | 4059 | AUGMENTATION | 63 | Delayed | 50 | 15/03/2023 | 31/10/2025 | 16/05/2025 | 28/08/2023 | 494.79 | 467.65
86 | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17240) | SM/17240 | 547.7 | 344 | AUGMENTATION | 64 | Delayed | 21 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 17/08/2023 | 112.48 | 112.48
87 | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17713) | SM/17713 | 743.39 | 230 | AUGMENTATION | 64 | Delayed | 34 | 17/03/2023 | 30/06/2025 | 16/05/2025 | 13/07/2023 | 251.91 | 251.91
88 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). (SM/17285) | SM/17285 | 622.12 | 3576 | AUGMENTATION | 64 | Delayed | 42 | 15/03/2023 | 31/08/2025 | 16/05/2025 | 23/02/2023 | 262.11 | 262.11
89 | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/16977) | SM/16977 | 234.93 | 350 | AUGMENTATION | 65 | Delayed | 14 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 28/03/2023 | 33.05 | 33.05
90 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17288) | SM/17288 | 976.27 | 780 | AUGMENTATION | 65 | Delayed | 19 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 24/07/2023 | 189.41 | 169.5
91 | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/18892) | SM/18892 | 799.62 | 100 | AUGMENTATION | 65 | Delayed | 12 | 05/10/2023 | 05/01/2025 | 16/05/2025 | 31/10/2023 | 97.33 | 97.33
92 | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16964) | SM/16964 | 694.01 | 748 | AUGMENTATION | 65 | Delayed | 27 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 01/08/2023 | 184.4 | 180.48
93 | Augmentation of Akui Zone-A Water Supply Scheme (SM/16943) | SM/16943 | 228.16 | 250 | AUGMENTATION | 65 | On track | 28 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 64.52 | 64.52
94 | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17704) | SM/17704 | 235.52 | 302 | AUGMENTATION | 65 | Delayed | 33 | 17/03/2023 | 30/06/2025 | 16/05/2025 | 14/08/2023 | 77.43 | 77.43
95 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17287) | SM/17287 | 260.78 | 490 | AUGMENTATION | 65 | Delayed | 41 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 18/07/2023 | 108.18 | 108.18
96 | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16967) | SM/16967 | 749.13 | 900 | AUGMENTATION | 65 | Delayed | 30 | 16/03/2023 | 30/11/2025 | 16/05/2025 | 24/07/2023 | 222.52 | 222.52
97 | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/16984) | SM/16984 | 500.19 | 470 | AUGMENTATION | 65 | On track | 20 | 16/03/2023 | 31/10/2025 | 16/05/2025 | 13/07/2023 | 101.81 | 101.81
98 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. (SM/09852) | SM/09852 | 580.47 | 0 | AUGMENTATION | 65 | Delayed | 41 | 03/12/2021 | 30/06/2025 | 16/05/2025 | 27/07/2021 | 236.93 | 236.93
99 | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16956) | SM/16956 | 632.16 | 968 | AUGMENTATION | 65 | Delayed | 44 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 24/07/2023 | 280.83 | 280.83
100 | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17251) | SM/17251 | 455.28 | 230 | AUGMENTATION | 65 | Delayed | 11 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 25/05/2023 | 48.98 | 38.43
101 | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). (SM/17303) | SM/17303 | 285.68 | 480 | AUGMENTATION | 65 | Delayed | 9 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 01/09/2023 | 24.64 | 24.64
102 | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16970) | SM/16970 | 488.77 | 500 | AUGMENTATION | 65 | Delayed | 22 | 16/03/2023 | 30/06/2025 | 16/05/2025 | 13/07/2023 | 109.45 | 109.45
103 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME (SM/15007) | SM/15007 | 362.07 | 565 | AUGMENTATION | 65 | Delayed | 28 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 101.03 | 101.03
104 | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17241) | SM/17241 | 499.85 | 150 | AUGMENTATION | 65 | Delayed | 19 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 18/07/2023 | 94.8 | 94.8
105 | Augmentation of Sashpur Zone-A Water Supply Scheme (SM/18114) | SM/18114 | 361.86 | 340 | AUGMENTATION | 65 | On track | 37 | 18/03/2023 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 134.36 | 134.36
106 | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/16957) | SM/16957 | 293.59 | 416 | AUGMENTATION | 66 | On track | 24 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 19/07/2023 | 71.27 | 71.27
107 | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17261) | SM/17261 | 439.33 | 710 | AUGMENTATION | 66 | On track | 18 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 14/08/2023 | 81.05 | 81.05
108 | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). (SM/18119) | SM/18119 | 387.1 | 520 | AUGMENTATION | 68 | On track | 39 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 27/07/2023 | 151.22 | 150.33
109 | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). (SM/17262) | SM/17262 | 348.2 | 260 | AUGMENTATION | 68 | Delayed | 9 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 14/08/2023 | 30.86 | 30.86
110 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME (SM/15009) | SM/15009 | 450.15 | 1428 | AUGMENTATION | 68 | Delayed | 29 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 130.71 | 130.71
111 | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). (SM/17253) | SM/17253 | 441.03 | 780 | AUGMENTATION | 69 | Delayed | 43 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 24/07/2023 | 188.39 | 184.32
112 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). (SM/17710) | SM/17710 | 631.55 | 950 | AUGMENTATION | 69 | Delayed | 37 | 17/03/2023 | 31/07/2025 | 16/05/2025 | 14/08/2023 | 231.45 | 231.45
113 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME (SM/15008) | SM/15008 | 454.11 | 957 | AUGMENTATION | 70 | On track | 31 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 142.03 | 142.03
114 | Augmentation of Prakash Zone-A Water Supply Scheme (SM/17222) | SM/17222 | 185.96 | 700 | AUGMENTATION | 70 | Delayed | 19 | 15/03/2023 | 31/10/2025 | 16/05/2025 | 18/07/2023 | 34.49 | 34.49
115 | Augmentation of Jayrambati Piped Water Supply Scheme. (SM/09880) | SM/09880 | 388.87 | 1287 | AUGMENTATION | 70 | Delayed | 58 | 08/12/2021 | 30/06/2025 | 16/05/2025 | 23/03/2022 | 225.72 | 225.72
116 | Augmentation of Amrul Zone-A Water Supply Scheme (SM/17229) | SM/17229 | 297.35 | 75 | AUGMENTATION | 70 | On track | 39 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 18/07/2023 | 115.5 | 115.5
117 | Augmentation of Amrul Zone-B Water Supply Scheme (SM/17230) | SM/17230 | 314.92 | 50 | AUGMENTATION | 70 | On track | 33 | 15/03/2023 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 105.28 | 105.28
118 | Augmentation of Chakuparsole Zone-A Water Supply Scheme (SM/17425) | SM/17425 | 423.84 | 360 | AUGMENTATION | 70 | On track | 39 | 18/03/2023 | 31/12/2025 | 16/05/2025 | 24/07/2023 | 166.09 | 166.09
119 | Augmentation of Chakuparsole Zone-B Water Supply Scheme (SM/17426) | SM/17426 | 357.24 | 172 | AUGMENTATION | 70 | On track | 19 | 18/03/2023 | 31/12/2025 | 16/05/2025 | 28/07/2023 | 68.98 | 68.98
120 | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) (SM/17254) | SM/17254 | 571.7 | 400 | AUGMENTATION | 70 | Delayed | 14 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 77.91 | 77.91
121 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME (SM/15005) | SM/15005 | 648.32 | 2578 | AUGMENTATION | 70 | On track | 33 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 216.58 | 216.58
122 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17440) | SM/17440 | 985.52 | 850 | AUGMENTATION | 70 | Delayed | 25 | 18/03/2023 | 30/06/2025 | 16/05/2025 | 13/07/2023 | 248.73 | 248.73
123 | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17711) | SM/17711 | 464.57 | 245 | AUGMENTATION | 70 | Delayed | 13 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 11/05/2023 | 62.6 | 62.6
124 | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17433) | SM/17433 | 489.22 | 350 | AUGMENTATION | 70 | Delayed | 14 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 30/03/2023 | 69.2 | 69.2
125 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). (SM/16974) | SM/16974 | 738.82 | 1080 | AUGMENTATION | 72 | On track | 31 | 16/03/2023 | 31/12/2025 | 12/03/2025 | 18/07/2023 | 227.02 | 227.02
126 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VI WATER SUPPLY SCHEME (SM/16260) | SM/16260 | 383.62 | 1381 | AUGMENTATION | 73 | On track | 33 | 24/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 125.03 | 125.03
127 | Augmentation of Sashpur Zone-B Water Supply Scheme (SM/17421) | SM/17421 | 344.8 | 318 | AUGMENTATION | 73 | On track | 41 | 18/03/2023 | 31/12/2025 | 16/05/2025 | 13/07/2023 | 142.4 | 142.4
128 | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. (SM/12380) | SM/12380 | 664.39 | 1259 | AUGMENTATION | 75 | Delayed | 45 | 13/09/2022 | 31/05/2025 | 16/05/2025 | 06/01/2022 | 299.68 | 299.68
129 | Augmentation of Somsar Water Supply Scheme (SM/17422) | SM/17422 | 152.16 | 85 | AUGMENTATION | 75 | Delayed | 32 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 28/03/2023 | 49.07 | 49.07
130 | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17250) | SM/17250 | 177.09 | 245 | AUGMENTATION | 75 | Delayed | 60 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 18/07/2023 | 106.12 | 106.12
131 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17286) | SM/17286 | 262.47 | 480 | AUGMENTATION | 75 | Delayed | 50 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 18/07/2023 | 131.65 | 127.45
132 | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. (SM/10294) | SM/10294 | 1011.34 | 3489 | AUGMENTATION | 75 | Delayed | 70 | 28/02/2022 | 30/06/2025 | 16/05/2025 | 24/09/2021 | 706.98 | 706.98
133 | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17730) | SM/17730 | 449.24 | 260 | AUGMENTATION | 75 | Delayed | 11 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 24/08/2023 | 47.98 | 47.98
134 | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura (SM/18036) | SM/18036 | 799.22 | 1120 | AUGMENTATION | 75 | Delayed | 42 | 17/03/2023 | 31/05/2025 | 16/05/2025 | 01/06/2023 | 331.93 | 331.93
135 | Augmentation of Dhengasole Water Supply Scheme (SM/17699) | SM/17699 | 323.64 | 448 | AUGMENTATION | 75 | Delayed | 28 | 17/03/2023 | 31/07/2025 | 16/05/2025 | 24/07/2023 | 90.96 | 90.96
136 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). (SM/17258) | SM/17258 | 367.1 | 260 | AUGMENTATION | 76 | Delayed | 29 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 23/03/2023 | 108.14 | 108.14
137 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. (SM/10295) | SM/10295 | 1828.18 | 2522 | AUGMENTATION | 76 | Delayed | 40 | 28/02/2022 | 30/06/2025 | 16/05/2025 | 17/04/2023 | 736.71 | 736.71
138 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17257) | SM/17257 | 492.36 | 420 | AUGMENTATION | 76 | Delayed | 29 | 15/03/2023 | 31/07/2025 | 16/05/2025 | 23/03/2023 | 143.4 | 143.4
139 | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17435) | SM/17435 | 861.68 | 312 | AUGMENTATION | 76 | Delayed | 17 | 18/03/2023 | 30/06/2025 | 16/05/2025 | 24/05/2023 | 147.19 | 146.61
140 | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17283) | SM/17283 | 759.85 | 250 | AUGMENTATION | 76 | Delayed | 10 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 13/07/2023 | 76.36 | 76.36
141 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). (SM/17284) | SM/17284 | 555.78 | 505 | AUGMENTATION | 76 | Delayed | 49 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 23/02/2023 | 272.29 | 272.29
142 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). (SM/17441) | SM/17441 | 226.63 | 367 | AUGMENTATION | 78 | Delayed | 9 | 18/03/2023 | 31/05/2025 | 16/05/2025 | 08/02/2024 | 20.61 | 20.61
143 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). (SM/17247) | SM/17247 | 586.37 | 1295 | AUGMENTATION | 78 | Delayed | 39 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 14/08/2023 | 226.92 | 226.92
144 | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. (SM/12381) | SM/12381 | 206.2 | 607 | AUGMENTATION | 78 | On track | 76 | 13/09/2022 | 30/11/2025 | 16/05/2025 | 28/01/2022 | 157.15 | 157.15
145 | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/16955) | SM/16955 | 478.49 | 820 | AUGMENTATION | 79 | On track | 45 | 16/03/2023 | 31/10/2025 | 16/05/2025 | 27/07/2023 | 216.32 | 216.32
146 | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme (SM/17438) | SM/17438 | 824.28 | 245 | AUGMENTATION | 79 | Delayed | 19 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 01/09/2023 | 159.23 | 130.76
147 | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme (SM/17281) | SM/17281 | 929.93 | 280 | AUGMENTATION | 79 | Delayed | 2 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 01/09/2023 | 17.21 | 17.21
148 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). (SM/16952) | SM/16952 | 172.5 | 180 | AUGMENTATION | 80 | On track | 45 | 16/03/2023 | 31/08/2025 | 16/05/2025 | 01/08/2023 | 78.48 | 78.48
149 | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17729) | SM/17729 | 459.25 | 600 | AUGMENTATION | 80 | Delayed | 23 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 02/06/2023 | 106.05 | 106.05
150 | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) (SM/17430) | SM/17430 | 457.56 | 310 | AUGMENTATION | 80 | Delayed | 12 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 17/03/2023 | 53.87 | 53.87
151 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17708) | SM/17708 | 408.45 | 270 | AUGMENTATION | 81 | On track | 44 | 17/03/2023 | 31/07/2025 | 16/05/2025 | 13/07/2023 | 178.64 | 178.64
152 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. (SM/10293) | SM/10293 | 1980.57 | 15728 | AUGMENTATION | 81 | Delayed | 58 | 28/02/2022 | 30/06/2025 | 16/05/2025 | 24/06/2020 | 1144.6 | 1144.6
153 | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17260) | SM/17260 | 436.62 | 120 | AUGMENTATION | 81 | Delayed | 7 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 17/03/2023 | 31.92 | 31.92
154 | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. (SM/17302) | SM/17302 | 966.49 | 305 | AUGMENTATION | 81 | Delayed | 69 | 15/03/2023 | 31/05/2025 | 16/05/2025 | 14/08/2023 | 668.36 | 663.79
155 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). (SM/17282) | SM/17282 | 551.35 | 797 | AUGMENTATION | 81 | Delayed | 40 | 15/03/2023 | 30/06/2025 | 16/05/2025 | 23/02/2023 | 218.44 | 218.44
156 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (SM/09877) | SM/09877 | 656.27 | 3690 | AUGMENTATION | 82 | On track | 40 | 08/12/2021 | 31/08/2025 | 16/05/2025 | 13/04/2022 | 263.41 | 263.41
157 | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17698) | SM/17698 | 443.04 | 545 | AUGMENTATION | 83 | Delayed | 35 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 18/07/2023 | 153.05 | 153.05
158 | Augmentation of Panchal Zone-I Water Supply Scheme (SM/17233) | SM/17233 | 23.84 | 6 | AUGMENTATION | 85 | Delayed | 96 | 15/03/2023 | 08/02/2025 | 16/05/2025 | 28/03/2023 | 22.91 | 22.91
159 | Augmentation of Somsar (BRGF) Water Supply Scheme (SM/17579) | SM/17579 | 104.34 | 320 | AUGMENTATION | 85 | Delayed | 44 | 18/03/2023 | 08/02/2025 | 16/05/2025 | 28/03/2023 | 46.29 | 38.81
160 | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). (SM/17695) | SM/17695 | 681.6 | 653 | AUGMENTATION | 85 | On track | 18 | 17/03/2023 | 31/12/2025 | 16/05/2025 | 06/11/2023 | 121.31 | 121.31
161 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). (SM/16951) | SM/16951 | 110.96 | 180 | AUGMENTATION | 85 | On track | 32 | 16/03/2023 | 31/07/2025 | 16/05/2025 | 24/07/2023 | 35.74 | 35.74
162 | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas (SM/12840) | SM/12840 | 997.56 | 1946 | AUGMENTATION | 85 | On track | 12 | 22/09/2022 | 31/10/2025 | 16/05/2025 | 23/02/2023 | 122.09 | 122.09
163 | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. (SM/16975) | SM/16975 | 282.39 | 475 | AUGMENTATION | 85 | On track | 34 | 16/03/2023 | 31/08/2025 | 16/05/2025 | 24/07/2023 | 96.79 | 96.79
164 | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme (SM/17725) | SM/17725 | 592.88 | 300 | AUGMENTATION | 85 | Delayed | 25 | 17/03/2023 | 31/05/2025 | 16/05/2025 | 13/07/2023 | 147.73 | 147.73
165 | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) (SM/17432) | SM/17432 | 436.2 | 180 | AUGMENTATION | 85 | On track | 8 | 18/03/2023 | 30/09/2025 | 16/05/2025 | 30/03/2023 | 35.6 | 35.6
166 | Augmentation of Joypur Piped Water Supply Scheme. (SM/09878) | SM/09878 | 822.71 | 3612 | AUGMENTATION | 85 | On track | 46 | 08/12/2021 | 31/07/2025 | 16/05/2025 | 01/02/2022 | 375.97 | 375.97
167 | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. (SM/17248) | SM/17248 | 394.85 | 265 | AUGMENTATION | 85 | On track | 28 | 15/03/2023 | 30/09/2025 | 16/05/2025 | 24/07/2023 | 112 | 112
168 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME (SM/15006) | SM/15006 | 246.43 | 608 | AUGMENTATION | 85 | On track | 31 | 04/02/2023 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 76.2 | 76.2
169 | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). (SM/16976) | SM/16976 | 306.48 | 765 | AUGMENTATION | 85 | Delayed | 29 | 16/03/2023 | 08/02/2025 | 16/05/2025 | 20/03/2023 | 89.09 | 89.09
170 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) (SM/08983) | SM/08983 | 672.25 | 2939 | AUGMENTATION | 85 | On track | 64 | 29/10/2021 | 30/07/2025 | 16/05/2025 | 25/05/2022 | 433.41 | 433.41
171 | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC (SM/12379) | SM/12379 | 590.96 | 1107 | AUGMENTATION | 85 | On track | 42 | 13/09/2022 | 31/12/2025 | 16/05/2025 | 24/05/2022 | 247.12 | 247.12
172 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09927) | SM/09927 | 308.91 | 1224 | AUGMENTATION | 85 | Delayed | 77 | 09/12/2021 | 31/05/2025 | 16/05/2025 | 12/05/2022 | 238.38 | 238.38
173 | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17731) | SM/17731 | 484.18 | 280 | AUGMENTATION | 85 | On track | 26 | 17/03/2023 | 30/09/2025 | 16/05/2025 | 17/03/2023 | 123.84 | 123.84
174 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). (SM/17701) | SM/17701 | 339.34 | 260 | AUGMENTATION | 86 | On track | 34 | 17/03/2023 | 30/06/2025 | 16/05/2025 | 30/03/2023 | 114.35 | 114.35
175 | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. (SM/16953) | SM/16953 | 183.46 | 770 | AUGMENTATION | 87 | On track | 65 | 16/03/2023 | 31/12/2025 | 16/05/2025 | 22/05/2023 | 118.89 | 118.89
176 | Augmentation of Panchal Zone-II Water Supply Scheme (SM/17423) | SM/17423 | 236.43 | 34 | AUGMENTATION | 90 | On track | 42 | 18/03/2023 | 30/06/2025 | 16/05/2025 | 27/07/2023 | 98.33 | 98.33
177 | Augmentation of Indas Water Supply Scheme (SM/17684) | SM/17684 | 178.2 | 280 | AUGMENTATION | 90 | Delayed | 58 | 17/03/2023 | 08/02/2025 | 16/05/2025 | 21/09/2023 | 102.8 | 102.8
178 | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t (SM/09853) | SM/09853 | 293.12 | 7078 | AUGMENTATION | 95 | On track | 79 | 03/12/2021 | 31/10/2025 | 16/05/2025 | 09/02/2022 | 232.46 | 232.46
179 | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' (SM/17706) | SM/17706 | 255.52 | 275 | AUGMENTATION | 95 | On track | 25 | 17/03/2023 | 31/10/2025 | 16/05/2025 | 18/07/2023 | 63.33 | 63.33
180 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. (SM/09926) | SM/09926 | 532.09 | 2525 | AUGMENTATION | 95 | On track | 83 | 09/12/2021 | 31/05/2025 | 16/05/2025 | 23/09/2021 | 440.62 | 440.62
181 | Augmentation of Morar Zone-B Water Supply Scheme. (SM/17243) | SM/17243 | 439.27 | 128 | AUGMENTATION | 95 | On track | 43 | 15/03/2023 | 31/08/2025 | 16/05/2025 | 28/07/2023 | 187.24 | 187.24
182 | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna (SM/10296) | SM/10296 | 2502.19 | 0 | AUGMENTATION | 95 | On track | 62 | 28/02/2022 | 31/10/2025 | 16/05/2025 | 10/08/2021 | 1554.8 | 1554.8
183 | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. (SM/12382) | SM/12382 | 600.05 | 1109 | AUGMENTATION | 95 | On track | 54 | 13/09/2022 | 31/10/2025 | 16/05/2025 | 14/11/2022 | 324.51 | 324.51
Total |  |  | 106485.93 | 183441 | [8 empty] | 33700.65 | 33519.29