## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | SOLARISATION OF WBSEDCL ENERGISED PUMPING INSTALLATION IN G.W.BASED CHITMU PWSS, BLOCK -JHALDA II UNDER PMD,PHE Dte.,DISTRICT- PURULIA (SM/14169) | SM/14169 | 5.73 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 09/01/2023 | 09/07/2023 | 12/06/2023 | 07/08/2023 | 0 | 0
2 | Contingency plan to combat Drought like situation in Summer season 2021 in the District of Purulia. (SM/07877) | SM/07877 | 249.11 | 0 | OTHERS | 0 | WO no issued | 0 | 19/01/2021 |  | 31/05/2021 |  | 0 | 0
3 | Supply of Chemicals & Consumables Glass Wares etc. required for smooth running of 17 NOS laboratories located at different blocks of Purulia District under Purulia Division, PHE Dte. (SM/19265) | SM/19265 | 372.4 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
4 | Supply of Chemicals & Consumables Glass Wares etc. required for smooth running of 17 NOS Laboratories located at different blocks of Purulia District under Purulia Division, PHE Dte. (SM/19266) | SM/19266 | 223.97 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 30/09/2024 | 0 | 0
5 | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19090) | SM/19090 | 155.07 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 04/12/2023 |  | 05/12/2023 | 26/08/2021 | 0 | 0
6 | Procurement of Computer and Peripherals for the office use in Purulia Mechanical Division and Sub-Division PHE Dte. and Office of the Assistant Chief Engineer Northern Zone PHE Dte. (SM/18738) | SM/18738 | 23.4 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 17/08/2023 |  | 17/08/2023 |  | 0 | 0
7 | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission (SM/17411) | SM/17411 | 78.13 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 20/03/2023 |  | 23/03/2023 | 31/08/2023 | 0 | 0
8 | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. (SM/17197) | SM/17197 | 82.63 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 | 05/08/2021 | 0 | 0
9 | Water sample collection charges by engagement of agency at different blocks of Purulia District under Purulia Division, PHE Dte. (SM/19291) | SM/19291 | 784.73 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
10 | Honorarium of Asha Workers & Self Help group in connection with FTK testing at different blocks of Purulia District under Purulia Division, PHE Dte. (SM/19290) | SM/19290 | 321.19 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
11 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II (SM/18641) | SM/18641 | 60986.55 | 0 | NEW | 1 | Delayed | 14 | 31/07/2023 | 31/07/2026 | 06/05/2024 | 14/08/2023 | 8595.26 | 8049.95
12 | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/15380) | SM/15380 | 32.84 | 44 | NEW | 1 | Delayed | 11 | 07/02/2023 | 31/03/2024 | 26/07/2023 | 08/02/2023 | 3.49 | 3.49
13 | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/14251) | SM/14251 | 29.24 | 22 | NEW | 1 | Delayed | 15 | 20/01/2023 | 31/03/2024 | 26/07/2023 | 24/02/2023 | 4.33 | 4.33
14 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) (SM/18731) | SM/18731 | 161758.31 | 0 | NEW | 1 | Delayed | 13 | 14/08/2023 | 14/08/2026 | 06/05/2024 | 17/08/2023 | 21474.84 | 21474.84
15 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) (SM/18333) | SM/18333 | 10279.85 | 74419 | NEW | 1 | Delayed | 0 | 30/06/2023 | 31/12/2025 | 24/09/2023 | 09/01/2024 | 0 | 0
16 | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) (SM/18528) | SM/18528 | 27591.27 | 286151 | NEW | 1 | Delayed | 6 | 26/07/2023 | 26/07/2026 | 06/05/2024 | 26/10/2023 | 1542.34 | 1542.34
17 | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/16570) | SM/16570 | 30.31 | 50 | NEW | 1 | Delayed | 8 | 09/03/2023 | 31/03/2024 | 26/07/2023 | 10/02/2023 | 2.28 | 2.28
18 | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME (SM/16091) | SM/16091 | 37.39 | 97 | NEW | 2 | Delayed | 8 | 22/02/2023 | 31/03/2024 | 26/07/2023 | 24/02/2023 | 2.84 | 2.84
19 | Left out Mouzas of Barabazar pipe water supply scheme (SM/18319) | SM/18319 | 6135.38 | 14878 | NEW | 3 | Delayed | 69 | 27/06/2023 | 28/12/2024 | 28/12/2023 | 12/07/2022 | 4239.9 | 2602.53
20 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III (SM/18653) | SM/18653 | 16409.28 | 0 | NEW | 4 | Delayed | 2 | 01/08/2023 | 01/02/2026 | 06/05/2024 | 14/08/2023 | 396.14 | 331.4
21 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) (SM/18654) | SM/18654 | 65922.47 | 0 | NEW | 5 | Delayed | 8 | 01/08/2023 | 01/08/2026 | 06/05/2024 | 08/08/2023 | 4964.38 | 4912.85
22 | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS (SM/15040) | SM/15040 | 396.97 | 0 | AUGMENTATION | 7 | Delayed | 44 | 04/02/2023 | 31/12/2024 | 05/08/2024 | 08/09/2023 | 175.51 | 175.51
23 | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS (SM/15336) | SM/15336 | 363.16 | 0 | AUGMENTATION | 8 | Delayed | 36 | 09/02/2023 | 31/10/2024 | 03/09/2024 | 19/07/2023 | 131.43 | 131.43
24 | Surface water based water supply scheme for Augmentation of Bagmundi PWSS (SM/15041) | SM/15041 | 298.83 | 0 | AUGMENTATION | 9 | Delayed | 59 | 04/02/2023 | 31/10/2024 | 06/05/2024 | 10/04/2023 | 177.15 | 177.15
25 | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss (SM/15039) | SM/15039 | 512.38 | 0 | AUGMENTATION | 13 | Delayed | 58 | 04/02/2023 | 31/03/2025 | 17/12/2024 | 10/08/2023 | 298.11 | 298.11
26 | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA (SM/16530) | SM/16530 | 216.9 | 0 | SOLARISATION | 15 | Delayed | 0 | 02/03/2023 | 30/06/2024 | 22/03/2024 | 01/08/2023 | 0 | 0
27 | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. (SM/18915) | SM/18915 | 666.74 | 0 | AUGMENTATION | 23 | Delayed | 17 | 09/10/2023 | 31/10/2024 | 06/06/2024 | 03/11/2023 | 113.2 | 113.2
28 | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project (SM/18779) | SM/18779 | 4685.1 | 1038 | AUGMENTATION | 40 | Delayed | 35 | 28/08/2023 | 31/12/2024 | 06/05/2024 | 29/08/2023 | 1617.49 | 1617.49
29 | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. (SM/09583) | SM/09583 | 103.56 | 1857 | AUGMENTATION | 41 | Delayed | 60 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 17/01/2022 | 62.35 | 62.35
30 | Augmentation of Bathanbari W/S Scheme (SM/09211) | SM/09211 | 167.09 | 988 | AUGMENTATION | 50 | Delayed | 90 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 07/03/2022 | 150.65 | 136.98
31 | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (SM/09582) | SM/09582 | 203.85 | 237 | AUGMENTATION | 52 | Delayed | 85 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 18/01/2022 | 172.49 | 172.49
32 | Augmentation of Baram Water Supply Scheme (SM/09213) | SM/09213 | 195.46 | 1241 | AUGMENTATION | 52 | Delayed | 74 | 30/10/2021 | 31/05/2024 | 06/05/2024 | 28/02/2022 | 145.54 | 145.54
33 | Augmentation of Beldi Water Supply Scheme (SM/09218) | SM/09218 | 128.6 | 1849 | AUGMENTATION | 54 | Delayed | 65 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 18/04/2022 | 83.31 | 83.31
34 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB (SM/18250) | SM/18250 | 1077.99 | 3798 | AUGMENTATION | 54 | Delayed | 31 | 16/06/2023 | 31/10/2024 | 06/05/2024 | 03/07/2023 | 337.69 | 337.69
35 | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/14143) | SM/14143 | 95.58 | 0 | SUPPORT-WQMSP | 55 | Delayed | 0 | 02/01/2023 | 31/08/2024 | 06/05/2024 | 27/12/2021 | 0 | 0
36 | Augmentation of Dubra Pipe Water Supply Scheme PWSS (SM/14460) | SM/14460 | 660.04 | 2424 | AUGMENTATION | 57 | Delayed | 68 | 20/01/2023 | 31/10/2024 | 06/05/2024 | 22/11/2022 | 451.33 | 451.33
37 | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. (SM/09580) | SM/09580 | 504.47 | 860 | AUGMENTATION | 60 | Delayed | 78 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 27/09/2021 | 393.36 | 393.36
38 | Augmentation of Lachhyara Piped Water Supply Scheme (SM/09212) | SM/09212 | 354.91 | 768 | AUGMENTATION | 60 | Delayed | 80 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 14/03/2022 | 282.21 | 282.21
39 | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (SM/09579) | SM/09579 | 463.03 | 1450 | AUGMENTATION | 61 | Delayed | 90 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 01/02/2022 | 415.72 | 410.12
40 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B (SM/18306) | SM/18306 | 1014.74 | 4471 | AUGMENTATION | 63 | Delayed | 32 | 26/06/2023 | 31/12/2024 | 31/07/2024 | 12/07/2023 | 328.41 | 328.41
41 | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) (SM/09216) | SM/09216 | 424.22 | 1140 | AUGMENTATION | 64 | Delayed | 77 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 15/12/2021 | 325.93 | 325.93
42 | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. (SM/09581) | SM/09581 | 288.49 | 81 | AUGMENTATION | 65 | Delayed | 93 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 13/12/2021 | 269.23 | 269.23
43 | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC (SM/09217) | SM/09217 | 386.08 | 271 | AUGMENTATION | 66 | Delayed | 80 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 07/01/2022 | 309.22 | 309.22
44 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II (SM/14669) | SM/14669 | 969.41 | 0 | AUGMENTATION | 66 | Delayed | 47 | 31/01/2023 | 31/10/2024 | 06/05/2024 | 27/02/2023 | 456.25 | 456.25
45 | Augmentation of Sonathali W/S Scheme (SM/09210) | SM/09210 | 401.87 | 1218 | AUGMENTATION | 67 | Delayed | 67 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 07/01/2022 | 268.85 | 268.85
46 | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) (SM/10347) | SM/10347 | 940.26 | 3104 | AUGMENTATION | 68 | Delayed | 52 | 16/03/2022 | 31/07/2024 | 06/05/2024 | 22/04/2022 | 486.08 | 486.08
47 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B (SM/14670) | SM/14670 | 984.33 | 3183 | AUGMENTATION | 68 | Delayed | 57 | 31/01/2023 | 31/10/2024 | 06/05/2024 | 07/02/2023 | 557.04 | 557.04
48 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A (SM/14022) | SM/14022 | 559.47 | 3393 | AUGMENTATION | 70 | Delayed | 10 | 05/12/2022 | 31/12/2024 | 06/05/2024 | 25/02/2021 | 56.09 | 54.12
49 | Augmentation of Satra Water Supply Scheme (SM/09038) | SM/09038 | 389.21 | 3823 | AUGMENTATION | 70 | Delayed | 88 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 17/12/2021 | 342.59 | 342.59
50 | Augmentation of Manguria-Lalpur W/S Scheme (SM/09943) | SM/09943 | 371.08 | 800 | AUGMENTATION | 70 | Delayed | 99 | 14/12/2021 | 30/06/2024 | 06/05/2024 | 15/12/2021 | 367.7 | 357.38
51 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII (SM/14023) | SM/14023 | 721.23 | 3400 | AUGMENTATION | 71 | Delayed | 36 | 05/12/2022 | 31/12/2024 | 06/05/2024 | 25/02/2021 | 256.07 | 254.33
52 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B (SM/14024) | SM/14024 | 782.25 | 3031 | AUGMENTATION | 71 | Delayed | 67 | 05/12/2022 | 31/10/2024 | 06/05/2024 | 25/02/2021 | 524.5 | 524.5
53 | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) (SM/10719) | SM/10719 | 1569.58 | 5016 | AUGMENTATION | 71 | Delayed | 63 | 18/05/2022 | 31/08/2024 | 06/05/2024 | 19/05/2022 | 981.24 | 981.24
54 | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) (SM/09037) | SM/09037 | 684.31 | 2031 | AUGMENTATION | 71 | Delayed | 63 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 13/12/2021 | 432.56 | 432.56
55 | Augmentation of Santuri Pipe Water Supply Scheme PWSS (SM/14459) | SM/14459 | 363.94 | 658 | AUGMENTATION | 71 | Delayed | 85 | 20/01/2023 | 31/08/2024 | 06/05/2024 | 20/01/2023 | 310.8 | 310.8
56 | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) (SM/09215) | SM/09215 | 514.62 | 2135 | AUGMENTATION | 74 | Delayed | 96 | 30/10/2021 | 31/07/2024 | 06/05/2024 | 31/01/2022 | 492.21 | 492.21
57 | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) (SM/10395) | SM/10395 | 1949.9 | 5991 | AUGMENTATION | 75 | Delayed | 52 | 29/03/2022 | 31/08/2024 | 06/05/2024 | 14/03/2022 | 1011.14 | 1011.14
58 | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme (SM/11453) | SM/11453 | 2367.56 | 6896 | AUGMENTATION | 75 | Delayed | 79 | 12/07/2022 | 31/08/2024 | 06/05/2024 | 25/02/2021 | 1867.97 | 1867.97
59 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A (SM/14025) | SM/14025 | 538.41 | 2868 | AUGMENTATION | 75 | Delayed | 53 | 05/12/2022 | 31/10/2024 | 06/05/2024 | 25/02/2021 | 282.91 | 282.91
60 | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) (SM/10722) | SM/10722 | 2195.7 | 7881 | AUGMENTATION | 77 | Delayed | 61 | 18/05/2022 | 31/08/2024 | 06/05/2024 | 23/05/2022 | 1343.09 | 1343.09
61 | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) (SM/09209) | SM/09209 | 590.04 | 2359 | AUGMENTATION | 78 | Delayed | 73 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 19/01/2022 | 431.76 | 431.02
62 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B (SM/16379) | SM/16379 | 814.73 | 1951 | AUGMENTATION | 78 | Delayed | 53 | 28/02/2023 | 31/12/2024 | 03/12/2024 | 20/04/2023 | 432.65 | 432.65
63 | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) (SM/09578) | SM/09578 | 785.53 | 4309 | AUGMENTATION | 79 | Delayed | 70 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 18/01/2022 | 546.55 | 546.55
64 | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) (SM/09036) | SM/09036 | 965.77 | 2888 | AUGMENTATION | 79 | Delayed | 68 | 30/10/2021 | 30/06/2024 | 06/05/2024 | 17/12/2021 | 658.17 | 653.07
65 | Sarbari Piped Water Supply Scheme to Accommodate FHTC (SM/10720) | SM/10720 | 1231.07 | 3650 | AUGMENTATION | 79 | Delayed | 84 | 18/05/2022 | 31/08/2024 | 06/05/2024 | 23/05/2022 | 1034.96 | 1034.96
66 | Augmentation of Saltore-Hijuli Water Supply Scheme (SM/10721) | SM/10721 | 1045.37 | 3676 | AUGMENTATION | 80 | Delayed | 79 | 18/05/2022 | 31/07/2024 | 06/05/2024 | 05/05/2022 | 821.24 | 821.24
67 | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC (SM/09577) | SM/09577 | 791.71 | 3531 | AUGMENTATION | 81 | Delayed | 85 | 22/11/2021 | 30/06/2024 | 06/05/2024 | 17/01/2022 | 676.37 | 676.37
68 | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) (SM/10718) | SM/10718 | 1670.03 | 6702 | AUGMENTATION | 82 | Delayed | 78 | 18/05/2022 | 31/07/2024 | 06/05/2024 | 23/05/2022 | 1305.59 | 1305.59
69 | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia (SM/10045) | SM/10045 | 1577.26 | 47 | AUGMENTATION | 84 | Delayed | 80 | 24/01/2022 | 30/06/2024 | 06/05/2024 | 06/12/2021 | 1253.97 | 1235.66
70 | Augmentation of Kotshila Water Supply Scheme. (SM/10723) | SM/10723 | 2091.4 | 8268 | AUGMENTATION | 84 | Delayed | 78 | 18/05/2022 | 31/08/2024 | 06/05/2024 | 23/05/2022 | 1624.24 | 1624.24
71 | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) (SM/10046) | SM/10046 | 2330.93 | 13173 | AUGMENTATION | 85 | Delayed | 50 | 24/01/2022 | 31/08/2024 | 06/05/2024 | 09/02/2022 | 1159.3 | 1159.3
72 | Augmentation of Manbazar-II Block(Part) Water Supply Scheme (SM/15936) | SM/15936 | 999.41 | 3421 | AUGMENTATION | 85 | Delayed | 94 | 22/02/2023 | 31/08/2024 | 06/05/2024 | 14/03/2023 | 939.09 | 939.09
73 | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) (SM/09028) | SM/09028 | 33.33 | 0 | SCHOOL | 85 | Delayed | 0 | 30/10/2021 | 31/08/2024 | 06/05/2024 | 20/01/2023 | 0 | 0
74 | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission (SM/08682) | SM/08682 | 34.33 | 0 | SUPPORT-WQMSP | 85 | Delayed | 0 | 19/08/2021 | 31/05/2024 | 06/05/2024 | 18/08/2021 | 0 | 0
75 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purulia District. (SM/09027) | SM/09027 | 437.58 | 0 | SUPPORT-M&E | 85 | WO no issued | 0 | 30/10/2021 | 31/07/2024 | 06/05/2024 | 19/08/2022 | 0 | 0
76 | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. (SM/10278) | SM/10278 | 937.2 | 0 | ANGANWADI | 87 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 19/04/2022 | 0 | 0
77 | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) (SM/10048) | SM/10048 | 1477.06 | 4501 | AUGMENTATION | 87 | Delayed | 94 | 24/01/2022 | 31/01/2024 | 06/05/2024 | 18/01/2021 | 1393.12 | 1393.12
78 | Augmentation of Kashipur Piped Water Supply Scheme (SM/10047) | SM/10047 | 1088.37 | 4032 | AUGMENTATION | 87 | Delayed | 62 | 24/01/2022 | 31/07/2024 | 06/05/2024 | 09/02/2022 | 671.51 | 671.51
79 | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. (SM/10257) | SM/10257 | 605.24 | 0 | SCHOOL | 88 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 25/04/2022 | 0 | 0
80 | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. (SM/10254) | SM/10254 | 937.2 | 0 | ANGANWADI | 88 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 05/08/2022 | 0 | 0
81 | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. (SM/10274) | SM/10274 | 824.09 | 0 | ANGANWADI | 89 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 02/05/2022 | 0 | 0
82 | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. (SM/10275) | SM/10275 | 937.2 | 0 | ANGANWADI | 89 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 21/04/2022 | 0 | 0
83 | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. (SM/10276) | SM/10276 | 880.65 | 0 | ANGANWADI | 89 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 16/03/2022 | 0 | 0
84 | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. (SM/10277) | SM/10277 | 937.2 | 0 | ANGANWADI | 89 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 02/05/2022 | 0 | 0
85 | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. (SM/10280) | SM/10280 | 912.96 | 0 | ANGANWADI | 90 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 19/04/2022 | 0 | 0
86 | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. (SM/10255) | SM/10255 | 824.09 | 0 | ANGANWADI | 90 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 16/03/2022 | 0 | 0
87 | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. (SM/10281) | SM/10281 | 872.57 | 0 | ANGANWADI | 90 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 22/03/2022 | 0 | 0
88 | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. (SM/10284) | SM/10284 | 937.2 | 0 | ANGANWADI | 90 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 29/03/2022 | 0 | 0
89 | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. (SM/08718) | SM/08718 | 552.02 | 1105 | ANGANWADI | 90 | Delayed | 0 | 03/09/2021 | 31/08/2024 | 06/05/2024 | 05/02/2021 | 0 | 0
90 | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. (SM/16414) | SM/16414 | 717.4 | 0 | AUGMENTATION | 90 | On track | 51 | 28/02/2023 | 31/12/2024 | 22/11/2024 | 16/05/2023 | 365.2 | 365.2
91 | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. (SM/10251) | SM/10251 | 937.2 | 0 | ANGANWADI | 90 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 29/03/2022 | 0 | 0
92 | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. (SM/10252) | SM/10252 | 937.2 | 0 | ANGANWADI | 91 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 19/04/2022 | 0 | 0
93 | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. (SM/10282) | SM/10282 | 937.2 | 0 | ANGANWADI | 91 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 29/03/2022 | 0 | 0
94 | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. (SM/10256) | SM/10256 | 771.24 | 0 | SCHOOL | 91 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 05/05/2022 | 0 | 0
95 | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. (SM/10253) | SM/10253 | 937.2 | 0 | ANGANWADI | 91 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 24/03/2022 | 0 | 0
96 | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. (SM/10279) | SM/10279 | 937.2 | 0 | ANGANWADI | 91 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 02/05/2022 | 0 | 0
97 | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. (SM/10285) | SM/10285 | 937.2 | 0 | ANGANWADI | 91 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 02/05/2022 | 0 | 0
98 | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. (SM/10227) | SM/10227 | 943.72 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 31/01/2022 | 0 | 0
99 | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. (SM/10224) | SM/10224 | 920.88 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 31/01/2022 | 0 | 0
100 | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. (SM/10223) | SM/10223 | 830.21 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 12/04/2022 | 0 | 0
101 | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. (SM/10286) | SM/10286 | 921.04 | 0 | ANGANWADI | 92 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 24/03/2022 | 0 | 0
102 | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. (SM/10225) | SM/10225 | 848.34 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 21/03/2022 | 0 | 0
103 | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. (SM/10226) | SM/10226 | 843.81 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 25/04/2022 | 0 | 0
104 | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. (SM/10228) | SM/10228 | 889.14 | 0 | SCHOOL | 92 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 25/04/2022 | 0 | 0
105 | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. (SM/10283) | SM/10283 | 937.2 | 0 | ANGANWADI | 92 | Delayed | 0 | 25/02/2022 | 31/07/2024 | 06/05/2024 | 02/05/2022 | 0 | 0
106 | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) (SM/10198) | SM/10198 | 1455.54 | 4421 | AUGMENTATION | 94 | On track | 71 | 22/02/2022 | 31/12/2024 | 22/11/2024 | 13/01/2022 | 1028 | 1028
107 | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. (SM/10230) | SM/10230 | 902.6 | 0 | SCHOOL | 94 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 05/05/2022 | 0 | 0
108 | Piped Water Supply Scheme from Marble Lake to adjoining areas. (SM/07764) | SM/07764 | 759.01 | 2122 | NEW | 94 | Delayed | 78 | 04/11/2020 | 31/05/2024 | 06/05/2024 | 25/02/2021 | 594.57 | 592.96
109 | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. (SM/10229) | SM/10229 | 889.17 | 0 | SCHOOL | 95 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 08/04/2022 | 0 | 0
110 | Providing FHTC under Arsha Water Supply Scheme (SM/10544) | SM/10544 | 317.07 | 0 | AUGMENTATION | 95 | Delayed | 50 | 18/04/2022 | 31/07/2024 | 06/05/2024 | 22/11/2022 | 157.68 | 157.68
111 | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. (SM/10222) | SM/10222 | 825.62 | 0 | SCHOOL | 96 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 08/04/2022 | 0 | 0
112 | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. (SM/10249) | SM/10249 | 783.7 | 0 | ANGANWADI | 97 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 03/07/2024 | 02/05/2022 | 0 | 0
113 | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. (SM/10250) | SM/10250 | 937.2 | 0 | ANGANWADI | 97 | Delayed | 0 | 24/02/2022 | 31/07/2024 | 06/05/2024 | 31/01/2022 | 0 | 0
114 | Augmentation of Balitora & its adjoining mouzas water supply scheme (SM/09214) | SM/09214 | 463.76 | 2672 | AUGMENTATION | 98 | On track | 90 | 30/10/2021 | 31/12/2024 | 22/11/2024 | 11/01/2021 | 416.27 | 416.27
115 | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/06939) | SM/06939 | 81.16 | 1259 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 | 31/08/2021 | 12/06/2023 | 29/12/2020 | 81.06 | 81.05
116 | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/06941) | SM/06941 | 68.58 | 1112 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 | 31/01/2021 | 12/06/2023 | 24/01/2022 | 68.58 | 65.51
117 | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07836) | SM/07836 | 91.65 | 1072 | RETROFITTING | 100 | 100% Physical | 97 | 14/01/2021 | 31/07/2022 | 12/06/2023 | 08/02/2021 | 88.98 | 88.98
118 | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/06940) | SM/06940 | 96.09 | 1849 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 | 31/07/2022 | 12/06/2023 | 29/12/2020 | 96.09 | 96.09
119 | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07564) | SM/07564 | 128.34 | 2672 | RETROFITTING | 100 | 100% Physical | 97 | 04/01/2021 | 31/08/2021 | 12/06/2023 | 11/01/2021 | 124.6 | 124.6
120 | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07566) | SM/07566 | 244.44 | 3763 | RETROFITTING | 100 | 100% Physical | 97 | 04/01/2021 | 31/07/2022 | 12/06/2023 | 01/09/2022 | 237.32 | 237.32
121 | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07838) | SM/07838 | 73.08 | 1218 | RETROFITTING | 100 | 100% Physical | 97 | 14/01/2021 | 30/04/2021 | 12/06/2023 | 22/11/2022 | 70.95 | 70.95
122 | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07840) | SM/07840 | 10.75 | 171 | RETROFITTING | 100 | 100% Physical | 100 | 14/01/2021 | 31/07/2022 | 12/06/2023 | 06/07/2021 | 10.74 | 9.2
123 | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07563) | SM/07563 | 185.57 | 5324 | RETROFITTING | 100 | 100% Physical | 100 | 04/01/2021 | 31/07/2022 | 12/06/2023 | 02/02/2021 | 185.54 | 185.54
124 | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. (SM/06826) | SM/06826 | 81.48 | 473 | AUGMENTATION | 100 | 100% Physical | 100 | 06/10/2020 | 31/07/2022 | 12/06/2023 | 29/12/2020 | 81.48 | 76.66
125 | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07837) | SM/07837 | 224.29 | 1801 | RETROFITTING | 100 | 100% Physical | 50 | 14/01/2021 | 31/07/2022 | 12/06/2023 | 15/01/2021 | 112.33 | 112.33
126 | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07841) | SM/07841 | 120.54 | 1864 | RETROFITTING | 100 | 100% Physical | 61 | 14/01/2021 | 31/07/2022 | 12/06/2023 | 02/08/2022 | 73.14 | 73.14
127 | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07565) | SM/07565 | 159.92 | 2058 | RETROFITTING | 100 | 100% Physical | 96 | 04/01/2021 | 31/08/2021 | 12/06/2023 | 10/02/2021 | 154.03 | 154.03
128 | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07567) | SM/07567 | 168.98 | 3823 | RETROFITTING | 100 | 100% Physical | 97 | 04/01/2021 | 31/07/2022 | 12/06/2023 | 15/01/2021 | 164.38 | 164.38
129 | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/08584) | SM/08584 | 474.74 | 2623 | RETROFITTING | 100 | 100% Physical | 97 | 03/02/2021 | 31/07/2022 | 12/06/2023 | 10/02/2021 | 462.01 | 462.01
130 | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/06942) | SM/06942 | 86.91 | 1241 | RETROFITTING | 100 | 100% Physical | 100 | 03/11/2020 | 31/07/2022 | 12/06/2023 | 22/11/2022 | 86.91 | 85.2
131 | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme (SM/07839) | SM/07839 | 175.07 | 2932 | RETROFITTING | 100 | 100% Physical | 97 | 14/01/2021 | 31/07/2022 | 12/06/2023 | 01/02/2021 | 169.97 | 169.94
132 | Procurement of Chemicals, Consumables, Glass wares etc. including annual maintenance contract (AMC) of Laboratories. (SM/06620) | SM/06620 | 75.01 | 0 | SUPPORT-WQMSP | 100 | WO no issued | 0 | 05/02/2020 |  | 24/02/2023 |  | 0 | 0
Total |  |  | 433268.56 | 561645 | [8 empty] | 75281.57 | 72912.38