## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Charkata Pukuria Piped Water Supply Scheme (SM/15290) | SM/15290 | 42.1 | 54 | NEW | 0 | 0% Physical | 0 | 09/02/2023 | 07/12/2024 | 12/08/2025 | 07/06/2023 | 0 | 0
2 | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. (SM/16446) | SM/16446 | 222.22 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 28/02/2023 | 02/08/2025 | 12/08/2025 | 17/07/2023 | 0 | 0
3 | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District (SM/19078) | SM/19078 | 43.3 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 05/05/2023 | 0 | 0
4 | Third Party Inspection job for Surface Water Based Piped Water Supply Scheme for Shyampur-I and II and Part of Bagnan-I and II and Uluberia -I Block (SM/15226) | SM/15226 | 641.78 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 07/02/2023 |  | 11/02/2023 | 31/08/2023 | 0 | 0
5 | Remuneration, Festival Bonus and Maintenance of 5 nos Laboratories in Howrah District related to Water Quality Monitoring and Surveillance activities under Jal Jeevan Mission 2024-2025 (SM/19318) | SM/19318 | 51.27 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/12/2024 |  | 27/12/2024 | 31/12/2024 | 0 | 0
6 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Howrah District. (SM/08989) | SM/08989 | 280.82 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 22/08/2022 | 0 | 0
7 | Regular Upkeepment, upgradation and Day to Day Activities of Mobile Laboratory Van (MLV) (SM/19281) | SM/19281 | 37.26 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
8 | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte (SM/19114) | SM/19114 | 71.48 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 1 | Delayed | 0 | 22/12/2023 | 31/12/2024 | 24/05/2024 |  | 0 | 0
9 | Orientation and Mass Awareness Generation (IEC) Activities related to judicious and safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Howrah District under Howrah Division, PHE Dte (SM/19091) | SM/19091 | 227.03 | 0 | SUPPORT- IEC / BCC/ IPC | 1 | Delayed | 0 | 06/12/2023 | 31/12/2024 | 24/05/2024 | 20/02/2024 | 0 | 0
10 | Baniban Zone-I Piped Water Supply Scheme (SM/18566) | SM/18566 | 1511.88 | 6036 | NEW | 2 | Delayed | 0 | 31/07/2023 | 31/12/2025 | 12/08/2025 | 16/08/2023 | 0 | 0
11 | Augmentation of Maju piped water supply scheme. (SM/10035) | SM/10035 | 1692.75 | 4749 | AUGMENTATION | 5 | Delayed | 68 | 19/01/2022 | 30/06/2025 | 12/08/2025 | 31/08/2022 | 1158.96 | 1158.96
12 | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. (SM/18748) | SM/18748 | 1400.74 | 5855 | NEW | 5 | Delayed | 0 | 17/08/2023 | 02/08/2025 | 12/08/2025 | 29/08/2023 | 3.55 | 3.55
13 | Chak Kadamtala Piped Water Supply scheme (SM/16557) | SM/16557 | 40.27 | 69 | NEW | 5 | Delayed | 0 | 10/03/2023 | 31/03/2025 | 12/08/2025 | 07/06/2023 | 0 | 0
14 | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. (SM/07931) | SM/07931 | 278.52 | 94793 | ANGANWADI | 6 | Delayed | 0 | 19/01/2021 | 30/06/2025 | 12/08/2025 | 23/02/2023 | 0 | 0
15 | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. (SM/08990) | SM/08990 | 7.68 | 0 | SUPPORT-M&E | 10 | Delayed | 0 | 29/10/2021 | 31/12/2024 | 22/05/2024 | 17/02/2022 | 0 | 0
16 | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte (SM/16933) | SM/16933 | 30.12 | 0 | SUPPORT-WQMSP | 10 | Delayed | 0 | 16/03/2023 | 31/12/2024 | 22/05/2024 | 05/05/2023 | 0 | 0
17 | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks (SM/19186) | SM/19186 | 55319.55 | 205921 | AUGMENTATION | 20 | Delayed | 6 | 06/03/2024 | 31/03/2026 | 12/08/2025 | 07/03/2024 | 3243.89 | 3243.25
18 | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte (SM/18274) | SM/18274 | 125.26 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 23/06/2023 | 31/12/2024 | 22/05/2024 |  | 0 | 0
19 | Source Augmentation of Sarda Water Supply Scheme (SM/18884) | SM/18884 | 138.99 | 0 | AUGMENTATION | 22 | Delayed | 4 | 05/10/2023 | 31/05/2025 | 12/08/2025 | 23/03/2023 | 4.9 | 4.9
20 | Jaynagar Piped Water Supply Scheme (SM/14865) | SM/14865 | 761.37 | 3079 | NEW | 22 | Delayed | 9 | 03/02/2023 | 31/10/2025 | 12/08/2025 | 18/04/2023 | 68.56 | 68.56
21 | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. (SM/11718) | SM/11718 | 706.38 | 1793 | NEW | 22 | Delayed | 10 | 03/08/2022 | 31/07/2025 | 12/08/2025 | 07/02/2022 | 68.13 | 68.13
22 | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. (SM/13749) | SM/13749 | 975.18 | 3486 | NEW | 22 | Delayed | 8 | 17/11/2022 | 31/12/2025 | 12/08/2025 | 05/05/2022 | 74.53 | 74.53
23 | Dakshin Panchla Piped Water Supply Scheme (SM/17196) | SM/17196 | 236.59 | 808 | NEW | 23 | Delayed | 3 | 15/03/2023 | 31/05/2025 | 12/08/2025 | 19/04/2023 | 7.58 | 7.58
24 | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. (SM/11717) | SM/11717 | 475.19 | 1398 | NEW | 23 | Delayed | 16 | 03/08/2022 | 31/07/2025 | 12/08/2025 | 01/11/2022 | 74.84 | 74.84
25 | Augmentation of surface water based Sankrail Piped water supply scheme (SM/19187) | SM/19187 | 33980.3 | 154792 | AUGMENTATION | 25 | Delayed | 12 | 06/03/2024 | 31/12/2025 | 12/08/2025 | 09/03/2024 | 3936.34 | 3936.34
26 | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. (SM/18747) | SM/18747 | 1102.79 | 3464 | NEW | 25 | Delayed | 9 | 17/08/2023 | 02/08/2025 | 12/08/2025 | 29/08/2023 | 100.69 | 100.69
27 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/08988) | SM/08988 | 23.7 | 0 | SUPPORT-WQMSP | 25 | WO no issued | 0 | 29/10/2021 | 31/12/2024 | 22/05/2024 |  | 0 | 0
28 | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme (SM/18565) | SM/18565 | 1175.93 | 3713 | AUGMENTATION | 30 | Delayed | 11 | 31/07/2023 | 31/07/2025 | 12/08/2025 | 07/08/2023 | 126.69 | 126.69
29 | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. (SM/16760) | SM/16760 | 999.07 | 3395 | NEW | 30 | Delayed | 13 | 13/03/2023 | 31/05/2025 | 12/08/2025 | 19/05/2023 | 132.21 | 132.21
30 | Gopalpur Piped Water Supply Scheme (SM/13748) | SM/13748 | 539.15 | 1519 | NEW | 30 | Delayed | 17 | 17/11/2022 | 31/05/2025 | 12/08/2025 | 30/12/2022 | 92.81 | 92.81
31 | Ground Water Based Raspur PWSS (SM/18719) | SM/18719 | 1398.26 | 3327 | NEW | 32 | Delayed | 23 | 10/08/2023 | 02/08/2025 | 12/08/2025 | 29/08/2023 | 327.97 | 327.12
32 | Source Augmentation of Bikihakola Water Supply Scheme (SM/18846) | SM/18846 | 458.77 | 0 | AUGMENTATION | 36 | Delayed | 17 | 29/09/2023 | 31/05/2025 | 12/08/2025 | 11/02/2021 | 78.17 | 63.64
33 | Baniban Zone-III Piped water Supply Scheme (SM/18564) | SM/18564 | 1606.96 | 3716 | NEW | 36 | Delayed | 0 | 31/07/2023 | 31/05/2025 | 12/08/2025 | 16/08/2023 | 7.16 | 7.16
34 | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district (SM/13747) | SM/13747 | 452.58 | 1053 | NEW | 40 | Delayed | 26 | 17/11/2022 | 31/12/2025 | 12/08/2025 | 22/02/2023 | 119.46 | 119.46
35 | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh (SM/15186) | SM/15186 | 826.95 | 3206 | AUGMENTATION | 41 | Delayed | 33 | 07/02/2023 | 30/05/2025 | 12/08/2025 | 16/08/2022 | 274.31 | 274.31
36 | Sherpur Piped Water Supply Scheme (SM/18426) | SM/18426 | 2000.35 | 5601 | NEW | 45 | Delayed | 22 | 18/07/2023 | 02/08/2025 | 12/08/2025 | 29/09/2023 | 444.71 | 444.71
37 | Augmentation of Bamunhati Water Supply Scheme (SM/12874) | SM/12874 | 1303.9 | 4238 | AUGMENTATION | 45 | Delayed | 12 | 23/09/2022 | 30/06/2025 | 12/08/2025 | 22/02/2023 | 157.29 | 157.29
38 | Ground Water Based Water Supply Scheme for Ajangachhi PWSS (SM/18561) | SM/18561 | 1636.21 | 3383 | NEW | 50 | Delayed | 26 | 31/07/2023 | 31/05/2025 | 12/08/2025 | 16/08/2023 | 425.29 | 425.29
39 | Source Augmentation of Amragari Water Supply Scheme (SM/18883) | SM/18883 | 491.99 | 0 | AUGMENTATION | 50 | Delayed | 16 | 05/10/2023 | 31/12/2025 | 12/08/2025 | 15/06/2020 | 77.95 | 77.95
40 | Source Augmentation of Balichak Water Supply Scheme (SM/18885) | SM/18885 | 177.16 | 0 | AUGMENTATION | 50 | Delayed | 33 | 05/10/2023 | 31/07/2025 | 12/08/2025 | 23/11/2023 | 59.29 | 59.29
41 | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. (SM/06614) | SM/06614 | 34.05 | 0 | SUPPORT-WQMSP | 50 | Delayed | 0 | 05/02/2020 | 31/12/2024 | 22/05/2024 | 08/07/2022 | 0 | 0
42 | Sealdanga Piped Water Supply Scheme (SM/14866) | SM/14866 | 689.76 | 1709 | NEW | 53 | Delayed | 15 | 03/02/2023 | 31/05/2025 | 12/08/2025 | 18/04/2023 | 100.48 | 75.76
43 | ICHAPUR PWSS (SM/13629) | SM/13629 | 586.48 | 1335 | NEW | 53 | Delayed | 44 | 11/11/2022 | 15/11/2025 | 12/08/2025 | 05/05/2022 | 257.73 | 257.73
44 | Shyamchak Mini Piped water Supply Scheme (SM/15284) | SM/15284 | 40.6 | 41 | NEW | 55 | Delayed | 53 | 09/02/2023 | 31/05/2025 | 12/08/2025 | 07/06/2023 | 21.4 | 21.4
45 | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. (SM/11719) | SM/11719 | 932.95 | 3480 | NEW | 55 | Delayed | 44 | 04/08/2022 | 31/12/2025 | 12/08/2025 | 30/09/2020 | 407.23 | 407.23
46 | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division (SM/14095) | SM/14095 | 8211.71 | 27364 | AUGMENTATION | 55 | Delayed | 47 | 14/12/2022 | 30/11/2025 | 12/08/2025 | 20/01/2023 | 3861.99 | 3835
47 | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. (SM/08684) | SM/08684 | 20.59 | 0 | SUPPORT-WQMSP | 55 | Delayed | 0 | 19/08/2021 | 31/12/2024 | 22/05/2024 | 30/06/2022 | 0 | 0
48 | Uttar Manasri Piped Water Supply Scheme. (SM/18914) | SM/18914 | 1046.52 | 4232 | NEW | 56 | Delayed | 50 | 09/10/2023 | 16/07/2025 | 12/08/2025 | 16/10/2023 | 522.47 | 522.47
49 | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. (SM/11641) | SM/11641 | 997.11 | 3060 | NEW | 60 | Delayed | 46 | 27/07/2022 | 30/09/2025 | 12/08/2025 | 01/11/2022 | 459.54 | 459.54
50 | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme (SM/18567) | SM/18567 | 1416.25 | 4781 | AUGMENTATION | 60 | Delayed | 29 | 31/07/2023 | 31/12/2025 | 12/08/2025 | 07/08/2023 | 413.35 | 413.35
51 | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. (SM/11720) | SM/11720 | 640.07 | 1232 | NEW | 60 | Delayed | 30 | 03/08/2022 | 31/08/2025 | 12/08/2025 | 07/02/2022 | 190.67 | 190.67
52 | Source Augmentation of Garbhabanipur Water Supply Scheme (SM/18849) | SM/18849 | 115.24 | 0 | AUGMENTATION | 60 | Delayed | 23 | 29/09/2023 | 31/12/2025 | 12/08/2025 | 29/02/2024 | 26.8 | 26.8
53 | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. (SM/17175) | SM/17175 | 986.69 | 3610 | NEW | 61 | Delayed | 44 | 16/03/2023 | 15/12/2025 | 12/08/2025 | 31/08/2022 | 433.87 | 433.87
54 | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. (SM/12562) | SM/12562 | 1842.31 | 5151 | NEW | 63 | Delayed | 56 | 14/09/2022 | 31/12/2025 | 12/08/2025 | 20/09/2022 | 1034.62 | 1034.62
55 | Source Augmentation of Sahapur Piped Water Supply Scheme (SM/18844) | SM/18844 | 152.8 | 0 | AUGMENTATION | 63 | Delayed | 5 | 29/09/2023 | 31/10/2025 | 12/08/2025 | 17/02/2022 | 7.57 | 7.57
56 | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. (SM/18560) | SM/18560 | 1424.21 | 5505 | AUGMENTATION | 64 | Delayed | 41 | 31/07/2023 | 31/10/2025 | 12/08/2025 | 07/08/2023 | 582.61 | 582.61
57 | Augmentation of Ground water based PWSS Jujarsah (SM/10146) | SM/10146 | 1600.62 | 9110 | AUGMENTATION | 66 | Delayed | 57 | 10/02/2022 | 30/06/2025 | 12/08/2025 | 09/09/2022 | 911.83 | 911.83
58 | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. (SM/11007) | SM/11007 | 697.67 | 1774 | NEW | 66 | Delayed | 55 | 01/06/2022 | 31/05/2025 | 12/08/2025 | 07/02/2022 | 386.02 | 386.02
59 | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme (SM/18398) | SM/18398 | 1887.15 | 8036 | AUGMENTATION | 67 | On track | 55 | 12/07/2023 | 31/03/2026 | 12/08/2025 | 18/07/2023 | 1033.86 | 1033.86
60 | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. (SM/13750) | SM/13750 | 524.14 | 1101 | NEW | 68 | Delayed | 31 | 17/11/2022 | 30/06/2025 | 12/08/2025 | 30/12/2022 | 164.83 | 164.83
61 | Augmentation of Ground water based PWSS Mellok Brahman Dakuria (SM/09347) | SM/09347 | 546.45 | 2789 | AUGMENTATION | 69 | Delayed | 76 | 12/11/2021 | 31/05/2025 | 12/08/2025 | 24/11/2021 | 417.91 | 417.91
62 | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. (SM/11000) | SM/11000 | 965.98 | 3323 | NEW | 70 | Delayed | 66 | 01/06/2022 | 31/05/2025 | 12/08/2025 | 07/02/2022 | 641.39 | 641.39
63 | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. (SM/11222) | SM/11222 | 469.24 | 1248 | NEW | 70 | Delayed | 57 | 15/06/2022 | 31/07/2025 | 12/08/2025 | 07/02/2022 | 265.5 | 265.5
64 | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur (SM/11894) | SM/11894 | 760.71 | 1819 | NEW | 70 | Delayed | 39 | 17/08/2022 | 15/12/2025 | 12/08/2025 | 12/08/2022 | 299.29 | 299.29
65 | Khadinan Piped Water Supply Scheme (SM/13847) | SM/13847 | 791.35 | 2051 | NEW | 72 | Delayed | 16 | 25/11/2022 | 31/05/2025 | 12/08/2025 | 15/09/2022 | 126.58 | 126.58
66 | PANCHLA PIPED WATER SUPPLY SCHEME. (SM/18563) | SM/18563 | 1342.84 | 6201 | NEW | 72 | Delayed | 35 | 31/07/2023 | 31/10/2025 | 12/08/2025 | 08/08/2023 | 467.59 | 467.59
67 | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah (SM/13751) | SM/13751 | 700.58 | 3095 | NEW | 73 | Delayed | 43 | 17/11/2022 | 30/09/2025 | 12/08/2025 | 27/02/2023 | 301.43 | 301.43
68 | Augmentation of Ground water based PWSS Mankur Deulgram (SM/09349) | SM/09349 | 993.4 | 5518 | AUGMENTATION | 74 | Delayed | 64 | 12/11/2021 | 31/12/2025 | 12/08/2025 | 24/11/2021 | 632.45 | 632.45
69 | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. (SM/11711) | SM/11711 | 1072.81 | 3591 | NEW | 74 | Delayed | 38 | 03/08/2022 | 30/09/2025 | 12/08/2025 | 31/08/2022 | 402.8 | 402.8
70 | Makardaha PWSS with provision of FHTC in connection of Domjur Block (SM/11159) | SM/11159 | 1084.15 | 3297 | AUGMENTATION | 75 | Delayed | 55 | 02/06/2022 | 15/12/2025 | 12/08/2025 | 31/08/2022 | 595.05 | 595.05
71 | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. (SM/11793) | SM/11793 | 896.37 | 3240 | NEW | 75 | Delayed | 33 | 05/08/2022 | 31/12/2025 | 12/08/2025 | 07/02/2022 | 292.26 | 292.26
72 | Source Augmentation of Chitnan Water Supply Scheme (SM/18848) | SM/18848 | 115.24 | 0 | AUGMENTATION | 75 | Delayed | 15 | 29/09/2023 | 30/07/2025 | 12/08/2025 | 16/12/2022 | 17.58 | 17.58
73 | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC (SM/11572) | SM/11572 | 920.9 | 3092 | NEW | 75 | Delayed | 36 | 22/07/2022 | 31/08/2025 | 12/08/2025 | 16/08/2022 | 334.86 | 334.86
74 | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. (SM/12270) | SM/12270 | 1326.85 | 4274 | NEW | 75 | Delayed | 33 | 09/09/2022 | 30/09/2025 | 12/08/2025 | 16/08/2022 | 438.38 | 438.38
75 | Khorda Etarai Piped Water Supply Scheme (SM/11892) | SM/11892 | 323.64 | 733 | NEW | 75 | Delayed | 62 | 17/08/2022 | 31/08/2025 | 12/08/2025 | 07/02/2022 | 199.24 | 199.24
76 | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. (SM/13770) | SM/13770 | 792.12 | 1774 | NEW | 76 | Delayed | 47 | 18/11/2022 | 20/08/2025 | 12/08/2025 | 05/05/2022 | 373.79 | 373.79
77 | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC (SM/10145) | SM/10145 | 1092.62 | 5786 | AUGMENTATION | 78 | Delayed | 70 | 10/02/2022 | 31/05/2025 | 12/08/2025 | 22/02/2022 | 762.8 | 762.8
78 | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. (SM/10020) | SM/10020 | 1524.22 | 7281 | AUGMENTATION | 78 | Delayed | 85 | 05/01/2022 | 30/06/2025 | 12/08/2025 | 24/06/2020 | 1303 | 1303
79 | Sonatala Piped Water Supply Scheme (SM/14949) | SM/14949 | 729.29 | 2988 | NEW | 78 | Delayed | 52 | 03/02/2023 | 31/07/2025 | 12/08/2025 | 22/02/2023 | 375.72 | 375.72
80 | Bhandardah PWSS with provision of FHTC connection (SM/14197) | SM/14197 | 1149.77 | 3527 | NEW | 80 | Delayed | 57 | 10/01/2023 | 30/07/2025 | 12/08/2025 | 22/02/2023 | 657.88 | 657.88
81 | Source Augmentation of Gobindapur Piped Water Supply Scheme (SM/18843) | SM/18843 | 145.28 | 0 | AUGMENTATION | 80 | On track | 53 | 29/09/2023 | 31/12/2025 | 12/08/2025 | 06/10/2023 | 76.38 | 76.38
82 | Shibgachhia Piped Water Supply Scheme (SM/18193) | SM/18193 | 507.75 | 761 | NEW | 80 | Delayed | 33 | 31/03/2023 | 31/07/2025 | 12/08/2025 | 12/05/2023 | 166.44 | 166.44
83 | Sibpur Piped Water Supply Scheme. (SM/13769) | SM/13769 | 597.87 | 1174 | NEW | 81 | Delayed | 43 | 18/11/2022 | 31/07/2025 | 12/08/2025 | 22/02/2023 | 259.33 | 259.33
84 | Augmentation of Ground water PWSS for Islampur (SM/09428) | SM/09428 | 754.25 | 4465 | AUGMENTATION | 81 | Delayed | 58 | 17/11/2021 | 30/06/2025 | 12/08/2025 | 01/12/2021 | 435.14 | 435.14
85 | Bedhi Chandrapur Piped Water Supply Scheme (SM/18490) | SM/18490 | 497.17 | 1254 | NEW | 82 | Delayed | 42 | 24/07/2023 | 30/07/2025 | 12/08/2025 | 31/07/2023 | 206.48 | 206.48
86 | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur (SM/11893) | SM/11893 | 1018.55 | 2273 | NEW | 82 | Delayed | 55 | 17/08/2022 | 31/10/2025 | 12/08/2025 | 12/08/2022 | 557.99 | 557.99
87 | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. (SM/11853) | SM/11853 | 1056.32 | 3518 | NEW | 83 | Delayed | 27 | 16/08/2022 | 31/08/2025 | 12/08/2025 | 30/12/2022 | 286.14 | 286.14
88 | Augmentation of Keshabpur Water supply scheme (SM/16947) | SM/16947 | 857.9 | 2824 | AUGMENTATION | 85 | Delayed | 27 | 16/03/2023 | 30/06/2025 | 12/08/2025 | 04/04/2023 | 229.68 | 229.68
89 | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. (SM/09930) | SM/09930 | 679.04 | 2475 | AUGMENTATION | 85 | Delayed | 56 | 09/12/2021 | 31/05/2025 | 12/08/2025 | 01/12/2021 | 381.39 | 381.39
90 | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah (SM/14155) | SM/14155 | 1118.67 | 4308 | NEW | 86 | Delayed | 46 | 05/01/2023 | 30/07/2025 | 12/08/2025 | 12/08/2022 | 519.15 | 519.15
91 | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. (SM/11573) | SM/11573 | 808.74 | 2942 | NEW | 88 | Delayed | 55 | 22/07/2022 | 31/08/2025 | 12/08/2025 | 16/08/2022 | 446 | 446
92 | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. (SM/11221) | SM/11221 | 612.7 | 1985 | NEW | 90 | Delayed | 56 | 15/06/2022 | 30/06/2025 | 12/08/2025 | 07/02/2022 | 342.91 | 342.91
93 | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH (SM/18562) | SM/18562 | 1384.19 | 3924 | NEW | 90 | Delayed | 33 | 31/07/2023 | 31/07/2025 | 12/08/2025 | 07/08/2023 | 459.6 | 459.6
94 | Source Augmentation of Nakubar Water Supply Scheme (SM/18847) | SM/18847 | 189.2 | 0 | AUGMENTATION | 90 | Delayed | 11 | 29/09/2023 | 30/06/2025 | 12/08/2025 | 22/07/2022 | 21 | 21
95 | Purbba Gazipur Piped Water Supply Scheme (SM/15287) | SM/15287 | 45.5 | 91 | NEW | 90 | Delayed | 48 | 09/02/2023 | 30/07/2025 | 12/08/2025 | 07/06/2023 | 22 | 22
96 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) (SM/07009) | SM/07009 | 50.47 | 639 | RETROFITTING | 90 | Delayed | 63 | 18/11/2020 | 31/05/2025 | 12/08/2025 | 27/11/2020 | 31.86 | 30.15
97 | Kamina Piped Water Supply Scheme with provision of FHTC (SM/16927) | SM/16927 | 721.94 | 2000 | NEW | 90 | On track | 67 | 16/03/2023 | 01/01/2026 | 12/08/2025 | 19/05/2023 | 480.99 | 480.99
98 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) (SM/07008) | SM/07008 | 98.14 | 1500 | RETROFITTING | 90 | Delayed | 100 | 18/11/2020 | 31/05/2025 | 12/08/2025 | 27/11/2020 | 98.14 | 90.55
99 | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. (SM/14154) | SM/14154 | 1460.26 | 4372 | AUGMENTATION | 90 | Delayed | 48 | 05/01/2023 | 30/06/2025 | 12/08/2025 | 16/08/2022 | 703.89 | 703.89
100 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) (SM/07885) | SM/07885 | 96.53 | 1505 | RETROFITTING | 91 | On track | 63 | 19/01/2021 | 31/08/2025 | 12/08/2025 | 16/02/2022 | 60.65 | 60.65
101 | Sankhali Piped Water Supply Scheme (SM/15289) | SM/15289 | 372.64 | 1058 | NEW | 91 | Delayed | 60 | 09/02/2023 | 31/05/2025 | 12/08/2025 | 22/02/2023 | 224.5 | 224.5
102 | Banharishpur PWSS with FHTC Block Panchla, District-Howrah (SM/11723) | SM/11723 | 853.17 | 3513 | AUGMENTATION | 91 | Delayed | 53 | 02/08/2022 | 30/06/2025 | 12/08/2025 | 19/09/2022 | 454.39 | 454.39
103 | Source Augmentation of Beldubi Water Supply Scheme (SM/18845) | SM/18845 | 155.14 | 0 | AUGMENTATION | 91 | Delayed | 22 | 29/09/2023 | 15/06/2025 | 12/08/2025 | 23/11/2023 | 34.34 | 34.34
104 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) (SM/07884) | SM/07884 | 135.21 | 2203 | RETROFITTING | 91 | On track | 68 | 19/01/2021 | 31/08/2025 | 12/08/2025 | 17/01/2022 | 91.45 | 91.45
105 | Augmentation of Khalatpur PWSS (SM/11271) | SM/11271 | 985.37 | 2484 | AUGMENTATION | 92 | On track | 37 | 24/06/2022 | 31/12/2025 | 12/08/2025 | 01/12/2021 | 361.34 | 361.34
106 | Source Augmentation of Bauria Water Supply Scheme (SM/18850) | SM/18850 | 115.24 | 0 | AUGMENTATION | 92 | On track | 78 | 29/09/2023 | 30/07/2025 | 12/08/2025 | 06/10/2023 | 89.54 | 89.54
107 | Rampur PWSS (SM/11168) | SM/11168 | 614.27 | 1965 | AUGMENTATION | 92 | Delayed | 56 | 02/06/2022 | 30/06/2025 | 12/08/2025 | 01/12/2021 | 343.3 | 343.3
108 | Paschim Panchla Piped Water Supply Scheme. (SM/13768) | SM/13768 | 716.22 | 4347 | NEW | 92 | Delayed | 49 | 18/11/2022 | 15/06/2025 | 12/08/2025 | 05/05/2022 | 349.52 | 349.52
109 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II (SM/07464) | SM/07464 | 164.03 | 2472 | RETROFITTING | 95 | On track | 66 | 30/12/2020 | 31/05/2025 | 12/08/2025 | 05/01/2021 | 107.56 | 107.56
110 | Augmentation of Kanpur Piped water supply scheme (Zone-II) (SM/10021) | SM/10021 | 1553.14 | 3664 | AUGMENTATION | 95 | On track | 45 | 05/01/2022 | 31/12/2025 | 12/08/2025 | 24/05/2022 | 694.72 | 694.72
111 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) (SM/06787) | SM/06787 | 90.51 | 2110 | RETROFITTING | 95 | On track | 77 | 22/09/2020 | 31/05/2025 | 12/08/2025 | 13/10/2020 | 70 | 70
112 | Augmentation of Nischintapur piped water supply scheme. (SM/09720) | SM/09720 | 589.85 | 0 | AUGMENTATION | 95 | Delayed | 71 | 26/11/2021 | 31/05/2025 | 12/08/2025 | 31/01/2022 | 416.47 | 416.47
113 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) (SM/06786) | SM/06786 | 94.88 | 1410 | RETROFITTING | 95 | On track | 84 | 22/09/2020 | 31/05/2025 | 12/08/2025 | 14/01/2021 | 80 | 79.67
114 | Patinan Piped Water Supply Scheme (SM/13848) | SM/13848 | 430.85 | 956 | NEW | 95 | On track | 59 | 25/11/2022 | 31/12/2025 | 12/08/2025 | 30/12/2022 | 252.09 | 252.09
115 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block (SM/07466) | SM/07466 | 167.14 | 2464 | RETROFITTING | 95 | On track | 91 | 30/12/2020 | 31/05/2025 | 12/08/2025 | 23/12/2021 | 151.27 | 151.27
116 | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. (SM/09105) | SM/09105 | 94.09 | 1033 | RETROFITTING | 95 | Delayed | 5 | 28/10/2021 | 31/05/2025 | 12/08/2025 | 07/12/2022 | 4.48 | 4.48
117 | Baniara PWSS with provision of FHTC connection (SM/11722) | SM/11722 | 803.44 | 1976 | NEW | 95 | On track | 61 | 03/08/2022 | 30/10/2025 | 12/08/2025 | 08/12/2022 | 489.14 | 489.14
118 | Source Augmentation of Laskarpur Piped Water Supply Scheme (SM/18842) | SM/18842 | 222.01 | 0 | AUGMENTATION | 95 | Delayed | 41 | 29/09/2023 | 15/06/2025 | 12/08/2025 | 06/10/2023 | 90.79 | 90.79
119 | Source Augmentaion of kulgacchi Water Supply Scheme (SM/18882) | SM/18882 | 251.54 | 0 | AUGMENTATION | 95 | On track | 53 | 05/10/2023 | 31/12/2025 | 12/08/2025 | 23/11/2023 | 134.45 | 134.45
120 | Augmentation of Ground water based PWSS Pancharul (SM/09348) | SM/09348 | 762.1 | 3479 | AUGMENTATION | 95 | Delayed | 70 | 12/11/2021 | 31/05/2025 | 12/08/2025 | 24/11/2021 | 534.65 | 534.65
121 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block (SM/07887) | SM/07887 | 147.18 | 2275 | RETROFITTING | 96 | On track | 66 | 19/01/2021 | 31/07/2025 | 12/08/2025 | 31/03/2022 | 97.77 | 97.77
122 | Augmentation of Ground water based PWSS Bhurshit Bamunpara (SM/09351) | SM/09351 | 618.61 | 2781 | AUGMENTATION | 96 | Delayed | 95 | 12/11/2021 | 31/05/2025 | 12/08/2025 | 01/12/2021 | 588.08 | 588.01
123 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme (SM/06788) | SM/06788 | 97.34 | 1494 | RETROFITTING | 96 | On track | 64 | 22/09/2020 | 31/12/2025 | 12/08/2025 | 12/10/2020 | 62 | 62
124 | Matinala Piped Water Supply Scheme (SM/15285) | SM/15285 | 797.05 | 4568 | NEW | 97 | On track | 63 | 09/02/2023 | 30/06/2025 | 12/08/2025 | 22/02/2023 | 498.96 | 498.96
125 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block (SM/07395) | SM/07395 | 158.03 | 2466 | RETROFITTING | 97 | On track | 89 | 30/12/2020 | 30/07/2025 | 12/08/2025 | 05/01/2021 | 140.97 | 140.97
126 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) (SM/06783) | SM/06783 | 83.47 | 1340 | RETROFITTING | 98 | On track | 100 | 22/09/2020 | 31/05/2025 | 12/08/2025 | 09/11/2020 | 83.47 | 83.47
127 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme (SM/06713) | SM/06713 | 63.09 | 846 | RETROFITTING | 98 | On track | 100 | 18/09/2020 | 30/07/2025 | 12/08/2025 | 04/11/2020 | 63.09 | 63.09
128 | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) (SM/08582) | SM/08582 | 3304.1 | 45330 | RETROFITTING | 98 | On track | 81 | 26/02/2021 | 31/07/2025 | 12/08/2025 | 06/11/2013 | 2686.42 | 2686.17
129 | Ghuteghari Piped Water Supply Scheme (SM/17198) | SM/17198 | 55.7 | 77 | NEW | 98 | Delayed | 1 | 15/03/2023 | 31/05/2025 | 12/08/2025 | 04/04/2023 | 0.33 | 0.33
130 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block (SM/07396) | SM/07396 | 139.91 | 2234 | RETROFITTING | 98 | On track | 97 | 30/12/2020 | 31/05/2025 | 12/08/2025 | 24/12/2021 | 135.83 | 135.83
131 | Augmentation of Ground water based PWSS Kanupat. (SM/09350) | SM/09350 | 414.71 | 1208 | AUGMENTATION | 98 | On track | 63 | 12/11/2021 | 30/07/2025 | 12/08/2025 | 24/11/2021 | 260.76 | 260.76
132 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme (SM/06714) | SM/06714 | 79.55 | 1160 | RETROFITTING | 98 | On track | 100 | 18/09/2020 | 31/05/2025 | 12/08/2025 | 09/11/2020 | 79.55 | 55.98
133 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme (SM/06715) | SM/06715 | 73.1 | 1042 | RETROFITTING | 98 | On track | 83 | 18/09/2020 | 31/05/2025 | 12/08/2025 | 09/11/2020 | 60.45 | 21.96
134 | Aumentation of PWSS for Surikhali (SM/09429) | SM/09429 | 333.75 | 992 | AUGMENTATION | 98 | On track | 61 | 17/11/2021 | 31/07/2025 | 12/08/2025 | 14/03/2022 | 203.72 | 203.67
135 | Chakur water supply scheme. (SM/08987) | SM/08987 | 292.32 | 800 | NEW | 98 | On track | 65 | 29/10/2021 | 31/07/2025 | 12/08/2025 | 11/01/2022 | 190.65 | 190.65
136 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) (SM/06784) | SM/06784 | 78.15 | 1195 | RETROFITTING | 98 | On track | 95 | 22/09/2020 | 31/05/2025 | 12/08/2025 | 09/11/2020 | 74.27 | 74.27
137 | Source Augmentation of Majhu Khetra Water Supply Scheme (SM/18841) | SM/18841 | 115.24 | 0 | AUGMENTATION | 98 | Delayed | 14 | 29/09/2023 | 15/06/2025 | 12/08/2025 | 23/11/2023 | 16.09 | 16.09
138 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) (SM/07075) | SM/07075 | 99.1 | 2600 | RETROFITTING | 98 | On track | 100 | 27/11/2020 | 30/07/2025 | 12/08/2025 | 17/02/2022 | 99.1 | 99.1
139 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme (SM/06717) | SM/06717 | 80.45 | 1150 | RETROFITTING | 98 | On track | 100 | 18/09/2020 | 30/07/2025 | 12/08/2025 | 04/11/2020 | 80.45 | 80.45
140 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme (SM/06721) | SM/06721 | 72.52 | 1051 | RETROFITTING | 98 | On track | 62 | 18/09/2020 | 31/12/2025 | 12/08/2025 | 20/06/2022 | 45.07 | 45.07
141 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block (SM/07881) | SM/07881 | 112.45 | 1744 | RETROFITTING | 98 | On track | 81 | 19/01/2021 | 31/07/2025 | 12/08/2025 | 06/04/2022 | 90.64 | 90.64
142 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block (SM/07886) | SM/07886 | 173.76 | 2721 | RETROFITTING | 98 | On track | 77 | 19/01/2021 | 30/07/2025 | 12/08/2025 | 14/01/2022 | 133.27 | 133.27
143 | Augmentation of Ground water based PWSS Pulgustia (SM/10143) | SM/10143 | 708.72 | 3842 | AUGMENTATION | 98 | Delayed | 97 | 09/02/2022 | 31/03/2025 | 12/08/2025 | 31/08/2022 | 688.08 | 688.08
144 | Rejuvenation of Amta Piped water supply scheme. (SM/08966) | SM/08966 | 2511.74 | 9981 | AUGMENTATION | 98 | On track | 85 | 28/10/2021 | 30/07/2025 | 12/08/2025 | 10/08/2022 | 2140.7 | 2140.7
145 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme (SM/06718) | SM/06718 | 94.59 | 1460 | RETROFITTING | 98 | On track | 90 | 18/09/2020 | 30/07/2025 | 12/08/2025 | 12/10/2020 | 85 | 79.25
146 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme (SM/06720) | SM/06720 | 92.54 | 1413 | RETROFITTING | 98 | On track | 99 | 18/09/2020 | 31/12/2025 | 12/08/2025 | 12/10/2020 | 92.08 | 92.08
147 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block (SM/07883) | SM/07883 | 140.91 | 2184 | RETROFITTING | 98 | On track | 84 | 19/01/2021 | 30/07/2025 | 12/08/2025 | 17/01/2022 | 118.68 | 118.68
148 | Augmentation of Ground Water Based PWSS for Shekrahati (SM/09586) | SM/09586 | 600.2 | 3440 | AUGMENTATION | 98 | On track | 67 | 22/11/2021 | 30/06/2025 | 12/08/2025 | 07/04/2022 | 403.71 | 403.71
149 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme (SM/06716) | SM/06716 | 93.35 | 1375 | RETROFITTING | 98 | On track | 100 | 18/09/2020 | 30/07/2025 | 12/08/2025 | 04/11/2020 | 93.35 | 93.35
150 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block (SM/07467) | SM/07467 | 232.33 | 3453 | RETROFITTING | 98 | On track | 97 | 30/12/2020 | 31/05/2025 | 12/08/2025 | 17/09/2021 | 225.46 | 227.77
151 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme (SM/06719) | SM/06719 | 67.6 | 952 | RETROFITTING | 98 | On track | 100 | 18/09/2020 | 31/12/2025 | 12/08/2025 | 12/10/2020 | 67.6 | 67.5
152 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block (SM/07882) | SM/07882 | 174.48 | 2697 | RETROFITTING | 98 | On track | 91 | 19/01/2021 | 31/12/2025 | 12/08/2025 | 06/04/2022 | 158.03 | 158.03
153 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS (SM/06774) | SM/06774 | 69.51 | 1035 | RETROFITTING | 98 | On track | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/11/2020 | 69.51 | 69.51
154 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) (SM/06785) | SM/06785 | 83.99 | 1211 | RETROFITTING | 98 | On track | 97 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 04/11/2020 | 81.55 | 81.55
155 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme (SM/06789) | SM/06789 | 59.15 | 777 | RETROFITTING | 98 | On track | 94 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 04/11/2020 | 55.77 | 55.77
156 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) (SM/06775) | SM/06775 | 99.82 | 1593 | RETROFITTING | 98 | On track | 99 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 25/08/2020 | 98.35 | 98.35
157 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) (SM/06778) | SM/06778 | 99.91 | 1590 | RETROFITTING | 98 | On track | 98 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 16/10/2020 | 98 | 65.94
158 | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. (SM/11458) | SM/11458 | 1187.53 | 3079 | NEW | 98 | On track | 76 | 12/07/2022 | 31/05/2025 | 12/08/2025 | 07/02/2022 | 907.37 | 907.37
159 | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. (SM/11790) | SM/11790 | 215.28 | 744 | NEW | 98 | On track | 73 | 05/08/2022 | 30/06/2025 | 12/08/2025 | 05/05/2022 | 157.42 | 157.42
160 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) (SM/07077) | SM/07077 | 99.1 | 1583 | RETROFITTING | 98 | On track | 51 | 27/11/2020 | 30/07/2025 | 12/08/2025 | 13/07/2021 | 50.36 | 50.36
161 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block (SM/07010) | SM/07010 | 99.28 | 1457 | RETROFITTING | 99 | On track | 97 | 18/11/2020 | 31/05/2025 | 12/08/2025 | 27/11/2020 | 96.39 | 96.08
162 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block (SM/07880) | SM/07880 | 157.59 | 2452 | RETROFITTING | 99 | On track | 91 | 19/01/2021 | 30/07/2025 | 12/08/2025 | 02/03/2022 | 143.94 | 143.94
163 | Senpur Dwitiya Piped Water Supply Scheme (SM/15199) | SM/15199 | 43.09 | 67 | NEW | 99 | On track | 50 | 07/02/2023 | 30/07/2025 | 12/08/2025 | 07/06/2023 | 21.73 | 21.73
164 | Mollar Chak Piped Water Supplu scheme (SM/15288) | SM/15288 | 44.36 | 68 | NEW | 99 | On track | 49 | 09/02/2023 | 30/06/2025 | 12/08/2025 | 07/06/2023 | 21.57 | 21.57
165 | Sankardari Mini Piped Water Supply Scheme (SM/15189) | SM/15189 | 45.72 | 91 | NEW | 99 | On track | 48 | 07/02/2023 | 30/07/2025 | 12/08/2025 | 07/06/2023 | 21.93 | 21.93
166 | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah (SM/13752) | SM/13752 | 927.57 | 11570 | NEW | 99 | On track | 53 | 17/11/2022 | 30/09/2025 | 12/08/2025 | 12/08/2022 | 493.36 | 492.63
167 | Manirampur Piped Water Supply Scheme (SM/15200) | SM/15200 | 43.19 | 75 | NEW | 99 | On track | 51 | 07/02/2023 | 31/07/2025 | 12/08/2025 | 07/06/2023 | 21.98 | 21.98
168 | Tulsiberia Piped Water Supply Scheme with provision of FHTC. (SM/11574) | SM/11574 | 699.66 | 2011 | NEW | 99 | On track | 67 | 22/07/2022 | 30/06/2025 | 12/08/2025 | 31/08/2022 | 465.9 | 465.9
169 | Rudrapur PWSS with provision of FHTC connection. (SM/11515) | SM/11515 | 914.73 | 2762 | NEW | 99 | On track | 57 | 19/07/2022 | 15/06/2025 | 12/08/2025 | 30/12/2022 | 522.33 | 522.33
170 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II (SM/06780) | SM/06780 | 77.58 | 1200 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/11/2020 | 77.58 | 77.58
171 | Sinking of Eight (08) Nos DWP ( Mark-II) Hand Tube Wells 100 mm x 40 mm dia 230 mtr deep within Sankrail Panchayat Samity under Howrah Division, PHE Dte in connection with super cyclone YAAS (SM/09352) | SM/09352 | 15.87 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 26/02/2025 | 12/08/2025 | 31/01/2022 | 0 | 0
172 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) (SM/07074) | SM/07074 | 99.1 | 1550 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/07/2025 | 12/08/2025 | 11/02/2021 | 99.1 | 99.1
173 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) (SM/06777) | SM/06777 | 99.91 | 1590 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/09/2022 | 99.91 | 100.74
174 | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte (SM/09002) | SM/09002 | 170.57 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 26/02/2025 | 12/08/2025 | 20/12/2021 | 0 | 0
175 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) (SM/06779) | SM/06779 | 89.06 | 1400 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/11/2020 | 89.06 | 89.06
176 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) (SM/07076) | SM/07076 | 99.1 | 1450 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 30/07/2025 | 12/08/2025 | 10/02/2021 | 99.1 | 99.1
177 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) (SM/06782) | SM/06782 | 68.15 | 1035 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/11/2020 | 68.15 | 62.97
178 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) (SM/06776) | SM/06776 | 99.91 | 1590 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 09/11/2020 | 99.91 | 99.91
179 | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. (SM/09424) | SM/09424 | 105.31 | 0 | DISASTER | 100 | 100% Physical | 0 | 17/11/2021 | 26/02/2025 | 12/08/2025 | 24/06/2020 | 0 | 0
180 | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. (SM/09353) | SM/09353 | 23.17 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 26/02/2025 | 12/08/2025 | 31/01/2022 | 0 | 0
181 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block (SM/07465) | SM/07465 | 123.54 | 1711 | RETROFITTING | 100 | 100% Physical | 95 | 30/12/2020 | 31/01/2025 | 12/08/2025 | 31/05/2021 | 117.7 | 117.7
182 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) (SM/06781) | SM/06781 | 69.04 | 1050 | RETROFITTING | 100 | 100% Physical | 100 | 22/09/2020 | 30/07/2025 | 12/08/2025 | 05/11/2020 | 69.04 | 69.04
Total |  |  | 194944.39 | 898352 | [8 empty] | 55457.45 | 55276.67