## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns (SM/09197) | SM/09197 | 267.9 | 0 | DISASTER | 0 | 0% Physical | 0 | 29/10/2021 |  | 04/11/2021 | 29/05/2021 | 0 | 0
2 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Uttar Damodarpur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributio (SM/12755) | SM/12755 | 44.87 | 114 | NEW | 0 | 0% Physical | 2 | 20/09/2022 | 30/06/2025 | 04/06/2025 | 13/03/2023 | 0.7 | 0.7
3 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kamarchak village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou (SM/12758) | SM/12758 | 43.88 | 91 | NEW | 0 | 0% Physical | 1 | 22/09/2022 | 30/06/2025 | 04/06/2025 | 13/03/2023 | 0.56 | 0.56
4 | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. (SM/09032) | SM/09032 | 272.84 | 0 | DISASTER | 0 | 0% Physical | 0 | 30/10/2021 |  | 02/11/2021 | 11/06/2021 | 0 | 0
5 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13828) | SM/13828 | 905.61 | 1734 | NEW | 0 | 0% Physical | 46 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 417.73 | 417.73
6 | GOPALNAGAR UTTAR ZONE-I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/15524) | SM/15524 | 1168.66 | 2817 | NEW | 0 | 0% Physical | 25 | 16/02/2023 | 31/12/2025 | 04/06/2025 | 31/03/2023 | 287.65 | 287.65
7 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC IN THE LEFT OUT AREAS IN ZONE-VI AT DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT - SOUTH (SM/14890) | SM/14890 | 117.28 | 770 | AUGMENTATION | 0 | 0% Physical | 4 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 18/02/2025 | 4.74 | 4.74
8 | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15502) | SM/15502 | 406.64 | 330 | AUGMENTATION | 0 | 0% Physical | 54 | 15/02/2023 | 31/12/2024 | 04/06/2025 | 10/02/2021 | 220.14 | 220.14
9 | AUGMENTATION FOR GROUND WATER BASED KHAS RAMKARCHAR, PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/18871) | SM/18871 | 763.97 | 1602 | AUGMENTATION | 0 | 0% Physical | 40 | 05/10/2023 | 30/04/2025 | 04/06/2025 | 04/03/2019 | 308.52 | 308.52
10 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Kuruli Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divisi (SM/18859) | SM/18859 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 23/08/2024 | 0 | 0
11 | Ground water based DIHI KASLAS piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas (SM/18568) | SM/18568 | 1184.22 | 3846 | AUGMENTATION | 0 | 0% Physical | 15 | 31/07/2023 | 30/12/2025 | 04/06/2025 | 11/08/2023 | 176.16 | 168.71
12 | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. (SM/09195) | SM/09195 | 287.56 | 0 | DISASTER | 0 | 0% Physical | 0 | 29/10/2021 |  | 04/11/2021 | 26/05/2021 | 0 | 0
13 | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11237) | SM/11237 | 468 | 5689 | NEW | 0 | 0% Physical | 10 | 22/06/2022 | 30/11/2025 | 04/06/2025 | 01/11/2022 | 47.12 | 47.12
14 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy (SM/13962) | SM/13962 | 44.52 | 106 | NEW | 0 | 0% Physical | 0 | 01/12/2022 | 30/06/2025 | 04/06/2025 | 15/03/2023 | 0 | 0
15 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Padmapukhuria village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, (SM/13963) | SM/13963 | 44.1 | 96 | NEW | 0 | 0% Physical | 0 | 01/12/2022 | 30/06/2025 | 04/06/2025 | 15/03/2023 | 0 | 0
16 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of RADHABALLABHPUR village of Dearak Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributi (SM/12984) | SM/12984 | 43.67 | 86 | NEW | 0 | 0% Physical | 1 | 28/09/2022 | 30/09/2025 | 04/06/2025 | 16/02/2023 | 0.53 | 0.53
17 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13801) | SM/13801 | 853.87 | 1548 | NEW | 0 | 0% Physical | 26 | 22/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 218.85 | 218.85
18 | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- II (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/14123) | SM/14123 | 1034.92 | 1564 | AUGMENTATION | 0 | 0% Physical | 49 | 02/01/2023 | 31/12/2025 | 04/06/2025 | 30/12/2022 | 503.61 | 500.63
19 | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15473) | SM/15473 | 421.46 | 449 | AUGMENTATION | 0 | 0% Physical | 28 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 18/02/2023 | 118.16 | 118.16
20 | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15088) | SM/15088 | 585.02 | 1600 | AUGMENTATION | 0 | 0% Physical | 46 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2021 | 272 | 261.78
21 | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS (SM/15527) | SM/15527 | 1015.67 | 2234 | NEW | 0 | 0% Physical | 41 | 16/02/2023 | 31/12/2025 | 04/06/2025 | 13/04/2023 | 414.41 | 414.41
22 | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18129) | SM/18129 | 691.26 | 1572 | NEW | 0 | 0% Physical | 22 | 29/03/2023 | 31/12/2025 | 04/06/2025 | 31/03/2023 | 150.51 | 147.12
23 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani (SM/18743) | SM/18743 | 44.44 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/08/2023 | 17/04/2025 | 04/06/2025 | 08/02/2024 | 0 | 0
24 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Mithakundu village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bo (SM/13073) | SM/13073 | 43.8 | 89 | NEW | 0 | 0% Physical | 1 | 29/09/2022 | 30/06/2025 | 04/06/2025 | 13/03/2023 | 0.55 | 0.55
25 | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS (SM/18280) | SM/18280 | 1664.52 | 4771 | AUGMENTATION | 0 | 0% Physical | 29 | 23/06/2023 | 30/12/2025 | 04/06/2025 | 15/07/2023 | 486.82 | 484.71
26 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kabasenre village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou (SM/12757) | SM/12757 | 43.28 | 77 | NEW | 0 | 0% Physical | 0 | 20/09/2022 | 30/06/2025 | 04/06/2025 | 10/03/2023 | 0 | 0
27 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for HOGALKURIA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Di (SM/18856) | SM/18856 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 09/02/2024 | 0 | 0
28 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Ramchandrapur PWSS at Sonarpur Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18857) | SM/18857 | 11.11 | 0 | SOLARISATION | 0 | WO no issued | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 |  | 0 | 0
29 | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT (SM/18983) | SM/18983 | 1043.06 | 2176 | AUGMENTATION | 0 | 0% Physical | 42 | 12/10/2023 | 30/07/2026 | 04/06/2025 | 04/11/2023 | 434.82 | 425.2
30 | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou (SM/12214) | SM/12214 | 648.73 | 2032 | AUGMENTATION | 0 | 0% Physical | 54 | 06/09/2022 | 31/05/2025 | 04/06/2025 | 01/12/2022 | 348.88 | 348.88
31 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PASCHIM SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13760) | SM/13760 | 680.98 | 1958 | NEW | 0 | 0% Physical | 75 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 20/07/2022 | 511.45 | 511.45
32 | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical (SM/09196) | SM/09196 | 285.78 | 0 | DISASTER | 0 | 0% Physical | 0 | 29/10/2021 |  | 04/11/2021 | 28/05/2021 | 0 | 0
33 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of HAZRABAND village of Netra Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syst (SM/12573) | SM/12573 | 45.25 | 123 | NEW | 0 | 0% Physical | 0 | 15/09/2022 | 15/03/2024 | 12/06/2023 | 16/02/2023 | 0 | 0
34 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bhairabitala village of Keoratala Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, (SM/12759) | SM/12759 | 44.57 | 107 | NEW | 0 | 0% Physical | 1 | 20/09/2022 | 31/12/2025 | 04/06/2025 | 10/03/2023 | 0.66 | 0.66
35 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13800) | SM/13800 | 606.73 | 1478 | NEW | 0 | 0% Physical | 82 | 22/11/2022 | 30/12/2025 | 04/06/2025 | 01/08/2022 | 499.83 | 489.09
36 | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/14124) | SM/14124 | 1350.75 | 1049 | AUGMENTATION | 0 | 0% Physical | 40 | 02/01/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 535.79 | 535.79
37 | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15107) | SM/15107 | 321 | 1500 | AUGMENTATION | 0 | 0% Physical | 35 | 04/02/2023 | 31/12/2024 | 04/06/2025 | 15/02/2023 | 112.34 | 112.34
38 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for DEARA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divisio (SM/18855) | SM/18855 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 09/02/2024 | 0 | 0
39 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for JELERHAT Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divi (SM/18861) | SM/18861 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 08/02/2024 | 0 | 0
40 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Sahebpur PWSS at Sonarpur Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18762) | SM/18762 | 11.11 | 0 | SOLARISATION | 0 | WO no issued | 0 | 23/08/2023 | 17/04/2025 | 04/06/2025 |  | 0 | 0
41 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Sitakundu (Zone-I) PWSS at Baruipur Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18742) | SM/18742 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/08/2023 | 17/04/2025 | 04/06/2025 | 22/08/2024 | 0 | 0
42 | Pilot scale implementation of IOT based Measurement & Monitoring of water service delivery in Srinagar Water Supply Scheme, Canning-II Block, South 24 Parganas under South 24-Pgs Mechanical Division, PHE Dte. (SM/18744) | SM/18744 | 5.18 | 0 | AUGMENTATION | 0 | WO no issued | 0 | 17/08/2023 | 17/04/2025 | 04/06/2025 |  | 0 | 0
43 | Providing Functional Household Tap Connection (FHTC) in Zone-III at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte (SM/11244) | SM/11244 | 619.31 | 7715 | NEW | 0 | 0% Physical | 19 | 22/06/2022 | 07/11/2025 | 04/06/2025 | 04/10/2023 | 116.96 | 116.96
44 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bijoyrampur village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, B (SM/12756) | SM/12756 | 44.14 | 97 | NEW | 0 | 0% Physical | 1 | 20/09/2022 | 30/06/2025 | 04/06/2025 | 10/03/2023 | 0.6 | 0.6
45 | AUGMENTATION FOR GROUND WATER BASED SHIBPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13788) | SM/13788 | 953.54 | 1906 | AUGMENTATION | 0 | 0% Physical | 37 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 351.63 | 351.63
46 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Boria and Bayarsing Water Supply Scheme in the district of South 24 Pgs under South 24 Pgs Mechanical Division, PHE (SM/18178) | SM/18178 | 12.37 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 31/03/2023 | 08/01/2025 | 04/06/2025 | 09/10/2023 | 0 | 0
47 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for KANTIPOTA Water Supply Scheme under SONARPUR Block in the district of South 24 Pgs under South 24 Pgs Mechanical Div (SM/18854) | SM/18854 | 11.11 | 0 | SOLARISATION | 0 | WO no issued | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 |  | 0 | 0
48 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Harimul Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divis (SM/18858) | SM/18858 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 23/08/2024 | 0 | 0
49 | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. (SM/11276) | SM/11276 | 803.97 | 2086 | NEW | 0 | 0% Physical | 47 | 24/06/2022 | 31/10/2025 | 04/06/2025 | 07/09/2022 | 377.38 | 377.38
50 | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/18375) | SM/18375 | 1133.47 | 5617 | AUGMENTATION | 0 | 0% Physical | 27 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 18/07/2023 | 311.61 | 311.61
51 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Kamaria, Zone-III PWSS at Jaynagar-I Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18763) | SM/18763 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 23/08/2023 | 17/04/2025 | 04/06/2025 | 23/08/2024 | 0 | 0
52 | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s (SM/12577) | SM/12577 | 38.67 | 34 | NEW | 0 | 0% Physical | 7 | 15/09/2022 | 31/12/2025 | 04/06/2025 | 16/02/2023 | 2.71 | 2.71
53 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Anduldaha Gopalpur village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sys (SM/13964) | SM/13964 | 44.52 | 106 | NEW | 0 | 0% Physical | 0 | 01/12/2022 | 30/06/2025 | 04/06/2025 | 15/03/2023 | 0 | 0
54 | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15471) | SM/15471 | 259.99 | 700 | AUGMENTATION | 0 | 0% Physical | 29 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2021 | 75.99 | 75.99
55 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR UTTAR SURENDRAGANJ, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13841) | SM/13841 | 637.52 | 1205 | NEW | 0 | 0% Physical | 91 | 25/11/2022 | 31/03/2025 | 04/06/2025 | 19/08/2022 | 581.22 | 579.33
56 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering for Jaytala Water Supply Scheme under Baruipur Block in the district of South 24 Pgs under South 24 Pgs Mechanical Divis (SM/18860) | SM/18860 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 03/10/2023 | 17/04/2025 | 04/06/2025 | 23/08/2024 | 0 | 0
57 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Haori PWSS at Budge Budge- II Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18741) | SM/18741 | 11.11 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/08/2023 | 17/04/2025 | 04/06/2025 | 22/08/2024 | 0 | 0
58 | Ground water based SRI KRISHNANAGAR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis (SM/12770) | SM/12770 | 661.26 | 1338 | AUGMENTATION | 0 | 0% Physical | 10 | 21/09/2022 | 31/08/2025 | 04/06/2025 | 27/01/2022 | 66.03 | 66.03
59 | Construction and installation of MANIFOLD and allied works at OHR site of Zone-9, Bishnupur-II Block, under of Surface Water Based Water Supply Scheme in the arsenic affected areas of south 24 parganas district. (SM/13370) | SM/13370 | 22.37 | 0 | AUGMENTATION | 0 | 0% Physical | 73 | 19/10/2022 | 31/03/2025 | 04/06/2025 | 03/11/2022 | 16.26 | 16.26
60 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Chak Ruplaskar village of Ramkishore Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system (SM/13961) | SM/13961 | 43.37 | 79 | NEW | 0 | 0% Physical | 0 | 01/12/2022 | 30/06/2025 | 04/06/2025 | 15/03/2023 | 0 | 0
61 | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT (SM/15633) | SM/15633 | 119.91 | 357 | NEW | 0 | 0% Physical | 2 | 15/02/2023 | 31/10/2025 | 04/06/2025 | 17/03/2023 | 2.39 | 2.39
62 | PROCUREMENT OF CHEMICALS AND GLASSWARE FOR THE 15 (FIFTEEN) NOS OF WATER TESTING LABORATORIES IN THE DISTRICT OF SOUTH 24 PARAGANAS UNDER ALIPORE DIVISION PHE DTE FOR THE PERIOD OF 365 DAYS (SM/17413) | SM/17413 | 64.85 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 20/03/2023 |  | 23/03/2023 | 28/09/2021 | 0 | 0
63 | REGULAR UPKEEPMENT OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) (SM/19283) | SM/19283 | 31.82 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 10/01/2024 | 0 | 0
64 | DRINKING WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KITS & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION (SM/18125) | SM/18125 | 164.27 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 29/03/2023 |  | 31/03/2023 |  | 0 | 0
65 | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District (SM/19092) | SM/19092 | 179.56 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 06/12/2023 |  | 06/12/2023 | 28/02/2024 | 0 | 0
66 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Baruipur Blocks. (SM/08062) | SM/08062 | 38.03 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 01/02/2021 |  | 31/05/2021 | 10/02/2021 | 0 | 0
67 | Chemical, Glassware & Instruments requirement for NABL Accreditation at Baruipur WTP Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Baruipur Sub Division under South 24 Parganas W/S Division-I. (SM/10195) | SM/10195 | 18.8 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 14/01/2022 |  | 18/02/2022 | 24/11/2021 | 0 | 0
68 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. (SM/08064) | SM/08064 | 38.18 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 01/02/2021 |  | 31/05/2021 | 25/03/2022 | 0 | 0
69 | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 (SM/11981) | SM/11981 | 84.54 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 31/08/2022 |  | 31/08/2022 | 23/01/2021 | 0 | 0
70 | Engagement of Implementation Suport Agency (ISA) for implementation of community mobilization and capacity building activities under Jal jeevan Mission (JJM) support Activities for 10 blocks under South 24 Pgns W/S Div-I. (SM/14489) | SM/14489 | 207.98 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 20/01/2023 |  | 29/01/2023 | 02/02/2023 | 0 | 0
71 | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. (SM/19286) | SM/19286 | 182.63 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 30/10/2024 | 0 | 0
72 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. (SM/08060) | SM/08060 | 37.25 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 01/02/2021 |  | 31/05/2021 |  | 0 | 0
73 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Budge Budge-I &II blocks in the District of South 24 Parganas. (SM/08065) | SM/08065 | 25.61 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 01/02/2021 |  | 31/05/2021 |  | 0 | 0
74 | Engagement of implementation support agency (ISA) under JJM for implementation of awareness generation and capacity building activities at grassroots level in the district of South 24 Paraganas for 19 nos. blocks under Alipore Division PHE Dte. (SM/09003) | SM/09003 | 379.7 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 20/05/2022 | 0 | 0
75 | Detail Project Report for Infrastruture developments and supply and installation of HEPA filter system with supply of Chemicals , necessary instruments at Dakshin Raipur State Referral Laboratory for addition of microbiological water qaulity parameters (SM/19341) | SM/19341 | 111.58 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 31/01/2025 |  | 24/02/2025 | 15/05/2025 | 0 | 0
76 | Collection, testing & online entry of drinking water samples through Field Test Kits (FTKs) of rural drinking water sources of 19 nos. blocks in the District of South 24 Parganas. (SM/09031) | SM/09031 | 74.75 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2021 |  | 02/11/2021 | 30/01/2025 | 0 | 0
77 | Collection & Field Testing of Drinking Water Sample and Online Entry Management, Analysis of water quality tests results in PHED Water Quality Dashboard & IMIS both monitoring water safety status of rural drinking water sources of 104 nos. Gram Panchayats (SM/08969) | SM/08969 | 32.94 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 |  | 0 | 0
78 | Operational & maintenance charges of 15 nos. PHED & NGO Managed Laboratories under Alipore Division within the District of South 24 parganas related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for the F.Y-2024-2025. (SM/19326) | SM/19326 | 139.57 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 26/12/2024 |  | 27/12/2024 |  | 0 | 0
79 | Allocation of remuneration to facilitator towards collection of water sample from different sources for testing in District Laboratory, or State Laboratory in South 24 Parganas District under Alipore Division, PHE Dte. (SM/19292) | SM/19292 | 45.54 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 23/05/2025 | 0 | 0
80 | Procurement of Chemicals & Consumables and Glassware etc. required for smooth running of different Laboratory. (SM/06636) | SM/06636 | 59.39 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 27/04/2022 | 0 | 0
81 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Mograhat-II blocks. (SM/08061) | SM/08061 | 27.55 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 01/02/2021 |  | 31/05/2021 | 10/02/2021 | 0 | 0
82 | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Joynagar-I blocks (SM/08063) | SM/08063 | 24.09 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 01/02/2021 |  | 31/05/2021 | 10/02/2021 | 0 | 0
83 | Supply, delivery and installation of desktop computers and other allied accessories (through GeM portal) for different water testing laboratories and Division & Subordinate Offices in the District of South 24 Parganas under Alipore Division, PHE Dte. (SM/10438) | SM/10438 | 37.14 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 12/04/2022 |  | 14/04/2022 | 08/10/2021 | 0 | 0
84 | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) (SM/12280) | SM/12280 | 30.88 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 09/09/2022 |  | 12/09/2022 | 11/10/2022 | 0 | 0
85 | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. (SM/11637) | SM/11637 | 44.89 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 27/07/2022 |  | 29/07/2022 |  | 0 | 0
86 | Project on drinking water availability in the climate change vulnerable Sundarban areas related to Research and Development activity under Jal Jeevan Mission Support Activity (SM/13447) | SM/13447 | 29.92 | 0 | SUPPORT-R&D | 0 | WO no issued | 0 | 02/11/2022 |  | 04/11/2022 |  | 0 | 0
87 | Supply , installation, testing and commissioning of video surveillance equipments at Dakshin Roypur WTP under South 24-Parganas Mechanical Division, PHE, Dte. (SM/18276) | SM/18276 | 59.06 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 23/06/2023 |  | 27/06/2023 |  | 0 | 0
88 | Implementation of ISO/IEC 17025-2017 for NABL Accreditation for Bijoygarh District Water Testing Laboratory at Bijoygarh State General Hospital Campus under Alipur Division. (SM/08679) | SM/08679 | 34.92 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 13/08/2021 |  | 15/08/2021 | 27/07/2021 | 0 | 0
89 | DPR FOR UP-KEEPMENT OF DAY TO DAY LABORATORY & LIBRARY ACTIVITY OF DAKSHIN ROYPUR WATER TREATMENT PLANT AND 02(TWO) SUB-DISTRICT WATER TESTING LABORATORIES OF SOUTH 24 PARGANAS DISTRICT UNDER SOUTH 24-PANGS W/S DIVISION-I, PHE DTE. FOR THE YEAR 2024-2025. (SM/19325) | SM/19325 | 132.24 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 26/12/2024 |  | 27/12/2024 |  | 0 | 0
90 | Chemicals and other required items related to smooth functioning of 15 Water Quality Testing Laboratories under Alipore Division P.H.E Dte. (SM/19340) | SM/19340 | 193.15 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 31/01/2025 |  | 24/02/2025 | 11/03/2025 | 0 | 0
91 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur Water Supply Scheme including one year (SM/09361) | SM/09361 | 101.2 | 500 | RETROFITTING | 3 | Delayed | 3 | 12/11/2021 | 11/12/2025 | 04/06/2025 |  | 3.08 | 3.08
92 | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) (SM/18867) | SM/18867 | 262.32 | 2215 | AUGMENTATION | 4 | Delayed | 8 | 05/10/2023 | 31/03/2025 | 04/06/2025 | 29/09/2022 | 20.86 | 20.86
93 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) (SM/18863) | SM/18863 | 103.56 | 0 | AUGMENTATION | 4 | Delayed | 0 | 05/10/2023 | 31/08/2025 | 04/06/2025 | 29/02/2024 | 0 | 0
94 | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08800) | SM/08800 | 100.52 | 2758 | RETROFITTING | 4 | Delayed | 21 | 13/09/2021 | 13/09/2025 | 04/06/2025 | 25/07/2024 | 21.45 | 21.45
95 | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas (SM/13444) | SM/13444 | 439.33 | 1718 | AUGMENTATION | 5 | Delayed | 13 | 02/11/2022 | 23/12/2025 | 04/06/2025 | 27/01/2022 | 58.94 | 58.94
96 | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18332) | SM/18332 | 2104.47 | 7140 | AUGMENTATION | 5 | Delayed | 0 | 27/06/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 5.51 | 5.51
97 | PROVIDING 100% FHTC IN ZONE I -A & ZONE I-B AT PURBA TATULBERIA MOUZA OF KULTALI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. (SM/11768) | SM/11768 | 992.71 | 14340 | AUGMENTATION | 5 | Delayed | 3 | 02/08/2022 | 07/11/2025 | 04/06/2025 | 22/09/2023 | 34.13 | 34.13
98 | Retrofitting of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. (SM/08796) | SM/08796 | 214.82 | 2994 | RETROFITTING | 5 | Delayed | 9 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 12/08/2021 | 19.93 | 19.93
99 | PROVIDING 100% FHTC IN ZONE I -A & ZONE I-B AT NAPUKURIA MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. (SM/11769) | SM/11769 | 760.33 | 9880 | AUGMENTATION | 5 | Delayed | 8 | 02/08/2022 | 07/11/2025 | 04/06/2025 | 27/10/2023 | 60.86 | 60.86
100 | Providing 100% FHTC in Zone-VI at Sadhukhan Ardari Ektara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11264) | SM/11264 | 747.46 | 9230 | NEW | 5 | Delayed | 9 | 23/06/2022 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 67.11 | 67.11
101 | Ground water based DHANPOTA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/13918) | SM/13918 | 976.25 | 2055 | AUGMENTATION | 5 | Delayed | 0 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 4.67 | 4.67
102 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sumatinagar Water Supply Scheme including one y (SM/09394) | SM/09394 | 246.56 | 1282 | RETROFITTING | 5 | Delayed | 4 | 17/11/2021 | 30/09/2025 | 04/06/2025 | 13/11/2024 | 8.93 | 8.93
103 | Proposed Ground water based MAGRAHAT piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/18578) | SM/18578 | 1112.2 | 3012 | AUGMENTATION | 5 | Delayed | 0 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 2.6 | 2.6
104 | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) (SM/11297) | SM/11297 | 192.77 | 813 | NEW | 5 | Delayed | 4 | 28/06/2022 | 31/03/2025 | 04/06/2025 | 23/08/2022 | 8.53 | 8.53
105 | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 (SM/15776) | SM/15776 | 527.72 | 1180 | AUGMENTATION | 5 | Delayed | 7 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 17/02/2023 | 39.03 | 39.03
106 | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou (SM/12772) | SM/12772 | 655.94 | 1561 | AUGMENTATION | 5 | Delayed | 4 | 21/09/2022 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 26.27 | 26.27
107 | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout (SM/14547) | SM/14547 | 1677.64 | 4890 | AUGMENTATION | 5 | Delayed | 5 | 30/01/2023 | 30/11/2025 | 04/06/2025 | 01/11/2022 | 78.49 | 78.49
108 | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist (SM/15777) | SM/15777 | 944.81 | 2368 | AUGMENTATION | 5 | Delayed | 8 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 73.18 | 73.18
109 | Augmentation of Sirakol Zone-I Water Supply Scheme of Magrahat-I Block under Alipore Division,PHE Dte. (SM/18865) | SM/18865 | 69.96 | 0 | AUGMENTATION | 5 | Delayed | 0 | 05/10/2023 | 30/09/2025 | 04/06/2025 | 15/03/2024 | 0 | 0
110 | Retrofitting for Providing FHTC at Ground Water Based Krishnanagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08803) | SM/08803 | 61.78 | 1624 | RETROFITTING | 6 | Delayed | 37 | 13/09/2021 | 30/09/2023 | 12/06/2023 | 01/08/2024 | 22.77 | 22.77
111 | Ground Water Based RAMKRISHNAPUR Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar - I Block under South 24 Parganas W/S Division - I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Ar (SM/18570) | SM/18570 | 1251.08 | 3080 | AUGMENTATION | 6 | Delayed | 2 | 31/07/2023 | 30/12/2025 | 04/06/2025 | 11/08/2023 | 21.77 | 21.77
112 | Retrofitting for Providing FHTC of Ground Water Based Ramchandranagar Water Supply Scheme (Phase - A) (SM/09466) | SM/09466 | 60.25 | 2052 | RETROFITTING | 7 | Delayed | 21 | 19/11/2021 | 30/09/2023 | 12/06/2023 | 19/10/2022 | 12.64 | 12.64
113 | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/15525) | SM/15525 | 1440.94 | 2415 | NEW | 7 | Delayed | 8 | 16/02/2023 | 30/09/2025 | 04/06/2025 | 15/02/2023 | 114.53 | 114.53
114 | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o (SM/14657) | SM/14657 | 839.75 | 2257 | AUGMENTATION | 8 | Delayed | 6 | 31/01/2023 | 30/06/2025 | 04/06/2025 | 01/11/2022 | 52.35 | 52.35
115 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including (SM/07583) | SM/07583 | 76.19 | 889 | RETROFITTING | 9 | Delayed | 7 | 31/12/2020 | 30/09/2025 | 04/06/2025 |  | 5.48 | 5.48
116 | Providing 100% FHTC in Zone-I at Bainch Beria Srichanda mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11265) | SM/11265 | 469.65 | 5799 | AUGMENTATION | 10 | Delayed | 8 | 23/06/2022 | 30/06/2025 | 04/06/2025 | 11/05/2023 | 35.72 | 35.72
117 | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/13919) | SM/13919 | 934.64 | 2231 | AUGMENTATION | 10 | Delayed | 4 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 39.47 | 39.47
118 | Ground water based MASTIKARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11779) | SM/11779 | 841.85 | 2056 | AUGMENTATION | 10 | Delayed | 5 | 02/08/2022 | 31/03/2025 | 04/06/2025 | 07/09/2022 | 39.96 | 39.96
119 | Proposed Ground water based BELARIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/14548) | SM/14548 | 1124.97 | 2889 | AUGMENTATION | 10 | Delayed | 0 | 30/01/2023 | 31/03/2025 | 04/06/2025 | 29/12/2022 | 2.76 | 2.76
120 | Ground water based KAMARIA ZONE - I piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/13775) | SM/13775 | 689.19 | 2051 | AUGMENTATION | 10 | Delayed | 19 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 13/02/2023 | 128.89 | 128.89
121 | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PART-B) (SM/16197) | SM/16197 | 835.04 | 3159 | AUGMENTATION | 10 | WO no issued | 0 | 24/02/2023 | 31/12/2025 | 04/06/2025 |  | 0 | 0
122 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAORAKHALI AND ADJOINING MOUZAS (BAKULTALA). (SM/18864) | SM/18864 | 223.79 | 0 | AUGMENTATION | 10 | Delayed | 0 | 05/10/2023 | 31/05/2025 | 04/06/2025 | 01/07/2024 | 0 | 0
123 | Proposed Ground water based RAYNAGAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/18577) | SM/18577 | 1284.63 | 3284 | AUGMENTATION | 10 | Delayed | 18 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 230.1 | 230.1
124 | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC)(PART-B) (SM/16195) | SM/16195 | 817.46 | 1797 | AUGMENTATION | 10 | Delayed | 15 | 24/02/2023 | 31/03/2025 | 04/06/2025 | 24/07/2023 | 121.62 | 121.62
125 | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | SM/11235 | 733.04 | 9193 | NEW | 10 | Delayed | 22 | 22/06/2022 | 30/11/2025 | 04/06/2025 | 24/04/2023 | 160.31 | 160.31
126 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of BAINTALA village of Tambuldaha-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syste (SM/12575) | SM/12575 | 44.39 | 103 | NEW | 12 | Delayed | 11 | 15/09/2022 | 31/03/2025 | 04/06/2025 | 15/02/2023 | 4.7 | 4.7
127 | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. (SM/08798) | SM/08798 | 99.12 | 1221 | RETROFITTING | 12 | Delayed | 6 | 13/09/2021 | 31/12/2025 | 04/06/2025 | 19/08/2021 | 5.63 | 5.63
128 | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE (SM/18286) | SM/18286 | 1168.82 | 4150 | AUGMENTATION | 15 | Delayed | 17 | 23/06/2023 | 31/12/2025 | 04/06/2025 | 20/07/2023 | 200.14 | 200.14
129 | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE (SM/13364) | SM/13364 | 189.79 | 3309 | RETROFITTING | 15 | Delayed | 12 | 19/10/2022 | 31/12/2025 | 04/06/2025 | 15/09/2022 | 23.1 | 23.1
130 | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas (SM/18569) | SM/18569 | 1125.46 | 2835 | AUGMENTATION | 15 | Delayed | 3 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 36.58 | 36.58
131 | Retrofitting of pipeline for FHTC drive including PWD road restoration on connection with pipe water supply scheme incluiding FHTC for CHOTTA GP in THAKURPUKUR MEHESTALA block under South 24 pgs. W/S division-I , PHE Dte (SM/12808) | SM/12808 | 382.59 | 400 | AUGMENTATION | 15 | Delayed | 89 | 21/09/2022 | 31/08/2025 | 04/06/2025 | 17/03/2023 | 339.75 | 339.75
132 | Providing Functional Household Tap Connection (FHTC) in Zone-VIII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11239) | SM/11239 | 465.42 | 5655 | NEW | 15 | Delayed | 18 | 22/06/2022 | 30/09/2025 | 04/06/2025 | 01/11/2022 | 83.94 | 83.94
133 | Providing Functional Household Tap Connection (FHTC) in Zone-IX at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11238) | SM/11238 | 286.44 | 3434 | NEW | 15 | Delayed | 29 | 22/06/2022 | 31/08/2025 | 04/06/2025 | 01/11/2022 | 84.31 | 84.31
134 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KRISHNADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13871) | SM/13871 | 649.44 | 936 | NEW | 16 | Delayed | 20 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 20/07/2022 | 128.93 | 128.93
135 | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-II,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE (SM/13360) | SM/13360 | 272.66 | 5721 | RETROFITTING | 16 | Delayed | 14 | 19/10/2022 | 31/03/2025 | 04/06/2025 | 15/09/2022 | 38.37 | 38.37
136 | Providing 100% FHTC in Zone-II at Rajballabhpur Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. (SM/11973) | SM/11973 | 503.71 | 6219 | AUGMENTATION | 16 | Delayed | 8 | 29/08/2022 | 31/10/2025 | 04/06/2025 | 24/08/2023 | 38.31 | 38.31
137 | Retrofitting for Providing FHTC at Ground Water Based Mansadwip & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08807) | SM/08807 | 78.11 | 2004 | RETROFITTING | 17 | Delayed | 16 | 13/09/2021 | 30/09/2025 | 04/06/2025 |  | 12.34 | 12.34
138 | Proposed Ground water based BANTRA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/18498) | SM/18498 | 1158.38 | 3046 | AUGMENTATION | 17 | Delayed | 15 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 03/08/2023 | 178.67 | 178.67
139 | Retrofitting for Providing FHTC at Ground Water Based Companir Char & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08802) | SM/08802 | 57.2 | 1508 | RETROFITTING | 17 | Delayed | 15 | 13/09/2021 | 30/09/2025 | 04/06/2025 | 07/07/2022 | 8.64 | 8.64
140 | PROPOSED GROUND WATER BASED JAMALHATI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BARUIPUR, SONARPUR BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT FOR AUGMENTATION GROUND WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFEC (SM/15780) | SM/15780 | 261.84 | 508 | AUGMENTATION | 18 | Delayed | 17 | 20/02/2023 | 31/08/2025 | 04/06/2025 | 12/05/2023 | 45.76 | 45.76
141 | Proposed Ground Water Based UTTARPARANIJ Piped Water Supply Scheme to accommodate FHTC in Jaynagar - I Block, under South 24 Parganas W/S Division - I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic A (SM/14849) | SM/14849 | 906.15 | 2168 | AUGMENTATION | 18 | Delayed | 5 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 28/02/2023 | 43.96 | 43.96
142 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl (SM/07410) | SM/07410 | 49.5 | 880 | RETROFITTING | 18 | Delayed | 11 | 29/12/2020 | 30/09/2025 | 04/06/2025 |  | 5.41 | 5.41
143 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPRASTHA PWSS , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13804) | SM/13804 | 433.48 | 841 | NEW | 19 | Delayed | 17 | 22/11/2022 | 30/09/2025 | 04/06/2025 | 01/08/2022 | 75.59 | 75.59
144 | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) (SM/18868) | SM/18868 | 113.58 | 1484 | AUGMENTATION | 19 | Delayed | 42 | 05/10/2023 | 30/09/2025 | 04/06/2025 | 13/05/2022 | 47.3 | 47.3
145 | Proposed Ground water based JALDHAPA piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/18269) | SM/18269 | 1123.3 | 3451 | AUGMENTATION | 20 | Delayed | 12 | 21/06/2023 | 31/10/2025 | 04/06/2025 | 14/07/2023 | 132.41 | 132.41
146 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one (SM/09395) | SM/09395 | 213.05 | 975 | RETROFITTING | 20 | Delayed | 23 | 17/11/2021 | 30/11/2025 | 04/06/2025 | 12/07/2022 | 49.74 | 49.74
147 | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout (SM/11772) | SM/11772 | 914.86 | 1904 | AUGMENTATION | 20 | Delayed | 22 | 02/08/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 196.7 | 196.7
148 | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde (SM/18499) | SM/18499 | 1516.18 | 2830 | AUGMENTATION | 20 | Delayed | 6 | 26/07/2023 | 31/03/2026 | 04/06/2025 | 04/08/2023 | 84.08 | 84.08
149 | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13787) | SM/13787 | 989.64 | 1764 | AUGMENTATION | 20 | Delayed | 22 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 09/12/2022 | 222.62 | 222.62
150 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN KASHINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13763) | SM/13763 | 610.98 | 1684 | NEW | 20 | Delayed | 25 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 01/08/2022 | 153.05 | 153.05
151 | Ground water based CHHAYANI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas Distric for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parga (SM/12217) | SM/12217 | 229.95 | 907 | AUGMENTATION | 20 | Delayed | 36 | 06/09/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 82.34 | 82.34
152 | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11267) | SM/11267 | 753.66 | 9305 | NEW | 20 | Delayed | 16 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 14/03/2023 | 118.45 | 118.45
153 | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af (SM/12804) | SM/12804 | 693.66 | 1672 | AUGMENTATION | 20 | Delayed | 5 | 21/09/2022 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 32.71 | 32.71
154 | MALIPUKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13515) | SM/13515 | 920.07 | 2076 | AUGMENTATION | 20 | Delayed | 9 | 02/11/2022 | 30/09/2025 | 04/06/2025 | 01/12/2022 | 86.29 | 86.29
155 | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15862) | SM/15862 | 874.24 | 1543 | AUGMENTATION | 20 | Delayed | 12 | 20/02/2023 | 30/09/2025 | 04/06/2025 | 15/03/2023 | 102.95 | 102.95
156 | AUGMENTATION AND RETROFITTING OF ADHIA (PART-B) (KAKRADAHA)PWSS FOR PROVIDING FHTC, BLOCK - CANNING-I (SM/15055) | SM/15055 | 615.9 | 955 | AUGMENTATION | 21 | Delayed | 9 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 18/04/2023 | 58.42 | 49.64
157 | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE (SM/13782) | SM/13782 | 888.31 | 2430 | AUGMENTATION | 21 | Delayed | 9 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 79.42 | 72.21
158 | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/14873) | SM/14873 | 944.81 | 2868 | AUGMENTATION | 22 | Delayed | 10 | 03/02/2023 | 31/07/2025 | 04/06/2025 | 04/05/2023 | 98.94 | 94.06
159 | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS (SM/18381) | SM/18381 | 2068.02 | 6774 | AUGMENTATION | 22 | Delayed | 6 | 11/07/2023 | 31/03/2025 | 04/06/2025 | 20/07/2023 | 114.41 | 114.41
160 | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15043) | SM/15043 | 666.83 | 1544 | AUGMENTATION | 22 | Delayed | 21 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 18/04/2023 | 142.72 | 142.72
161 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu (SM/09471) | SM/09471 | 162.44 | 2421 | RETROFITTING | 22 | Delayed | 22 | 19/11/2021 | 30/09/2025 | 04/06/2025 | 07/07/2021 | 35.93 | 35.93
162 | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. (SM/13784) | SM/13784 | 835.96 | 1749 | AUGMENTATION | 24 | Delayed | 13 | 18/11/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 109.9 | 109.9
163 | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. (SM/13756) | SM/13756 | 483.56 | 995 | AUGMENTATION | 24 | Delayed | 19 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 21/12/2020 | 91.07 | 91.07
164 | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A (SM/12805) | SM/12805 | 664.21 | 1580 | AUGMENTATION | 25 | Delayed | 15 | 21/09/2022 | 31/05/2025 | 04/06/2025 | 20/05/2022 | 102.01 | 102.01
165 | Ground water based PETUA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12047) | SM/12047 | 707.63 | 1422 | AUGMENTATION | 25 | Delayed | 6 | 01/09/2022 | 31/12/2025 | 04/06/2025 | 14/09/2022 | 44.93 | 44.93
166 | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT MONIRTAT MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11247) | SM/11247 | 685.07 | 8108 | AUGMENTATION | 25 | Delayed | 13 | 22/06/2022 | 31/07/2025 | 04/06/2025 | 30/03/2023 | 89.83 | 89.83
167 | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe (SM/13921) | SM/13921 | 860.97 | 1571 | AUGMENTATION | 25 | Delayed | 4 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 33.69 | 33.69
168 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So (SM/14724) | SM/14724 | 1926.73 | 0 | AUGMENTATION | 25 | Delayed | 23 | 31/01/2023 | 31/05/2025 | 04/06/2025 | 27/01/2022 | 433.98 | 433.98
169 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VII AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRI (SM/14891) | SM/14891 | 247.47 | 950 | AUGMENTATION | 25 | Delayed | 0 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 27/01/2025 | 0 | 0
170 | PROVIDING 100% FHTC IN ZONE-IV AT GARDOANI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11249) | SM/11249 | 959.87 | 12937 | AUGMENTATION | 25 | Delayed | 18 | 22/06/2022 | 31/08/2025 | 04/06/2025 | 19/12/2022 | 168.75 | 168.75
171 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II at RAJBALLABHPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. (SM/18707) | SM/18707 | 1438.58 | 0 | AUGMENTATION | 25 | Delayed | 23 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 335.08 | 335.08
172 | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13785) | SM/13785 | 995.63 | 2039 | AUGMENTATION | 25 | Delayed | 11 | 18/11/2022 | 31/05/2025 | 04/06/2025 | 09/12/2022 | 111.88 | 111.88
173 | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18225) | SM/18225 | 1283.05 | 3040 | AUGMENTATION | 25 | Delayed | 11 | 27/04/2023 | 31/07/2025 | 04/06/2025 | 03/05/2023 | 136.91 | 136.91
174 | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte (SM/18574) | SM/18574 | 1318.37 | 4562 | AUGMENTATION | 25 | Delayed | 2 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 31.02 | 31.02
175 | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18548) | SM/18548 | 1481.3 | 2582 | AUGMENTATION | 25 | Delayed | 11 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 04/08/2023 | 160.21 | 160.21
176 | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS (SM/14157) | SM/14157 | 1196.88 | 3540 | NEW | 25 | Delayed | 17 | 05/01/2023 | 31/03/2025 | 04/06/2025 | 31/01/2023 | 208.86 | 208.86
177 | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08793) | SM/08793 | 66.55 | 1753 | RETROFITTING | 25 | Delayed | 24 | 13/09/2021 | 30/09/2025 | 04/06/2025 |  | 15.78 | 15.68
178 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH (SM/14473) | SM/14473 | 265.91 | 1470 | AUGMENTATION | 25 | Delayed | 0 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 11/04/2023 | 0 | 0
179 | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas (SM/18866) | SM/18866 | 233.39 | 0 | AUGMENTATION | 26 | Delayed | 0 | 05/10/2023 | 31/08/2025 | 04/06/2025 | 29/02/2024 | 0 | 0
180 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including (SM/07404) | SM/07404 | 93.55 | 1263 | RETROFITTING | 26 | Delayed | 25 | 29/12/2020 | 30/09/2025 | 04/06/2025 | 16/10/2020 | 22.97 | 14.96
181 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one (SM/09393) | SM/09393 | 270.16 | 1623 | RETROFITTING | 26 | Delayed | 39 | 17/11/2021 | 30/09/2025 | 04/06/2025 | 20/01/2022 | 105 | 105
182 | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08801) | SM/08801 | 136.66 | 4037 | RETROFITTING | 27 | Delayed | 26 | 13/09/2021 | 30/09/2025 | 04/06/2025 | 10/09/2021 | 35.3 | 35.3
183 | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08805) | SM/08805 | 121.55 | 3444 | RETROFITTING | 28 | Delayed | 27 | 13/09/2021 | 30/09/2025 | 04/06/2025 | 09/09/2021 | 32.3 | 32.3
184 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION (SM/13868) | SM/13868 | 661.26 | 1338 | NEW | 28 | Delayed | 26 | 25/11/2022 | 30/09/2025 | 04/06/2025 | 19/08/2022 | 174.28 | 174.28
185 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. (SM/15954) | SM/15954 | 435.54 | 1196 | AUGMENTATION | 28 | Delayed | 13 | 22/02/2023 | 31/03/2025 | 04/06/2025 | 26/10/2021 | 57.27 | 57.27
186 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl (SM/07760) | SM/07760 | 264.49 | 3867 | RETROFITTING | 29 | Delayed | 28 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 08/02/2021 | 73.77 | 73.77
187 | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/15871) | SM/15871 | 469.57 | 839 | AUGMENTATION | 29 | Delayed | 13 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 12/05/2023 | 60.88 | 50.23
188 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR TAMBUL DAHA (PART - II) UNDER ALIPORE DIVISION, BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/12745) | SM/12745 | 54.38 | 143 | AUGMENTATION | 29 | Delayed | 22 | 20/09/2022 | 31/03/2025 | 04/06/2025 | 09/03/2023 | 12.18 | 12.18
189 | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/12636) | SM/12636 | 753.69 | 1675 | NEW | 29 | Delayed | 37 | 19/09/2022 | 31/12/2025 | 04/06/2025 | 13/12/2022 | 281.91 | 281.91
190 | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. (SM/11278) | SM/11278 | 464.16 | 918 | NEW | 29 | Delayed | 21 | 24/06/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 97.44 | 97.44
191 | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar (SM/15867) | SM/15867 | 482.09 | 682 | AUGMENTATION | 30 | Delayed | 7 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 33.33 | 29.75
192 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A (SM/18380) | SM/18380 | 1622.84 | 1853 | AUGMENTATION | 30 | Delayed | 13 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 04/08/2023 | 212.46 | 212.46
193 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. (SM/14729) | SM/14729 | 2446.13 | 0 | AUGMENTATION | 30 | Delayed | 29 | 31/01/2023 | 31/05/2025 | 04/06/2025 | 12/11/2021 | 707.38 | 707.38
194 | GROUND WATER BASED BHUBANNAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS (SM/16294) | SM/16294 | 840.39 | 2427 | NEW | 30 | Delayed | 13 | 24/02/2023 | 31/07/2025 | 04/06/2025 | 01/03/2023 | 108.03 | 108.03
195 | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte (SM/11263) | SM/11263 | 749.74 | 9256 | NEW | 30 | Delayed | 25 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 31/08/2022 | 185.98 | 185.98
196 | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT (SM/18873) | SM/18873 | 798.04 | 2050 | AUGMENTATION | 30 | Delayed | 21 | 05/10/2023 | 30/04/2025 | 04/06/2025 | 14/12/2023 | 169.49 | 169.49
197 | Retrofitting for Providing FHTC of Ground Water Based Nebutala Water Supply Scheme (Phase - A) (SM/09465) | SM/09465 | 30.88 | 820 | RETROFITTING | 30 | Delayed | 16 | 19/11/2021 | 31/03/2025 | 04/06/2025 |  | 5.05 | 5.05
198 | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff (SM/13781) | SM/13781 | 931 | 1742 | AUGMENTATION | 30 | Delayed | 0 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 2.7 | 2.7
199 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-VI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) (SM/18376) | SM/18376 | 1502.9 | 1477 | AUGMENTATION | 30 | Delayed | 25 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 15/05/2023 | 378.25 | 378.25
200 | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o (SM/12806) | SM/12806 | 639.17 | 1642 | AUGMENTATION | 30 | Delayed | 1 | 21/09/2022 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 5.08 | 5.08
201 | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11849) | SM/11849 | 653.78 | 1387 | NEW | 30 | Delayed | 23 | 16/08/2022 | 31/12/2025 | 04/06/2025 | 31/01/2022 | 147.99 | 147.99
202 | PROVIDING 100% FHTC IN ZONE-VII A & ZONE-VII B AT MAIPIT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11254) | SM/11254 | 803.21 | 9506 | NEW | 30 | Delayed | 32 | 22/06/2022 | 31/03/2025 | 04/06/2025 | 20/10/2022 | 260.7 | 260.7
203 | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. (SM/12802) | SM/12802 | 649.12 | 1615 | AUGMENTATION | 30 | Delayed | 1 | 21/09/2022 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 8.49 | 8.49
204 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER DIA (SM/13832) | SM/13832 | 668.65 | 1683 | AUGMENTATION | 30 | Delayed | 12 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 23/09/2022 | 82.45 | 82.45
205 | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15861) | SM/15861 | 999.91 | 2106 | AUGMENTATION | 30 | Delayed | 19 | 20/02/2023 | 31/07/2025 | 04/06/2025 | 03/03/2023 | 192.71 | 192.71
206 | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District (SM/12883) | SM/12883 | 713.57 | 1611 | AUGMENTATION | 30 | Delayed | 4 | 23/09/2022 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 27.09 | 27.09
207 | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. (SM/12801) | SM/12801 | 715.64 | 1785 | AUGMENTATION | 30 | Delayed | 16 | 21/09/2022 | 30/09/2025 | 04/06/2025 | 20/05/2022 | 113.48 | 113.48
208 | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic (SM/14550) | SM/14550 | 1191.73 | 3208 | AUGMENTATION | 30 | Delayed | 5 | 30/01/2023 | 31/10/2025 | 04/06/2025 | 29/12/2022 | 63.23 | 63.23
209 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15972) | SM/15972 | 637.96 | 951 | AUGMENTATION | 30 | Delayed | 39 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 13/03/2023 | 249.38 | 249.38
210 | AUGMENTATION OF GROUND WATER BASED KHAN SAHEBER ABAD PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT (SM/18874) | SM/18874 | 512.39 | 1272 | AUGMENTATION | 30 | Delayed | 32 | 05/10/2023 | 31/12/2025 | 04/06/2025 | 06/10/2023 | 165.26 | 165.26
211 | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT (SM/18876) | SM/18876 | 869.32 | 1875 | AUGMENTATION | 30 | Delayed | 42 | 05/10/2023 | 31/12/2025 | 04/06/2025 | 07/11/2023 | 361.61 | 361.61
212 | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11877) | SM/11877 | 803.64 | 2362 | NEW | 30 | Delayed | 32 | 17/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 257.24 | 257.24
213 | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18392) | SM/18392 | 1014.76 | 2846 | NEW | 30 | Delayed | 29 | 11/07/2023 | 30/09/2025 | 04/06/2025 | 12/04/2023 | 290.75 | 290.75
214 | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar (SM/14549) | SM/14549 | 1217.03 | 3406 | AUGMENTATION | 30 | Delayed | 7 | 30/01/2023 | 31/07/2025 | 04/06/2025 | 02/05/2023 | 86.36 | 64.47
215 | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/15774) | SM/15774 | 500.43 | 878 | AUGMENTATION | 30 | Delayed | 23 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 06/03/2023 | 115.64 | 115.64
216 | Regular Up-gradation and Up-Keepment of Water Quality Monitoring, Programme Management & its implementation throughout the State related to WQMSP under Jal Jeevan Mission. (SM/13890) | SM/13890 | 437.98 | 0 | SUPPORT-WQMSP | 30 | Delayed | 0 | 25/11/2022 | 31/03/2024 | 27/03/2024 | 24/01/2023 | 0 | 0
217 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i (SM/07636) | SM/07636 | 276.48 | 3898 | RETROFITTING | 31 | Delayed | 60 | 07/01/2021 | 30/09/2025 | 04/06/2025 | 23/03/2022 | 167.22 | 167.22
218 | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/13780) | SM/13780 | 935.03 | 2477 | AUGMENTATION | 31 | Delayed | 24 | 18/11/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 223.63 | 223.63
219 | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou (SM/15866) | SM/15866 | 988.68 | 2078 | AUGMENTATION | 31 | Delayed | 13 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 06/03/2023 | 129.5 | 129.5
220 | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o (SM/18266) | SM/18266 | 1103.92 | 3239 | AUGMENTATION | 32 | Delayed | 17 | 21/06/2023 | 31/07/2025 | 04/06/2025 | 14/07/2023 | 182.54 | 182.54
221 | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/18681) | SM/18681 | 1377.33 | 3721 | AUGMENTATION | 32 | Delayed | 34 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 466.15 | 451.83
222 | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/14871) | SM/14871 | 945.98 | 2259 | AUGMENTATION | 32 | Delayed | 35 | 03/02/2023 | 31/08/2025 | 04/06/2025 | 01/11/2022 | 328.46 | 328.46
223 | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/14466) | SM/14466 | 737.38 | 1167 | AUGMENTATION | 32 | Delayed | 18 | 20/01/2023 | 31/12/2025 | 04/06/2025 | 28/03/2023 | 130.08 | 130.08
224 | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM (SM/14419) | SM/14419 | 1079.94 | 0 | NEW | 32 | Delayed | 32 | 20/01/2023 | 31/05/2025 | 04/06/2025 | 27/01/2023 | 345.14 | 345.14
225 | Retrofitting for Providing FHTC at Ground Water Based Kamalpur Rudranagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08795) | SM/08795 | 100.31 | 2791 | RETROFITTING | 33 | Delayed | 32 | 13/09/2021 | 30/09/2025 | 04/06/2025 | 09/09/2021 | 32.05 | 32.05
226 | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) (SM/09922) | SM/09922 | 1213.9 | 3659 | AUGMENTATION | 33 | Delayed | 29 | 10/12/2021 | 31/12/2025 | 04/06/2025 | 10/08/2021 | 356.6 | 356.6
227 | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14861) | SM/14861 | 983.21 | 2497 | AUGMENTATION | 33 | Delayed | 23 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 28/02/2023 | 225.54 | 225.54
228 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. (SM/15050) | SM/15050 | 109.97 | 387 | NEW | 33 | Delayed | 7 | 03/02/2023 | 31/08/2025 | 04/06/2025 | 11/04/2023 | 7.3 | 7.3
229 | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/14658) | SM/14658 | 601.24 | 1687 | AUGMENTATION | 34 | Delayed | 14 | 31/01/2023 | 31/03/2025 | 04/06/2025 | 27/01/2022 | 86.68 | 86.68
230 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SURENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13799) | SM/13799 | 670.02 | 1810 | NEW | 34 | Delayed | 32 | 22/11/2022 | 30/09/2025 | 04/06/2025 | 01/08/2022 | 215.53 | 215.53
231 | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11497) | SM/11497 | 564.67 | 853 | NEW | 35 | Delayed | 35 | 19/07/2022 | 30/06/2025 | 04/06/2025 | 25/04/2022 | 196.33 | 196.33
232 | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18328) | SM/18328 | 1508.19 | 3295 | AUGMENTATION | 35 | Delayed | 20 | 27/06/2023 | 31/07/2025 | 04/06/2025 | 02/08/2023 | 300.75 | 296.12
233 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s (SM/13513) | SM/13513 | 717.38 | 0 | AUGMENTATION | 35 | Delayed | 15 | 02/11/2022 | 31/03/2025 | 04/06/2025 | 15/03/2022 | 108.78 | 108.78
234 | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U (SM/18497) | SM/18497 | 1442.59 | 2503 | AUGMENTATION | 35 | Delayed | 23 | 26/07/2023 | 02/03/2025 | 04/06/2025 | 03/08/2023 | 337.56 | 337.56
235 | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18500) | SM/18500 | 1193.59 | 2549 | AUGMENTATION | 35 | Delayed | 12 | 26/07/2023 | 02/11/2025 | 04/06/2025 | 11/08/2023 | 147.03 | 147.03
236 | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) (SM/09468) | SM/09468 | 85.95 | 2939 | RETROFITTING | 35 | Delayed | 33 | 19/11/2021 | 30/09/2025 | 04/06/2025 | 01/09/2021 | 28.67 | 28.67
237 | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/13985) | SM/13985 | 946.1 | 2556 | AUGMENTATION | 35 | Delayed | 6 | 01/12/2022 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 59.27 | 53.76
238 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S (SM/14726) | SM/14726 | 1485.87 | 0 | AUGMENTATION | 35 | Delayed | 8 | 31/01/2023 | 31/08/2025 | 04/06/2025 | 25/03/2022 | 116.3 | 116.3
239 | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15771) | SM/15771 | 825.04 | 1377 | AUGMENTATION | 35 | Delayed | 18 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 10/03/2023 | 151.72 | 151.72
240 | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/11281) | SM/11281 | 1003.59 | 3451 | AUGMENTATION | 36 | Delayed | 39 | 28/06/2022 | 30/09/2025 | 04/06/2025 | 03/09/2021 | 390.29 | 390.29
241 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-VII, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER (SM/18377) | SM/18377 | 3043.4 | 2514 | AUGMENTATION | 36 | Delayed | 36 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 04/08/2023 | 1086.77 | 1086.77
242 | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/18244) | SM/18244 | 1201.85 | 2325 | AUGMENTATION | 37 | Delayed | 29 | 16/06/2023 | 31/12/2025 | 04/06/2025 | 04/08/2023 | 344.01 | 344.01
243 | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. (SM/12635) | SM/12635 | 766.05 | 1433 | NEW | 37 | Delayed | 25 | 19/09/2022 | 31/12/2025 | 04/06/2025 | 17/10/2022 | 191.14 | 191.14
244 | Proposed Ground water based JANGALIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/13986) | SM/13986 | 779.62 | 1690 | AUGMENTATION | 37 | Delayed | 12 | 01/12/2022 | 30/06/2025 | 04/06/2025 | 01/03/2023 | 92.28 | 76.38
245 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS (SM/18674) | SM/18674 | 4858.69 | 9792 | AUGMENTATION | 37 | Delayed | 37 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 07/08/2023 | 1795.96 | 1795.96
246 | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS (SM/13839) | SM/13839 | 677.84 | 1466 | NEW | 38 | Delayed | 32 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 17/03/2023 | 217.58 | 217.58
247 | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/14462) | SM/14462 | 1407.08 | 2708 | NEW | 38 | Delayed | 27 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 25/01/2023 | 374.04 | 374.04
248 | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe (SM/16131) | SM/16131 | 783.62 | 1692 | AUGMENTATION | 38 | Delayed | 18 | 22/02/2023 | 31/03/2025 | 04/06/2025 | 17/03/2023 | 137.74 | 137.74
249 | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr (SM/13779) | SM/13779 | 966.64 | 1967 | AUGMENTATION | 38 | Delayed | 22 | 18/11/2022 | 30/04/2025 | 04/06/2025 | 21/02/2023 | 214.85 | 214.85
250 | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di (SM/18573) | SM/18573 | 1066 | 4257 | AUGMENTATION | 39 | Delayed | 35 | 31/07/2023 | 31/08/2025 | 04/06/2025 | 16/08/2023 | 373.11 | 373.11
251 | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/13923) | SM/13923 | 807.06 | 1806 | AUGMENTATION | 39 | Delayed | 35 | 29/11/2022 | 31/07/2025 | 04/06/2025 | 01/03/2023 | 286.19 | 286.19
252 | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/15864) | SM/15864 | 577.52 | 1424 | AUGMENTATION | 39 | Delayed | 15 | 20/02/2023 | 30/11/2025 | 04/06/2025 | 17/03/2023 | 85.43 | 85.43
253 | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08809) | SM/08809 | 58.39 | 1467 | RETROFITTING | 40 | Delayed | 32 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 09/09/2021 | 18.95 | 18.95
254 | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08810) | SM/08810 | 69.52 | 1861 | RETROFITTING | 40 | Delayed | 31 | 13/09/2021 | 31/12/2025 | 04/06/2025 | 01/09/2021 | 21.84 | 21.84
255 | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15478) | SM/15478 | 306.56 | 1500 | AUGMENTATION | 40 | Delayed | 2 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 15/02/2023 | 7.41 | 7.41
256 | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan (SM/16930) | SM/16930 | 523.27 | 1238 | AUGMENTATION | 40 | Delayed | 29 | 16/03/2023 | 30/08/2026 | 04/06/2025 | 27/01/2022 | 151.98 | 149.68
257 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- (SM/18706) | SM/18706 | 2440.32 | 0 | AUGMENTATION | 40 | Delayed | 29 | 04/08/2023 | 31/07/2025 | 04/06/2025 | 16/08/2023 | 711.99 | 711.99
258 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH (SM/13969) | SM/13969 | 329.74 | 2000 | AUGMENTATION | 40 | Delayed | 39 | 01/12/2022 | 31/12/2025 | 04/06/2025 | 13/03/2023 | 128.31 | 128.31
259 | Proposed ground water based CHAK BALAIBAG piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTE (SM/13783) | SM/13783 | 964.1 | 2793 | AUGMENTATION | 40 | Delayed | 16 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 27/01/2022 | 156.43 | 156.43
260 | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So (SM/12803) | SM/12803 | 690.8 | 1684 | AUGMENTATION | 40 | Delayed | 8 | 21/09/2022 | 31/03/2025 | 04/06/2025 | 15/12/2022 | 56.95 | 56.95
261 | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/18697) | SM/18697 | 1210.86 | 1802 | AUGMENTATION | 40 | Delayed | 23 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 281.55 | 281.55
262 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DIGAMBERPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13764) | SM/13764 | 691.66 | 2030 | NEW | 40 | Delayed | 36 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 247.29 | 247.23
263 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH (SM/14140) | SM/14140 | 2417.25 | 0 | AUGMENTATION | 40 | Delayed | 19 | 02/01/2023 | 31/07/2025 | 04/06/2025 | 27/12/2021 | 458.81 | 458.81
264 | GROUND WATER BASED MRINALNAGAR PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS (SM/16292) | SM/16292 | 965.59 | 2770 | NEW | 40 | Delayed | 36 | 24/02/2023 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 346.03 | 346.03
265 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VII OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 2 (SM/18400) | SM/18400 | 1869.02 | 5851 | AUGMENTATION | 40 | Delayed | 21 | 12/07/2023 | 31/12/2025 | 04/06/2025 | 17/07/2023 | 395.24 | 395.24
266 | Providing Functional Household Tap Connection (FHTC) in Zone-I at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11245) | SM/11245 | 744.81 | 9379 | NEW | 40 | Delayed | 9 | 22/06/2022 | 31/10/2025 | 04/06/2025 | 24/08/2023 | 69.31 | 69.31
267 | Providing Functional Household Tap Connection (FHTC) in Zone-VI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11240) | SM/11240 | 265.35 | 3156 | NEW | 40 | Delayed | 19 | 22/06/2022 | 31/05/2025 | 04/06/2025 | 28/03/2023 | 49.88 | 49.88
268 | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11243) | SM/11243 | 765.3 | 9619 | NEW | 40 | Delayed | 18 | 22/06/2022 | 31/08/2025 | 04/06/2025 | 24/04/2023 | 139.79 | 139.79
269 | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM (SM/12043) | SM/12043 | 981.18 | 2290 | NEW | 40 | Delayed | 18 | 01/09/2022 | 30/06/2025 | 04/06/2025 | 26/09/2022 | 181.04 | 181.04
270 | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/14986) | SM/14986 | 909.79 | 1197 | AUGMENTATION | 40 | Delayed | 22 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 16/03/2023 | 198.08 | 198.08
271 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN (SM/15485) | SM/15485 | 2125.83 | 0 | AUGMENTATION | 40 | Delayed | 59 | 15/02/2023 | 31/08/2025 | 04/06/2025 | 24/04/2023 | 1255.68 | 1255.68
272 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dt (SM/18219) | SM/18219 | 3818.38 | 0 | AUGMENTATION | 40 | Delayed | 54 | 27/04/2023 | 30/11/2025 | 04/06/2025 | 14/01/2022 | 2073.55 | 2073.55
273 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- IV AT DIAMOND HARBOUR II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DIS (SM/13912) | SM/13912 | 631.92 | 2650 | AUGMENTATION | 40 | Delayed | 4 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 17/07/2023 | 26.66 | 26.66
274 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV (SM/15484) | SM/15484 | 1932.84 | 0 | AUGMENTATION | 40 | Delayed | 47 | 15/02/2023 | 31/07/2025 | 04/06/2025 | 26/10/2021 | 901.83 | 901.83
275 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South (SM/18655) | SM/18655 | 1782.14 | 0 | AUGMENTATION | 40 | Delayed | 36 | 04/08/2023 | 30/11/2025 | 04/06/2025 | 02/03/2022 | 637.11 | 637.11
276 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South (SM/18708) | SM/18708 | 1824.04 | 0 | AUGMENTATION | 40 | Delayed | 32 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 585.7 | 585.7
277 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME (SM/15468) | SM/15468 | 506.99 | 708 | AUGMENTATION | 40 | Delayed | 11 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 03/11/2023 | 57.29 | 57.29
278 | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS (SM/16291) | SM/16291 | 959.66 | 2815 | NEW | 40 | Delayed | 26 | 24/02/2023 | 31/12/2025 | 04/06/2025 | 01/03/2023 | 252.89 | 252.89
279 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o (SM/07591) | SM/07591 | 66.06 | 1075 | RETROFITTING | 40 | Delayed | 27 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 17/03/2022 | 17.9 | 17.9
280 | Providing 100% FHTC in Mograhat-1/IV at Hijalghat Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. (SM/11972) | SM/11972 | 511.19 | 6310 | AUGMENTATION | 40 | Delayed | 8 | 29/08/2022 | 31/05/2025 | 04/06/2025 | 24/07/2023 | 38.87 | 38.87
281 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includi (SM/07588) | SM/07588 | 91.66 | 780 | RETROFITTING | 40 | Delayed | 38 | 31/12/2020 | 30/09/2025 | 04/06/2025 | 08/02/2021 | 34.83 | 34.83
282 | Augmentation of Canning Water Supply Scheme. (SM/13116) | SM/13116 | 3144.76 | 9947 | AUGMENTATION | 40 | Delayed | 39 | 10/10/2022 | 31/12/2025 | 04/06/2025 | 23/02/2022 | 1230.57 | 1230.57
283 | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/12045) | SM/12045 | 466.33 | 750 | NEW | 41 | Delayed | 29 | 01/09/2022 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 136.89 | 136.89
284 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea (SM/09358) | SM/09358 | 383.9 | 1655 | RETROFITTING | 41 | Delayed | 39 | 12/11/2021 | 30/09/2025 | 04/06/2025 | 04/04/2022 | 151.22 | 151.22
285 | Ground water based HARIHARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/14860) | SM/14860 | 873.42 | 2142 | AUGMENTATION | 41 | Delayed | 15 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 130.57 | 130.57
286 | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11647) | SM/11647 | 686.61 | 2051 | AUGMENTATION | 41 | Delayed | 4 | 27/07/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 26.65 | 26.65
287 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including (SM/07413) | SM/07413 | 82.02 | 1957 | RETROFITTING | 42 | Delayed | 40 | 29/12/2020 | 30/09/2025 | 04/06/2025 | 15/10/2020 | 33.18 | 33.18
288 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER D (SM/15321) | SM/15321 | 1279.51 | 4527 | AUGMENTATION | 42 | Delayed | 14 | 09/02/2023 | 31/12/2025 | 04/06/2025 | 23/09/2022 | 181.21 | 181.21
289 | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14876) | SM/14876 | 939.62 | 2779 | AUGMENTATION | 43 | Delayed | 10 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 95.38 | 95.38
290 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11255) | SM/11255 | 776.49 | 9189 | AUGMENTATION | 43 | Delayed | 17 | 22/06/2022 | 30/04/2026 | 04/06/2025 | 19/12/2022 | 128.29 | 128.29
291 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS (SM/13978) | SM/13978 | 88.28 | 264 | NEW | 44 | Delayed | 32 | 01/12/2022 | 31/08/2025 | 04/06/2025 | 05/08/2022 | 28.68 | 28.68
292 | Ground water based RASAPUNJA piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESTALA block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte (SM/18576) | SM/18576 | 1526.57 | 5908 | AUGMENTATION | 44 | Delayed | 42 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 10/08/2023 | 636.49 | 636.49
293 | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT (SM/11850) | SM/11850 | 547.06 | 1030 | NEW | 44 | Delayed | 49 | 16/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 270.13 | 270.13
294 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-I OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - (SM/14476) | SM/14476 | 469.18 | 3240 | AUGMENTATION | 45 | Delayed | 23 | 20/01/2023 | 30/04/2026 | 04/06/2025 | 04/02/2023 | 106.34 | 106.34
295 | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/15965) | SM/15965 | 895.39 | 2159 | AUGMENTATION | 45 | Delayed | 39 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 22/02/2023 | 352.86 | 344.61
296 | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou (SM/15775) | SM/15775 | 655.37 | 1097 | AUGMENTATION | 45 | Delayed | 40 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 28/04/2023 | 259.73 | 259.73
297 | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12230) | SM/12230 | 922.96 | 1991 | AUGMENTATION | 45 | Delayed | 30 | 06/09/2022 | 31/03/2025 | 04/06/2025 | 13/02/2023 | 274.65 | 274.65
298 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o (SM/09075) | SM/09075 | 125.25 | 1133 | RETROFITTING | 45 | Delayed | 44 | 29/10/2021 | 30/09/2025 | 04/06/2025 | 25/02/2022 | 54.89 | 44.89
299 | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un (SM/18546) | SM/18546 | 1055.04 | 1766 | AUGMENTATION | 45 | Delayed | 34 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 03/08/2023 | 359.96 | 359.96
300 | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/14041) | SM/14041 | 1041.53 | 1170 | AUGMENTATION | 45 | Delayed | 42 | 12/12/2022 | 31/12/2025 | 04/06/2025 | 07/07/2021 | 435.55 | 435.55
301 | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12211) | SM/12211 | 992.71 | 1892 | AUGMENTATION | 45 | Delayed | 18 | 06/09/2022 | 31/05/2025 | 04/06/2025 | 07/11/2022 | 176.35 | 176.35
302 | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI (SM/15044) | SM/15044 | 315.24 | 620 | AUGMENTATION | 45 | Delayed | 47 | 04/02/2023 | 30/10/2026 | 04/06/2025 | 12/10/2020 | 149.08 | 135.27
303 | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/18331) | SM/18331 | 1112.74 | 3624 | AUGMENTATION | 45 | Delayed | 17 | 27/06/2023 | 31/07/2025 | 04/06/2025 | 24/08/2023 | 188.24 | 188.24
304 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i (SM/07756) | SM/07756 | 136.4 | 1447 | RETROFITTING | 45 | Delayed | 43 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 04/03/2019 | 59.13 | 59.13
305 | PROVIDING 100% FHTC IN ZONE-III A & ZONE-III B AT BELADURGANAGAR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11256) | SM/11256 | 653.33 | 7731 | AUGMENTATION | 45 | Delayed | 18 | 22/06/2022 | 31/10/2025 | 04/06/2025 | 25/07/2023 | 116.64 | 116.64
306 | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM (SM/12016) | SM/12016 | 925.13 | 2255 | NEW | 45 | Delayed | 23 | 01/09/2022 | 31/12/2025 | 04/06/2025 | 26/09/2022 | 214.52 | 214.52
307 | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE (SM/18281) | SM/18281 | 3613.64 | 5901 | AUGMENTATION | 45 | Delayed | 9 | 23/06/2023 | 31/12/2025 | 04/06/2025 | 24/03/2023 | 338.29 | 338.29
308 | AUGMENTATION OF GROUND WATER BASED PURUSOTTAMPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE IN SOUTH 24 PARGANAS DISTRICT (SM/18875) | SM/18875 | 754.23 | 1351 | AUGMENTATION | 45 | Delayed | 36 | 05/10/2023 | 30/04/2025 | 04/06/2025 | 14/12/2023 | 271.13 | 271.13
309 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE (SM/18378) | SM/18378 | 1225.12 | 2111 | AUGMENTATION | 45 | Delayed | 32 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 13/10/2020 | 391.33 | 391.33
310 | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/17225) | SM/17225 | 233.48 | 700 | AUGMENTATION | 45 | Delayed | 23 | 15/03/2023 | 31/12/2025 | 04/06/2025 | 13/06/2023 | 54.14 | 54.14
311 | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. (SM/18394) | SM/18394 | 1245.72 | 2677 | NEW | 45 | Delayed | 42 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 17/07/2023 | 517.57 | 517.57
312 | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/14857) | SM/14857 | 999.01 | 2247 | AUGMENTATION | 45 | Delayed | 8 | 03/02/2023 | 31/05/2025 | 04/06/2025 | 24/04/2023 | 75.58 | 75.58
313 | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS (SM/13836) | SM/13836 | 455.48 | 753 | NEW | 46 | Delayed | 33 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 151.83 | 151.83
314 | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS (SM/16013) | SM/16013 | 792.87 | 2098 | AUGMENTATION | 46 | Delayed | 37 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 11/04/2023 | 294.42 | 294.42
315 | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p (SM/11771) | SM/11771 | 873.29 | 1604 | AUGMENTATION | 46 | Delayed | 37 | 02/08/2022 | 30/06/2025 | 04/06/2025 | 02/09/2022 | 325.6 | 322.92
316 | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. (SM/12234) | SM/12234 | 555.18 | 901 | AUGMENTATION | 46 | Delayed | 30 | 07/09/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 165.28 | 165.28
317 | Proposed Ground water based DAKSHIN GOURIPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic A (SM/18330) | SM/18330 | 1122.98 | 3883 | AUGMENTATION | 46 | Delayed | 26 | 27/06/2023 | 31/12/2025 | 04/06/2025 | 08/08/2023 | 286.98 | 286.98
318 | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/12572) | SM/12572 | 1333.27 | 3853 | AUGMENTATION | 46 | Delayed | 46 | 15/09/2022 | 31/03/2025 | 04/06/2025 | 13/10/2022 | 609.73 | 609.73
319 | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/15786) | SM/15786 | 487.09 | 917 | AUGMENTATION | 46 | Delayed | 33 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 06/03/2023 | 159.76 | 159.76
320 | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/15563) | SM/15563 | 940.63 | 1161 | AUGMENTATION | 46 | Delayed | 20 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 18/04/2023 | 190.02 | 190.02
321 | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS (SM/13834) | SM/13834 | 449.63 | 888 | NEW | 47 | Delayed | 27 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 121.81 | 116.59
322 | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11780) | SM/11780 | 759.14 | 1815 | AUGMENTATION | 47 | Delayed | 34 | 02/08/2022 | 30/07/2026 | 04/06/2025 | 07/09/2022 | 258.2 | 248.09
323 | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI (SM/15503) | SM/15503 | 324.17 | 550 | AUGMENTATION | 47 | Delayed | 65 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 211.31 | 201.38
324 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sridharnagar W/S Scheme includ (SM/07625) | SM/07625 | 136.98 | 1493 | RETROFITTING | 47 | Delayed | 63 | 07/01/2021 | 30/09/2025 | 04/06/2025 | 21/05/2021 | 86.47 | 86.47
325 | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM (SM/12017) | SM/12017 | 996.63 | 2075 | NEW | 47 | Delayed | 36 | 01/09/2022 | 30/09/2025 | 04/06/2025 | 26/09/2022 | 359.77 | 359.77
326 | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11730) | SM/11730 | 486.48 | 790 | AUGMENTATION | 48 | Delayed | 28 | 03/08/2022 | 30/11/2025 | 04/06/2025 | 01/11/2022 | 136.32 | 136.32
327 | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/10482) | SM/10482 | 522.46 | 1799 | AUGMENTATION | 48 | Delayed | 19 | 13/04/2022 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 98.99 | 98.99
328 | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist (SM/11296) | SM/11296 | 302.26 | 1100 | NEW | 48 | Delayed | 48 | 28/06/2022 | 31/03/2025 | 04/06/2025 | 28/09/2022 | 144.46 | 144.46
329 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-V OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARG (SM/13913) | SM/13913 | 817.13 | 2258 | AUGMENTATION | 48 | Delayed | 12 | 29/11/2022 | 30/09/2025 | 04/06/2025 | 15/09/2022 | 98.61 | 98.61
330 | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) (SM/11298) | SM/11298 | 236.09 | 1032 | NEW | 48 | Delayed | 84 | 28/06/2022 | 30/09/2025 | 04/06/2025 | 07/09/2022 | 198.71 | 198.71
331 | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS (SM/15100) | SM/15100 | 926.63 | 2430 | AUGMENTATION | 48 | Delayed | 27 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 15/02/2023 | 251.56 | 251.56
332 | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff (SM/18678) | SM/18678 | 1071.38 | 2530 | AUGMENTATION | 48 | Delayed | 20 | 04/08/2023 | 30/12/2025 | 04/06/2025 | 11/08/2023 | 212.1 | 212.1
333 | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/13776) | SM/13776 | 639.19 | 2051 | AUGMENTATION | 48 | Delayed | 40 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 13/02/2023 | 252.54 | 252.54
334 | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of (SM/15865) | SM/15865 | 858.78 | 1608 | AUGMENTATION | 48 | Delayed | 43 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 17/03/2023 | 371.34 | 371.34
335 | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. (SM/11277) | SM/11277 | 813.74 | 1909 | NEW | 49 | Delayed | 72 | 24/06/2022 | 31/03/2025 | 04/06/2025 | 22/09/2022 | 587.03 | 587.03
336 | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. (SM/18128) | SM/18128 | 150.23 | 356 | NEW | 49 | Delayed | 42 | 29/03/2023 | 31/12/2025 | 04/06/2025 | 11/04/2023 | 63.65 | 63.65
337 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/11745) | SM/11745 | 515.83 | 1079 | NEW | 50 | Delayed | 46 | 03/08/2022 | 31/03/2025 | 04/06/2025 | 08/08/2022 | 238.43 | 235.45
338 | AUGMENTATION OF GROUND WATER BASED DAKSHIN RAYPUR PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/11213) | SM/11213 | 1218.77 | 4966 | AUGMENTATION | 50 | Delayed | 40 | 13/06/2022 | 31/12/2025 | 04/06/2025 | 08/09/2021 | 484.4 | 484.4
339 | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11788) | SM/11788 | 632.8 | 2051 | AUGMENTATION | 50 | Delayed | 41 | 03/08/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 256.68 | 256.68
340 | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11253) | SM/11253 | 585.88 | 6789 | NEW | 50 | Delayed | 29 | 22/06/2022 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 172.32 | 172.32
341 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/14984) | SM/14984 | 359.72 | 766 | NEW | 50 | Delayed | 22 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 21/02/2023 | 78.79 | 78.79
342 | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15476) | SM/15476 | 138.66 | 410 | AUGMENTATION | 50 | Delayed | 48 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 66.73 | 66.73
343 | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. (SM/15963) | SM/15963 | 754.5 | 1593 | AUGMENTATION | 50 | Delayed | 39 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 17/04/2023 | 290.77 | 290.77
344 | Providing Functional Household Tap Connection (FHTC) in Zone-XI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11236) | SM/11236 | 190.17 | 2329 | NEW | 50 | Delayed | 17 | 22/06/2022 | 31/10/2025 | 04/06/2025 | 17/08/2023 | 32.05 | 32.05
345 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRANARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13827) | SM/13827 | 533.61 | 1453 | NEW | 50 | Delayed | 34 | 25/11/2022 | 30/04/2025 | 04/06/2025 | 01/08/2022 | 183.72 | 183.72
346 | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/14487) | SM/14487 | 1446.08 | 2842 | AUGMENTATION | 50 | Delayed | 19 | 20/01/2023 | 31/07/2025 | 04/06/2025 | 01/03/2023 | 267.6 | 267.6
347 | Providing 100% FHTC in Zone-VIII at Khela Rampur Sirakol mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11260) | SM/11260 | 913 | 11274 | NEW | 50 | Delayed | 13 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 14/03/2023 | 114.4 | 114.4
348 | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13500) | SM/13500 | 939.52 | 1611 | AUGMENTATION | 50 | Delayed | 36 | 02/11/2022 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 336.68 | 336.68
349 | Providing 100% FHTC in Zone-VII at Ajodhyanagar mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11261) | SM/11261 | 277.69 | 3427 | NEW | 50 | Delayed | 15 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 42.22 | 42.22
350 | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11262) | SM/11262 | 387.24 | 9799 | NEW | 50 | Delayed | 73 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 16/01/2023 | 283.34 | 283.34
351 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN (SM/12204) | SM/12204 | 482.42 | 0 | AUGMENTATION | 50 | Delayed | 35 | 06/09/2022 | 31/07/2025 | 04/06/2025 | 26/04/2022 | 169.04 | 169.04
352 | AUGMENTATION OF GROUND WATER BASED RAKHALPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/14987) | SM/14987 | 830.49 | 815 | AUGMENTATION | 50 | Delayed | 7 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 56 | 56
353 | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. (SM/16116) | SM/16116 | 736.03 | 1220 | AUGMENTATION | 50 | Delayed | 37 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 12/05/2022 | 269.07 | 269.07
354 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- (SM/18715) | SM/18715 | 841.46 | 0 | AUGMENTATION | 50 | Delayed | 50 | 10/08/2023 | 31/05/2025 | 04/06/2025 | 16/08/2023 | 422.41 | 422.41
355 | Detailed project report for KHARAMBA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Und (SM/18545) | SM/18545 | 1691.33 | 3153 | AUGMENTATION | 50 | Delayed | 11 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 03/08/2023 | 183.25 | 183.25
356 | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12209) | SM/12209 | 715.25 | 1057 | AUGMENTATION | 50 | Delayed | 18 | 06/09/2022 | 30/06/2025 | 04/06/2025 | 16/02/2023 | 129.31 | 129.31
357 | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of (SM/18571) | SM/18571 | 1161.95 | 2838 | AUGMENTATION | 50 | Delayed | 36 | 31/07/2023 | 31/03/2026 | 04/06/2025 | 11/08/2023 | 414.52 | 414.52
358 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/18549) | SM/18549 | 2067.43 | 7293 | AUGMENTATION | 50 | Delayed | 20 | 26/07/2023 | 31/03/2025 | 04/06/2025 | 25/08/2023 | 422.08 | 422.08
359 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on (SM/07405) | SM/07405 | 71.63 | 1536 | RETROFITTING | 50 | Delayed | 50 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 01/08/2023 | 35.69 | 35.69
360 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year (SM/09014) | SM/09014 | 82.73 | 1529 | RETROFITTING | 50 | Delayed | 37 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 02/11/2021 | 30.59 | 30.59
361 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI (SM/15975) | SM/15975 | 870.09 | 1519 | AUGMENTATION | 50 | Delayed | 42 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 22/02/2023 | 369.12 | 369.12
362 | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13570) | SM/13570 | 1617.17 | 1131 | AUGMENTATION | 50 | Delayed | 41 | 09/11/2022 | 31/12/2025 | 04/06/2025 | 14/11/2022 | 666.44 | 666.44
363 | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. (SM/11280) | SM/11280 | 721.27 | 1510 | NEW | 50 | Delayed | 50 | 24/06/2022 | 31/03/2025 | 04/06/2025 | 22/09/2022 | 363.06 | 363.06
364 | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM (SM/12044) | SM/12044 | 919.88 | 1893 | NEW | 50 | Delayed | 28 | 01/09/2022 | 31/05/2025 | 04/06/2025 | 26/09/2022 | 258.71 | 258.71
365 | JAYKRISHNAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13514) | SM/13514 | 939.07 | 1718 | AUGMENTATION | 50 | Delayed | 28 | 02/11/2022 | 31/03/2025 | 04/06/2025 | 01/12/2022 | 265.3 | 265.3
366 | Retrofitting of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. (SM/08797) | SM/08797 | 252.25 | 2619 | RETROFITTING | 50 | Delayed | 7 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 17/08/2021 | 18.77 | 18.77
367 | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. (SM/15225) | SM/15225 | 1124.06 | 4010 | AUGMENTATION | 50 | Delayed | 3 | 06/02/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 32.43 | 32.43
368 | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under (SM/15757) | SM/15757 | 997.26 | 2064 | AUGMENTATION | 50 | Delayed | 25 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 03/03/2023 | 250.55 | 250.55
369 | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08808) | SM/08808 | 50.16 | 1212 | RETROFITTING | 50 | Delayed | 47 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 09/09/2021 | 23.51 | 23.51
370 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year (SM/09017) | SM/09017 | 287.5 | 6768 | RETROFITTING | 50 | Delayed | 96 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 06/12/2021 | 277.1 | 277.1
371 | PROVIDING 100% FHTC IN ZONE VII -A & ZONE VII-B AT NALGORA MOUZA OF JOYNAGAR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. (SM/11770) | SM/11770 | 838.69 | 11912 | AUGMENTATION | 50 | Delayed | 25 | 02/08/2022 | 31/10/2025 | 04/06/2025 | 21/07/2023 | 213.01 | 213.01
372 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER (SM/15506) | SM/15506 | 386.34 | 595 | AUGMENTATION | 50 | Delayed | 21 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 18/07/2023 | 80.88 | 80.88
373 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply (SM/16187) | SM/16187 | 1161.61 | 0 | AUGMENTATION | 50 | Delayed | 42 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 09/03/2023 | 492.36 | 492.36
374 | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11645) | SM/11645 | 660.2 | 1753 | AUGMENTATION | 50 | Delayed | 34 | 27/07/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 223.26 | 223.26
375 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BHAJNA UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/12732) | SM/12732 | 662.57 | 1638 | NEW | 50 | Delayed | 43 | 20/09/2022 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 282.52 | 282.52
376 | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13876) | SM/13876 | 850.59 | 1623 | AUGMENTATION | 50 | Delayed | 24 | 25/11/2022 | 31/03/2025 | 04/06/2025 | 06/09/2022 | 207.54 | 207.17
377 | AUGMENTATION OF SONAKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS (SM/16005) | SM/16005 | 550.27 | 903 | AUGMENTATION | 50 | Delayed | 40 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 26/10/2021 | 221.99 | 221.99
378 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI (SM/15957) | SM/15957 | 922.56 | 1464 | AUGMENTATION | 50 | Delayed | 46 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 13/04/2023 | 423.41 | 423.41
379 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one (SM/08631) | SM/08631 | 116.34 | 1624 | RETROFITTING | 50 | Delayed | 12 | 31/05/2021 | 30/04/2025 | 04/06/2025 | 09/11/2021 | 14.11 | 14.11
380 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year (SM/09509) | SM/09509 | 261.42 | 4876 | RETROFITTING | 50 | Delayed | 26 | 19/11/2021 | 31/12/2025 | 04/06/2025 | 12/06/2019 | 68.04 | 68.04
381 | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/13797) | SM/13797 | 536.65 | 1566 | NEW | 50 | Delayed | 46 | 22/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 248.15 | 248.15
382 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/18379) | SM/18379 | 1121.79 | 1453 | AUGMENTATION | 50 | Delayed | 28 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 01/11/2023 | 315.85 | 315.85
383 | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS (SM/18675) | SM/18675 | 1014.14 | 1981 | AUGMENTATION | 50 | Delayed | 15 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 07/08/2023 | 153.03 | 153.03
384 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/18550) | SM/18550 | 1014.94 | 6682 | AUGMENTATION | 50 | Delayed | 5 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 14/08/2023 | 46.53 | 46.53
385 | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories (SM/06621) | SM/06621 | 52.91 | 0 | SUPPORT-WQMSP | 50 |  | 0 | 05/02/2020 | 30/06/2021 | 31/05/2021 | 02/03/2020 | 0 | 0
386 | Chemical, Glassware & Instruments requirement and allied Civil, Electro Mechanical works for NABL Accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Amtala Sub Division under South 24 Parganas W/S Division-I. (SM/10196) | SM/10196 | 61.7 | 0 | SUPPORT-WQMSP | 50 | Delayed | 0 | 14/01/2022 | 31/03/2024 | 27/03/2024 | 24/11/2021 | 0 | 0
387 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOPALNAGAR UTTAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 (SM/13870) | SM/13870 | 635.06 | 1601 | NEW | 51 | Delayed | 54 | 25/11/2022 | 31/08/2025 | 04/06/2025 | 19/08/2022 | 343.77 | 343.77
388 | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas (SM/18680) | SM/18680 | 1017.88 | 3023 | AUGMENTATION | 51 | Delayed | 24 | 04/08/2023 | 31/08/2025 | 04/06/2025 | 22/08/2023 | 243.45 | 243.45
389 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl (SM/07635) | SM/07635 | 124.87 | 1432 | RETROFITTING | 51 | Delayed | 50 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 23/02/2021 | 61.84 | 61.76
390 | AUGMENTATION OF GROUND WATER BASED AMTALI (ZONE-I & II), PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/14120) | SM/14120 | 1004.99 | 1997 | AUGMENTATION | 51 | Delayed | 56 | 02/01/2023 | 31/12/2025 | 04/06/2025 | 27/02/2023 | 558.9 | 558.9
391 | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o (SM/16137) | SM/16137 | 474.65 | 853 | AUGMENTATION | 51 | Delayed | 27 | 22/02/2023 | 31/03/2025 | 04/06/2025 | 06/03/2023 | 126.77 | 126.77
392 | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist (SM/11299) | SM/11299 | 214.92 | 910 | NEW | 51 | Delayed | 49 | 28/06/2022 | 31/05/2025 | 04/06/2025 | 07/09/2022 | 105.66 | 105.66
393 | Ground water based KURULI piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11500) | SM/11500 | 741.27 | 1516 | NEW | 51 | Delayed | 52 | 19/07/2022 | 31/12/2025 | 04/06/2025 | 25/04/2022 | 382.44 | 382.44
394 | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11501) | SM/11501 | 768.07 | 1419 | NEW | 51 | Delayed | 17 | 19/07/2022 | 30/07/2026 | 04/06/2025 | 25/04/2022 | 128.69 | 127.81
395 | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11781) | SM/11781 | 466.89 | 868 | AUGMENTATION | 51 | Delayed | 40 | 02/08/2022 | 30/06/2025 | 04/06/2025 | 01/11/2022 | 187.48 | 186.66
396 | Proposed Ground water based PURANDARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/16129) | SM/16129 | 489.69 | 934 | AUGMENTATION | 51 | Delayed | 25 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 06/03/2023 | 124.07 | 124.07
397 | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/15834) | SM/15834 | 876.71 | 2905 | AUGMENTATION | 51 | Delayed | 37 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 03/02/2023 | 327.7 | 327.7
398 | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15196) | SM/15196 | 480.91 | 1500 | AUGMENTATION | 51 | Delayed | 53 | 06/02/2023 | 31/12/2025 | 04/06/2025 | 15/02/2023 | 252.89 | 252.89
399 | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba (SM/15561) | SM/15561 | 587.95 | 1032 | AUGMENTATION | 51 | Delayed | 42 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 14/03/2023 | 248.95 | 248.95
400 | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/13443) | SM/13443 | 619.79 | 1970 | AUGMENTATION | 52 | Delayed | 47 | 02/11/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 288.88 | 288.88
401 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 07 seven nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including (SM/08632) | SM/08632 | 157.27 | 1352 | RETROFITTING | 52 | Delayed | 50 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 03/10/2023 | 79.35 | 79.35
402 | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS (SM/17200) | SM/17200 | 831.19 | 1474 | AUGMENTATION | 52 | Delayed | 46 | 15/03/2023 | 31/12/2025 | 04/06/2025 | 10/06/2022 | 384.9 | 384.9
403 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includin (SM/07758) | SM/07758 | 100.03 | 1224 | RETROFITTING | 52 | Delayed | 100 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 12/10/2020 | 100.03 | 100.03
404 | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS (SM/13840) | SM/13840 | 592.21 | 1300 | NEW | 52 | Delayed | 31 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 16/02/2023 | 184.82 | 184.82
405 | AUGMENTATION OF KUMIRMARI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/18285) | SM/18285 | 1284.98 | 2963 | AUGMENTATION | 52 | Delayed | 18 | 23/06/2023 | 31/12/2025 | 04/06/2025 | 12/07/2023 | 232.71 | 232.71
406 | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] (SM/10783) | SM/10783 | 1056.66 | 2233 | AUGMENTATION | 52 | Delayed | 72 | 25/05/2022 | 31/12/2025 | 04/06/2025 | 07/07/2022 | 765.14 | 765.14
407 | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15974) | SM/15974 | 638.17 | 1382 | AUGMENTATION | 52 | Delayed | 45 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 22/02/2023 | 284.71 | 284.71
408 | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/16125) | SM/16125 | 710.57 | 1025 | AUGMENTATION | 52 | Delayed | 17 | 22/02/2023 | 31/05/2025 | 04/06/2025 | 17/03/2023 | 119.96 | 107.65
409 | DEARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18329) | SM/18329 | 1172.73 | 2233 | AUGMENTATION | 52 | Delayed | 30 | 27/06/2023 | 31/07/2025 | 04/06/2025 | 18/07/2023 | 353.01 | 353.01
410 | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. (SM/13757) | SM/13757 | 999.02 | 3872 | AUGMENTATION | 52 | Delayed | 21 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 03/02/2023 | 211.37 | 211.37
411 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11250) | SM/11250 | 794.81 | 9404 | AUGMENTATION | 52 | Delayed | 68 | 22/06/2022 | 31/03/2025 | 04/06/2025 | 11/03/2022 | 543.82 | 543.82
412 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including (SM/08628) | SM/08628 | 204.05 | 1993 | RETROFITTING | 52 | Delayed | 77 | 31/05/2021 | 31/12/2025 | 04/06/2025 | 17/08/2021 | 156.84 | 156.42
413 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR (SM/18399) | SM/18399 | 2073.34 | 6323 | AUGMENTATION | 52 | Delayed | 29 | 12/07/2023 | 30/09/2025 | 04/06/2025 | 26/07/2023 | 608.84 | 608.84
414 | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS (SM/18718) | SM/18718 | 1280.39 | 2575 | NEW | 52 | Delayed | 42 | 10/08/2023 | 31/03/2025 | 04/06/2025 | 11/08/2023 | 534.87 | 534.87
415 | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district (SM/11783) | SM/11783 | 548.13 | 910 | AUGMENTATION | 53 | Delayed | 30 | 02/08/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 164.79 | 147.84
416 | Proposed Ground water based DEHIMEDAN MALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec (SM/14856) | SM/14856 | 780.38 | 2670 | AUGMENTATION | 53 | Delayed | 19 | 03/02/2023 | 30/08/2026 | 04/06/2025 | 01/03/2023 | 148.33 | 137.78
417 | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/16008) | SM/16008 | 584.4 | 921 | AUGMENTATION | 53 | Delayed | 42 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2023 | 248.17 | 248.17
418 | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS (SM/18673) | SM/18673 | 1192.64 | 2300 | NEW | 53 | Delayed | 24 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 286.59 | 286.59
419 | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri (SM/15180) | SM/15180 | 261.09 | 841 | AUGMENTATION | 53 | Delayed | 20 | 07/02/2023 | 31/03/2025 | 04/06/2025 | 04/04/2023 | 51.22 | 51.22
420 | Proposed Ground water based CHAKAR BAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/15784) | SM/15784 | 439.92 | 737 | AUGMENTATION | 53 | Delayed | 10 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 06/03/2023 | 45.53 | 45.53
421 | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/16133) | SM/16133 | 522.52 | 1004 | AUGMENTATION | 53 | Delayed | 30 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 06/03/2023 | 155.37 | 155.37
422 | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS (SM/13842) | SM/13842 | 428.95 | 1092 | NEW | 54 | Delayed | 31 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 131.35 | 131.35
423 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on (SM/07403) | SM/07403 | 75.56 | 1536 | RETROFITTING | 55 | Delayed | 54 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 15/10/2020 | 40.63 | 40.63
424 | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district (SM/14858) | SM/14858 | 903 | 2949 | AUGMENTATION | 55 | Delayed | 34 | 03/02/2023 | 31/08/2025 | 04/06/2025 | 04/04/2023 | 310.51 | 310.51
425 | TARDAHA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/14488) | SM/14488 | 1353.88 | 2297 | AUGMENTATION | 55 | Delayed | 36 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 27/01/2023 | 490.98 | 490.98
426 | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18501) | SM/18501 | 1828.53 | 3298 | AUGMENTATION | 55 | Delayed | 44 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 03/08/2023 | 797.55 | 797.55
427 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT JALABERIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11251) | SM/11251 | 794.73 | 9403 | AUGMENTATION | 55 | Delayed | 20 | 22/06/2022 | 31/03/2025 | 04/06/2025 | 20/10/2022 | 157.46 | 157.46
428 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/B at KALOKAPOTA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- (SM/14728) | SM/14728 | 1501.8 | 0 | AUGMENTATION | 55 | Delayed | 36 | 31/01/2023 | 30/11/2025 | 04/06/2025 | 15/03/2022 | 546.2 | 546.2
429 | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S (SM/12771) | SM/12771 | 724.78 | 1585 | AUGMENTATION | 55 | Delayed | 31 | 21/09/2022 | 30/06/2025 | 04/06/2025 | 20/05/2022 | 222.28 | 222.28
430 | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/15783) | SM/15783 | 559.05 | 990 | AUGMENTATION | 55 | Delayed | 38 | 20/02/2023 | 30/11/2025 | 04/06/2025 | 17/03/2023 | 212.92 | 212.92
431 | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18391) | SM/18391 | 1135.95 | 3576 | AUGMENTATION | 55 | Delayed | 46 | 11/07/2023 | 31/12/2025 | 04/06/2025 | 09/08/2023 | 520.58 | 520.58
432 | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13771) | SM/13771 | 844.34 | 1724 | AUGMENTATION | 55 | Delayed | 22 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 09/12/2022 | 182.87 | 182.87
433 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S (SM/07411) | SM/07411 | 92.29 | 2943 | RETROFITTING | 55 | Delayed | 86 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 79.54 | 79.54
434 | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar (SM/14875) | SM/14875 | 983.49 | 3180 | AUGMENTATION | 55 | Delayed | 26 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 260.29 | 260.29
435 | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. (SM/18684) | SM/18684 | 1300.88 | 3019 | NEW | 55 | Delayed | 57 | 04/08/2023 | 30/09/2025 | 04/06/2025 | 14/08/2023 | 738.88 | 738.88
436 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS (SM/15531) | SM/15531 | 3281.96 | 8312 | AUGMENTATION | 55 | Delayed | 36 | 16/02/2023 | 31/12/2025 | 04/06/2025 | 17/02/2022 | 1196.14 | 1196.14
437 | AUGMENTATION OF GROUND WATER BASED DHASPARA (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/15221) | SM/15221 | 1223.98 | 2075 | AUGMENTATION | 55 | Delayed | 39 | 06/02/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 478.17 | 475.71
438 | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS (SM/15566) | SM/15566 | 497.11 | 933 | AUGMENTATION | 55 | Delayed | 43 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 18/04/2023 | 213.87 | 213.87
439 | PROPOSED GROUND WATER BASED DAKSHIN KALYANPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BARUIPUR BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT AUGMENTATION OF SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTE (SM/15779) | SM/15779 | 489.75 | 968 | AUGMENTATION | 55 | Delayed | 28 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 03/03/2023 | 137.49 | 137.49
440 | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District (SM/13309) | SM/13309 | 790.68 | 1773 | AUGMENTATION | 56 | Delayed | 41 | 17/10/2022 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 325.63 | 325.63
441 | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district (SM/14862) | SM/14862 | 924.59 | 2688 | AUGMENTATION | 56 | Delayed | 45 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 30/03/2023 | 419.61 | 419.61
442 | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09931) | SM/09931 | 867.99 | 4871 | AUGMENTATION | 56 | Delayed | 48 | 10/12/2021 | 31/12/2025 | 04/06/2025 | 22/03/2022 | 412.91 | 412.91
443 | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/13011) | SM/13011 | 941.69 | 1531 | NEW | 56 | Delayed | 22 | 29/09/2022 | 31/03/2025 | 04/06/2025 | 17/10/2022 | 211.15 | 211.15
444 | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric (SM/15337) | SM/15337 | 918.99 | 2971 | AUGMENTATION | 56 | Delayed | 40 | 07/02/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 369.97 | 369.97
445 | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/18267) | SM/18267 | 1104.75 | 1598 | AUGMENTATION | 56 | Delayed | 30 | 21/06/2023 | 31/12/2025 | 04/06/2025 | 17/07/2023 | 334.6 | 334.6
446 | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08804) | SM/08804 | 76.86 | 2030 | RETROFITTING | 57 | Delayed | 96 | 13/09/2021 | 31/07/2025 | 04/06/2025 | 01/09/2021 | 74.02 | 74.02
447 | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13798) | SM/13798 | 925.05 | 1882 | NEW | 57 | Delayed | 63 | 22/11/2022 | 30/09/2025 | 04/06/2025 | 01/08/2022 | 580.15 | 580.15
448 | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/14872) | SM/14872 | 926.21 | 2904 | AUGMENTATION | 57 | Delayed | 35 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 325.15 | 325.15
449 | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15472) | SM/15472 | 491.27 | 2500 | AUGMENTATION | 57 | Delayed | 57 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 18/02/2023 | 279.03 | 279.03
450 | Augmentation & Retrofitting of Purba Radhanagar (Zone- I) PWSS for Providing (FHTC) , Block - Gosaba (SM/15966) | SM/15966 | 514.06 | 1415 | AUGMENTATION | 57 | Delayed | 49 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 22/02/2023 | 253.62 | 232.9
451 | AUGMENTATION OF GROUND WATER BASED NEBUTALA, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11750) | SM/11750 | 521.71 | 743 | AUGMENTATION | 57 | Delayed | 26 | 03/08/2022 | 31/08/2025 | 04/06/2025 | 08/08/2022 | 135.81 | 135.81
452 | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/18677) | SM/18677 | 1238.15 | 4292 | AUGMENTATION | 57 | On track | 35 | 04/08/2023 | 31/03/2026 | 04/06/2025 | 11/08/2023 | 437.57 | 437.57
453 | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12231) | SM/12231 | 679.33 | 1761 | AUGMENTATION | 58 | Delayed | 35 | 06/09/2022 | 31/03/2025 | 04/06/2025 | 27/01/2022 | 235.41 | 235.41
454 | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT KATAMARI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. (SM/11257) | SM/11257 | 856.61 | 11590 | AUGMENTATION | 58 | Delayed | 87 | 22/06/2022 | 31/12/2025 | 04/06/2025 | 02/06/2023 | 743.92 | 743.92
455 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/16002) | SM/16002 | 616.86 | 1893 | AUGMENTATION | 58 | Delayed | 67 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2023 | 411.42 | 411.42
456 | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. (SM/13837) | SM/13837 | 739.08 | 1615 | NEW | 58 | Delayed | 34 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 248.83 | 244.76
457 | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of (SM/18869) | SM/18869 | 698.19 | 1763 | AUGMENTATION | 58 | On track | 12 | 05/10/2023 | 30/06/2026 | 04/06/2025 | 20/10/2023 | 83.31 | 83.31
458 | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13117) | SM/13117 | 1606.67 | 2806 | AUGMENTATION | 59 | Delayed | 66 | 10/10/2022 | 31/12/2025 | 04/06/2025 | 06/09/2022 | 1060.08 | 1058.29
459 | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/18984) | SM/18984 | 2134.57 | 7887 | AUGMENTATION | 59 | Delayed | 22 | 12/10/2023 | 30/04/2025 | 04/06/2025 | 31/10/2023 | 463.39 | 463.39
460 | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11787) | SM/11787 | 864.45 | 1857 | AUGMENTATION | 59 | Delayed | 77 | 02/08/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 667.92 | 667.92
461 | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS (SM/14985) | SM/14985 | 455.02 | 741 | AUGMENTATION | 59 | Delayed | 44 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 15/02/2023 | 198.98 | 194.69
462 | RANIGACHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15863) | SM/15863 | 748.34 | 1320 | AUGMENTATION | 60 | Delayed | 12 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 10/03/2023 | 92.05 | 92.05
463 | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o (SM/16132) | SM/16132 | 540.74 | 998 | AUGMENTATION | 60 | On track | 25 | 22/02/2023 | 30/10/2026 | 04/06/2025 | 03/03/2023 | 133.39 | 131.47
464 | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09935) | SM/09935 | 875.73 | 6898 | AUGMENTATION | 60 | Delayed | 33 | 13/12/2021 | 31/05/2025 | 04/06/2025 | 06/04/2022 | 288.32 | 288.32
465 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-III OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 2 (SM/15529) | SM/15529 | 1593.85 | 4948 | AUGMENTATION | 60 | Delayed | 45 | 16/02/2023 | 31/12/2025 | 04/06/2025 | 15/09/2022 | 724.29 | 724.29
466 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI (SM/15976) | SM/15976 | 723.29 | 1142 | AUGMENTATION | 60 | Delayed | 41 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 22/02/2023 | 300.16 | 294.29
467 | Providing Functional Household Tap Connection (FHTC) in Zone-IV at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11242) | SM/11242 | 186.05 | 2270 | NEW | 60 | Delayed | 40 | 22/06/2022 | 31/08/2025 | 04/06/2025 | 17/03/2023 | 73.98 | 73.98
468 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUMARPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/11746) | SM/11746 | 822.67 | 1473 | NEW | 60 | Delayed | 37 | 03/08/2022 | 31/12/2025 | 04/06/2025 | 23/11/2021 | 304.54 | 304.54
469 | GROUND WATER BASED WATER SUPPLY SCHEME FOR DAKSHIN MADHUSUDANPUR UNDER ALIPORE DIVISION, BLOCK-PATAHRPRATIMA,DISTRICT - SOUTH 24 PARGANAS (SM/13977) | SM/13977 | 563.02 | 1664 | NEW | 60 | Delayed | 35 | 01/12/2022 | 30/04/2025 | 04/06/2025 | 20/07/2022 | 195.16 | 195.16
470 | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar (SM/16134) | SM/16134 | 262.46 | 556 | AUGMENTATION | 60 | Delayed | 51 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 09/03/2023 | 134.1 | 133.9
471 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) (SM/18872) | SM/18872 | 312.1 | 339 | AUGMENTATION | 60 | Delayed | 0 | 05/10/2023 | 31/12/2025 | 04/06/2025 | 07/08/2024 | 0 | 0
472 | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS (SM/13846) | SM/13846 | 707.91 | 1632 | NEW | 60 | Delayed | 42 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 295.76 | 295.76
473 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Makhaltala Water Supply (SM/07638) | SM/07638 | 129.74 | 2447 | RETROFITTING | 60 | Delayed | 93 | 07/01/2021 | 31/12/2025 | 04/06/2025 | 18/02/2021 | 121.22 | 121.22
474 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (one) no. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gangacheri Water Supply Scheme including one yea (SM/08634) | SM/08634 | 38.38 | 673 | RETROFITTING | 60 | Delayed | 92 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 19/07/2021 | 35.15 | 35.15
475 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/15530) | SM/15530 | 1376.48 | 5302 | AUGMENTATION | 60 | Delayed | 22 | 16/02/2023 | 31/03/2025 | 04/06/2025 | 23/09/2022 | 304.38 | 304.38
476 | Dakshin Durgapur Piped Water Supply Scheme. (SM/16758) | SM/16758 | 800.27 | 1359 | NEW | 60 | Delayed | 54 | 13/03/2023 | 31/10/2025 | 04/06/2025 | 24/03/2023 | 431.9 | 431.9
477 | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15773) | SM/15773 | 988.51 | 1683 | AUGMENTATION | 60 | Delayed | 45 | 20/02/2023 | 31/07/2025 | 04/06/2025 | 10/03/2023 | 444.86 | 444.86
478 | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI (SM/18279) | SM/18279 | 1134.85 | 2343 | AUGMENTATION | 60 | Delayed | 20 | 23/06/2023 | 31/12/2025 | 04/06/2025 | 12/07/2023 | 224.33 | 224.33
479 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/18554) | SM/18554 | 2100.55 | 7276 | AUGMENTATION | 60 | Delayed | 25 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 26/07/2023 | 525.45 | 525.45
480 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc (SM/07409) | SM/07409 | 75.22 | 927 | RETROFITTING | 60 | Delayed | 62 | 29/12/2020 | 30/09/2025 | 04/06/2025 | 15/10/2020 | 46.69 | 39.61
481 | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11805) | SM/11805 | 947.14 | 1303 | AUGMENTATION | 60 | Delayed | 39 | 05/08/2022 | 31/03/2025 | 04/06/2025 | 08/08/2022 | 367.54 | 367.54
482 | GROUND WATER BASED RAMGOPALPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS (SM/13976) | SM/13976 | 632.65 | 1735 | NEW | 60 | Delayed | 41 | 01/12/2022 | 31/12/2025 | 04/06/2025 | 05/08/2022 | 260.8 | 260.8
483 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR (SM/14892) | SM/14892 | 544.13 | 3250 | AUGMENTATION | 60 | Delayed | 29 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 17/07/2023 | 159.35 | 159.35
484 | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U (SM/18547) | SM/18547 | 1243.06 | 2308 | AUGMENTATION | 60 | Delayed | 24 | 26/07/2023 | 31/03/2026 | 04/06/2025 | 04/08/2023 | 303.15 | 303.15
485 | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT (SM/10480) | SM/10480 | 939.99 | 3633 | AUGMENTATION | 60 | Delayed | 59 | 13/04/2022 | 31/12/2025 | 04/06/2025 | 08/09/2021 | 550.18 | 550.18
486 | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15754) | SM/15754 | 991.55 | 2089 | AUGMENTATION | 60 | Delayed | 20 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 03/03/2023 | 195.72 | 195.72
487 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D (SM/18220) | SM/18220 | 2893.58 | 0 | AUGMENTATION | 60 | Delayed | 61 | 27/04/2023 | 30/11/2025 | 04/06/2025 | 10/03/2022 | 1778.79 | 1778.79
488 | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/18268) | SM/18268 | 1027.33 | 3029 | AUGMENTATION | 60 | Delayed | 27 | 21/06/2023 | 28/02/2026 | 04/06/2025 | 14/07/2023 | 280.56 | 280.56
489 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, (SM/13891) | SM/13891 | 543.76 | 11350 | AUGMENTATION | 60 | Delayed | 72 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/04/2023 | 389.16 | 389.16
490 | BHABANIPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13308) | SM/13308 | 693.14 | 1292 | AUGMENTATION | 60 | Delayed | 26 | 17/10/2022 | 31/03/2025 | 04/06/2025 | 01/12/2022 | 177.06 | 177.06
491 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI (SM/15053) | SM/15053 | 997.42 | 2624 | AUGMENTATION | 60 | Delayed | 54 | 03/02/2023 | 31/05/2025 | 04/06/2025 | 03/02/2023 | 539.68 | 539.68
492 | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. (SM/18395) | SM/18395 | 1289.96 | 3621 | NEW | 60 | Delayed | 35 | 11/07/2023 | 30/09/2025 | 04/06/2025 | 17/07/2023 | 445.36 | 445.36
493 | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U (SM/18572) | SM/18572 | 1145.1 | 2856 | AUGMENTATION | 60 | Delayed | 35 | 31/07/2023 | 02/11/2025 | 04/06/2025 | 11/08/2023 | 395.9 | 395.9
494 | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18683) | SM/18683 | 1103.18 | 2308 | NEW | 60 | Delayed | 38 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 14/08/2023 | 417.55 | 417.55
495 | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr (SM/15177) | SM/15177 | 476.26 | 1426 | AUGMENTATION | 61 | Delayed | 49 | 07/02/2023 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 235.44 | 235.44
496 | RAYPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13773) | SM/13773 | 930.04 | 1992 | AUGMENTATION | 61 | Delayed | 33 | 18/11/2022 | 31/05/2025 | 04/06/2025 | 15/12/2022 | 311.23 | 311.23
497 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including (SM/08635) | SM/08635 | 124.75 | 2332 | RETROFITTING | 61 | Delayed | 13 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 17/08/2021 | 16 | 16
498 | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/15526) | SM/15526 | 1200.11 | 2424 | AUGMENTATION | 61 | Delayed | 27 | 16/02/2023 | 31/12/2025 | 04/06/2025 | 21/02/2023 | 328.62 | 328.62
499 | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11503) | SM/11503 | 467.26 | 924 | NEW | 61 | Delayed | 41 | 19/07/2022 | 31/05/2025 | 04/06/2025 | 25/04/2022 | 189.92 | 173.37
500 | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS (SM/13843) | SM/13843 | 707.69 | 1331 | NEW | 61 | Delayed | 27 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 189.17 | 184.47
501 | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15045) | SM/15045 | 232.1 | 200 | AUGMENTATION | 61 | Delayed | 37 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 15/02/2023 | 86.24 | 80.37
502 | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11749) | SM/11749 | 735.22 | 2183 | AUGMENTATION | 62 | Delayed | 30 | 03/08/2022 | 31/08/2025 | 04/06/2025 | 08/08/2022 | 223.85 | 223.85
503 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one (SM/09007) | SM/09007 | 220.12 | 4117 | RETROFITTING | 62 | Delayed | 39 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 27/05/2022 | 86.32 | 81.86
504 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DURGA GOBINDOPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13803) | SM/13803 | 614.26 | 1526 | NEW | 62 | Delayed | 29 | 22/11/2022 | 31/03/2025 | 04/06/2025 | 01/08/2022 | 177.04 | 177.04
505 | AUGMENTATION AND RETROFITTING OF ATHARABEKI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15097) | SM/15097 | 335.72 | 1700 | AUGMENTATION | 62 | Delayed | 62 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 15/02/2023 | 208.54 | 208.54
506 | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec (SM/17299) | SM/17299 | 633.36 | 1306 | AUGMENTATION | 62 | Delayed | 40 | 15/03/2023 | 30/06/2025 | 04/06/2025 | 24/03/2023 | 255.43 | 255.43
507 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ (SM/09077) | SM/09077 | 154.41 | 1508 | RETROFITTING | 62 | Delayed | 58 | 29/10/2021 | 30/09/2025 | 04/06/2025 | 20/01/2022 | 89.29 | 89.29
508 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including (SM/07581) | SM/07581 | 77.62 | 2076 | RETROFITTING | 62 | Delayed | 60 | 31/12/2020 | 30/09/2025 | 04/06/2025 | 15/10/2020 | 46.63 | 46.63
509 | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11498) | SM/11498 | 504.82 | 822 | NEW | 62 | Delayed | 38 | 19/07/2022 | 31/03/2025 | 04/06/2025 | 19/07/2022 | 193.22 | 193.22
510 | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS (SM/13975) | SM/13975 | 786.59 | 1703 | NEW | 62 | Delayed | 55 | 01/12/2022 | 31/12/2025 | 04/06/2025 | 15/02/2023 | 428.86 | 428.86
511 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 24 (twenty four) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Chhota Molla Khali WS Sche (SM/08791) | SM/08791 | 461.43 | 7148 | RETROFITTING | 62 | Delayed | 95 | 13/09/2021 | 30/06/2026 | 04/06/2025 | 28/09/2021 | 439.8 | 439.8
512 | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS (SM/18676) | SM/18676 | 1032.99 | 3555 | AUGMENTATION | 62 | Delayed | 52 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 07/08/2023 | 541.74 | 541.74
513 | AUGMENTATION OF GROUND WATER BASED RAJNAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/13875) | SM/13875 | 519.75 | 520 | AUGMENTATION | 62 | Delayed | 29 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 01/08/2022 | 149.78 | 149.78
514 | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. (SM/18127) | SM/18127 | 217.56 | 441 | NEW | 62 | Delayed | 28 | 29/03/2023 | 31/08/2025 | 04/06/2025 | 31/03/2023 | 60.44 | 60.44
515 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 17 (seventeen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandrakhali Water Supply Scheme inclu (SM/09009) | SM/09009 | 232.94 | 4343 | RETROFITTING | 63 | Delayed | 71 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 165.86 | 165.86
516 | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/16126) | SM/16126 | 427.17 | 668 | AUGMENTATION | 63 | Delayed | 26 | 22/02/2023 | 31/05/2025 | 04/06/2025 | 03/03/2023 | 109.94 | 109.94
517 | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08792) | SM/08792 | 69 | 1830 | RETROFITTING | 63 | Delayed | 62 | 13/09/2021 | 30/09/2025 | 04/06/2025 | 15/11/2022 | 42.74 | 42.74
518 | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district (SM/15660) | SM/15660 | 2707.92 | 606 | AUGMENTATION | 63 | Delayed | 46 | 20/02/2023 | 30/06/2025 | 04/06/2025 | 24/05/2022 | 1251.42 | 1248.27
519 | Ground water based PARULDAHA (ZONE-26) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri (SM/15778) | SM/15778 | 325.99 | 729 | AUGMENTATION | 64 | Delayed | 55 | 20/02/2023 | 31/08/2025 | 04/06/2025 | 08/06/2023 | 177.83 | 177.83
520 | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12061) | SM/12061 | 664.62 | 2233 | AUGMENTATION | 64 | Delayed | 47 | 01/09/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 311.19 | 305.27
521 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' (SM/13911) | SM/13911 | 740.12 | 2644 | AUGMENTATION | 65 | Delayed | 36 | 29/11/2022 | 31/12/2025 | 04/06/2025 | 15/09/2022 | 266.08 | 266.08
522 | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14643) | SM/14643 | 984.92 | 3076 | AUGMENTATION | 65 | Delayed | 31 | 31/01/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 301.35 | 301.35
523 | MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13778) | SM/13778 | 996.17 | 1996 | AUGMENTATION | 65 | Delayed | 45 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 01/03/2023 | 449.75 | 449.75
524 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR UNDER ZONE-III, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAP (SM/15469) | SM/15469 | 734.1 | 1274 | AUGMENTATION | 65 | On track | 29 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 10/05/2023 | 210.82 | 210.82
525 | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14870) | SM/14870 | 844.2 | 2171 | AUGMENTATION | 65 | Delayed | 11 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 93.55 | 82.43
526 | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/11875) | SM/11875 | 643.29 | 549 | AUGMENTATION | 65 | Delayed | 11 | 17/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 67.92 | 67.92
527 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU (SM/18552) | SM/18552 | 2895.68 | 8848 | AUGMENTATION | 65 | Delayed | 53 | 26/07/2023 | 31/12/2025 | 04/06/2025 | 04/08/2023 | 1530.42 | 1530.42
528 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15959) | SM/15959 | 715.27 | 1522 | AUGMENTATION | 65 | Delayed | 50 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 03/02/2023 | 356.14 | 356.14
529 | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di (SM/15756) | SM/15756 | 460.15 | 943 | AUGMENTATION | 65 | Delayed | 54 | 20/02/2023 | 30/09/2025 | 04/06/2025 | 02/03/2023 | 247.25 | 247.25
530 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B (SM/13914) | SM/13914 | 152.41 | 0 | AUGMENTATION | 65 | Delayed | 64 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 17/11/2017 | 97.75 | 97.75
531 | AUGMENTATION IN DISTRIBUTION SYSTEM INCLUDING OHR WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALT (SM/14901) | SM/14901 | 407.52 | 0 | AUGMENTATION | 65 | On track | 42 | 04/02/2023 | 30/04/2026 | 04/06/2025 | 06/06/2023 | 172.54 | 172.54
532 | AUGMENTATION OF GROUND WATER BASED NAGANDRAGANJ (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/12626) | SM/12626 | 1284.74 | 1940 | AUGMENTATION | 65 | Delayed | 39 | 19/09/2022 | 31/03/2025 | 04/06/2025 | 22/08/2022 | 501.95 | 501.95
533 | PROVIDING 100% FHTC IN ZONE- VI AT RADHA BALLAVPUR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11248) | SM/11248 | 494.23 | 5849 | AUGMENTATION | 65 | Delayed | 50 | 22/06/2022 | 07/11/2025 | 04/06/2025 | 02/03/2023 | 247.52 | 247.52
534 | NATAGACHHI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13499) | SM/13499 | 744.8 | 1022 | AUGMENTATION | 65 | Delayed | 32 | 02/11/2022 | 31/05/2025 | 04/06/2025 | 01/12/2022 | 238.75 | 235.53
535 | KHODAHATI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13772) | SM/13772 | 916.1 | 1720 | AUGMENTATION | 65 | Delayed | 34 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 15/12/2022 | 308.38 | 308.38
536 | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/13812) | SM/13812 | 631.67 | 1761 | AUGMENTATION | 65 | Delayed | 20 | 22/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 123.68 | 123.68
537 | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/14662) | SM/14662 | 1038.47 | 2475 | AUGMENTATION | 65 | Delayed | 30 | 31/01/2023 | 30/06/2025 | 04/06/2025 | 29/12/2022 | 315.2 | 305.89
538 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS (SM/14681) | SM/14681 | 1020.93 | 2939 | AUGMENTATION | 65 | Delayed | 43 | 14/06/2023 | 31/07/2025 | 04/06/2025 | 27/07/2022 | 441.42 | 441.42
539 | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/14859) | SM/14859 | 903.02 | 2089 | AUGMENTATION | 65 | Delayed | 48 | 03/02/2023 | 31/08/2025 | 04/06/2025 | 10/04/2023 | 435.69 | 435.69
540 | Ground water based JAGADISHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/13075) | SM/13075 | 253.5 | 859 | AUGMENTATION | 65 | Delayed | 74 | 29/09/2022 | 31/03/2025 | 04/06/2025 | 12/10/2022 | 186.71 | 186.71
541 | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15464) | SM/15464 | 405.86 | 700 | AUGMENTATION | 65 | Delayed | 59 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 04/04/2023 | 239.63 | 239.63
542 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IX OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SU (SM/14469) | SM/14469 | 120.72 | 0 | AUGMENTATION | 65 | Delayed | 65 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 26/11/2020 | 78.09 | 78.09
543 | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba (SM/15968) | SM/15968 | 786.86 | 1153 | AUGMENTATION | 65 | Delayed | 41 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 29/03/2022 | 323.78 | 323.78
544 | PROVIDING 100% FHTC IN ZONE- IV AT DASKHIN GARANKATHI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11252) | SM/11252 | 468.16 | 5540 | AUGMENTATION | 65 | Delayed | 74 | 22/06/2022 | 30/12/2025 | 04/06/2025 | 28/08/2023 | 346.95 | 346.95
545 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - (SM/15322) | SM/15322 | 1390 | 4980 | AUGMENTATION | 65 | Delayed | 38 | 09/02/2023 | 31/12/2025 | 04/06/2025 | 23/09/2022 | 533.68 | 533.68
546 | Proposed Ground water based CHANDANPUKUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/15785) | SM/15785 | 498.45 | 949 | AUGMENTATION | 65 | Delayed | 31 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 02/05/2023 | 152.76 | 152.76
547 | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13786) | SM/13786 | 999.23 | 2871 | AUGMENTATION | 65 | Delayed | 26 | 18/11/2022 | 31/03/2025 | 04/06/2025 | 15/12/2022 | 257.04 | 257.04
548 | GROUND WATER BASED WATER SUPPLY SCHEME FOR PURBA DWAROKAPUR UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA,DISTRICT-SOUTH 24 PARGANAS (SM/13867) | SM/13867 | 587.37 | 1220 | NEW | 66 | Delayed | 39 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 226.72 | 226.72
549 | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11502) | SM/11502 | 450.06 | 932 | NEW | 66 | Delayed | 40 | 19/07/2022 | 30/06/2025 | 04/06/2025 | 25/04/2022 | 178.93 | 178.93
550 | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/15969) | SM/15969 | 607.14 | 1296 | AUGMENTATION | 66 | Delayed | 37 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 13/04/2023 | 222.64 | 222.64
551 | Proposed Ground water based DUDHNAI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/16118) | SM/16118 | 474.36 | 661 | AUGMENTATION | 66 | On track | 49 | 22/02/2023 | 30/07/2026 | 04/06/2025 | 06/03/2023 | 234.06 | 231.31
552 | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis (SM/11782) | SM/11782 | 510.08 | 865 | AUGMENTATION | 66 | Delayed | 36 | 02/08/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 184.48 | 184.48
553 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - III OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA (SM/14823) | SM/14823 | 751.73 | 6507 | AUGMENTATION | 66 | Delayed | 43 | 04/02/2023 | 30/06/2025 | 04/06/2025 | 21/02/2023 | 326.15 | 326.15
554 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13869) | SM/13869 | 611.8 | 1545 | NEW | 66 | Delayed | 34 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 205.93 | 205.93
555 | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan (SM/12240) | SM/12240 | 389.9 | 1143 | AUGMENTATION | 66 | Delayed | 30 | 08/09/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 116.65 | 116.65
556 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including (SM/09360) | SM/09360 | 123.14 | 1232 | RETROFITTING | 66 | Delayed | 71 | 12/11/2021 | 31/08/2025 | 04/06/2025 | 20/01/2022 | 87.27 | 57.94
557 | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. (SM/18682) | SM/18682 | 1677.13 | 5082 | NEW | 66 | Delayed | 13 | 04/08/2023 | 31/08/2025 | 04/06/2025 | 08/08/2023 | 211.28 | 211.28
558 | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11496) | SM/11496 | 479.9 | 821 | NEW | 66 | Delayed | 36 | 19/07/2022 | 30/06/2025 | 04/06/2025 | 25/04/2022 | 173.02 | 173.02
559 | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15500) | SM/15500 | 273.3 | 755 | AUGMENTATION | 66 | Delayed | 65 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 04/01/2022 | 177.91 | 177.91
560 | Ground water based BARUIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12261) | SM/12261 | 715.99 | 1018 | AUGMENTATION | 67 | Delayed | 28 | 07/09/2022 | 30/09/2025 | 04/06/2025 | 27/09/2022 | 201.44 | 201.44
561 | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11732) | SM/11732 | 483.4 | 882 | AUGMENTATION | 67 | Delayed | 37 | 03/08/2022 | 30/11/2025 | 04/06/2025 | 01/11/2022 | 179.57 | 179.57
562 | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11493) | SM/11493 | 480.88 | 1038 | NEW | 67 | Delayed | 36 | 19/07/2022 | 31/03/2025 | 04/06/2025 | 25/04/2022 | 175.13 | 175.13
563 | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11646) | SM/11646 | 603.94 | 1753 | AUGMENTATION | 67 | Delayed | 37 | 27/07/2022 | 30/11/2025 | 04/06/2025 | 02/09/2022 | 226 | 225.18
564 | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) (SM/09997) | SM/09997 | 1249.92 | 2627 | AUGMENTATION | 67 | Delayed | 68 | 22/12/2021 | 31/03/2025 | 04/06/2025 | 21/06/2022 | 851.87 | 851.87
565 | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15477) | SM/15477 | 245.88 | 420 | AUGMENTATION | 67 | Delayed | 29 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 27/11/2020 | 72.25 | 72.25
566 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including (SM/09076) | SM/09076 | 120.65 | 1169 | RETROFITTING | 67 | Delayed | 65 | 29/10/2021 | 30/09/2025 | 04/06/2025 | 23/03/2022 | 78.75 | 78.75
567 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBNAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13844) | SM/13844 | 1030.27 | 1999 | NEW | 68 | Delayed | 15 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 149.46 | 149.46
568 | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/13845) | SM/13845 | 518.82 | 972 | NEW | 68 | Delayed | 36 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 189.1 | 189.1
569 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/15992) | SM/15992 | 666.01 | 1271 | AUGMENTATION | 68 | Delayed | 47 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2023 | 312.87 | 312.87
570 | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11495) | SM/11495 | 740.19 | 1527 | NEW | 68 | Delayed | 61 | 19/07/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 450.43 | 450.43
571 | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric (SM/11733) | SM/11733 | 494.04 | 985 | AUGMENTATION | 68 | Delayed | 33 | 02/08/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 161.91 | 161.91
572 | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af (SM/13922) | SM/13922 | 295.01 | 738 | AUGMENTATION | 68 | Delayed | 44 | 29/11/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 129.04 | 121.24
573 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. (SM/15056) | SM/15056 | 951.43 | 2519 | AUGMENTATION | 68 | Delayed | 58 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 06/02/2023 | 549.1 | 549.1
574 | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. (SM/11988) | SM/11988 | 351.79 | 543 | NEW | 68 | Delayed | 59 | 01/09/2022 | 31/07/2025 | 04/06/2025 | 25/04/2022 | 205.82 | 205.82
575 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year (SM/09359) | SM/09359 | 87.59 | 488 | RETROFITTING | 69 | Delayed | 72 | 12/11/2021 | 31/08/2025 | 04/06/2025 | 22/11/2021 | 62.78 | 62.78
576 | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. (SM/13442) | SM/13442 | 536.43 | 1430 | AUGMENTATION | 69 | Delayed | 36 | 02/11/2022 | 31/05/2025 | 04/06/2025 | 29/11/2022 | 195.07 | 195.07
577 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including (SM/07398) | SM/07398 | 59.32 | 869 | RETROFITTING | 69 | Delayed | 68 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 02/03/2022 | 40.08 | 40.08
578 | AUGMENTATION FOR FOR GROUND WATER BASED MAHISMARI(ZONE- I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13872) | SM/13872 | 944.38 | 1033 | AUGMENTATION | 69 | Delayed | 32 | 25/11/2022 | 31/08/2025 | 04/06/2025 | 06/09/2022 | 302.56 | 302.56
579 | Ground water based BARULI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12212) | SM/12212 | 875.83 | 1435 | AUGMENTATION | 70 | Delayed | 32 | 07/09/2022 | 30/06/2025 | 04/06/2025 | 09/02/2023 | 280.89 | 280.89
580 | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A (SM/14659) | SM/14659 | 995.53 | 2595 | AUGMENTATION | 70 | On track | 35 | 31/01/2023 | 30/11/2025 | 04/06/2025 | 29/12/2022 | 347.82 | 341.65
581 | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM (SM/13341) | SM/13341 | 998.34 | 1942 | AUGMENTATION | 70 | Delayed | 66 | 17/10/2022 | 31/07/2025 | 04/06/2025 | 01/03/2023 | 657.56 | 657.56
582 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-IX at GHOLA NOAPARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. (SM/14725) | SM/14725 | 1046.17 | 0 | AUGMENTATION | 70 | Delayed | 43 | 31/01/2023 | 31/05/2025 | 04/06/2025 | 08/02/2023 | 444.86 | 444.86
583 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D (SM/18224) | SM/18224 | 2657.13 | 0 | AUGMENTATION | 70 | Delayed | 24 | 27/04/2023 | 30/11/2025 | 04/06/2025 | 06/04/2022 | 631.87 | 631.87
584 | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09932) | SM/09932 | 293.91 | 1687 | AUGMENTATION | 70 | Delayed | 68 | 10/12/2021 | 30/06/2025 | 04/06/2025 | 17/02/2022 | 200.2 | 200.2
585 | AUGMENTATION OF GROUND WATER BASED KUSUMTALA, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/12731) | SM/12731 | 738.38 | 472 | AUGMENTATION | 70 | Delayed | 35 | 20/09/2022 | 31/08/2025 | 04/06/2025 | 19/10/2022 | 261.9 | 261.9
586 | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. (SM/12206) | SM/12206 | 811.97 | 1220 | AUGMENTATION | 70 | Delayed | 36 | 06/09/2022 | 31/03/2025 | 04/06/2025 | 07/11/2022 | 291.05 | 291.05
587 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15467) | SM/15467 | 566.92 | 938 | AUGMENTATION | 70 | Delayed | 53 | 04/02/2023 | 31/05/2025 | 04/06/2025 | 17/05/2023 | 301.58 | 301.58
588 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-V at BARIJPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- Sout (SM/14727) | SM/14727 | 1363.72 | 0 | AUGMENTATION | 70 | Delayed | 22 | 31/01/2023 | 31/08/2025 | 04/06/2025 | 19/09/2022 | 295.97 | 295.97
589 | Ramnagar Abad Piped Water Supply Scheme. (SM/16759) | SM/16759 | 948.46 | 1847 | NEW | 70 | Delayed | 36 | 13/03/2023 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 346.15 | 346.15
590 | BENIABOW piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13774) | SM/13774 | 628.73 | 1079 | AUGMENTATION | 70 | Delayed | 31 | 18/11/2022 | 31/12/2025 | 04/06/2025 | 27/12/2022 | 193.54 | 193.54
591 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15564) | SM/15564 | 412.18 | 816 | AUGMENTATION | 70 | Delayed | 68 | 15/02/2023 | 30/12/2025 | 04/06/2025 | 11/05/2023 | 281.19 | 265.73
592 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, (SM/16183) | SM/16183 | 1817.52 | 0 | AUGMENTATION | 70 | Delayed | 39 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 21/07/2023 | 710.44 | 710.44
593 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 (SM/16190) | SM/16190 | 1547.3 | 0 | AUGMENTATION | 70 | Delayed | 44 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 13/04/2022 | 682.48 | 682.48
594 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one y (SM/09097) | SM/09097 | 119.6 | 1999 | RETROFITTING | 70 | Delayed | 88 | 29/10/2021 | 31/12/2025 | 04/06/2025 | 24/02/2022 | 104.98 | 104.98
595 | AUGMENTATION OF GROUND WATER BASED DWARIKNAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS. (SM/11847) | SM/11847 | 654.57 | 644 | AUGMENTATION | 70 | Delayed | 30 | 16/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 194.56 | 191.45
596 | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. (SM/13674) | SM/13674 | 990.8 | 2135 | AUGMENTATION | 70 | Delayed | 50 | 02/11/2022 | 31/03/2025 | 04/06/2025 | 27/02/2023 | 500.04 | 500.04
597 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 (SM/14902) | SM/14902 | 375.18 | 2400 | AUGMENTATION | 70 | Delayed | 51 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 13/07/2017 | 192.16 | 192.16
598 | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. (SM/12207) | SM/12207 | 927.96 | 1717 | AUGMENTATION | 70 | Delayed | 40 | 06/09/2022 | 31/05/2025 | 04/06/2025 | 01/11/2022 | 367.46 | 367.46
599 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PIPRAKHALI UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/11846) | SM/11846 | 463.3 | 702 | NEW | 70 | Delayed | 37 | 16/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 170.71 | 170.71
600 | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr (SM/11789) | SM/11789 | 539.41 | 868 | AUGMENTATION | 70 | Delayed | 46 | 03/08/2022 | 31/07/2025 | 04/06/2025 | 01/11/2022 | 245.47 | 240.08
601 | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15475) | SM/15475 | 341.66 | 1400 | AUGMENTATION | 70 | Delayed | 51 | 04/02/2023 | 30/09/2025 | 04/06/2025 | 09/11/2020 | 172.61 | 172.61
602 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. (SM/15495) | SM/15495 | 177.9 | 624 | AUGMENTATION | 70 | Delayed | 30 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 29/12/2021 | 52.85 | 52.85
603 | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM (SM/13307) | SM/13307 | 980.16 | 2114 | AUGMENTATION | 70 | Delayed | 47 | 17/10/2022 | 31/03/2025 | 04/06/2025 | 27/02/2023 | 462.58 | 462.58
604 | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT (SM/10484) | SM/10484 | 727.33 | 2444 | AUGMENTATION | 70 | Delayed | 63 | 13/04/2022 | 31/12/2025 | 04/06/2025 | 08/09/2021 | 456.43 | 456.43
605 | PROVIDING 100% FHTC IN ZONE- VIII AT NIMPITH MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. (SM/11246) | SM/11246 | 616.99 | 7302 | AUGMENTATION | 70 | Delayed | 47 | 22/06/2022 | 30/11/2025 | 04/06/2025 | 13/10/2022 | 287.5 | 287.5
606 | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11731) | SM/11731 | 530.84 | 815 | AUGMENTATION | 70 | Delayed | 40 | 02/08/2022 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 213.63 | 200.32
607 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE (SM/18221) | SM/18221 | 2879.31 | 0 | AUGMENTATION | 70 | On track | 59 | 27/04/2023 | 31/12/2025 | 04/06/2025 | 08/03/2022 | 1688.38 | 1688.38
608 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, (SM/18222) | SM/18222 | 2324.6 | 0 | AUGMENTATION | 70 | Delayed | 47 | 27/04/2023 | 30/11/2025 | 04/06/2025 | 02/03/2022 | 1092.44 | 1092.44
609 | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S (SM/14874) | SM/14874 | 763.97 | 2209 | AUGMENTATION | 71 | Delayed | 42 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 320.97 | 320.97
610 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme includin (SM/07406) | SM/07406 | 75.91 | 1328 | RETROFITTING | 71 | Delayed | 98 | 29/12/2020 | 30/09/2025 | 04/06/2025 | 24/02/2021 | 74.33 | 74.33
611 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme including (SM/07407) | SM/07407 | 56.09 | 1328 | RETROFITTING | 71 | Delayed | 56 | 29/12/2020 | 30/09/2025 | 04/06/2025 | 24/02/2021 | 31.51 | 31.51
612 | GROUND WATER BASED MADHUSUDANPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/18126) | SM/18126 | 577.33 | 1927 | NEW | 72 | Delayed | 48 | 29/03/2023 | 31/05/2025 | 04/06/2025 | 23/05/2023 | 277.18 | 277.18
613 | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS (SM/13973) | SM/13973 | 523.48 | 1366 | NEW | 72 | Delayed | 48 | 01/12/2022 | 31/12/2025 | 04/06/2025 | 05/08/2022 | 250.84 | 250.84
614 | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15499) | SM/15499 | 629.83 | 200 | AUGMENTATION | 72 | On track | 18 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 26/08/2022 | 116.33 | 116.33
615 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including (SM/07580) | SM/07580 | 58.99 | 869 | RETROFITTING | 72 | Delayed | 70 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 41.24 | 41.24
616 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Amlamethi Water Supply Scheme including one y (SM/09008) | SM/09008 | 212.32 | 3313 | RETROFITTING | 72 | Delayed | 97 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 22/11/2021 | 206.14 | 206.14
617 | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. (SM/11160) | SM/11160 | 2170.37 | 10728 | NEW | 72 | Delayed | 73 | 02/06/2022 | 31/03/2025 | 04/06/2025 | 25/02/2022 | 1576.54 | 1576.54
618 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem (SM/07631) | SM/07631 | 214.03 | 4025 | RETROFITTING | 72 | Delayed | 42 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 88.96 | 88.96
619 | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. (SM/11279) | SM/11279 | 888.39 | 1906 | NEW | 72 | Delayed | 29 | 24/06/2022 | 31/05/2025 | 04/06/2025 | 07/09/2022 | 255.33 | 253.91
620 | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/16117) | SM/16117 | 361.89 | 621 | AUGMENTATION | 72 | On track | 42 | 22/02/2023 | 07/11/2025 | 04/06/2025 | 24/04/2023 | 152.31 | 152.31
621 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 03 (three) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhuri Water Supply Scheme including one year (SM/09012) | SM/09012 | 96.07 | 1786 | RETROFITTING | 72 | Delayed | 19 | 27/05/2021 | 31/03/2025 | 04/06/2025 | 02/11/2021 | 17.89 | 17.89
622 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including o (SM/09011) | SM/09011 | 178.14 | 3376 | RETROFITTING | 72 | Delayed | 54 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 22/11/2021 | 96.92 | 89.92
623 | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09998) | SM/09998 | 1645.98 | 9445 | AUGMENTATION | 72 | Delayed | 47 | 22/12/2021 | 31/10/2025 | 04/06/2025 | 11/11/2022 | 768 | 768
624 | Proposed Ground water based BAGDAHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/15782) | SM/15782 | 494.87 | 850 | AUGMENTATION | 72 | Delayed | 37 | 20/02/2023 | 31/03/2025 | 04/06/2025 | 17/03/2023 | 181.3 | 181.3
625 | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS (SM/14158) | SM/14158 | 1030 | 2365 | NEW | 72 | Delayed | 17 | 05/01/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 170.87 | 170.87
626 | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS (SM/15961) | SM/15961 | 730.89 | 1542 | AUGMENTATION | 72 | On track | 43 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 19/04/2023 | 311.06 | 310.27
627 | GROUND WATER BASED CHHOTO BANASHYAM NAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13835) | SM/13835 | 864.51 | 1808 | NEW | 73 | On track | 31 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 19/08/2022 | 271.07 | 271.07
628 | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15081) | SM/15081 | 597.89 | 1800 | AUGMENTATION | 73 | Delayed | 54 | 04/02/2023 | 30/04/2025 | 04/06/2025 | 15/02/2023 | 323.82 | 319.21
629 | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas (SM/12053) | SM/12053 | 383 | 911 | AUGMENTATION | 73 | Delayed | 41 | 01/09/2022 | 31/03/2025 | 04/06/2025 | 02/09/2022 | 156.1 | 156.1
630 | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12237) | SM/12237 | 844.87 | 2215 | AUGMENTATION | 73 | Delayed | 51 | 07/09/2022 | 31/03/2025 | 04/06/2025 | 14/09/2022 | 426.85 | 426.85
631 | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri (SM/11784) | SM/11784 | 744.9 | 1967 | AUGMENTATION | 74 | Delayed | 69 | 03/08/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 516.47 | 516.47
632 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-V, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. (SM/15508) | SM/15508 | 341.02 | 1488 | AUGMENTATION | 74 | Delayed | 58 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 07/02/2022 | 199.21 | 199.21
633 | AUGMENTATION & RETROFITTING OF UTTAR ANGADBERIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15501) | SM/15501 | 237.68 | 200 | AUGMENTATION | 74 | Delayed | 29 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 15/02/2023 | 69.72 | 69.72
634 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA (SM/15973) | SM/15973 | 616.86 | 1075 | AUGMENTATION | 74 | On track | 49 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 23/02/2023 | 300.96 | 300.96
635 | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15104) | SM/15104 | 490.26 | 1500 | AUGMENTATION | 74 | Delayed | 76 | 04/02/2023 | 31/08/2025 | 04/06/2025 | 27/01/2021 | 373.07 | 373.07
636 | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric (SM/13310) | SM/13310 | 609.2 | 1182 | AUGMENTATION | 74 | On track | 46 | 17/10/2022 | 31/12/2025 | 04/06/2025 | 01/11/2022 | 278.61 | 278.61
637 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayangarh Water Supply Scheme including one (SM/09015) | SM/09015 | 63.53 | 2385 | RETROFITTING | 75 | Delayed | 94 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 02/11/2021 | 60 | 60
638 | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/10336) | SM/10336 | 1777.03 | 11552 | AUGMENTATION | 75 | On track | 43 | 14/03/2022 | 31/12/2025 | 04/06/2025 | 23/02/2021 | 763.88 | 763.88
639 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-V OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BA (SM/13915) | SM/13915 | 122.23 | 0 | AUGMENTATION | 75 | Delayed | 12 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 12/05/2021 | 14.31 | 14.31
640 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-X OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/18553) | SM/18553 | 1612.47 | 9578 | AUGMENTATION | 75 | Delayed | 61 | 26/07/2023 | 30/09/2025 | 04/06/2025 | 04/08/2023 | 984.87 | 984.87
641 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on (SM/07416) | SM/07416 | 69.83 | 1957 | RETROFITTING | 75 | WO no issued | 8 | 29/12/2020 | 31/08/2025 | 04/06/2025 | 07/08/2020 | 5.65 | 5.65
642 | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. (SM/12873) | SM/12873 | 792.29 | 2991 | NEW | 75 | Delayed | 30 | 23/09/2022 | 30/06/2025 | 04/06/2025 | 17/10/2022 | 239.75 | 239.75
643 | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri (SM/12213) | SM/12213 | 312.99 | 848 | AUGMENTATION | 75 | Delayed | 61 | 06/09/2022 | 31/03/2025 | 04/06/2025 | 25/04/2022 | 190.44 | 190.44
644 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAKHASKHALI , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13802) | SM/13802 | 981.09 | 1668 | NEW | 75 | Delayed | 53 | 22/11/2022 | 31/08/2025 | 04/06/2025 | 01/08/2022 | 520.16 | 518.4
645 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR (SM/14465) | SM/14465 | 633.13 | 2458 | AUGMENTATION | 75 | Delayed | 54 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 15/09/2022 | 340.76 | 340.76
646 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE (SM/16186) | SM/16186 | 2189.82 | 0 | AUGMENTATION | 75 | On track | 34 | 20/02/2023 | 30/11/2025 | 04/06/2025 | 08/03/2022 | 751 | 751
647 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one (SM/09098) | SM/09098 | 125.76 | 2110 | RETROFITTING | 75 | Delayed | 73 | 29/10/2021 | 31/12/2025 | 04/06/2025 | 23/03/2022 | 91.87 | 91.87
648 | AUGMENTATION OF KUMARKHALI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) UNDER BASANTI BLOCK OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT (SM/10478) | SM/10478 | 938.04 | 2968 | AUGMENTATION | 75 | Delayed | 72 | 13/04/2022 | 31/03/2025 | 04/06/2025 | 18/08/2021 | 676.46 | 676.46
649 | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/14159) | SM/14159 | 1074.54 | 2297 | AUGMENTATION | 75 | On track | 68 | 05/01/2023 | 31/12/2025 | 04/06/2025 | 29/12/2022 | 735.73 | 735.19
650 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-XI at MANDIRBAZAR block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, P (SM/16188) | SM/16188 | 905.6 | 0 | AUGMENTATION | 75 | Delayed | 50 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 09/03/2023 | 452.7 | 452.7
651 | AUGMENTATION OF GROUND WATER BASED RAMTANUNAGAR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11751) | SM/11751 | 457.78 | 756 | AUGMENTATION | 75 | Delayed | 56 | 03/08/2022 | 31/03/2025 | 04/06/2025 | 08/08/2022 | 258.24 | 258.24
652 | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12208) | SM/12208 | 486.27 | 1261 | AUGMENTATION | 75 | On track | 38 | 06/09/2022 | 31/12/2025 | 04/06/2025 | 27/01/2022 | 183.33 | 183.33
653 | Ground water based RAJAK GOHALIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr (SM/11778) | SM/11778 | 464.19 | 963 | AUGMENTATION | 75 | Delayed | 32 | 02/08/2022 | 30/06/2025 | 04/06/2025 | 01/11/2022 | 150.07 | 145.25
654 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-V OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDE (SM/14472) | SM/14472 | 461.17 | 4527 | AUGMENTATION | 75 | On track | 24 | 20/01/2023 | 31/12/2025 | 04/06/2025 | 04/02/2023 | 111.19 | 111.19
655 | Proposed Ground water based CHAK HARANANDAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic (SM/14864) | SM/14864 | 641.48 | 1956 | AUGMENTATION | 75 | Delayed | 14 | 03/02/2023 | 30/06/2025 | 04/06/2025 | 15/03/2023 | 91.42 | 91.42
656 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South (SM/16191) | SM/16191 | 1247.95 | 0 | AUGMENTATION | 75 | Delayed | 61 | 20/02/2023 | 31/07/2025 | 04/06/2025 | 15/03/2022 | 757.16 | 757.16
657 | Augmentation of ground water based PADMAJALA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. (SM/13766) | SM/13766 | 611.29 | 1761 | AUGMENTATION | 75 | On track | 41 | 18/11/2022 | 30/08/2026 | 04/06/2025 | 21/11/2022 | 252.7 | 251.8
658 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15052) | SM/15052 | 999.02 | 2245 | AUGMENTATION | 75 | On track | 47 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 469.65 | 469.65
659 | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15772) | SM/15772 | 989.64 | 1985 | AUGMENTATION | 75 | Delayed | 31 | 20/02/2023 | 31/08/2025 | 04/06/2025 | 10/03/2023 | 309.96 | 309.96
660 | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12266) | SM/12266 | 707.77 | 1571 | AUGMENTATION | 76 | On track | 48 | 06/09/2022 | 30/11/2025 | 04/06/2025 | 14/09/2022 | 340.45 | 340.3
661 | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/10051) | SM/10051 | 1700.47 | 8106 | AUGMENTATION | 76 | On track | 60 | 24/01/2022 | 31/12/2025 | 04/06/2025 | 16/03/2022 | 1022.31 | 1022.31
662 | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/14518) | SM/14518 | 1345.28 | 2065 | AUGMENTATION | 76 | Delayed | 38 | 30/01/2023 | 31/08/2025 | 04/06/2025 | 16/10/2020 | 509.33 | 509.33
663 | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/10092) | SM/10092 | 1160.08 | 4770 | AUGMENTATION | 76 | Delayed | 55 | 01/02/2022 | 31/05/2025 | 04/06/2025 | 27/09/2021 | 641.35 | 641.35
664 | Retrofitting for Providing FHTC of Ground Water Based Kasinagar Water Supply Scheme (Phase - A) (SM/09464) | SM/09464 | 67.56 | 4586 | RETROFITTING | 77 | Delayed | 55 | 19/11/2021 | 31/03/2025 | 04/06/2025 | 06/09/2021 | 37.01 | 37.01
665 | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A (SM/15781) | SM/15781 | 646.08 | 1608 | AUGMENTATION | 77 | On track | 42 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 17/03/2023 | 270.46 | 270.46
666 | Ground water based piped water supply scheme at Kalyanpur, Khodarbazar (Khodarbazar CT, J.L-40), Baruipur Block under South 24 Parganas dist.(PART-I) (SM/11294) | SM/11294 | 169.02 | 813 | NEW | 77 | Delayed | 53 | 28/06/2022 | 31/05/2025 | 04/06/2025 | 23/08/2022 | 88.84 | 88.84
667 | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS (SM/13838) | SM/13838 | 615.74 | 1443 | NEW | 78 | On track | 50 | 25/11/2022 | 31/12/2025 | 04/06/2025 | 20/02/2023 | 306.74 | 296.19
668 | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 (SM/18870) | SM/18870 | 273.32 | 917 | AUGMENTATION | 78 | On track | 47 | 05/10/2023 | 30/11/2025 | 04/06/2025 | 17/10/2023 | 129.43 | 126.33
669 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on (SM/07582) | SM/07582 | 98.18 | 1386 | RETROFITTING | 78 | Delayed | 70 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 15/10/2020 | 69.17 | 69.17
670 | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. (SM/13441) | SM/13441 | 787.76 | 2505 | AUGMENTATION | 78 | On track | 60 | 02/11/2022 | 31/12/2025 | 04/06/2025 | 11/11/2022 | 469.16 | 469.16
671 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one (SM/08636) | SM/08636 | 134.28 | 1350 | RETROFITTING | 78 | Delayed | 96 | 31/05/2021 | 31/12/2025 | 04/06/2025 | 27/07/2021 | 129.48 | 129.48
672 | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte (SM/15870) | SM/15870 | 418.82 | 634 | AUGMENTATION | 78 | Delayed | 37 | 20/02/2023 | 31/05/2025 | 04/06/2025 | 03/03/2023 | 156.72 | 156.72
673 | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. (SM/08181) | SM/08181 | 260.42 | 2123 | RETROFITTING | 79 | Delayed | 81 | 09/02/2021 | 31/03/2025 | 04/06/2025 | 26/02/2021 | 211.85 | 211.85
674 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT (SM/13072) | SM/13072 | 413.58 | 997 | AUGMENTATION | 79 | On track | 32 | 29/09/2022 | 30/06/2026 | 04/06/2025 | 07/07/2021 | 130.41 | 129.63
675 | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal (SM/11275) | SM/11275 | 828 | 2260 | NEW | 80 | Delayed | 57 | 24/06/2022 | 31/03/2025 | 04/06/2025 | 29/06/2022 | 474.62 | 474.62
676 | Improvement of W/S including providing FHTC for Chandanpukur, Bagdaha, Dhanberia & Durgapur mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. (SM/08180) | SM/08180 | 225.68 | 1315 | RETROFITTING | 80 | Delayed | 70 | 09/02/2021 | 31/03/2025 | 04/06/2025 | 26/02/2021 | 159.03 | 159.03
677 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-III) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13577) | SM/13577 | 50.52 | 148 | AUGMENTATION | 80 | Delayed | 77 | 09/11/2022 | 31/03/2025 | 04/06/2025 | 03/03/2023 | 39.04 | 39.04
678 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST (SM/15532) | SM/15532 | 1410.79 | 8053 | AUGMENTATION | 80 | Delayed | 83 | 16/02/2023 | 31/03/2025 | 04/06/2025 | 15/02/2022 | 1170.57 | 1170.57
679 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-IV, PURBA RANAGHAT PIPED WATER SUPPLY SCHEME, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY S (SM/18716) | SM/18716 | 143.17 | 792 | AUGMENTATION | 80 | Delayed | 77 | 10/08/2023 | 30/04/2025 | 04/06/2025 | 11/08/2023 | 110.54 | 110.54
680 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy (SM/12576) | SM/12576 | 45.21 | 122 | NEW | 80 | Delayed | 58 | 15/09/2022 | 31/03/2025 | 04/06/2025 | 15/02/2023 | 26.16 | 26.16
681 | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12046) | SM/12046 | 244.81 | 472 | AUGMENTATION | 80 | Delayed | 38 | 01/09/2022 | 31/03/2025 | 04/06/2025 | 14/09/2022 | 94.01 | 94.01
682 | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12051) | SM/12051 | 449.87 | 941 | AUGMENTATION | 80 | On track | 56 | 01/09/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 253.36 | 253.36
683 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VIII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13580) | SM/13580 | 73.53 | 247 | AUGMENTATION | 80 | Delayed | 74 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 06/03/2023 | 54.48 | 54.48
684 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR TAMBUL DAHA (PART - I) UNDER ALIPORE DIVISION, BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/12744) | SM/12744 | 63.13 | 143 | AUGMENTATION | 80 | On track | 89 | 20/09/2022 | 31/12/2025 | 04/06/2025 | 09/03/2023 | 56.38 | 56.38
685 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-II BLOCK PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15498) | SM/15498 | 216.4 | 866 | AUGMENTATION | 80 | Delayed | 14 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 13/06/2022 | 30.63 | 30.63
686 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI (SM/15505) | SM/15505 | 642.88 | 1357 | AUGMENTATION | 80 | Delayed | 48 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 11/05/2023 | 307.31 | 307.31
687 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. (SM/15504) | SM/15504 | 200.81 | 807 | AUGMENTATION | 80 | Delayed | 72 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 11/03/2020 | 144.98 | 144.98
688 | Providing 100% FHTC in Zone-IX at Ghola Noapara Usthi mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11259) | SM/11259 | 430.01 | 5309 | AUGMENTATION | 80 | Delayed | 45 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 07/09/2022 | 193.03 | 193.03
689 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D (SM/15466) | SM/15466 | 368.17 | 1095 | AUGMENTATION | 80 | Delayed | 53 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 30/11/2021 | 195 | 195
690 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU (SM/15320) | SM/15320 | 2499.96 | 5259 | AUGMENTATION | 80 | On track | 31 | 09/02/2023 | 31/12/2025 | 04/06/2025 | 15/09/2022 | 785.55 | 785.55
691 | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist (SM/15755) | SM/15755 | 707.53 | 1885 | AUGMENTATION | 80 | On track | 47 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 02/03/2023 | 331.83 | 331.83
692 | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas (SM/08869) | SM/08869 | 59421.43 | 90081 | AUGMENTATION | 80 | On track | 36 | 14/09/2021 | 31/12/2025 | 04/06/2025 | 18/01/2021 | 21474.84 | 21474.84
693 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN (SM/12205) | SM/12205 | 669.5 | 0 | AUGMENTATION | 80 | Delayed | 53 | 07/09/2022 | 31/05/2025 | 04/06/2025 | 28/03/2023 | 352.25 | 352.25
694 | Providing Functional Household Tap Connection (FHTC) in Zone-V at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11241) | SM/11241 | 316.26 | 3829 | NEW | 80 | On track | 66 | 22/06/2022 | 07/11/2025 | 04/06/2025 | 31/08/2023 | 209.2 | 209.2
695 | SATBERIA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal (SM/11274) | SM/11274 | 913.42 | 1721 | NEW | 80 | Delayed | 69 | 24/06/2022 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 633.24 | 633.24
696 | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta (SM/15497) | SM/15497 | 205.87 | 846 | AUGMENTATION | 80 | On track | 20 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 29/12/2021 | 40.32 | 40.32
697 | AUGMENTATION AND RETROFITTING OF BANSRA (ZONE - I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15490) | SM/15490 | 513.12 | 2000 | AUGMENTATION | 80 | Delayed | 69 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 20/02/2023 | 354.62 | 354.62
698 | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS (SM/18698) | SM/18698 | 1116.01 | 1259 | AUGMENTATION | 80 | On track | 23 | 04/08/2023 | 31/12/2025 | 04/06/2025 | 14/08/2023 | 254.38 | 248.28
699 | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/11748) | SM/11748 | 837.74 | 1403 | AUGMENTATION | 80 | On track | 71 | 03/08/2022 | 31/12/2025 | 04/06/2025 | 03/11/2020 | 593.54 | 593.54
700 | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/12733) | SM/12733 | 713.69 | 2113 | NEW | 80 | Delayed | 64 | 20/09/2022 | 30/04/2025 | 04/06/2025 | 22/09/2022 | 453.23 | 443.17
701 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-IV), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13585) | SM/13585 | 44.46 | 70 | AUGMENTATION | 80 | Delayed | 73 | 09/11/2022 | 31/03/2025 | 04/06/2025 | 14/11/2022 | 32.29 | 32.29
702 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC (SM/14463) | SM/14463 | 406.93 | 1825 | AUGMENTATION | 80 | Delayed | 50 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 04/02/2023 | 203.23 | 203.23
703 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC IN THE LEFT OUT AREAS IN ZONE-I AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UND (SM/13970) | SM/13970 | 574.64 | 3450 | AUGMENTATION | 80 | Delayed | 77 | 01/12/2022 | 30/09/2025 | 04/06/2025 | 16/03/2023 | 444.23 | 444.23
704 | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15198) | SM/15198 | 377.13 | 620 | AUGMENTATION | 80 | On track | 75 | 06/02/2023 | 31/12/2025 | 04/06/2025 | 04/04/2023 | 281.46 | 281.46
705 | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. (SM/18253) | SM/18253 | 2827.8 | 23728 | AUGMENTATION | 80 | Delayed | 42 | 16/06/2023 | 30/04/2025 | 04/06/2025 | 31/07/2023 | 1175.72 | 1175.72
706 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, (SM/18656) | SM/18656 | 1120.85 | 0 | AUGMENTATION | 80 | Delayed | 36 | 04/08/2023 | 31/03/2025 | 04/06/2025 | 22/02/2022 | 406.73 | 406.73
707 | BHAGABANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18575) | SM/18575 | 1339.6 | 3047 | AUGMENTATION | 80 | On track | 36 | 31/07/2023 | 31/12/2025 | 04/06/2025 | 11/08/2023 | 476.4 | 476.4
708 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) (SM/07630) | SM/07630 | 170.64 | 3606 | RETROFITTING | 80 | Delayed | 73 | 07/01/2021 | 30/09/2025 | 04/06/2025 | 15/12/2020 | 124.82 | 124.82
709 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/14471) | SM/14471 | 742.41 | 3856 | AUGMENTATION | 80 | Delayed | 21 | 20/01/2023 | 30/06/2025 | 04/06/2025 | 27/07/2022 | 154.43 | 154.43
710 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 (SM/14477) | SM/14477 | 341.86 | 2180 | AUGMENTATION | 80 | Delayed | 39 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 04/02/2023 | 132.05 | 132.05
711 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15491) | SM/15491 | 287.23 | 833 | AUGMENTATION | 80 | Delayed | 34 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 24/12/2020 | 97.61 | 97.61
712 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH (SM/17182) | SM/17182 | 371.8 | 2458 | AUGMENTATION | 80 | Delayed | 74 | 15/03/2023 | 31/03/2025 | 04/06/2025 | 09/08/2017 | 275.87 | 275.87
713 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali (SM/07629) | SM/07629 | 272.76 | 3199 | RETROFITTING | 80 | Delayed | 66 | 07/01/2021 | 31/07/2025 | 04/06/2025 | 12/10/2020 | 179.81 | 179.53
714 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VI) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13573) | SM/13573 | 52.71 | 148 | AUGMENTATION | 80 | Delayed | 57 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 10/11/2022 | 30.14 | 30.14
715 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-IX) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13581) | SM/13581 | 59.59 | 173 | AUGMENTATION | 80 | Delayed | 64 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 03/03/2023 | 38.31 | 38.31
716 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/13909) | SM/13909 | 746.69 | 4113 | AUGMENTATION | 80 | Delayed | 28 | 29/11/2022 | 30/06/2025 | 04/06/2025 | 22/03/2023 | 209.37 | 209.37
717 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, (SM/16185) | SM/16185 | 1555.02 | 0 | AUGMENTATION | 80 | On track | 35 | 20/02/2023 | 30/11/2025 | 04/06/2025 | 22/02/2022 | 551.08 | 551.08
718 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water su (SM/16184) | SM/16184 | 746.86 | 0 | AUGMENTATION | 80 | On track | 21 | 20/02/2023 | 30/09/2025 | 04/06/2025 | 28/04/2023 | 157.44 | 157.44
719 | Providing 100% FHTC in Zone-III at Pratapberia (Baneswarpur) mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11266) | SM/11266 | 332.14 | 4369 | AUGMENTATION | 80 | Delayed | 44 | 23/06/2022 | 31/05/2025 | 04/06/2025 | 28/04/2023 | 144.93 | 144.93
720 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA (SM/14474) | SM/14474 | 953.38 | 5140 | AUGMENTATION | 80 | Delayed | 52 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 496.57 | 496.57
721 | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec (SM/14877) | SM/14877 | 145.71 | 0 | AUGMENTATION | 80 | Delayed | 70 | 03/02/2023 | 30/06/2025 | 04/06/2025 | 24/02/2023 | 101.92 | 101.92
722 | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal (SM/11273) | SM/11273 | 993.75 | 2662 | NEW | 80 | On track | 70 | 24/06/2022 | 30/07/2026 | 04/06/2025 | 29/06/2022 | 693.03 | 692.14
723 | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11499) | SM/11499 | 638.47 | 1095 | NEW | 80 | On track | 57 | 19/07/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 366.93 | 366.93
724 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Moukhali Water Suppl (SM/07639) | SM/07639 | 217.52 | 1977 | RETROFITTING | 81 | Delayed | 54 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 21/06/2021 | 117.75 | 117.46
725 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply (SM/07640) | SM/07640 | 275.12 | 5270 | RETROFITTING | 81 | Delayed | 81 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 223.2 | 223.2
726 | Retrofitting of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. (SM/08799) | SM/08799 | 210.24 | 2889 | RETROFITTING | 81 | Delayed | 81 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 19/08/2021 | 169.68 | 169.68
727 | Ground water based piped water supply scheme at Chitrasali (Chitrasali,J.L-112), Baruipur Block under South 24 Parganas dist (SM/11295) | SM/11295 | 149.12 | 520 | NEW | 81 | Delayed | 46 | 28/06/2022 | 31/03/2025 | 04/06/2025 | 07/09/2022 | 67.93 | 67.93
728 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-X) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13572) | SM/13572 | 75.74 | 198 | AUGMENTATION | 81 | Delayed | 89 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 06/03/2023 | 67.4 | 67.4
729 | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P (SM/13917) | SM/13917 | 286.9 | 620 | AUGMENTATION | 81 | Delayed | 29 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 82.8 | 74.37
730 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in (SM/07749) | SM/07749 | 108.22 | 1178 | RETROFITTING | 82 | Delayed | 45 | 08/01/2021 | 31/08/2025 | 04/06/2025 | 01/10/2020 | 48.41 | 46.56
731 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME (SM/15470) | SM/15470 | 286.46 | 1090 | AUGMENTATION | 82 | Delayed | 62 | 04/02/2023 | 30/04/2025 | 04/06/2025 | 16/02/2022 | 176.59 | 176.59
732 | Ground water based INDRAPALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12264) | SM/12264 | 532.77 | 1009 | AUGMENTATION | 82 | On track | 43 | 06/09/2022 | 31/12/2025 | 04/06/2025 | 14/09/2022 | 230.12 | 230.12
733 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS (SM/15577) | SM/15577 | 218.88 | 542 | NEW | 82 | Delayed | 81 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 17/02/2023 | 177.1 | 177.1
734 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-V) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13578) | SM/13578 | 76.27 | 247 | AUGMENTATION | 82 | Delayed | 87 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 03/03/2023 | 66.49 | 66.49
735 | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS (SM/11848) | SM/11848 | 886.26 | 1975 | NEW | 82 | On track | 46 | 16/08/2022 | 31/12/2025 | 04/06/2025 | 11/11/2022 | 409.42 | 409.42
736 | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. (SM/11494) | SM/11494 | 491.24 | 983 | NEW | 83 | On track | 36 | 19/07/2022 | 31/12/2025 | 04/06/2025 | 25/04/2022 | 175.19 | 169.83
737 | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/13311) | SM/13311 | 719.78 | 2040 | AUGMENTATION | 83 | Delayed | 53 | 17/10/2022 | 31/03/2025 | 04/06/2025 | 21/02/2023 | 379.98 | 379.98
738 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Adhia Water Supply Sche (SM/07596) | SM/07596 | 92.66 | 1625 | RETROFITTING | 83 | Delayed | 54 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 08/10/2020 | 50 | 50
739 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hiranmoypur Water Supply Scheme including one (SM/09013) | SM/09013 | 193.76 | 3602 | RETROFITTING | 83 | On track | 87 | 26/05/2021 | 31/12/2025 | 04/06/2025 | 22/11/2021 | 169.26 | 169.26
740 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-XI) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13582) | SM/13582 | 80 | 272 | AUGMENTATION | 83 | Delayed | 89 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 06/03/2023 | 71.04 | 71.04
741 | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff (SM/16128) | SM/16128 | 145.09 | 332 | AUGMENTATION | 83 | On track | 26 | 22/02/2023 | 31/12/2025 | 04/06/2025 | 26/04/2023 | 37.27 | 37.27
742 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- (SM/14475) | SM/14475 | 347.31 | 2510 | AUGMENTATION | 84 | On track | 35 | 20/01/2023 | 31/12/2025 | 04/06/2025 | 04/02/2023 | 120.47 | 118.09
743 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ananda Abad Water Supply S (SM/07593) | SM/07593 | 65.34 | 1195 | RETROFITTING | 84 | On track | 93 | 31/12/2020 | 31/12/2025 | 04/06/2025 | 19/02/2021 | 61.04 | 61.04
744 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S (SM/09016) | SM/09016 | 86.12 | 1592 | RETROFITTING | 84 | Delayed | 92 | 26/05/2021 | 31/03/2025 | 04/06/2025 | 03/03/2021 | 79.5 | 79.5
745 | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] (SM/10151) | SM/10151 | 1068.69 | 1995 | AUGMENTATION | 84 | On track | 83 | 10/02/2022 | 30/09/2025 | 04/06/2025 | 10/09/2021 | 884.26 | 884.26
746 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GAYADHAM, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/11744) | SM/11744 | 585.72 | 1076 | NEW | 84 | On track | 59 | 03/08/2022 | 31/08/2025 | 04/06/2025 | 08/08/2022 | 345.48 | 345.48
747 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl (SM/07633) | SM/07633 | 241.76 | 5480 | RETROFITTING | 85 | Delayed | 83 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 24/03/2021 | 199.51 | 199.51
748 | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par (SM/12058) | SM/12058 | 237.52 | 494 | AUGMENTATION | 85 | On track | 54 | 01/09/2022 | 31/08/2025 | 04/06/2025 | 02/09/2022 | 127.41 | 127.41
749 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XIII OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' U (SM/13910) | SM/13910 | 943.26 | 3170 | AUGMENTATION | 85 | Delayed | 46 | 29/11/2022 | 30/06/2025 | 04/06/2025 | 15/09/2022 | 435.14 | 435.14
750 | AUGMENTATION FOR GROUND WATER BASED TAKTIPUR ABAD (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11876) | SM/11876 | 833.48 | 682 | AUGMENTATION | 85 | On track | 58 | 17/08/2022 | 31/12/2025 | 04/06/2025 | 18/08/2022 | 484.48 | 484.48
751 | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic (SM/14551) | SM/14551 | 1117.57 | 3706 | AUGMENTATION | 85 | On track | 53 | 30/01/2023 | 30/11/2025 | 04/06/2025 | 15/03/2023 | 592.38 | 592.38
752 | AUGMENTATION OF GROUND WATER BASED GURUDASPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/10486) | SM/10486 | 843.18 | 3286 | AUGMENTATION | 85 | Delayed | 36 | 13/04/2022 | 31/07/2025 | 04/06/2025 | 27/09/2021 | 304.04 | 304.04
753 | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/14663) | SM/14663 | 999.99 | 3314 | AUGMENTATION | 85 | Delayed | 63 | 31/01/2023 | 31/03/2025 | 04/06/2025 | 15/03/2023 | 626.87 | 626.87
754 | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14863) | SM/14863 | 788.04 | 2247 | AUGMENTATION | 85 | Delayed | 38 | 03/02/2023 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 302.12 | 302.12
755 | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15095) | SM/15095 | 254.86 | 500 | AUGMENTATION | 85 | Delayed | 82 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 209.04 | 209.04
756 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-I OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA (SM/14470) | SM/14470 | 155.77 | 0 | AUGMENTATION | 85 | On track | 89 | 20/01/2023 | 31/08/2025 | 04/06/2025 | 19/02/2021 | 138.52 | 138.52
757 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-II), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/12746) | SM/12746 | 48.4 | 70 | AUGMENTATION | 85 | Delayed | 88 | 20/09/2022 | 31/03/2025 | 04/06/2025 | 02/03/2023 | 42.79 | 42.79
758 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B (SM/13916) | SM/13916 | 122.23 | 0 | AUGMENTATION | 85 | Delayed | 84 | 29/11/2022 | 31/03/2025 | 04/06/2025 | 01/10/2021 | 103.13 | 103.13
759 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13579) | SM/13579 | 83.55 | 345 | AUGMENTATION | 85 | On track | 91 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 06/03/2023 | 76.12 | 76.12
760 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P (SM/15474) | SM/15474 | 129.48 | 814 | AUGMENTATION | 85 | Delayed | 67 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 31/01/2022 | 86.91 | 86.91
761 | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis (SM/15634) | SM/15634 | 716.58 | 1885 | AUGMENTATION | 85 | Delayed | 46 | 15/02/2023 | 30/06/2025 | 04/06/2025 | 24/02/2023 | 328.5 | 328.5
762 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/18551) | SM/18551 | 1245.82 | 3320 | AUGMENTATION | 85 | Delayed | 32 | 26/07/2023 | 31/03/2025 | 04/06/2025 | 03/11/2023 | 402.13 | 402.13
763 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ (SM/07408) | SM/07408 | 76.56 | 1158 | RETROFITTING | 85 | On track | 85 | 29/12/2020 | 31/12/2025 | 04/06/2025 | 19/08/2020 | 65.09 | 65.05
764 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sambhunagar WS Scheme includin (SM/08633) | SM/08633 | 167.07 | 2581 | RETROFITTING | 85 | On track | 96 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 29/10/2021 | 160.3 | 160.3
765 | Ground water based DHANBERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12054) | SM/12054 | 312.87 | 209 | AUGMENTATION | 85 | Delayed | 19 | 01/09/2022 | 30/06/2025 | 04/06/2025 | 02/09/2022 | 59.54 | 59.54
766 | Ground water based DAKSHIN SASAN (P) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12057) | SM/12057 | 736.18 | 1759 | AUGMENTATION | 85 | On track | 40 | 01/09/2022 | 30/09/2025 | 04/06/2025 | 02/09/2022 | 291.76 | 291.76
767 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-I), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13584) | SM/13584 | 51.31 | 105 | AUGMENTATION | 85 | On track | 94 | 09/11/2022 | 31/12/2025 | 04/06/2025 | 14/11/2022 | 48.47 | 48.47
768 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-VI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D (SM/15465) | SM/15465 | 230.56 | 416 | AUGMENTATION | 85 | Delayed | 47 | 04/02/2023 | 30/04/2025 | 04/06/2025 | 14/03/2023 | 109.14 | 109.14
769 | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13569) | SM/13569 | 1208.65 | 1735 | AUGMENTATION | 85 | On track | 67 | 09/11/2022 | 31/12/2025 | 04/06/2025 | 06/09/2022 | 810.68 | 810.68
770 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU (SM/14468) | SM/14468 | 518.03 | 0 | AUGMENTATION | 85 | On track | 85 | 20/01/2023 | 31/12/2025 | 04/06/2025 | 11/04/2023 | 439.58 | 439.58
771 | KANTIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/13777) | SM/13777 | 981.49 | 1783 | AUGMENTATION | 85 | On track | 34 | 18/11/2022 | 30/09/2025 | 04/06/2025 | 15/12/2022 | 337.46 | 337.46
772 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER DIA (SM/13833) | SM/13833 | 672.9 | 2184 | AUGMENTATION | 85 | On track | 35 | 25/11/2022 | 30/04/2026 | 04/06/2025 | 23/09/2022 | 235.82 | 235.82
773 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-XII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13583) | SM/13583 | 87.98 | 297 | AUGMENTATION | 86 | Delayed | 82 | 09/11/2022 | 31/03/2025 | 04/06/2025 | 14/11/2022 | 72.21 | 72.21
774 | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/16135) | SM/16135 | 199.17 | 348 | AUGMENTATION | 86 | Delayed | 53 | 22/02/2023 | 31/05/2025 | 04/06/2025 | 09/03/2023 | 104.65 | 99.98
775 | SAHEBPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. (SM/13675) | SM/13675 | 883.61 | 2108 | AUGMENTATION | 86 | On track | 41 | 02/11/2022 | 30/07/2026 | 04/06/2025 | 01/12/2022 | 360.83 | 350.16
776 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-IV) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13574) | SM/13574 | 54.45 | 124 | AUGMENTATION | 86 | Delayed | 73 | 09/11/2022 | 31/03/2025 | 04/06/2025 | 14/11/2022 | 39.92 | 39.92
777 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR NARAYANGANJ, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS. (SM/15046) | SM/15046 | 94.46 | 418 | NEW | 86 | On track | 62 | 03/02/2023 | 31/12/2025 | 04/06/2025 | 02/08/2022 | 58.57 | 58.57
778 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15492) | SM/15492 | 390.64 | 1319 | AUGMENTATION | 86 | Delayed | 86 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 24/02/2022 | 334.58 | 334.58
779 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:197 to 198 and Adjoining Areas under Budge Budge-I Block (SM/07014) | SM/07014 | 28.3 | 696 | RETROFITTING | 88 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 23/11/2020 | 28.3 | 27.08
780 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Uttar Roypur, Balarampur (Part) and Chak Nabasan (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09946) | SM/09946 | 157.01 | 50 | RETROFITTING | 88 | On track | 97 | 14/12/2021 | 31/07/2025 | 04/06/2025 | 02/11/2021 | 152.14 | 152.14
781 | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09948) | SM/09948 | 64.96 | 200 | RETROFITTING | 88 | On track | 98 | 14/12/2021 | 30/11/2025 | 04/06/2025 | 25/10/2021 | 63.82 | 63.82
782 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09954) | SM/09954 | 287.71 | 118 | RETROFITTING | 88 | Delayed | 87 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 09/11/2021 | 250.68 | 250.68
783 | Retrofitting of distribution System For Nandarampur W/S Scheme for Booth No:170 and Adjoining Areas under Budge Budge-I Block (SM/07020) | SM/07020 | 94.56 | 1800 | RETROFITTING | 88 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 11/12/2020 | 94.56 | 94.56
784 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte (SM/09944) | SM/09944 | 135.17 | 40 | RETROFITTING | 88 | On track | 40 | 14/12/2021 | 31/07/2025 | 04/06/2025 | 02/11/2021 | 53.62 | 53.62
785 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09945) | SM/09945 | 163.9 | 440 | RETROFITTING | 88 | On track | 54 | 14/12/2021 | 31/07/2025 | 04/06/2025 | 02/11/2021 | 88.02 | 88.02
786 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ (SM/09006) | SM/09006 | 131.88 | 1221 | RETROFITTING | 88 | On track | 89 | 31/05/2021 | 31/12/2025 | 04/06/2025 | 21/05/2021 | 117.39 | 117.39
787 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13965) | SM/13965 | 725.37 | 1486 | NEW | 88 | On track | 76 | 01/12/2022 | 31/08/2025 | 04/06/2025 | 20/07/2022 | 551.38 | 551.38
788 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13576) | SM/13576 | 55.09 | 148 | AUGMENTATION | 88 | Delayed | 87 | 09/11/2022 | 31/03/2025 | 04/06/2025 | 12/08/2022 | 47.95 | 47.95
789 | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-II) (PART I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13873) | SM/13873 | 845.93 | 734 | AUGMENTATION | 88 | On track | 68 | 25/11/2022 | 31/08/2025 | 04/06/2025 | 01/08/2022 | 575.33 | 575.33
790 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:153 to 169 under Budge Budge-I Block with allied works (SM/07053) | SM/07053 | 99.78 | 1637 | RETROFITTING | 88 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 27/07/2022 | 99.78 | 82.75
791 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 197 to 198) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09953) | SM/09953 | 42.18 | 506 | RETROFITTING | 88 | Delayed | 80 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 25/10/2021 | 33.73 | 33.73
792 | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur (SM/07052) | SM/07052 | 68.39 | 1090 | RETROFITTING | 88 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 21/12/2020 | 68.39 | 63.57
793 | Ground water based KESHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12059) | SM/12059 | 511.47 | 591 | AUGMENTATION | 88 | On track | 42 | 01/09/2022 | 31/12/2025 | 04/06/2025 | 02/09/2022 | 215.79 | 214.42
794 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works (SM/07050) | SM/07050 | 88.77 | 2183 | RETROFITTING | 88 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 11/12/2020 | 88.77 | 86.5
795 | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09950) | SM/09950 | 89.53 | 394 | RETROFITTING | 88 | Delayed | 94 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 25/10/2021 | 84.08 | 84.08
796 | Retrofitting of distribution System For Nandarampur W/S Scheme for Chak Nabashan Mouza and adjoining areas under Budge Budge-I Block (SM/07019) | SM/07019 | 26.02 | 640 | RETROFITTING | 89 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 23/11/2020 | 26.02 | 24.42
797 | Retrofitting of distribution System For Jamalpur W/S Scheme for habitations of Jamalpur Mouza and adjoining areas under Budge Budge-I Block with allied works (SM/07056) | SM/07056 | 82.14 | 1286 | RETROFITTING | 89 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 31/01/2023 | 82.14 | 80.03
798 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:141 to 144 and Adjoining Areas under Budge Budge-I Block (SM/07017) | SM/07017 | 96.57 | 2088 | RETROFITTING | 89 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 14/12/2020 | 96.57 | 91.31
799 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144 ) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09956) | SM/09956 | 299.18 | 80 | RETROFITTING | 89 | Delayed | 96 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 09/11/2021 | 286.45 | 286.45
800 | Retrofitting of pipeline for supporting FHTC drive for under Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza including Balarampur Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas (SM/09947) | SM/09947 | 163.78 | 1526 | RETROFITTING | 89 | Delayed | 97 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 02/11/2021 | 159 | 159
801 | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic (SM/13920) | SM/13920 | 292.37 | 768 | AUGMENTATION | 89 | On track | 61 | 29/11/2022 | 30/11/2025 | 04/06/2025 | 01/12/2022 | 179.66 | 179.66
802 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09955) | SM/09955 | 290.16 | 96 | RETROFITTING | 89 | On track | 57 | 14/12/2021 | 31/07/2025 | 04/06/2025 | 09/11/2021 | 166.72 | 166.72
803 | Providing Functional Household Tap Connection for Atmarampur W/S Scheme for Atmarampur,Chingripota and Santoshpur Mouza under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur. (SM/07051) | SM/07051 | 99.79 | 1627 | RETROFITTING | 89 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 31/01/2023 | 99.79 | 93.94
804 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:186 to 190 and 192 and 196 and Adjoining Areas under Budge Budge-I Block (SM/07015) | SM/07015 | 95.42 | 1949 | RETROFITTING | 89 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 14/12/2020 | 95.42 | 92.26
805 | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. (SM/11488) | SM/11488 | 999.64 | 7460 | NEW | 89 | Delayed | 47 | 15/07/2022 | 31/03/2025 | 04/06/2025 | 08/07/2022 | 471.71 | 471.71
806 | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. (SM/12884) | SM/12884 | 179.46 | 0 | AUGMENTATION | 89 | Delayed | 74 | 23/09/2022 | 31/05/2025 | 04/06/2025 | 30/11/2022 | 132.48 | 132.48
807 | Augmentation for providing balance FHTC in Buita Chingripota Nischintipur Rajibpur & Uttar Roypur GP under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/16962) | SM/16962 | 99.8 | 0 | AUGMENTATION | 89 | On track | 68 | 16/03/2023 | 07/11/2025 | 04/06/2025 | 20/10/2023 | 68.11 | 68.11
808 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works (SM/07054) | SM/07054 | 99.29 | 1910 | RETROFITTING | 89 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 31/01/2023 | 99.29 | 97.33
809 | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte (SM/09951) | SM/09951 | 91.19 | 250 | RETROFITTING | 89 | Delayed | 95 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 25/10/2021 | 87.06 | 87.06
810 | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09952) | SM/09952 | 65.43 | 200 | RETROFITTING | 89 | Delayed | 95 | 14/12/2021 | 31/03/2025 | 04/06/2025 | 25/10/2021 | 62.08 | 62.08
811 | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. (SM/11487) | SM/11487 | 792.98 | 2630 | NEW | 89 | On track | 82 | 15/07/2022 | 30/12/2025 | 04/06/2025 | 25/04/2022 | 646.41 | 646.41
812 | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works (SM/07055) | SM/07055 | 99.25 | 1550 | RETROFITTING | 89 | Delayed | 100 | 25/11/2020 | 31/03/2025 | 04/06/2025 | 11/12/2020 | 99.25 | 91.45
813 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:137 to 140 and Adjoining Areas under Budge Budge-I Block (SM/07016) | SM/07016 | 98.72 | 2227 | RETROFITTING | 89 | Delayed | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 14/12/2020 | 98.72 | 90.33
814 | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas (SM/13297) | SM/13297 | 167.2 | 669 | AUGMENTATION | 89 | On track | 88 | 17/10/2022 | 30/06/2025 | 04/06/2025 | 01/12/2022 | 147.73 | 147.73
815 | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09949) | SM/09949 | 100.01 | 200 | RETROFITTING | 89 | On track | 98 | 14/12/2021 | 30/11/2025 | 04/06/2025 | 25/10/2021 | 98.2 | 98.2
816 | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/07750) | SM/07750 | 114.21 | 1827 | RETROFITTING | 90 | Delayed | 77 | 08/01/2021 | 31/05/2025 | 04/06/2025 | 24/12/2020 | 87.85 | 87.85
817 | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South (SM/09505) | SM/09505 | 235.76 | 4562 | RETROFITTING | 90 | Delayed | 89 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 15/02/2022 | 210.48 | 210.48
818 | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi (SM/10532) | SM/10532 | 154.34 | 718 | AUGMENTATION | 90 | Delayed | 61 | 13/04/2022 | 31/05/2025 | 04/06/2025 | 05/04/2023 | 93.52 | 93.52
819 | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore (SM/10520) | SM/10520 | 360.84 | 4362 | AUGMENTATION | 90 | Delayed | 77 | 13/04/2022 | 31/05/2025 | 04/06/2025 | 14/08/2020 | 277.36 | 277.36
820 | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/07752) | SM/07752 | 127.48 | 2151 | RETROFITTING | 90 | Delayed | 92 | 08/01/2021 | 31/05/2025 | 04/06/2025 | 08/10/2020 | 117.86 | 101.96
821 | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/09398) | SM/09398 | 97.07 | 1692 | RETROFITTING | 90 | Delayed | 97 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 20/01/2022 | 94.25 | 94.25
822 | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/09399) | SM/09399 | 209.29 | 4243 | RETROFITTING | 90 | Delayed | 96 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 16/02/2022 | 200.04 | 200.04
823 | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math (SM/10218) | SM/10218 | 489.03 | 8596 | AUGMENTATION | 90 | Delayed | 17 | 24/02/2022 | 31/05/2025 | 04/06/2025 | 04/04/2022 | 84.67 | 84.67
824 | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi (SM/10217) | SM/10217 | 547.24 | 7650 | AUGMENTATION | 90 | Delayed | 12 | 24/02/2022 | 31/05/2025 | 04/06/2025 | 29/12/2022 | 64.28 | 64.28
825 | Retrofitting of Distribution System of Zone-XVII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09396) | SM/09396 | 116.46 | 2049 | RETROFITTING | 90 | Delayed | 11 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 17/05/2023 | 12.62 | 12.62
826 | Retrofitting of Distribution System of Zone-XII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09557) | SM/09557 | 93.7 | 1684 | RETROFITTING | 90 | Delayed | 97 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 10/06/2022 | 90.97 | 90.97
827 | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09769) | SM/09769 | 183.73 | 3541 | RETROFITTING | 90 | Delayed | 74 | 30/11/2021 | 31/05/2025 | 04/06/2025 | 18/08/2022 | 136.49 | 136.49
828 | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/09770) | SM/09770 | 142.98 | 2742 | RETROFITTING | 90 | Delayed | 82 | 30/11/2021 | 31/05/2025 | 04/06/2025 | 17/02/2022 | 117.7 | 117.7
829 | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS (SM/14156) | SM/14156 | 1277.6 | 2770 | NEW | 90 | On track | 40 | 05/01/2023 | 31/12/2025 | 04/06/2025 | 31/01/2023 | 513.32 | 513.32
830 | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/08124) | SM/08124 | 454.88 | 19401 | RETROFITTING | 90 | Delayed | 87 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 19/02/2021 | 395.98 | 395.98
831 | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur (SM/08118) | SM/08118 | 491.98 | 3835 | RETROFITTING | 90 | Delayed | 98 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 31/01/2022 | 481.63 | 481.63
832 | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08119) | SM/08119 | 356.83 | 1329 | RETROFITTING | 90 | Delayed | 90 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 12/05/2021 | 320.37 | 320.21
833 | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/07751) | SM/07751 | 158.44 | 1827 | RETROFITTING | 90 | Delayed | 76 | 08/01/2021 | 31/05/2025 | 04/06/2025 | 13/08/2021 | 120.41 | 120.41
834 | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/07755) | SM/07755 | 127.96 | 2091 | RETROFITTING | 90 | Delayed | 71 | 08/01/2021 | 31/05/2025 | 04/06/2025 | 08/10/2020 | 90.32 | 90.31
835 | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08121) | SM/08121 | 383.26 | 4362 | RETROFITTING | 90 | Delayed | 62 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 19/02/2021 | 237.63 | 237.63
836 | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse (SM/14661) | SM/14661 | 691.87 | 1962 | AUGMENTATION | 90 | Delayed | 27 | 31/01/2023 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 189.11 | 189.11
837 | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/07401) | SM/07401 | 91.79 | 1280 | RETROFITTING | 90 | Delayed | 97 | 29/12/2020 | 31/05/2025 | 04/06/2025 | 08/10/2020 | 89.12 | 80.73
838 | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem (SM/07577) | SM/07577 | 62.28 | 870 | RETROFITTING | 90 | Delayed | 94 | 31/12/2020 | 31/05/2025 | 04/06/2025 | 30/12/2020 | 58.34 | 58.34
839 | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/07578) | SM/07578 | 86.88 | 1351 | RETROFITTING | 90 | Delayed | 97 | 31/12/2020 | 31/05/2025 | 04/06/2025 | 30/12/2020 | 84.35 | 84.35
840 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-I including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divis (SM/09973) | SM/09973 | 197.83 | 3342 | RETROFITTING | 90 | Delayed | 10 | 15/12/2021 | 31/05/2025 | 04/06/2025 | 27/07/2022 | 20.59 | 20.59
841 | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09397) | SM/09397 | 153.42 | 3000 | RETROFITTING | 90 | Delayed | 95 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 17/02/2022 | 145.42 | 145.42
842 | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09400) | SM/09400 | 229.18 | 4679 | RETROFITTING | 90 | Delayed | 28 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 12/07/2022 | 65 | 65
843 | Retrofitting of Distribution System of Zone-III, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09771) | SM/09771 | 131.44 | 2742 | RETROFITTING | 90 | Delayed | 46 | 30/11/2021 | 31/05/2025 | 04/06/2025 | 17/02/2022 | 60.03 | 60.03
844 | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/13811) | SM/13811 | 851.09 | 2218 | AUGMENTATION | 90 | On track | 49 | 22/11/2022 | 31/12/2025 | 04/06/2025 | 18/02/2021 | 413.51 | 413.51
845 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15058) | SM/15058 | 349.37 | 1013 | AUGMENTATION | 90 | Delayed | 44 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 16/12/2021 | 152.77 | 152.77
846 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVI, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. (SM/15480) | SM/15480 | 38.02 | 102 | AUGMENTATION | 90 | On track | 57 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 20/01/2022 | 21.5 | 21.5
847 | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15759) | SM/15759 | 858.13 | 1435 | AUGMENTATION | 90 | On track | 38 | 20/02/2023 | 31/12/2025 | 04/06/2025 | 10/03/2023 | 325.48 | 325.48
848 | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math (SM/08120) | SM/08120 | 389.87 | 1666 | RETROFITTING | 90 | Delayed | 89 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 24/02/2021 | 348.07 | 295.07
849 | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur (SM/08122) | SM/08122 | 357.03 | 1203 | RETROFITTING | 90 | Delayed | 82 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 12/05/2021 | 291.64 | 291.64
850 | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa (SM/09425) | SM/09425 | 286.94 | 5866 | RETROFITTING | 90 | Delayed | 96 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 07/04/2022 | 275.97 | 275.97
851 | Retrofitting of Distribution System of Zone-VIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09555) | SM/09555 | 175.13 | 2196 | RETROFITTING | 90 | Delayed | 80 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 07/07/2022 | 140.26 | 140.26
852 | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J (SM/09512) | SM/09512 | 102.7 | 1957 | RETROFITTING | 90 | Delayed | 97 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 22/11/2021 | 99.39 | 99.39
853 | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM (SM/09513) | SM/09513 | 106.53 | 1573 | RETROFITTING | 90 | Delayed | 70 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 22/11/2021 | 74.79 | 74.79
854 | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) (SM/09515) | SM/09515 | 125.82 | 2491 | RETROFITTING | 90 | Delayed | 88 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 31/01/2022 | 111.26 | 111.26
855 | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09556) | SM/09556 | 21.75 | 252 | RETROFITTING | 90 | Delayed | 80 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 20/01/2022 | 17.47 | 17.37
856 | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore (SM/10534) | SM/10534 | 208.5 | 1769 | AUGMENTATION | 90 | Delayed | 6 | 13/04/2022 | 31/05/2025 | 04/06/2025 | 23/02/2023 | 13.28 | 13.28
857 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi (SM/09974) | SM/09974 | 164.33 | 2745 | RETROFITTING | 90 | Delayed | 12 | 15/12/2021 | 31/05/2025 | 04/06/2025 | 15/09/2022 | 19.15 | 19.15
858 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/13575) | SM/13575 | 53.09 | 124 | AUGMENTATION | 90 | On track | 96 | 09/11/2022 | 31/07/2025 | 04/06/2025 | 02/03/2023 | 50.93 | 50.93
859 | SANGUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/14545) | SM/14545 | 1250.69 | 2506 | AUGMENTATION | 90 | Delayed | 40 | 30/01/2023 | 31/03/2025 | 04/06/2025 | 20/02/2023 | 497.97 | 497.07
860 | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone VI including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South (SM/09506) | SM/09506 | 97.92 | 1833 | RETROFITTING | 90 | Delayed | 93 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 22/11/2021 | 91.01 | 91.01
861 | Retrofitting of Distribution system of Zone IX Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08123) | SM/08123 | 271.61 | 624 | RETROFITTING | 90 | Delayed | 95 | 19/02/2021 | 31/05/2025 | 04/06/2025 | 24/02/2021 | 258.99 | 249.76
862 | Retrofitting of Distribution System of Zone-VIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem (SM/07753) | SM/07753 | 145.53 | 2520 | RETROFITTING | 90 | Delayed | 96 | 08/01/2021 | 31/05/2025 | 04/06/2025 | 12/02/2021 | 140.35 | 140.35
863 | Retrofitting of Distribution System of Zone-IV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/09401) | SM/09401 | 274.75 | 5399 | RETROFITTING | 90 | Delayed | 90 | 17/11/2021 | 31/05/2025 | 04/06/2025 | 11/04/2022 | 248.04 | 248.04
864 | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S (SM/09507) | SM/09507 | 158.51 | 3174 | RETROFITTING | 90 | Delayed | 25 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 04/01/2022 | 38.95 | 38.95
865 | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc (SM/09508) | SM/09508 | 425.04 | 3722 | RETROFITTING | 90 | Delayed | 6 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 07/07/2022 | 23.55 | 23.55
866 | Retrofitting of Distribution System of Zone-VII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Fal (SM/09510) | SM/09510 | 323.42 | 3042 | RETROFITTING | 90 | Delayed | 97 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 12/05/2021 | 315.29 | 315.29
867 | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & (SM/09514) | SM/09514 | 197.25 | 1840 | RETROFITTING | 90 | Delayed | 91 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 22/11/2021 | 179.29 | 179.29
868 | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo (SM/09558) | SM/09558 | 253.22 | 3983 | RETROFITTING | 90 | Delayed | 38 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 26/02/2020 | 95.14 | 95.14
869 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI (SM/15479) | SM/15479 | 89.53 | 275 | AUGMENTATION | 90 | On track | 61 | 04/02/2023 | 31/12/2025 | 04/06/2025 | 30/11/2021 | 55.06 | 55.06
870 | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal (SM/09511) | SM/09511 | 131.93 | 1475 | RETROFITTING | 90 | Delayed | 84 | 19/11/2021 | 31/05/2025 | 04/06/2025 | 31/01/2022 | 110.64 | 110.63
871 | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) (SM/10197) | SM/10197 | 106.68 | 0 | SUPPORT-WQMSP | 90 | Delayed | 0 | 14/01/2022 | 31/03/2024 | 13/12/2023 | 22/09/2021 | 0 | 0
872 | Improvement of W/S by interconnection from existing big dia TW and laying distribution system with CIDF, UPVC pipes including providing FHTC by retrofitting of scheme Improvement of WS [Phase-III] in Baruipur and Mograhat-II Block of Sankarpur-II GP withi (SM/08182) | SM/08182 | 200.38 | 1497 | RETROFITTING | 92 | Delayed | 92 | 09/02/2021 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 184.05 | 184.05
873 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- (SM/09470) | SM/09470 | 107.52 | 1505 | RETROFITTING | 92 | Delayed | 56 | 19/11/2021 | 31/03/2025 | 04/06/2025 | 23/02/2021 | 60.45 | 60.45
874 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE (SM/18223) | SM/18223 | 2958.02 | 0 | AUGMENTATION | 92 | On track | 82 | 27/04/2023 | 31/08/2025 | 04/06/2025 | 13/07/2022 | 2423.29 | 2423.29
875 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including (SM/07590) | SM/07590 | 74.27 | 2329 | RETROFITTING | 92 | Delayed | 91 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 67.55 | 67.55
876 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-IX, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D (SM/15481) | SM/15481 | 196.11 | 711 | AUGMENTATION | 92 | Delayed | 28 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 15/05/2023 | 55.87 | 55.87
877 | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS (SM/16027) | SM/16027 | 802.18 | 2540 | NEW | 92 | On track | 61 | 22/02/2023 | 31/10/2025 | 04/06/2025 | 19/04/2023 | 486.38 | 486.38
878 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone (SM/09469) | SM/09469 | 148.34 | 2297 | RETROFITTING | 92 | Delayed | 47 | 19/11/2021 | 31/03/2025 | 04/06/2025 | 23/02/2021 | 69.35 | 68.35
879 | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. (SM/13974) | SM/13974 | 798.36 | 1535 | NEW | 93 | On track | 55 | 01/12/2022 | 31/12/2025 | 04/06/2025 | 20/07/2022 | 436.41 | 436.41
880 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-III), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS (SM/12747) | SM/12747 | 43.19 | 105 | AUGMENTATION | 93 | Delayed | 97 | 20/09/2022 | 31/03/2025 | 04/06/2025 | 02/03/2023 | 41.88 | 41.88
881 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-II) W/S (SM/07415) | SM/07415 | 96.04 | 1515 | RETROFITTING | 94 | Delayed | 94 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 90.16 | 60.16
882 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-II) W/S (SM/07414) | SM/07414 | 99.77 | 1600 | RETROFITTING | 94 | Delayed | 93 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 92.87 | 92.87
883 | AUGMENTATION OF GROUND WATER BASED NAMKHANA PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT (SM/10535) | SM/10535 | 838.4 | 3149 | AUGMENTATION | 94 | Delayed | 92 | 13/04/2022 | 31/03/2025 | 04/06/2025 | 01/09/2021 | 770.54 | 770.54
884 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10114) | SM/10114 | 798.04 | 0 | SCHOOL | 95 | Delayed | 0 | 08/02/2022 | 31/03/2025 | 04/06/2025 | 12/07/2022 | 0 | 0
885 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH (SM/10118) | SM/10118 | 967.94 | 0 | SCHOOL | 95 | Delayed | 0 | 08/02/2022 | 31/03/2025 | 04/06/2025 | 31/03/2022 | 0 | 0
886 | AUGMENTATION OF GROUND WATER BASED MRITYUNJAYNAGAR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/11698) | SM/11698 | 665.26 | 632 | AUGMENTATION | 95 | On track | 59 | 29/07/2022 | 31/08/2025 | 04/06/2025 | 07/07/2022 | 390.64 | 390.64
887 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p (SM/16189) | SM/16189 | 1691.01 | 0 | AUGMENTATION | 95 | On track | 50 | 20/02/2023 | 31/08/2025 | 04/06/2025 | 13/07/2022 | 844.02 | 844.02
888 | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10113) | SM/10113 | 934.61 | 0 | SCHOOL | 95 | On track | 0 | 08/02/2022 | 30/06/2025 | 04/06/2025 | 12/07/2022 | 0 | 0
889 | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. (SM/14988) | SM/14988 | 523.55 | 1517 | NEW | 95 | Delayed | 59 | 04/02/2023 | 31/03/2025 | 04/06/2025 | 08/02/2023 | 306.64 | 306.64
890 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- IX AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 (SM/14464) | SM/14464 | 395.19 | 1535 | AUGMENTATION | 95 | Delayed | 70 | 20/01/2023 | 31/03/2025 | 04/06/2025 | 04/02/2023 | 276.21 | 276.21
891 | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas (SM/09020) | SM/09020 | 650.96 | 0 | DISASTER | 95 | Delayed | 0 | 30/10/2021 | 31/03/2025 | 04/06/2025 | 08/10/2020 | 0 | 0
892 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10117) | SM/10117 | 663.13 | 0 | SCHOOL | 95 | On track | 0 | 08/02/2022 | 31/07/2025 | 04/06/2025 | 12/07/2022 | 0 | 0
893 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10116) | SM/10116 | 879.72 | 0 | SCHOOL | 95 | On track | 0 | 08/02/2022 | 30/06/2025 | 04/06/2025 | 31/03/2022 | 0 | 0
894 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10119) | SM/10119 | 546.43 | 0 | SCHOOL | 95 | Delayed | 0 | 08/02/2022 | 31/03/2025 | 04/06/2025 | 12/07/2022 | 0 | 0
895 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15494) | SM/15494 | 147.31 | 416 | AUGMENTATION | 95 | On track | 72 | 15/02/2023 | 31/12/2025 | 04/06/2025 | 12/02/2021 | 106.36 | 106.36
896 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10115) | SM/10115 | 762.86 | 0 | SCHOOL | 95 | Delayed | 0 | 08/02/2022 | 31/03/2025 | 04/06/2025 | 31/03/2022 | 0 | 0
897 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 (SM/14680) | SM/14680 | 3361.02 | 8074 | AUGMENTATION | 95 | On track | 57 | 31/01/2023 | 31/12/2025 | 04/06/2025 | 13/09/2022 | 1930.03 | 1930.03
898 | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. (SM/08806) | SM/08806 | 172.36 | 2721 | RETROFITTING | 96 | On track | 95 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 01/11/2022 | 163.78 | 163.78
899 | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) (SM/08794) | SM/08794 | 208.29 | 3972 | RETROFITTING | 96 | On track | 28 | 13/09/2021 | 31/03/2025 | 04/06/2025 | 06/09/2021 | 57.32 | 57.32
900 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp (SM/07762) | SM/07762 | 280.36 | 4308 | RETROFITTING | 96 | On track | 93 | 08/01/2021 | 31/12/2025 | 04/06/2025 | 18/02/2021 | 261.1 | 261.1
901 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15493) | SM/15493 | 219.73 | 660 | AUGMENTATION | 97 | On track | 97 | 15/02/2023 | 31/07/2025 | 04/06/2025 | 10/06/2022 | 213.02 | 213.02
902 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA (SM/13952) | SM/13952 | 334.04 | 2180 | AUGMENTATION | 97 | On track | 97 | 01/12/2022 | 31/07/2025 | 04/06/2025 | 15/03/2022 | 324.31 | 324.31
903 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S (SM/07761) | SM/07761 | 185.64 | 2937 | RETROFITTING | 98 | On track | 98 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 14/10/2020 | 181.03 | 180.84
904 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi (SM/09010) | SM/09010 | 102.43 | 1888 | RETROFITTING | 98 | On track | 97 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 06/01/2021 | 99.84 | 99.84
905 | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/11747) | SM/11747 | 748.92 | 1690 | AUGMENTATION | 98 | On track | 87 | 03/08/2022 | 31/08/2025 | 04/06/2025 | 05/12/2018 | 653.55 | 653.55
906 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. (SM/15496) | SM/15496 | 220.17 | 860 | AUGMENTATION | 98 | Delayed | 97 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 11/04/2022 | 213.75 | 213.75
907 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-VII, MATHURAPUR PIPED WATER SUPPLY SCHEME, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE (SM/15507) | SM/15507 | 72.1 | 344 | AUGMENTATION | 98 | Delayed | 97 | 15/02/2023 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 70 | 70
908 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including (SM/08629) | SM/08629 | 111.49 | 1845 | RETROFITTING | 98 | On track | 80 | 31/05/2021 | 30/06/2025 | 04/06/2025 | 09/11/2021 | 88.74 | 88.74
909 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst (SM/12574) | SM/12574 | 45.17 | 121 | NEW | 98 | On track | 82 | 15/09/2022 | 31/03/2025 | 04/06/2025 | 10/11/2022 | 36.93 | 36.93
910 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc (SM/07589) | SM/07589 | 43.41 | 1160 | RETROFITTING | 98 | On track | 59 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 10/09/2021 | 25.78 | 25.78
911 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on (SM/08630) | SM/08630 | 166.84 | 2079 | RETROFITTING | 98 | On track | 97 | 31/05/2021 | 31/08/2025 | 04/06/2025 | 05/05/2022 | 161.98 | 161.98
912 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S (SM/07412) | SM/07412 | 82.69 | 4374 | RETROFITTING | 98 | On track | 83 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 68.8 | 68.8
913 | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09435) | SM/09435 | 252 | 680 | AUGMENTATION | 98 | On track | 39 | 18/11/2021 | 31/03/2025 | 04/06/2025 | 03/12/2020 | 97.43 | 97.43
914 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche (SM/07592) | SM/07592 | 95.32 | 1675 | RETROFITTING | 98 | On track | 97 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 20/05/2022 | 92.55 | 92.55
915 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o (SM/09095) | SM/09095 | 261.46 | 4630 | RETROFITTING | 98 | On track | 97 | 29/10/2021 | 31/03/2025 | 04/06/2025 | 29/03/2022 | 253.69 | 253.69
916 | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) (SM/09467) | SM/09467 | 44.84 | 1416 | RETROFITTING | 99 | On track | 98 | 19/11/2021 | 31/03/2025 | 04/06/2025 | 20/01/2022 | 44.16 | 44.16
917 | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. (SM/08986) | SM/08986 | 66.7 | 0 | DISASTER | 99 | On track | 0 | 29/10/2021 | 13/03/2025 | 04/06/2025 | 21/02/2022 | 0 | 0
918 | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. (SM/09727) | SM/09727 | 399.53 | 0 | DISASTER | 99 | On track | 0 | 26/11/2021 | 13/03/2025 | 04/06/2025 | 22/05/2021 | 0 | 0
919 | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. (SM/09736) | SM/09736 | 2084.46 | 0 | DISASTER | 99 | On track | 0 | 29/11/2021 | 13/03/2025 | 04/06/2025 | 01/06/2020 | 0 | 0
920 | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' (SM/09436) | SM/09436 | 796.11 | 0 | DISASTER | 99 | On track | 0 | 18/11/2021 | 13/03/2025 | 04/06/2025 | 22/05/2021 | 0 | 0
921 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme includ (SM/07400) | SM/07400 | 72.43 | 1774 | RETROFITTING | 100 | 100% Physical | 85 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 61.46 | 61.46
922 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including (SM/07757) | SM/07757 | 135.9 | 1447 | RETROFITTING | 100 | 100% Physical | 37 | 08/01/2021 | 31/03/2025 | 04/06/2025 | 19/02/2021 | 49.87 | 49.87
923 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc (SM/07759) | SM/07759 | 101.4 | 987 | RETROFITTING | 100 | 100% Physical | 79 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 26/09/2020 | 80.51 | 80.3
924 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year (SM/09096) | SM/09096 | 165.49 | 2857 | RETROFITTING | 100 | 100% Physical | 45 | 29/10/2021 | 31/03/2025 | 04/06/2025 | 24/02/2022 | 73.69 | 73.69
925 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ (SM/07397) | SM/07397 | 93.47 | 1016 | RETROFITTING | 100 | 100% Physical | 81 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 12/10/2020 | 75.51 | 75.48
926 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bansra Water Supply Scheme (SM/08028) | SM/08028 | 352.06 | 6607 | RETROFITTING | 100 | 100% Physical | 59 | 29/01/2021 | 31/03/2025 | 04/06/2025 | 13/07/2021 | 208.81 | 208.81
927 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu (SM/07399) | SM/07399 | 58.55 | 1557 | RETROFITTING | 100 | 100% Physical | 68 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 39.75 | 28.38
928 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche (SM/07627) | SM/07627 | 204.47 | 3820 | RETROFITTING | 100 | 100% Physical | 94 | 07/01/2021 | 31/10/2025 | 04/06/2025 | 08/02/2021 | 192.23 | 192.23
929 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ (SM/07402) | SM/07402 | 92.72 | 1276 | RETROFITTING | 100 | 100% Physical | 97 | 29/12/2020 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 90.02 | 83.7
930 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ (SM/07584) | SM/07584 | 80.41 | 1613 | RETROFITTING | 100 | 100% Physical | 100 | 31/12/2020 | 31/12/2025 | 04/06/2025 | 12/10/2020 | 80.41 | 80.41
931 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch (SM/07628) | SM/07628 | 169.04 | 2601 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 31/08/2025 | 04/06/2025 | 07/07/2021 | 164.11 | 164.11
932 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat (SM/07634) | SM/07634 | 175.16 | 3369 | RETROFITTING | 100 | 100% Physical | 91 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 158.68 | 158.68
933 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche (SM/07597) | SM/07597 | 87.3 | 1323 | RETROFITTING | 100 | 100% Physical | 74 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 65 | 17.92
934 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply (SM/07642) | SM/07642 | 117.22 | 2122 | RETROFITTING | 100 | 100% Physical | 95 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 01/10/2020 | 111.07 | 110.74
935 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jyotishpur Water Supply S (SM/07643) | SM/07643 | 117.77 | 2153 | RETROFITTING | 100 | 100% Physical | 73 | 07/01/2021 | 31/12/2025 | 04/06/2025 | 01/10/2020 | 86.25 | 86.25
936 | Retrofitting of distribution System For Nischintipur W/S Scheme for Nischintipur Mouza near Head Work Site and Adjoining Areas under Budge Budge-I Block (SM/07018) | SM/07018 | 94.23 | 1500 | RETROFITTING | 100 | 100% Physical | 100 | 18/11/2020 | 31/03/2025 | 04/06/2025 | 08/12/2020 | 94.23 | 80.02
937 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ (SM/07587) | SM/07587 | 79.53 | 1074 | RETROFITTING | 100 | 100% Physical | 48 | 31/12/2020 | 31/12/2025 | 04/06/2025 | 12/10/2020 | 38.49 | 38.49
938 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Singheswar Water Supply S (SM/07594) | SM/07594 | 72.82 | 1349 | RETROFITTING | 100 | 100% Physical | 89 | 31/12/2020 | 31/05/2025 | 04/06/2025 | 19/02/2021 | 64.86 | 64.86
939 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Uttar Angadberia Water (SM/07637) | SM/07637 | 114.83 | 2101 | RETROFITTING | 100 | 100% Physical | 68 | 07/01/2021 | 31/12/2025 | 04/06/2025 | 18/02/2021 | 78.13 | 78.13
940 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme (SM/07754) | SM/07754 | 150.06 | 1417 | RETROFITTING | 100 | 100% Physical | 55 | 08/01/2021 | 30/09/2025 | 04/06/2025 | 23/02/2021 | 82.92 | 82.92
941 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year (SM/08637) | SM/08637 | 157.43 | 2953 | RETROFITTING | 100 | 100% Physical | 70 | 27/05/2021 | 31/12/2025 | 04/06/2025 | 27/07/2021 | 109.55 | 154.7
942 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Luxbagan Water Supply Sche (SM/07595) | SM/07595 | 72.33 | 1119 | RETROFITTING | 100 | 100% Physical | 97 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 19/02/2021 | 70.23 | 70.23
943 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Koaberia W/S Scheme including (SM/07579) | SM/07579 | 82.67 | 1071 | RETROFITTING | 100 | 100% Physical | 66 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 08/02/2021 | 54.74 | 54.52
944 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ (SM/07585) | SM/07585 | 61.06 | 1888 | RETROFITTING | 100 | 100% Physical | 88 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 07/07/2021 | 53.84 | 53.84
945 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl (SM/07641) | SM/07641 | 207.07 | 3908 | RETROFITTING | 100 | 100% Physical | 74 | 07/01/2021 | 31/12/2025 | 04/06/2025 | 12/10/2020 | 152.47 | 151.85
946 | ADDITIONAL WORK FOR RETROFITTING OF DISTRIBUTION SYSTEM FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ADDITIONAL HOUSEHOLD (1219 NOS.) IN EXCESS OF IMIS IN CONNECTION FOR LOT NO. - 126 WATER SUPPLY SCHEME INCLUDING ONE YEAR OPERATION AND MAI (SM/10560) | SM/10560 | 73.48 | 1219 | AUGMENTATION | 100 | 100% Physical | 15 | 18/04/2022 | 31/10/2025 | 04/06/2025 | 08/04/2022 | 11.34 | 11.34
947 | AUGMENTATION FOR GROUND WATER BASED RADHAKRISHNAPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/13972) | SM/13972 | 688.41 | 806 | AUGMENTATION | 100 | 100% Physical | 34 | 01/12/2022 | 30/09/2025 | 04/06/2025 | 05/12/2018 | 231.26 | 231.26
948 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including (SM/07576) | SM/07576 | 88.57 | 1104 | RETROFITTING | 100 | 100% Physical | 70 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 19/08/2020 | 61.62 | 60.68
949 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ (SM/07586) | SM/07586 | 61.02 | 877 | RETROFITTING | 100 | 100% Physical | 32 | 31/12/2020 | 31/03/2025 | 04/06/2025 | 19/02/2021 | 19.32 | 19.32
950 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bhaleya Water Supply Sch (SM/07598) | SM/07598 | 92.37 | 1641 | RETROFITTING | 100 | 100% Physical | 81 | 31/12/2020 | 31/12/2025 | 04/06/2025 | 28/08/2020 | 74.66 | 74.66
951 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y (SM/09094) | SM/09094 | 95.53 | 1513 | RETROFITTING | 100 | 100% Physical | 86 | 29/10/2021 | 31/12/2025 | 04/06/2025 | 27/08/2020 | 82.01 | 82.01
952 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc (SM/07763) | SM/07763 | 119.81 | 1745 | RETROFITTING | 100 | 100% Physical | 96 | 08/01/2021 | 31/12/2025 | 04/06/2025 | 08/01/2021 | 115.42 | 115.42
953 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in (SM/07626) | SM/07626 | 225.98 | 3074 | RETROFITTING | 100 | 100% Physical | 75 | 07/01/2021 | 30/09/2025 | 04/06/2025 | 12/02/2021 | 169.03 | 169.03
954 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayanpur Water Supply Sc (SM/07632) | SM/07632 | 126.68 | 2005 | RETROFITTING | 100 | 100% Physical | 69 | 07/01/2021 | 31/03/2025 | 04/06/2025 | 18/02/2021 | 87.49 | 87.49
955 | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. (SM/13512) | SM/13512 | 797.02 | 1406 | AUGMENTATION | 100 | 100% Physical | 64 | 02/11/2022 | 31/05/2025 | 04/06/2025 | 27/02/2023 | 507.9 | 507.9
956 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc (SM/07644) | SM/07644 | 147.9 | 2754 | RETROFITTING | 100 | 100% Physical | 35 | 07/01/2021 | 31/12/2025 | 04/06/2025 | 12/10/2020 | 52.48 | 51.98
Total |  |  | 644261.26 | 2042953 | [8 empty] | 230495.59 | 229731.32