## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kamarchak village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou (SM/12758) | SM/12758 | 43.88 | 91 | NEW | 0 | WO no issued | 1 | 22/09/2022 | 30/06/2025 | 03/04/2025 | 13/03/2023 | 0.56 | 0.56
2 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Chak Ruplaskar village of Ramkishore Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system (SM/13961) | SM/13961 | 43.37 | 79 | NEW | 0 | WO no issued | 0 | 01/12/2022 | 30/06/2025 | 03/04/2025 | 15/03/2023 | 0 | 0
3 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Ramchandrapur PWSS at Sonarpur Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18857) | SM/18857 | 11.11 | 0 | SOLARISATION | 0 | WO no issued | 0 | 03/10/2023 | 17/04/2025 | 03/04/2025 |  | 0 | 0
4 | Ground water based DIHI KASLAS piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas (SM/18568) | SM/18568 | 1184.22 | 3846 | AUGMENTATION | 0 | WO no issued | 15 | 31/07/2023 | 30/12/2025 | 03/04/2025 | 11/08/2023 | 176.16 | 168.71
5 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering at Sitakundu (Zone-I) PWSS at Baruipur Block under South 24 Pgs Mechanical Division, PHE Dte. (SM/18742) | SM/18742 | 11.11 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/08/2023 | 17/04/2025 | 03/04/2025 | 22/08/2024 | 0 | 0
6 | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani (SM/18743) | SM/18743 | 44.44 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/08/2023 | 17/04/2025 | 03/04/2025 | 08/02/2024 | 0 | 0
7 | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08800) | SM/08800 | 100.52 | 2758 | RETROFITTING | 4 | WO no issued | 21 | 13/09/2021 | 13/09/2025 | 03/04/2025 | 25/07/2024 | 21.45 | 16.99
8 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sumatinagar Water Supply Scheme including one y (SM/09394) | SM/09394 | 246.56 | 1282 | RETROFITTING | 5 | WO no issued | 4 | 17/11/2021 | 30/09/2025 | 03/04/2025 | 13/11/2024 | 8.93 | 8.93
9 | Ground Water Based RAMKRISHNAPUR Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar - I Block under South 24 Parganas W/S Division - I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Ar (SM/18570) | SM/18570 | 1251.08 | 3080 | AUGMENTATION | 6 | WO no issued | 2 | 31/07/2023 | 30/12/2025 | 03/04/2025 | 11/08/2023 | 21.77 | 21.77
10 | Retrofitting for Providing FHTC of Ground Water Based Ramchandranagar Water Supply Scheme (Phase - A) (SM/09466) | SM/09466 | 60.25 | 2052 | RETROFITTING | 7 | WO no issued | 21 | 19/11/2021 | 30/09/2023 | 12/06/2023 | 19/10/2022 | 12.64 | 12.64
11 | Providing 100% FHTC in Zone-I at Bainch Beria Srichanda mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11265) | SM/11265 | 469.65 | 5799 | AUGMENTATION | 10 | WO no issued | 8 | 23/06/2022 | 31/03/2025 | 03/04/2025 | 11/05/2023 | 35.72 | 35.72
12 | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC)(PART-B) (SM/16195) | SM/16195 | 817.46 | 1797 | AUGMENTATION | 10 | WO no issued | 15 | 24/02/2023 | 31/03/2025 | 03/04/2025 | 24/07/2023 | 121.62 | 121.62
13 | Retrofitting for Providing FHTC at Ground Water Based Companir Char & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08802) | SM/08802 | 57.2 | 1508 | RETROFITTING | 17 | WO no issued | 15 | 13/09/2021 | 30/09/2025 | 03/04/2025 | 07/07/2022 | 8.64 | 8.64
14 | Retrofitting for Providing FHTC at Ground Water Based Mansadwip & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08807) | SM/08807 | 78.11 | 2004 | RETROFITTING | 17 | WO no issued | 16 | 13/09/2021 | 30/09/2025 | 03/04/2025 |  | 12.34 | 12.34
15 | Proposed Ground water based BANTRA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/18498) | SM/18498 | 1158.38 | 3046 | AUGMENTATION | 17 | WO no issued | 15 | 26/07/2023 | 31/12/2025 | 03/04/2025 | 03/08/2023 | 178.67 | 178.67
16 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl (SM/07410) | SM/07410 | 49.5 | 880 | RETROFITTING | 18 | WO no issued | 11 | 29/12/2020 | 30/09/2025 | 03/04/2025 |  | 5.41 | 5.41
17 | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af (SM/12804) | SM/12804 | 693.66 | 1672 | AUGMENTATION | 20 | WO no issued | 5 | 21/09/2022 | 31/03/2025 | 03/04/2025 | 20/05/2022 | 32.71 | 32.71
18 | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15043) | SM/15043 | 666.83 | 1544 | AUGMENTATION | 22 | WO no issued | 21 | 03/02/2023 | 31/12/2025 | 03/04/2025 | 18/04/2023 | 142.72 | 142.72
19 | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. (SM/13784) | SM/13784 | 835.96 | 1749 | AUGMENTATION | 24 | WO no issued | 13 | 18/11/2022 | 31/05/2025 | 03/04/2025 | 01/11/2022 | 109.9 | 109.9
20 | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08793) | SM/08793 | 66.55 | 1753 | RETROFITTING | 25 | WO no issued | 24 | 13/09/2021 | 30/09/2025 | 03/04/2025 |  | 15.78 | 15.68
21 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II at RAJBALLABHPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. (SM/18707) | SM/18707 | 1438.58 | 0 | AUGMENTATION | 25 | WO no issued | 23 | 04/08/2023 | 31/12/2025 | 03/04/2025 | 10/08/2023 | 335.08 | 335.08
22 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. (SM/15954) | SM/15954 | 435.54 | 1196 | AUGMENTATION | 28 | WO no issued | 13 | 22/02/2023 | 31/03/2025 | 03/04/2025 | 26/10/2021 | 57.27 | 57.27
23 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl (SM/07760) | SM/07760 | 264.49 | 3867 | RETROFITTING | 29 | WO no issued | 28 | 08/01/2021 | 30/09/2025 | 03/04/2025 | 08/02/2021 | 73.77 | 73.77
24 | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS (SM/11877) | SM/11877 | 803.64 | 2362 | NEW | 30 | WO no issued | 32 | 17/08/2022 | 31/12/2025 | 03/04/2025 | 18/08/2022 | 257.24 | 253.1
25 | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. (SM/12801) | SM/12801 | 715.64 | 1785 | AUGMENTATION | 30 | WO no issued | 16 | 21/09/2022 | 30/09/2025 | 03/04/2025 | 20/05/2022 | 113.48 | 113.48
26 | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. (SM/12802) | SM/12802 | 649.12 | 1615 | AUGMENTATION | 30 | WO no issued | 1 | 21/09/2022 | 31/03/2025 | 03/04/2025 | 20/05/2022 | 8.49 | 8.49
27 | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar (SM/15867) | SM/15867 | 482.09 | 682 | AUGMENTATION | 30 | WO no issued | 7 | 20/02/2023 | 31/03/2025 | 03/04/2025 | 15/03/2023 | 33.33 | 29.75
28 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15972) | SM/15972 | 637.96 | 951 | AUGMENTATION | 30 | WO no issued | 39 | 22/02/2023 | 31/12/2025 | 03/04/2025 | 13/03/2023 | 249.38 | 249.38
29 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A (SM/18380) | SM/18380 | 1622.84 | 1853 | AUGMENTATION | 30 | WO no issued | 13 | 11/07/2023 | 31/12/2025 | 03/04/2025 | 04/08/2023 | 212.46 | 211.98
30 | Retrofitting for Providing FHTC of Ground Water Based Nebutala Water Supply Scheme (Phase - A) (SM/09465) | SM/09465 | 30.88 | 820 | RETROFITTING | 30 | WO no issued | 16 | 19/11/2021 | 31/03/2025 | 03/04/2025 |  | 5.05 | 5.05
31 | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14861) | SM/14861 | 983.21 | 2497 | AUGMENTATION | 33 | WO no issued | 23 | 03/02/2023 | 31/03/2025 | 03/04/2025 | 28/02/2023 | 225.54 | 225.54
32 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SURENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13799) | SM/13799 | 670.02 | 1810 | NEW | 34 | WO no issued | 32 | 22/11/2022 | 30/09/2025 | 03/04/2025 | 01/08/2022 | 215.53 | 215.53
33 | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/18500) | SM/18500 | 1193.59 | 2549 | AUGMENTATION | 35 | WO no issued | 12 | 26/07/2023 | 02/11/2025 | 03/04/2025 | 11/08/2023 | 147.03 | 147.03
34 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS (SM/18674) | SM/18674 | 4858.69 | 9792 | AUGMENTATION | 37 | WO no issued | 37 | 04/08/2023 | 31/12/2025 | 03/04/2025 | 07/08/2023 | 1795.96 | 1787.41
35 | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of (SM/15864) | SM/15864 | 577.52 | 1424 | AUGMENTATION | 39 | WO no issued | 15 | 20/02/2023 | 30/11/2025 | 03/04/2025 | 17/03/2023 | 85.43 | 85.43
36 | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/14986) | SM/14986 | 909.79 | 1197 | AUGMENTATION | 40 | WO no issued | 22 | 04/02/2023 | 31/12/2025 | 03/04/2025 | 16/03/2023 | 198.08 | 198.08
37 | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan (SM/16930) | SM/16930 | 523.27 | 1238 | AUGMENTATION | 40 | WO no issued | 29 | 16/03/2023 | 31/03/2025 | 03/04/2025 | 27/01/2022 | 151.98 | 149.68
38 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dt (SM/18219) | SM/18219 | 3818.38 | 0 | AUGMENTATION | 40 | WO no issued | 54 | 27/04/2023 | 30/11/2025 | 03/04/2025 | 14/01/2022 | 2073.55 | 2073.55
39 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea (SM/09358) | SM/09358 | 383.9 | 1655 | RETROFITTING | 41 | WO no issued | 39 | 12/11/2021 | 30/09/2025 | 03/04/2025 | 04/04/2022 | 151.22 | 151.22
40 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-I OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - (SM/14476) | SM/14476 | 469.18 | 3240 | AUGMENTATION | 45 | WO no issued | 23 | 20/01/2023 | 31/03/2025 | 03/04/2025 | 04/02/2023 | 106.34 | 106.34
41 | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/17225) | SM/17225 | 233.48 | 700 | AUGMENTATION | 45 | WO no issued | 23 | 15/03/2023 | 31/12/2025 | 03/04/2025 | 13/06/2023 | 54.14 | 54.14
42 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o (SM/09075) | SM/09075 | 125.25 | 1133 | RETROFITTING | 45 | WO no issued | 44 | 29/10/2021 | 30/09/2025 | 03/04/2025 | 25/02/2022 | 54.89 | 44.89
43 | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11780) | SM/11780 | 759.14 | 1815 | AUGMENTATION | 47 | WO no issued | 34 | 02/08/2022 | 31/03/2025 | 03/04/2025 | 07/09/2022 | 258.2 | 248.09
44 | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI (SM/15503) | SM/15503 | 324.17 | 550 | AUGMENTATION | 47 | WO no issued | 65 | 15/02/2023 | 31/12/2025 | 03/04/2025 | 04/04/2023 | 211.31 | 201.38
45 | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. (SM/11277) | SM/11277 | 813.74 | 1909 | NEW | 49 | WO no issued | 72 | 24/06/2022 | 31/03/2025 | 03/04/2025 | 22/09/2022 | 587.03 | 587.03
46 | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE (SM/11253) | SM/11253 | 585.88 | 6789 | NEW | 50 | WO no issued | 29 | 22/06/2022 | 31/03/2025 | 03/04/2025 | 01/11/2022 | 172.32 | 172.32
47 | AUGMENTATION OF GROUND WATER BASED RAKHALPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS (SM/14987) | SM/14987 | 830.49 | 815 | AUGMENTATION | 50 | WO no issued | 7 | 04/02/2023 | 31/12/2025 | 03/04/2025 | 29/12/2022 | 56 | 49.77
48 | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12209) | SM/12209 | 715.25 | 1057 | AUGMENTATION | 50 | WO no issued | 18 | 06/09/2022 | 30/06/2025 | 03/04/2025 | 16/02/2023 | 129.31 | 129.31
49 | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS (SM/18675) | SM/18675 | 1014.14 | 1981 | AUGMENTATION | 50 | WO no issued | 15 | 04/08/2023 | 31/12/2025 | 03/04/2025 | 07/08/2023 | 153.03 | 153.03
50 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year (SM/09017) | SM/09017 | 287.5 | 6768 | RETROFITTING | 50 | WO no issued | 96 | 26/05/2021 | 31/12/2025 | 03/04/2025 | 06/12/2021 | 277.1 | 277.1
51 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one (SM/08631) | SM/08631 | 116.34 | 1624 | RETROFITTING | 50 | WO no issued | 12 | 31/05/2021 | 30/04/2025 | 03/04/2025 | 09/11/2021 | 14.11 | 14.11
52 | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. (SM/13757) | SM/13757 | 999.02 | 3872 | AUGMENTATION | 52 | WO no issued | 21 | 18/11/2022 | 31/12/2025 | 03/04/2025 | 03/02/2023 | 211.37 | 211.37
53 | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected (SM/16125) | SM/16125 | 710.57 | 1025 | AUGMENTATION | 52 | WO no issued | 17 | 22/02/2023 | 31/05/2025 | 03/04/2025 | 17/03/2023 | 119.96 | 107.65
54 | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/15783) | SM/15783 | 559.05 | 990 | AUGMENTATION | 55 | WO no issued | 38 | 20/02/2023 | 30/11/2025 | 03/04/2025 | 17/03/2023 | 212.92 | 212.92
55 | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/09931) | SM/09931 | 867.99 | 4871 | AUGMENTATION | 56 | WO no issued | 48 | 10/12/2021 | 31/12/2025 | 03/04/2025 | 22/03/2022 | 412.91 | 412.91
56 | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS (SM/13798) | SM/13798 | 925.05 | 1882 | NEW | 57 | WO no issued | 63 | 22/11/2022 | 30/09/2025 | 03/04/2025 | 01/08/2022 | 580.15 | 538.46
57 | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15472) | SM/15472 | 491.27 | 2500 | AUGMENTATION | 57 | WO no issued | 57 | 04/02/2023 | 31/12/2025 | 03/04/2025 | 18/02/2023 | 279.03 | 279.03
58 | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/18677) | SM/18677 | 1238.15 | 4292 | AUGMENTATION | 57 | WO no issued | 35 | 04/08/2023 | 31/03/2026 | 03/04/2025 | 11/08/2023 | 437.57 | 437.57
59 | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) (SM/08804) | SM/08804 | 76.86 | 2030 | RETROFITTING | 57 | WO no issued | 96 | 13/09/2021 | 31/03/2025 | 03/04/2025 | 01/09/2021 | 74.02 | 74.02
60 | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. (SM/13837) | SM/13837 | 739.08 | 1615 | NEW | 58 | WO no issued | 34 | 25/11/2022 | 31/12/2025 | 03/04/2025 | 20/02/2023 | 248.83 | 220.5
61 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, (SM/13891) | SM/13891 | 543.76 | 11350 | AUGMENTATION | 60 | WO no issued | 72 | 25/11/2022 | 31/03/2025 | 03/04/2025 | 19/04/2023 | 389.16 | 365.33
62 | RANIGACHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/15863) | SM/15863 | 748.34 | 1320 | AUGMENTATION | 60 | WO no issued | 12 | 20/02/2023 | 31/05/2025 | 03/04/2025 | 10/03/2023 | 92.05 | 92.05
63 | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o (SM/16132) | SM/16132 | 540.74 | 998 | AUGMENTATION | 60 | WO no issued | 25 | 22/02/2023 | 31/03/2025 | 03/04/2025 | 03/03/2023 | 133.39 | 131.47
64 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D (SM/18220) | SM/18220 | 2893.58 | 0 | AUGMENTATION | 60 | WO no issued | 61 | 27/04/2023 | 30/11/2025 | 03/04/2025 | 10/03/2022 | 1778.79 | 1778.79
65 | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15045) | SM/15045 | 232.1 | 200 | AUGMENTATION | 61 | WO no issued | 37 | 04/02/2023 | 31/12/2025 | 03/04/2025 | 15/02/2023 | 86.24 | 80.37
66 | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS (SM/18676) | SM/18676 | 1032.99 | 3555 | AUGMENTATION | 62 | WO no issued | 52 | 04/08/2023 | 31/12/2025 | 03/04/2025 | 07/08/2023 | 541.74 | 541.74
67 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS (SM/14681) | SM/14681 | 1020.93 | 2939 | AUGMENTATION | 65 | WO no issued | 43 | 14/06/2023 | 31/07/2025 | 03/04/2025 | 27/07/2022 | 441.42 | 438.31
68 | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area (SM/14870) | SM/14870 | 844.2 | 2171 | AUGMENTATION | 65 | WO no issued | 11 | 03/02/2023 | 31/03/2025 | 03/04/2025 | 15/03/2023 | 93.55 | 82.43
69 | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di (SM/15756) | SM/15756 | 460.15 | 943 | AUGMENTATION | 65 | WO no issued | 54 | 20/02/2023 | 30/09/2025 | 03/04/2025 | 02/03/2023 | 247.25 | 247.25
70 | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis (SM/11782) | SM/11782 | 510.08 | 865 | AUGMENTATION | 66 | WO no issued | 36 | 02/08/2022 | 31/05/2025 | 03/04/2025 | 01/11/2022 | 184.48 | 184.48
71 | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11732) | SM/11732 | 483.4 | 882 | AUGMENTATION | 67 | WO no issued | 37 | 03/08/2022 | 30/11/2025 | 03/04/2025 | 01/11/2022 | 179.57 | 179.57
72 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including (SM/07398) | SM/07398 | 59.32 | 869 | RETROFITTING | 69 | WO no issued | 68 | 29/12/2020 | 31/03/2025 | 03/04/2025 | 02/03/2022 | 40.08 | 40.08
73 | Ground water based BARULI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12212) | SM/12212 | 875.83 | 1435 | AUGMENTATION | 70 | WO no issued | 32 | 07/09/2022 | 30/06/2025 | 03/04/2025 | 09/02/2023 | 280.89 | 280.89
74 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme includin (SM/07406) | SM/07406 | 75.91 | 1328 | RETROFITTING | 71 | WO no issued | 98 | 29/12/2020 | 30/09/2025 | 03/04/2025 | 24/02/2021 | 74.33 | 74.33
75 | AUGMENTATION & RETROFITTING OF UTTAR ANGADBERIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (SM/15501) | SM/15501 | 237.68 | 200 | AUGMENTATION | 74 | WO no issued | 29 | 15/02/2023 | 31/03/2025 | 03/04/2025 | 15/02/2023 | 69.72 | 69.72
76 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one (SM/09098) | SM/09098 | 125.76 | 2110 | RETROFITTING | 75 | WO no issued | 73 | 29/10/2021 | 31/12/2025 | 03/04/2025 | 23/03/2022 | 91.87 | 91.87
77 | Ground water based RAJAK GOHALIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr (SM/11778) | SM/11778 | 464.19 | 963 | AUGMENTATION | 75 | WO no issued | 32 | 02/08/2022 | 30/06/2025 | 03/04/2025 | 01/11/2022 | 150.07 | 145.25
78 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-V OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDE (SM/14472) | SM/14472 | 461.17 | 4527 | AUGMENTATION | 75 | WO no issued | 24 | 20/01/2023 | 31/12/2025 | 03/04/2025 | 04/02/2023 | 111.19 | 111.19
79 | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS (SM/14159) | SM/14159 | 1074.54 | 2297 | AUGMENTATION | 75 | WO no issued | 68 | 05/01/2023 | 31/12/2025 | 03/04/2025 | 29/12/2022 | 735.73 | 701.44
80 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one (SM/08636) | SM/08636 | 134.28 | 1350 | RETROFITTING | 78 | WO no issued | 96 | 31/05/2021 | 31/12/2025 | 03/04/2025 | 27/07/2021 | 129.48 | 129.48
81 | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte (SM/15870) | SM/15870 | 418.82 | 634 | AUGMENTATION | 78 | WO no issued | 37 | 20/02/2023 | 31/05/2025 | 03/04/2025 | 03/03/2023 | 156.72 | 156.72
82 | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. (SM/08181) | SM/08181 | 260.42 | 2123 | RETROFITTING | 79 | WO no issued | 81 | 09/02/2021 | 31/03/2025 | 03/04/2025 | 26/02/2021 | 211.85 | 211.85
83 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) (SM/07630) | SM/07630 | 170.64 | 3606 | RETROFITTING | 80 | WO no issued | 73 | 07/01/2021 | 30/09/2025 | 03/04/2025 | 15/12/2020 | 124.82 | 124.82
84 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy (SM/12576) | SM/12576 | 45.21 | 122 | NEW | 80 | WO no issued | 58 | 15/09/2022 | 31/03/2025 | 03/04/2025 | 15/02/2023 | 26.16 | 26.16
85 | SATBERIA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal (SM/11274) | SM/11274 | 913.42 | 1721 | NEW | 80 | WO no issued | 69 | 24/06/2022 | 31/03/2025 | 03/04/2025 | 01/11/2022 | 633.24 | 633.24
86 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (SM/15491) | SM/15491 | 287.23 | 833 | AUGMENTATION | 80 | WO no issued | 34 | 15/02/2023 | 31/03/2025 | 03/04/2025 | 24/12/2020 | 97.61 | 97.61
87 | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. (SM/18253) | SM/18253 | 2827.8 | 23728 | AUGMENTATION | 80 | WO no issued | 42 | 16/06/2023 | 30/04/2025 | 03/04/2025 | 31/07/2023 | 1175.72 | 1175.72
88 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH (SM/17182) | SM/17182 | 371.8 | 2458 | AUGMENTATION | 80 | WO no issued | 74 | 15/03/2023 | 31/03/2025 | 03/04/2025 | 09/08/2017 | 275.87 | 275.87
89 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME (SM/15470) | SM/15470 | 286.46 | 1090 | AUGMENTATION | 82 | WO no issued | 62 | 04/02/2023 | 30/04/2025 | 03/04/2025 | 16/02/2022 | 176.59 | 171.05
90 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS (SM/15577) | SM/15577 | 218.88 | 542 | NEW | 82 | WO no issued | 81 | 15/02/2023 | 31/03/2025 | 03/04/2025 | 17/02/2023 | 177.1 | 177.1
91 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S (SM/09016) | SM/09016 | 86.12 | 1592 | RETROFITTING | 84 | WO no issued | 92 | 26/05/2021 | 31/03/2025 | 03/04/2025 | 03/03/2021 | 79.5 | 79.5
92 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl (SM/07633) | SM/07633 | 241.76 | 5480 | RETROFITTING | 85 | WO no issued | 83 | 07/01/2021 | 31/03/2025 | 03/04/2025 | 24/03/2021 | 199.51 | 199.51
93 | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are (SM/16135) | SM/16135 | 199.17 | 348 | AUGMENTATION | 86 | WO no issued | 53 | 22/02/2023 | 31/05/2025 | 03/04/2025 | 09/03/2023 | 104.65 | 99.98
94 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:153 to 169 under Budge Budge-I Block with allied works (SM/07053) | SM/07053 | 99.78 | 1637 | RETROFITTING | 88 | WO no issued | 100 | 25/11/2020 | 31/03/2025 | 03/04/2025 | 27/07/2022 | 99.78 | 82.75
95 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09945) | SM/09945 | 163.9 | 440 | RETROFITTING | 88 | WO no issued | 54 | 14/12/2021 | 31/07/2025 | 03/04/2025 | 02/11/2021 | 88.02 | 88.02
96 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09954) | SM/09954 | 287.71 | 118 | RETROFITTING | 88 | WO no issued | 87 | 14/12/2021 | 31/03/2025 | 03/04/2025 | 09/11/2021 | 250.68 | 250.68
97 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte (SM/09944) | SM/09944 | 135.17 | 40 | RETROFITTING | 88 | WO no issued | 40 | 14/12/2021 | 31/07/2025 | 03/04/2025 | 02/11/2021 | 53.62 | 53.62
98 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works (SM/07054) | SM/07054 | 99.29 | 1910 | RETROFITTING | 89 | WO no issued | 100 | 25/11/2020 | 31/03/2025 | 03/04/2025 | 31/01/2023 | 99.29 | 97.33
99 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144 ) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/09956) | SM/09956 | 299.18 | 80 | RETROFITTING | 89 | WO no issued | 96 | 14/12/2021 | 31/03/2025 | 03/04/2025 | 09/11/2021 | 286.45 | 286.45
100 | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f (SM/07401) | SM/07401 | 91.79 | 1280 | RETROFITTING | 90 | WO no issued | 97 | 29/12/2020 | 31/05/2025 | 03/04/2025 | 08/10/2020 | 89.12 | 80.73
101 | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08119) | SM/08119 | 356.83 | 1329 | RETROFITTING | 90 | WO no issued | 90 | 19/02/2021 | 31/05/2025 | 03/04/2025 | 12/05/2021 | 320.37 | 320.21
102 | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme (SM/07578) | SM/07578 | 86.88 | 1351 | RETROFITTING | 90 | WO no issued | 97 | 31/12/2020 | 31/05/2025 | 03/04/2025 | 30/12/2020 | 84.35 | 84.35
103 | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo (SM/09558) | SM/09558 | 253.22 | 3983 | RETROFITTING | 90 | WO no issued | 38 | 19/11/2021 | 31/05/2025 | 03/04/2025 | 26/02/2020 | 95.14 | 95.14
104 | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08121) | SM/08121 | 383.26 | 4362 | RETROFITTING | 90 | WO no issued | 62 | 19/02/2021 | 31/05/2025 | 03/04/2025 | 19/02/2021 | 237.63 | 237.63
105 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-I including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divis (SM/09973) | SM/09973 | 197.83 | 3342 | RETROFITTING | 90 | WO no issued | 10 | 15/12/2021 | 31/05/2025 | 03/04/2025 | 27/07/2022 | 20.59 | 20.59
106 | SANGUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM (SM/14545) | SM/14545 | 1250.69 | 2506 | AUGMENTATION | 90 | WO no issued | 40 | 30/01/2023 | 31/03/2025 | 03/04/2025 | 20/02/2023 | 497.97 | 497.07
107 | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math (SM/08120) | SM/08120 | 389.87 | 1666 | RETROFITTING | 90 | WO no issued | 89 | 19/02/2021 | 31/05/2025 | 03/04/2025 | 24/02/2021 | 348.07 | 295.07
108 | Retrofitting of Distribution system of Zone IX Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu (SM/08123) | SM/08123 | 271.61 | 624 | RETROFITTING | 90 | WO no issued | 95 | 19/02/2021 | 31/05/2025 | 03/04/2025 | 24/02/2021 | 258.99 | 249.38
109 | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South (SM/09505) | SM/09505 | 235.76 | 4562 | RETROFITTING | 90 | WO no issued | 89 | 19/11/2021 | 31/05/2025 | 03/04/2025 | 15/02/2022 | 210.48 | 210.48
110 | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM (SM/09513) | SM/09513 | 106.53 | 1573 | RETROFITTING | 90 | WO no issued | 70 | 19/11/2021 | 31/05/2025 | 03/04/2025 | 22/11/2021 | 74.79 | 73.63
111 | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math (SM/10218) | SM/10218 | 489.03 | 8596 | AUGMENTATION | 90 | WO no issued | 17 | 24/02/2022 | 31/05/2025 | 03/04/2025 | 04/04/2022 | 84.67 | 84.67
112 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including (SM/07590) | SM/07590 | 74.27 | 2329 | RETROFITTING | 92 | WO no issued | 91 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 18/02/2021 | 67.55 | 67.55
113 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10115) | SM/10115 | 762.86 | 0 | SCHOOL | 95 | WO no issued | 0 | 08/02/2022 | 31/03/2025 | 03/04/2025 | 31/03/2022 | 0 | 0
114 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p (SM/16189) | SM/16189 | 1691.01 | 0 | AUGMENTATION | 95 | WO no issued | 50 | 20/02/2023 | 31/08/2025 | 03/04/2025 | 13/07/2022 | 844.02 | 844.02
115 | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas (SM/09020) | SM/09020 | 650.96 | 0 | DISASTER | 95 | WO no issued | 0 | 30/10/2021 | 31/03/2025 | 03/04/2025 | 08/10/2020 | 0 | 0
116 | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. (SM/10116) | SM/10116 | 879.72 | 0 | SCHOOL | 95 | WO no issued | 0 | 08/02/2022 | 30/06/2025 | 03/04/2025 | 31/03/2022 | 0 | 0
117 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc (SM/07589) | SM/07589 | 43.41 | 1160 | RETROFITTING | 98 | WO no issued | 59 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 10/09/2021 | 25.78 | 25.78
118 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-VII, MATHURAPUR PIPED WATER SUPPLY SCHEME, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE (SM/15507) | SM/15507 | 72.1 | 344 | AUGMENTATION | 98 | WO no issued | 97 | 15/02/2023 | 31/03/2025 | 03/04/2025 | 18/02/2021 | 70 | 70
119 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche (SM/07592) | SM/07592 | 95.32 | 1675 | RETROFITTING | 98 | WO no issued | 97 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 20/05/2022 | 92.55 | 92.55
120 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S (SM/07761) | SM/07761 | 185.64 | 2937 | RETROFITTING | 98 | WO no issued | 98 | 08/01/2021 | 30/09/2025 | 03/04/2025 | 14/10/2020 | 181.03 | 180.84
121 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi (SM/09010) | SM/09010 | 102.43 | 1888 | RETROFITTING | 98 | WO no issued | 97 | 27/05/2021 | 31/12/2025 | 03/04/2025 | 06/01/2021 | 99.84 | 99.84
122 | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) (SM/09467) | SM/09467 | 44.84 | 1416 | RETROFITTING | 99 | WO no issued | 98 | 19/11/2021 | 31/03/2025 | 03/04/2025 | 20/01/2022 | 44.16 | 44.16
123 | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. (SM/09727) | SM/09727 | 399.53 | 0 | DISASTER | 99 | WO no issued | 0 | 26/11/2021 | 13/03/2025 | 03/04/2025 | 22/05/2021 | 0 | 0
124 | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. (SM/08986) | SM/08986 | 66.7 | 0 | DISASTER | 99 | WO no issued | 0 | 29/10/2021 | 13/03/2025 | 03/04/2025 | 21/02/2022 | 0 | 0
125 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including (SM/07757) | SM/07757 | 135.9 | 1447 | RETROFITTING | 100 | WO no issued | 37 | 08/01/2021 | 31/03/2025 | 03/04/2025 | 19/02/2021 | 49.87 | 49.87
126 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc (SM/07759) | SM/07759 | 101.4 | 987 | RETROFITTING | 100 | WO no issued | 79 | 08/01/2021 | 30/09/2025 | 03/04/2025 | 26/09/2020 | 80.51 | 80.3
127 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year (SM/08637) | SM/08637 | 157.43 | 2953 | RETROFITTING | 100 | WO no issued | 70 | 27/05/2021 | 31/12/2025 | 03/04/2025 | 27/07/2021 | 109.55 | 154.7
128 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y (SM/09094) | SM/09094 | 95.53 | 1513 | RETROFITTING | 100 | WO no issued | 86 | 29/10/2021 | 31/12/2025 | 03/04/2025 | 27/08/2020 | 82.01 | 80.52
129 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including (SM/07576) | SM/07576 | 88.57 | 1104 | RETROFITTING | 100 | WO no issued | 70 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 19/08/2020 | 61.62 | 60.68
130 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ (SM/07584) | SM/07584 | 80.41 | 1613 | RETROFITTING | 100 | WO no issued | 100 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 12/10/2020 | 80.41 | 80.41
131 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche (SM/07597) | SM/07597 | 87.3 | 1323 | RETROFITTING | 100 | WO no issued | 74 | 31/12/2020 | 31/03/2025 | 03/04/2025 | 08/02/2021 | 65 | 17.92
132 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply (SM/07642) | SM/07642 | 117.22 | 2122 | RETROFITTING | 100 | WO no issued | 95 | 07/01/2021 | 31/03/2025 | 03/04/2025 | 01/10/2020 | 111.07 | 110.74
133 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year (SM/09096) | SM/09096 | 165.49 | 2857 | RETROFITTING | 100 | WO no issued | 45 | 29/10/2021 | 31/03/2025 | 03/04/2025 | 24/02/2022 | 73.69 | 73.69
Total |  |  | 72213.64 | 275337 | [8 empty] | 26574.44 | 26232.31