## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Solarization of grid connected pumping installation at Nona Pingla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17363) | SM/17363 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
2 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS (SM/06921) | SM/06921 | 57.62 | 1246 | RETROFITTING | 0 | 0% Physical | 31 | 09/10/2020 | 07/11/2025 | 19/05/2025 | 26/11/2020 | 17.86 | 3.4
3 | Solarization of grid connected pumping installation at Dhaneswarpur (Pingla) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17751) | SM/17751 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
4 | Solarization of grid connected pumping installation Gokulpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17752) | SM/17752 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
5 | Solarization of grid connected pumping installation at Ukhla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17371) | SM/17371 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
6 | Solarization of grid connected pumping installation Jamboda Godamouli PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/18113) | SM/18113 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 31/03/2023 | 0 | 0
7 | Solarization of grid connected pumping installation at Julkapore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17319) | SM/17319 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 0 | 0
8 | Solarization of grid connected pumping installation at Keshpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17382) | SM/17382 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
9 | Solarization of grid connected pumping installation at Sarta PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17312) | SM/17312 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
10 | Solarization of grid connected pumping installation at Mohanpur (Ghatal) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17744) | SM/17744 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
11 | Solarization of grid connected pumping installation at Sonakhali PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17370) | SM/17370 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
12 | Solarization of grid connected pumping installation at Jote Ghanashyam PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17407) | SM/17407 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 24/03/2023 | 0 | 0
13 | Solarization of grid connected pumping installation at Maligram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17333) | SM/17333 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
14 | Solarization of grid connected pumping installation at Kalaimuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17362) | SM/17362 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
15 | Solarization of grid connected pumping installation at Salbani PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17365) | SM/17365 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
16 | Solarization of grid connected pumping installation Kalshibhanga PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17749) | SM/17749 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
17 | Solarization of grid connected pumping installation at Nona Ragpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17368) | SM/17368 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
18 | Solarization of grid connected pumping installation at Nona Madhabchak PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17338) | SM/17338 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
19 | Solarization of grid connected pumping installation at Chandrakona Road, Zone-I& Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17330) | SM/17330 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
20 | Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. (SM/17818) | SM/17818 | 24.79 | 0 | AUGMENTATION | 0 | 0% Physical | 1 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0.19 | 0.19
21 | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block (SM/06935) | SM/06935 | 77.64 | 1580 | RETROFITTING | 0 | 0% Physical | 97 | 09/10/2020 | 07/11/2025 | 19/05/2025 | 26/11/2020 | 75.35 | 54.23
22 | Retrofitting to accommodate FHTC under JJM in Krishnapriya PWSS under Pingla Block in Paschim Medinipur District (SM/09707) | SM/09707 | 46.32 | 876 | RETROFITTING | 0 | 0% Physical | 74 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 02/05/2022 | 34.43 | 34.43
23 | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17377) | SM/17377 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 24/03/2023 | 0 | 0
24 | Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. (SM/17776) | SM/17776 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 3 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0.41 | 0.41
25 | Solarization of grid connected pumping installation Balarampur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17810) | SM/17810 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
26 | Solarization of grid connected pumping installation at Mohanpur (Mohanpur) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17381) | SM/17381 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
27 | Solarization of grid connected pumping installation Ranibazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17821) | SM/17821 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
28 | Solarization of grid connected pumping installation at Sutkujhuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17383) | SM/17383 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
29 | Solarization of grid connected pumping installation Panpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17732) | SM/17732 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
30 | Solarization of grid connected pumping installation Chatra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17735) | SM/17735 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
31 | Solarization of grid connected pumping installation at Belda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17357) | SM/17357 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
32 | Solarization of grid connected pumping installation at Satkui PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17327) | SM/17327 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
33 | Solarization of grid connected pumping installation Ranapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17819) | SM/17819 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
34 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS (SM/06904) | SM/06904 | 99.98 | 2053 | RETROFITTING | 0 | 0% Physical | 97 | 09/10/2020 | 07/11/2025 | 19/05/2025 | 26/11/2020 | 97.4 | 85.57
35 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS (SM/06910) | SM/06910 | 99.8 | 2016 | RETROFITTING | 0 | 0% Physical | 97 | 09/10/2020 | 07/11/2025 | 19/05/2025 | 26/11/2020 | 96.88 | 91.18
36 | Solarization of grid connected pumping installation Chakismilepur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17763) | SM/17763 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
37 | Solarization of grid connected pumping installation Rajnagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17766) | SM/17766 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
38 | Solarization of grid connected pumping installation at Dhengasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17384) | SM/17384 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
39 | Solarization of grid connected pumping installation at Palashi (Debra)PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17356) | SM/17356 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
40 | Solarization of grid connected pumping installation Goaltore PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17745) | SM/17745 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
41 | Solarization of grid connected pumping installation at Paschim Pathari PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17369) | SM/17369 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
42 | Solarization of grid connected pumping installation at Bhabaninagar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17374) | SM/17374 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
43 | Solarization of grid connected pumping installation at Nayagram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17344) | SM/17344 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
44 | Solarization of grid connected pumping installation Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17795) | SM/17795 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
45 | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. (SM/19037) | SM/19037 | 1764.69 | 8197 | AUGMENTATION | 0 | 0% Physical | 14 | 08/11/2023 | 31/12/2025 | 19/05/2025 | 15/01/2024 | 252.65 | 210.28
46 | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL (SM/14107) | SM/14107 | 304.19 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 21/12/2022 |  | 21/12/2022 | 15/03/2022 | 0 | 0
47 | OPERATIONAL CHARGES OF WATER TESTING LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JALO JEEVAN MISSION FOR THE FINANCIAL TEAR 2022-2023. (SM/14086) | SM/14086 | 91.88 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 12/12/2022 |  | 15/12/2022 | 30/09/2021 | 0 | 0
48 | SUPPLY,DELIVERY AND INSTALLATION OF DESKTOP COMPUTER,UPS,SCANNER,PRINTER ETC.THROUGH GeM PORTAL FOR OFFICE OF THE EXECUTIVE ENGINEER UNDER MIDNAPORE DIVISION,PHE Dte. (SM/12378) | SM/12378 | 48.05 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 13/09/2022 |  | 14/09/2022 |  | 0 | 0
49 | Collection,Testing & Uploading charges of Drinking Water Samples through Field Test Kits(FTKs) in Paschim Medinipur District(Phase-II) related to Water Quality Monitoring & Surveillance Program Under Jal Jeevan Mission. (SM/19089) | SM/19089 | 27.93 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 05/03/2025 | 0 | 0
50 | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. (SM/19061) | SM/19061 | 145.68 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 24/11/2023 |  | 30/11/2023 | 29/12/2021 | 0 | 0
51 | Proposal of Engagement of Additional Manpower as Project Management & Monitoring Specialist at DPMU ofPaschim Medinipur District under Jal Jeevan Mission (JJM). (SM/19350) | SM/19350 | 18.6 | 0 | SUPPORT - HRD | 0 | WO no issued | 0 | 04/03/2025 |  | 21/03/2025 |  | 0 | 0
52 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Medinipur District. (SM/08999) | SM/08999 | 466.54 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 09/11/2022 | 0 | 0
53 | Regular Upkeep of Drinking Water Testing Laboratory in Paschim Medinipur Under Midnapore Division, PHE dte. Related to Water Quality Monitoring and Surveillance Support Activities under Jal Jeevan Mission. (SM/18277) | SM/18277 | 98.71 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 | 06/12/2024 | 0 | 0
54 | Estimate for procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Laboratories for the year 2024- 2025 in the District of Paschim Medinipur Under Midnapore Division P.H.E. Dte. (SM/19270) | SM/19270 | 167.92 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
55 | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE FOR JJM RELATED WORKS IN MIDNAPORE MECHANICAL DIVISION AND SUBSEQUENT SUB DIVISION OFFICES, UNDER MMD, PHE DTE. (SM/14687) | SM/14687 | 20.67 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 31/01/2023 |  | 03/02/2023 |  | 0 | 0
56 | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission under Midnapore Division, PHE Dte. (SM/12633) | SM/12633 | 78.13 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/09/2022 |  | 20/09/2022 | 13/03/2023 | 0 | 0
57 | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) (SM/19285) | SM/19285 | 145.75 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 13/09/2024 | 0 | 0
58 | Drinking Water sample collection and testing through Field Test Kit(FTKs) and uploading charges for the same related to water quality monitoring and surveillance programme under Jal Jeevan Mission. (SM/19214) | SM/19214 | 58.68 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/06/2024 |  | 25/06/2024 |  | 0 | 0
59 | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues and WASH issues under Jal Jeevan Mission (JJM) Support Activities at Paschim Medinipur District. (SM/19172) | SM/19172 | 125.2 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 08/02/2024 |  | 15/02/2024 | 14/01/2025 | 0 | 0
60 | Regular Upkeepment of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents. accessories and safety (SM/19282) | SM/19282 | 37.26 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 26/12/2024 | 0 | 0
61 | Retrofitting to accommodate FHTC under JJM in Gurguripal PWSS, Block - Midnapore Sadar, District - Paschim Medinipur. (SM/09088) | SM/09088 | 72.62 | 1486 | RETROFITTING | 1 | Delayed | 0 | 28/10/2021 | 31/08/2025 | 19/05/2025 | 29/08/2024 | 0 | 0
62 | GOKULPUR AND ADJOINING MOUJAS PWSS (SM/14649) | SM/14649 | 646.43 | 1546 | NEW | 1 | Delayed | 22 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 22/03/2023 | 141.77 | 141.77
63 | Retrofitting to accommodate FHTC under JJM in Paschim Beguni PWSS under Debra Block in Paschim Medinipur District (SM/09711) | SM/09711 | 38.75 | 735 | RETROFITTING | 1 | Delayed | 0 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 01/12/2021 | 0 | 0
64 | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS (SM/12384) | SM/12384 | 522.3 | 1614 | NEW | 1 | Delayed | 56 | 13/09/2022 | 31/03/2026 | 19/05/2025 | 12/04/2023 | 293.49 | 281.89
65 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/15576) | SM/15576 | 412.64 | 264 | AUGMENTATION | 1 | Delayed | 0 | 15/02/2023 | 08/02/2025 | 19/05/2025 | 22/01/2024 | 1.63 | 1.63
66 | URIYASHAI AND ADJOINING MOUJAS PWSS (SM/13130) | SM/13130 | 514.82 | 1433 | NEW | 2 | Delayed | 2 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 8.81 | 8.81
67 | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION (SM/17569) | SM/17569 | 725.94 | 1367 | NEW | 2 | Delayed | 3 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 22.54 | 22.54
68 | BENYA AND IT'S ADJOINING MOUJAS PWSS. (SM/14721) | SM/14721 | 619.5 | 1800 | NEW | 2 | Delayed | 52 | 31/01/2023 | 31/03/2026 | 19/05/2025 | 20/03/2023 | 321.45 | 320.06
69 | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS (SM/17618) | SM/17618 | 616.34 | 2170 | NEW | 2 | Delayed | 4 | 21/03/2023 | 07/11/2025 | 19/05/2025 | 24/03/2023 | 26.53 | 26.53
70 | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. (SM/18538) | SM/18538 | 1463.05 | 4261 | NEW | 2 | Delayed | 6 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 86.53 | 86.53
71 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/15574) | SM/15574 | 433.78 | 164 | AUGMENTATION | 2 | Delayed | 10 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 16/03/2021 | 43.22 | 38.9
72 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/17396) | SM/17396 | 254.45 | 33 | AUGMENTATION | 2 | Delayed | 6 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 08/03/2021 | 14.96 | 14.96
73 | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. (SM/18620) | SM/18620 | 1571.38 | 4793 | NEW | 2 | Delayed | 14 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 07/08/2023 | 214.46 | 178.6
74 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE (SM/18249) | SM/18249 | 1158.17 | 3102 | NEW | 3 | Delayed | 0 | 16/06/2023 | 31/12/2025 | 19/05/2025 | 25/07/2023 | 1.97 | 1.97
75 | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. (SM/18539) | SM/18539 | 1312.49 | 3339 | NEW | 3 | Delayed | 6 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 74.43 | 74.43
76 | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS (SM/17615) | SM/17615 | 415.89 | 1377 | NEW | 3 | Delayed | 17 | 21/03/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 72.17 | 72.17
77 | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14646) | SM/14646 | 518.24 | 1188 | NEW | 3 | Delayed | 1 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 25/04/2023 | 2.66 | 2.66
78 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. (SM/18541) | SM/18541 | 1339.54 | 2915 | NEW | 3 | Delayed | 4 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 47.51 | 47.51
79 | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS (SM/19100) | SM/19100 | 1115.72 | 3462 | NEW | 4 | Delayed | 3 | 14/12/2023 | 31/12/2025 | 19/05/2025 | 21/09/2023 | 31.58 | 31.58
80 | BIRSINGPUR AND ADJOINING MOUJAS PWSS (SM/14994) | SM/14994 | 613.69 | 1673 | NEW | 5 | Delayed | 2 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 15.08 | 15.08
81 | TRILOCHANPUR PWSS (SM/13049) | SM/13049 | 607.64 | 2231 | NEW | 5 | Delayed | 8 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 50.56 | 50.56
82 | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. (SM/06925) | SM/06925 | 95.44 | 1891 | RETROFITTING | 5 | Delayed | 88 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 83.77 | 83.64
83 | Solarization of grid connected pumping installation at Abashgarh PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17380) | SM/17380 | 8.3 | 0 | SOLARISATION | 5 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
84 | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur (SM/09080) | SM/09080 | 35.97 | 694 | RETROFITTING | 5 | Delayed | 74 | 28/10/2021 | 31/12/2025 | 19/05/2025 | 02/05/2022 | 26.53 | 26.53
85 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/12827) | SM/12827 | 468.57 | 0 | AUGMENTATION | 5 | Delayed | 6 | 22/09/2022 | 31/12/2025 | 19/05/2025 | 17/12/2021 | 28.56 | 28.56
86 | Solarization of grid connected pumping installation at Lutunia PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17375) | SM/17375 | 8.3 | 0 | SOLARISATION | 5 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
87 | Khirinda Piped Water Supply Scheme. (SM/07393) | SM/07393 | 900.72 | 2201 | NEW | 5 | Delayed | 4 | 21/12/2020 | 31/08/2025 | 19/05/2025 | 25/07/2022 | 37.03 | 37.03
88 | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block - Dantan-II in the district of Paschim Medinipur. (SM/08697) | SM/08697 | 92.77 | 1836 | RETROFITTING | 5 | Delayed | 54 | 01/09/2021 | 31/05/2025 | 19/05/2025 | 07/09/2021 | 50 | 43.4
89 | GAHIRA AND ADJOINING MOUJAS PWSS (SM/13010) | SM/13010 | 497.53 | 1499 | NEW | 5 | Delayed | 2 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 11.07 | 11.07
90 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18237) | SM/18237 | 1370.39 | 2583 | NEW | 6 | Delayed | 6 | 12/06/2023 | 07/11/2025 | 19/05/2025 | 22/06/2023 | 76.63 | 76.63
91 | BRAHMAN KHALISA & ADJOINING MOUZAS (SM/13051) | SM/13051 | 435.5 | 1722 | NEW | 8 | Delayed | 11 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 31/12/2022 | 46.41 | 30.26
92 | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS (SM/13023) | SM/13023 | 735.57 | 2635 | NEW | 8 | Delayed | 14 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 104.75 | 31.49
93 | BAMANSAI AND IT'S ADJOINING MOUJAS PWSS (SM/13047) | SM/13047 | 376.6 | 1255 | NEW | 9 | Delayed | 2 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 7.72 | 7.72
94 | JAHALDA AND IT'S ADJOINING MOUJAS PWSS (SM/13086) | SM/13086 | 428.16 | 1502 | NEW | 10 | Delayed | 15 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 01/11/2022 | 64.87 | 48.36
95 | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS (SM/13029) | SM/13029 | 458.25 | 1445 | NEW | 10 | Delayed | 3 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 14.89 | 13.68
96 | PUNYA AND IT'S ADJOINING MOUJAS PWSS (SM/13033) | SM/13033 | 488.08 | 1731 | NEW | 10 | Delayed | 4 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 31/12/2022 | 20.67 | 19.45
97 | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/17567) | SM/17567 | 513.09 | 863 | NEW | 10 | Delayed | 2 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 9.68 | 9.68
98 | KEDAR AND ITS ADJOINING MOUJAS PWSS (SM/17621) | SM/17621 | 359.64 | 1112 | NEW | 10 | Delayed | 22 | 21/03/2023 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 79.98 | 52.5
99 | BELDA AND IT'S ADJOINING MOUJAS (SM/13048) | SM/13048 | 526.18 | 1848 | NEW | 10 | Delayed | 7 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 36.4 | 22.42
100 | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS (SM/13139) | SM/13139 | 518.94 | 2410 | NEW | 10 | Delayed | 9 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 46.45 | 23.8
101 | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17561) | SM/17561 | 660.76 | 1379 | NEW | 10 | Delayed | 39 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 256.21 | 256.21
102 | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. (SM/13025) | SM/13025 | 509.99 | 1953 | NEW | 10 | Delayed | 5 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 25.08 | 23.82
103 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/16999) | SM/16999 | 255.39 | 75 | AUGMENTATION | 10 | Delayed | 7 | 16/03/2023 | 08/02/2025 | 19/05/2025 | 25/04/2023 | 18.83 | 18.83
104 | SHASHINDA SVS PWSS (SM/18017) | SM/18017 | 458 | 1042 | NEW | 10 | Delayed | 2 | 17/03/2023 | 08/02/2025 | 19/05/2025 | 21/06/2023 | 8.04 | 8.04
105 | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. (SM/18758) | SM/18758 | 812.77 | 2311 | NEW | 10 | Delayed | 4 | 23/08/2023 | 07/11/2025 | 19/05/2025 | 29/08/2023 | 35.8 | 35.8
106 | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. (SM/09430) | SM/09430 | 997.1 | 3411 | AUGMENTATION | 10 | Delayed | 69 | 17/11/2021 | 31/03/2026 | 25/08/2023 | 28/03/2022 | 687.37 | 687.37
107 | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS (SM/13050) | SM/13050 | 464.86 | 1765 | NEW | 10 | Delayed | 15 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 68.49 | 31.06
108 | RELA AND IT'S ADJOINING MOUJAS PWSS (SM/13036) | SM/13036 | 398.86 | 1179 | NEW | 10 | Delayed | 15 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 59.28 | 33.05
109 | KADAMDIHA AND IT'S ADJOINING MOUJAS PWSS (SM/16620) | SM/16620 | 883.71 | 1800 | NEW | 11 | Delayed | 2 | 14/03/2023 | 07/11/2025 | 19/05/2025 | 27/03/2023 | 18.49 | 18.49
110 | Jankapur Piped Water Supply Scheme. (SM/18786) | SM/18786 | 806.7 | 2381 | NEW | 12 | Delayed | 16 | 29/08/2023 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 126.7 | 126.7
111 | BAJGERYA AND ITS ADJOINING MOUZAS PWSS (SM/18658) | SM/18658 | 1216.26 | 2904 | NEW | 12 | Delayed | 4 | 04/08/2023 | 07/11/2025 | 19/05/2025 | 07/08/2023 | 43.19 | 43.19
112 | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/15325) | SM/15325 | 892.54 | 2182 | NEW | 13 | Delayed | 2 | 09/02/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 17.78 | 17.78
113 | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. (SM/17558) | SM/17558 | 585.04 | 1304 | NEW | 14 | Delayed | 5 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 29.04 | 29.04
114 | SHUJA AND ADJOINING MOUJAS PWSS (SM/13109) | SM/13109 | 443.41 | 1273 | NEW | 15 | Delayed | 22 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 96.72 | 96.72
115 | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12986) | SM/12986 | 421.82 | 1137 | NEW | 15 | Delayed | 43 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 179.73 | 179.73
116 | BABALPUR AND ADJOINING MOUJAS PWSS (SM/13754) | SM/13754 | 462.01 | 1391 | NEW | 15 | Delayed | 16 | 17/11/2022 | 31/03/2026 | 19/05/2025 | 02/02/2023 | 74.37 | 74.37
117 | MALIGHATI AND ITS ADJOINING MOUJAS PWSS (SM/13027) | SM/13027 | 516.76 | 1763 | NEW | 15 | Delayed | 30 | 28/09/2022 | 31/03/2026 | 19/05/2025 | 31/12/2022 | 153.64 | 153.64
118 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS (SM/13035) | SM/13035 | 583.12 | 1832 | NEW | 15 | Delayed | 48 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 282.51 | 282.51
119 | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS (SM/14940) | SM/14940 | 394.66 | 1113 | NEW | 15 | Delayed | 50 | 03/02/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 195.76 | 195.76
120 | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. (SM/17000) | SM/17000 | 931.61 | 3272 | AUGMENTATION | 15 | Delayed | 0 | 16/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 3.16 | 0
121 | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS (SM/17624) | SM/17624 | 342.58 | 1014 | NEW | 15 | Delayed | 41 | 21/03/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 141.17 | 141.17
122 | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12988) | SM/12988 | 521.64 | 1811 | NEW | 15 | Delayed | 20 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 105.63 | 105.63
123 | BAHURUPA AND ADJOINING MOUJAS PWSS (SM/13755) | SM/13755 | 590.76 | 2418 | NEW | 15 | Delayed | 9 | 17/11/2022 | 31/03/2026 | 19/05/2025 | 02/02/2023 | 53.49 | 53.49
124 | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR (SM/13031) | SM/13031 | 521.14 | 1579 | NEW | 15 | Delayed | 62 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 29/12/2022 | 322.9 | 322.9
125 | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/15118) | SM/15118 | 756.61 | 2175 | NEW | 15 | Delayed | 6 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 13/06/2023 | 42.15 | 42.15
126 | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14998) | SM/14998 | 236.26 | 478 | NEW | 15 | Delayed | 3 | 04/02/2023 | 31/03/2026 | 19/05/2025 | 04/04/2023 | 7.37 | 7.37
127 | BHAGABANPUR PIPED WATER SUPPLY SCHEME (SM/12202) | SM/12202 | 454.8 | 1421 | NEW | 15 | Delayed | 27 | 07/09/2022 | 07/11/2025 | 19/05/2025 | 29/12/2022 | 120.74 | 110.19
128 | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS (SM/12411) | SM/12411 | 338.8 | 826 | NEW | 15 | Delayed | 27 | 13/09/2022 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 91.12 | 91.12
129 | JAGARDANGA AND ADJOINING MOUJAS PWSS (SM/13055) | SM/13055 | 550.06 | 1679 | NEW | 16 | Delayed | 1 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 8.08 | 8.08
130 | GHAGRASOL AND ADJOINING MOUJAS PWSS (SM/14647) | SM/14647 | 63.13 | 136 | NEW | 16 | Delayed | 18 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 11.17 | 11.17
131 | NANASOL AND ADJOINING MOUJAS PWSS (SM/13808) | SM/13808 | 294.11 | 529 | NEW | 16 | Delayed | 14 | 22/11/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 40.16 | 40.16
132 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10779) | SM/10779 | 79.49 | 0 | AUGMENTATION | 16 | Delayed | 46 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 29/09/2021 | 36.26 | 36.26
133 | BARAKURYA AND ADJOINING MOUJAS PWSS (SM/13068) | SM/13068 | 328.47 | 585 | NEW | 16 | Delayed | 16 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 51.47 | 51.47
134 | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. (SM/16296) | SM/16296 | 273.33 | 895 | AUGMENTATION | 16 | Delayed | 14 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 21/03/2022 | 38.76 | 38.76
135 | UMRAPATA AND ADJOINING MOUJAS PWSS (SM/15123) | SM/15123 | 142.4 | 290 | NEW | 16 | Delayed | 1 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 1.79 | 1.79
136 | PATAJHARIA AND ADJOINING MOUJAS PWSS (SM/15027) | SM/15027 | 316.05 | 535 | NEW | 16 | Delayed | 9 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 27 | 27
137 | METELDEBIGHATA AND ADJOINING MOUJAS PWSS (SM/14624) | SM/14624 | 81 | 118 | NEW | 16 | Delayed | 0 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 0 | 0
138 | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/16632) | SM/16632 | 550.96 | 803 | NEW | 17 | Delayed | 15 | 14/03/2023 | 31/03/2026 | 19/05/2025 | 20/03/2023 | 83.25 | 83.25
139 | MAKLI AND ADJOINING MOUJAS PWSS (SM/13096) | SM/13096 | 378.34 | 710 | NEW | 17 | Delayed | 40 | 10/10/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 151.75 | 151.75
140 | BALARAMPUR AND ADJOINING MOUJAS PWSS (SM/13063) | SM/13063 | 388.69 | 915 | NEW | 17 | Delayed | 4 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 15.2 | 15.2
141 | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS (SM/13076) | SM/13076 | 932.03 | 3408 | NEW | 18 | Delayed | 24 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 225.66 | 225.66
142 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18236) | SM/18236 | 1026.01 | 2547 | NEW | 18 | Delayed | 4 | 12/06/2023 | 31/12/2025 | 19/05/2025 | 22/06/2023 | 40.48 | 31.61
143 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. (SM/18233) | SM/18233 | 1127.03 | 3522 | NEW | 18 | Delayed | 19 | 12/06/2023 | 31/12/2025 | 19/05/2025 | 22/06/2023 | 211.1 | 211.1
144 | RAUTMANI AND ITS ADJOINING MOUZAS PWSS (SM/18523) | SM/18523 | 1076.55 | 3259 | NEW | 18 | Delayed | 8 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 23/08/2023 | 88.75 | 88.75
145 | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/18585) | SM/18585 | 1078.74 | 2796 | NEW | 18 | Delayed | 24 | 31/07/2023 | 31/12/2025 | 19/05/2025 | 09/08/2023 | 264.13 | 257.13
146 | BANKIBANDH AND ADJOINING MOUJAS PWSS (SM/13065) | SM/13065 | 409.26 | 1170 | NEW | 18 | Delayed | 17 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 68.89 | 68.89
147 | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR (SM/12201) | SM/12201 | 452.65 | 1300 | NEW | 19 | Delayed | 44 | 07/09/2022 | 31/03/2026 | 19/05/2025 | 29/12/2022 | 199.61 | 196.61
148 | BHATMARA AND ADJOINING MOUJAS PWSS (SM/14644) | SM/14644 | 188.68 | 320 | NEW | 20 | Delayed | 30 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 56.01 | 56.01
149 | Islampur Piped Water Supply Scheme. (SM/18782) | SM/18782 | 801.48 | 2431 | NEW | 20 | Delayed | 7 | 29/08/2023 | 07/11/2025 | 19/05/2025 | 05/10/2023 | 54.6 | 54.6
150 | TALBANDI AND ITS ADJOINING MOUJAS PWSS (SM/17614) | SM/17614 | 299.88 | 712 | NEW | 20 | Delayed | 18 | 21/03/2023 | 31/12/2025 | 19/05/2025 | 28/03/2023 | 53.63 | 29.77
151 | RAIPUR AND ITS ADJOINING MOUJAS PWSS (SM/13170) | SM/13170 | 538.65 | 2219 | NEW | 20 | Delayed | 7 | 12/10/2022 | 30/09/2025 | 19/05/2025 | 02/02/2023 | 36.5 | 36.5
152 | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS (SM/13635) | SM/13635 | 658.87 | 2099 | NEW | 20 | Delayed | 15 | 11/11/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 99.21 | 99.21
153 | BENUCHA AND ADJOINING MOUJAS PWSS (SM/13069) | SM/13069 | 458.71 | 1447 | NEW | 20 | Delayed | 19 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 04/05/2023 | 87.78 | 76.25
154 | CHHATNI AND ADJOINING MOUJAS PWSS (SM/13007) | SM/13007 | 285.05 | 583 | NEW | 20 | Delayed | 17 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 47.93 | 47.93
155 | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. (SM/12331) | SM/12331 | 650.74 | 1995 | NEW | 20 | Delayed | 5 | 09/09/2022 | 30/09/2025 | 19/05/2025 | 07/08/2023 | 30.39 | 30.39
156 | BALIBANDH AND ADJOINING MOUJAS PWSS (SM/14990) | SM/14990 | 545.5 | 1211 | NEW | 20 | Delayed | 12 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 64.19 | 64.19
157 | KOREDAN AND ADJOINING MOUJAS PWSS (SM/14034) | SM/14034 | 484.66 | 1332 | NEW | 20 | Delayed | 20 | 05/12/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 94.71 | 94.71
158 | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. (SM/17755) | SM/17755 | 24.79 | 0 | AUGMENTATION | 20 | Delayed | 34 | 17/03/2023 | 31/12/2026 | 19/05/2025 | 29/03/2023 | 8.46 | 8.46
159 | DAMODARPUR AND ADJOINING MOUJAS PWSS (SM/13008) | SM/13008 | 676.15 | 1668 | NEW | 20 | Delayed | 23 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 157.3 | 157.3
160 | TARUA AND ADJOINING MOUJAS PWSS (SM/13166) | SM/13166 | 848.24 | 2426 | NEW | 20 | Delayed | 14 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 07/08/2023 | 120.69 | 120.69
161 | ASHARI AND IT'S ADJOINING MOUJAS PWSS (SM/12198) | SM/12198 | 407.59 | 1230 | NEW | 20 | Delayed | 41 | 07/09/2022 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 169.03 | 154.09
162 | DUMURIA AND ADJOINING MOUJAS PWSS (SM/14032) | SM/14032 | 744.52 | 1968 | NEW | 20 | Delayed | 6 | 05/12/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 47.36 | 47.36
163 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. (SM/14485) | SM/14485 | 54.66 | 0 | AUGMENTATION | 20 | Delayed | 0 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 26/12/2022 | 0.19 | 0.19
164 | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17398) | SM/17398 | 963.46 | 2241 | NEW | 20 | Delayed | 4 | 15/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 38.53 | 38.53
165 | GANGANI AND ADJOINING MOUJAS PWSS (SM/19099) | SM/19099 | 1411.27 | 4606 | NEW | 20 | Delayed | 4 | 14/12/2023 | 31/12/2025 | 19/05/2025 | 21/09/2023 | 56.76 | 56.76
166 | AKANDA AND ADJOINING MOUJAS PWSS (SM/13176) | SM/13176 | 549.46 | 1771 | NEW | 20 | Delayed | 5 | 12/10/2022 | 30/09/2025 | 19/05/2025 | 06/03/2023 | 28.49 | 28.49
167 | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/18696) | SM/18696 | 1028.72 | 2375 | NEW | 20 | Delayed | 20 | 04/08/2023 | 07/11/2025 | 19/05/2025 | 07/08/2023 | 210.81 | 182.77
168 | BARGOPAL AND ADJOINING MOUJAS PWSS (SM/13004) | SM/13004 | 782.23 | 2500 | NEW | 20 | Delayed | 4 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 29.72 | 29.72
169 | DUKI AND ADJOINING MOUJAS PWSS (SM/14645) | SM/14645 | 619.63 | 1290 | NEW | 20 | Delayed | 27 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 166.41 | 166.41
170 | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION (SM/17566) | SM/17566 | 662.1 | 1032 | NEW | 20 | Delayed | 16 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 106.7 | 106.7
171 | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. (SM/18621) | SM/18621 | 1780.9 | 5440 | NEW | 20 | Delayed | 2 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 09/08/2023 | 30.66 | 25.78
172 | Solarization of grid connected pumping installation Debhog PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17806) | SM/17806 | 8.3 | 0 | SOLARISATION | 20 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
173 | HARI PURA AND ADJOINING MOUJAS PWSS (SM/13053) | SM/13053 | 455.91 | 1721 | NEW | 21 | Delayed | 25 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 112.5 | 112.5
174 | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS (SM/13034) | SM/13034 | 387.21 | 1120 | NEW | 22 | Delayed | 47 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 183.61 | 183.61
175 | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS (SM/17622) | SM/17622 | 387.04 | 1118 | NEW | 22 | Delayed | 8 | 21/03/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 30.4 | 30.4
176 | RAUTARA AND ADJOINING MOUJAS PWSS (SM/13218) | SM/13218 | 453.04 | 1327 | NEW | 22 | Delayed | 22 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 101.49 | 101.49
177 | AMRA TARYA AND ADJOINING MOUJAS PWSS (SM/13178) | SM/13178 | 466.23 | 1194 | NEW | 23 | Delayed | 24 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 112.8 | 112.8
178 | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/15120) | SM/15120 | 233.1 | 667 | NEW | 23 | Delayed | 33 | 04/02/2023 | 31/03/2026 | 19/05/2025 | 04/05/2023 | 76.94 | 72.05
179 | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS (SM/17619) | SM/17619 | 356.79 | 1196 | NEW | 23 | Delayed | 44 | 21/03/2023 | 31/03/2026 | 19/05/2025 | 24/03/2023 | 157.9 | 157.9
180 | NAYAPUKUR AND ADJOINING MOUJAS PWSS (SM/13102) | SM/13102 | 628.1 | 1845 | NEW | 23 | Delayed | 27 | 10/10/2022 | 30/09/2025 | 19/05/2025 | 07/08/2023 | 168.29 | 168.29
181 | MALIHATI AND IT'S ADJOINING MOUJAS PWSS (SM/16615) | SM/16615 | 381.45 | 1268 | NEW | 23 | Delayed | 52 | 14/03/2023 | 31/03/2026 | 19/05/2025 | 04/05/2023 | 198.82 | 143.84
182 | BAKALSABAKARAM PWSS (SM/12199) | SM/12199 | 603.79 | 2008 | NEW | 24 | Delayed | 27 | 07/09/2022 | 07/11/2025 | 19/05/2025 | 29/12/2022 | 161.49 | 161.49
183 | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS (SM/17623) | SM/17623 | 515.24 | 1556 | NEW | 24 | Delayed | 37 | 21/03/2023 | 31/03/2026 | 19/05/2025 | 20/03/2023 | 191.16 | 191.16
184 | BHAUDI AND ADJOINING MOUJAS PWSS (SM/13070) | SM/13070 | 409.94 | 1182 | NEW | 25 | Delayed | 29 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 118.57 | 118.24
185 | BANAMALIPUR AND ADJOINING MOUJAS PWSS (SM/13064) | SM/13064 | 471.29 | 1125 | NEW | 25 | Delayed | 28 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 133.49 | 89.89
186 | JHETA JAMBONI PIPED WATER SUPPLY SCHEME (SM/13806) | SM/13806 | 913.04 | 2561 | NEW | 25 | Delayed | 12 | 22/11/2022 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 105.42 | 24.04
187 | KANKRISOL AND ADJOINING MOUJAS PWSS (SM/14033) | SM/14033 | 302.42 | 474 | NEW | 25 | Delayed | 26 | 05/12/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 79.2 | 79.2
188 | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/16262) | SM/16262 | 873.13 | 2053 | NEW | 25 | Delayed | 19 | 23/02/2023 | 31/12/2025 | 19/05/2025 | 27/03/2023 | 163.43 | 155.24
189 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. (SM/15122) | SM/15122 | 753.44 | 1809 | NEW | 25 | Delayed | 7 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 54.98 | 54.98
190 | PATHRAJURI AND ADJOINING MOUJAS PWSS (SM/15535) | SM/15535 | 175.06 | 345 | NEW | 25 | Delayed | 19 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 33.21 | 33.21
191 | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/18192) | SM/18192 | 566.06 | 1258 | NEW | 25 | Delayed | 10 | 31/03/2023 | 31/12/2025 | 19/05/2025 | 25/04/2023 | 57.31 | 57.31
192 | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS (SM/17617) | SM/17617 | 680.25 | 3088 | NEW | 25 | Delayed | 39 | 21/03/2023 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 263.8 | 263.8
193 | CHOTA TARA AND ADJOINING MOUJAS PWSS (SM/18619) | SM/18619 | 1023.13 | 3330 | NEW | 25 | Delayed | 16 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 30/10/2023 | 168.15 | 168.15
194 | SHUKHNATOR AND ADJOINING MOUJAS PWSS (SM/18020) | SM/18020 | 820.59 | 2791 | NEW | 25 | Delayed | 17 | 17/03/2023 | 07/11/2025 | 19/05/2025 | 30/10/2023 | 140.18 | 140.18
195 | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17573) | SM/17573 | 583.8 | 1276 | NEW | 25 | Delayed | 5 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 28.64 | 15.87
196 | NALBONA AND ADJOINING MOUJAS PWSS (SM/13101) | SM/13101 | 496.83 | 1566 | NEW | 25 | Delayed | 22 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 109.37 | 109.37
197 | BULANPUR AND ADJOINING MOUJAS PWSS (SM/14031) | SM/14031 | 461.25 | 1102 | NEW | 25 | Delayed | 27 | 05/12/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 123.52 | 115.2
198 | MANGAL BANDI AND ADJOINING MOUJAS PWSS (SM/15020) | SM/15020 | 596.58 | 1649 | NEW | 25 | Delayed | 23 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 137.34 | 137.34
199 | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14651) | SM/14651 | 516.44 | 1690 | NEW | 25 | Delayed | 19 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 99.39 | 99.39
200 | JAMUNA AND ADJOINING MOUJAS PWSS (SM/13056) | SM/13056 | 512.93 | 1788 | NEW | 26 | Delayed | 4 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 19.66 | 19.66
201 | BARAKEUNDI AND ADJOINING MOUJAS PWSS (SM/13002) | SM/13002 | 520.65 | 1445 | NEW | 26 | Delayed | 43 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 222.67 | 214.94
202 | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS (SM/13087) | SM/13087 | 747.82 | 2388 | NEW | 27 | Delayed | 53 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 398.16 | 398.16
203 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. (SM/19047) | SM/19047 | 1000.02 | 2739 | NEW | 27 | Delayed | 6 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 28/11/2023 | 61.17 | 56.68
204 | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/18540) | SM/18540 | 1571.76 | 3529 | NEW | 27 | Delayed | 22 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 01/08/2023 | 343.6 | 197.71
205 | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14997) | SM/14997 | 648.75 | 1741 | NEW | 27 | Delayed | 7 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 24/03/2023 | 46.34 | 46.34
206 | PALAIBANI AND ADJOINING MOUJAS PWSS (SM/15026) | SM/15026 | 341.93 | 563 | NEW | 28 | Delayed | 44 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 151.34 | 151.34
207 | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. (SM/19101) | SM/19101 | 1054.32 | 3442 | NEW | 28 | Delayed | 18 | 14/12/2023 | 31/03/2026 | 19/05/2025 | 18/12/2023 | 186.17 | 158.44
208 | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/15119) | SM/15119 | 790.98 | 1783 | NEW | 28 | Delayed | 8 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 62.84 | 47.49
209 | SASHA BEDIA AND ADJOINING MOUJAS PWSS (SM/18001) | SM/18001 | 995.57 | 2599 | NEW | 28 | Delayed | 44 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 10/04/2023 | 434.22 | 434.22
210 | PACHADAHARA & ADJOINING MOUJAS PWSS (SM/14732) | SM/14732 | 515.32 | 1729 | NEW | 28 | Delayed | 30 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 155.25 | 155.25
211 | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. (SM/18622) | SM/18622 | 1370.84 | 4213 | NEW | 29 | Delayed | 25 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 09/08/2023 | 340.19 | 233.1
212 | BISHNUPUR AND ADJOINING MOUJAS PWSS (SM/13006) | SM/13006 | 324.37 | 684 | NEW | 29 | Delayed | 31 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 99.45 | 97.88
213 | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/18586) | SM/18586 | 1080.54 | 2335 | NEW | 29 | Delayed | 31 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 09/08/2023 | 331.88 | 244.71
214 | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS (SM/13078) | SM/13078 | 554.62 | 1636 | NEW | 30 | Delayed | 39 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 10/04/2023 | 214.07 | 214.07
215 | BAGBASA AND ADJOINING MOUJAS PWSS (SM/13805) | SM/13805 | 532.96 | 1755 | NEW | 30 | Delayed | 44 | 22/11/2022 | 31/12/2025 | 19/05/2025 | 02/06/2023 | 231.93 | 217.88
216 | KANTAL AND ADJOINING MOUJAS PWSS (SM/13060) | SM/13060 | 497.33 | 1434 | NEW | 30 | Delayed | 8 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 37.73 | 37.73
217 | ABHAYA AND ADJOINING MOUJAS PWSS (SM/14689) | SM/14689 | 158.04 | 245 | NEW | 30 | Delayed | 26 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 41.64 | 41.64
218 | BAGRUI AND ITS ADJOINING MOUZAS PWSS (SM/19052) | SM/19052 | 1237.75 | 3124 | NEW | 30 | Delayed | 17 | 24/11/2023 | 29/11/2025 | 19/05/2025 | 29/11/2023 | 215.76 | 154.97
219 | NAYA BASAT AND ADJOINING MOUJAS PWSS (SM/14130) | SM/14130 | 921.59 | 2553 | NEW | 30 | Delayed | 27 | 02/01/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 247.48 | 247.48
220 | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/18502) | SM/18502 | 1663.94 | 2838 | NEW | 30 | Delayed | 10 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 160.35 | 160.35
221 | GARMAL AND ADJOINING MOUJAS PWSS (SM/14090) | SM/14090 | 482.26 | 950 | NEW | 30 | Delayed | 6 | 12/12/2022 | 07/11/2025 | 19/05/2025 | 24/07/2023 | 27.8 | 20.18
222 | LENGA MARA AND IT'S ADJOINING MOUJAS (SM/13094) | SM/13094 | 719.67 | 2249 | NEW | 30 | Delayed | 25 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 12/04/2023 | 176.92 | 176.92
223 | GHOSHPUR PIPED WATER SUPPLY SCHEME (SM/18535) | SM/18535 | 1126.19 | 3457 | NEW | 30 | Delayed | 15 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 163.61 | 163.61
224 | KUNARPUR AND ADJOINING MOUJAS PWSS (SM/13122) | SM/13122 | 551.76 | 1773 | NEW | 30 | Delayed | 25 | 10/10/2022 | 30/09/2025 | 19/05/2025 | 07/08/2023 | 138.29 | 138.29
225 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/12826) | SM/12826 | 380.48 | 0 | AUGMENTATION | 30 | Delayed | 10 | 22/09/2022 | 31/12/2025 | 19/05/2025 | 17/03/2022 | 37.56 | 37.56
226 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. (SM/19046) | SM/19046 | 1040.03 | 2571 | NEW | 30 | Delayed | 18 | 24/11/2023 | 31/03/2026 | 19/05/2025 | 29/11/2023 | 183.25 | 183.25
227 | DURIA AND ADJOINING MOUJAS PWSS (SM/13009) | SM/13009 | 738.92 | 1299 | NEW | 30 | Delayed | 2 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 12.08 | 12.08
228 | FATEHSINGPUR AND ADJOINING MOUJAS PWSS (SM/13062) | SM/13062 | 374.97 | 1095 | NEW | 30 | Delayed | 32 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 121.62 | 91.54
229 | KHARIPARA AND IT'S ADJOINING MOUJAS (SM/13125) | SM/13125 | 443.87 | 1525 | NEW | 30 | Delayed | 28 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 122.43 | 122.43
230 | BAGDOBA AND ADJOINING MOUJAS PWSS (SM/14690) | SM/14690 | 407.83 | 799 | NEW | 30 | Delayed | 25 | 31/01/2023 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 102.07 | 102.07
231 | PERUABAD AND ADJOINING MOUJAS PWSS (SM/13107) | SM/13107 | 416.62 | 1219 | NEW | 30 | Delayed | 48 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 200.17 | 178.74
232 | AMSOL AND ADJOINING MOUJAS PWSS (SM/13179) | SM/13179 | 405.45 | 1053 | NEW | 30 | Delayed | 23 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 93.84 | 93.84
233 | AMLASULI AND ADJOINING MOUJAS PWSS (SM/14989) | SM/14989 | 562.97 | 1681 | NEW | 30 | Delayed | 27 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 154.04 | 154.04
234 | SHAL DAHARA AND ADJOINING MOUJAS PWWSS (SM/18013) | SM/18013 | 353.79 | 528 | NEW | 30 | Delayed | 28 | 17/03/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 100.27 | 100.27
235 | MANIKDIPABARA AND AJOINING MOUJAS PWSS (SM/13097) | SM/13097 | 470.46 | 1551 | NEW | 30 | Delayed | 30 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 142.56 | 142.56
236 | GOTSHINGLA AND ADJOINING MOUJAS PWSS (SM/15010) | SM/15010 | 331.03 | 616 | NEW | 31 | Delayed | 23 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 76.61 | 76.61
237 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. (SM/13167) | SM/13167 | 984.13 | 3783 | NEW | 31 | Delayed | 49 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 480.93 | 480.93
238 | BALADAGHATA AND ADJOINING MOUJAS PWSS (SM/12990) | SM/12990 | 673.25 | 2473 | NEW | 31 | Delayed | 35 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 237.73 | 227.34
239 | DHOBABARIA AND ADJOINIONG MOUJAS PWSS (SM/13140) | SM/13140 | 695.29 | 2896 | NEW | 31 | Delayed | 29 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 202.13 | 202.13
240 | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS (SM/18524) | SM/18524 | 1114.38 | 2885 | NEW | 31 | Delayed | 20 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 224.1 | 224.1
241 | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS (SM/13038) | SM/13038 | 551.17 | 2027 | NEW | 31 | Delayed | 56 | 28/09/2022 | 31/03/2026 | 19/05/2025 | 20/03/2023 | 310.57 | 310.57
242 | ELUNI PIPED WATER SUPPLY SCHEME (SM/13081) | SM/13081 | 626.21 | 1756 | NEW | 32 | Delayed | 37 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 229.35 | 79.64
243 | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. (SM/18486) | SM/18486 | 3340.14 | 42531 | RETROFITTING | 32 | Delayed | 0 | 24/07/2023 | 31/03/2026 | 19/05/2025 | 10/08/2023 | 0 | 0
244 | SINNIBAR PIPED WATER SUPPLY SCHEME (SM/18527) | SM/18527 | 1143.77 | 3416 | NEW | 32 | Delayed | 2 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 27.44 | 27.44
245 | BHATUIGERYA PIPED WATER SUPPLY SCHEME (SM/15509) | SM/15509 | 1064.86 | 2554 | NEW | 32 | Delayed | 27 | 16/02/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 285.89 | 202.98
246 | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14131) | SM/14131 | 946.33 | 2711 | NEW | 33 | Delayed | 11 | 02/01/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 99.53 | 99.53
247 | KADAM DIHA AND ADJOINING MOUJAS PWSS (SM/15012) | SM/15012 | 302.22 | 536 | NEW | 33 | Delayed | 33 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 100.34 | 100.34
248 | SATPATI AND ADJOINING MOUJAS PWSS (SM/18009) | SM/18009 | 576.07 | 1796 | NEW | 33 | Delayed | 21 | 17/03/2023 | 07/11/2025 | 19/05/2025 | 30/10/2023 | 121.21 | 121.21
249 | NERASOL AND ADJOINING MOUJAS PWSS (SM/13103) | SM/13103 | 925.39 | 3131 | NEW | 33 | Delayed | 59 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 546.83 | 492.09
250 | PARBATIPUR AND ADJOINING MOUJAS PWSS (SM/13105) | SM/13105 | 958.61 | 3421 | NEW | 34 | Delayed | 28 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 264.09 | 232.36
251 | SHYAMNAGAR AND ADJOINING MOUJAS PWSS (SM/13173) | SM/13173 | 805.07 | 3356 | NEW | 34 | Delayed | 32 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 260.34 | 260.34
252 | MURAKATI AND ADJOINING MOUJAS PWSS (SM/14004) | SM/14004 | 468.71 | 1346 | NEW | 34 | Delayed | 29 | 05/12/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 138.11 | 138.11
253 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18028) | SM/18028 | 850.47 | 1649 | NEW | 34 | Delayed | 29 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 12/04/2023 | 244.93 | 244.93
254 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/15595) | SM/15595 | 978.29 | 2700 | NEW | 34 | Delayed | 13 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 27/03/2023 | 127.38 | 127.38
255 | DHENGADAHA AND ADJOINING MOUJAS PWSS (SM/13000) | SM/13000 | 482.32 | 1623 | NEW | 34 | Delayed | 48 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 232.87 | 232.87
256 | BARABOLABANDI AND ADJOINING MOUJAS PWSS (SM/13066) | SM/13066 | 364.98 | 963 | NEW | 34 | Delayed | 40 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 145.17 | 135.9
257 | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS (SM/14002) | SM/14002 | 151.1 | 309 | NEW | 34 | Delayed | 31 | 05/12/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 46.1 | 46.1
258 | PIRRAKULI AND ADJOINING MOUJAS PWSS (SM/15028) | SM/15028 | 558.66 | 1413 | NEW | 34 | Delayed | 36 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 02/06/2023 | 203.51 | 203.51
259 | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS (SM/18532) | SM/18532 | 1054.1 | 2792 | NEW | 34 | Delayed | 31 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 325.25 | 325.25
260 | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS (SM/12412) | SM/12412 | 443.43 | 1406 | NEW | 34 | Delayed | 37 | 13/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 165 | 129.49
261 | PUKHARIA SOL AND ADJOINING MOUJAS PWSS (SM/15029) | SM/15029 | 465.21 | 1022 | NEW | 35 | Delayed | 37 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 173.68 | 173.68
262 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. (SM/18184) | SM/18184 | 857.57 | 3060 | NEW | 35 | Delayed | 5 | 31/03/2023 | 31/12/2025 | 19/05/2025 | 12/04/2023 | 41.67 | 41.67
263 | KARNAGAR AND ADJOINING MAOUJAS PWSS (SM/13001) | SM/13001 | 561.85 | 1735 | NEW | 35 | Delayed | 26 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 17/07/2023 | 145.66 | 137.77
264 | SHAKHA BAI AND ADJOINING MOUJAS PWSS (SM/13220) | SM/13220 | 391.07 | 807 | NEW | 35 | Delayed | 36 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 140.58 | 140.58
265 | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. (SM/09084) | SM/09084 | 50.05 | 977 | RETROFITTING | 35 | Delayed | 39 | 28/10/2021 | 31/12/2025 | 19/05/2025 | 12/08/2022 | 19.63 | 19.63
266 | KUSUMPUR AND ADJOINING MOUJAS (SM/13093) | SM/13093 | 584.14 | 1958 | NEW | 35 | Delayed | 29 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 166.95 | 166.95
267 | KADAM BANDHI AND ADJOINING MOUJAS PWSS (SM/13058) | SM/13058 | 412.47 | 893 | NEW | 35 | Delayed | 47 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 192.7 | 157.29
268 | KARANJIMURA AND ADJOINING MOUJAS PWSS (SM/13061) | SM/13061 | 430.57 | 1476 | NEW | 35 | Delayed | 39 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 166.44 | 166.44
269 | BARAMURA AND ADJOINING MOUJAS PWSS (SM/12994) | SM/12994 | 465.08 | 1734 | NEW | 35 | Delayed | 37 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 30/10/2023 | 172.16 | 161.43
270 | THAUR AND ITS ADJOINING MOUZAS PWSS (SM/15906) | SM/15906 | 844.2 | 2748 | NEW | 35 | Delayed | 7 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 27/03/2023 | 56.55 | 56.55
271 | SAIYADPUR AND ADJOINING MOUJAS PWSS (SM/17996) | SM/17996 | 409.72 | 820 | NEW | 35 | Delayed | 35 | 17/03/2023 | 07/11/2025 | 19/05/2025 | 30/10/2023 | 143.5 | 143.5
272 | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/11898) | SM/11898 | 1602.83 | 6502 | AUGMENTATION | 35 | Delayed | 22 | 22/08/2022 | 31/12/2025 | 19/05/2025 | 24/06/2021 | 353.1 | 353.1
273 | KULDIHA AND ITS ADJOINING MOUZAS PWSS (SM/14655) | SM/14655 | 701.03 | 2237 | NEW | 35 | Delayed | 3 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 22.81 | 20.11
274 | AGRA & ADJOINING MOUJAS PWSS (SM/13052) | SM/13052 | 343.16 | 1728 | NEW | 35 | Delayed | 50 | 29/09/2022 | 08/02/2025 | 19/05/2025 | 21/09/2023 | 171.52 | 143.21
275 | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. (SM/18507) | SM/18507 | 1156.66 | 3430 | NEW | 35 | Delayed | 66 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 759.46 | 682.08
276 | ANAR AND ADJOINING MOUJAS PWSS (SM/13180) | SM/13180 | 614.95 | 2111 | NEW | 35 | Delayed | 28 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 171.66 | 171.66
277 | MADHUPUR AND ADJOINING MOUJAS PWSS (SM/14035) | SM/14035 | 517.09 | 1284 | NEW | 35 | Delayed | 42 | 05/12/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 217.01 | 217.01
278 | MURARI AND ADJOINING MOUJAS PWSS (SM/15021) | SM/15021 | 643.92 | 1713 | NEW | 35 | Delayed | 31 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 199.52 | 199.52
279 | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS (SM/16259) | SM/16259 | 614.44 | 1847 | NEW | 35 | Delayed | 33 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 201.37 | 201.37
280 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. (SM/13111) | SM/13111 | 455.02 | 1101 | NEW | 35 | Delayed | 4 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 16.96 | 16.96
281 | KANPUR AND ADJOINING MOUJAS PWSS (SM/13059) | SM/13059 | 562.67 | 1842 | NEW | 35 | Delayed | 28 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 157.16 | 152
282 | SONIAKON AND ADJOINING MOUJAS PWSS (SM/13221) | SM/13221 | 452.97 | 1507 | NEW | 35 | Delayed | 37 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 167.74 | 167.74
283 | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS (SM/14996) | SM/14996 | 378.53 | 837 | NEW | 35 | Delayed | 10 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 38.85 | 38.85
284 | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/15011) | SM/15011 | 236.77 | 472 | NEW | 35 | Delayed | 34 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 04/05/2023 | 79.81 | 79.81
285 | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16542) | SM/16542 | 684.72 | 2069 | NEW | 35 | Delayed | 26 | 10/03/2023 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 177.86 | 177.86
286 | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS (SM/18525) | SM/18525 | 1179.7 | 2053 | NEW | 36 | Delayed | 20 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 234.41 | 234.41
287 | PIASALA AND ADJOINING MOUJAS PWSS (SM/14628) | SM/14628 | 986.11 | 3077 | NEW | 36 | Delayed | 28 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 271.49 | 271.49
288 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE (SM/18032) | SM/18032 | 867.28 | 2189 | NEW | 36 | Delayed | 34 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 294.77 | 294.77
289 | MOHANPUR & ADJOINING MOUJAS PWSS (SM/13028) | SM/13028 | 556.08 | 1922 | NEW | 36 | Delayed | 51 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 284.19 | 248.33
290 | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/17575) | SM/17575 | 424.54 | 490 | NEW | 37 | Delayed | 14 | 18/03/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 59.48 | 59.48
291 | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. (SM/11879) | SM/11879 | 642.57 | 1700 | NEW | 37 | Delayed | 25 | 17/08/2022 | 07/11/2025 | 19/05/2025 | 21/03/2022 | 161.9 | 161.9
292 | PATHRI AND AJOINING MOUJAS (SM/13807) | SM/13807 | 455.19 | 1116 | NEW | 37 | Delayed | 31 | 22/11/2022 | 31/12/2025 | 19/05/2025 | 17/07/2023 | 139.74 | 139.74
293 | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14656) | SM/14656 | 604.67 | 1647 | NEW | 37 | Delayed | 18 | 31/01/2023 | 31/03/2026 | 19/05/2025 | 28/04/2023 | 111.8 | 105.55
294 | NAMJABA AND ADJOINING MOUJAS PWSS (SM/14723) | SM/14723 | 818.48 | 2741 | NEW | 37 | Delayed | 32 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 258.37 | 258.37
295 | BHANSRA AND ADJOINING MOUJAS PWSS (SM/13005) | SM/13005 | 531.78 | 1934 | NEW | 38 | Delayed | 30 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 157.04 | 140.81
296 | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. (SM/12876) | SM/12876 | 1524.21 | 5092 | NEW | 38 | Delayed | 25 | 23/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 377.28 | 377.28
297 | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/19049) | SM/19049 | 1423.36 | 3706 | NEW | 38 | Delayed | 23 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 29/11/2023 | 328.45 | 321.73
298 | BHATURBANDI AND ADJOINING MOUJAS PWSS (SM/14825) | SM/14825 | 302.13 | 491 | NEW | 38 | Delayed | 31 | 03/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 95.14 | 95.14
299 | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. (SM/12335) | SM/12335 | 726.75 | 2121 | NEW | 39 | Delayed | 45 | 09/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 325.74 | 294.12
300 | NAHARPUR AND ADJOINING MOUJAS PWSS (SM/15024) | SM/15024 | 883.16 | 2932 | NEW | 39 | Delayed | 11 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 22/03/2023 | 100.4 | 100.4
301 | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09421) | SM/09421 | 226.03 | 3130 | RETROFITTING | 40 | Delayed | 41 | 17/11/2021 | 31/12/2025 | 19/05/2025 | 03/06/2022 | 92.51 | 77.3
302 | BENACHAPRA AND ADJOINING MOUJAS PWSS (SM/14992) | SM/14992 | 401.48 | 1096 | NEW | 40 | Delayed | 27 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 110.12 | 110.12
303 | GILABANI AND ADJOINING MOUJAS PWSS (SM/13142) | SM/13142 | 688.15 | 2528 | NEW | 40 | Delayed | 29 | 12/10/2022 | 08/02/2025 | 19/05/2025 | 21/09/2023 | 198.8 | 198.8
304 | KUBIR CHAK PIPED WATER SUPPLY SCHEME (SM/14484) | SM/14484 | 810.71 | 1529 | NEW | 40 | Delayed | 23 | 20/01/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 185.5 | 181.92
305 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/18506) | SM/18506 | 1410.87 | 5272 | AUGMENTATION | 40 | Delayed | 37 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 526.13 | 517.15
306 | GAMA AND ADJOINING MOUJAS PWSS (SM/13083) | SM/13083 | 581.95 | 1955 | NEW | 40 | Delayed | 37 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 02/02/2023 | 215.35 | 215.35
307 | TORIA PIPED WATER SUPPLY SCHEME (SM/18494) | SM/18494 | 1100.72 | 2702 | NEW | 40 | Delayed | 29 | 26/07/2023 | 31/12/2025 | 19/05/2025 | 04/08/2023 | 323.51 | 323.51
308 | DUBRAJI AND ITS ADJOINING MOUZAS PWSS (SM/18533) | SM/18533 | 1086.95 | 3108 | NEW | 40 | Delayed | 52 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 561 | 561
309 | JADABBATI AND ADJOINING MOUJAS PWSS (SM/13143) | SM/13143 | 570.68 | 1829 | NEW | 40 | Delayed | 39 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 224.15 | 224.15
310 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/15072) | SM/15072 | 309.98 | 502 | AUGMENTATION | 40 | Delayed | 6 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 30/12/2022 | 20.07 | 20.07
311 | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur (SM/13026) | SM/13026 | 516.09 | 1515 | NEW | 40 | Delayed | 71 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 367.65 | 347.85
312 | Solarization of grid connected pumping installation at Barisha, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17343) | SM/17343 | 16.61 | 0 | SOLARISATION | 40 | Delayed | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
313 | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. (SM/09725) | SM/09725 | 41.57 | 399 | RETROFITTING | 40 | Delayed | 81 | 26/11/2021 | 29/08/2025 | 19/05/2025 | 01/12/2021 | 33.59 | 33.59
314 | BARANAGARA AND ADJOINING MOUJAS PWSS (SM/13003) | SM/13003 | 416.39 | 1424 | NEW | 40 | Delayed | 42 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 173.02 | 159.73
315 | KARSA AND ADJOINING MOUJAS PWSS (SM/13090) | SM/13090 | 422.45 | 921 | NEW | 40 | Delayed | 33 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 138.81 | 134.44
316 | PATHARISOL AND ADJOINING MOUJAS PWSS (SM/13030) | SM/13030 | 448.99 | 2128 | NEW | 40 | Delayed | 39 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 176.12 | 159.86
317 | GANUA AND ADJOINING MOUJAS PWSS (SM/15000) | SM/15000 | 871.74 | 2731 | NEW | 40 | Delayed | 0 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 22/03/2023 | 0 | 0
318 | MIRGA AND ADJOINING MOUJAS PWSS (SM/13099) | SM/13099 | 512.97 | 1297 | NEW | 40 | Delayed | 29 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 148.8 | 148.8
319 | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. (SM/14493) | SM/14493 | 582.95 | 1844 | NEW | 40 | Delayed | 31 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 180.56 | 180.56
320 | HARINASULI & ADJOINING MOUJAS PWSS (SM/13085) | SM/13085 | 619.34 | 2431 | NEW | 40 | Delayed | 57 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 355.81 | 252.23
321 | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION (SM/17565) | SM/17565 | 533.58 | 722 | NEW | 40 | Delayed | 7 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 21/03/2023 | 35.95 | 35.95
322 | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME (SM/18508) | SM/18508 | 1397.29 | 2819 | NEW | 40 | Delayed | 22 | 26/07/2023 | 08/02/2025 | 19/05/2025 | 04/08/2023 | 312.67 | 312.67
323 | KULBANI AND ADJOINING MOUJAS PWSS (SM/13121) | SM/13121 | 730.87 | 2763 | NEW | 40 | Delayed | 26 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 188.49 | 188.49
324 | BARDIHA AND ADJOINING MOUJAS PWSS (SM/14692) | SM/14692 | 231.83 | 428 | NEW | 40 | Delayed | 26 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 59.79 | 59.79
325 | Kutulpur Piped Water Supply Scheme. (SM/09988) | SM/09988 | 533.31 | 1428 | NEW | 41 | Delayed | 23 | 16/12/2021 | 31/12/2025 | 19/05/2025 | 20/09/2022 | 124.06 | 119.57
326 | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME (SM/13810) | SM/13810 | 819.54 | 2435 | NEW | 41 | Delayed | 31 | 22/11/2022 | 07/11/2025 | 19/05/2025 | 24/03/2023 | 250.53 | 241.31
327 | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. (SM/12875) | SM/12875 | 1450.08 | 4151 | NEW | 41 | Delayed | 28 | 23/09/2022 | 07/11/2025 | 19/05/2025 | 15/12/2022 | 400.25 | 400.25
328 | GAMARIA PIPED WATER SUPPLY SCHEME (SM/13141) | SM/13141 | 804.45 | 1611 | NEW | 42 | Delayed | 28 | 12/10/2022 | 08/02/2025 | 19/05/2025 | 31/12/2022 | 224.14 | 224.14
329 | KHARIKA AND ITS ADJOINING MOUZAS PWSS (SM/15015) | SM/15015 | 981.96 | 2790 | NEW | 42 | Delayed | 27 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 267.04 | 220.53
330 | KUTKI AND ADJOINING MOUJAS PWSS (SM/15016) | SM/15016 | 616.35 | 1711 | NEW | 42 | Delayed | 8 | 04/02/2023 | 30/06/2025 | 19/05/2025 | 27/03/2023 | 50.91 | 50.91
331 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. (SM/16252) | SM/16252 | 999.16 | 2767 | NEW | 42 | Delayed | 30 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 25/04/2023 | 296.79 | 296.79
332 | RUPARGHAGRA AND ADJOINING MOUJAS PWSS (SM/13108) | SM/13108 | 307.94 | 507 | NEW | 42 | Delayed | 42 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 130.51 | 130.19
333 | HATKATA AND ITS ADJOINING MOUZAS PWSS (SM/15592) | SM/15592 | 908.02 | 2882 | NEW | 42 | Delayed | 36 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 27/03/2023 | 330.16 | 330.16
334 | GODAPIASOL AND ADJOINING MOUJAS PWSS (SM/13077) | SM/13077 | 352.83 | 837 | NEW | 42 | Delayed | 23 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 17/07/2023 | 82.58 | 82.58
335 | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I (SM/19102) | SM/19102 | 1449.22 | 4183 | NEW | 42 | Delayed | 11 | 14/12/2023 | 31/03/2026 | 19/05/2025 | 18/12/2023 | 164.16 | 159.46
336 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18235) | SM/18235 | 1084.55 | 3516 | NEW | 44 | Delayed | 31 | 12/06/2023 | 31/12/2025 | 19/05/2025 | 22/06/2023 | 331.55 | 331.55
337 | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/19043) | SM/19043 | 1038.63 | 2144 | NEW | 44 | Delayed | 45 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 29/11/2023 | 464.78 | 433.45
338 | SANTRAPUR AND ADJOINING MOUJAS PWSS (SM/13219) | SM/13219 | 542.41 | 1983 | NEW | 45 | Delayed | 22 | 12/10/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 121.55 | 118.74
339 | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. (SM/16378) | SM/16378 | 758.08 | 2648 | NEW | 45 | Delayed | 45 | 28/02/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 343.86 | 343.86
340 | ANGUA AND ADJOINING MOUJAS PWSS (SM/12989) | SM/12989 | 403.88 | 1045 | NEW | 45 | Delayed | 16 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 06/03/2023 | 63.71 | 52.9
341 | SINGLA AND IT'S ADJOINING MOUJAS (SM/13110) | SM/13110 | 317.84 | 725 | NEW | 45 | Delayed | 47 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 149.18 | 138.83
342 | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/14479) | SM/14479 | 528.53 | 327 | AUGMENTATION | 45 | Delayed | 57 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 23/08/2022 | 301.33 | 301.33
343 | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS (SM/13057) | SM/13057 | 467.81 | 1565 | NEW | 45 | Delayed | 23 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 105.59 | 53.8
344 | CHANDANA AND ADJOINING MOUJAS PWSS (SM/13074) | SM/13074 | 347.23 | 835 | NEW | 45 | Delayed | 32 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 110.48 | 107.59
345 | TELIJANT AND IT'S ADJOINING MOUJAS PWSS (SM/13175) | SM/13175 | 751.27 | 2372 | NEW | 45 | Delayed | 44 | 12/10/2022 | 08/02/2025 | 19/05/2025 | 21/09/2023 | 333.97 | 333.97
346 | GAGANESHWAR AND ADJOINING MOUJAS PWSS (SM/13082) | SM/13082 | 903.4 | 2546 | NEW | 45 | Delayed | 36 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 325.96 | 325.96
347 | KUSUMDAHARI PIPED WATER SUPPLY SCHEME (SM/18531) | SM/18531 | 1253.84 | 1869 | NEW | 45 | Delayed | 31 | 26/07/2023 | 08/02/2025 | 19/05/2025 | 04/08/2023 | 385.21 | 184.86
348 | PATHARTERIA AND ADJOINING MOUJAS PWSS (SM/13106) | SM/13106 | 471.45 | 1013 | NEW | 45 | Delayed | 45 | 10/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 214.16 | 195
349 | TEGHARI AND ITS ADJOINING MOUZAS PWSS (SM/15594) | SM/15594 | 907.61 | 2049 | NEW | 45 | Delayed | 14 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 27/03/2023 | 124.35 | 25.12
350 | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. (SM/19044) | SM/19044 | 1212.3 | 2568 | NEW | 45 | Delayed | 59 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 29/11/2023 | 720.08 | 720.08
351 | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS (SM/18526) | SM/18526 | 1264.33 | 4023 | NEW | 45 | Delayed | 32 | 26/07/2023 | 07/11/2025 | 19/05/2025 | 04/08/2023 | 404.94 | 404.94
352 | SAORAPIR AND ADJOINING MOUJAS PWSS (SM/13172) | SM/13172 | 345.99 | 957 | NEW | 45 | Delayed | 11 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 24/03/2023 | 37.9 | 37.9
353 | KADRA AND ADJOINING MOUJAS PWSS (SM/13144) | SM/13144 | 398.56 | 1184 | NEW | 45 | Delayed | 63 | 12/10/2022 | 30/11/2025 | 19/05/2025 | 13/03/2023 | 252.25 | 252.25
354 | MARKHA AND ITS ADJOINING MOUZAS PWSS (SM/15593) | SM/15593 | 990.58 | 3197 | NEW | 45 | Delayed | 31 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 27/03/2023 | 307.23 | 262.55
355 | BABAIBASA AND ADJOINING MOUJAS PWSS (SM/13753) | SM/13753 | 387.81 | 972 | NEW | 45 | Delayed | 38 | 17/11/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 148.63 | 148.63
356 | JHARBHANGA AND ADJOINING MOUJAS PWSS (SM/14652) | SM/14652 | 696.1 | 1882 | NEW | 45 | Delayed | 47 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 326.73 | 326.73
357 | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. (SM/17946) | SM/17946 | 580.85 | 657 | AUGMENTATION | 47 | Delayed | 12 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 30/09/2022 | 72.47 | 17.77
358 | KONTORE AND ADJOINING MOUJAS PWSS (SM/13113) | SM/13113 | 371.42 | 1030 | NEW | 47 | Delayed | 39 | 10/10/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 143.96 | 143.96
359 | MAHASOL AND ADJOINING MOUJAS PWSS (SM/14036) | SM/14036 | 579.21 | 1526 | NEW | 47 | Delayed | 41 | 05/12/2022 | 31/12/2025 | 19/05/2025 | 14/07/2023 | 237.82 | 237.82
360 | DINGAL AND ITS ADJOINING MOUJAS PWSS (SM/12828) | SM/12828 | 477.55 | 1388 | NEW | 48 | Delayed | 64 | 22/09/2022 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 306.51 | 306.51
361 | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/15533) | SM/15533 | 1680.25 | 4781 | NEW | 48 | Delayed | 23 | 16/02/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 394.09 | 392.57
362 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT PIRAKATA AND OTHER 35 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. (SM/17184) | SM/17184 | 72.89 | 0 | AUGMENTATION | 50 | Delayed | 42 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 30/03/2023 | 30.32 | 30.32
363 | BARBHUNA BASAN STAND ALONE PWSS (SM/12841) | SM/12841 | 55.5 | 102 | NEW | 50 | Delayed | 8 | 22/09/2022 | 08/02/2025 | 19/05/2025 | 27/03/2023 | 4.35 | 4.35
364 | Monoharpur Piped Water Supply Scheme. (SM/10017) | SM/10017 | 928.81 | 257 | NEW | 50 | Delayed | 27 | 30/12/2021 | 31/05/2025 | 19/05/2025 | 07/09/2022 | 255.13 | 255.13
365 | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS (SM/12999) | SM/12999 | 391.87 | 1429 | NEW | 50 | Delayed | 13 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 52.06 | 52.06
366 | SOLPOTA AND ADJOINING MOUJAS PWSS (SM/13174) | SM/13174 | 462.56 | 1358 | NEW | 50 | Delayed | 44 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 204.44 | 204.44
367 | MAHISAMURA PWSS (SM/13095) | SM/13095 | 455.65 | 1396 | NEW | 50 | Delayed | 30 | 10/10/2022 | 08/02/2025 | 19/05/2025 | 26/10/2023 | 134.98 | 134.98
368 | BARANGI AND ADJOINING MOUJAS PWSS (SM/12996) | SM/12996 | 692.38 | 2375 | NEW | 50 | Delayed | 28 | 28/09/2022 | 31/03/2026 | 19/05/2025 | 06/03/2023 | 192.96 | 192.96
369 | PANCHYAR AND ADJOINING MOUJAS PWSS (SM/13216) | SM/13216 | 502.34 | 1494 | NEW | 50 | Delayed | 20 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 101.63 | 101.63
370 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/15218) | SM/15218 | 132.3 | 0 | AUGMENTATION | 50 | Delayed | 70 | 07/02/2023 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 92.19 | 92.19
371 | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/14483) | SM/14483 | 1112.97 | 2422 | NEW | 50 | Delayed | 36 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 04/05/2023 | 405.78 | 401.17
372 | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION (SM/17568) | SM/17568 | 572.61 | 1153 | NEW | 50 | Delayed | 6 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 35.98 | 35.98
373 | BARAKALANKI AND ADJOINING MOUJAS PWSS (SM/13067) | SM/13067 | 580.05 | 1981 | NEW | 50 | Delayed | 41 | 29/09/2022 | 31/03/2026 | 19/05/2025 | 02/02/2023 | 239.18 | 239.18
374 | KADABANI AND ADJOINING MOUJAS PWSS (SM/18188) | SM/18188 | 298.95 | 792 | NEW | 50 | Delayed | 41 | 31/03/2023 | 08/02/2025 | 19/05/2025 | 12/04/2023 | 121.28 | 121.28
375 | AMDA AND ADJOINING MOUJAS PWSS (SM/13177) | SM/13177 | 502.42 | 1406 | NEW | 50 | Delayed | 25 | 12/10/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 125.21 | 125.21
376 | BARA MAHANPUR AND ADJOINING MOUJAS PWSS (SM/14941) | SM/14941 | 469.58 | 1551 | NEW | 50 | Delayed | 27 | 03/02/2023 | 07/11/2025 | 19/05/2025 | 06/03/2023 | 127.03 | 127.03
377 | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. (SM/17820) | SM/17820 | 24.79 | 0 | AUGMENTATION | 50 | Delayed | 33 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 8.24 | 8.24
378 | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. (SM/19051) | SM/19051 | 2476.73 | 1140 | AUGMENTATION | 50 | Delayed | 6 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 29/11/2023 | 140.38 | 16.07
379 | NARMA AND ADJOINING MOUJAS PWSS (SM/18229) | SM/18229 | 1112.06 | 3347 | NEW | 51 | Delayed | 29 | 15/05/2023 | 07/11/2025 | 19/05/2025 | 25/10/2023 | 326.58 | 326.58
380 | BIKRAMPUR PWSS (SM/12203) | SM/12203 | 461.76 | 1430 | NEW | 52 | Delayed | 58 | 07/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 266.38 | 223.16
381 | BARAKADRA AND ADJOINING MOUJAS PWSS (SM/14991) | SM/14991 | 482.93 | 1409 | NEW | 52 | Delayed | 43 | 04/02/2023 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 206.93 | 206.93
382 | KALAGRAM AND ITS ADJOINING MOUZAS PWSS (SM/15013) | SM/15013 | 830.33 | 2756 | NEW | 53 | Delayed | 43 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 06/04/2023 | 356.89 | 353.4
383 | CHANDABILA & ADJOINING MOUJAS PWSS (SM/13054) | SM/13054 | 399.22 | 1049 | NEW | 53 | Delayed | 59 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 236.38 | 211.65
384 | DOSATINA AND ITS ADJOINING MOUZAS PWSS (SM/15589) | SM/15589 | 979.63 | 3208 | NEW | 54 | Delayed | 55 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 27/03/2023 | 542.45 | 537.2
385 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18027) | SM/18027 | 737.78 | 1761 | NEW | 54 | Delayed | 43 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 10/04/2023 | 320.19 | 320.19
386 | KESHIA AND ADJOINING MOUJAS PWSS (SM/13124) | SM/13124 | 504.98 | 1553 | NEW | 54 | Delayed | 50 | 10/10/2022 | 31/03/2026 | 19/05/2025 | 13/03/2023 | 251.11 | 251.11
387 | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/15017) | SM/15017 | 556.8 | 1396 | NEW | 55 | Delayed | 52 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 23/02/2023 | 288.04 | 287.9
388 | KHAS JANGAL PIPED WATER SUPPLY SCHEME (SM/14506) | SM/14506 | 920.87 | 1970 | NEW | 55 | Delayed | 40 | 20/01/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 369.9 | 369.9
389 | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/15590) | SM/15590 | 198.18 | 679 | NEW | 55 | Delayed | 34 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 05/04/2023 | 67.98 | 67.98
390 | GHRITAGRAM AND ADJOINING MOUJAS PWSS (SM/14648) | SM/14648 | 921.37 | 2324 | NEW | 55 | Delayed | 24 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 223.66 | 223.66
391 | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS (SM/18583) | SM/18583 | 1274.01 | 3445 | NEW | 55 | Delayed | 51 | 31/07/2023 | 31/12/2025 | 19/05/2025 | 09/08/2023 | 650.31 | 638.69
392 | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS (SM/13089) | SM/13089 | 321.5 | 886 | NEW | 55 | Delayed | 64 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 28/03/2023 | 205.71 | 205.71
393 | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. (SM/15092) | SM/15092 | 459.82 | 1326 | AUGMENTATION | 55 | Delayed | 30 | 04/02/2023 | 31/03/2026 | 19/05/2025 | 30/09/2022 | 138.9 | 138.9
394 | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17559) | SM/17559 | 641 | 1404 | NEW | 55 | Delayed | 41 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 262.18 | 240.27
395 | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/19050) | SM/19050 | 1217.19 | 6478 | AUGMENTATION | 56 | On track | 22 | 24/11/2023 | 01/11/2026 | 19/05/2025 | 29/11/2023 | 270.95 | 267.58
396 | TUTRANGA AND ADJOINING MOUJAS PWSS (SM/13131) | SM/13131 | 477.78 | 1539 | NEW | 60 | Delayed | 22 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 106.97 | 106.97
397 | Retrofitting to accommodate FHTC under JJM in Khagragerya PWSS under Sbang Block in Paschim Medinipur District (SM/09709) | SM/09709 | 125.44 | 2433 | RETROFITTING | 60 | Delayed | 35 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 10/12/2021 | 43.38 | 43.38
398 | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS (SM/15025) | SM/15025 | 556.37 | 1488 | NEW | 60 | Delayed | 35 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 193.28 | 193.28
399 | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & (SM/16202) | SM/16202 | 502.93 | 2600 | NEW | 60 | Delayed | 51 | 23/02/2023 | 31/12/2025 | 19/05/2025 | 17/03/2023 | 255.46 | 245.65
400 | KHURSI AND ADJOINING MOUJAS PWSS (SM/13126) | SM/13126 | 642.36 | 2556 | NEW | 60 | Delayed | 44 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 285.47 | 285.47
401 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE (SM/15569) | SM/15569 | 469.04 | 2835 | AUGMENTATION | 60 | Delayed | 26 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 30/12/2022 | 119.87 | 119.87
402 | Solarization of grid connected pumping installation at Dhamsai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17320) | SM/17320 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
403 | Panna Piped Water Supply Scheme. (SM/10065) | SM/10065 | 407.47 | 868 | NEW | 60 | Delayed | 34 | 27/01/2022 | 31/12/2025 | 19/05/2025 | 12/08/2022 | 138.08 | 134.96
404 | DUDHE BUDE AND ADJOINING MOUJAS PWSS (SM/13080) | SM/13080 | 699.28 | 2195 | NEW | 60 | Delayed | 29 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 201.09 | 192.27
405 | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17560) | SM/17560 | 723.92 | 1614 | NEW | 60 | Delayed | 42 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 301.99 | 301.99
406 | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17572) | SM/17572 | 740.3 | 1707 | NEW | 60 | Delayed | 22 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 163.63 | 163.63
407 | RERIPUR AND ADJ0INING MOUJAS PWSS (SM/18530) | SM/18530 | 1185.9 | 3833 | NEW | 60 | Delayed | 32 | 26/07/2023 | 08/02/2025 | 19/05/2025 | 25/10/2023 | 384.42 | 384.42
408 | BHIKUBAR AND ADJOINING MOUJAS PWSS (SM/13071) | SM/13071 | 404.49 | 1208 | NEW | 60 | Delayed | 33 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 134 | 134
409 | BHETIAMLA AND ADJOINING MOUJAS PWSS (SM/12998) | SM/12998 | 539.86 | 1671 | NEW | 60 | Delayed | 24 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 128.69 | 128.69
410 | RADHANAGAR AND ADJOINING MOUJAS PWSS (SM/13217) | SM/13217 | 669 | 2155 | NEW | 60 | Delayed | 13 | 12/10/2022 | 30/06/2025 | 19/05/2025 | 07/08/2023 | 85.05 | 85.05
411 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/15219) | SM/15219 | 145.33 | 0 | AUGMENTATION | 60 | Delayed | 65 | 07/02/2023 | 07/11/2025 | 19/05/2025 | 27/09/2021 | 93.78 | 86.94
412 | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. (SM/17562) | SM/17562 | 919.79 | 2208 | NEW | 60 | Delayed | 38 | 18/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 351.69 | 344.83
413 | DAKSHINDIHA AND ADJOINING MOUJAS PWSS (SM/13079) | SM/13079 | 482.22 | 1519 | NEW | 60 | Delayed | 37 | 29/09/2022 | 07/11/2025 | 19/05/2025 | 26/10/2023 | 179.73 | 160.42
414 | Rejuvenation of Electro-Mechanical components of Lutunia PWSS in the District of Paschim Medinipur under JJM programme. (SM/17792) | SM/17792 | 12.39 | 0 | AUGMENTATION | 60 | Delayed | 48 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 5.98 | 5.98
415 | GOHALDANGA AND ADJOINING MOUJAS PWSS (SM/15004) | SM/15004 | 607.84 | 1538 | NEW | 60 | Delayed | 41 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 13/03/2023 | 249.32 | 249.32
416 | AMLA BANI AND ITS ADJOINING MOUZAS PWSS (SM/18584) | SM/18584 | 1219.81 | 2353 | NEW | 60 | Delayed | 56 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 09/08/2023 | 678.58 | 676.65
417 | ASTI AND ADJOINING MOUJAS PWSS (SM/13655) | SM/13655 | 780.7 | 3312 | NEW | 61 | Delayed | 4 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 34.05 | 34.05
418 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. (SM/10124) | SM/10124 | 1049.92 | 213 | AUGMENTATION | 61 | Delayed | 56 | 08/02/2022 | 30/11/2025 | 19/05/2025 | 09/03/2022 | 586.67 | 580.46
419 | Retrofitting to accommodate FHTC under JJM in Chandipur PWSS under Daspur-I Block in Paschim Medinipur District (SM/09702) | SM/09702 | 97.46 | 1938 | RETROFITTING | 62 | Delayed | 19 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 01/12/2021 | 18.26 | 15.8
420 | MELERACHAK AND ITS ADJOINING MOUZAS PWSS (SM/18587) | SM/18587 | 1114.57 | 3612 | NEW | 62 | Delayed | 51 | 31/07/2023 | 07/11/2025 | 19/05/2025 | 09/08/2023 | 573.2 | 573.2
421 | UTATR KARKARA AND ADJOINING MOUJAS PWSS (SM/13129) | SM/13129 | 533.93 | 1863 | NEW | 64 | Delayed | 16 | 10/10/2022 | 30/06/2025 | 19/05/2025 | 07/08/2023 | 84.09 | 84.09
422 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. (SM/13822) | SM/13822 | 439.58 | 2456 | AUGMENTATION | 65 | Delayed | 21 | 25/11/2022 | 31/12/2025 | 19/05/2025 | 11/01/2021 | 93.66 | 93.66
423 | PAKURSENI AND ADJOINING MOUJAS PWSS (SM/13104) | SM/13104 | 807.74 | 2623 | NEW | 65 | Delayed | 34 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 02/02/2023 | 273.19 | 273.19
424 | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS (SM/12200) | SM/12200 | 276.09 | 832 | NEW | 65 | Delayed | 59 | 07/09/2022 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 161.73 | 147.75
425 | KUKRADA AND ITS ADJOINING MOUZAS PWSS (SM/14654) | SM/14654 | 668.88 | 2191 | NEW | 65 | Delayed | 20 | 31/01/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 130.47 | 130.47
426 | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME (SM/16374) | SM/16374 | 786.27 | 2432 | NEW | 65 | On track | 34 | 28/02/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 268.17 | 265.69
427 | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. (SM/11622) | SM/11622 | 902.09 | 2926 | NEW | 65 | Delayed | 33 | 26/07/2022 | 31/12/2025 | 19/05/2025 | 21/11/2022 | 296.49 | 296.49
428 | DUAN-II AND ITS ADJOINING MOUJAS PWSS (SM/17616) | SM/17616 | 537.93 | 1560 | NEW | 65 | Delayed | 68 | 21/03/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 366.24 | 366.24
429 | ANTRI AND ADJOINING MOUJAS PWSS (SM/13636) | SM/13636 | 880.01 | 3227 | NEW | 65 | Delayed | 42 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 371.97 | 358.44
430 | KASHBA AND ITS ADJOINING MOUZAS PWSS (SM/14653) | SM/14653 | 291.2 | 514 | NEW | 65 | On track | 19 | 31/01/2023 | 31/12/2025 | 19/05/2025 | 30/05/2023 | 55.17 | 55.17
431 | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS (SM/17004) | SM/17004 | 827.32 | 1871 | NEW | 65 | On track | 50 | 16/03/2023 | 31/12/2025 | 19/05/2025 | 25/04/2023 | 414.64 | 366.56
432 | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. (SM/09933) | SM/09933 | 902.55 | 4583 | AUGMENTATION | 70 | Delayed | 59 | 13/12/2021 | 31/08/2025 | 19/05/2025 | 10/08/2021 | 532.77 | 532.77
433 | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS (SM/12410) | SM/12410 | 368.13 | 1115 | NEW | 70 | On track | 72 | 13/09/2022 | 07/11/2025 | 19/05/2025 | 24/03/2023 | 264.38 | 216.27
434 | KATAI AND IT'S ADJOINING MOUJAS PWSS (SM/13088) | SM/13088 | 459.37 | 1585 | NEW | 70 | Delayed | 53 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 241.76 | 220.5
435 | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/14481) | SM/14481 | 484.52 | 211 | AUGMENTATION | 70 | On track | 52 | 20/01/2023 | 31/03/2026 | 19/05/2025 | 23/08/2022 | 253.34 | 250.9
436 | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS (SM/14995) | SM/14995 | 643.38 | 1946 | NEW | 70 | On track | 43 | 04/02/2023 | 07/11/2025 | 19/05/2025 | 20/03/2023 | 278.12 | 278.12
437 | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/19053) | SM/19053 | 1504.74 | 3462 | NEW | 70 | On track | 13 | 24/11/2023 | 02/09/2026 | 19/05/2025 | 29/11/2023 | 196.45 | 189.66
438 | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. (SM/10649) | SM/10649 | 849.85 | 2611 | NEW | 70 | Delayed | 51 | 22/04/2022 | 31/12/2025 | 19/05/2025 | 30/09/2021 | 436.99 | 436.99
439 | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS (SM/17620) | SM/17620 | 584.61 | 1792 | NEW | 70 | On track | 58 | 21/03/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 338.66 | 319.36
440 | BENADIHA AND ADJOINING MOUJAS PWSS (SM/14993) | SM/14993 | 858.52 | 3218 | NEW | 70 | On track | 51 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 18/07/2023 | 438.23 | 438.23
441 | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division (SM/07876) | SM/07876 | 99.92 | 2038 | RETROFITTING | 70 | Delayed | 15 | 19/01/2021 | 31/07/2025 | 19/05/2025 | 26/11/2020 | 15.04 | 15.04
442 | Amjor Piped Water Supply Scheme. (SM/10318) | SM/10318 | 510.66 | 1352 | NEW | 72 | On track | 42 | 04/03/2022 | 31/12/2025 | 19/05/2025 | 27/06/2022 | 215.94 | 212.24
443 | AMJOR AND ADJOINING MOUJAS PWSS (SM/13707) | SM/13707 | 350.18 | 863 | NEW | 72 | On track | 1 | 14/11/2022 | 31/12/2025 | 19/05/2025 | 14/07/2023 | 2.5 | 0
444 | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS (SM/13024) | SM/13024 | 388.14 | 1029 | NEW | 72 | Delayed | 62 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 241.12 | 232.88
445 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. (SM/18234) | SM/18234 | 1444.1 | 4219 | NEW | 73 | On track | 30 | 12/06/2023 | 31/10/2025 | 19/05/2025 | 22/06/2023 | 437.87 | 437.87
446 | MURAKATA AND ADJOINING MOUJAS PWSS (SM/13100) | SM/13100 | 643.19 | 2133 | NEW | 73 | On track | 47 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 07/08/2023 | 303.2 | 303.2
447 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. (SM/15567) | SM/15567 | 370.93 | 325 | AUGMENTATION | 74 | On track | 19 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 30/12/2022 | 68.62 | 59.01
448 | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09107) | SM/09107 | 69.43 | 824 | RETROFITTING | 75 | Delayed | 50 | 28/10/2021 | 31/10/2025 | 19/05/2025 | 24/12/2021 | 34.99 | 34.99
449 | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/19048) | SM/19048 | 1163.14 | 3751 | NEW | 75 | On track | 21 | 24/11/2023 | 31/12/2025 | 19/05/2025 | 29/11/2023 | 240.94 | 240.94
450 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10821) | SM/10821 | 196.55 | 0 | AUGMENTATION | 75 | On track | 84 | 27/05/2022 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 165.32 | 165.32
451 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/12825) | SM/12825 | 414.31 | 0 | AUGMENTATION | 75 | On track | 25 | 22/09/2022 | 31/12/2025 | 19/05/2025 | 21/03/2022 | 103.67 | 96.15
452 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/15570) | SM/15570 | 384.24 | 317 | AUGMENTATION | 75 | On track | 19 | 15/02/2023 | 07/11/2025 | 19/05/2025 | 30/12/2022 | 72.83 | 72.83
453 | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION (SM/17005) | SM/17005 | 773.92 | 1707 | NEW | 75 | On track | 31 | 16/03/2023 | 07/11/2025 | 19/05/2025 | 25/04/2023 | 239.59 | 239.01
454 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/15084) | SM/15084 | 408.2 | 522 | AUGMENTATION | 75 | Delayed | 14 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 30/12/2022 | 56.86 | 56.86
455 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/18172) | SM/18172 | 948.79 | 3044 | NEW | 75 | On track | 46 | 29/03/2023 | 07/11/2025 | 19/05/2025 | 29/08/2023 | 436.87 | 436.87
456 | BAMANDA AND ADJOINING MOUJAS PWSS (SM/12993) | SM/12993 | 564.82 | 2299 | NEW | 75 | Delayed | 58 | 28/09/2022 | 30/06/2025 | 19/05/2025 | 01/11/2022 | 330.08 | 292.64
457 | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS (SM/13084) | SM/13084 | 642.4 | 2399 | NEW | 75 | On track | 46 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 297.99 | 271.8
458 | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/14492) | SM/14492 | 821.55 | 1909 | NEW | 75 | On track | 55 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 20/03/2023 | 448.43 | 448.43
459 | SALIKOTHA AND ADJOINING MOUJAS PWSS (SM/13171) | SM/13171 | 976.28 | 3481 | NEW | 75 | On track | 54 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 02/05/2023 | 528.94 | 485.2
460 | Retrofitting to accommodate FHTC under JJM in Bajpara PWSS under Midnapore Sadar Block in Paschim Medinipur District (SM/09704) | SM/09704 | 78.3 | 1524 | RETROFITTING | 75 | Delayed | 64 | 26/11/2021 | 31/07/2025 | 19/05/2025 | 01/12/2021 | 50 | 45.24
461 | TRIKALPUR AND ADJOINING MOUJAS PWSS (SM/13112) | SM/13112 | 512.54 | 1509 | NEW | 75 | Delayed | 36 | 10/10/2022 | 30/06/2025 | 19/05/2025 | 07/08/2023 | 186.02 | 186.02
462 | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS (SM/06931) | SM/06931 | 98.97 | 2050 | RETROFITTING | 76 | Delayed | 40 | 09/10/2020 | 29/08/2025 | 19/05/2025 | 26/11/2020 | 39.39 | 39.39
463 | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS (SM/14939) | SM/14939 | 376.72 | 1218 | NEW | 76 | On track | 66 | 03/02/2023 | 31/12/2025 | 19/05/2025 | 04/05/2023 | 248.76 | 241.2
464 | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/10717) | SM/10717 | 56.09 | 187 | NEW | 76 | On track | 69 | 18/05/2022 | 31/12/2025 | 19/05/2025 | 29/12/2022 | 38.73 | 29.27
465 | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/10657) | SM/10657 | 165.46 | 514 | NEW | 76 | On track | 56 | 22/04/2022 | 31/12/2025 | 19/05/2025 | 17/08/2021 | 93.1 | 93.1
466 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/15572) | SM/15572 | 348.84 | 280 | AUGMENTATION | 76 | Delayed | 8 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 30/12/2022 | 27.26 | 27.26
467 | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. (SM/09086) | SM/09086 | 140.08 | 2763 | RETROFITTING | 77 | Delayed | 63 | 28/10/2021 | 31/12/2025 | 19/05/2025 | 17/12/2021 | 87.79 | 79.78
468 | Gobindanagar Piped Water Supply Scheme (SM/10066) | SM/10066 | 412.08 | 1360 | NEW | 78 | On track | 88 | 27/01/2022 | 31/10/2025 | 19/05/2025 | 23/08/2021 | 362.47 | 359.88
469 | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. (SM/14999) | SM/14999 | 610.33 | 2225 | NEW | 79 | On track | 48 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 28/04/2023 | 292.87 | 251.08
470 | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS (SM/06903) | SM/06903 | 99.71 | 2034 | RETROFITTING | 80 | Delayed | 79 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 78.49 | 77.76
471 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. (SM/10091) | SM/10091 | 1772.16 | 9572 | AUGMENTATION | 80 | Delayed | 39 | 01/02/2022 | 31/07/2025 | 19/05/2025 | 30/08/2021 | 687.08 | 686.35
472 | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme. (SM/17754) | SM/17754 | 12.39 | 0 | AUGMENTATION | 80 | On track | 70 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 8.64 | 8.64
473 | Solarization of grid connected pumping installation at Chandpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17360) | SM/17360 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
474 | Solarization of grid connected pumping installation at Gobardhanpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17310) | SM/17310 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 0 | 0
475 | Solarization of grid connected pumping installation at Karkai PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17311) | SM/17311 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
476 | Solarization of grid connected pumping installation at Khasbar, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17326) | SM/17326 | 16.61 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
477 | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17300) | SM/17300 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
478 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/15217) | SM/15217 | 75.1 | 0 | AUGMENTATION | 80 | On track | 97 | 07/02/2023 | 31/12/2025 | 19/05/2025 | 27/09/2021 | 72.85 | 72.85
479 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/15905) | SM/15905 | 400.66 | 998 | AUGMENTATION | 80 | Delayed | 18 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 07/09/2022 | 70.42 | 70.42
480 | Solarization of grid connected pumping installation at Chaita PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/16983) | SM/16983 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 16/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
481 | Solarization of grid connected pumping installation Adasimla PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17759) | SM/17759 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
482 | Solarization of grid connected pumping installation Shanrpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17737) | SM/17737 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
483 | Rejuvenation of Electro-Mechanical components of Gobardhanpur PWSS in the District of Paschim Medinipur under JJM programme. (SM/17822) | SM/17822 | 12.39 | 0 | AUGMENTATION | 80 | On track | 8 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0.96 | 0.96
484 | Solarization of grid connected pumping installation at Debra PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/18120) | SM/18120 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 31/03/2023 | 0 | 0
485 | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17733) | SM/17733 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
486 | Solarization of grid connected pumping installation at Bajpara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17316) | SM/17316 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
487 | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME (SM/12997) | SM/12997 | 819.71 | 2374 | NEW | 80 | On track | 51 | 28/09/2022 | 31/12/2025 | 19/05/2025 | 23/02/2023 | 414.26 | 414.26
488 | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09420) | SM/09420 | 181.41 | 3350 | RETROFITTING | 80 | Delayed | 2 | 17/11/2021 | 30/09/2025 | 19/05/2025 | 23/06/2021 | 3.08 | 3.08
489 | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/13123) | SM/13123 | 482.44 | 652 | AUGMENTATION | 80 | On track | 39 | 10/10/2022 | 31/12/2025 | 19/05/2025 | 24/01/2023 | 187.35 | 187.35
490 | SARANG AND ADJOINING MOUJAS PWSS (SM/13809) | SM/13809 | 711.37 | 2253 | NEW | 80 | Delayed | 50 | 22/11/2022 | 30/06/2025 | 19/05/2025 | 01/11/2022 | 353.51 | 349.25
491 | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/14478) | SM/14478 | 687.52 | 0 | AUGMENTATION | 80 | On track | 52 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 03/02/2022 | 360.47 | 360.47
492 | Solarization of grid connected pumping installation at Madpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17354) | SM/17354 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 24/03/2023 | 0 | 0
493 | Solarization of grid connected pumping installation Anandapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17727) | SM/17727 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
494 | Solarization of grid connected pumping installation at Dharmma PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17346) | SM/17346 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
495 | BAMANBIRUA AND ADJOINING MOUJAS PWSS (SM/12991) | SM/12991 | 554.34 | 1790 | NEW | 80 | Delayed | 61 | 28/09/2022 | 30/06/2025 | 19/05/2025 | 01/11/2022 | 339.63 | 334.97
496 | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/14480) | SM/14480 | 211.1 | 109 | AUGMENTATION | 80 | On track | 46 | 20/01/2023 | 31/12/2025 | 19/05/2025 | 23/08/2022 | 97.29 | 97.29
497 | Solarization of grid connected pumping installation at Keshiary PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17342) | SM/17342 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
498 | Solarization of grid connected pumping installation Bhikni Nischintapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17734) | SM/17734 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
499 | Solarization of grid connected pumping installation at Khasbazar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17328) | SM/17328 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 24/03/2023 | 0 | 0
500 | Solarization of grid connected pumping installation Supapursuri PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17811) | SM/17811 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
501 | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS (SM/13032) | SM/13032 | 965.49 | 2725 | NEW | 80 | On track | 37 | 28/09/2022 | 07/11/2025 | 19/05/2025 | 13/07/2023 | 358.61 | 352.33
502 | Solarization of grid connected pumping installation at Khanjapur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17307) | SM/17307 | 16.61 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
503 | Solarization of grid connected pumping installation at Khagragerya PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17414) | SM/17414 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 20/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
504 | AKRA MARKANDAPUR PWSS (SM/17003) | SM/17003 | 45.14 | 124 | NEW | 80 | On track | 41 | 16/03/2023 | 31/12/2025 | 19/05/2025 | 25/04/2023 | 18.34 | 18.34
505 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. (SM/09431) | SM/09431 | 589.71 | 2295 | AUGMENTATION | 80 | On track | 56 | 17/11/2021 | 31/12/2025 | 19/05/2025 | 04/04/2022 | 332.89 | 332.89
506 | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. (SM/17949) | SM/17949 | 482.36 | 362 | AUGMENTATION | 80 | On track | 23 | 17/03/2023 | 07/11/2025 | 19/05/2025 | 06/04/2023 | 111.24 | 111.24
507 | Solarization of grid connected pumping installation Kolanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17778) | SM/17778 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
508 | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17739) | SM/17739 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
509 | Solarization of grid connected pumping installation at Chotkhelna PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17306) | SM/17306 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
510 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/18615) | SM/18615 | 1048.75 | 3468 | NEW | 80 | On track | 37 | 31/07/2023 | 31/12/2025 | 19/05/2025 | 07/08/2023 | 390.52 | 390.52
511 | Solarization of grid connected pumping installation Birsingha PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17797) | SM/17797 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
512 | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Sabang & 1 No. PWSS within Pingla Block (SM/06932) | SM/06932 | 51.23 | 803 | RETROFITTING | 80 | Delayed | 100 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 51.23 | 39.55
513 | PALASIA AND ADJOINING MOUJAS PWSS (SM/13168) | SM/13168 | 473.81 | 1687 | NEW | 80 | On track | 49 | 12/10/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 230.09 | 213.44
514 | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE (SM/16928) | SM/16928 | 285.82 | 0 | SOLARISATION | 80 | On track | 0 | 16/03/2023 | 31/12/2025 | 19/05/2025 | 15/05/2023 | 0 | 0
515 | Solarization of grid connected pumping installation at Maliara PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17376) | SM/17376 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 24/03/2023 | 0 | 0
516 | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17799) | SM/17799 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
517 | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17738) | SM/17738 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 0 | 0
518 | Solarization of grid connected pumping installation at Daspur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17373) | SM/17373 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
519 | Solarization of grid connected pumping installation at Amrakuchi PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17325) | SM/17325 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
520 | Solarization of grid connected pumping installation at Bamanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17335) | SM/17335 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 23/03/2023 | 0 | 0
521 | Solarization of grid connected pumping installation at Pratappur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17345) | SM/17345 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
522 | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme. (SM/17812) | SM/17812 | 12.39 | 0 | AUGMENTATION | 80 | On track | 72 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 8.89 | 0
523 | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09684) | SM/09684 | 57.28 | 231 | NEW | 80 | On track | 94 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 05/08/2021 | 53.78 | 53.78
524 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. (SM/10000) | SM/10000 | 1840.05 | 7812 | AUGMENTATION | 80 | Delayed | 53 | 20/12/2021 | 30/06/2025 | 19/05/2025 | 01/08/2022 | 968.67 | 968.67
525 | PUNDRA AND ADJOINING MOUJAS PWSS (SM/13169) | SM/13169 | 500.02 | 1808 | NEW | 80 | Delayed | 60 | 12/10/2022 | 30/06/2025 | 19/05/2025 | 01/11/2022 | 300.23 | 293.94
526 | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/15591) | SM/15591 | 846.53 | 2187 | NEW | 80 | On track | 51 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 27/03/2023 | 433.5 | 433.5
527 | Solarization of grid connected pumping installation Mulgram PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17760) | SM/17760 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
528 | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17765) | SM/17765 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
529 | Solarization of grid connected pumping installation at Kurul PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17358) | SM/17358 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/08/2026 | 19/05/2025 | 24/03/2023 | 0 | 0
530 | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17321) | SM/17321 | 8.3 | 0 | SOLARISATION | 80 | On track | 0 | 15/03/2023 | 31/12/2025 | 19/05/2025 | 23/03/2023 | 0 | 0
531 | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS (SM/06927) | SM/06927 | 97.83 | 2012 | RETROFITTING | 81 | Delayed | 68 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 66.49 | 55.13
532 | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS (SM/06906) | SM/06906 | 99.91 | 2016 | RETROFITTING | 81 | Delayed | 79 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 79.25 | 76.09
533 | Retrofitting to accomodate FHTC under JJM in Panpara PWSS (SM/06924) | SM/06924 | 97.15 | 1950 | RETROFITTING | 82 | Delayed | 92 | 09/10/2020 | 30/08/2025 | 19/05/2025 | 26/11/2020 | 89.44 | 57.08
534 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/18171) | SM/18171 | 999.09 | 3039 | NEW | 82 | On track | 36 | 29/03/2023 | 31/12/2025 | 19/05/2025 | 07/08/2023 | 358.27 | 358.27
535 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. (SM/09585) | SM/09585 | 778.43 | 2940 | AUGMENTATION | 83 | On track | 42 | 22/11/2021 | 31/10/2025 | 19/05/2025 | 30/03/2021 | 325.48 | 325.48
536 | Gopinathpur Piped Water Supply Scheme. (SM/07964) | SM/07964 | 653.2 | 1142 | NEW | 85 | Delayed | 43 | 11/01/2021 | 31/05/2025 | 19/05/2025 | 25/07/2022 | 283.56 | 283.56
537 | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. (SM/06913) | SM/06913 | 97.02 | 1982 | RETROFITTING | 85 | Delayed | 68 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 65.94 | 61.99
538 | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/18191) | SM/18191 | 288.28 | 418 | AUGMENTATION | 85 | On track | 26 | 30/03/2023 | 31/12/2025 | 19/05/2025 | 12/04/2023 | 74.61 | 66.62
539 | KASHIPUR AND ADJOINING MOUJAS PWSS (SM/15014) | SM/15014 | 899.9 | 2634 | NEW | 85 | On track | 66 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 18/07/2023 | 597.99 | 597.99
540 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/15578) | SM/15578 | 263.49 | 342 | AUGMENTATION | 85 | On track | 5 | 15/02/2023 | 31/12/2025 | 19/05/2025 | 07/09/2022 | 12.77 | 12.77
541 | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur (SM/18785) | SM/18785 | 44.88 | 225 | NEW | 85 | Delayed | 44 | 29/08/2023 | 08/02/2025 | 19/05/2025 | 31/08/2023 | 19.93 | 17.8
542 | MARKUNDA AND ADJOINING MOUJAS PWSS (SM/13098) | SM/13098 | 450.45 | 1278 | NEW | 85 | On track | 78 | 10/10/2022 | 31/03/2026 | 19/05/2025 | 18/07/2023 | 352.49 | 352.49
543 | LOYADA AND ITS ADJOINING MOUJAS PWSS (SM/12992) | SM/12992 | 354.05 | 1251 | NEW | 85 | On track | 69 | 28/09/2022 | 31/03/2026 | 19/05/2025 | 24/03/2023 | 243.76 | 243.76
544 | Retrofitting to accommodate FHTC under JJM in Narayanbar Piped Water Supply Scheme. (SM/06896) | SM/06896 | 95.91 | 1943 | RETROFITTING | 85 | On track | 84 | 09/10/2020 | 30/08/2025 | 19/05/2025 | 26/11/2020 | 80.2 | 57.97
545 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/11880) | SM/11880 | 387.99 | 0 | AUGMENTATION | 85 | On track | 36 | 17/08/2022 | 31/12/2025 | 19/05/2025 | 17/03/2022 | 138.55 | 138.55
546 | Tanuya Piped Water Supply Scheme. (SM/09992) | SM/09992 | 883.09 | 2479 | NEW | 85 | On track | 57 | 16/12/2021 | 12/12/2025 | 19/05/2025 | 07/01/2022 | 505.09 | 505.09
547 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. (SM/18173) | SM/18173 | 815.03 | 2892 | NEW | 85 | On track | 50 | 29/03/2023 | 07/11/2025 | 19/05/2025 | 08/04/2022 | 405.56 | 405.56
548 | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District (SM/09703) | SM/09703 | 64.66 | 1265 | RETROFITTING | 85 | On track | 55 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 10/05/2022 | 35.54 | 35.54
549 | IRPALA Piped Water Supply Scheme. (SM/07386) | SM/07386 | 728.89 | 55 | NEW | 86 | On track | 53 | 03/12/2020 | 22/10/2025 | 19/05/2025 | 17/12/2021 | 388.4 | 388.4
550 | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. (SM/11624) | SM/11624 | 901.96 | 2760 | NEW | 86 | On track | 45 | 26/07/2022 | 31/12/2025 | 19/05/2025 | 21/11/2022 | 406.73 | 406.73
551 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. (SM/09455) | SM/09455 | 237.68 | 480 | AUGMENTATION | 86 | On track | 59 | 19/11/2021 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 141.1 | 141.1
552 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/15121) | SM/15121 | 784.7 | 1764 | NEW | 88 | On track | 57 | 04/02/2023 | 31/03/2026 | 19/05/2025 | 21/03/2023 | 446.02 | 446.02
553 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. (SM/09923) | SM/09923 | 1045.66 | 5235 | AUGMENTATION | 88 | On track | 42 | 10/12/2021 | 30/10/2025 | 19/05/2025 | 31/08/2022 | 437.99 | 437.99
554 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. (SM/09980) | SM/09980 | 1222.34 | 4584 | AUGMENTATION | 90 | On track | 66 | 16/12/2021 | 31/12/2025 | 19/05/2025 | 26/10/2021 | 809.44 | 809.44
555 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. (SM/09999) | SM/09999 | 1007.98 | 3518 | AUGMENTATION | 90 | On track | 74 | 20/12/2021 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 743.32 | 737.52
556 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. (SM/09979) | SM/09979 | 1022.06 | 3889 | AUGMENTATION | 90 | On track | 68 | 16/12/2021 | 31/05/2025 | 19/05/2025 | 22/08/2022 | 690.74 | 687.37
557 | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS (SM/06926) | SM/06926 | 97.54 | 1969 | RETROFITTING | 90 | On track | 74 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 72.45 | 72.4
558 | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. (SM/08211) | SM/08211 | 115.14 | 284 | RETROFITTING | 90 | On track | 45 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 26/02/2021 | 52.28 | 50.84
559 | Retrofitting of Ground Water Based Chatra Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09106) | SM/09106 | 16.51 | 108 | RETROFITTING | 90 | On track | 9 | 28/10/2021 | 31/05/2025 | 19/05/2025 | 08/01/2021 | 1.46 | 1.46
560 | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS (SM/06907) | SM/06907 | 88.73 | 1755 | RETROFITTING | 90 | On track | 86 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 76.44 | 76.44
561 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10686) | SM/10686 | 87.88 | 0 | AUGMENTATION | 90 | On track | 77 | 06/05/2022 | 31/12/2025 | 19/05/2025 | 16/07/2021 | 67.84 | 67.84
562 | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. (SM/08079) | SM/08079 | 652.85 | 13373 | RETROFITTING | 90 | On track | 32 | 04/02/2021 | 31/12/2025 | 19/05/2025 | 24/02/2021 | 208.61 | 189.39
563 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. (SM/13826) | SM/13826 | 281.35 | 853 | AUGMENTATION | 90 | Delayed | 55 | 25/11/2022 | 30/04/2025 | 19/05/2025 | 10/02/2021 | 154.4 | 154.4
564 | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-I) PWSS (SM/06920) | SM/06920 | 90.08 | 1853 | RETROFITTING | 90 | On track | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 87.46 | 63.02
565 | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. (SM/11623) | SM/11623 | 631.92 | 1678 | NEW | 90 | On track | 52 | 26/07/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 331.66 | 331.66
566 | Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. (SM/17728) | SM/17728 | 12.39 | 0 | AUGMENTATION | 90 | On track | 83 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 10.32 | 10.32
567 | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District (SM/09706) | SM/09706 | 79.89 | 1603 | RETROFITTING | 90 | On track | 97 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 17/12/2021 | 77.56 | 77.56
568 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10685) | SM/10685 | 123.54 | 0 | AUGMENTATION | 90 | On track | 73 | 06/05/2022 | 31/12/2025 | 19/05/2025 | 29/09/2021 | 90.22 | 90.22
569 | Rejuvenation of Electro-Mechanical components of Satkui PWSS in the District of Paschim Medinipur under JJM programme. (SM/17785) | SM/17785 | 12.39 | 0 | AUGMENTATION | 90 | On track | 40 | 17/03/2023 | 31/08/2026 | 19/05/2025 | 29/03/2023 | 4.95 | 4.95
570 | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. (SM/13709) | SM/13709 | 239.63 | 127 | AUGMENTATION | 91 | On track | 24 | 14/11/2022 | 31/12/2025 | 19/05/2025 | 23/08/2022 | 58.36 | 58.36
571 | Retrofitting to accommodate FHTC under JJM in Gobardhanpur Piped Water Supply Scheme. (SM/06916) | SM/06916 | 90.78 | 1800 | RETROFITTING | 91 | On track | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 87.65 | 81.86
572 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS (SM/06918) | SM/06918 | 76.98 | 1579 | RETROFITTING | 94 | On track | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 74.72 | 33.75
573 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE (SM/17574) | SM/17574 | 66.85 | 105 | NEW | 95 | On track | 46 | 18/03/2023 | 15/05/2025 | 19/05/2025 | 13/07/2023 | 30.59 | 30.59
574 | Sabra Piped Water Supply Scheme. (SM/11460) | SM/11460 | 1011.95 | 3679 | NEW | 95 | On track | 69 | 12/07/2022 | 30/09/2025 | 19/05/2025 | 09/11/2022 | 701.12 | 701.12
575 | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. (SM/06914) | SM/06914 | 96.46 | 1900 | RETROFITTING | 95 | On track | 95 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 91.57 | 91.57
576 | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District (SM/09705) | SM/09705 | 47.69 | 910 | RETROFITTING | 95 | On track | 97 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 30/09/2021 | 46.3 | 46.3
577 | Antla Piped Water Supply Scheme. (SM/09991) | SM/09991 | 669.25 | 50 | NEW | 95 | On track | 67 | 16/12/2021 | 31/05/2025 | 19/05/2025 | 28/12/2021 | 450.47 | 450.27
578 | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS under Midnapore Sadar Block in Paschim Medinipur District (SM/09701) | SM/09701 | 132.83 | 2688 | RETROFITTING | 95 | On track | 83 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 03/12/2021 | 109.69 | 99.49
579 | Retrofitting to accommodate FHTC under JJM in Palashi Piped Water Supply Scheme. (SM/06930) | SM/06930 | 89.32 | 1820 | RETROFITTING | 95 | On track | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 02/02/2021 | 86.72 | 86.19
580 | Retrofitting to accommodate FHTC under JJM in Kanchangeria PWSS, Block - Debra, District - Paschim Medinipur. (SM/09085) | SM/09085 | 89.46 | 1738 | RETROFITTING | 95 | On track | 40 | 28/10/2021 | 25/12/2025 | 19/05/2025 | 27/05/2022 | 35.47 | 35.47
581 | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. (SM/06912) | SM/06912 | 97.5 | 1960 | RETROFITTING | 95 | On track | 87 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 22/02/2021 | 84.95 | 84.95
582 | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/13823) | SM/13823 | 210.14 | 719 | AUGMENTATION | 97 | On track | 55 | 25/11/2022 | 30/09/2025 | 19/05/2025 | 25/06/2021 | 116.18 | 114.77
583 | Retrofitting to accomodate FHTC under JJM in Mugbasan PWSS (SM/08218) | SM/08218 | 71.14 | 1445 | RETROFITTING | 98 | On track | 96 | 09/02/2021 | 31/12/2025 | 19/05/2025 | 02/07/2021 | 68.18 | 68.18
584 | Retrofitting to accomodate FHTC under JJM in Satkui PWSS (SM/08219) | SM/08219 | 63.45 | 1348 | RETROFITTING | 98 | On track | 97 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 26/02/2021 | 61.61 | 61.12
585 | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. (SM/15257) | SM/15257 | 759.46 | 1976 | NEW | 98 | On track | 77 | 07/02/2023 | 31/03/2026 | 19/05/2025 | 20/03/2023 | 584.15 | 584.15
586 | Retrofitting to accomodate FHTC under JJM in Tararui PWSS (SM/08220) | SM/08220 | 76.79 | 1562 | RETROFITTING | 98 | On track | 96 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 22/02/2021 | 73.75 | 73.75
587 | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur (SM/08212) | SM/08212 | 42.65 | 840 | RETROFITTING | 99 | On track | 79 | 09/02/2021 | 31/12/2025 | 19/05/2025 | 26/02/2021 | 33.58 | 28.78
588 | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. (SM/06900) | SM/06900 | 50.84 | 1005 | RETROFITTING | 99 | On track | 95 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 48.39 | 48.39
589 | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. (SM/08205) | SM/08205 | 41.47 | 142 | RETROFITTING | 99 | On track | 45 | 09/02/2021 | 31/12/2025 | 19/05/2025 | 15/02/2022 | 18.75 | 18.75
590 | Retrofitting to accomodate FHTC under JJM in Malara PWSS (SM/08221) | SM/08221 | 23.54 | 486 | RETROFITTING | 99 | On track | 85 | 09/02/2021 | 31/12/2025 | 19/05/2025 | 25/02/2021 | 20 | 18.78
591 | Retrofitting to accomodate FHTC under JJM in Maliara PWSS (SM/06898) | SM/06898 | 44.54 | 959 | RETROFITTING | 99 | On track | 97 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 43.24 | 42.93
592 | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. (SM/08203) | SM/08203 | 112.39 | 2300 | RETROFITTING | 99 | On track | 96 | 09/02/2021 | 31/12/2025 | 19/05/2025 | 25/02/2021 | 108.05 | 105.71
593 | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. (SM/06895) | SM/06895 | 98.9 | 1889 | RETROFITTING | 99 | On track | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 96.02 | 96.02
594 | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur (SM/09675) | SM/09675 | 71.71 | 237 | NEW | 99 | On track | 80 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 31/01/2022 | 57.63 | 57.63
595 | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. (SM/06915) | SM/06915 | 69.14 | 1439 | RETROFITTING | 100 | 100% Physical | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 67.13 | 67.01
596 | Retrofitting to accomodate FHTC under JJM in Bural (Zone-I) PWSS (SM/06917) | SM/06917 | 99.8 | 1937 | RETROFITTING | 100 | 100% Physical | 94 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 93.72 | 93.72
597 | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas (SM/09442) | SM/09442 | 43.73 | 156 | NEW | 100 | 100% Physical | 95 | 29/10/2021 | 31/05/2025 | 19/05/2025 | 05/08/2021 | 41.53 | 41.4
598 | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur (SM/08207) | SM/08207 | 97.87 | 2031 | RETROFITTING | 100 | 100% Physical | 96 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 26/02/2021 | 94.14 | 94.14
599 | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. (SM/08213) | SM/08213 | 36.08 | 120 | RETROFITTING | 100 | 100% Physical | 5 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 24/02/2021 | 1.94 | 1.94
600 | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. (SM/09721) | SM/09721 | 110.6 | 1394 | RETROFITTING | 100 | 100% Physical | 84 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 92.56 | 92.56
601 | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. (SM/06901) | SM/06901 | 98.04 | 1950 | RETROFITTING | 100 | 100% Physical | 97 | 09/10/2020 | 31/03/2026 | 19/05/2025 | 26/11/2020 | 95.18 | 89.53
602 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/11811) | SM/11811 | 84.32 | 0 | AUGMENTATION | 100 | 100% Physical | 77 | 16/08/2022 | 31/05/2025 | 19/05/2025 | 28/09/2021 | 65.13 | 65.13
603 | Retrofitting to accomodate FHTC under JJM in Bishnupur PWSS Block Sabang District Paschim Medinipur (SM/08209) | SM/08209 | 92.74 | 1941 | RETROFITTING | 100 | 100% Physical | 80 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 22/02/2021 | 73.87 | 73.87
604 | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/10648) | SM/10648 | 110.76 | 433 | NEW | 100 | 100% Physical | 77 | 22/04/2022 | 31/05/2025 | 19/05/2025 | 17/08/2021 | 84.9 | 84.9
605 | Retrofitting of Ground Water Based Kalshibhanga Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09419) | SM/09419 | 13.42 | 57 | RETROFITTING | 100 | 100% Physical | 77 | 17/11/2021 | 31/05/2025 | 19/05/2025 | 04/03/2022 | 10.33 | 10.33
606 | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur Piped Water Supply Scheme. (SM/06911) | SM/06911 | 94.57 | 1916 | RETROFITTING | 100 | 100% Physical | 95 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 89.65 | 89.4
607 | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. (SM/06899) | SM/06899 | 98.16 | 2150 | RETROFITTING | 100 | 100% Physical | 100 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 25/02/2021 | 98.16 | 94.3
608 | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS (SM/06909) | SM/06909 | 86.43 | 1691 | RETROFITTING | 100 | 100% Physical | 91 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 78.75 | 64.49
609 | Retrofitting to accommodate FHTC under JJM in Nabin Mahespur PWSS, Block - Daspur-I, District - Paschim Medinipur. (SM/09081) | SM/09081 | 62.19 | 1204 | RETROFITTING | 100 | 100% Physical | 88 | 28/10/2021 | 31/05/2025 | 19/05/2025 | 04/04/2022 | 54.76 | 50
610 | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. (SM/09087) | SM/09087 | 221.59 | 4449 | RETROFITTING | 100 | 100% Physical | 20 | 28/10/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 43.73 | 43.73
611 | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas (SM/09440) | SM/09440 | 47.32 | 182 | NEW | 100 | 100% Physical | 76 | 29/10/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 36.13 | 37.27
612 | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas (SM/09441) | SM/09441 | 40.12 | 140 | NEW | 100 | 100% Physical | 88 | 29/10/2021 | 31/05/2025 | 19/05/2025 | 05/08/2021 | 35.22 | 35.22
613 | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur (SM/08210) | SM/08210 | 73.21 | 1457 | RETROFITTING | 100 | 100% Physical | 96 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 26/02/2021 | 70.09 | 70.09
614 | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/08676) | SM/08676 | 53.89 | 665 | RETROFITTING | 100 | 100% Physical | 93 | 20/07/2021 | 31/12/2025 | 19/05/2025 | 17/12/2021 | 49.9 | 49.9
615 | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur (SM/09681) | SM/09681 | 238.97 | 1008 | NEW | 100 | 100% Physical | 92 | 24/11/2021 | 31/05/2025 | 19/05/2025 | 31/01/2022 | 219.65 | 219.65
616 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10778) | SM/10778 | 140.59 | 0 | AUGMENTATION | 100 | 100% Physical | 70 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 98.24 | 98.24
617 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10731) | SM/10731 | 120.16 | 0 | AUGMENTATION | 100 | 100% Physical | 58 | 19/05/2022 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 70.16 | 68.96
618 | Retrofitting to accomodate FHTC under JJM in Bural (Zone-II) PWSS (SM/06919) | SM/06919 | 99.9 | 2018 | RETROFITTING | 100 | 100% Physical | 95 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 94.89 | 82.56
619 | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. (SM/13046) | SM/13046 | 295.97 | 0 | AUGMENTATION | 100 | 100% Physical | 87 | 29/09/2022 | 31/12/2025 | 19/05/2025 | 09/03/2022 | 258.25 | 258.25
620 | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur (SM/08217) | SM/08217 | 89.04 | 1828 | RETROFITTING | 100 | 100% Physical | 88 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 22/02/2021 | 78.77 | 78.77
621 | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District (SM/09710) | SM/09710 | 72.27 | 1400 | RETROFITTING | 100 | 100% Physical | 81 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 01/12/2021 | 58.45 | 58.4
622 | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09678) | SM/09678 | 91.62 | 350 | NEW | 100 | 100% Physical | 94 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 30/11/2021 | 85.85 | 85.6
623 | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur (SM/10658) | SM/10658 | 103.58 | 380 | NEW | 100 | 100% Physical | 76 | 22/04/2022 | 31/05/2025 | 19/05/2025 | 12/04/2022 | 79.21 | 79.2
624 | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. (SM/06933) | SM/06933 | 93.43 | 1886 | RETROFITTING | 100 | 100% Physical | 93 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 87.09 | 84.03
625 | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. (SM/06908) | SM/06908 | 95.43 | 1900 | RETROFITTING | 100 | 100% Physical | 95 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 90.94 | 90.94
626 | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. (SM/06928) | SM/06928 | 89.26 | 1831 | RETROFITTING | 100 | 100% Physical | 76 | 09/10/2020 | 31/12/2025 | 19/05/2025 | 26/11/2020 | 68.01 | 68.01
627 | Retrofitting to accomodate FHTC under JJM in Julkapur PWSS (SM/06929) | SM/06929 | 50.26 | 1036 | RETROFITTING | 100 | 100% Physical | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 48.8 | 47.25
628 | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. (SM/09432) | SM/09432 | 323.02 | 1380 | AUGMENTATION | 100 | 100% Physical | 45 | 17/11/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 143.97 | 143.97
629 | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (SM/08204) | SM/08204 | 259.13 | 4200 | RETROFITTING | 100 | 100% Physical | 63 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 25/02/2021 | 164.02 | 164
630 | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10839) | SM/10839 | 896.27 | 4191 | AUGMENTATION | 100 | 100% Physical | 85 | 30/05/2022 | 31/05/2025 | 19/05/2025 | 16/07/2021 | 761.65 | 761.65
631 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/14720) | SM/14720 | 90.31 | 0 | AUGMENTATION | 100 | 100% Physical | 76 | 31/01/2023 | 31/05/2025 | 19/05/2025 | 28/09/2021 | 68.47 | 68.47
632 | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme. (SM/17750) | SM/17750 | 5.55 | 0 | AUGMENTATION | 100 | 100% Physical | 91 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 5.07 | 5.07
633 | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS (SM/06934) | SM/06934 | 95.64 | 1945 | RETROFITTING | 100 | 100% Physical | 96 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 92.08 | 91.92
634 | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. (SM/06897) | SM/06897 | 97.58 | 1992 | RETROFITTING | 100 | 100% Physical | 96 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 93.31 | 90.35
635 | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas (SM/09439) | SM/09439 | 45.94 | 175 | NEW | 100 | 100% Physical | 88 | 29/10/2021 | 31/12/2025 | 19/05/2025 | 24/01/2022 | 40.29 | 40.16
636 | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. (SM/08208) | SM/08208 | 38.64 | 84 | RETROFITTING | 100 | 100% Physical | 41 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 01/02/2022 | 15.82 | 15.77
637 | Retrofitting of Ground Water Based Bhimpur Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/08675) | SM/08675 | 38.98 | 418 | RETROFITTING | 100 | 100% Physical | 94 | 20/07/2021 | 31/05/2025 | 19/05/2025 | 08/02/2022 | 36.56 | 36.56
638 | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. (SM/08215) | SM/08215 | 36.97 | 253 | RETROFITTING | 100 | 100% Physical | 49 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 28/12/2021 | 17.95 | 17.95
639 | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. (SM/08696) | SM/08696 | 250.75 | 5208 | RETROFITTING | 100 | 100% Physical | 97 | 01/09/2021 | 31/05/2025 | 19/05/2025 | 03/09/2021 | 242.69 | 237.89
640 | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/11858) | SM/11858 | 119.24 | 466 | NEW | 100 | 100% Physical | 78 | 17/08/2022 | 31/12/2025 | 19/05/2025 | 16/08/2021 | 93.49 | 93.49
641 | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS (SM/08695) | SM/08695 | 125.78 | 2444 | RETROFITTING | 100 | 100% Physical | 76 | 01/09/2021 | 31/05/2025 | 19/05/2025 | 03/09/2021 | 95.6 | 91.25
642 | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/08678) | SM/08678 | 20.35 | 172 | RETROFITTING | 100 | 100% Physical | 89 | 20/07/2021 | 31/03/2025 | 19/05/2025 | 28/12/2021 | 18.17 | 18.17
643 | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. (SM/16949) | SM/16949 | 16.47 | 150 | RETROFITTING | 100 | 100% Physical | 83 | 16/03/2023 | 31/05/2025 | 19/05/2025 | 17/07/2023 | 13.72 | 13.72
644 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. (SM/17395) | SM/17395 | 162.04 | 70 | AUGMENTATION | 100 | 100% Physical | 2 | 15/03/2023 |  | 12/06/2023 | 23/06/2021 | 3.69 | 1.66
645 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/11895) | SM/11895 | 56.64 | 0 | AUGMENTATION | 100 | 100% Physical | 95 | 18/08/2022 | 31/05/2025 | 19/05/2025 | 28/09/2021 | 53.69 | 53.69
646 | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. (SM/06905) | SM/06905 | 73.67 | 1489 | RETROFITTING | 100 | 100% Physical | 100 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 73.51 | 69.47
647 | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. (SM/09722) | SM/09722 | 100.27 | 1040 | RETROFITTING | 100 | 100% Physical | 64 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 63.83 | 63.83
648 | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. (SM/09723) | SM/09723 | 61.9 | 593 | RETROFITTING | 100 | 100% Physical | 68 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 07/01/2022 | 42.13 | 42.13
649 | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. (SM/09726) | SM/09726 | 424.38 | 4098 | RETROFITTING | 100 | 100% Physical | 88 | 26/11/2021 | 31/05/2025 | 19/05/2025 | 03/12/2021 | 372.93 | 368.95
650 | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur (SM/12117) | SM/12117 | 72.98 | 1374 | RETROFITTING | 100 | 100% Physical | 84 | 06/09/2022 | 31/05/2025 | 19/05/2025 | 07/09/2022 | 61.11 | 61.11
651 | Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. (SM/17779) | SM/17779 | 12.39 | 0 | AUGMENTATION | 100 | 100% Physical | 91 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 11.28 | 11.28
652 | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. (SM/09082) | SM/09082 | 33.9 | 687 | RETROFITTING | 100 | 100% Physical | 85 | 28/10/2021 | 31/12/2025 | 19/05/2025 | 11/12/2020 | 28.76 | 28.38
653 | Retrofitting of Ground Water Based Keudi Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09417) | SM/09417 | 11.59 | 41 | RETROFITTING | 100 | 100% Physical | 66 | 17/11/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 7.62 | 7.62
654 | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. (SM/08206) | SM/08206 | 65.82 | 363 | RETROFITTING | 100 | 100% Physical | 57 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 17/02/2022 | 37.36 | 37.36
655 | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur (SM/08214) | SM/08214 | 102.3 | 2005 | RETROFITTING | 100 | 100% Physical | 68 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 24/02/2021 | 69.49 | 69.49
656 | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur (SM/08216) | SM/08216 | 91.33 | 1839 | RETROFITTING | 100 | 100% Physical | 97 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 26/02/2021 | 88.67 | 88.67
657 | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. (SM/09724) | SM/09724 | 119.15 | 1195 | RETROFITTING | 100 | 100% Physical | 79 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 03/12/2021 | 93.85 | 93.85
658 | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09676) | SM/09676 | 51.48 | 252 | NEW | 100 | 100% Physical | 91 | 24/11/2021 | 31/05/2025 | 19/05/2025 | 01/02/2022 | 46.67 | 46.67
659 | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. (SM/09677) | SM/09677 | 37.49 | 106 | NEW | 100 | 100% Physical | 77 | 24/11/2021 | 31/05/2025 | 19/05/2025 | 31/01/2022 | 28.98 | 28.98
660 | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09683) | SM/09683 | 116.45 | 530 | NEW | 100 | 100% Physical | 95 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 31/01/2022 | 110.37 | 110.37
661 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10841) | SM/10841 | 93.67 | 0 | AUGMENTATION | 100 | 100% Physical | 28 | 30/05/2022 | 31/12/2025 | 19/05/2025 | 29/09/2021 | 26.57 | 26.57
662 | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/10655) | SM/10655 | 110.1 | 380 | NEW | 100 | 100% Physical | 78 | 22/04/2022 | 31/05/2025 | 19/05/2025 | 23/08/2022 | 85.65 | 85.49
663 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10840) | SM/10840 | 64.89 | 0 | AUGMENTATION | 100 | 100% Physical | 76 | 30/05/2022 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 49.42 | 49.42
664 | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. (SM/10002) | SM/10002 | 100.55 | 298 | NEW | 100 | 100% Physical | 74 | 22/12/2021 | 31/05/2025 | 19/05/2025 | 17/02/2022 | 74.34 | 73.37
665 | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. (SM/06923) | SM/06923 | 96.2 | 1986 | RETROFITTING | 100 | 100% Physical | 73 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 03/02/2022 | 70.21 | 66
666 | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17798) | SM/17798 | 8.3 | 0 | SOLARISATION | 100 | 100% Physical | 0 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 0 | 0
667 | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR (SM/17008) | SM/17008 | 42.51 | 135 | NEW | 100 | 100% Physical | 65 | 16/03/2023 | 31/05/2025 | 19/05/2025 | 18/07/2023 | 27.57 | 27.57
668 | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-II) PWSS (SM/06922) | SM/06922 | 83.25 | 1705 | RETROFITTING | 100 | 100% Physical | 90 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 74.59 | 63.89
669 | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. (SM/09083) | SM/09083 | 89.12 | 1726 | RETROFITTING | 100 | 100% Physical | 67 | 28/10/2021 | 31/05/2025 | 19/05/2025 | 04/03/2022 | 59.82 | 59.82
670 | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/08677) | SM/08677 | 23.22 | 222 | RETROFITTING | 100 | 100% Physical | 53 | 20/07/2021 | 31/05/2025 | 19/05/2025 | 24/02/2021 | 12.41 | 12.41
671 | Retrofitting to accommodate FHTC in Bamanda PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (SM/09101) | SM/09101 | 28.75 | 573 | RETROFITTING | 100 | 100% Physical | 92 | 28/10/2021 | 30/04/2025 | 19/05/2025 | 06/11/2020 | 26.38 | 25.77
672 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/10842) | SM/10842 | 87.89 | 0 | AUGMENTATION | 100 | 100% Physical | 97 | 30/05/2022 | 31/12/2025 | 19/05/2025 | 28/09/2021 | 85.32 | 79.37
673 | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. (SM/06902) | SM/06902 | 50.48 | 864 | RETROFITTING | 100 | 100% Physical | 97 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 49.01 | 49.01
674 | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. (SM/15220) | SM/15220 | 112.33 | 372 | NEW | 100 | 100% Physical | 76 | 07/02/2023 | 31/03/2026 | 19/05/2025 | 12/08/2021 | 85.37 | 84.03
675 | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme. (SM/17796) | SM/17796 | 5.55 | 0 | AUGMENTATION | 100 | 100% Physical | 91 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 5.07 | 5.07
676 | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. (SM/06894) | SM/06894 | 78.36 | 1716 | RETROFITTING | 100 | 100% Physical | 93 | 09/10/2020 | 31/05/2025 | 19/05/2025 | 26/11/2020 | 72.53 | 71.23
677 | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. (SM/09418) | SM/09418 | 37.56 | 374 | RETROFITTING | 100 | 100% Physical | 71 | 17/11/2021 | 31/05/2025 | 19/05/2025 | 17/12/2021 | 26.8 | 26.8
678 | Retrofitting to accommodate FHTC under JJM in Madpur PWSS (SM/08694) | SM/08694 | 99.66 | 2028 | RETROFITTING | 100 | 100% Physical | 90 | 01/09/2021 | 31/05/2025 | 19/05/2025 | 07/09/2021 | 89.95 | 75.6
679 | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09679) | SM/09679 | 31 | 57 | NEW | 100 | 100% Physical | 81 | 24/11/2021 | 31/03/2025 | 19/05/2025 | 31/01/2022 | 25.14 | 25.14
680 | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. (SM/09680) | SM/09680 | 48.8 | 189 | NEW | 100 | 100% Physical | 96 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 16/12/2021 | 46.73 | 45.35
681 | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. (SM/09682) | SM/09682 | 34.95 | 122 | NEW | 100 | 100% Physical | 89 | 24/11/2021 | 31/05/2025 | 19/05/2025 | 16/12/2021 | 31.19 | 31.06
682 | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur (SM/09795) | SM/09795 | 116.29 | 413 | NEW | 100 | 100% Physical | 85 | 01/12/2021 | 31/05/2025 | 19/05/2025 | 31/01/2022 | 98.63 | 98.63
683 | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District (SM/09708) | SM/09708 | 118.7 | 2322 | RETROFITTING | 100 | 100% Physical | 82 | 26/11/2021 | 31/12/2025 | 19/05/2025 | 03/12/2021 | 97.59 | 96.48
684 | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. (SM/10003) | SM/10003 | 211.08 | 734 | NEW | 100 | 100% Physical | 80 | 22/12/2021 | 31/05/2025 | 19/05/2025 | 15/02/2022 | 168.68 | 168.68
685 | Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. (SM/17758) | SM/17758 | 12.39 | 0 | AUGMENTATION | 100 | 100% Physical | 43 | 17/03/2023 | 31/12/2025 | 19/05/2025 | 29/03/2023 | 5.29 | 5.29
Total |  |  | 305880.56 | 1039373 | [8 empty] | 93625.54 | 89878