## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12401) | SM/12401 | 706.42 | 2186 | NEW | 0 | 0% Physical | 8 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 53.04 | 53.04
2 | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. (SM/16671) | SM/16671 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 55 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 6.88 | 6.88
3 | Solarization of grid connected pumping installation at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17753) | SM/17753 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
4 | Solarization of grid connected pumping installation at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17808) | SM/17808 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
5 | Solarization of grid connected pumping installation at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17736) | SM/17736 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
6 | Solarization of grid connected pumping installation at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17294) | SM/17294 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
7 | Solarization of grid connected pumping installation at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17332) | SM/17332 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
8 | Solarization of grid connected pumping installation at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17815) | SM/17815 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
9 | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. (SM/16655) | SM/16655 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0.01 | 0.01
10 | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme (SM/16658) | SM/16658 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 84 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 10.44 | 10.44
11 | Solarization of grid connected pumping installation at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17781) | SM/17781 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
12 | Solarization of grid connected pumping installation at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17366) | SM/17366 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
13 | Solarization of grid connected pumping installation at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17823) | SM/17823 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
14 | Solarization of grid connected pumping installation at Mahammadpur (Bhagwanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17790) | SM/17790 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
15 | Solarization of grid connected pumping installation at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17350) | SM/17350 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
16 | Solarization of grid connected pumping installation at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17794) | SM/17794 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
17 | Solarization of grid connected pumping installation at Srirampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17715) | SM/17715 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
18 | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17388) | SM/17388 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
19 | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17305) | SM/17305 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
20 | Solarization of grid connected pumping installation at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17334) | SM/17334 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
21 | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17648) | SM/17648 | 107.96 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 22/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
22 | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. (SM/12307) | SM/12307 | 514.51 | 1198 | NEW | 0 | 0% Physical | 10 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 51.65 | 51.65
23 | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS (SM/13696) | SM/13696 | 422.36 | 792 | NEW | 0 | 0% Physical | 11 | 14/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 45.75 | 45.75
24 | AMARPUR & ADJOINING MOUZAS (SM/12132) | SM/12132 | 537.37 | 1297 | NEW | 0 | 0% Physical | 41 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 28/03/2023 | 218.2 | 218.2
25 | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE (SM/16929) | SM/16929 | 166.73 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 15/05/2023 | 0 | 0
26 | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme. (SM/16664) | SM/16664 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 58 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 7.15 | 7.15
27 | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme. (SM/16665) | SM/16665 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 55 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 6.77 | 6.77
28 | Solarization of grid connected pumping installation at Moyna, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17782) | SM/17782 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
29 | Solarization of grid connected pumping installation at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17317) | SM/17317 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
30 | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17722) | SM/17722 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
31 | Solarization of grid connected pumping installation at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17814) | SM/17814 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
32 | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme. (SM/16654) | SM/16654 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 74 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 9.23 | 9.23
33 | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. (SM/16666) | SM/16666 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 59 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 7.32 | 7.32
34 | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. (SM/16650) | SM/16650 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 1 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0.15 | 0.15
35 | Solarization of grid connected pumping installation at Chandibeniya, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17355) | SM/17355 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
36 | Solarization of grid connected pumping installation at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17339) | SM/17339 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
37 | Solarization of grid connected pumping installation at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17336) | SM/17336 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
38 | PURANDA AND IT'S ADJOINING MOUJAS PWSS (SM/12818) | SM/12818 | 640.79 | 1330 | NEW | 0 | 0% Physical | 30 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 193.45 | 193.45
39 | BARA BHAGIA AND ADJOINING MOUJAS PWSS (SM/12704) | SM/12704 | 498.09 | 1110 | NEW | 0 | 0% Physical | 11 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 54.22 | 54.22
40 | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme. (SM/16670) | SM/16670 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 47 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 5.82 | 5.82
41 | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17756) | SM/17756 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
42 | Solarization of grid connected pumping installation at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17780) | SM/17780 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
43 | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17803) | SM/17803 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
44 | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17720) | SM/17720 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
45 | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17359) | SM/17359 | 24.91 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
46 | Solarization of grid connected pumping installation at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17348) | SM/17348 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
47 | Solarization of grid connected pumping installation at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17293) | SM/17293 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
48 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II (SM/15843) | SM/15843 | 487.15 | 238 | AUGMENTATION | 0 | 0% Physical | 21 | 20/02/2023 | 07/11/2025 | 26/06/2025 | 25/04/2023 | 102.24 | 102.24
49 | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17761) | SM/17761 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
50 | Solarization of grid connected pumping installation at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17361) | SM/17361 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
51 | Solarization of grid connected pumping installation at Uttar Sonamui PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17747) | SM/17747 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
52 | Solarization of grid connected pumping installation at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17816) | SM/17816 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
53 | KAJI BASAN AND ADJOINING MOUJAS PWSS (SM/12499) | SM/12499 | 576.08 | 1276 | NEW | 0 | 0% Physical | 33 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 188.37 | 188.37
54 | PANCHBERYA PIPED WATER SUPPLY SCHEME (SM/16201) | SM/16201 | 171.95 | 131 | NEW | 0 | 0% Physical | 2 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 4.29 | 4.29
55 | DAHA DAYA PIPED WATER SUPPLY SCHEME. (SM/15849) | SM/15849 | 158.24 | 270 | NEW | 0 | 0% Physical | 9 | 20/02/2023 | 07/11/2025 | 26/06/2025 | 25/04/2023 | 14.28 | 14.28
56 | Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme. (SM/16662) | SM/16662 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 35 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 15/03/2023 | 4.4 | 4.4
57 | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17768) | SM/17768 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
58 | Solarization of grid connected pumping installation at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17773) | SM/17773 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
59 | Solarization of grid connected pumping installation at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17777) | SM/17777 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
60 | Solarization of grid connected pumping installation at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17787) | SM/17787 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
61 | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme. (SM/16653) | SM/16653 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 44 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 5.47 | 5.47
62 | Solarization of grid connected pumping installation at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17718) | SM/17718 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
63 | Solarization of grid connected pumping installation at Thenkuachak Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17746) | SM/17746 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
64 | Solarization of grid connected pumping installation at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17298) | SM/17298 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
65 | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computer of Different Water Testing Laboratories Under Tamluk Division P.H.E. Dte. (SM/19271) | SM/19271 | 180.02 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
66 | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19289) | SM/19289 | 134.77 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
67 | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 (SM/19093) | SM/19093 | 191.8 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 06/12/2023 |  | 06/12/2023 | 20/12/2023 | 0 | 0
68 | Regular Upkeement & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme Related to Jal Jeevan Mission. (SM/19338) | SM/19338 | 37.57 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 31/01/2025 |  | 24/02/2025 |  | 0 | 0
69 | PROPOSAL OF ENGAGEMENT OF ADDITIONAL MANPOWER AS PROJECT MANAGEMENT & MONITORING SPECIALIST AND MANAGEMENT INFORMATION SPECIALIST AT DPMU OF PURBA MEDINIPUR DISTRCT UNDER JAL JIVAN MISSION. (JJM) (SM/19245) | SM/19245 | 14.4 | 0 | SUPPORT - HRD | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
70 | Drinking Water Sample Collection & testing through Filed Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. (SM/19087) | SM/19087 | 137.53 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 11/01/2024 | 0 | 0
71 | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. (SM/12484) | SM/12484 | 482.07 | 1463 | NEW | 2 | Delayed | 40 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 194.02 | 194.02
72 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. (SM/16288) | SM/16288 | 522.2 | 782 | AUGMENTATION | 5 | Delayed | 33 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 19/07/2023 | 170.03 | 170.03
73 | MURARI KALUA PWSS (SM/14693) | SM/14693 | 236.53 | 425 | NEW | 5 | Delayed | 0 | 31/01/2023 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 0 | 0
74 | Piped water Supply Scheme for Chirulia-Chatla Zone-1 (SM/16284) | SM/16284 | 403.81 | 162 | AUGMENTATION | 5 | Delayed | 33 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 135.26 | 135.26
75 | Piped Water Supply Scheme for Bathuari Zone-IV (SM/15845) | SM/15845 | 428.01 | 48 | AUGMENTATION | 5 | Delayed | 9 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 28/04/2023 | 38.03 | 38.03
76 | BADALPUR PIPED WATER SUPPLY SCHEME. (SM/15852) | SM/15852 | 74.39 | 162 | NEW | 5 | Delayed | 9 | 20/02/2023 | 31/03/2026 | 26/06/2025 | 25/04/2023 | 6.96 | 6.96
77 | Piped Water Supply Scheme for Bathuari Zone-III (SM/16300) | SM/16300 | 396.8 | 55 | AUGMENTATION | 5 | Delayed | 21 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 28/04/2023 | 81.77 | 81.77
78 | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. (SM/12319) | SM/12319 | 532.38 | 1165 | NEW | 5 | Delayed | 28 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 147.97 | 147.97
79 | FULESHWAR AND ADJOINING MOUJAS PWSS (SM/12500) | SM/12500 | 658.22 | 1268 | NEW | 5 | Delayed | 31 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 205.1 | 205.1
80 | SHOULA BHERI AND ADJOINING MOUJAS PWSS (SM/12496) | SM/12496 | 922.95 | 2921 | NEW | 5 | Delayed | 30 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 274.39 | 274.39
81 | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission (SM/14458) | SM/14458 | 78.13 | 0 | SUPPORT-WQMSP | 5 | Delayed | 0 | 20/01/2023 | 31/03/2024 | 05/10/2023 | 20/09/2023 | 0 | 0
82 | JAMUASHANKARPUR PWSS (SM/14694) | SM/14694 | 344.23 | 312 | NEW | 6 | Delayed | 5 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 16.9 | 16.9
83 | TANIA BILA AND ADJOINING MOUJAS PWSS (SM/12145) | SM/12145 | 510.18 | 1236 | NEW | 6 | Delayed | 39 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 197.17 | 197.17
84 | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS (SM/12134) | SM/12134 | 706.44 | 1988 | NEW | 10 | Delayed | 11 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 02/05/2023 | 78.15 | 78.15
85 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. (SM/16463) | SM/16463 | 130.27 | 920 | AUGMENTATION | 10 | Delayed | 5 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 6.52 | 6.52
86 | MANIKJOR AND ADJOINING MOUJAS PWSS (SM/12171) | SM/12171 | 927.42 | 2206 | NEW | 10 | Delayed | 25 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 12/05/2023 | 227.91 | 227.91
87 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV (SM/16286) | SM/16286 | 461.03 | 209 | AUGMENTATION | 10 | Delayed | 54 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 246.89 | 246.89
88 | PALPARA AND ADJOINING MOUJAS PWSS (SM/12508) | SM/12508 | 754.82 | 2861 | NEW | 10 | Delayed | 22 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 166.7 | 166.7
89 | KEKAI & ADJOINING MOUJAS PWSS (SM/12168) | SM/12168 | 742.03 | 1793 | NEW | 10 | Delayed | 24 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 181.34 | 181.34
90 | RUKMINIPUR AND ADJOINING MOUJAS PWSS (SM/12176) | SM/12176 | 739.06 | 1588 | NEW | 10 | Delayed | 35 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 256.88 | 256.88
91 | POTA PAKURIA AND IT'S ADJOINING MOUJAS (SM/13886) | SM/13886 | 555.33 | 981 | NEW | 10 | Delayed | 20 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 112.9 | 112.9
92 | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme (SM/16464) | SM/16464 | 665.82 | 1636 | AUGMENTATION | 10 | Delayed | 1 | 03/03/2023 | 07/11/2025 | 26/06/2025 | 27/03/2023 | 3.49 | 3.49
93 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16948) | SM/16948 | 71.27 | 322 | NEW | 10 | Delayed | 0 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 05/04/2023 | 0 | 0
94 | KSHETRAPAL AND IT'S ADJOINING MOUJAS (SM/12513) | SM/12513 | 695.17 | 1880 | NEW | 10 | Delayed | 42 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 293.78 | 293.78
95 | KASBAPATASHPUR & ADJOINING MOUJAS PWSS (SM/12172) | SM/12172 | 664.72 | 1875 | NEW | 10 | Delayed | 7 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 49.75 | 49.75
96 | Piped Water Supply Scheme for Sankarpur Zone-II (SM/14842) | SM/14842 | 70.89 | 197 | AUGMENTATION | 10 | Delayed | 26 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 18.43 | 18.43
97 | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS (SM/14457) | SM/14457 | 317.67 | 570 | NEW | 10 | Delayed | 20 | 20/01/2023 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 64.03 | 64.03
98 | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur (SM/18402) | SM/18402 | 49821.56 | 39657 | NEW | 10 | Delayed | 2 | 12/07/2023 | 31/03/2026 | 26/06/2025 | 31/05/2023 | 779.41 | 779.41
99 | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11949) | SM/11949 | 71.08 | 0 | AUGMENTATION | 10 | Delayed | 17 | 24/08/2022 | 31/12/2025 | 26/06/2025 | 10/05/2023 | 11.77 | 11.77
100 | KALABERIA & ADJOINING MOUZAS (SM/12136) | SM/12136 | 743.49 | 3184 | NEW | 10 | Delayed | 8 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 29/12/2022 | 61.24 | 61.24
101 | BHATSALIA & IT'S ADJOINING MOUJAS PWSS (SM/16203) | SM/16203 | 166.63 | 337 | NEW | 10 | Delayed | 55 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 08/06/2023 | 91.22 | 91.22
102 | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16279) | SM/16279 | 80.74 | 0 | AUGMENTATION | 10 | Delayed | 43 | 24/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 34.73 | 34.73
103 | SHIPUR AND ADJOINING MOUJAS PWSS (SM/12503) | SM/12503 | 698.5 | 1484 | NEW | 10 | Delayed | 27 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 186.17 | 186.17
104 | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS (SM/13691) | SM/13691 | 571.07 | 985 | NEW | 10 | Delayed | 42 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 237.86 | 237.86
105 | NAIPUR & ADJOINING MOUZAS (SM/12135) | SM/12135 | 550.96 | 1575 | NEW | 10 | Delayed | 37 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 29/12/2022 | 203.48 | 203.48
106 | MATHURA AND IT'S ADJOINING MOUJAS PWSS (SM/13745) | SM/13745 | 732.18 | 2170 | NEW | 10 | Delayed | 25 | 17/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 183.94 | 183.94
107 | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/14745) | SM/14745 | 216.7 | 236 | NEW | 10 | Delayed | 43 | 31/01/2023 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 93.48 | 93.48
108 | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS (SM/12404) | SM/12404 | 572.81 | 1656 | NEW | 10 | Delayed | 2 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 13.98 | 13.98
109 | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS (SM/12495) | SM/12495 | 581.74 | 1623 | NEW | 10 | Delayed | 21 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 124.65 | 124.65
110 | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12400) | SM/12400 | 465.14 | 1112 | NEW | 10 | Delayed | 42 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 197.19 | 197.19
111 | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS (SM/11946) | SM/11946 | 984.88 | 4142 | NEW | 10 | Delayed | 7 | 24/08/2022 | 31/12/2025 | 26/06/2025 | 03/05/2023 | 64.78 | 64.78
112 | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/12886) | SM/12886 | 531.79 | 1045 | NEW | 10 | Delayed | 10 | 23/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 51.93 | 51.93
113 | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS (SM/13854) | SM/13854 | 749.32 | 1503 | NEW | 10 | Delayed | 22 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 166.86 | 166.86
114 | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12151) | SM/12151 | 687.4 | 2338 | NEW | 10 | Delayed | 5 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 02/05/2023 | 32.14 | 32.14
115 | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/13695) | SM/13695 | 719.9 | 1991 | NEW | 10 | Delayed | 32 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 02/05/2023 | 230.23 | 230.23
116 | KHARAT KATBAR & ADJOINING MOUJAS PWSS (SM/12175) | SM/12175 | 725.48 | 1895 | NEW | 10 | Delayed | 19 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 135.09 | 135.09
117 | HOGALBERYA AND ADJOINING MOUJAS PWSS (SM/12150) | SM/12150 | 762.45 | 2680 | NEW | 10 | Delayed | 1 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 9.27 | 9.27
118 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) (SM/19188) | SM/19188 | 74155.64 | 85853 | NEW | 12 | Delayed | 1 | 07/03/2024 | 31/03/2026 | 26/06/2025 | 13/03/2024 | 1090.74 | 770.67
119 | CHALTI AND ADJOINING MOUJAS PWSS (SM/12505) | SM/12505 | 592.82 | 1098 | NEW | 15 | Delayed | 17 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 98.9 | 98.9
120 | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS (SM/12405) | SM/12405 | 466.31 | 893 | NEW | 15 | Delayed | 5 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 28/03/2023 | 23.03 | 23.03
121 | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS (SM/12433) | SM/12433 | 540.95 | 1833 | NEW | 15 | Delayed | 3 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 14.72 | 14.72
122 | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11859) | SM/11859 | 37.95 | 0 | AUGMENTATION | 15 | Delayed | 22 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 18/08/2022 | 8.29 | 8.29
123 | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS (SM/14673) | SM/14673 | 642.05 | 614 | NEW | 15 | Delayed | 32 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 202.99 | 202.99
124 | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. (SM/13851) | SM/13851 | 167.94 | 249 | NEW | 15 | Delayed | 39 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 66.17 | 66.17
125 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III (SM/15841) | SM/15841 | 432.64 | 99 | AUGMENTATION | 15 | Delayed | 3 | 20/02/2023 | 07/11/2025 | 26/06/2025 | 25/04/2023 | 13.16 | 13.16
126 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) (SM/16458) | SM/16458 | 170.2 | 675 | AUGMENTATION | 15 | Delayed | 6 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 10.8 | 10.8
127 | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS (SM/12160) | SM/12160 | 751.44 | 2064 | NEW | 15 | Delayed | 49 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 368.7 | 368.7
128 | ERENDA AND ADJOINING MOUJAS PWSS (SM/12298) | SM/12298 | 697.48 | 1749 | NEW | 15 | Delayed | 38 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 264.12 | 264.12
129 | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12399) | SM/12399 | 696.35 | 1808 | NEW | 15 | Delayed | 23 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 157.84 | 157.84
130 | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS (SM/13853) | SM/13853 | 507.49 | 1023 | NEW | 15 | Delayed | 3 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 15.85 | 15.85
131 | SELMABAD AND ADJOINING MOUJAS PWSS (SM/12518) | SM/12518 | 757.8 | 2717 | NEW | 15 | Delayed | 22 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 167.52 | 167.52
132 | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme (SM/15034) | SM/15034 | 635.84 | 1807 | AUGMENTATION | 15 | Delayed | 3 | 04/02/2023 | 07/11/2025 | 26/06/2025 | 27/03/2023 | 22.19 | 22.19
133 | SATSATMAL & ADJOINING MOUJAS PWSS (SM/12163) | SM/12163 | 975.7 | 2638 | NEW | 15 | Delayed | 38 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 366.27 | 366.27
134 | GOBINDAPUR & ADJOINING MOUZAS (SM/12149) | SM/12149 | 385.96 | 910 | NEW | 15 | Delayed | 5 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 19.08 | 19.08
135 | BASANTA CHAK AND ADJOINING MOUJAS PWSS (SM/12144) | SM/12144 | 564.98 | 2072 | NEW | 15 | Delayed | 60 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 340.06 | 340.06
136 | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12774) | SM/12774 | 676.58 | 1680 | NEW | 15 | Delayed | 23 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 157.26 | 157.26
137 | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16938) | SM/16938 | 80.74 | 0 | AUGMENTATION | 15 | Delayed | 59 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 47.36 | 47.36
138 | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16939) | SM/16939 | 62.87 | 0 | AUGMENTATION | 15 | Delayed | 1 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 0.83 | 0.83
139 | KANTHI BARI AND ADJOINING MOUJAS PWSS (SM/12289) | SM/12289 | 795.33 | 1276 | NEW | 15 | Delayed | 55 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 437.91 | 437.91
140 | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS (SM/14749) | SM/14749 | 342.28 | 425 | NEW | 15 | Delayed | 9 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 29.96 | 29.96
141 | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13690) | SM/13690 | 464.83 | 695 | NEW | 15 | Delayed | 27 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 123.71 | 123.71
142 | CHAK BHABANI & ADJOINING MOUJAS PWSS (SM/15512) | SM/15512 | 1095.47 | 2843 | NEW | 15 | Delayed | 60 | 16/02/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 655.41 | 655.41
143 | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) (SM/16465) | SM/16465 | 122.31 | 0 | AUGMENTATION | 15 | Delayed | 20 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 25.01 | 25.01
144 | PATNA & ADJOINING MOUZAS (SM/12164) | SM/12164 | 1065.08 | 2930 | NEW | 15 | Delayed | 45 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 482.23 | 482.23
145 | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS (SM/14671) | SM/14671 | 471.07 | 1040 | NEW | 15 | Delayed | 32 | 31/01/2023 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 149.21 | 149.21
146 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III (SM/15510) | SM/15510 | 1406.2 | 4683 | AUGMENTATION | 15 | Delayed | 40 | 16/02/2023 | 31/03/2026 | 26/06/2025 | 04/05/2023 | 565.6 | 565.6
147 | Piped Water Supply Scheme for Sankarpur Zone-III (SM/15846) | SM/15846 | 338.75 | 267 | AUGMENTATION | 15 | Delayed | 10 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 35.28 | 35.28
148 | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. (SM/12321) | SM/12321 | 630.08 | 1155 | NEW | 15 | Delayed | 46 | 09/09/2022 | 31/03/2026 | 26/06/2025 | 20/03/2023 | 291.54 | 291.54
149 | DURMUT AND ADJOINING MOUJAS PWSS (SM/12820) | SM/12820 | 690.44 | 1698 | NEW | 15 | Delayed | 9 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 24/03/2023 | 60.15 | 60.15
150 | NONAKOURDA AND IT'S ADJOINING MOUJAS (SM/13857) | SM/13857 | 428.88 | 1018 | NEW | 15 | Delayed | 18 | 25/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 77.5 | 77.5
151 | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. (SM/12322) | SM/12322 | 556 | 1709 | NEW | 15 | Delayed | 34 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 189.35 | 189.35
152 | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13740) | SM/13740 | 669.57 | 1327 | NEW | 15 | Delayed | 32 | 17/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 215.15 | 215.15
153 | MASHAGON AND ITS ADJOINING MOUJAS PWSS (SM/13883) | SM/13883 | 204.23 | 401 | NEW | 15 | Delayed | 1 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 2.47 | 2.47
154 | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) (SM/16946) | SM/16946 | 85.63 | 0 | AUGMENTATION | 15 | Delayed | 66 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 19/05/2023 | 56.28 | 56.28
155 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/18765) | SM/18765 | 63.12 | 0 | AUGMENTATION | 15 | Delayed | 0 | 23/08/2023 | 31/12/2025 | 26/06/2025 | 29/11/2023 | 0 | 0
156 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. (SM/09022) | SM/09022 | 548.34 | 0 | SUPPORT-M&E | 15 | Delayed | 0 | 30/10/2021 | 31/03/2024 | 05/10/2023 | 22/08/2022 | 0 | 0
157 | GULURI AND IT'S ADJOING MOUJAS (SM/13888) | SM/13888 | 533.49 | 1376 | NEW | 18 | Delayed | 27 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 17/04/2023 | 142.52 | 142.52
158 | BIRAMPUT AND ADJOINING MOUJAS PWSS (SM/12497) | SM/12497 | 512.1 | 940 | NEW | 20 | Delayed | 45 | 13/09/2022 | 31/03/2026 | 26/06/2025 | 20/03/2023 | 230.5 | 230.5
159 | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme (SM/16194) | SM/16194 | 730.61 | 1427 | AUGMENTATION | 20 | Delayed | 29 | 24/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 210.27 | 210.27
160 | DEULI & IT'S ADJOINING MOUJAS PWSS (SM/13744) | SM/13744 | 725.58 | 1586 | NEW | 20 | Delayed | 43 | 17/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 310.38 | 310.38
161 | TAJPUR AND ADJOINING MOUJAS PWSS (SM/12284) | SM/12284 | 815.19 | 2785 | NEW | 20 | Delayed | 44 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 357.01 | 357.01
162 | KIARANA AND ADJOINING MOUJAS PWSS (SM/12628) | SM/12628 | 710.87 | 1424 | NEW | 20 | Delayed | 34 | 19/09/2022 | 31/03/2025 | 26/06/2025 | 31/12/2022 | 244.5 | 244.5
163 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. (SM/14486) | SM/14486 | 42.52 | 0 | AUGMENTATION | 20 | Delayed | 0 | 20/01/2023 | 31/12/2026 | 26/06/2025 | 20/02/2023 | 0 | 0
164 | Augmentation of Astichak (Zone-II) PWSS (SM/15035) | SM/15035 | 768.16 | 2196 | AUGMENTATION | 20 | Delayed | 59 | 04/02/2023 | 07/11/2025 | 26/06/2025 | 27/03/2023 | 454.91 | 454.91
165 | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS (SM/12130) | SM/12130 | 411.46 | 1566 | NEW | 20 | Delayed | 25 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 104.11 | 104.11
166 | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS (SM/13856) | SM/13856 | 227.92 | 477 | NEW | 20 | Delayed | 34 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 77.29 | 77.29
167 | BIJAYNAGAR & ADJOINING MOUJAS PWSS (SM/12157) | SM/12157 | 695.66 | 1750 | NEW | 20 | Delayed | 46 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 19/07/2023 | 320 | 320
168 | BAHADURPUR AND ADJOINING MOUJAS PWSS (SM/12169) | SM/12169 | 915.42 | 2470 | NEW | 20 | Delayed | 48 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 12/05/2023 | 440.51 | 440.51
169 | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 (SM/14840) | SM/14840 | 154.51 | 27 | AUGMENTATION | 20 | Delayed | 41 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 64.07 | 64.07
170 | GURGRAM & ADJOINING MOUZAS (SM/18311) | SM/18311 | 1027.99 | 2897 | NEW | 20 | Delayed | 64 | 26/06/2023 | 31/12/2025 | 26/06/2025 | 25/07/2023 | 656.92 | 656.92
171 | BARNAN AND ITS ADJOINING MOUJAS PWSS (SM/11884) | SM/11884 | 404.59 | 0 | NEW | 20 | Delayed | 23 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 94.47 | 94.47
172 | BARAGECHA AND ADJOINING MOUJAS PWSS (SM/13885) | SM/13885 | 461.96 | 785 | NEW | 20 | Delayed | 17 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 79.56 | 79.56
173 | BANCHBERA AND ITS ADJOINING MOUJAS PWSS (SM/16200) | SM/16200 | 197.46 | 147 | NEW | 20 | Delayed | 69 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 135.8 | 135.8
174 | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS (SM/11885) | SM/11885 | 410.86 | 1306 | NEW | 20 | Delayed | 27 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 110.61 | 110.61
175 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II (SM/13716) | SM/13716 | 1060.08 | 3882 | AUGMENTATION | 20 | Delayed | 56 | 17/11/2022 | 31/12/2025 | 26/06/2025 | 31/08/2022 | 597.45 | 597.45
176 | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. (SM/13369) | SM/13369 | 56.79 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 20 | Delayed | 0 | 19/10/2022 | 31/03/2024 | 05/10/2023 |  | 0 | 0
177 | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11860) | SM/11860 | 106.95 | 0 | AUGMENTATION | 22 | Delayed | 40 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 18/08/2022 | 42.55 | 42.55
178 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II (SM/10594) | SM/10594 | 819.79 | 2508 | AUGMENTATION | 22 | Delayed | 34 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 281.18 | 281.18
179 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) (SM/16461) | SM/16461 | 131.18 | 176 | AUGMENTATION | 25 | Delayed | 24 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 31.42 | 31.42
180 | Piped Water Supply Scheme for Sankarpur Zone-V (SM/15847) | SM/15847 | 342.52 | 321 | AUGMENTATION | 25 | Delayed | 27 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 92.95 | 92.95
181 | Piped Water Supply Scheme for Bathuari Zone-II (SM/15853) | SM/15853 | 439.72 | 12 | AUGMENTATION | 25 | Delayed | 30 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 28/04/2023 | 131.38 | 131.38
182 | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS (SM/11947) | SM/11947 | 565.75 | 3857 | NEW | 25 | Delayed | 45 | 24/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 255.22 | 255.22
183 | PURBA RADHAPUR & ADJOINING MOUZAS (SM/12154) | SM/12154 | 758.06 | 1870 | NEW | 25 | Delayed | 41 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 309.35 | 309.35
184 | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS (SM/13683) | SM/13683 | 710.43 | 2111 | NEW | 25 | Delayed | 42 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 11/04/2023 | 296.92 | 296.92
185 | DUBDA IT'S ADJOINING MOUJAS PWSS (SM/15513) | SM/15513 | 1290.54 | 4067 | NEW | 25 | Delayed | 24 | 16/02/2023 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 303.45 | 303.45
186 | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS (SM/18303) | SM/18303 | 1458.55 | 4497 | NEW | 25 | Delayed | 33 | 26/06/2023 | 31/12/2025 | 26/06/2025 | 12/07/2023 | 479.41 | 479.41
187 | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. (SM/12483) | SM/12483 | 520.66 | 1068 | NEW | 25 | Delayed | 35 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 180.26 | 180.26
188 | BAMANPUR AND ADJOINING MOUJAS PWSS (SM/12493) | SM/12493 | 606.04 | 1362 | NEW | 25 | Delayed | 40 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 20/04/2023 | 243.82 | 243.82
189 | SAHARA AND ADJOINING MOUJAS PWSS (SM/12296) | SM/12296 | 500.78 | 1155 | NEW | 25 | Delayed | 35 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 28/03/2023 | 172.81 | 172.81
190 | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/14844) | SM/14844 | 62.78 | 0 | AUGMENTATION | 25 | Delayed | 60 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 37.59 | 37.59
191 | BAINCHA AND IT'S ADJOINING MOUJAS PWSS (SM/14455) | SM/14455 | 412.43 | 700 | NEW | 25 | Delayed | 45 | 20/01/2023 | 31/03/2025 | 26/06/2025 | 28/03/2023 | 185.73 | 185.73
192 | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 (SM/15844) | SM/15844 | 444.01 | 173 | AUGMENTATION | 25 | Delayed | 1 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 2.89 | 2.89
193 | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) (SM/12268) | SM/12268 | 1409.77 | 6014 | AUGMENTATION | 25 | Delayed | 43 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 28/01/2022 | 611.75 | 611.75
194 | SATKALUA AND IT'S ADJOINING MOUJAS PWSS (SM/14695) | SM/14695 | 374.28 | 816 | NEW | 25 | Delayed | 23 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 87.56 | 87.56
195 | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. (SM/15851) | SM/15851 | 74.9 | 250 | NEW | 25 | Delayed | 82 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 61.25 | 61.25
196 | GAR BHERA & ADJOINING MOUZAS (SM/12159) | SM/12159 | 596.45 | 1275 | NEW | 25 | Delayed | 61 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 10/04/2023 | 366.16 | 366.16
197 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) (SM/16460) | SM/16460 | 139.71 | 172 | AUGMENTATION | 25 | Delayed | 29 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 41.14 | 41.14
198 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I (SM/14841) | SM/14841 | 207.52 | 69 | AUGMENTATION | 25 | Delayed | 30 | 03/02/2023 | 07/11/2025 | 26/06/2025 | 25/04/2023 | 63.23 | 63.23
199 | SHWNIA AND ADJOINING MOUJAS PWSS (SM/12494) | SM/12494 | 453.35 | 734 | NEW | 25 | Delayed | 28 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 129.09 | 129.09
200 | KHAGA AND IT'S ADJOINING MOUJAS PWSS (SM/12504) | SM/12504 | 764.31 | 1806 | NEW | 25 | Delayed | 41 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 310.87 | 310.87
201 | PURBA NUKHA AND ADJOINING MOUJAS (SM/14742) | SM/14742 | 668.28 | 2344 | NEW | 25 | Delayed | 25 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 164.89 | 164.89
202 | JAHANABAD AND IT'S ADJOINING MOUJAS (SM/12813) | SM/12813 | 974.08 | 2411 | NEW | 25 | Delayed | 39 | 20/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 379.28 | 379.28
203 | Piped Water Supply Scheme for Sankarpur Zone-I (SM/18766) | SM/18766 | 370.29 | 486 | AUGMENTATION | 25 | Delayed | 28 | 23/08/2023 | 31/12/2025 | 26/06/2025 | 28/11/2022 | 105.07 | 105.07
204 | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/11612) | SM/11612 | 69.8 | 0 | AUGMENTATION | 28 | Delayed | 55 | 26/07/2022 | 31/03/2025 | 26/06/2025 | 18/03/2021 | 38.3 | 38.3
205 | PANUSI AND ADJOINING MOUJAS PWSS (SM/12506) | SM/12506 | 788.16 | 2037 | NEW | 30 | Delayed | 44 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 27/04/2023 | 343.05 | 343.05
206 | Augmentation of Ramnagar (Zone-I) PWSS (SM/12485) | SM/12485 | 835.22 | 3086 | AUGMENTATION | 30 | Delayed | 30 | 13/09/2022 | 31/12/2026 | 26/06/2025 | 19/01/2023 | 254.43 | 254.43
207 | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS (SM/12129) | SM/12129 | 582.43 | 2545 | NEW | 30 | Delayed | 84 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 03/05/2023 | 489.58 | 489.58
208 | ABAS BERYA & ADJOINING MOUZAS (SM/12162) | SM/12162 | 620.61 | 1576 | NEW | 30 | Delayed | 24 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 148.41 | 146.4
209 | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/14845) | SM/14845 | 66.74 | 0 | AUGMENTATION | 30 | Delayed | 57 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 10/02/2023 | 38.32 | 38.32
210 | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. (SM/12303) | SM/12303 | 135.48 | 2340 | RETROFITTING | 30 | Delayed | 51 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 17/02/2023 | 68.75 | 68.75
211 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte (SM/17173) | SM/17173 | 448.63 | 840 | NEW | 30 | Delayed | 70 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 05/04/2023 | 312.63 | 312.63
212 | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS (SM/12407) | SM/12407 | 545.08 | 1020 | NEW | 30 | Delayed | 46 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 11/04/2023 | 251.4 | 251.4
213 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. (SM/10585) | SM/10585 | 969 | 1356 | NEW | 30 | Delayed | 78 | 18/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 758.96 | 758.96
214 | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16204) | SM/16204 | 76.08 | 0 | AUGMENTATION | 30 | Delayed | 63 | 24/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 47.92 | 47.92
215 | MIRJAPUR AND IT'S ADJOINING MOUJAS (SM/12516) | SM/12516 | 515.17 | 1035 | NEW | 30 | Delayed | 13 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 19/04/2023 | 68.34 | 68.34
216 | MADHYA HINGLI AND ADJOINING MOUJAS PWSS (SM/12498) | SM/12498 | 767.33 | 1757 | NEW | 30 | Delayed | 45 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 347.22 | 347.22
217 | CHANDPUR AND ADJOINING MOUJAS PWSS (SM/13693) | SM/13693 | 613.46 | 1358 | NEW | 30 | Delayed | 27 | 14/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 164.33 | 164.33
218 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. (SM/10620) | SM/10620 | 992 | 1279 | NEW | 30 | Delayed | 65 | 20/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 644.24 | 644.24
219 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. (SM/10618) | SM/10618 | 969 | 1306 | NEW | 30 | Delayed | 50 | 20/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 487.06 | 487.06
220 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10619) | SM/10619 | 974 | 1080 | NEW | 30 | Delayed | 50 | 20/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 484.2 | 484.2
221 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. (SM/10621) | SM/10621 | 989 | 1105 | NEW | 30 | Delayed | 77 | 20/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 761.49 | 761.49
222 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) (SM/16453) | SM/16453 | 115.08 | 1321 | RETROFITTING | 30 | Delayed | 22 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 08/06/2023 | 25.27 | 25.27
223 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/09021) | SM/09021 | 43.76 | 0 | SUPPORT-WQMSP | 30 | Delayed | 0 | 30/10/2021 | 31/12/2023 | 05/10/2023 | 25/11/2021 | 0 | 0
224 | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. (SM/11816) | SM/11816 | 89.61 | 0 | SUPPORT-WQMSP | 30 | Delayed | 0 | 16/08/2022 | 31/03/2024 | 05/10/2023 | 30/12/2020 | 0 | 0
225 | KANCHANPUR AND ADJOINING MOUJAS PWSS (SM/12403) | SM/12403 | 584.24 | 1704 | NEW | 35 | Delayed | 37 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 216.5 | 216.5
226 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. (SM/14837) | SM/14837 | 704.17 | 2069 | AUGMENTATION | 35 | Delayed | 36 | 03/02/2023 | 07/11/2025 | 26/06/2025 | 27/02/2023 | 252.65 | 252.65
227 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. (SM/16712) | SM/16712 | 143.36 | 0 | AUGMENTATION | 35 | Delayed | 48 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 69.52 | 69.52
228 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I (SM/10725) | SM/10725 | 1006.09 | 3032 | AUGMENTATION | 35 | Delayed | 33 | 18/05/2022 | 31/03/2026 | 26/06/2025 | 12/07/2022 | 334.39 | 334.39
229 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). (SM/11615) | SM/11615 | 915.35 | 3857 | AUGMENTATION | 35 | Delayed | 22 | 26/07/2022 | 31/12/2025 | 26/06/2025 | 22/09/2022 | 200.37 | 200.37
230 | JAMITTA & ADJOINING MOUZAS (SM/12137) | SM/12137 | 373.67 | 1163 | NEW | 35 | Delayed | 39 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 15/03/2023 | 145.99 | 145.99
231 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) (SM/10589) | SM/10589 | 980.6 | 0 | AUGMENTATION | 35 | Delayed | 53 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 07/09/2022 | 523.27 | 523.27
232 | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. (SM/11613) | SM/11613 | 68.66 | 0 | AUGMENTATION | 35 | Delayed | 0 | 26/07/2022 | 31/12/2025 | 26/06/2025 | 18/08/2022 | 0 | 0
233 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. (SM/16713) | SM/16713 | 140.37 | 0 | AUGMENTATION | 35 | Delayed | 0 | 14/03/2023 | 31/03/2025 | 26/06/2025 | 25/04/2023 | 0 | 0
234 | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13741) | SM/13741 | 357.16 | 580 | NEW | 35 | Delayed | 46 | 17/11/2022 | 07/11/2025 | 26/06/2025 | 30/10/2023 | 163.68 | 163.68
235 | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS (SM/12507) | SM/12507 | 593.43 | 1702 | NEW | 35 | Delayed | 24 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 31/12/2022 | 144.53 | 144.53
236 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). (SM/12364) | SM/12364 | 1068.67 | 5100 | AUGMENTATION | 35 | Delayed | 46 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 22/09/2022 | 489.58 | 489.58
237 | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/11896) | SM/11896 | 62.49 | 0 | AUGMENTATION | 35 | Delayed | 15 | 18/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 9.66 | 9.66
238 | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS (SM/13686) | SM/13686 | 520.05 | 1135 | NEW | 35 | Delayed | 39 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 202.71 | 202.71
239 | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16941) | SM/16941 | 448.63 | 896 | NEW | 35 | Delayed | 4 | 16/03/2023 | 31/12/2025 | 26/06/2025 | 05/04/2023 | 19.78 | 19.78
240 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. (SM/10617) | SM/10617 | 977.46 | 704 | NEW | 35 | Delayed | 81 | 20/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 795.03 | 795.03
241 | DKSHIM ANKHA & IT'S ADJOINING MOUJAS (SM/12515) | SM/12515 | 657.71 | 1635 | NEW | 35 | Delayed | 59 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 27/04/2023 | 387.74 | 387.74
242 | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12402) | SM/12402 | 650.26 | 1669 | NEW | 35 | Delayed | 29 | 13/09/2022 | 30/09/2025 | 26/06/2025 | 10/04/2023 | 186.38 | 186.38
243 | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS (SM/11883) | SM/11883 | 428.89 | 1643 | NEW | 35 | Delayed | 29 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 122.29 | 122.29
244 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) (SM/16462) | SM/16462 | 128.06 | 428 | AUGMENTATION | 35 | Delayed | 12 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 15.67 | 15.67
245 | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17221) | SM/17221 | 80.74 | 0 | AUGMENTATION | 35 | Delayed | 52 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 41.88 | 41.88
246 | URURI AND ADJOINING MOUJAS PWSS (SM/12166) | SM/12166 | 816.68 | 2233 | NEW | 35 | Delayed | 37 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 10/03/2023 | 298.7 | 298.7
247 | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia (SM/12491) | SM/12491 | 745.53 | 3188 | AUGMENTATION | 35 | Delayed | 45 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 333.32 | 333.32
248 | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS (SM/12509) | SM/12509 | 683.07 | 1660 | NEW | 35 | Delayed | 53 | 13/09/2022 | 31/03/2026 | 26/06/2025 | 19/04/2023 | 362.79 | 362.79
249 | KAPASDA & IT'S ADJOINING MOUJAS PWSS (SM/13692) | SM/13692 | 778.74 | 1475 | NEW | 35 | Delayed | 23 | 14/11/2022 | 31/03/2025 | 26/06/2025 | 12/05/2023 | 175.4 | 175.4
250 | JHAUGERYA PIPED WATER SUPPLY SCHEME. (SM/15842) | SM/15842 | 179.26 | 158 | NEW | 35 | Delayed | 56 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 99.79 | 99.79
251 | AMRITBERYA AND ADJOINING MOUJAS (SM/15511) | SM/15511 | 1024.73 | 3440 | NEW | 35 | Delayed | 39 | 16/02/2023 | 31/03/2026 | 26/06/2025 | 04/05/2023 | 400.29 | 400.29
252 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V (SM/16295) | SM/16295 | 458.23 | 184 | AUGMENTATION | 35 | Delayed | 42 | 23/02/2023 | 31/03/2026 | 26/06/2025 | 25/04/2023 | 192.99 | 192.99
253 | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. (SM/11887) | SM/11887 | 57.27 | 0 | AUGMENTATION | 35 | Delayed | 65 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 24/11/2022 | 37.18 | 37.18
254 | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS (SM/12816) | SM/12816 | 600.38 | 1500 | NEW | 35 | Delayed | 58 | 20/09/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 345.61 | 345.61
255 | Piped Water Supply Scheme for Bathuari Zone-I (SM/14839) | SM/14839 | 181.49 | 23 | AUGMENTATION | 35 | Delayed | 48 | 03/02/2023 | 07/11/2025 | 26/06/2025 | 28/04/2023 | 87.07 | 87.07
256 | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS (SM/13855) | SM/13855 | 786.94 | 1908 | NEW | 35 | Delayed | 60 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 12/05/2023 | 473.78 | 473.78
257 | AILAN AND IT'S ADJOINING MOUJAS PWSS (SM/15514) | SM/15514 | 1127.65 | 3046 | NEW | 35 | Delayed | 12 | 16/02/2023 | 07/11/2025 | 26/06/2025 | 04/05/2023 | 140.85 | 140.85
258 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. (SM/15635) | SM/15635 | 58.07 | 0 | AUGMENTATION | 35 | Delayed | 96 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 55.82 | 55.82
259 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11471) | SM/11471 | 745.37 | 0 | AUGMENTATION | 35 | Delayed | 41 | 14/07/2022 | 31/12/2025 | 26/06/2025 | 22/11/2022 | 303.41 | 303.41
260 | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. (SM/11710) | SM/11710 | 146.89 | 0 | SUPPORT-WQMSP | 35 | Delayed | 0 | 03/08/2022 | 31/03/2024 | 05/10/2023 | 10/05/2022 | 0 | 0
261 | JAYNAGAR AND ADJOINING MOUJAS PWSS (SM/12502) | SM/12502 | 773.24 | 2174 | NEW | 38 | Delayed | 30 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 228.7 | 228.7
262 | SOYA DIGHI AND IT'S ADJOINING MOUJAS (SM/12809) | SM/12809 | 554.17 | 1914 | NEW | 40 | Delayed | 16 | 20/09/2022 | 31/03/2025 | 26/06/2025 | 02/05/2023 | 91.24 | 91.24
263 | SRIKANTHA AND ADJOINING MOUJAS PWSS (SM/12512) | SM/12512 | 756.99 | 2575 | NEW | 40 | Delayed | 24 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 180.52 | 180.52
264 | JERTHAN AND ADJOINING MOUJAS PWSS (SM/12308) | SM/12308 | 762.33 | 2232 | NEW | 40 | Delayed | 44 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 337.29 | 337.29
265 | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12141) | SM/12141 | 894.23 | 2407 | NEW | 40 | Delayed | 30 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 29/12/2022 | 272.04 | 272.04
266 | Augmentation of Astichak (Zone-I) PWSS (SM/15462) | SM/15462 | 679.21 | 1291 | AUGMENTATION | 40 | Delayed | 5 | 04/02/2023 | 07/11/2025 | 26/06/2025 | 27/03/2023 | 35.8 | 35.8
267 | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16390) | SM/16390 | 161.69 | 0 | AUGMENTATION | 40 | Delayed | 43 | 28/02/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 70.29 | 70.29
268 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) (SM/10591) | SM/10591 | 703.33 | 0 | AUGMENTATION | 40 | Delayed | 35 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 14/10/2022 | 247.2 | 247.2
269 | Augmentation of Moyna (Zone-I) PWSS (SM/11614) | SM/11614 | 998.4 | 4527 | AUGMENTATION | 40 | Delayed | 55 | 26/07/2022 | 31/03/2026 | 26/06/2025 | 03/01/2022 | 548.35 | 548.35
270 | TELAMI AND ADJOINING MOUJAS PWSS (SM/12288) | SM/12288 | 462.76 | 724 | NEW | 40 | Delayed | 30 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 137.91 | 137.91
271 | HALUD BARI AND ADJOINING MOUJAS (SM/12821) | SM/12821 | 728 | 2543 | NEW | 40 | Delayed | 72 | 20/09/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 525.6 | 525.6
272 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/14843) | SM/14843 | 63.12 | 0 | AUGMENTATION | 40 | Delayed | 32 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 20.19 | 20.19
273 | Solarization of grid connected pumping installation at Chapbasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17378) | SM/17378 | 8.3 | 0 | SOLARISATION | 40 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
274 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I (SM/12487) | SM/12487 | 989.31 | 4400 | AUGMENTATION | 40 | Delayed | 26 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 17/06/2022 | 261.86 | 261.86
275 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. (SM/11979) | SM/11979 | 1668.76 | 7010 | AUGMENTATION | 40 | Delayed | 37 | 31/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 614.52 | 614.52
276 | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16205) | SM/16205 | 75.38 | 0 | AUGMENTATION | 40 | Delayed | 65 | 24/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 48.81 | 48.81
277 | BALGOBINDAPUR & ADJOINING MOUZAS (SM/12143) | SM/12143 | 879.41 | 2138 | NEW | 40 | Delayed | 7 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 29/12/2022 | 60.99 | 60.99
278 | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. (SM/14113) | SM/14113 | 1300.67 | 5920 | AUGMENTATION | 40 | Delayed | 67 | 02/01/2023 | 31/12/2025 | 26/06/2025 | 07/01/2022 | 868.13 | 868.13
279 | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/15038) | SM/15038 | 85.63 | 0 | AUGMENTATION | 40 | Delayed | 48 | 04/02/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 41.51 | 41.51
280 | TALADIHA AND ADJOINING MOUJAS PWSS (SM/12283) | SM/12283 | 496.8 | 1324 | NEW | 40 | Delayed | 27 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 131.69 | 131.69
281 | KAYEMGERYA AND ADJOINING MOUJAS PWSS (SM/12167) | SM/12167 | 744.93 | 2055 | NEW | 40 | Delayed | 45 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 333.41 | 333.41
282 | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS (SM/12406) | SM/12406 | 1061.78 | 2186 | NEW | 40 | Delayed | 58 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 619.2 | 619.2
283 | UTTAR SAUTANCHAK Piped Water Supply Scheme. (SM/14741) | SM/14741 | 299.47 | 461 | NEW | 40 | Delayed | 38 | 31/01/2023 | 31/03/2026 | 26/06/2025 | 04/05/2023 | 113.75 | 113.75
284 | KAKRA & ADJOINING MOUZAS (SM/12138) | SM/12138 | 784.19 | 3218 | NEW | 40 | Delayed | 67 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 522.94 | 522.94
285 | ITA BARIA & ADJOINING MOUZAS (SM/14042) | SM/14042 | 934.72 | 2068 | NEW | 40 | Delayed | 51 | 12/12/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 477.64 | 477.64
286 | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17194) | SM/17194 | 161.69 | 0 | AUGMENTATION | 40 | Delayed | 42 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 68.48 | 68.48
287 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I (SM/12489) | SM/12489 | 712.69 | 2596 | AUGMENTATION | 42 | Delayed | 57 | 13/09/2022 | 31/03/2026 | 26/06/2025 | 08/02/2022 | 402.68 | 402.68
288 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) (SM/10590) | SM/10590 | 585.68 | 4830 | AUGMENTATION | 42 | Delayed | 58 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 27/01/2022 | 337.98 | 337.98
289 | HARINAN PWSS & ADJOINING MOUJAS (SM/12152) | SM/12152 | 708.52 | 2360 | NEW | 44 | Delayed | 63 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 444.9 | 444.9
290 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I (SM/12118) | SM/12118 | 1079.89 | 3903 | AUGMENTATION | 44 | Delayed | 62 | 06/09/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 664.79 | 664.79
291 | BASANTIA AND IT'S ADJOINING MOUJAS PWSS (SM/14451) | SM/14451 | 525.09 | 1581 | NEW | 45 | Delayed | 26 | 20/01/2023 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 136.41 | 136.41
292 | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16257) | SM/16257 | 520.9 | 958 | NEW | 45 | Delayed | 17 | 24/02/2023 | 31/03/2025 | 26/06/2025 | 28/03/2023 | 90.75 | 90.75
293 | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS (SM/12510) | SM/12510 | 755.87 | 2000 | NEW | 45 | Delayed | 24 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 178.88 | 178.88
294 | BARDA AND ADJOINING MOUJAS PWSS (SM/12306) | SM/12306 | 594.37 | 1396 | NEW | 45 | Delayed | 20 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 116.53 | 116.53
295 | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS (SM/13699) | SM/13699 | 1097.22 | 3181 | NEW | 45 | Delayed | 62 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 682.23 | 682.23
296 | MAYACHAR AND ADJOINING MOUJAS PWSS (SM/12281) | SM/12281 | 575.5 | 1306 | NEW | 45 | Delayed | 39 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 222.47 | 222.47
297 | BARTTANA & IT'S ADJOINING MOUJAS PWSS (SM/13697) | SM/13697 | 695.93 | 1639 | NEW | 45 | Delayed | 27 | 14/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 186.13 | 186.13
298 | BARTTAN AND ADJOINING MOUJAS PWSS (SM/12501) | SM/12501 | 1048.66 | 3076 | NEW | 45 | Delayed | 39 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 404.82 | 404.82
299 | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) (SM/13238) | SM/13238 | 143.18 | 364 | RETROFITTING | 45 | Delayed | 45 | 14/10/2022 | 31/12/2025 | 26/06/2025 | 16/09/2022 | 64.7 | 64.7
300 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) (SM/10592) | SM/10592 | 903.71 | 0 | AUGMENTATION | 45 | Delayed | 56 | 18/04/2022 | 31/03/2025 | 26/06/2025 | 23/08/2022 | 508.76 | 508.76
301 | Augmentation of Moyna (Zone-II) PWSS (SM/11639) | SM/11639 | 990.17 | 3745 | AUGMENTATION | 45 | Delayed | 73 | 27/07/2022 | 31/03/2026 | 26/06/2025 | 03/01/2022 | 719.39 | 719.39
302 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. (SM/10586) | SM/10586 | 992 | 1311 | NEW | 45 | Delayed | 77 | 18/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 763.96 | 763.96
303 | KURPAI AND ADJOINING MOUJAS PWSS (SM/11882) | SM/11882 | 498.52 | 1684 | NEW | 45 | Delayed | 17 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 85.13 | 85.13
304 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11470) | SM/11470 | 869.93 | 8505 | AUGMENTATION | 47 | Delayed | 77 | 14/07/2022 | 31/12/2025 | 26/06/2025 | 05/04/2022 | 672.93 | 672.93
305 | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS (SM/12293) | SM/12293 | 665.46 | 1638 | NEW | 48 | Delayed | 32 | 09/09/2022 | 31/03/2025 | 26/06/2025 | 12/05/2023 | 210.21 | 210.21
306 | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. (SM/12310) | SM/12310 | 899.01 | 2095 | NEW | 48 | Delayed | 52 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 465.38 | 465.38
307 | Augmentation of Suadighi piped water supply scheme. (SM/09919) | SM/09919 | 2222.11 | 6915 | AUGMENTATION | 50 | Delayed | 53 | 10/12/2021 | 31/12/2025 | 26/06/2025 | 31/01/2022 | 1179.6 | 1179.6
308 | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District (SM/09273) | SM/09273 | 249.69 | 1592 | AUGMENTATION | 50 | Delayed | 28 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 20/01/2022 | 69.05 | 69.05
309 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10689) | SM/10689 | 963 | 2443 | NEW | 50 | Delayed | 90 | 12/05/2022 | 31/12/2025 | 26/06/2025 | 05/04/2023 | 870.96 | 870.96
310 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11473) | SM/11473 | 873.48 | 0 | AUGMENTATION | 50 | Delayed | 28 | 14/07/2022 | 31/12/2025 | 26/06/2025 | 01/11/2022 | 247.48 | 247.48
311 | BISWANATHPUR PIPED WATER SUPPLY SCHEME. (SM/13850) | SM/13850 | 179.48 | 230 | NEW | 50 | Delayed | 56 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 100.92 | 100.92
312 | SIMULYA & IT'S ADJOINING MOUJAS PWSS (SM/12492) | SM/12492 | 917.62 | 2740 | NEW | 50 | Delayed | 32 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 297.84 | 297.84
313 | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. (SM/11552) | SM/11552 | 617.59 | 2646 | AUGMENTATION | 50 | Delayed | 57 | 22/07/2022 | 31/12/2025 | 26/06/2025 | 01/02/2022 | 351.49 | 351.49
314 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. (SM/09283) | SM/09283 | 686.91 | 3478 | AUGMENTATION | 50 | Delayed | 70 | 03/11/2021 | 31/03/2025 | 26/06/2025 | 02/12/2021 | 478.06 | 478.06
315 | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/15036) | SM/15036 | 242.53 | 0 | AUGMENTATION | 50 | Delayed | 48 | 04/02/2023 | 31/12/2025 | 26/06/2025 | 06/04/2023 | 115.33 | 115.33
316 | DEKHALI AND ADJOINING MOUJAS PWSS (SM/15515) | SM/15515 | 1239.4 | 2820 | NEW | 50 | Delayed | 71 | 16/02/2023 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 878.48 | 878.48
317 | Solarization of grid connected pumping installation at Mohisda, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17762) | SM/17762 | 16.61 | 0 | SOLARISATION | 50 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
318 | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. (SM/10072) | SM/10072 | 581.76 | 1833 | AUGMENTATION | 50 | Delayed | 53 | 27/01/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 306.15 | 306.15
319 | NAICHHANPUR AND ADJOINING MOUJAS PWSS (SM/12295) | SM/12295 | 593.04 | 1513 | NEW | 50 | Delayed | 68 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 02/05/2023 | 402.66 | 402.66
320 | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. (SM/16663) | SM/16663 | 12.39 | 0 | AUGMENTATION | 50 | Delayed | 1 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0.18 | 0.18
321 | MIRJAPUR AND ADJOINING MOUJAS PWSS (SM/12153) | SM/12153 | 939.19 | 2305 | NEW | 50 | Delayed | 56 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 523.49 | 523.49
322 | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) (SM/16466) | SM/16466 | 39.56 | 305 | RETROFITTING | 50 | Delayed | 65 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 25.66 | 25.66
323 | GOPINATHPUR & ADJOINING MOUZAS (SM/12158) | SM/12158 | 727.42 | 1851 | NEW | 50 | Delayed | 63 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 460.51 | 460.51
324 | ILASHPUR AND ADJOINING MOUJAS PWSS (SM/12294) | SM/12294 | 847.64 | 2038 | NEW | 50 | Delayed | 50 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 04/05/2023 | 423.18 | 423.18
325 | CHISTIPUR AND ADJOINING MOUJAS (SM/14672) | SM/14672 | 668.48 | 2004 | NEW | 50 | Delayed | 2 | 31/01/2023 | 31/12/2025 | 26/06/2025 | 28/03/2023 | 11.96 | 11.96
326 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M (SM/16469) | SM/16469 | 108.21 | 1180 | RETROFITTING | 50 | Delayed | 73 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 79.29 | 79.29
327 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. (SM/10683) | SM/10683 | 1126.18 | 5528 | AUGMENTATION | 50 | Delayed | 76 | 06/05/2022 | 31/03/2025 | 26/06/2025 | 01/12/2021 | 851.65 | 851.65
328 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) (SM/10664) | SM/10664 | 599.83 | 0 | AUGMENTATION | 50 | Delayed | 16 | 22/04/2022 | 31/03/2025 | 26/06/2025 | 01/11/2022 | 93.83 | 93.83
329 | MAKRAMPUR AND ADJOINING MOUJAS PWSS (SM/12282) | SM/12282 | 752.28 | 1422 | NEW | 50 | Delayed | 11 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 83.52 | 83.52
330 | BAISPUR AND ADJOINING MOUJAS PWSS (SM/12290) | SM/12290 | 495.84 | 1251 | NEW | 50 | Delayed | 40 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 197.95 | 197.95
331 | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) (SM/16467) | SM/16467 | 72.07 | 319 | RETROFITTING | 50 | Delayed | 79 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 57.26 | 57.26
332 | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17193) | SM/17193 | 80.74 | 0 | AUGMENTATION | 50 | Delayed | 41 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 32.81 | 32.81
333 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda (SM/10128) | SM/10128 | 1634.61 | 5364 | AUGMENTATION | 53 | Delayed | 38 | 08/02/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 622.3 | 622.3
334 | GARABAR PIPED WATER SUPPLY SCHEME. (SM/15850) | SM/15850 | 166.18 | 150 | NEW | 55 | Delayed | 58 | 20/02/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 96.41 | 96.41
335 | BRINDABANPUR & ADJOINING MOUJAS PWSS (SM/12148) | SM/12148 | 429.14 | 1023 | NEW | 55 | Delayed | 60 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 06/06/2023 | 257.11 | 257.11
336 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10666) | SM/10666 | 980.83 | 1451 | NEW | 55 | Delayed | 59 | 26/04/2022 | 31/03/2026 | 26/06/2025 | 09/03/2023 | 582.79 | 582.79
337 | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10681) | SM/10681 | 1073.49 | 6101 | AUGMENTATION | 55 | Delayed | 53 | 06/05/2022 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 573.44 | 573.44
338 | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11553) | SM/11553 | 944.76 | 4374 | AUGMENTATION | 55 | Delayed | 47 | 22/07/2022 | 31/12/2025 | 26/06/2025 | 01/02/2022 | 446.04 | 446.04
339 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. (SM/09274) | SM/09274 | 359.88 | 967 | AUGMENTATION | 55 | Delayed | 51 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 182.43 | 182.43
340 | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS (SM/12398) | SM/12398 | 645.5 | 1806 | NEW | 55 | Delayed | 32 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 204.1 | 204.1
341 | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11549) | SM/11549 | 850.53 | 5686 | AUGMENTATION | 56 | Delayed | 71 | 22/07/2022 | 31/03/2026 | 26/06/2025 | 03/02/2022 | 602.2 | 602.2
342 | PANCHET AND ADJOINING MOUJAS PWSS (SM/12170) | SM/12170 | 897.82 | 1919 | NEW | 59 | Delayed | 26 | 07/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 234.32 | 234.32
343 | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/12570) | SM/12570 | 1708.39 | 7341 | AUGMENTATION | 60 | Delayed | 70 | 14/09/2022 | 31/12/2025 | 26/06/2025 | 09/12/2022 | 1201.37 | 1201.37
344 | KIA AND IT'S ADJOINING MOUJAS (SM/12814) | SM/12814 | 720.1 | 1897 | NEW | 60 | Delayed | 28 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 28/03/2023 | 203.48 | 203.48
345 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. (SM/14838) | SM/14838 | 897.92 | 2173 | AUGMENTATION | 60 | Delayed | 30 | 03/02/2023 | 31/03/2026 | 26/06/2025 | 27/03/2023 | 273.61 | 273.61
346 | GOYALDA & ADJOINING MOUZAS PWSS (SM/12155) | SM/12155 | 579.91 | 1582 | NEW | 60 | Delayed | 43 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 29/12/2022 | 249.05 | 249.05
347 | Augmentation of Ground water Based Betkundu Water Supply Scheme (SM/11206) | SM/11206 | 1317.43 | 5997 | AUGMENTATION | 60 | Delayed | 71 | 08/06/2022 | 31/03/2025 | 26/06/2025 | 11/01/2022 | 938.06 | 938.06
348 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme (SM/09276) | SM/09276 | 340.42 | 909 | AUGMENTATION | 60 | Delayed | 49 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 167.18 | 167.18
349 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) (SM/10588) | SM/10588 | 999.73 | 7796 | AUGMENTATION | 60 | Delayed | 71 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 08/08/2022 | 706.69 | 706.69
350 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) (SM/11948) | SM/11948 | 533.3 | 4380 | AUGMENTATION | 60 | Delayed | 80 | 24/08/2022 | 31/12/2025 | 26/06/2025 | 11/01/2022 | 427.94 | 423.3
351 | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme. (SM/16657) | SM/16657 | 12.39 | 0 | AUGMENTATION | 60 | On track | 0 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
352 | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. (SM/12634) | SM/12634 | 503.6 | 1062 | NEW | 60 | Delayed | 15 | 19/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 76.5 | 76.5
353 | Augmentation of Ground Water based Jalpai Water Supply Scheme. (SM/11920) | SM/11920 | 2009.45 | 7890 | AUGMENTATION | 60 | Delayed | 63 | 22/08/2022 | 31/12/2025 | 26/06/2025 | 05/04/2022 | 1259.41 | 1259.41
354 | KADUA AND IT'S ADJOINING MOUJAS (SM/13689) | SM/13689 | 741.86 | 2150 | NEW | 60 | On track | 34 | 14/11/2022 | 31/03/2026 | 26/06/2025 | 12/05/2023 | 250.85 | 250.85
355 | Solarization of grid connected pumping installation at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17764) | SM/17764 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
356 | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17386) | SM/17386 | 8.3 | 0 | SOLARISATION | 60 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
357 | EREKHALI AND ADJOINING MOUJAS PWSS (SM/12139) | SM/12139 | 627.99 | 1713 | NEW | 60 | Delayed | 49 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 28/02/2023 | 305.1 | 305.1
358 | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. (SM/12320) | SM/12320 | 674.76 | 1497 | NEW | 60 | Delayed | 30 | 09/09/2022 | 07/12/2025 | 26/06/2025 | 31/12/2022 | 204.97 | 204.97
359 | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS (SM/12431) | SM/12431 | 827.64 | 1342 | NEW | 60 | Delayed | 45 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 19/07/2023 | 368.78 | 368.78
360 | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS (SM/12291) | SM/12291 | 717.02 | 1648 | NEW | 60 | Delayed | 45 | 09/09/2022 | 31/03/2025 | 26/06/2025 | 31/12/2022 | 321.97 | 321.97
361 | AGAR & ADJOINING MOUJAS PWSS (SM/12131) | SM/12131 | 388.58 | 832 | NEW | 60 | Delayed | 37 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 31/05/2023 | 145.39 | 145.39
362 | Solarization of grid connected pumping installation at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17783) | SM/17783 | 8.3 | 0 | SOLARISATION | 60 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
363 | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division (SM/08683) | SM/08683 | 15.07 | 0 | SUPPORT-WQMSP | 60 | Delayed | 0 | 23/08/2021 | 31/12/2023 | 22/05/2023 | 25/08/2021 | 0 | 0
364 | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS (SM/12878) | SM/12878 | 721.18 | 1527 | NEW | 62 | Delayed | 5 | 23/09/2022 | 31/12/2025 | 26/06/2025 | 28/03/2023 | 36.61 | 36.61
365 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. (SM/10682) | SM/10682 | 1414.27 | 5547 | AUGMENTATION | 65 | Delayed | 79 | 06/05/2022 | 31/03/2026 | 26/06/2025 | 01/12/2021 | 1118.22 | 1118.22
366 | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS (SM/12434) | SM/12434 | 617.73 | 1267 | NEW | 65 | Delayed | 59 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 363.1 | 363.1
367 | GATHRA AND ADJOINING MOUJAS PWSS (SM/12299) | SM/12299 | 627.78 | 3418 | NEW | 65 | Delayed | 49 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 17/04/2023 | 307.49 | 307.49
368 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11472) | SM/11472 | 834.19 | 8206 | AUGMENTATION | 65 | Delayed | 71 | 14/07/2022 | 31/12/2025 | 26/06/2025 | 05/04/2022 | 594.96 | 594.96
369 | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 (SM/14836) | SM/14836 | 391.4 | 210 | AUGMENTATION | 65 | Delayed | 23 | 03/02/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 90.57 | 90.57
370 | PUTPUTIA PWSS (SM/11886) | SM/11886 | 581.53 | 1670 | NEW | 65 | Delayed | 49 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 287.21 | 287.21
371 | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/13742) | SM/13742 | 694.6 | 1517 | NEW | 65 | Delayed | 70 | 17/11/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 487.75 | 487.75
372 | Providing FHTC (Functional Household Tap Connection) with Augmentation of Murisai Water Supply Scheme (SM/13889) | SM/13889 | 133.52 | 0 | AUGMENTATION | 65 | Delayed | 0 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 01/08/2023 | 0 | 0
373 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) (SM/11554) | SM/11554 | 742.35 | 5512 | AUGMENTATION | 65 | Delayed | 66 | 22/07/2022 | 31/12/2025 | 26/06/2025 | 18/01/2021 | 490.36 | 490.36
374 | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09336) | SM/09336 | 556.34 | 1784 | AUGMENTATION | 65 | Delayed | 69 | 12/11/2021 | 31/12/2025 | 26/06/2025 | 08/02/2022 | 381.24 | 381.24
375 | DANGAR TULSI AND ADJOINING MOUJAS PWSS (SM/12285) | SM/12285 | 712.76 | 1347 | NEW | 65 | Delayed | 32 | 09/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 229.55 | 229.55
376 | BELDA AND IT'S ADJOINING MOUJAS PWSS (SM/12710) | SM/12710 | 699.88 | 2385 | NEW | 65 | Delayed | 29 | 20/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 205.76 | 205.76
377 | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS (SM/13694) | SM/13694 | 625.23 | 1365 | NEW | 65 | Delayed | 49 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 24/07/2023 | 304.51 | 304.51
378 | JUMKI AND ADJOINING MOUJAS PWSS (SM/12995) | SM/12995 | 620.99 | 1636 | NEW | 65 | Delayed | 46 | 28/09/2022 | 07/11/2025 | 26/06/2025 | 31/12/2022 | 285.02 | 285.02
379 | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09913) | SM/09913 | 1104.23 | 6158 | AUGMENTATION | 65 | Delayed | 76 | 10/12/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 838.88 | 838.88
380 | DEPAL AND ADJOINING MOUJAS PWSS (SM/12287) | SM/12287 | 640.15 | 1789 | NEW | 65 | On track | 44 | 09/09/2022 | 31/03/2026 | 26/06/2025 | 31/12/2022 | 283.22 | 283.22
381 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. (SM/10030) | SM/10030 | 1321.6 | 707 | AUGMENTATION | 66 | Delayed | 80 | 19/01/2022 | 31/03/2025 | 26/06/2025 | 02/12/2021 | 1050.97 | 1050.96
382 | TULIA AND ADJOINING MOUJAS PWSS (SM/15037) | SM/15037 | 572.93 | 2059 | NEW | 68 | Delayed | 20 | 04/02/2023 | 31/12/2025 | 26/06/2025 | 27/03/2023 | 112.1 | 112.1
383 | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS (SM/12517) | SM/12517 | 743.4 | 2007 | NEW | 68 | Delayed | 36 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 269.06 | 269.06
384 | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09337) | SM/09337 | 529.85 | 1862 | AUGMENTATION | 69 | Delayed | 77 | 12/11/2021 | 31/03/2025 | 26/06/2025 | 02/12/2021 | 406.52 | 406.33
385 | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09402) | SM/09402 | 535.02 | 2132 | AUGMENTATION | 70 | Delayed | 53 | 17/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 286.03 | 286.03
386 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. (SM/09282) | SM/09282 | 890.9 | 4747 | AUGMENTATION | 70 | Delayed | 78 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 691.4 | 691.4
387 | Augmentation of Ground Water Based Bagmari Water Supply Scheme (SM/16711) | SM/16711 | 339.13 | 929 | AUGMENTATION | 70 | Delayed | 52 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 176.47 | 176.47
388 | Solarization of grid connected pumping installation at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17767) | SM/17767 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
389 | Solarization of grid connected pumping installation at Jagatpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17805) | SM/17805 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
390 | Solarization of grid connected pumping installation at Dakhsin Mechogram PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17367) | SM/17367 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
391 | Solarization of grid connected pumping installation at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17340) | SM/17340 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
392 | Solarization of grid connected pumping installation at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17314) | SM/17314 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
393 | Solarization of grid connected pumping installation at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17324) | SM/17324 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/10/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
394 | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17296) | SM/17296 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 15/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
395 | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) (SM/10433) | SM/10433 | 178.42 | 304 | RETROFITTING | 70 | Delayed | 40 | 12/04/2022 | 31/03/2025 | 26/06/2025 | 03/08/2022 | 72.2 | 72.2
396 | PANCH BAJARI & ADJOINING MOUJAS PWSS (SM/12173) | SM/12173 | 484.28 | 1015 | NEW | 70 | Delayed | 33 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 160.57 | 160.57
397 | Tilkhoja & Adjoining mouzas (SM/12133) | SM/12133 | 714.12 | 2331 | NEW | 70 | Delayed | 51 | 07/09/2022 | 31/03/2025 | 26/06/2025 | 29/12/2022 | 367.31 | 367.31
398 | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. (SM/10120) | SM/10120 | 1515.48 | 7239 | AUGMENTATION | 70 | Delayed | 73 | 08/02/2022 | 31/12/2025 | 26/06/2025 | 18/01/2022 | 1112.83 | 1112.83
399 | Solarization of grid connected pumping installation at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17341) | SM/17341 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 15/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
400 | Solarization of grid connected pumping installation at Gogras keshab bar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17723) | SM/17723 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
401 | Solarization of grid connected pumping installation at Erasal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17724) | SM/17724 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
402 | Solarization of grid connected pumping installation at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17793) | SM/17793 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
403 | Solarization of grid connected pumping installation at Bagmari (Egra-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17351) | SM/17351 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
404 | Solarization of grid connected pumping installation at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17309) | SM/17309 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
405 | Solarization of grid connected pumping installation at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17353) | SM/17353 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
406 | AJANGECHHYA PIPED WATER SUPPLY SCHEME. (SM/13852) | SM/13852 | 166.59 | 314 | NEW | 70 | Delayed | 25 | 25/11/2022 | 31/12/2025 | 26/06/2025 | 13/04/2023 | 41.55 | 41.55
407 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. (SM/09278) | SM/09278 | 678.53 | 3059 | AUGMENTATION | 70 | Delayed | 72 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 486.36 | 486.36
408 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) (SM/11617) | SM/11617 | 843.08 | 6291 | AUGMENTATION | 70 | Delayed | 49 | 26/07/2022 | 31/12/2025 | 26/06/2025 | 02/11/2022 | 415.97 | 415.97
409 | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. (SM/12482) | SM/12482 | 1000.8 | 2478 | NEW | 70 | Delayed | 58 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 20/04/2023 | 575.72 | 575.72
410 | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme. (SM/16667) | SM/16667 | 12.39 | 0 | AUGMENTATION | 70 | On track | 0 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
411 | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme. (SM/16668) | SM/16668 | 12.39 | 0 | AUGMENTATION | 70 | On track | 0 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
412 | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17772) | SM/17772 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
413 | Solarization of grid connected pumping installation at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17807) | SM/17807 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
414 | Solarization of grid connected pumping installation at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17331) | SM/17331 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
415 | Solarization of grid connected pumping installation at Manoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17813) | SM/17813 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
416 | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10121) | SM/10121 | 2314.83 | 9661 | AUGMENTATION | 70 | Delayed | 71 | 08/02/2022 | 31/03/2025 | 26/06/2025 | 08/12/2021 | 1632.91 | 1632.88
417 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. (SM/10031) | SM/10031 | 1041.15 | 5167 | AUGMENTATION | 70 | Delayed | 76 | 19/01/2022 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 790.43 | 790.43
418 | RADHABALLAV CHAK & ADJOINING MOUZAS (SM/12156) | SM/12156 | 715.87 | 2026 | NEW | 70 | Delayed | 54 | 07/09/2022 | 31/03/2025 | 26/06/2025 | 29/12/2022 | 387.5 | 387.5
419 | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme. (SM/16659) | SM/16659 | 12.39 | 0 | AUGMENTATION | 70 | On track | 85 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 10.53 | 10.53
420 | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme. (SM/16661) | SM/16661 | 12.39 | 0 | AUGMENTATION | 70 | On track | 80 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 9.89 | 9.89
421 | Solarization of grid connected pumping installation at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17379) | SM/17379 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
422 | Solarization of grid connected pumping installation at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17757) | SM/17757 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
423 | Solarization of grid connected pumping installation at Haldia (Ramnagar)PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17770) | SM/17770 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
424 | Solarization of grid connected pumping installation at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17788) | SM/17788 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
425 | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme. (SM/16652) | SM/16652 | 12.39 | 0 | AUGMENTATION | 70 | Delayed | 1 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0.18 | 0.18
426 | Solarization of grid connected pumping installation at Chatra (Sahid Matangini) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17387) | SM/17387 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
427 | Solarization of grid connected pumping installation at Bhagabanpur, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17364) | SM/17364 | 16.61 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
428 | Solarization of grid connected pumping installation at Simulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17748) | SM/17748 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
429 | Solarization of grid connected pumping installation at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17308) | SM/17308 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
430 | PACHAHRI & ADJOINING MOUJAS PWSS (SM/12292) | SM/12292 | 614.09 | 2014 | NEW | 70 | Delayed | 51 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 14/03/2023 | 314.54 | 314.54
431 | Solarization of grid connected pumping installation at Haur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17775) | SM/17775 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
432 | Solarization of grid connected pumping installation at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17784) | SM/17784 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
433 | Solarization of grid connected pumping installation at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17802) | SM/17802 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
434 | Solarization of grid connected pumping installation at Alinan, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17385) | SM/17385 | 16.61 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
435 | Solarization of grid connected pumping installation at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17337) | SM/17337 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
436 | Solarization of grid connected pumping installation at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17318) | SM/17318 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
437 | Solarization of grid connected pumping installation at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17347) | SM/17347 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 15/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
438 | Solarization of grid connected pumping installation at Anantapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17349) | SM/17349 | 16.61 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
439 | Solarization of grid connected pumping installation at Bishnubarh PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17322) | SM/17322 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
440 | KAINARA & IT'S ADJOING MOUJAS (SM/12514) | SM/12514 | 784.6 | 2233 | NEW | 70 | Delayed | 41 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 322.81 | 322.81
441 | Piped Water Supply Scheme for Sankarpur Zone-IV (SM/16305) | SM/16305 | 340.44 | 294 | AUGMENTATION | 70 | On track | 31 | 23/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 106.25 | 106.25
442 | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17771) | SM/17771 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
443 | Solarization of grid connected pumping installation at Purba Bakulda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17774) | SM/17774 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
444 | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17789) | SM/17789 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
445 | Solarization of grid connected pumping installation at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17824) | SM/17824 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
446 | Solarization of grid connected pumping installation at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17315) | SM/17315 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
447 | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS (SM/11881) | SM/11881 | 595.37 | 2526 | NEW | 70 | Delayed | 49 | 17/08/2022 | 31/03/2025 | 26/06/2025 | 20/04/2023 | 293.65 | 293.65
448 | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/12511) | SM/12511 | 524.62 | 1138 | NEW | 70 | Delayed | 25 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 132.54 | 132.54
449 | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11474) | SM/11474 | 997.01 | 6217 | AUGMENTATION | 70 | Delayed | 54 | 14/07/2022 | 31/03/2025 | 26/06/2025 | 03/02/2022 | 539.08 | 539.08
450 | GOURANGA CHAK AND ADJOINING MOUJAS PWSS (SM/13884) | SM/13884 | 589.91 | 1427 | NEW | 70 | Delayed | 36 | 25/11/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 212.7 | 212.7
451 | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. (SM/16660) | SM/16660 | 12.39 | 0 | AUGMENTATION | 70 | On track | 0 | 14/03/2023 | 31/12/2026 | 26/06/2025 | 30/03/2023 | 0 | 0
452 | Solarization of grid connected pumping installation at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17717) | SM/17717 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
453 | Solarization of grid connected pumping installation at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17800) | SM/17800 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
454 | Solarization of grid connected pumping installation at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17372) | SM/17372 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
455 | Solarization of grid connected pumping installation at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17791) | SM/17791 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
456 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda (SM/10344) | SM/10344 | 952 | 3155 | AUGMENTATION | 70 | Delayed | 52 | 16/03/2022 | 31/03/2025 | 26/06/2025 | 14/01/2022 | 492.39 | 492.39
457 | KHAR & IT'S ADJOINING MOUJAS PWSS (SM/13743) | SM/13743 | 987.25 | 2849 | NEW | 70 | Delayed | 5 | 17/11/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 49.04 | 49.04
458 | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. (SM/16669) | SM/16669 | 12.39 | 0 | AUGMENTATION | 70 | Delayed | 2 | 14/03/2023 | 31/12/2025 | 26/06/2025 | 28/04/2023 | 0.26 | 0.26
459 | Solarization of grid connected pumping installation at Kapaseria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17769) | SM/17769 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 17/03/2023 | 31/12/2026 | 26/06/2025 | 29/03/2023 | 0 | 0
460 | Solarization of grid connected pumping installation at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17786) | SM/17786 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
461 | Solarization of grid connected pumping installation at Gobindanagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17801) | SM/17801 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
462 | Solarization of grid connected pumping installation at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17804) | SM/17804 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
463 | Solarization of grid connected pumping installation at Uttardalhara Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17809) | SM/17809 | 16.61 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
464 | Solarization of grid connected pumping installation at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17323) | SM/17323 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 15/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
465 | Solarization of grid connected pumping installation at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17726) | SM/17726 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
466 | Solarization of grid connected pumping installation at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17329) | SM/17329 | 8.3 | 0 | SOLARISATION | 70 | On track | 0 | 15/03/2023 | 31/12/2026 | 26/06/2025 | 23/03/2023 | 0 | 0
467 | Solarization of grid connected pumping installation at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17352) | SM/17352 | 33.22 | 0 | SOLARISATION | 70 | Delayed | 0 | 15/03/2023 | 31/12/2025 | 26/06/2025 | 23/03/2023 | 0 | 0
468 | Solarization of grid connected pumping installation at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17817) | SM/17817 | 8.3 | 0 | SOLARISATION | 70 | Delayed | 0 | 17/03/2023 | 31/12/2025 | 26/06/2025 | 29/03/2023 | 0 | 0
469 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme (SM/09448) | SM/09448 | 802.36 | 4327 | AUGMENTATION | 73 | Delayed | 91 | 19/11/2021 | 31/12/2025 | 26/06/2025 | 18/01/2022 | 733.75 | 733.73
470 | Augmentation of Madhakhali piped water supply scheme. (SM/09920) | SM/09920 | 2333.22 | 7098 | AUGMENTATION | 74 | Delayed | 64 | 10/12/2021 | 31/03/2025 | 26/06/2025 | 31/01/2022 | 1483.62 | 1483.62
471 | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11862) | SM/11862 | 69.86 | 0 | AUGMENTATION | 74 | Delayed | 87 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 18/08/2022 | 60.6 | 60.6
472 | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09272) | SM/09272 | 366.83 | 2201 | AUGMENTATION | 75 | Delayed | 90 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 25/01/2022 | 331.54 | 331.54
473 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme (SM/10122) | SM/10122 | 1492.39 | 6387 | AUGMENTATION | 75 | Delayed | 74 | 08/02/2022 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 1110.85 | 1110.85
474 | FATEPUR AND ADJOINING MOUJAS PWSS (SM/13687) | SM/13687 | 231 | 377 | NEW | 75 | On track | 38 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 20/04/2023 | 88.39 | 88.39
475 | GOJINA AND IT'S ADJOINING MOUJAS PWSS (SM/12812) | SM/12812 | 766.35 | 2437 | NEW | 75 | On track | 51 | 20/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 391.01 | 391.01
476 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. (SM/09338) | SM/09338 | 685.69 | 3736 | AUGMENTATION | 75 | Delayed | 55 | 12/11/2021 | 30/06/2025 | 26/06/2025 | 02/12/2021 | 378.83 | 378.83
477 | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji (SM/09447) | SM/09447 | 663.05 | 2940 | AUGMENTATION | 75 | Delayed | 48 | 19/11/2021 | 31/03/2025 | 26/06/2025 | 14/01/2022 | 320.98 | 320.98
478 | GOBRADAN & ADJOINING MOUZAS (SM/12161) | SM/12161 | 569.73 | 1420 | NEW | 75 | On track | 52 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 20/03/2023 | 297.85 | 297.85
479 | BASUDEVBERYA AND ADJOINING MOUJAS PWSS (SM/12297) | SM/12297 | 541.09 | 1064 | NEW | 75 | On track | 37 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 10/03/2023 | 202.85 | 202.85
480 | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. (SM/12300) | SM/12300 | 94.16 | 1841 | RETROFITTING | 75 | On track | 73 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 26/09/2022 | 69.04 | 69.04
481 | GOKULNAGAR AND ADJOINING MOUJAS (SM/12165) | SM/12165 | 821.18 | 2421 | NEW | 75 | On track | 50 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 407.64 | 407.64
482 | KHARUI AND ADJOINING MOUZAS PWSS (SM/11945) | SM/11945 | 637.14 | 2574 | NEW | 75 | On track | 40 | 24/08/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 253.99 | 253.99
483 | BAGMARI AND IT'S ADJOINING MOUJAS PWSS (SM/12429) | SM/12429 | 560.42 | 1230 | NEW | 75 | On track | 60 | 13/09/2022 | 31/03/2026 | 26/06/2025 | 04/05/2023 | 338.01 | 338.01
484 | AJAYA & ADJOINING MOUJAS PWSS (SM/12174) | SM/12174 | 817.13 | 3771 | NEW | 75 | On track | 62 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 17/07/2023 | 504.13 | 504.13
485 | URDDHABMAL AND ADJOINING MOUJAS PWSS (SM/13698) | SM/13698 | 803.45 | 1797 | NEW | 78 | On track | 40 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 319.51 | 319.51
486 | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (SM/10684) | SM/10684 | 1309.53 | 8284 | AUGMENTATION | 78 | On track | 89 | 06/05/2022 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 1162.7 | 1162.7
487 | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09444) | SM/09444 | 726.52 | 2915 | AUGMENTATION | 78 | On track | 64 | 19/11/2021 | 31/03/2026 | 26/06/2025 | 17/02/2022 | 465.58 | 463.76
488 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK (SM/08746) | SM/08746 | 98.91 | 1575 | RETROFITTING | 79 | Delayed | 97 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 95.93 | 95.93
489 | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me (SM/16452) | SM/16452 | 110.15 | 610 | RETROFITTING | 79 | On track | 72 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 79.22 | 79.22
490 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II (SM/12490) | SM/12490 | 662.45 | 2244 | AUGMENTATION | 80 | On track | 57 | 13/09/2022 | 31/03/2026 | 26/06/2025 | 08/02/2022 | 374.34 | 374.34
491 | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. (SM/12318) | SM/12318 | 727.81 | 1929 | NEW | 80 | On track | 48 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 31/12/2022 | 347.66 | 347.66
492 | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. (SM/09977) | SM/09977 | 1187.36 | 7229 | AUGMENTATION | 80 | On track | 60 | 17/12/2021 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 715.28 | 714.52
493 | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS (SM/12142) | SM/12142 | 722.2 | 1730 | NEW | 80 | On track | 43 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 10/04/2023 | 312.55 | 312.55
494 | PADIMA AND ADJOINING MOUJAS PWSS (SM/12430) | SM/12430 | 460.25 | 960 | NEW | 80 | On track | 58 | 13/09/2022 | 07/11/2025 | 26/06/2025 | 20/03/2023 | 266.36 | 266.36
495 | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block (SM/10432) | SM/10432 | 126.97 | 2488 | RETROFITTING | 80 | Delayed | 0 | 12/04/2022 | 31/12/2025 | 26/06/2025 | 25/04/2022 | 0 | 0
496 | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. (SM/12301) | SM/12301 | 112.8 | 2244 | RETROFITTING | 80 | On track | 61 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 26/09/2022 | 68.76 | 68.76
497 | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS (SM/15848) | SM/15848 | 241.71 | 227 | NEW | 80 | On track | 29 | 20/02/2023 | 31/03/2026 | 26/06/2025 | 25/04/2023 | 69.59 | 69.59
498 | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) (SM/09056) | SM/09056 | 88.01 | 1600 | RETROFITTING | 80 | Delayed | 97 | 29/10/2021 | 31/12/2025 | 26/06/2025 | 02/11/2021 | 85.36 | 85.36
499 | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. (SM/09804) | SM/09804 | 166.66 | 2783 | RETROFITTING | 80 | Delayed | 69 | 01/12/2021 | 31/03/2025 | 26/06/2025 | 19/01/2022 | 115.23 | 115.23
500 | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10593) | SM/10593 | 995.98 | 4937 | AUGMENTATION | 80 | On track | 76 | 18/04/2022 | 31/12/2025 | 26/06/2025 | 21/01/2022 | 758.35 | 758.35
501 | BAKCHA AND ADJOINING MOUJAS PWSS (SM/12146) | SM/12146 | 623.54 | 2046 | NEW | 80 | On track | 55 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 29/12/2022 | 343.4 | 343.4
502 | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda (SM/09445) | SM/09445 | 822.22 | 3171 | AUGMENTATION | 80 | On track | 68 | 19/11/2021 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 560.08 | 560.08
503 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme (SM/09284) | SM/09284 | 739.47 | 2879 | AUGMENTATION | 80 | Delayed | 90 | 03/11/2021 | 31/03/2025 | 26/06/2025 | 01/12/2021 | 662.67 | 662.67
504 | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12428) | SM/12428 | 412.24 | 618 | NEW | 80 | Delayed | 51 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 209.28 | 209.28
505 | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09914) | SM/09914 | 1060.63 | 4407 | AUGMENTATION | 80 | On track | 80 | 10/12/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 843.6 | 843.6
506 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti (SM/10126) | SM/10126 | 1145.17 | 3753 | AUGMENTATION | 81 | On track | 57 | 08/02/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 655.27 | 655.27
507 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) (SM/11616) | SM/11616 | 838.08 | 0 | AUGMENTATION | 82 | On track | 85 | 26/07/2022 | 31/12/2025 | 26/06/2025 | 02/11/2022 | 711.24 | 711.24
508 | RAMCHANDRAPUR AND ADJOINING MOUJAS (SM/12147) | SM/12147 | 656.72 | 2232 | NEW | 85 | On track | 56 | 07/09/2022 | 31/03/2026 | 26/06/2025 | 11/05/2023 | 370.4 | 370.4
509 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS (SM/12140) | SM/12140 | 582.1 | 2038 | NEW | 85 | On track | 62 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 17/04/2023 | 358.01 | 358.01
510 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) (SM/11618) | SM/11618 | 806.74 | 6291 | AUGMENTATION | 85 | On track | 98 | 26/07/2022 | 31/12/2025 | 26/06/2025 | 02/11/2022 | 788.49 | 788.49
511 | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani (SM/10127) | SM/10127 | 1418.64 | 5256 | AUGMENTATION | 85 | On track | 58 | 08/02/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 821.33 | 819.84
512 | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. (SM/10396) | SM/10396 | 1547.92 | 7163 | AUGMENTATION | 85 | On track | 69 | 29/03/2022 | 31/03/2026 | 26/06/2025 | 19/01/2022 | 1071.3 | 1071.3
513 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II (SM/12488) | SM/12488 | 740.92 | 2338 | AUGMENTATION | 85 | On track | 53 | 13/09/2022 | 31/12/2025 | 26/06/2025 | 21/06/2022 | 390.43 | 390.43
514 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut (SM/10323) | SM/10323 | 1166.79 | 3895 | AUGMENTATION | 86 | On track | 62 | 07/03/2022 | 31/12/2025 | 26/06/2025 | 14/01/2022 | 718.04 | 715.07
515 | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai (SM/09446) | SM/09446 | 710.98 | 2679 | AUGMENTATION | 87 | On track | 60 | 19/11/2021 | 31/12/2026 | 26/06/2025 | 06/08/2021 | 423.41 | 423.41
516 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur (SM/10342) | SM/10342 | 800.14 | 2162 | AUGMENTATION | 89 | Delayed | 51 | 14/03/2022 | 31/03/2025 | 26/06/2025 | 14/01/2022 | 406.29 | 406.29
517 | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) (SM/09286) | SM/09286 | 764.17 | 4335 | AUGMENTATION | 90 | On track | 87 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 661.86 | 661.27
518 | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11861) | SM/11861 | 43.42 | 0 | AUGMENTATION | 90 | On track | 65 | 17/08/2022 | 31/12/2025 | 26/06/2025 | 18/08/2022 | 28.25 | 28.25
519 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11984) | SM/11984 | 1454.18 | 7156 | AUGMENTATION | 90 | Delayed | 83 | 01/09/2022 | 31/03/2025 | 26/06/2025 | 03/01/2022 | 1206.8 | 1206.8
520 | BADALPUR AND IT'S ADJOINING MOUJAS (SM/13887) | SM/13887 | 381.66 | 635 | NEW | 90 | Delayed | 72 | 25/11/2022 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 274.31 | 274.31
521 | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. (SM/09281) | SM/09281 | 681.09 | 2920 | AUGMENTATION | 90 | Delayed | 88 | 03/11/2021 | 31/03/2025 | 26/06/2025 | 01/12/2021 | 597.79 | 597.79
522 | Augmentation of Ramnagar (Zone-II) PWSS (SM/12486) | SM/12486 | 889.59 | 2941 | AUGMENTATION | 90 | Delayed | 36 | 13/09/2022 | 31/03/2025 | 26/06/2025 | 19/01/2023 | 319.26 | 319.26
523 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11469) | SM/11469 | 570.27 | 2587 | AUGMENTATION | 90 | On track | 64 | 14/07/2022 | 31/03/2026 | 26/06/2025 | 06/01/2022 | 363.48 | 363.48
524 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara (SM/09288) | SM/09288 | 850.34 | 3398 | AUGMENTATION | 90 | Delayed | 66 | 03/11/2021 | 31/03/2025 | 26/06/2025 | 01/12/2021 | 559.76 | 559.76
525 | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. (SM/12302) | SM/12302 | 45.03 | 763 | RETROFITTING | 90 | On track | 94 | 09/09/2022 | 31/12/2025 | 26/06/2025 | 19/12/2022 | 42.38 | 42.38
526 | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS (SM/12286) | SM/12286 | 776 | 2130 | NEW | 90 | Delayed | 51 | 09/09/2022 | 31/03/2025 | 26/06/2025 | 12/05/2023 | 393.68 | 393.68
527 | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS (SM/14456) | SM/14456 | 351.84 | 672 | NEW | 90 | Delayed | 63 | 20/01/2023 | 31/03/2025 | 26/06/2025 | 20/03/2023 | 220.73 | 220.73
528 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. (SM/09285) | SM/09285 | 932.77 | 4622 | AUGMENTATION | 90 | On track | 83 | 03/11/2021 | 31/03/2026 | 26/06/2025 | 01/11/2021 | 773.92 | 773.92
529 | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. (SM/12177) | SM/12177 | 154.98 | 2657 | RETROFITTING | 90 | On track | 52 | 07/09/2022 | 31/12/2025 | 26/06/2025 | 01/11/2022 | 81.24 | 81.24
530 | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. (SM/08759) | SM/08759 | 471.12 | 1600 | RETROFITTING | 90 | On track | 83 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 11/01/2022 | 392.24 | 392.24
531 | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. (SM/10431) | SM/10431 | 106.97 | 1718 | RETROFITTING | 92 | On track | 97 | 12/04/2022 | 31/03/2026 | 26/06/2025 | 31/03/2022 | 103.86 | 103.86
532 | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. (SM/08698) | SM/08698 | 746.17 | 0 | NEW | 95 | Delayed | 84 | 01/09/2021 | 31/03/2025 | 26/06/2025 | 28/12/2021 | 628.1 | 628.1
533 | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya (SM/09034) | SM/09034 | 829.85 | 3041 | AUGMENTATION | 95 | On track | 64 | 30/10/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 527.31 | 527.31
534 | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. (SM/09800) | SM/09800 | 149.22 | 2550 | RETROFITTING | 95 | On track | 71 | 01/12/2021 | 31/03/2025 | 26/06/2025 | 19/01/2022 | 106.19 | 106.19
535 | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. (SM/09802) | SM/09802 | 164.09 | 2753 | RETROFITTING | 95 | On track | 55 | 01/12/2021 | 31/12/2025 | 26/06/2025 | 19/01/2022 | 90.9 | 90.9
536 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) (SM/16468) | SM/16468 | 34.18 | 545 | RETROFITTING | 95 | On track | 89 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 30.37 | 30.37
537 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK (SM/08753) | SM/08753 | 100.13 | 1950 | RETROFITTING | 95 | On track | 97 | 09/09/2021 | 31/03/2025 | 26/06/2025 | 10/09/2021 | 97.49 | 97.49
538 | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. (SM/07659) | SM/07659 | 228.34 | 4683 | RETROFITTING | 95 | On track | 98 | 07/01/2021 | 30/09/2025 | 26/06/2025 | 08/02/2021 | 222.75 | 222.75
539 | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S (SM/09073) | SM/09073 | 21.74 | 300 | RETROFITTING | 95 | On track | 94 | 28/10/2021 | 31/03/2025 | 26/06/2025 | 22/11/2021 | 20.5 | 18.98
540 | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) (SM/10125) | SM/10125 | 2077.89 | 9676 | AUGMENTATION | 95 | Delayed | 68 | 08/02/2022 | 31/03/2025 | 26/06/2025 | 05/02/2021 | 1410.88 | 1410.88
541 | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/12279) | SM/12279 | 1684.91 | 4912 | AUGMENTATION | 95 | Delayed | 73 | 09/09/2022 | 31/03/2025 | 26/06/2025 | 09/12/2022 | 1234.76 | 1234.76
542 | KATARI AND ADJOINING MOUJAS PWSS (SM/12815) | SM/12815 | 416.52 | 767 | NEW | 95 | On track | 45 | 20/09/2022 | 31/12/2025 | 26/06/2025 | 20/03/2023 | 189.47 | 189.47
543 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA (SM/16470) | SM/16470 | 59.08 | 851 | RETROFITTING | 95 | On track | 86 | 03/03/2023 | 31/12/2025 | 26/06/2025 | 19/04/2023 | 51.09 | 51.09
544 | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. (SM/10346) | SM/10346 | 26.17 | 410 | RETROFITTING | 95 | On track | 73 | 16/03/2022 | 30/09/2025 | 26/06/2025 | 08/03/2022 | 19.06 | 19.06
545 | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16206) | SM/16206 | 74.78 | 0 | AUGMENTATION | 95 | On track | 63 | 24/02/2023 | 31/12/2025 | 26/06/2025 | 25/04/2023 | 47.33 | 47.33
546 | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. (SM/07653) | SM/07653 | 116.61 | 2382 | RETROFITTING | 95 | On track | 98 | 07/01/2021 | 31/03/2025 | 26/06/2025 | 05/02/2021 | 114.56 | 114.36
547 | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. (SM/09275) | SM/09275 | 478.65 | 1878 | AUGMENTATION | 95 | On track | 94 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 449.54 | 449.54
548 | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. (SM/10393) | SM/10393 | 787.03 | 2729 | AUGMENTATION | 95 | Delayed | 70 | 29/03/2022 | 31/03/2025 | 26/06/2025 | 06/01/2022 | 550.65 | 550.65
549 | SAR BERYA AND ADJOINING MOUJAS PWSS (SM/13688) | SM/13688 | 479.68 | 875 | NEW | 95 | On track | 53 | 14/11/2022 | 31/12/2025 | 26/06/2025 | 28/02/2023 | 255.89 | 255.89
550 | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09277) | SM/09277 | 315.94 | 1586 | AUGMENTATION | 95 | On track | 83 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 262.85 | 262.85
551 | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09279) | SM/09279 | 366.62 | 2139 | AUGMENTATION | 95 | On track | 95 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 349.09 | 349.09
552 | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. (SM/09280) | SM/09280 | 445.45 | 2013 | AUGMENTATION | 96 | On track | 52 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 231.26 | 231.26
553 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. (SM/09801) | SM/09801 | 160.98 | 2862 | RETROFITTING | 98 | On track | 90 | 01/12/2021 | 31/12/2025 | 26/06/2025 | 21/03/2022 | 144.09 | 144.09
554 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai (SM/09287) | SM/09287 | 349.47 | 986 | AUGMENTATION | 98 | On track | 79 | 03/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 275.14 | 275.06
555 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) (SM/10647) | SM/10647 | 539.62 | 5157 | AUGMENTATION | 98 | On track | 98 | 22/04/2022 | 31/12/2025 | 26/06/2025 | 07/01/2022 | 527.18 | 527.18
556 | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme (SM/08232) | SM/08232 | 102.22 | 1375 | RETROFITTING | 98 | On track | 95 | 09/02/2021 | 31/12/2025 | 26/06/2025 | 25/02/2021 | 97.26 | 97.26
557 | Retorfitting to accommodate FHTC under JJM in Dulalpur PWSS. (SM/09057) | SM/09057 | 59.18 | 1166 | RETROFITTING | 98 | On track | 97 | 29/10/2021 | 31/03/2025 | 26/06/2025 | 02/11/2021 | 57.41 | 57.41
558 | Augmentation of Ground Water Based Piped Supply Scheme for Majna (SM/09335) | SM/09335 | 556.85 | 2501 | AUGMENTATION | 98 | On track | 67 | 12/11/2021 | 31/12/2025 | 26/06/2025 | 01/12/2021 | 370.87 | 370.87
559 | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. (SM/09334) | SM/09334 | 704.29 | 2536 | AUGMENTATION | 98 | On track | 66 | 12/11/2021 | 31/12/2025 | 26/06/2025 | 02/12/2021 | 465.05 | 465.05
560 | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block (SM/07478) | SM/07478 | 46.94 | 937 | RETROFITTING | 99 | On track | 96 | 29/12/2020 | 31/12/2025 | 26/06/2025 | 04/02/2021 | 45.25 | 45.25
561 | Shyampur Piped Water Supply Scheme. (SM/08878) | SM/08878 | 800.17 | 2571 | NEW | 99 | On track | 75 | 24/09/2021 | 31/03/2025 | 26/06/2025 | 17/11/2021 | 602.16 | 602.16
562 | Baharampur Piped Water Supply Scheme. (SM/08879) | SM/08879 | 688.64 | 2296 | NEW | 99 | On track | 82 | 24/09/2021 | 31/03/2025 | 26/06/2025 | 31/01/2022 | 561.38 | 561.38
563 | Narikeldaha Piped Water Supply Scheme. (SM/09342) | SM/09342 | 848.91 | 2272 | NEW | 99 | On track | 89 | 12/11/2021 | 31/03/2025 | 26/06/2025 | 30/11/2021 | 754.94 | 754.94
564 | Balance Work for Retrofitting to Accommodate FHTC (152 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of different nodal point of Dona Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk (SM/09443) | SM/09443 | 48.34 | 152 | RETROFITTING | 99 | On track | 98 | 19/11/2021 | 31/12/2025 | 26/06/2025 | 13/12/2021 | 47.35 | 45.8
565 | Retrofitting to accommodate FHTC under JJM in Uttar Charikhia PWSS under Contai I Block (Phase-II). (SM/09047) | SM/09047 | 17.78 | 180 | RETROFITTING | 99 | On track | 97 | 29/10/2021 | 31/12/2025 | 26/06/2025 | 02/11/2021 | 17.26 | 17.26
566 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. (SM/08756) | SM/08756 | 42.75 | 899 | RETROFITTING | 99 | On track | 97 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 41.31 | 41.31
567 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. (SM/08755) | SM/08755 | 91.37 | 1897 | RETROFITTING | 99 | On track | 100 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 90.94 | 90.94
568 | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme (SM/07098) | SM/07098 | 99.86 | 2000 | RETROFITTING | 100 | 100% Physical | 80 | 26/11/2020 | 31/03/2025 | 26/06/2025 | 22/02/2021 | 80 | 63.71
569 | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme (SM/06884) | SM/06884 | 37.82 | 745 | RETROFITTING | 100 | 100% Physical | 98 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 37 | 35.43
570 | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme (SM/06886) | SM/06886 | 99.67 | 2020 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 96.5 | 96.26
571 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XIII (SM/07118) | SM/07118 | 99.86 | 1985 | RETROFITTING | 100 | 100% Physical | 98 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 05/01/2021 | 98.11 | 97.89
572 | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur (SM/07661) | SM/07661 | 201.91 | 4231 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 30/09/2025 | 26/06/2025 | 05/02/2021 | 196.51 | 196.51
573 | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS (SM/06890) | SM/06890 | 90.86 | 1842 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 90 | 88.17
574 | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di (SM/09356) | SM/09356 | 68.86 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 19/07/2021 | 0 | 0
575 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. (SM/08757) | SM/08757 | 25.02 | 548 | RETROFITTING | 100 | 100% Physical | 96 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 24 | 24
576 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II (SM/08758) | SM/08758 | 17.38 | 220 | RETROFITTING | 100 | 100% Physical | 90 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 15.68 | 15.68
577 | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) (SM/09054) | SM/09054 | 50.27 | 400 | RETROFITTING | 100 | 100% Physical | 99 | 29/10/2021 | 28/02/2025 | 26/06/2025 | 02/11/2021 | 50 | 46.55
578 | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) (SM/09340) | SM/09340 | 449.59 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 18/01/2021 | 0 | 0
579 | Retrofitting to Accommodate FHTC (Balance Work) (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-V, Bloc (SM/10437) | SM/10437 | 19.89 | 200 | RETROFITTING | 100 | 100% Physical | 81 | 12/04/2022 | 30/09/2025 | 26/06/2025 | 05/04/2022 | 16.09 | 16.09
580 | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. (SM/09803) | SM/09803 | 120.85 | 2633 | RETROFITTING | 100 | 100% Physical | 87 | 01/12/2021 | 31/03/2025 | 26/06/2025 | 19/01/2022 | 105 | 104.47
581 | Retrofitting to accomodate FHTC under JJM in Saripur PWSS (SM/06889) | SM/06889 | 57.01 | 1114 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 57 | 57
582 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli (SM/09912) | SM/09912 | 1029.45 | 3862 | AUGMENTATION | 100 | 100% Physical | 70 | 10/12/2021 | 31/03/2025 | 26/06/2025 | 02/12/2021 | 718.16 | 718.16
583 | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme (SM/07096) | SM/07096 | 34.92 | 717 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 21/01/2021 | 34 | 33.44
584 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII (SM/07116) | SM/07116 | 99.8 | 1945 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 28/01/2021 | 96.73 | 96.73
585 | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur (SM/07660) | SM/07660 | 169.11 | 3545 | RETROFITTING | 100 | 100% Physical | 98 | 07/01/2021 | 28/02/2025 | 26/06/2025 | 25/02/2021 | 165.63 | 164.82
586 | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme (SM/06891) | SM/06891 | 83.27 | 1698 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 83 | 82.64
587 | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. (SM/06651) | SM/06651 | 28.92 | 74 | NEW | 100 | 100% Physical | 97 | 12/02/2020 | 25/02/2025 | 26/06/2025 |  | 28.06 | 28.06
588 | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. (SM/07477) | SM/07477 | 45.95 | 904 | RETROFITTING | 100 | 100% Physical | 93 | 29/12/2020 | 31/03/2026 | 26/06/2025 | 10/02/2021 | 42.75 | 42.75
589 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) (SM/07480) | SM/07480 | 87.9 | 1724 | RETROFITTING | 100 | 100% Physical | 99 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 27/01/2021 | 87.01 | 86.89
590 | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. (SM/07483) | SM/07483 | 76.83 | 1571 | RETROFITTING | 100 | 100% Physical | 96 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 27/01/2021 | 73.99 | 73.99
591 | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. (SM/08754) | SM/08754 | 60.34 | 1100 | RETROFITTING | 100 | 100% Physical | 94 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 56.73 | 56.73
592 | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) (SM/08225) | SM/08225 | 27.04 | 300 | RETROFITTING | 100 | 100% Physical | 87 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 23.49 | 23.49
593 | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. (SM/09074) | SM/09074 | 61.29 | 335 | RETROFITTING | 100 | 100% Physical | 47 | 28/10/2021 | 28/02/2025 | 26/06/2025 | 22/11/2021 | 28.56 | 28.56
594 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X (SM/07117) | SM/07117 | 99.53 | 1905 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 23/12/2020 | 97 | 96.92
595 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VIA (SM/07111) | SM/07111 | 54.94 | 1159 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 11/05/2021 | 53 | 51.1
596 | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme (SM/07094) | SM/07094 | 99.43 | 2010 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 09/02/2021 | 96.38 | 96.38
597 | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme (SM/07100) | SM/07100 | 90.02 | 1800 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 31/03/2025 | 26/06/2025 | 05/01/2021 | 89.5 | 88.18
598 | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme (SM/06878) | SM/06878 | 77.32 | 1574 | RETROFITTING | 100 | 100% Physical | 96 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 73.99 | 73.96
599 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II (SM/07114) | SM/07114 | 99.94 | 1905 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 05/01/2021 | 96 | 96
600 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme (SM/07119) | SM/07119 | 78.45 | 1517 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 23/12/2020 | 77.77 | 77.76
601 | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur (SM/07657) | SM/07657 | 177.82 | 3634 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 172.13 | 169.2
602 | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme (SM/07108) | SM/07108 | 97.82 | 1900 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 05/01/2021 | 96.59 | 93.09
603 | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme (SM/07109) | SM/07109 | 99.52 | 2024 | RETROFITTING | 100 | 100% Physical | 100 | 26/11/2020 | 31/03/2025 | 26/06/2025 | 05/01/2021 | 99.52 | 99.19
604 | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. (SM/09354) | SM/09354 | 199.18 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 26/03/2021 | 0 | 0
605 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II (SM/08745) | SM/08745 | 104.08 | 670 | RETROFITTING | 100 | 100% Physical | 100 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 104 | 101.34
606 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK (SM/08750) | SM/08750 | 99.92 | 1500 | RETROFITTING | 100 | 100% Physical | 96 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 96.12 | 96.12
607 | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). (SM/09048) | SM/09048 | 37.06 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 28/02/2025 | 26/06/2025 | 02/11/2021 | 35.66 | 35.66
608 | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) (SM/09339) | SM/09339 | 125.52 | 314 | RETROFITTING | 100 | 100% Physical | 98 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 11/06/2019 | 122.89 | 122.73
609 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII (SM/08790) | SM/08790 | 353.17 | 7511 | RETROFITTING | 100 | 100% Physical | 97 | 13/09/2021 | 30/09/2025 | 26/06/2025 | 15/09/2021 | 342.75 | 342.75
610 | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme (SM/06888) | SM/06888 | 93.57 | 1955 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 93 | 90.78
611 | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme (SM/06879) | SM/06879 | 38.01 | 745 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 18/12/2020 | 37.66 | 37.66
612 | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur (SM/07656) | SM/07656 | 164.81 | 3451 | RETROFITTING | 100 | 100% Physical | 92 | 07/01/2021 | 31/03/2025 | 26/06/2025 | 08/02/2021 | 152.25 | 152.11
613 | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block (SM/07658) | SM/07658 | 178.36 | 3662 | RETROFITTING | 100 | 100% Physical | 93 | 07/01/2021 | 31/12/2025 | 26/06/2025 | 05/02/2021 | 165.43 | 165.25
614 | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme (SM/07106) | SM/07106 | 99.2 | 2000 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 11/01/2021 | 95.92 | 95.87
615 | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. (SM/07481) | SM/07481 | 26.99 | 550 | RETROFITTING | 100 | 100% Physical | 29 | 29/12/2020 | 31/03/2025 | 26/06/2025 | 18/12/2020 | 7.75 | 7.75
616 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. (SM/07485) | SM/07485 | 99.81 | 2050 | RETROFITTING | 100 | 100% Physical | 100 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 05/02/2021 | 99.72 | 98.39
617 | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. (SM/09355) | SM/09355 | 123.45 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 26/03/2021 | 0 | 0
618 | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) (SM/08229) | SM/08229 | 31.23 | 206 | RETROFITTING | 100 | 100% Physical | 97 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 01/09/2023 | 30.18 | 30.18
619 | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block (SM/09052) | SM/09052 | 76.42 | 76 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/12/2025 | 26/06/2025 | 02/11/2021 | 74 | 74
620 | Balance work for Retrofitting to accommodate FHTC (907 Nos.) and laying of laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for (SM/09058) | SM/09058 | 130.31 | 907 | RETROFITTING | 100 | 100% Physical | 89 | 29/10/2021 | 30/09/2025 | 26/06/2025 | 08/11/2021 | 115.86 | 115.86
621 | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, (SM/10434) | SM/10434 | 82 | 200 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 30/09/2025 | 26/06/2025 | 05/04/2022 | 79.61 | 79.61
622 | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme (SM/07101) | SM/07101 | 58.04 | 1167 | RETROFITTING | 100 | 100% Physical | 91 | 26/11/2020 | 31/03/2025 | 26/06/2025 | 28/01/2021 | 53 | 52.6
623 | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme (SM/07095) | SM/07095 | 88.28 | 1850 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 21/01/2021 | 86 | 56.88
624 | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) (SM/09055) | SM/09055 | 71.42 | 160 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 31/12/2025 | 26/06/2025 | 02/11/2021 | 67.37 | 67.16
625 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme (SM/07120) | SM/07120 | 79 | 1561 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 05/01/2021 | 76.78 | 76.68
626 | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme (SM/06887) | SM/06887 | 99.71 | 1995 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 99 | 96.73
627 | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme (SM/06892) | SM/06892 | 90.8 | 1791 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 90 | 86.96
628 | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme (SM/07107) | SM/07107 | 62.75 | 1258 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 20/01/2021 | 61 | 60.84
629 | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme (SM/07110) | SM/07110 | 72.71 | 1500 | RETROFITTING | 100 | 100% Physical | 76 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 14/01/2021 | 55 | 47.29
630 | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block (SM/07652) | SM/07652 | 129.4 | 2629 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 28/02/2025 | 26/06/2025 | 04/02/2021 | 126.08 | 125.97
631 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II (SM/08748) | SM/08748 | 60.25 | 700 | RETROFITTING | 100 | 100% Physical | 93 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 56.29 | 56.26
632 | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I (SM/08223) | SM/08223 | 203.44 | 2832 | RETROFITTING | 100 | 100% Physical | 97 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 25/02/2021 | 197.96 | 197.96
633 | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) (SM/08228) | SM/08228 | 37.55 | 310 | RETROFITTING | 100 | 100% Physical | 92 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 34.68 | 34.68
634 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone I (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-I) (SM/09050) | SM/09050 | 61.99 | 1100 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 30/09/2025 | 26/06/2025 | 02/11/2021 | 59.87 | 59.87
635 | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. (SM/10345) | SM/10345 | 43.75 | 13 | RETROFITTING | 100 | 100% Physical | 8 | 16/03/2022 | 28/02/2025 | 26/06/2025 | 08/03/2022 | 3.52 | 3.52
636 | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl (SM/10436) | SM/10436 | 99.32 | 862 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 30/09/2025 | 26/06/2025 | 21/06/2022 | 96.36 | 96.36
637 | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- (SM/08985) | SM/08985 | 119.8 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 | 28/02/2025 | 26/06/2025 | 01/06/2021 | 0 | 0
638 | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block (SM/08233) | SM/08233 | 216.57 | 2466 | RETROFITTING | 100 | 100% Physical | 80 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 25/02/2021 | 172.89 | 172.89
639 | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme (SM/06883) | SM/06883 | 99.43 | 2000 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 96.5 | 95.63
640 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II (SM/08752) | SM/08752 | 145.47 | 1000 | RETROFITTING | 100 | 100% Physical | 99 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 143.66 | 143.26
641 | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme (SM/06881) | SM/06881 | 99.51 | 1960 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 96.5 | 95.79
642 | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme (SM/07093) | SM/07093 | 73.12 | 1511 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 01/02/2021 | 71 | 70.61
643 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme (SM/07097) | SM/07097 | 99.87 | 1890 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 28/01/2021 | 99.1 | 99.1
644 | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme (SM/06880) | SM/06880 | 81.66 | 1656 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 79 | 76.77
645 | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme (SM/06882) | SM/06882 | 99.43 | 1950 | RETROFITTING | 100 | 100% Physical | 98 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 97 | 97
646 | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme (SM/06885) | SM/06885 | 99.63 | 1966 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 96.5 | 87.27
647 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IXA (SM/07113) | SM/07113 | 99.88 | 2091 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 05/01/2021 | 96.71 | 96.7
648 | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. (SM/07655) | SM/07655 | 114.11 | 2288 | RETROFITTING | 100 | 100% Physical | 55 | 07/01/2021 | 28/02/2025 | 26/06/2025 | 04/02/2021 | 62.66 | 62.21
649 | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d (SM/09357) | SM/09357 | 223.89 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 28/02/2025 | 26/06/2025 | 26/03/2021 | 0 | 0
650 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II (SM/08751) | SM/08751 | 45.72 | 400 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/12/2025 | 26/06/2025 | 10/09/2021 | 44.38 | 44.38
651 | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) (SM/08224) | SM/08224 | 98.97 | 680 | RETROFITTING | 100 | 100% Physical | 88 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 11/05/2021 | 87.23 | 86.69
652 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone X (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-III) (SM/09051) | SM/09051 | 93.24 | 1600 | RETROFITTING | 100 | 100% Physical | 90 | 29/10/2021 | 30/09/2025 | 26/06/2025 | 08/11/2021 | 84.01 | 84.01
653 | Retrofitting to Accommodate FHTC (Balance Work) (579 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-IV, Blo (SM/10435) | SM/10435 | 94.29 | 579 | RETROFITTING | 100 | 100% Physical | 69 | 12/04/2022 | 30/09/2025 | 26/06/2025 | 05/04/2022 | 65.2 | 65.2
654 | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme (SM/06877) | SM/06877 | 99.46 | 2030 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 96.5 | 87.65
655 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX (SM/07112) | SM/07112 | 56.55 | 1196 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 11/01/2021 | 54.91 | 54.91
656 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI (SM/07115) | SM/07115 | 99.73 | 1985 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 05/01/2021 | 97.14 | 97.13
657 | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme (SM/06893) | SM/06893 | 75.12 | 1551 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 28/02/2025 | 26/06/2025 | 05/11/2020 | 75 | 72.23
658 | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) (SM/08230) | SM/08230 | 11.32 | 150 | RETROFITTING | 100 | 100% Physical | 94 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 10.63 | 10.63
659 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) (SM/08231) | SM/08231 | 176.93 | 1389 | RETROFITTING | 100 | 100% Physical | 99 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 23/06/2021 | 175.93 | 175.93
660 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II (SM/08747) | SM/08747 | 23.05 | 250 | RETROFITTING | 100 | 100% Physical | 92 | 09/09/2021 | 31/03/2025 | 26/06/2025 | 10/09/2021 | 21.15 | 21.15
661 | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) (SM/08222) | SM/08222 | 92.76 | 1215 | RETROFITTING | 100 | 100% Physical | 70 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 20/04/2023 | 65.29 | 65.29
662 | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. (SM/09049) | SM/09049 | 41.88 | 505 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 28/02/2025 | 26/06/2025 | 02/11/2021 | 40.65 | 40.65
663 | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) (SM/09053) | SM/09053 | 14.94 | 200 | RETROFITTING | 100 | 100% Physical | 82 | 29/10/2021 | 31/12/2025 | 26/06/2025 | 02/11/2021 | 12.23 | 12.22
664 | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme (SM/07099) | SM/07099 | 99.16 | 2025 | RETROFITTING | 100 | 100% Physical | 100 | 26/11/2020 | 30/09/2025 | 26/06/2025 | 11/01/2021 | 99 | 98.91
665 | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme (SM/07102) | SM/07102 | 99.76 | 2000 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 05/01/2021 | 96.83 | 96.83
666 | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) (SM/07976) | SM/07976 | 1280.9 | 27063 | RETROFITTING | 100 | 100% Physical | 94 | 21/01/2021 | 30/09/2025 | 26/06/2025 | 29/01/2021 | 1203.9 | 1202.42
667 | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme (SM/07105) | SM/07105 | 99.66 | 2020 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 21/12/2020 | 96.67 | 96.67
668 | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block (SM/07479) | SM/07479 | 79.84 | 1612 | RETROFITTING | 100 | 100% Physical | 96 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 11/02/2021 | 76.95 | 76.67
669 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) (SM/07482) | SM/07482 | 53.02 | 992 | RETROFITTING | 100 | 100% Physical | 97 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 05/01/2021 | 51.25 | 51.25
670 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. (SM/07484) | SM/07484 | 99.86 | 2070 | RETROFITTING | 100 | 100% Physical | 97 | 29/12/2020 | 28/02/2025 | 26/06/2025 | 05/02/2021 | 96.68 | 96.68
671 | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block (SM/07654) | SM/07654 | 117.41 | 2449 | RETROFITTING | 100 | 100% Physical | 74 | 07/01/2021 | 31/03/2025 | 26/06/2025 | 04/02/2021 | 86.9 | 86.8
672 | Retrofitting to accomodate FHTC under JJM in Bagmari W/S Scheme Potashpur-II Block (PHASE-II) (SM/08226) | SM/08226 | 91.23 | 1220 | RETROFITTING | 100 | 100% Physical | 63 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 11/05/2021 | 57.72 | 57.72
673 | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme (SM/07104) | SM/07104 | 97.26 | 2000 | RETROFITTING | 100 | 100% Physical | 87 | 26/11/2020 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 84.71 | 84.71
674 | Balance Work for Retrofitting to Accommodate FHTC (750 Nos.) and Laying of left-out portion UPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-XI, Block-Kolaghat in this (SM/10095) | SM/10095 | 95.4 | 750 | RETROFITTING | 100 | 100% Physical | 97 | 01/02/2022 | 30/09/2025 | 26/06/2025 | 08/02/2022 | 93 | 92.89
675 | Balance work for Retrofitting to Accommodate FHTC (951 Nos.) and laying of Left-out portion UPVC pipeline due to uncovered area of this Zone and Damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme under Zone-III (SM/10096) | SM/10096 | 89.89 | 951 | RETROFITTING | 100 | 100% Physical | 86 | 01/02/2022 | 30/09/2025 | 26/06/2025 | 23/02/2022 | 77.04 | 77.04
676 | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) (SM/08227) | SM/08227 | 27.42 | 427 | RETROFITTING | 100 | 100% Physical | 93 | 09/02/2021 | 28/02/2025 | 26/06/2025 | 22/02/2021 | 25.48 | 25.15
677 | Rejuvenation to accommodate FHTC under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division PHE Dte Purba Medinipur Phase II (SM/08749) | SM/08749 | 65.32 | 450 | RETROFITTING | 100 | 100% Physical | 95 | 09/09/2021 | 28/02/2025 | 26/06/2025 | 10/09/2021 | 62.26 | 62.26
678 | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. (SM/06626) | SM/06626 | 106.33 | 0 | SUPPORT-WQMSP | 100 | 100% Physical | 0 | 05/02/2020 | 25/02/2025 | 26/06/2025 | 30/12/2020 | 0 | 0
Total |  |  | 402760.79 | 1153968 | [8 empty] | 137239.96 | 136787.18