## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Solarization of grid connected pumping installation at Basudebberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17379) | SM/17379 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
2 | Solarization of grid connected pumping installation at Mohisda, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17762) | SM/17762 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
3 | Solarization of grid connected pumping installation at Haldia (Ramnagar)PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17770) | SM/17770 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
4 | Solarization of grid connected pumping installation at Gobindanagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17801) | SM/17801 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
5 | Solarization of grid connected pumping installation at Natshallakhya, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17803) | SM/17803 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
6 | Solarization of grid connected pumping installation at Jagatpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17805) | SM/17805 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
7 | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme. (SM/16652) | SM/16652 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
8 | Solarization of grid connected pumping installation at Chaitanyapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17361) | SM/17361 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
9 | Solarization of grid connected pumping installation at Bamunia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17324) | SM/17324 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
10 | Solarization of grid connected pumping installation at Gogras keshab bar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17723) | SM/17723 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
11 | Solarization of grid connected pumping installation at Basudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17347) | SM/17347 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
12 | Solarization of grid connected pumping installation at Bagmari (Potashpur - II) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17350) | SM/17350 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
13 | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12399) | SM/12399 | 696.35 | 1808 | NEW | 0 | 0% Physical | 0 | 13/09/2022 | 13/03/2024 | 12/06/2023 | 31/12/2022 | 0 | 0
14 | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12401) | SM/12401 | 706.42 | 2186 | NEW | 0 | 0% Physical | 0 | 13/09/2022 | 13/03/2024 | 12/06/2023 | 20/03/2023 | 0 | 0
15 | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme. (SM/16668) | SM/16668 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
16 | Solarization of grid connected pumping installation at KANKTYA PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17756) | SM/17756 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
17 | Solarization of grid connected pumping installation at Manikpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17771) | SM/17771 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
18 | Solarization of grid connected pumping installation at Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17772) | SM/17772 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
19 | Solarization of grid connected pumping installation at Haur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17775) | SM/17775 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
20 | Solarization of grid connected pumping installation at Alinan, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17385) | SM/17385 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
21 | Solarization of grid connected pumping installation at Dakshin chak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17308) | SM/17308 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
22 | Solarization of grid connected pumping installation at Solat PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17726) | SM/17726 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
23 | Solarization of grid connected pumping installation at Khejurberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17793) | SM/17793 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
24 | Solarization of grid connected pumping installation at Anantapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17349) | SM/17349 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
25 | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme. (SM/16654) | SM/16654 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
26 | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. (SM/16669) | SM/16669 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 28/04/2023 | 0 | 0
27 | Solarization of grid connected pumping installation at Durmut PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17789) | SM/17789 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
28 | Solarization of grid connected pumping installation at Gopalpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17800) | SM/17800 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
29 | Solarization of grid connected pumping installation at Tajpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17804) | SM/17804 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
30 | Solarization of grid connected pumping installation at Dakhsin Mechogram PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17367) | SM/17367 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
31 | Solarization of grid connected pumping installation at Golaranji PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17823) | SM/17823 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
32 | Solarization of grid connected pumping installation at Anurai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17337) | SM/17337 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
33 | Solarization of grid connected pumping installation at Barbasudebpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17305) | SM/17305 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
34 | Solarization of grid connected pumping installation at Keshabpur Jalpai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17791) | SM/17791 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
35 | Solarization of grid connected pumping installation at Bagmari (Egra-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17351) | SM/17351 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
36 | Solarization of grid connected pumping installation at Barchunfali PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17331) | SM/17331 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
37 | Solarization of grid connected pumping installation at Manoharpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17813) | SM/17813 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
38 | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. (SM/16663) | SM/16663 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
39 | Solarization of grid connected pumping installation at Mahammadpur (Nandigram) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17717) | SM/17717 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
40 | Solarization of grid connected pumping installation at Purba Bakulda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17774) | SM/17774 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
41 | Solarization of grid connected pumping installation at Uttar Sonamui PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17747) | SM/17747 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
42 | Solarization of grid connected pumping installation at Bargodagoda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17372) | SM/17372 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
43 | Solarization of grid connected pumping installation at Chirulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17323) | SM/17323 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
44 | Solarization of grid connected pumping installation at Badhia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17309) | SM/17309 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
45 | Solarization of grid connected pumping installation at Bankiput PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17353) | SM/17353 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
46 | Solarization of grid connected pumping installation at Kanakpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17814) | SM/17814 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
47 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. (SM/14486) | SM/14486 | 42.52 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 20/01/2023 | 20/07/2023 | 12/06/2023 | 20/02/2023 | 0 | 0
48 | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. (SM/16660) | SM/16660 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 30/03/2023 | 0 | 0
49 | Solarization of grid connected pumping installation at Dona PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17777) | SM/17777 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
50 | Solarization of grid connected pumping installation at Rajarampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17784) | SM/17784 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
51 | Solarization of grid connected pumping installation at Haipur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17786) | SM/17786 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
52 | Solarization of grid connected pumping installation at Chatra (Sahid Matangini) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17387) | SM/17387 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
53 | Solarization of grid connected pumping installation at Chandibeniya, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17355) | SM/17355 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
54 | Solarization of grid connected pumping installation at Asthichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17329) | SM/17329 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
55 | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme. (SM/16667) | SM/16667 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
56 | Solarization of grid connected pumping installation at Natshallakhya, Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17757) | SM/17757 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
57 | Solarization of grid connected pumping installation at Rangibasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17764) | SM/17764 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
58 | Solarization of grid connected pumping installation at Kapaseria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17769) | SM/17769 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
59 | Solarization of grid connected pumping installation at Dhenkua PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17317) | SM/17317 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
60 | Solarization of grid connected pumping installation at Majna PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17817) | SM/17817 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
61 | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme. (SM/16657) | SM/16657 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
62 | Solarization of grid connected pumping installation at Dwariberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17761) | SM/17761 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
63 | Solarization of grid connected pumping installation at Madhabpur (Balighai) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17767) | SM/17767 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
64 | Solarization of grid connected pumping installation at Kudi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17773) | SM/17773 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
65 | Solarization of grid connected pumping installation at Moyna, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17782) | SM/17782 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
66 | Solarization of grid connected pumping installation at Mandar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17788) | SM/17788 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
67 | Solarization of grid connected pumping installation at Kasbagola PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17802) | SM/17802 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
68 | Solarization of grid connected pumping installation at Uttardalhara Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17809) | SM/17809 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
69 | Solarization of grid connected pumping installation at Damudarpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17341) | SM/17341 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
70 | Solarization of grid connected pumping installation at Dakshin Dalhara PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17314) | SM/17314 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
71 | Solarization of grid connected pumping installation at Erasal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17724) | SM/17724 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
72 | Solarization of grid connected pumping installation at Baichberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17318) | SM/17318 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
73 | Solarization of grid connected pumping installation at Bishnubarh PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17322) | SM/17322 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
74 | Solarization of grid connected pumping installation at Barsundra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17296) | SM/17296 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
75 | Solarization of grid connected pumping installation at Gobra PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17783) | SM/17783 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
76 | Solarization of grid connected pumping installation at Kolsar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17807) | SM/17807 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
77 | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. (SM/16650) | SM/16650 | 12.39 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
78 | Solarization of grid connected pumping installation at Chandanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17386) | SM/17386 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
79 | Solarization of grid connected pumping installation at Bhagabanpur, Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17364) | SM/17364 | 16.61 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
80 | Solarization of grid connected pumping installation at Kanpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17824) | SM/17824 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 29/03/2023 | 0 | 0
81 | Solarization of grid connected pumping installation at Chapbasan PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17378) | SM/17378 | 8.3 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
82 | Solarization of grid connected pumping installation at Chirulia Chalta PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17352) | SM/17352 | 33.22 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 15/03/2023 | 15/09/2023 | 12/06/2023 | 23/03/2023 | 0 | 0
83 | Drinking Water Sample Collection & testing through Filed Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. (SM/19087) | SM/19087 | 137.53 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 11/01/2024 | 0 | 0
84 | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Purba Medinipur District July 2023 (SM/19093) | SM/19093 | 191.8 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 06/12/2023 |  | 06/12/2023 | 20/12/2023 | 0 | 0
85 | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS (SM/12398) | SM/12398 | 645.5 | 1806 | NEW | 1 | On track | 3 | 13/09/2022 | 31/12/2025 | 02/04/2024 | 20/03/2023 | 18.26 | 14.98
86 | MURARI KALUA PWSS (SM/14693) | SM/14693 | 236.53 | 425 | NEW | 2 | Delayed | 0 | 31/01/2023 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
87 | HALUD BARI AND ADJOINING MOUJAS (SM/12821) | SM/12821 | 728 | 1961 | NEW | 2 | Delayed | 42 | 20/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 305.79 | 289.96
88 | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12400) | SM/12400 | 465.14 | 1112 | NEW | 3 | Delayed | 13 | 13/09/2022 | 31/12/2025 | 26/04/2024 | 31/12/2022 | 58.5 | 44.93
89 | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16939) | SM/16939 | 62.87 | 0 | AUGMENTATION | 3 | Delayed | 1 | 16/03/2023 | 31/03/2024 | 12/09/2023 | 25/04/2023 | 0.83 | 0.83
90 | SATSATMAL & ADJOINING MOUJAS PWSS (SM/12163) | SM/12163 | 975.7 | 2638 | NEW | 3 | Delayed | 29 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 283.68 | 225.71
91 | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme (SM/15034) | SM/15034 | 635.84 | 1807 | AUGMENTATION | 4 | Delayed | 1 | 04/02/2023 | 31/12/2024 | 08/09/2023 | 27/03/2023 | 3.2 | 3.2
92 | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme (SM/16464) | SM/16464 | 665.82 | 1636 | AUGMENTATION | 4 | Delayed | 1 | 03/03/2023 | 31/12/2024 | 08/09/2023 | 27/03/2023 | 3.49 | 3.49
93 | Piped water Supply Scheme for Chirulia-Chatla Zone-1 (SM/16284) | SM/16284 | 403.81 | 162 | AUGMENTATION | 4 | Delayed | 1 | 23/02/2023 | 30/09/2024 | 28/08/2023 | 25/04/2023 | 4.01 | 4.01
94 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. (SM/16713) | SM/16713 | 140.37 | 0 | AUGMENTATION | 4 | Delayed | 0 | 14/03/2023 | 31/03/2024 | 12/09/2023 | 25/04/2023 | 0 | 0
95 | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS (SM/11885) | SM/11885 | 410.86 | 1306 | NEW | 4 | Delayed | 9 | 17/08/2022 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 38.46 | 38.46
96 | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme (SM/16194) | SM/16194 | 730.61 | 1427 | AUGMENTATION | 4 | Delayed | 16 | 24/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 119.1 | 39.33
97 | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur (SM/18402) | SM/18402 | 49821.56 | 39657 | NEW | 4 | Delayed | 0 | 12/07/2023 | 12/07/2026 | 18/04/2024 | 31/05/2023 | 68.61 | 68.61
98 | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 (SM/15844) | SM/15844 | 444.01 | 173 | AUGMENTATION | 4 | Delayed | 1 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 2.89 | 2.89
99 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. (SM/16288) | SM/16288 | 522.2 | 782 | AUGMENTATION | 4 | Delayed | 12 | 23/02/2023 | 31/12/2024 | 08/09/2023 | 19/07/2023 | 60.99 | 60.99
100 | BARNAN AND ITS ADJOINING MOUJAS PWSS (SM/11884) | SM/11884 | 404.59 | 0 | NEW | 4 | Delayed | 0 | 17/08/2022 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 0 | 0
101 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10689) | SM/10689 | 963 | 2443 | NEW | 4 | Delayed | 40 | 12/05/2022 | 31/03/2024 | 12/09/2023 | 05/04/2023 | 389.22 | 389.22
102 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16948) | SM/16948 | 71.27 | 322 | NEW | 4 | Delayed | 0 | 16/03/2023 | 31/03/2024 | 12/09/2023 | 05/04/2023 | 0 | 0
103 | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS (SM/12495) | SM/12495 | 581.74 | 1623 | NEW | 5 | Delayed | 3 | 13/09/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 16.41 | 16.41
104 | TANIA BILA AND ADJOINING MOUJAS PWSS (SM/12145) | SM/12145 | 510.18 | 1236 | NEW | 5 | Delayed | 0 | 07/09/2022 | 31/03/2024 | 12/09/2023 | 29/12/2022 | 0 | 0
105 | KEKAI & ADJOINING MOUJAS PWSS (SM/12168) | SM/12168 | 742.03 | 1793 | NEW | 5 | Delayed | 2 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 18.52 | 14.98
106 | Tilkhoja & Adjoining mouzas (SM/12133) | SM/12133 | 714.12 | 2331 | NEW | 5 | Delayed | 27 | 07/09/2022 | 31/12/2025 | 14/03/2024 | 29/12/2022 | 191.6 | 124.57
107 | MATHURA AND IT'S ADJOINING MOUJAS PWSS (SM/13745) | SM/13745 | 732.18 | 2170 | NEW | 5 | Delayed | 0 | 17/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
108 | BELDA AND IT'S ADJOINING MOUJAS PWSS (SM/12710) | SM/12710 | 699.88 | 2385 | NEW | 5 | Delayed | 1 | 20/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 5.42 | 2.39
109 | Piped Water Supply Scheme for Bathuari Zone-II (SM/15853) | SM/15853 | 439.72 | 12 | AUGMENTATION | 5 | Delayed | 3 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 28/04/2023 | 15.15 | 3.1
110 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I (SM/14841) | SM/14841 | 207.52 | 69 | AUGMENTATION | 5 | Delayed | 1 | 03/02/2023 | 31/12/2024 | 08/09/2023 | 25/04/2023 | 2.95 | 2.95
111 | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. (SM/12307) | SM/12307 | 514.51 | 1198 | NEW | 5 | Delayed | 0 | 09/09/2022 | 31/12/2024 | 18/04/2024 | 31/12/2022 | 0 | 0
112 | BASANTA CHAK AND ADJOINING MOUJAS PWSS (SM/12144) | SM/12144 | 564.98 | 2072 | NEW | 5 | Delayed | 21 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 29/12/2022 | 115.91 | 100.19
113 | BARA BHAGIA AND ADJOINING MOUJAS PWSS (SM/12704) | SM/12704 | 498.09 | 1110 | NEW | 5 | Delayed | 6 | 20/09/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 29 | 29
114 | SELMABAD AND ADJOINING MOUJAS PWSS (SM/12518) | SM/12518 | 757.8 | 2717 | NEW | 5 | Delayed | 2 | 13/09/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 11.51 | 0
115 | TELAMI AND ADJOINING MOUJAS PWSS (SM/12288) | SM/12288 | 462.76 | 724 | NEW | 5 | Delayed | 13 | 09/09/2022 | 31/12/2025 | 19/04/2024 | 31/12/2022 | 60.42 | 47.73
116 | NAIPUR & ADJOINING MOUZAS (SM/12135) | SM/12135 | 550.96 | 1575 | NEW | 5 | Delayed | 8 | 07/09/2022 | 31/12/2025 | 12/03/2024 | 29/12/2022 | 44.58 | 41.45
117 | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. (SM/12319) | SM/12319 | 532.38 | 1165 | NEW | 5 | Delayed | 0 | 09/09/2022 | 31/12/2024 | 12/03/2024 | 31/12/2022 | 1.87 | 1.87
118 | NONAKOURDA AND IT'S ADJOINING MOUJAS (SM/13857) | SM/13857 | 428.88 | 1018 | NEW | 5 | Delayed | 0 | 25/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
119 | BAKCHA AND ADJOINING MOUJAS PWSS (SM/12146) | SM/12146 | 623.54 | 2046 | NEW | 5 | Delayed | 13 | 07/09/2022 | 31/12/2025 | 14/03/2024 | 29/12/2022 | 81.3 | 28.39
120 | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS (SM/12509) | SM/12509 | 683.07 | 1660 | NEW | 5 | Delayed | 45 | 13/09/2022 | 31/12/2024 | 06/03/2024 | 19/04/2023 | 306.43 | 306.43
121 | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/12511) | SM/12511 | 524.62 | 1138 | NEW | 5 | Delayed | 2 | 13/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 11.61 | 7.49
122 | KALABERIA & ADJOINING MOUZAS (SM/12136) | SM/12136 | 743.49 | 3184 | NEW | 5 | Delayed | 2 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 29/12/2022 | 17.54 | 0
123 | KHARUI AND ADJOINING MOUZAS PWSS (SM/11945) | SM/11945 | 637.14 | 2574 | NEW | 5 | Delayed | 31 | 24/08/2022 | 31/12/2025 | 06/03/2024 | 20/03/2023 | 199.44 | 190.45
124 | KHAR & IT'S ADJOINING MOUJAS PWSS (SM/13743) | SM/13743 | 987.25 | 2849 | NEW | 5 | Delayed | 1 | 17/11/2022 | 31/12/2025 | 19/04/2024 | 20/03/2023 | 5.83 | 0
125 | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS (SM/14457) | SM/14457 | 317.67 | 570 | NEW | 5 | Delayed | 6 | 20/01/2023 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 18.74 | 0
126 | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS (SM/13854) | SM/13854 | 749.32 | 1354 | NEW | 5 | Delayed | 4 | 25/11/2022 | 31/12/2025 | 29/04/2024 | 20/03/2023 | 33.58 | 29.95
127 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III (SM/15510) | SM/15510 | 1406.2 | 4683 | AUGMENTATION | 5 | Delayed | 39 | 16/02/2023 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 541.7 | 535.19
128 | Piped Water Supply Scheme for Bathuari Zone-IV (SM/15845) | SM/15845 | 428.01 | 48 | AUGMENTATION | 5 | Delayed | 1 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 28/04/2023 | 2.98 | 2.98
129 | BARTTANA & IT'S ADJOINING MOUJAS PWSS (SM/13697) | SM/13697 | 695.93 | 1639 | NEW | 5 | Delayed | 6 | 14/11/2022 | 31/12/2025 | 19/04/2024 | 20/03/2023 | 44.93 | 39.6
130 | PURANDA AND IT'S ADJOINING MOUJAS PWSS (SM/12818) | SM/12818 | 640.79 | 1330 | NEW | 5 | Delayed | 5 | 20/09/2022 | 31/12/2025 | 19/04/2024 | 20/03/2023 | 31.57 | 21.83
131 | KSHETRAPAL AND IT'S ADJOINING MOUJAS (SM/12513) | SM/12513 | 695.17 | 1880 | NEW | 5 | Delayed | 4 | 13/09/2022 | 31/12/2025 | 23/04/2024 | 20/03/2023 | 25.7 | 0
132 | RADHABALLAV CHAK & ADJOINING MOUZAS (SM/12156) | SM/12156 | 715.87 | 2026 | NEW | 5 | Delayed | 10 | 07/09/2022 | 31/12/2025 | 22/03/2024 | 29/12/2022 | 70.35 | 39.44
133 | MAKRAMPUR AND ADJOINING MOUJAS PWSS (SM/12282) | SM/12282 | 752.28 | 1422 | NEW | 5 | Delayed | 1 | 09/09/2022 | 31/12/2025 | 10/05/2024 | 31/12/2022 | 5.32 | 0
134 | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS (SM/12510) | SM/12510 | 755.87 | 2000 | NEW | 5 | Delayed | 4 | 13/09/2022 | 31/12/2025 | 23/04/2024 | 20/03/2023 | 32 | 25.64
135 | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS (SM/12433) | SM/12433 | 540.95 | 1833 | NEW | 5 | Delayed | 0 | 13/09/2022 | 31/03/2024 | 06/11/2023 | 20/03/2023 | 0 | 0
136 | JUMKI AND ADJOINING MOUJAS PWSS (SM/12995) | SM/12995 | 620.99 | 1636 | NEW | 5 | Delayed | 34 | 28/09/2022 | 31/12/2025 | 19/04/2024 | 31/12/2022 | 209.5 | 201.24
137 | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 (SM/14840) | SM/14840 | 154.51 | 27 | AUGMENTATION | 5 | Delayed | 21 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 32.68 | 32.68
138 | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS (SM/14673) | SM/14673 | 642.05 | 614 | NEW | 5 | Delayed | 0 | 31/01/2023 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
139 | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. (SM/13851) | SM/13851 | 167.94 | 249 | NEW | 5 | Delayed | 19 | 25/11/2022 | 31/03/2024 | 12/09/2023 | 20/04/2023 | 31.79 | 31.79
140 | TAJPUR AND ADJOINING MOUJAS PWSS (SM/12284) | SM/12284 | 815.19 | 2785 | NEW | 5 | Delayed | 24 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 192.45 | 183.73
141 | GOBRADAN & ADJOINING MOUZAS (SM/12161) | SM/12161 | 569.73 | 1420 | NEW | 5 | Delayed | 12 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 69.96 | 14.91
142 | GOKULNAGAR AND ADJOINING MOUJAS (SM/12165) | SM/12165 | 821.18 | 2421 | NEW | 5 | Delayed | 8 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 61.96 | 17.79
143 | KASBAPATASHPUR & ADJOINING MOUJAS PWSS (SM/12172) | SM/12172 | 664.72 | 1875 | NEW | 5 | Delayed | 4 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 31/12/2022 | 23.74 | 23.74
144 | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. (SM/12318) | SM/12318 | 727.81 | 1929 | NEW | 5 | Delayed | 15 | 09/09/2022 | 31/12/2025 | 09/04/2024 | 31/12/2022 | 107.06 | 70.98
145 | KIA AND IT'S ADJOINING MOUJAS (SM/12814) | SM/12814 | 720.1 | 1897 | NEW | 5 | Delayed | 11 | 20/09/2022 | 31/12/2024 | 13/03/2024 | 28/03/2023 | 79.18 | 70.66
146 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II (SM/15843) | SM/15843 | 487.15 | 238 | AUGMENTATION | 5 | Delayed | 3 | 20/02/2023 | 31/12/2024 | 08/09/2023 | 25/04/2023 | 15.11 | 3.06
147 | AILAN AND IT'S ADJOINING MOUJAS PWSS (SM/15514) | SM/15514 | 1127.65 | 3046 | NEW | 5 | Delayed | 4 | 16/02/2023 | 16/02/2025 | 13/03/2024 | 04/05/2023 | 48.85 | 48.85
148 | DAHA DAYA PIPED WATER SUPPLY SCHEME. (SM/15849) | SM/15849 | 158.24 | 270 | NEW | 5 | Delayed | 0 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 0 | 0
149 | FULESHWAR AND ADJOINING MOUJAS PWSS (SM/12500) | SM/12500 | 658.22 | 1268 | NEW | 5 | Delayed | 12 | 13/09/2022 | 31/12/2025 | 06/03/2024 | 20/03/2023 | 80.75 | 77.51
150 | CHALTI AND ADJOINING MOUJAS PWSS (SM/12505) | SM/12505 | 592.82 | 1098 | NEW | 5 | Delayed | 4 | 13/09/2022 | 31/12/2024 | 18/04/2024 | 31/12/2022 | 24.53 | 24.53
151 | KAJI BASAN AND ADJOINING MOUJAS PWSS (SM/12499) | SM/12499 | 576.08 | 1276 | NEW | 5 | Delayed | 1 | 13/09/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 4.19 | 2.12
152 | BAISPUR AND ADJOINING MOUJAS PWSS (SM/12290) | SM/12290 | 495.84 | 1251 | NEW | 5 | Delayed | 3 | 09/09/2022 | 31/12/2024 | 18/04/2024 | 31/12/2022 | 17.21 | 17.21
153 | CHANDPUR AND ADJOINING MOUJAS PWSS (SM/13693) | SM/13693 | 613.46 | 1358 | NEW | 5 | Delayed | 3 | 14/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 18.74 | 0
154 | PATNA & ADJOINING MOUZAS (SM/12164) | SM/12164 | 1065.08 | 2930 | NEW | 5 | Delayed | 38 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 406.34 | 398.88
155 | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. (SM/12320) | SM/12320 | 674.76 | 1497 | NEW | 5 | Delayed | 7 | 09/09/2022 | 31/12/2025 | 19/04/2024 | 31/12/2022 | 45.33 | 36.14
156 | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS (SM/13853) | SM/13853 | 507.49 | 1023 | NEW | 5 | Delayed | 0 | 25/11/2022 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 0 | 0
157 | Piped Water Supply Scheme for Bathuari Zone-III (SM/16300) | SM/16300 | 396.8 | 55 | AUGMENTATION | 5 | Delayed | 4 | 23/02/2023 | 30/09/2024 | 09/08/2023 | 28/04/2023 | 16.41 | 2.89
158 | SHOULA BHERI AND ADJOINING MOUJAS PWSS (SM/12496) | SM/12496 | 922.95 | 2921 | NEW | 5 | Delayed | 0 | 13/09/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
159 | SHWNIA AND ADJOINING MOUJAS PWSS (SM/12494) | SM/12494 | 453.35 | 734 | NEW | 5 | Delayed | 8 | 13/09/2022 | 31/12/2024 | 13/03/2024 | 20/03/2023 | 34.71 | 17.17
160 | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS (SM/12405) | SM/12405 | 466.31 | 893 | NEW | 5 | Delayed | 4 | 13/09/2022 | 31/03/2024 | 12/09/2023 | 28/03/2023 | 17.54 | 0
161 | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS (SM/11883) | SM/11883 | 428.89 | 1643 | NEW | 5 | Delayed | 21 | 17/08/2022 | 31/12/2025 | 23/04/2024 | 20/04/2023 | 88.1 | 69.09
162 | GOURANGA CHAK AND ADJOINING MOUJAS PWSS (SM/13884) | SM/13884 | 589.91 | 1427 | NEW | 5 | Delayed | 5 | 25/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 32.07 | 23.28
163 | Piped Water Supply Scheme for Sankarpur Zone-II (SM/14842) | SM/14842 | 70.89 | 197 | AUGMENTATION | 5 | Delayed | 25 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 27/03/2023 | 18.01 | 18.01
164 | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS (SM/14671) | SM/14671 | 471.07 | 1040 | NEW | 5 | Delayed | 4 | 31/01/2023 | 31/12/2024 | 12/03/2024 | 20/03/2023 | 16.99 | 16.99
165 | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/14745) | SM/14745 | 216.7 | 236 | NEW | 5 | Delayed | 33 | 31/01/2023 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 72.35 | 60.82
166 | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III (SM/15841) | SM/15841 | 432.64 | 99 | AUGMENTATION | 5 | Delayed | 1 | 20/02/2023 | 31/12/2024 | 08/09/2023 | 25/04/2023 | 3.22 | 3.22
167 | PANCHBERYA PIPED WATER SUPPLY SCHEME (SM/16201) | SM/16201 | 171.95 | 131 | NEW | 5 | Delayed | 0 | 23/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 0 | 0
168 | BHATSALIA & IT'S ADJOINING MOUJAS PWSS (SM/16203) | SM/16203 | 166.63 | 337 | NEW | 5 | Delayed | 31 | 23/02/2023 | 31/12/2024 | 18/04/2024 | 08/06/2023 | 51.71 | 51.71
169 | KIARANA AND ADJOINING MOUJAS PWSS (SM/12628) | SM/12628 | 710.87 | 1424 | NEW | 5 | Delayed | 8 | 19/09/2022 | 31/12/2025 | 14/03/2024 | 31/12/2022 | 54.48 | 27.44
170 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. (SM/11979) | SM/11979 | 1668.76 | 7010 | AUGMENTATION | 5 | Delayed | 20 | 31/08/2022 | 31/03/2024 | 13/07/2023 | 20/03/2023 | 329.66 | 280.13
171 | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12141) | SM/12141 | 894.23 | 2407 | NEW | 5 | Delayed | 6 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 29/12/2022 | 55.5 | 23.4
172 | SHIPUR AND ADJOINING MOUJAS PWSS (SM/12503) | SM/12503 | 698.5 | 1484 | NEW | 5 | Delayed | 8 | 13/09/2022 | 31/12/2024 | 13/03/2024 | 31/12/2022 | 52.82 | 52.82
173 | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. (SM/12634) | SM/12634 | 503.6 | 1062 | NEW | 5 | Delayed | 8 | 19/09/2022 | 31/12/2025 | 19/03/2024 | 31/12/2022 | 40.82 | 30.35
174 | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS (SM/13696) | SM/13696 | 422.36 | 792 | NEW | 5 | Delayed | 0 | 14/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
175 | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12774) | SM/12774 | 676.58 | 1680 | NEW | 5 | Delayed | 0 | 20/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 3.29 | 0
176 | GOJINA AND IT'S ADJOINING MOUJAS PWSS (SM/12812) | SM/12812 | 766.35 | 2437 | NEW | 5 | Delayed | 31 | 20/09/2022 | 31/12/2025 | 14/03/2024 | 20/03/2023 | 234.14 | 210.7
177 | Piped Water Supply Scheme for Bathuari Zone-I (SM/14839) | SM/14839 | 181.49 | 23 | AUGMENTATION | 5 | Delayed | 2 | 03/02/2023 | 31/12/2024 | 08/09/2023 | 28/04/2023 | 2.95 | 2.95
178 | POTA PAKURIA AND IT'S ADJOINING MOUJAS (SM/13886) | SM/13886 | 555.33 | 981 | NEW | 5 | Delayed | 1 | 25/11/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 3.45 | 0
179 | Providing FHTC (Functional Household Tap Connection) with Augmentation of Murisai Water Supply Scheme (SM/13889) | SM/13889 | 133.52 | 0 | AUGMENTATION | 5 | Delayed | 0 | 25/11/2022 | 31/12/2024 | 18/04/2024 | 01/08/2023 | 0 | 0
180 | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission (SM/14458) | SM/14458 | 78.13 | 0 | SUPPORT-WQMSP | 5 | Delayed | 0 | 20/01/2023 | 31/03/2024 | 05/10/2023 | 20/09/2023 | 0 | 0
181 | CHISTIPUR AND ADJOINING MOUJAS (SM/14672) | SM/14672 | 668.48 | 2004 | NEW | 6 | Delayed | 0 | 31/01/2023 | 31/12/2024 | 18/04/2024 | 28/03/2023 | 0 | 0
182 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV (SM/16286) | SM/16286 | 461.03 | 209 | AUGMENTATION | 6 | Delayed | 28 | 23/02/2023 | 31/12/2025 | 09/01/2024 | 25/04/2023 | 128.3 | 119.74
183 | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS (SM/13686) | SM/13686 | 520.05 | 1135 | NEW | 6 | Delayed | 0 | 14/11/2022 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 0 | 0
184 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) (SM/16460) | SM/16460 | 139.71 | 172 | AUGMENTATION | 6 | Delayed | 20 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 27/03/2023 | 28.15 | 28.15
185 | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16279) | SM/16279 | 80.74 | 0 | AUGMENTATION | 6 | Delayed | 0 | 24/02/2023 | 31/12/2023 | 07/09/2023 | 25/04/2023 | 0 | 0
186 | TALADIHA AND ADJOINING MOUJAS PWSS (SM/12283) | SM/12283 | 496.8 | 1324 | NEW | 6 | Delayed | 25 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 122.58 | 110.88
187 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/18765) | SM/18765 | 63.12 | 0 | AUGMENTATION | 6 | Delayed | 0 | 23/08/2023 | 31/12/2024 | 18/04/2024 | 29/11/2023 | 0 | 0
188 | JERTHAN AND ADJOINING MOUJAS PWSS (SM/12308) | SM/12308 | 762.33 | 2232 | NEW | 6 | Delayed | 41 | 09/09/2022 | 31/12/2025 | 21/03/2024 | 31/12/2022 | 308.8 | 295.45
189 | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13690) | SM/13690 | 464.83 | 533 | NEW | 6 | Delayed | 12 | 14/11/2022 | 31/12/2025 | 13/03/2024 | 20/03/2023 | 53.93 | 34.66
190 | BARDA AND ADJOINING MOUJAS PWSS (SM/12306) | SM/12306 | 594.37 | 1396 | NEW | 6 | Delayed | 6 | 09/09/2022 | 31/12/2025 | 21/03/2024 | 31/12/2022 | 35.78 | 26.32
191 | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS (SM/12878) | SM/12878 | 721.18 | 1527 | NEW | 6 | Delayed | 2 | 23/09/2022 | 31/12/2025 | 18/04/2024 | 28/03/2023 | 13.64 | 0
192 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. (SM/16712) | SM/16712 | 143.36 | 0 | AUGMENTATION | 6 | Delayed | 21 | 14/03/2023 | 31/12/2025 | 12/09/2023 | 25/04/2023 | 30.15 | 18.96
193 | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS (SM/14749) | SM/14749 | 342.28 | 425 | NEW | 6 | Delayed | 0 | 31/01/2023 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
194 | BADALPUR PIPED WATER SUPPLY SCHEME. (SM/15852) | SM/15852 | 74.39 | 248 | NEW | 6 | Delayed | 2 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 25/04/2023 | 1.82 | 0.95
195 | Piped Water Supply Scheme for Sankarpur Zone-III (SM/15846) | SM/15846 | 338.75 | 267 | AUGMENTATION | 6 | Delayed | 6 | 20/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 20.47 | 4.44
196 | DUBDA IT'S ADJOINING MOUJAS PWSS (SM/15513) | SM/15513 | 1290.54 | 4067 | NEW | 6 | Delayed | 3 | 16/02/2023 | 31/12/2024 | 18/04/2024 | 04/05/2023 | 43.53 | 40.63
197 | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V (SM/16295) | SM/16295 | 458.23 | 184 | AUGMENTATION | 6 | Delayed | 23 | 23/02/2023 | 31/12/2025 | 14/12/2023 | 25/04/2023 | 106.34 | 86.91
198 | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS (SM/11947) | SM/11947 | 565.75 | 3857 | NEW | 6 | Delayed | 22 | 24/08/2022 | 31/12/2025 | 09/02/2024 | 20/03/2023 | 125.43 | 116.72
199 | KURPAI AND ADJOINING MOUJAS PWSS (SM/11882) | SM/11882 | 498.52 | 1684 | NEW | 6 | Delayed | 13 | 17/08/2022 | 31/12/2025 | 10/01/2024 | 04/05/2023 | 66.39 | 57.75
200 | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/14843) | SM/14843 | 63.12 | 0 | AUGMENTATION | 6 | Delayed | 0 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 06/04/2023 | 0 | 0
201 | MASHAGON AND ITS ADJOINING MOUJAS PWSS (SM/13883) | SM/13883 | 204.23 | 401 | NEW | 6 | Delayed | 0 | 25/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 0 | 0
202 | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS (SM/12507) | SM/12507 | 593.43 | 1702 | NEW | 6 | Delayed | 3 | 13/09/2022 | 31/12/2024 | 06/03/2024 | 31/12/2022 | 17.54 | 17.54
203 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) (SM/16462) | SM/16462 | 128.06 | 428 | AUGMENTATION | 7 | Delayed | 0 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 27/03/2023 | 0 | 0
204 | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/15038) | SM/15038 | 85.63 | 0 | AUGMENTATION | 7 | Delayed | 28 | 04/02/2023 | 31/12/2024 | 18/04/2024 | 06/04/2023 | 24.14 | 24.14
205 | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. (SM/15851) | SM/15851 | 74.9 | 250 | NEW | 7 | Delayed | 24 | 20/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 18.2 | 0
206 | DURMUT AND ADJOINING MOUJAS PWSS (SM/12820) | SM/12820 | 690.44 | 1698 | NEW | 7 | Delayed | 7 | 20/09/2022 | 31/12/2025 | 18/04/2024 | 24/03/2023 | 47.21 | 37.76
207 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. (SM/16463) | SM/16463 | 130.27 | 920 | AUGMENTATION | 7 | Delayed | 5 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 19/04/2023 | 6.52 | 6.52
208 | Piped Water Supply Scheme for Sankarpur Zone-V (SM/15847) | SM/15847 | 342.52 | 321 | AUGMENTATION | 7 | Delayed | 3 | 20/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 10.33 | 4.26
209 | Piped Water Supply Scheme for Sankarpur Zone-IV (SM/16305) | SM/16305 | 340.44 | 294 | AUGMENTATION | 7 | Delayed | 4 | 23/02/2023 | 31/12/2025 | 14/12/2023 | 25/04/2023 | 13.35 | 6.08
210 | Augmentation of Astichak (Zone-II) PWSS (SM/15035) | SM/15035 | 768.16 | 2196 | AUGMENTATION | 7 | Delayed | 5 | 04/02/2023 | 31/12/2025 | 13/12/2023 | 27/03/2023 | 35.04 | 27.43
211 | DANGAR TULSI AND ADJOINING MOUJAS PWSS (SM/12285) | SM/12285 | 712.76 | 1347 | NEW | 7 | Delayed | 11 | 09/09/2022 | 31/12/2025 | 13/03/2024 | 31/12/2022 | 77.97 | 64.98
212 | SRIKANTHA AND ADJOINING MOUJAS PWSS (SM/12512) | SM/12512 | 756.99 | 2575 | NEW | 7 | Delayed | 7 | 13/09/2022 | 31/12/2025 | 09/05/2024 | 20/03/2023 | 54.11 | 18.96
213 | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS (SM/12160) | SM/12160 | 751.44 | 2064 | NEW | 7 | Delayed | 21 | 07/09/2022 | 31/12/2025 | 09/05/2024 | 29/12/2022 | 159.97 | 117.62
214 | KHARAT KATBAR & ADJOINING MOUJAS PWSS (SM/12175) | SM/12175 | 725.48 | 1895 | NEW | 7 | Delayed | 6 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 43.11 | 27.56
215 | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS (SM/13691) | SM/13691 | 571.07 | 985 | NEW | 7 | Delayed | 19 | 14/11/2022 | 31/12/2025 | 13/03/2024 | 20/03/2023 | 108.14 | 103.89
216 | CHAK BHABANI & ADJOINING MOUJAS PWSS (SM/15512) | SM/15512 | 1095.47 | 2843 | NEW | 7 | Delayed | 33 | 16/02/2023 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 362.63 | 0
217 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) (SM/16461) | SM/16461 | 131.18 | 176 | AUGMENTATION | 7 | Delayed | 21 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 27/03/2023 | 27.05 | 27.05
218 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. (SM/10617) | SM/10617 | 977.46 | 704 | NEW | 8 | Delayed | 33 | 20/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 323.49 | 323.49
219 | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. (SM/12483) | SM/12483 | 520.66 | 1068 | NEW | 8 | Delayed | 31 | 13/09/2022 | 31/12/2025 | 26/04/2024 | 31/12/2022 | 160.32 | 146.75
220 | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 (SM/14836) | SM/14836 | 391.4 | 210 | AUGMENTATION | 8 | Delayed | 23 | 03/02/2023 | 31/12/2025 | 18/04/2024 | 27/03/2023 | 90.57 | 81.91
221 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. (SM/10585) | SM/10585 | 969 | 1356 | NEW | 8 | Delayed | 62 | 18/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 596.38 | 596.38
222 | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. (SM/12321) | SM/12321 | 630.08 | 1155 | NEW | 8 | Delayed | 31 | 09/09/2022 | 31/12/2025 | 19/04/2024 | 20/03/2023 | 193.12 | 184.39
223 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10666) | SM/10666 | 980.83 | 1451 | NEW | 8 | Delayed | 35 | 26/04/2022 | 31/12/2023 | 14/09/2023 | 09/03/2023 | 339.13 | 339.13
224 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. (SM/10619) | SM/10619 | 974 | 1080 | NEW | 8 | Delayed | 41 | 20/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 396.25 | 396.25
225 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. (SM/10618) | SM/10618 | 969 | 1306 | NEW | 8 | Delayed | 47 | 20/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 456.05 | 456.05
226 | Augmentation of Astichak (Zone-I) PWSS (SM/15462) | SM/15462 | 679.21 | 1291 | AUGMENTATION | 8 | Delayed | 5 | 04/02/2023 | 31/12/2025 | 13/12/2023 | 27/03/2023 | 32.07 | 24.35
227 | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17221) | SM/17221 | 80.74 | 0 | AUGMENTATION | 8 | Delayed | 0 | 15/03/2023 | 31/12/2023 | 07/09/2023 | 25/04/2023 | 0 | 0
228 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. (SM/10621) | SM/10621 | 989 | 1105 | NEW | 8 | Delayed | 65 | 20/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 645.9 | 645.9
229 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. (SM/10586) | SM/10586 | 992 | 1047 | NEW | 8 | Delayed | 59 | 18/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 587.71 | 585.67
230 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. (SM/10620) | SM/10620 | 992 | 1279 | NEW | 8 | Delayed | 63 | 20/04/2022 | 31/12/2023 | 05/10/2023 | 09/03/2023 | 623.66 | 623.66
231 | SATKALUA AND IT'S ADJOINING MOUJAS PWSS (SM/14695) | SM/14695 | 374.28 | 816 | NEW | 8 | Delayed | 1 | 31/01/2023 | 31/12/2025 | 02/05/2024 | 04/05/2023 | 4.11 | 0
232 | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme (SM/12402) | SM/12402 | 650.26 | 1669 | NEW | 9 | Delayed | 4 | 13/09/2022 | 31/03/2024 | 12/09/2023 | 10/04/2023 | 26.61 | 26.61
233 | PALPARA AND ADJOINING MOUJAS PWSS (SM/12508) | SM/12508 | 754.82 | 2861 | NEW | 9 | Delayed | 3 | 13/09/2022 | 31/12/2024 | 06/03/2024 | 20/03/2023 | 19.32 | 19.32
234 | SOYA DIGHI AND IT'S ADJOINING MOUJAS (SM/12809) | SM/12809 | 554.17 | 1914 | NEW | 9 | Delayed | 0 | 20/09/2022 | 31/03/2024 | 12/09/2023 | 02/05/2023 | 0 | 0
235 | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME (SM/16257) | SM/16257 | 520.9 | 958 | NEW | 9 | Delayed | 7 | 24/02/2023 | 31/03/2024 | 12/09/2023 | 28/03/2023 | 36.99 | 36.99
236 | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS (SM/12293) | SM/12293 | 665.46 | 1638 | NEW | 9 | Delayed | 6 | 09/09/2022 | 31/12/2024 | 18/04/2024 | 12/05/2023 | 36.63 | 36.63
237 | JHAUGERYA PIPED WATER SUPPLY SCHEME. (SM/15842) | SM/15842 | 179.26 | 158 | NEW | 9 | Delayed | 41 | 20/02/2023 | 31/03/2024 | 06/11/2023 | 25/04/2023 | 74.37 | 59.91
238 | ABAS BERYA & ADJOINING MOUZAS (SM/12162) | SM/12162 | 620.61 | 1576 | NEW | 9 | Delayed | 2 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 29/12/2022 | 9.71 | 9.71
239 | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/12886) | SM/12886 | 531.79 | 1045 | NEW | 9 | Delayed | 5 | 23/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 24.89 | 0
240 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. (SM/14838) | SM/14838 | 897.92 | 2173 | AUGMENTATION | 9 | Delayed | 18 | 03/02/2023 | 31/12/2025 | 05/01/2024 | 27/03/2023 | 158.51 | 143.64
241 | PURBA RADHAPUR & ADJOINING MOUZAS (SM/12154) | SM/12154 | 758.06 | 1870 | NEW | 9 | Delayed | 39 | 07/09/2022 | 31/03/2024 | 03/11/2023 | 29/12/2022 | 294.14 | 294.14
242 | BARAGECHA AND ADJOINING MOUJAS PWSS (SM/13885) | SM/13885 | 461.96 | 785 | NEW | 9 | Delayed | 11 | 25/11/2022 | 31/12/2024 | 18/04/2024 | 04/05/2023 | 51.58 | 51.58
243 | GOBINDAPUR & ADJOINING MOUZAS (SM/12149) | SM/12149 | 385.96 | 910 | NEW | 9 | Delayed | 3 | 07/09/2022 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 10.71 | 0
244 | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS (SM/13683) | SM/13683 | 710.43 | 2111 | NEW | 9 | Delayed | 20 | 14/11/2022 | 31/03/2024 | 12/09/2023 | 11/04/2023 | 145.19 | 145.19
245 | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS (SM/12134) | SM/12134 | 706.44 | 1988 | NEW | 9 | Delayed | 7 | 07/09/2022 | 31/03/2024 | 12/09/2023 | 02/05/2023 | 49.37 | 49.37
246 | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS (SM/12404) | SM/12404 | 572.81 | 1656 | NEW | 9 | Delayed | 0 | 13/09/2022 | 31/03/2024 | 12/09/2023 | 10/04/2023 | 0 | 0
247 | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS (SM/12434) | SM/12434 | 617.73 | 1267 | NEW | 9 | Delayed | 37 | 13/09/2022 | 31/12/2024 | 12/02/2024 | 20/03/2023 | 228.19 | 209.44
248 | BASANTIA AND IT'S ADJOINING MOUJAS PWSS (SM/14451) | SM/14451 | 525.09 | 1581 | NEW | 9 | Delayed | 3 | 20/01/2023 | 31/03/2024 | 12/09/2023 | 20/03/2023 | 16.72 | 16.72
249 | SAHARA AND ADJOINING MOUJAS PWSS (SM/12296) | SM/12296 | 500.78 | 1155 | NEW | 9 | Delayed | 6 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 28/03/2023 | 28.09 | 28.09
250 | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. (SM/12322) | SM/12322 | 556 | 1709 | NEW | 9 | Delayed | 29 | 09/09/2022 | 31/12/2024 | 12/02/2024 | 20/03/2023 | 162.23 | 153.4
251 | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13740) | SM/13740 | 669.57 | 1327 | NEW | 9 | Delayed | 2 | 17/11/2022 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 10.58 | 10.58
252 | HOGALBERYA AND ADJOINING MOUJAS PWSS (SM/12150) | SM/12150 | 762.45 | 2680 | NEW | 9 | Delayed | 0 | 07/09/2022 | 31/03/2024 | 12/09/2023 | 29/12/2022 | 0 | 0
253 | RAMCHANDRAPUR AND ADJOINING MOUJAS (SM/12147) | SM/12147 | 656.72 | 2232 | NEW | 10 | Delayed | 31 | 07/09/2022 | 31/12/2025 | 05/01/2024 | 11/05/2023 | 200.8 | 130.71
254 | BIJAYNAGAR & ADJOINING MOUJAS PWSS (SM/12157) | SM/12157 | 695.66 | 1750 | NEW | 10 | Delayed | 41 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 19/07/2023 | 283.83 | 276.21
255 | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS (SM/11946) | SM/11946 | 984.88 | 4142 | NEW | 10 | Delayed | 6 | 24/08/2022 | 31/12/2025 | 10/01/2024 | 03/05/2023 | 63.44 | 32.13
256 | BAHADURPUR AND ADJOINING MOUJAS PWSS (SM/12169) | SM/12169 | 915.42 | 2470 | NEW | 10 | Delayed | 42 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 12/05/2023 | 383.57 | 379.57
257 | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. (SM/16671) | SM/16671 | 12.39 | 0 | AUGMENTATION | 10 | Delayed | 41 | 14/03/2023 | 31/12/2025 | 13/12/2023 | 23/03/2023 | 5.03 | 0
258 | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS (SM/18303) | SM/18303 | 1458.55 | 4497 | NEW | 10 | Delayed | 22 | 26/06/2023 | 31/12/2025 | 18/04/2024 | 12/07/2023 | 321.31 | 291.77
259 | DKSHIM ANKHA & IT'S ADJOINING MOUJAS (SM/12515) | SM/12515 | 657.71 | 1635 | NEW | 10 | Delayed | 30 | 13/09/2022 | 31/12/2025 | 14/03/2024 | 27/04/2023 | 197.35 | 180.22
260 | MIRJAPUR AND IT'S ADJOINING MOUJAS (SM/12516) | SM/12516 | 515.17 | 1035 | NEW | 10 | Delayed | 10 | 13/09/2022 | 31/12/2025 | 19/04/2024 | 19/04/2023 | 51.89 | 32.5
261 | BIRAMPUT AND ADJOINING MOUJAS PWSS (SM/12497) | SM/12497 | 512.1 | 940 | NEW | 10 | Delayed | 15 | 13/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 79.09 | 65.19
262 | DEPAL AND ADJOINING MOUJAS PWSS (SM/12287) | SM/12287 | 640.15 | 1789 | NEW | 10 | Delayed | 39 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 249.7 | 225.07
263 | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS (SM/12431) | SM/12431 | 827.64 | 2353 | NEW | 10 | Delayed | 17 | 13/09/2022 | 31/12/2025 | 25/01/2024 | 19/07/2023 | 140.42 | 119.62
264 | RUKMINIPUR AND ADJOINING MOUJAS PWSS (SM/12176) | SM/12176 | 739.06 | 1588 | NEW | 10 | Delayed | 32 | 07/09/2022 | 31/12/2025 | 10/05/2024 | 04/05/2023 | 238.03 | 234.51
265 | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS (SM/12816) | SM/12816 | 600.38 | 1500 | NEW | 10 | Delayed | 30 | 20/09/2022 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 179.36 | 164.75
266 | KADUA AND IT'S ADJOINING MOUJAS (SM/13689) | SM/13689 | 741.86 | 2150 | NEW | 10 | Delayed | 19 | 14/11/2022 | 31/12/2025 | 09/01/2024 | 12/05/2023 | 138.67 | 117.29
267 | ITA BARIA & ADJOINING MOUZAS (SM/14042) | SM/14042 | 934.72 | 2068 | NEW | 10 | Delayed | 47 | 12/12/2022 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 436.16 | 432.62
268 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. (SM/15635) | SM/15635 | 58.07 | 0 | AUGMENTATION | 10 | Delayed | 96 | 20/02/2023 | 31/12/2024 | 18/04/2024 | 20/04/2023 | 55.82 | 55.82
269 | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS (SM/12407) | SM/12407 | 545.08 | 1020 | NEW | 10 | Delayed | 32 | 13/09/2022 | 31/12/2025 | 15/04/2024 | 11/04/2023 | 173.16 | 165.31
270 | PANCH BAJARI & ADJOINING MOUJAS PWSS (SM/12173) | SM/12173 | 484.28 | 1015 | NEW | 10 | Delayed | 21 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 10/04/2023 | 103.73 | 99.63
271 | AMRITBERYA AND ADJOINING MOUJAS (SM/15511) | SM/15511 | 1024.73 | 3440 | NEW | 10 | Delayed | 19 | 16/02/2023 | 31/12/2024 | 18/04/2024 | 04/05/2023 | 190.71 | 190.71
272 | URURI AND ADJOINING MOUJAS PWSS (SM/12166) | SM/12166 | 816.68 | 2233 | NEW | 10 | Delayed | 24 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 10/03/2023 | 199.09 | 180.37
273 | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS (SM/13856) | SM/13856 | 227.92 | 477 | NEW | 10 | Delayed | 5 | 25/11/2022 | 31/12/2025 | 29/04/2024 | 20/03/2023 | 11.33 | 2.94
274 | BASUDEVBERYA AND ADJOINING MOUJAS PWSS (SM/12297) | SM/12297 | 541.09 | 1064 | NEW | 10 | Delayed | 33 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 10/03/2023 | 180.88 | 174.27
275 | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS (SM/12130) | SM/12130 | 411.46 | 1566 | NEW | 10 | Delayed | 6 | 07/09/2022 | 31/12/2025 | 29/04/2024 | 04/05/2023 | 26.59 | 8.11
276 | BAINCHA AND IT'S ADJOINING MOUJAS PWSS (SM/14455) | SM/14455 | 412.43 | 700 | NEW | 10 | Delayed | 27 | 20/01/2023 | 31/12/2025 | 14/03/2024 | 28/03/2023 | 112.85 | 101.25
277 | TULIA AND ADJOINING MOUJAS PWSS (SM/15037) | SM/15037 | 572.93 | 2059 | NEW | 10 | Delayed | 6 | 04/02/2023 | 31/12/2025 | 18/04/2024 | 27/03/2023 | 35.85 | 17.95
278 | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) (SM/16466) | SM/16466 | 39.56 | 305 | RETROFITTING | 10 | Delayed | 65 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 19/04/2023 | 25.66 | 25.66
279 | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) (SM/16946) | SM/16946 | 85.63 | 0 | AUGMENTATION | 10 | Delayed | 59 | 16/03/2023 | 31/03/2024 | 12/09/2023 | 19/05/2023 | 50.65 | 50.65
280 | PANUSI AND ADJOINING MOUJAS PWSS (SM/12506) | SM/12506 | 788.16 | 2037 | NEW | 10 | Delayed | 40 | 13/09/2022 | 31/12/2025 | 06/03/2024 | 27/04/2023 | 313.52 | 257.05
281 | PANCHET AND ADJOINING MOUJAS PWSS (SM/12170) | SM/12170 | 897.82 | 1919 | NEW | 10 | Delayed | 1 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 10.97 | 0
282 | PURBA NUKHA AND ADJOINING MOUJAS (SM/14742) | SM/14742 | 668.28 | 2344 | NEW | 10 | Delayed | 1 | 31/01/2023 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 6.37 | 2.98
283 | Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme. (SM/16662) | SM/16662 | 12.39 | 0 | AUGMENTATION | 10 | On track | 34 | 14/03/2023 | 31/12/2025 | 05/04/2024 | 15/03/2023 | 4.22 | 0
284 | KANTHI BARI AND ADJOINING MOUJAS PWSS (SM/12289) | SM/12289 | 795.33 | 1276 | NEW | 10 | Delayed | 40 | 09/09/2022 | 31/12/2025 | 10/05/2024 | 31/12/2022 | 321.41 | 305.65
285 | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. (SM/12484) | SM/12484 | 482.07 | 1463 | NEW | 10 | Delayed | 6 | 13/09/2022 | 31/12/2025 | 11/03/2024 | 20/03/2023 | 26.78 | 0
286 | AGAR & ADJOINING MOUJAS PWSS (SM/12131) | SM/12131 | 388.58 | 832 | NEW | 10 | Delayed | 6 | 07/09/2022 | 31/12/2025 | 29/04/2024 | 31/05/2023 | 23.99 | 0
287 | JAHANABAD AND IT'S ADJOINING MOUJAS (SM/12813) | SM/12813 | 974.08 | 2411 | NEW | 10 | Delayed | 30 | 20/09/2022 | 31/03/2024 | 06/11/2023 | 04/05/2023 | 290.39 | 290.39
288 | KHAGA AND IT'S ADJOINING MOUJAS PWSS (SM/12504) | SM/12504 | 764.31 | 1806 | NEW | 10 | Delayed | 16 | 13/09/2022 | 31/12/2025 | 03/05/2024 | 20/03/2023 | 124.68 | 121.81
289 | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS (SM/13694) | SM/13694 | 625.23 | 1365 | NEW | 10 | Delayed | 45 | 14/11/2022 | 31/12/2025 | 18/04/2024 | 24/07/2023 | 282.79 | 274.23
290 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) (SM/16458) | SM/16458 | 170.2 | 675 | AUGMENTATION | 11 | Delayed | 4 | 03/03/2023 | 31/03/2024 | 08/08/2023 | 27/03/2023 | 7.52 | 7.52
291 | ERENDA AND ADJOINING MOUJAS PWSS (SM/12298) | SM/12298 | 697.48 | 1749 | NEW | 11 | Delayed | 12 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 84.37 | 80.07
292 | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12151) | SM/12151 | 687.4 | 2338 | NEW | 11 | Delayed | 5 | 07/09/2022 | 31/12/2025 | 25/01/2024 | 02/05/2023 | 32.09 | 21.48
293 | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11949) | SM/11949 | 71.08 | 0 | AUGMENTATION | 11 | Delayed | 17 | 24/08/2022 | 31/12/2025 | 15/04/2024 | 10/05/2023 | 11.77 | 2.11
294 | GOYALDA & ADJOINING MOUZAS PWSS (SM/12155) | SM/12155 | 579.91 | 1582 | NEW | 11 | Delayed | 30 | 07/09/2022 | 31/12/2025 | 13/12/2023 | 29/12/2022 | 171.31 | 129.17
295 | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/14845) | SM/14845 | 66.74 | 0 | AUGMENTATION | 12 | Delayed | 35 | 03/02/2023 | 31/12/2024 | 18/04/2024 | 10/02/2023 | 23.66 | 23.66
296 | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16206) | SM/16206 | 74.78 | 0 | AUGMENTATION | 12 | Delayed | 46 | 24/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 34.7 | 34.7
297 | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17194) | SM/17194 | 161.69 | 0 | AUGMENTATION | 13 | Delayed | 35 | 15/03/2023 | 31/12/2025 | 21/02/2024 | 06/04/2023 | 57.17 | 35.83
298 | MAYACHAR AND ADJOINING MOUJAS PWSS (SM/12281) | SM/12281 | 575.5 | 1306 | NEW | 13 | Delayed | 31 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 19/04/2023 | 177.23 | 147.07
299 | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16205) | SM/16205 | 75.38 | 0 | AUGMENTATION | 14 | Delayed | 51 | 24/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 38.24 | 25.43
300 | AMARPUR & ADJOINING MOUZAS (SM/12132) | SM/12132 | 537.37 | 1297 | NEW | 14 | Delayed | 4 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 28/03/2023 | 21.29 | 0
301 | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16204) | SM/16204 | 76.08 | 0 | AUGMENTATION | 14 | Delayed | 46 | 24/02/2023 | 31/12/2023 | 11/09/2023 | 25/04/2023 | 35.22 | 35.22
302 | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11553) | SM/11553 | 944.76 | 4374 | AUGMENTATION | 14 | Delayed | 37 | 22/07/2022 | 31/12/2025 | 08/09/2023 | 01/02/2022 | 349.51 | 340.92
303 | JAMUASHANKARPUR PWSS (SM/14694) | SM/14694 | 344.23 | 312 | NEW | 14 | Delayed | 4 | 31/01/2023 | 31/12/2024 | 18/04/2024 | 20/03/2023 | 14.98 | 14.98
304 | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. (SM/14837) | SM/14837 | 704.17 | 2069 | AUGMENTATION | 14 | Delayed | 23 | 03/02/2023 | 31/12/2025 | 27/11/2023 | 27/02/2023 | 160.64 | 148.37
305 | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) (SM/13238) | SM/13238 | 143.18 | 364 | RETROFITTING | 14 | Delayed | 31 | 14/10/2022 | 31/03/2024 | 14/09/2023 | 16/09/2022 | 44.59 | 44.59
306 | KANCHANPUR AND ADJOINING MOUJAS PWSS (SM/12403) | SM/12403 | 584.24 | 1704 | NEW | 15 | Delayed | 29 | 13/09/2022 | 31/12/2025 | 09/05/2024 | 20/03/2023 | 170.69 | 150.65
307 | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS (SM/12129) | SM/12129 | 582.43 | 2545 | NEW | 15 | Delayed | 47 | 07/09/2022 | 31/12/2025 | 14/12/2023 | 03/05/2023 | 272.05 | 248.92
308 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA (SM/16470) | SM/16470 | 59.08 | 851 | RETROFITTING | 15 | Delayed | 85 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 19/04/2023 | 50.36 | 50.36
309 | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) (SM/12268) | SM/12268 | 1409.77 | 6014 | AUGMENTATION | 15 | Delayed | 43 | 09/09/2022 | 31/12/2024 | 18/04/2024 | 28/01/2022 | 611.75 | 498.63
310 | BALGOBINDAPUR & ADJOINING MOUZAS (SM/12143) | SM/12143 | 879.41 | 2138 | NEW | 15 | Delayed | 5 | 07/09/2022 | 31/12/2025 | 23/04/2024 | 29/12/2022 | 46.18 | 0
311 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). (SM/12364) | SM/12364 | 1068.67 | 5100 | AUGMENTATION | 15 | Delayed | 44 | 13/09/2022 | 31/12/2025 | 31/10/2023 | 22/09/2022 | 471.09 | 471.09
312 | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS (SM/15848) | SM/15848 | 241.71 | 227 | NEW | 15 | Delayed | 11 | 20/02/2023 | 31/12/2025 | 18/04/2024 | 25/04/2023 | 27.31 | 27.31
313 | Augmentation of Ramnagar (Zone-II) PWSS (SM/12486) | SM/12486 | 889.59 | 2941 | AUGMENTATION | 15 | Delayed | 33 | 13/09/2022 | 31/12/2025 | 09/01/2024 | 19/01/2023 | 295.61 | 268.83
314 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. (SM/09022) | SM/09022 | 548.34 | 0 | SUPPORT-M&E | 15 | Delayed | 0 | 30/10/2021 | 31/03/2024 | 05/10/2023 | 22/08/2022 | 0 | 0
315 | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/16941) | SM/16941 | 448.63 | 896 | NEW | 16 | Delayed | 2 | 16/03/2023 | 31/03/2024 | 12/09/2023 | 05/04/2023 | 10.62 | 10.62
316 | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte (SM/17173) | SM/17173 | 448.63 | 840 | NEW | 16 | Delayed | 64 | 16/03/2023 | 31/03/2024 | 12/09/2023 | 05/04/2023 | 286.62 | 284.36
317 | Augmentation of Ramnagar (Zone-I) PWSS (SM/12485) | SM/12485 | 835.22 | 3086 | AUGMENTATION | 18 | Delayed | 22 | 13/09/2022 | 31/12/2023 | 14/09/2023 | 19/01/2023 | 180.2 | 175.53
318 | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS (SM/12291) | SM/12291 | 717.02 | 1648 | NEW | 18 | Delayed | 24 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 31/12/2022 | 169.99 | 166.29
319 | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/11896) | SM/11896 | 62.49 | 0 | AUGMENTATION | 19 | Delayed | 15 | 18/08/2022 | 31/12/2025 | 15/04/2024 | 20/03/2023 | 9.66 | 0
320 | PADIMA AND ADJOINING MOUJAS PWSS (SM/12430) | SM/12430 | 460.25 | 960 | NEW | 19 | Delayed | 29 | 13/09/2022 | 31/12/2025 | 29/04/2024 | 20/03/2023 | 134.16 | 100.23
321 | PACHAHRI & ADJOINING MOUJAS PWSS (SM/12292) | SM/12292 | 614.09 | 2014 | NEW | 19 | Delayed | 37 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 14/03/2023 | 224.71 | 217.46
322 | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) (SM/16465) | SM/16465 | 122.31 | 0 | AUGMENTATION | 20 | Delayed | 10 | 03/03/2023 | 31/12/2025 | 13/03/2024 | 27/03/2023 | 11.77 | 0
323 | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. (SM/12482) | SM/12482 | 1000.8 | 2478 | NEW | 20 | Delayed | 37 | 13/09/2022 | 31/12/2025 | 06/11/2023 | 20/04/2023 | 372.96 | 344.65
324 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II (SM/10594) | SM/10594 | 819.79 | 2508 | AUGMENTATION | 20 | Delayed | 24 | 18/04/2022 | 31/12/2025 | 31/08/2023 | 14/01/2022 | 199.76 | 173.95
325 | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer under Tamluk Division, PHE Dte. (SM/13369) | SM/13369 | 56.79 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 20 | Delayed | 0 | 19/10/2022 | 31/03/2024 | 05/10/2023 |  | 0 | 0
326 | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/14844) | SM/14844 | 62.78 | 0 | AUGMENTATION | 21 | Delayed | 60 | 03/02/2023 | 31/12/2025 | 29/04/2024 | 06/04/2023 | 37.59 | 26.5
327 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11471) | SM/11471 | 745.37 | 0 | AUGMENTATION | 22 | Delayed | 35 | 14/07/2022 | 31/12/2025 | 03/10/2023 | 22/11/2022 | 262.31 | 262.31
328 | Piped Water Supply Scheme for Sankarpur Zone-I (SM/18766) | SM/18766 | 370.29 | 486 | AUGMENTATION | 23 | On track | 10 | 23/08/2023 | 31/12/2025 | 18/04/2024 | 28/11/2022 | 35.55 | 27.72
329 | KAPASDA & IT'S ADJOINING MOUJAS PWSS (SM/13692) | SM/13692 | 778.74 | 1475 | NEW | 24 | Delayed | 14 | 14/11/2022 | 31/03/2024 | 03/11/2023 | 12/05/2023 | 111.7 | 111.7
330 | MANIKJOR AND ADJOINING MOUJAS PWSS (SM/12171) | SM/12171 | 927.42 | 2206 | NEW | 24 | Delayed | 19 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 12/05/2023 | 180.62 | 180.62
331 | SIMULYA & IT'S ADJOINING MOUJAS PWSS (SM/12492) | SM/12492 | 917.62 | 2740 | NEW | 24 | Delayed | 30 | 13/09/2022 | 31/12/2025 | 03/05/2024 | 04/05/2023 | 274.61 | 259.88
332 | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11860) | SM/11860 | 106.95 | 0 | AUGMENTATION | 25 | On track | 40 | 17/08/2022 | 31/12/2025 | 19/03/2024 | 18/08/2022 | 42.55 | 29.11
333 | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. (SM/11887) | SM/11887 | 57.27 | 0 | AUGMENTATION | 25 | Delayed | 46 | 17/08/2022 | 31/12/2025 | 14/09/2023 | 24/11/2022 | 26.3 | 16.64
334 | AJAYA & ADJOINING MOUJAS PWSS (SM/12174) | SM/12174 | 817.13 | 1847 | NEW | 25 | On track | 43 | 07/09/2022 | 31/12/2025 | 09/05/2024 | 17/07/2023 | 347.94 | 323.85
335 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) (SM/16468) | SM/16468 | 34.18 | 545 | RETROFITTING | 25 | Delayed | 81 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 19/04/2023 | 27.83 | 27.83
336 | MADHYA HINGLI AND ADJOINING MOUJAS PWSS (SM/12498) | SM/12498 | 767.33 | 1757 | NEW | 25 | Delayed | 28 | 13/09/2022 | 31/12/2025 | 18/04/2024 | 10/04/2023 | 211.73 | 190.57
337 | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/11612) | SM/11612 | 69.8 | 0 | AUGMENTATION | 27 | Delayed | 40 | 26/07/2022 | 31/12/2025 | 08/02/2024 | 18/03/2021 | 28 | 15.35
338 | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS (SM/12406) | SM/12406 | 1061.78 | 2186 | NEW | 27 | On track | 41 | 13/09/2022 | 31/12/2025 | 05/01/2024 | 31/12/2022 | 433.97 | 406.98
339 | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS (SM/12517) | SM/12517 | 743.4 | 2007 | NEW | 29 | On track | 4 | 13/09/2022 | 31/12/2025 | 06/03/2024 | 20/03/2023 | 26.11 | 0
340 | GULURI AND IT'S ADJOING MOUJAS (SM/13888) | SM/13888 | 533.49 | 1376 | NEW | 29 | Delayed | 23 | 25/11/2022 | 31/12/2025 | 18/04/2024 | 17/04/2023 | 122.48 | 117.63
341 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) (SM/11554) | SM/11554 | 742.35 | 5512 | AUGMENTATION | 30 | Delayed | 58 | 22/07/2022 | 31/12/2025 | 06/11/2023 | 18/01/2021 | 431.54 | 408.1
342 | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme. (SM/16665) | SM/16665 | 12.39 | 0 | AUGMENTATION | 30 | Delayed | 55 | 14/03/2023 | 31/12/2025 | 05/09/2023 | 23/03/2023 | 6.77 | 6.77
343 | Solarization of grid connected pumping installation at Kotbar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17787) | SM/17787 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 23/02/2024 | 29/03/2023 | 0 | 0
344 | Solarization of grid connected pumping installation at Bajkul, Zone-I, Zone-II & Zone-III PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17359) | SM/17359 | 24.91 | 0 | SOLARISATION | 30 | On track | 0 | 15/03/2023 | 31/12/2025 | 27/03/2024 | 23/03/2023 | 0 | 0
345 | Solarization of grid connected pumping installation at Dariapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17340) | SM/17340 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 15/03/2023 | 31/12/2025 | 21/03/2024 | 23/03/2023 | 0 | 0
346 | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. (SM/12177) | SM/12177 | 154.98 | 2657 | RETROFITTING | 30 | Delayed | 52 | 07/09/2022 | 31/12/2024 | 18/04/2024 | 01/11/2022 | 81.24 | 81.24
347 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) (SM/16453) | SM/16453 | 115.08 | 1321 | RETROFITTING | 30 | Delayed | 22 | 03/03/2023 | 31/03/2024 | 19/07/2023 | 08/06/2023 | 25.27 | 8.14
348 | Solarization of grid connected pumping installation at Srirampur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17715) | SM/17715 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/03/2024 | 29/03/2023 | 0 | 0
349 | Solarization of grid connected pumping installation at Habichak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17781) | SM/17781 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 23/02/2024 | 29/03/2023 | 0 | 0
350 | Solarization of grid connected pumping installation at Gholpukuria, Zone-I PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17722) | SM/17722 | 16.61 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 16/04/2024 | 29/03/2023 | 0 | 0
351 | Solarization of grid connected pumping installation at Paramanandapur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17794) | SM/17794 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 19/03/2024 | 29/03/2023 | 0 | 0
352 | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) (SM/16467) | SM/16467 | 72.07 | 319 | RETROFITTING | 30 | Delayed | 79 | 03/03/2023 | 31/03/2024 | 12/09/2023 | 19/04/2023 | 57.26 | 57.26
353 | Solarization of grid connected pumping installation at Mahammadpur (Bhagwanpur-I) PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17790) | SM/17790 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 15/04/2024 | 29/03/2023 | 0 | 0
354 | Solarization of grid connected pumping installation at Muradpur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17753) | SM/17753 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 23/02/2024 | 29/03/2023 | 0 | 0
355 | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. (SM/12303) | SM/12303 | 135.48 | 2340 | RETROFITTING | 30 | Delayed | 51 | 09/09/2022 | 31/03/2024 | 12/09/2023 | 17/02/2023 | 68.75 | 68.75
356 | Solarization of grid connected pumping installation at Saripur PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17780) | SM/17780 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 23/02/2024 | 29/03/2023 | 0 | 0
357 | Solarization of grid connected pumping installation at Thenkuachak Zone-I & Zone-II PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17746) | SM/17746 | 16.61 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 15/04/2024 | 29/03/2023 | 0 | 0
358 | Solarization of grid connected pumping installation at Simulia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17748) | SM/17748 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 17/03/2023 | 31/12/2025 | 23/02/2024 | 29/03/2023 | 0 | 0
359 | Solarization of grid connected pumping installation at Baharchandberya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17315) | SM/17315 | 8.3 | 0 | SOLARISATION | 30 | On track | 0 | 15/03/2023 | 31/12/2025 | 23/02/2024 | 23/03/2023 | 0 | 0
360 | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (SM/09021) | SM/09021 | 43.76 | 0 | SUPPORT-WQMSP | 30 | Delayed | 0 | 30/10/2021 | 31/12/2023 | 05/10/2023 | 25/11/2021 | 0 | 0
361 | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. (SM/11816) | SM/11816 | 89.61 | 0 | SUPPORT-WQMSP | 30 | Delayed | 0 | 16/08/2022 | 31/03/2024 | 05/10/2023 | 30/12/2020 | 0 | 0
362 | SAR BERYA AND ADJOINING MOUJAS PWSS (SM/13688) | SM/13688 | 479.68 | 875 | NEW | 31 | Delayed | 38 | 14/11/2022 | 31/12/2025 | 07/12/2023 | 28/02/2023 | 183.81 | 163.44
363 | BAMANPUR AND ADJOINING MOUJAS PWSS (SM/12493) | SM/12493 | 606.04 | 1362 | NEW | 31 | Delayed | 23 | 13/09/2022 | 31/12/2025 | 26/04/2024 | 20/04/2023 | 138.06 | 128
364 | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/15036) | SM/15036 | 242.53 | 0 | AUGMENTATION | 31 | Delayed | 41 | 04/02/2023 | 31/12/2025 | 14/12/2023 | 06/04/2023 | 99.74 | 75.89
365 | BANCHBERA AND ITS ADJOINING MOUJAS PWSS (SM/16200) | SM/16200 | 197.46 | 147 | NEW | 32 | On track | 38 | 23/02/2023 | 31/12/2025 | 25/04/2024 | 19/04/2023 | 74.09 | 47.02
366 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) (SM/10590) | SM/10590 | 585.68 | 4830 | AUGMENTATION | 32 | Delayed | 53 | 18/04/2022 | 31/12/2023 | 14/09/2023 | 27/01/2022 | 308.78 | 308.78
367 | JAMITTA & ADJOINING MOUZAS (SM/12137) | SM/12137 | 373.67 | 1163 | NEW | 32 | Delayed | 20 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 15/03/2023 | 75.9 | 50.2
368 | DEULI & IT'S ADJOINING MOUJAS PWSS (SM/13744) | SM/13744 | 725.58 | 1586 | NEW | 32 | On track | 41 | 17/11/2022 | 31/12/2025 | 14/03/2024 | 20/03/2023 | 299.74 | 291.5
369 | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I (SM/10725) | SM/10725 | 1006.09 | 3032 | AUGMENTATION | 33 | Delayed | 33 | 18/05/2022 | 31/03/2024 | 12/06/2023 | 12/07/2022 | 334.39 | 334.39
370 | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS (SM/13741) | SM/13741 | 357.16 | 580 | NEW | 33 | Delayed | 26 | 17/11/2022 | 31/12/2024 | 12/03/2024 | 30/10/2023 | 91.15 | 77.76
371 | KAINARA & IT'S ADJOING MOUJAS (SM/12514) | SM/12514 | 784.6 | 2233 | NEW | 34 | On track | 38 | 13/09/2022 | 31/12/2025 | 22/03/2024 | 20/03/2023 | 296.67 | 290.21
372 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) (SM/10589) | SM/10589 | 980.6 | 0 | AUGMENTATION | 35 | Delayed | 21 | 18/04/2022 | 31/12/2023 | 12/06/2023 | 07/09/2022 | 202.83 | 131.76
373 | Solarization of grid connected pumping installation at Bara Subarna Nagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17334) | SM/17334 | 8.3 | 0 | SOLARISATION | 35 | On track | 0 | 15/03/2023 | 31/12/2025 | 30/10/2023 | 23/03/2023 | 0 | 0
374 | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11474) | SM/11474 | 997.01 | 6217 | AUGMENTATION | 35 | Delayed | 51 | 14/07/2022 | 31/12/2025 | 17/01/2024 | 03/02/2022 | 506.31 | 493.35
375 | Solarization of grid connected pumping installation at Junbani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17718) | SM/17718 | 8.3 | 0 | SOLARISATION | 35 | On track | 0 | 17/03/2023 | 31/12/2025 | 30/10/2023 | 29/03/2023 | 0 | 0
376 | Solarization of grid connected pumping installation at Chandiveti PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17339) | SM/17339 | 8.3 | 0 | SOLARISATION | 35 | On track | 0 | 15/03/2023 | 31/12/2025 | 30/10/2023 | 23/03/2023 | 0 | 0
377 | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. (SM/11613) | SM/11613 | 68.66 | 0 | AUGMENTATION | 35 | Delayed | 0 | 26/07/2022 | 31/12/2023 | 12/06/2023 | 18/08/2022 | 0 | 0
378 | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). (SM/11615) | SM/11615 | 915.35 | 3857 | AUGMENTATION | 35 | Delayed | 19 | 26/07/2022 | 31/12/2025 | 02/08/2023 | 22/09/2022 | 170.74 | 160.31
379 | Annual Procurement of Chemicals, Consumables, Glassware & A.M.C. of Computers of Different Water Testing Laboratories under Tamluk Division, PHE Dte. (SM/11710) | SM/11710 | 146.89 | 0 | SUPPORT-WQMSP | 35 | Delayed | 0 | 03/08/2022 | 31/03/2024 | 05/10/2023 | 10/05/2022 | 0 | 0
380 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) (SM/10592) | SM/10592 | 903.71 | 0 | AUGMENTATION | 36 | Delayed | 36 | 18/04/2022 | 31/12/2023 | 14/09/2023 | 23/08/2022 | 329.2 | 328.25
381 | UTTAR SAUTANCHAK Piped Water Supply Scheme. (SM/14741) | SM/14741 | 299.47 | 461 | NEW | 36 | On track | 0 | 31/01/2023 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 0.87 | 0
382 | Augmentation of Ground water Based Betkundu Water Supply Scheme (SM/11206) | SM/11206 | 1317.43 | 5997 | AUGMENTATION | 38 | Delayed | 59 | 08/06/2022 | 31/12/2025 | 19/03/2024 | 11/01/2022 | 771.94 | 767.1
383 | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/17193) | SM/17193 | 80.74 | 0 | AUGMENTATION | 38 | On track | 25 | 15/03/2023 | 31/12/2025 | 07/09/2023 | 25/04/2023 | 20.25 | 20.25
384 | BADALPUR AND IT'S ADJOINING MOUJAS (SM/13887) | SM/13887 | 381.66 | 635 | NEW | 38 | On track | 52 | 25/11/2022 | 31/12/2025 | 12/02/2024 | 20/03/2023 | 200.06 | 175.54
385 | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16938) | SM/16938 | 80.74 | 0 | AUGMENTATION | 38 | On track | 43 | 16/03/2023 | 31/12/2025 | 31/10/2023 | 25/04/2023 | 34.39 | 34.39
386 | GURGRAM & ADJOINING MOUZAS (SM/18311) | SM/18311 | 1027.99 | 2897 | NEW | 39 | On track | 64 | 26/06/2023 | 31/12/2025 | 18/04/2024 | 25/07/2023 | 655.6 | 621.67
387 | Solarization of grid connected pumping installation at Surface Water Based Water Supply Scheme for Panskura-II Block of Purba Medinipur District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17648) | SM/17648 | 107.96 | 0 | SOLARISATION | 39 | On track | 0 | 22/03/2023 | 31/12/2025 | 27/03/2024 | 29/03/2023 | 0 | 0
388 | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS (SM/12286) | SM/12286 | 776 | 2130 | NEW | 39 | On track | 48 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 12/05/2023 | 372.5 | 366.67
389 | GAR BHERA & ADJOINING MOUZAS (SM/12159) | SM/12159 | 596.45 | 1275 | NEW | 39 | On track | 44 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 10/04/2023 | 262.58 | 204.83
390 | GATHRA AND ADJOINING MOUJAS PWSS (SM/12299) | SM/12299 | 627.78 | 3418 | NEW | 39 | On track | 48 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 17/04/2023 | 299.53 | 288.11
391 | Solarization of grid connected pumping installation at Guria PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17294) | SM/17294 | 8.3 | 0 | SOLARISATION | 40 | On track | 0 | 15/03/2023 | 31/12/2025 | 08/04/2024 | 23/03/2023 | 0 | 0
392 | Solarization of grid connected pumping installation at Amtalia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17366) | SM/17366 | 8.3 | 0 | SOLARISATION | 40 | On track | 0 | 15/03/2023 | 31/12/2025 | 21/03/2024 | 23/03/2023 | 0 | 0
393 | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. (SM/16655) | SM/16655 | 12.39 | 0 | AUGMENTATION | 40 | On track | 0 | 14/03/2023 | 31/12/2025 | 03/10/2023 | 23/03/2023 | 0.01 | 0.01
394 | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme (SM/16658) | SM/16658 | 12.39 | 0 | AUGMENTATION | 40 | On track | 84 | 14/03/2023 | 31/12/2025 | 09/02/2024 | 23/03/2023 | 10.44 | 0
395 | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme. (SM/16661) | SM/16661 | 12.39 | 0 | AUGMENTATION | 40 | On track | 80 | 14/03/2023 | 31/12/2025 | 09/02/2024 | 23/03/2023 | 9.89 | 0
396 | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme. (SM/16670) | SM/16670 | 12.39 | 0 | AUGMENTATION | 40 | On track | 47 | 14/03/2023 | 31/12/2025 | 27/11/2023 | 23/03/2023 | 5.82 | 5.82
397 | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme. (SM/16659) | SM/16659 | 12.39 | 0 | AUGMENTATION | 40 | On track | 85 | 14/03/2023 | 31/12/2025 | 12/02/2024 | 23/03/2023 | 10.53 | 0
398 | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme. (SM/16653) | SM/16653 | 12.39 | 0 | AUGMENTATION | 40 | On track | 44 | 14/03/2023 | 31/12/2025 | 08/04/2024 | 23/03/2023 | 5.47 | 0
399 | Solarization of grid connected pumping installation at Arjunnagar PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17348) | SM/17348 | 8.3 | 0 | SOLARISATION | 40 | On track | 0 | 15/03/2023 | 31/12/2025 | 03/04/2024 | 23/03/2023 | 0 | 0
400 | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. (SM/16390) | SM/16390 | 161.69 | 0 | AUGMENTATION | 40 | On track | 27 | 28/02/2023 | 31/12/2025 | 09/08/2023 | 06/04/2023 | 44.39 | 44.39
401 | Solarization of grid connected pumping installation at Argoal PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17332) | SM/17332 | 8.3 | 0 | SOLARISATION | 40 | On track | 0 | 15/03/2023 | 31/12/2025 | 03/05/2024 | 23/03/2023 | 0 | 0
402 | Solarization of grid connected pumping installation at Dakshin Gumai PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17336) | SM/17336 | 8.3 | 0 | SOLARISATION | 40 | On track | 0 | 15/03/2023 | 31/12/2025 | 15/04/2024 | 23/03/2023 | 0 | 0
403 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) (SM/10591) | SM/10591 | 703.33 | 0 | AUGMENTATION | 40 | Delayed | 21 | 18/04/2022 | 31/12/2023 | 12/06/2023 | 14/10/2022 | 149.26 | 149.26
404 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II (SM/12490) | SM/12490 | 662.45 | 2244 | AUGMENTATION | 42 | On track | 47 | 13/09/2022 | 31/12/2025 | 27/11/2023 | 08/02/2022 | 311.22 | 281.16
405 | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS (SM/13695) | SM/13695 | 719.9 | 1991 | NEW | 43 | On track | 25 | 14/11/2022 | 31/12/2025 | 29/04/2024 | 02/05/2023 | 181.83 | 165
406 | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS (SM/12142) | SM/12142 | 722.2 | 1730 | NEW | 43 | On track | 37 | 07/09/2022 | 31/12/2025 | 11/03/2024 | 10/04/2023 | 268.22 | 254.83
407 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I (SM/12489) | SM/12489 | 712.69 | 2596 | AUGMENTATION | 43 | Delayed | 46 | 13/09/2022 | 31/12/2023 | 06/11/2023 | 08/02/2022 | 327.92 | 311.32
408 | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11470) | SM/11470 | 869.93 | 8505 | AUGMENTATION | 43 | On track | 77 | 14/07/2022 | 31/12/2025 | 07/12/2023 | 05/04/2022 | 672.93 | 672.93
409 | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS (SM/12428) | SM/12428 | 412.24 | 618 | NEW | 43 | On track | 41 | 13/09/2022 | 31/12/2025 | 22/12/2023 | 20/03/2023 | 169.37 | 140.86
410 | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji (SM/09447) | SM/09447 | 663.05 | 2940 | AUGMENTATION | 44 | On track | 41 | 19/11/2021 | 31/12/2025 | 11/03/2024 | 14/01/2022 | 271.95 | 256.52
411 | BARTTAN AND ADJOINING MOUJAS PWSS (SM/12501) | SM/12501 | 1048.66 | 3076 | NEW | 44 | On track | 37 | 13/09/2022 | 31/12/2025 | 06/03/2024 | 04/05/2023 | 385.86 | 379.93
412 | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS (SM/13699) | SM/13699 | 1097.22 | 3181 | NEW | 44 | On track | 35 | 14/11/2022 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 383.02 | 353.52
413 | ILASHPUR AND ADJOINING MOUJAS PWSS (SM/12294) | SM/12294 | 847.64 | 2038 | NEW | 44 | On track | 48 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 405.87 | 386.69
414 | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS (SM/13855) | SM/13855 | 786.94 | 1908 | NEW | 44 | On track | 48 | 25/11/2022 | 31/12/2025 | 09/02/2024 | 12/05/2023 | 381.04 | 372.9
415 | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT KALINDI AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE (SM/16929) | SM/16929 | 166.73 | 0 | SOLARISATION | 45 | On track | 0 | 16/03/2023 | 31/12/2025 | 02/02/2024 | 15/05/2023 | 0 | 0
416 | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. (SM/12310) | SM/12310 | 899.01 | 2095 | NEW | 46 | On track | 36 | 09/09/2022 | 31/12/2025 | 31/10/2023 | 04/05/2023 | 323.08 | 305.61
417 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. (SM/09274) | SM/09274 | 359.88 | 967 | AUGMENTATION | 46 | Delayed | 51 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 182.43 | 182.43
418 | FATEPUR AND ADJOINING MOUJAS PWSS (SM/13687) | SM/13687 | 231 | 377 | NEW | 47 | On track | 38 | 14/11/2022 | 31/12/2025 | 22/12/2023 | 20/04/2023 | 88.25 | 76.25
419 | AJANGECHHYA PIPED WATER SUPPLY SCHEME. (SM/13852) | SM/13852 | 166.59 | 314 | NEW | 47 | On track | 24 | 25/11/2022 | 31/12/2025 | 25/01/2024 | 13/04/2023 | 39.48 | 26.21
420 | KATARI AND ADJOINING MOUJAS PWSS (SM/12815) | SM/12815 | 416.52 | 767 | NEW | 47 | On track | 27 | 20/09/2022 | 31/12/2025 | 25/01/2024 | 20/03/2023 | 113.46 | 102.42
421 | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11859) | SM/11859 | 37.95 | 0 | AUGMENTATION | 47 | On track | 22 | 17/08/2022 | 31/12/2025 | 13/10/2023 | 18/08/2022 | 8.29 | 8.29
422 | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS (SM/11881) | SM/11881 | 595.37 | 2526 | NEW | 47 | On track | 38 | 17/08/2022 | 31/12/2025 | 25/01/2024 | 20/04/2023 | 229.18 | 209.35
423 | BISWANATHPUR PIPED WATER SUPPLY SCHEME. (SM/13850) | SM/13850 | 179.48 | 230 | NEW | 48 | On track | 53 | 25/11/2022 | 31/12/2025 | 22/12/2023 | 20/04/2023 | 95.51 | 91.4
424 | KAYEMGERYA AND ADJOINING MOUJAS PWSS (SM/12167) | SM/12167 | 744.93 | 2055 | NEW | 48 | On track | 41 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 29/12/2022 | 306 | 285.94
425 | HARINAN PWSS & ADJOINING MOUJAS (SM/12152) | SM/12152 | 708.52 | 2360 | NEW | 48 | On track | 63 | 07/09/2022 | 31/12/2025 | 31/08/2023 | 29/12/2022 | 444.39 | 404.81
426 | NAICHHANPUR AND ADJOINING MOUJAS PWSS (SM/12295) | SM/12295 | 593.04 | 1513 | NEW | 48 | On track | 57 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 02/05/2023 | 340.37 | 323.76
427 | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/12279) | SM/12279 | 1684.91 | 4912 | AUGMENTATION | 49 | On track | 71 | 09/09/2022 | 31/12/2025 | 18/04/2024 | 09/12/2022 | 1189.95 | 1161.04
428 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I (SM/12118) | SM/12118 | 1079.89 | 3903 | AUGMENTATION | 49 | On track | 57 | 06/09/2022 | 31/12/2025 | 21/03/2024 | 14/01/2022 | 616.16 | 596.15
429 | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS (SM/13742) | SM/13742 | 694.6 | 1517 | NEW | 49 | On track | 47 | 17/11/2022 | 31/12/2025 | 29/04/2024 | 20/03/2023 | 325.55 | 305.84
430 | DEKHALI AND ADJOINING MOUJAS PWSS (SM/15515) | SM/15515 | 1239.4 | 2820 | NEW | 49 | On track | 50 | 16/02/2023 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 621.51 | 595.32
431 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda (SM/10344) | SM/10344 | 952 | 3155 | AUGMENTATION | 49 | On track | 49 | 16/03/2022 | 31/12/2025 | 15/04/2024 | 14/01/2022 | 468.64 | 454.77
432 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. (SM/10683) | SM/10683 | 1126.18 | 5528 | AUGMENTATION | 50 | Delayed | 69 | 06/05/2022 | 31/12/2023 | 12/06/2023 | 01/12/2021 | 782.27 | 782.27
433 | Solarization of grid connected pumping installation at lakshya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17768) | SM/17768 | 8.3 | 0 | SOLARISATION | 50 | On track | 0 | 17/03/2023 | 31/12/2025 | 10/10/2023 | 29/03/2023 | 0 | 0
434 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. (SM/09283) | SM/09283 | 686.91 | 3478 | AUGMENTATION | 50 | Delayed | 56 | 03/11/2021 | 31/12/2023 | 12/06/2023 | 02/12/2021 | 383.28 | 383.28
435 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) (SM/10664) | SM/10664 | 599.83 | 0 | AUGMENTATION | 50 | Delayed | 4 | 22/04/2022 | 31/12/2023 | 12/06/2023 | 01/11/2022 | 26.36 | 26.36
436 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11473) | SM/11473 | 873.48 | 0 | AUGMENTATION | 50 | On track | 27 | 14/07/2022 | 31/12/2025 | 07/12/2023 | 01/11/2022 | 233.91 | 213.45
437 | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. (SM/10072) | SM/10072 | 581.76 | 1833 | AUGMENTATION | 50 | Delayed | 53 | 27/01/2022 | 31/12/2023 | 12/06/2023 | 14/01/2022 | 306.15 | 306.15
438 | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District (SM/09273) | SM/09273 | 249.69 | 1592 | AUGMENTATION | 50 | Delayed | 28 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 20/01/2022 | 69.05 | 69.05
439 | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. (SM/10393) | SM/10393 | 787.03 | 2729 | AUGMENTATION | 51 | Delayed | 58 | 29/03/2022 | 31/03/2024 | 06/11/2023 | 06/01/2022 | 456.5 | 456.5
440 | PUTPUTIA PWSS (SM/11886) | SM/11886 | 581.53 | 1670 | NEW | 51 | On track | 49 | 17/08/2022 | 31/12/2025 | 13/09/2023 | 10/04/2023 | 287.21 | 247.32
441 | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11549) | SM/11549 | 850.53 | 5686 | AUGMENTATION | 52 | On track | 71 | 22/07/2022 | 31/12/2025 | 14/09/2023 | 03/02/2022 | 600.13 | 590.49
442 | GARABAR PIPED WATER SUPPLY SCHEME. (SM/15850) | SM/15850 | 166.18 | 150 | NEW | 52 | On track | 44 | 20/02/2023 | 31/12/2025 | 18/04/2024 | 19/04/2023 | 72.33 | 56.43
443 | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. (SM/14113) | SM/14113 | 1300.67 | 5920 | AUGMENTATION | 52 | On track | 62 | 02/01/2023 | 31/12/2025 | 18/04/2024 | 07/01/2022 | 809.98 | 809.44
444 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda (SM/10128) | SM/10128 | 1634.61 | 5364 | AUGMENTATION | 53 | On track | 37 | 08/02/2022 | 31/12/2025 | 13/10/2023 | 14/01/2022 | 598.84 | 598.84
445 | Augmentation of Ground Water based Jalpai Water Supply Scheme. (SM/11920) | SM/11920 | 2009.45 | 7890 | AUGMENTATION | 54 | On track | 58 | 22/08/2022 | 31/12/2025 | 16/08/2023 | 05/04/2022 | 1162.18 | 1155.49
446 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II (SM/12488) | SM/12488 | 740.92 | 2338 | AUGMENTATION | 55 | On track | 32 | 13/09/2022 | 31/12/2025 | 06/11/2023 | 21/06/2022 | 236.8 | 220.84
447 | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10681) | SM/10681 | 1073.49 | 6101 | AUGMENTATION | 55 | Delayed | 52 | 06/05/2022 | 31/12/2023 | 12/06/2023 | 01/12/2021 | 554.97 | 554.97
448 | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) (SM/10588) | SM/10588 | 999.73 | 7796 | AUGMENTATION | 56 | On track | 67 | 18/04/2022 | 31/12/2025 | 07/09/2023 | 08/08/2022 | 668.35 | 657.38
449 | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11472) | SM/11472 | 834.19 | 8206 | AUGMENTATION | 56 | Delayed | 71 | 14/07/2022 | 31/03/2024 | 14/09/2023 | 05/04/2022 | 590.84 | 590.84
450 | BRINDABANPUR & ADJOINING MOUJAS PWSS (SM/12148) | SM/12148 | 429.14 | 1023 | NEW | 56 | On track | 40 | 07/09/2022 | 31/12/2025 | 01/02/2024 | 06/06/2023 | 173.34 | 130.29
451 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11469) | SM/11469 | 570.27 | 2587 | AUGMENTATION | 56 | On track | 64 | 14/07/2022 | 31/12/2025 | 09/05/2024 | 06/01/2022 | 363.48 | 352.52
452 | KAKRA & ADJOINING MOUZAS (SM/12138) | SM/12138 | 784.19 | 3218 | NEW | 57 | On track | 65 | 07/09/2022 | 31/12/2025 | 31/10/2023 | 04/05/2023 | 507.76 | 485.79
453 | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11861) | SM/11861 | 43.42 | 0 | AUGMENTATION | 59 | On track | 52 | 17/08/2022 | 31/12/2025 | 05/01/2024 | 18/08/2022 | 22.77 | 11.46
454 | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09402) | SM/09402 | 535.02 | 2132 | AUGMENTATION | 59 | On track | 28 | 17/11/2021 | 31/12/2025 | 05/01/2024 | 02/12/2021 | 147.44 | 133.47
455 | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/12570) | SM/12570 | 1708.39 | 7341 | AUGMENTATION | 59 | On track | 56 | 14/09/2022 | 31/12/2025 | 03/05/2024 | 09/12/2022 | 955.94 | 952.68
456 | Solarization of grid connected pumping installation at Kulbari PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17815) | SM/17815 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2025 | 13/10/2023 | 29/03/2023 | 0 | 0
457 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) (SM/11948) | SM/11948 | 533.3 | 4380 | AUGMENTATION | 60 | Delayed | 70 | 24/08/2022 | 31/12/2023 | 12/06/2023 | 11/01/2022 | 373.72 | 353.66
458 | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. (SM/16666) | SM/16666 | 12.39 | 0 | AUGMENTATION | 60 | On track | 58 | 14/03/2023 | 31/12/2025 | 14/12/2023 | 23/03/2023 | 7.15 | 0
459 | Solarization of grid connected pumping installation at Asadtaliya PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17388) | SM/17388 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 15/03/2023 | 31/12/2025 | 16/10/2023 | 23/03/2023 | 0 | 0
460 | Solarization of grid connected pumping installation at Betkundu PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17298) | SM/17298 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 15/03/2023 | 31/12/2025 | 10/10/2023 | 23/03/2023 | 0 | 0
461 | Solarization of grid connected pumping installation at Begunberia PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17293) | SM/17293 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 15/03/2023 | 31/12/2025 | 16/10/2023 | 23/03/2023 | 0 | 0
462 | Solarization of grid connected pumping installation at Mandarmani PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte (SM/17808) | SM/17808 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2025 | 30/10/2023 | 29/03/2023 | 0 | 0
463 | Solarization of grid connected pumping installation at Kanaidighi PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17736) | SM/17736 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2025 | 06/11/2023 | 29/03/2023 | 0 | 0
464 | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme. (SM/16664) | SM/16664 | 12.39 | 0 | AUGMENTATION | 60 | On track | 58 | 14/03/2023 | 31/12/2025 | 13/12/2023 | 23/03/2023 | 7.15 | 0
465 | Solarization of grid connected pumping installation at Rashikachak PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17720) | SM/17720 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2025 | 13/10/2023 | 29/03/2023 | 0 | 0
466 | Solarization of grid connected pumping installation at Kumirda PWSS in Purba Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. (SM/17816) | SM/17816 | 8.3 | 0 | SOLARISATION | 60 | On track | 0 | 17/03/2023 | 31/12/2025 | 06/11/2023 | 29/03/2023 | 0 | 0
467 | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division (SM/08683) | SM/08683 | 15.07 | 0 | SUPPORT-WQMSP | 60 | Delayed | 0 | 23/08/2021 | 31/12/2023 | 22/05/2023 | 25/08/2021 | 0 | 0
468 | EREKHALI AND ADJOINING MOUJAS PWSS (SM/12139) | SM/12139 | 627.99 | 1713 | NEW | 61 | On track | 38 | 07/09/2022 | 31/12/2025 | 29/04/2024 | 28/02/2023 | 236.54 | 230.28
469 | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09336) | SM/09336 | 556.34 | 1784 | AUGMENTATION | 62 | On track | 68 | 12/11/2021 | 31/12/2025 | 16/10/2023 | 08/02/2022 | 380.42 | 377.18
470 | GOPINATHPUR & ADJOINING MOUZAS (SM/12158) | SM/12158 | 727.42 | 1851 | NEW | 62 | On track | 63 | 07/09/2022 | 31/12/2025 | 18/04/2024 | 04/05/2023 | 460.51 | 438.62
471 | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. (SM/11552) | SM/11552 | 617.59 | 2646 | AUGMENTATION | 63 | On track | 55 | 22/07/2022 | 31/12/2025 | 09/05/2024 | 01/02/2022 | 339.15 | 332.52
472 | MIRJAPUR AND ADJOINING MOUJAS PWSS (SM/12153) | SM/12153 | 939.19 | 2305 | NEW | 63 | On track | 55 | 07/09/2022 | 31/12/2025 | 03/11/2023 | 19/04/2023 | 516.86 | 483.68
473 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS (SM/12140) | SM/12140 | 582.1 | 2038 | NEW | 63 | On track | 31 | 07/09/2022 | 31/12/2025 | 23/02/2024 | 17/04/2023 | 181.94 | 152.78
474 | Augmentation of Suadighi piped water supply scheme. (SM/09919) | SM/09919 | 2222.11 | 6915 | AUGMENTATION | 63 | Delayed | 50 | 10/12/2021 | 31/03/2024 | 06/11/2023 | 31/01/2022 | 1114.54 | 1066.99
475 | Augmentation of Ground Water Based Bagmari Water Supply Scheme (SM/16711) | SM/16711 | 339.13 | 929 | AUGMENTATION | 64 | Delayed | 52 | 14/03/2023 | 31/03/2024 | 03/11/2023 | 20/04/2023 | 175.83 | 175.83
476 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. (SM/10030) | SM/10030 | 1321.6 | 707 | AUGMENTATION | 64 | On track | 70 | 19/01/2022 | 31/12/2025 | 07/12/2023 | 02/12/2021 | 930.87 | 930.29
477 | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS (SM/14456) | SM/14456 | 351.84 | 672 | NEW | 64 | On track | 35 | 20/01/2023 | 31/12/2025 | 18/04/2024 | 20/03/2023 | 122.84 | 114.45
478 | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09913) | SM/09913 | 1104.23 | 6158 | AUGMENTATION | 65 | Delayed | 68 | 10/12/2021 | 31/12/2023 | 12/06/2023 | 02/12/2021 | 749.53 | 749.53
479 | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. (SM/10396) | SM/10396 | 1547.92 | 7163 | AUGMENTATION | 65 | On track | 66 | 29/03/2022 | 31/12/2025 | 14/09/2023 | 19/01/2022 | 1018.11 | 1016.94
480 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. (SM/10682) | SM/10682 | 1414.27 | 5547 | AUGMENTATION | 65 | Delayed | 78 | 06/05/2022 | 31/12/2023 | 14/09/2023 | 01/12/2021 | 1106.1 | 1106.1
481 | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09337) | SM/09337 | 529.85 | 1862 | AUGMENTATION | 65 | On track | 77 | 12/11/2021 | 31/12/2025 | 16/10/2023 | 02/12/2021 | 406.52 | 406.33
482 | BAGMARI AND IT'S ADJOINING MOUJAS PWSS (SM/12429) | SM/12429 | 560.42 | 1230 | NEW | 66 | On track | 58 | 13/09/2022 | 31/12/2025 | 23/11/2023 | 04/05/2023 | 327.56 | 301.52
483 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I (SM/12487) | SM/12487 | 989.31 | 4400 | AUGMENTATION | 67 | Delayed | 22 | 13/09/2022 | 28/02/2024 | 06/11/2023 | 17/06/2022 | 219.27 | 219.27
484 | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (SM/11984) | SM/11984 | 1454.18 | 7156 | AUGMENTATION | 67 | On track | 64 | 01/09/2022 | 31/12/2025 | 09/05/2024 | 03/01/2022 | 931.02 | 909.47
485 | Augmentation of Madhakhali piped water supply scheme. (SM/09920) | SM/09920 | 2333.22 | 7098 | AUGMENTATION | 67 | Delayed | 59 | 10/12/2021 | 31/12/2023 | 03/11/2023 | 31/01/2022 | 1375.34 | 1333.42
486 | Augmentation of Moyna (Zone-II) PWSS (SM/11639) | SM/11639 | 990.17 | 3745 | AUGMENTATION | 68 | On track | 66 | 27/07/2022 | 31/12/2025 | 07/12/2023 | 03/01/2022 | 650.33 | 633.38
487 | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia (SM/12491) | SM/12491 | 745.53 | 3188 | AUGMENTATION | 68 | On track | 41 | 13/09/2022 | 31/12/2025 | 06/11/2023 | 14/01/2022 | 302 | 276.58
488 | Augmentation of Moyna (Zone-I) PWSS (SM/11614) | SM/11614 | 998.4 | 4527 | AUGMENTATION | 69 | On track | 51 | 26/07/2022 | 31/12/2025 | 06/11/2023 | 03/01/2022 | 512.61 | 503
489 | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) (SM/10433) | SM/10433 | 178.42 | 304 | RETROFITTING | 70 | Delayed | 40 | 12/04/2022 | 31/12/2023 | 12/06/2023 | 03/08/2022 | 71.72 | 71.72
490 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) (SM/11617) | SM/11617 | 843.08 | 6291 | AUGMENTATION | 70 | On track | 23 | 26/07/2022 | 31/12/2025 | 02/08/2023 | 02/11/2022 | 194.5 | 181.74
491 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. (SM/10031) | SM/10031 | 1041.15 | 5167 | AUGMENTATION | 70 | Delayed | 76 | 19/01/2022 | 31/12/2023 | 12/06/2023 | 02/12/2021 | 790.2 | 778.89
492 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. (SM/09282) | SM/09282 | 890.9 | 4747 | AUGMENTATION | 70 | Delayed | 72 | 03/11/2021 | 31/12/2023 | 12/06/2023 | 01/12/2021 | 642.6 | 642.6
493 | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) (SM/10125) | SM/10125 | 2077.89 | 9676 | AUGMENTATION | 72 | Delayed | 66 | 08/02/2022 | 31/12/2023 | 03/11/2023 | 05/02/2021 | 1361.51 | 1342.77
494 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme (SM/09448) | SM/09448 | 802.36 | 4327 | AUGMENTATION | 73 | Delayed | 91 | 19/11/2021 | 31/12/2023 | 12/06/2023 | 18/01/2022 | 733.75 | 733.73
495 | JAYNAGAR AND ADJOINING MOUJAS PWSS (SM/12502) | SM/12502 | 773.24 | 2174 | NEW | 74 | On track | 26 | 13/09/2022 | 31/12/2024 | 06/03/2024 | 20/03/2023 | 203.58 | 202.63
496 | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. (SM/11862) | SM/11862 | 69.86 | 0 | AUGMENTATION | 74 | Delayed | 82 | 17/08/2022 | 31/12/2023 | 12/06/2023 | 18/08/2022 | 57.12 | 57.12
497 | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10121) | SM/10121 | 2314.83 | 9661 | AUGMENTATION | 74 | On track | 66 | 08/02/2022 | 31/12/2025 | 06/11/2023 | 08/12/2021 | 1518.65 | 1518.48
498 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II (SM/13716) | SM/13716 | 1060.08 | 3882 | AUGMENTATION | 74 | On track | 39 | 17/11/2022 | 31/12/2025 | 18/04/2024 | 31/08/2022 | 418.36 | 388.63
499 | URDDHABMAL AND ADJOINING MOUJAS PWSS (SM/13698) | SM/13698 | 803.45 | 1797 | NEW | 75 | On track | 36 | 14/11/2022 | 31/12/2025 | 18/04/2024 | 10/04/2023 | 289.4 | 285.43
500 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme (SM/09276) | SM/09276 | 340.42 | 909 | AUGMENTATION | 75 | On track | 43 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 01/12/2021 | 147.46 | 147.46
501 | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. (SM/12300) | SM/12300 | 94.16 | 1841 | RETROFITTING | 75 | On track | 73 | 09/09/2022 | 31/12/2024 | 18/04/2024 | 26/09/2022 | 69.04 | 69.04
502 | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me (SM/16452) | SM/16452 | 110.15 | 610 | RETROFITTING | 75 | Delayed | 72 | 03/03/2023 | 31/12/2023 | 14/09/2023 | 19/04/2023 | 79.22 | 79.22
503 | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme (SM/07098) | SM/07098 | 99.86 | 2000 | RETROFITTING | 75 | On track | 80 | 26/11/2020 | 31/12/2024 | 18/04/2024 | 22/02/2021 | 80 | 63.71
504 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. (SM/09338) | SM/09338 | 685.69 | 3736 | AUGMENTATION | 75 | Delayed | 55 | 12/11/2021 | 31/12/2023 | 12/06/2023 | 02/12/2021 | 378.83 | 378.83
505 | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. (SM/09977) | SM/09977 | 1187.36 | 7229 | AUGMENTATION | 75 | Delayed | 59 | 17/12/2021 | 31/12/2023 | 12/06/2023 | 01/12/2021 | 703.98 | 703.98
506 | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme (SM/09284) | SM/09284 | 739.47 | 2879 | AUGMENTATION | 76 | Delayed | 78 | 03/11/2021 | 31/10/2023 | 14/09/2023 | 01/12/2021 | 579.67 | 579.67
507 | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. (SM/07655) | SM/07655 | 114.11 | 2288 | RETROFITTING | 77 | On track | 55 | 07/01/2021 | 31/12/2024 | 18/04/2024 | 04/02/2021 | 62.66 | 62.21
508 | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (SM/10684) | SM/10684 | 1309.53 | 8284 | AUGMENTATION | 77 | On track | 88 | 06/05/2022 | 31/12/2025 | 14/09/2023 | 01/12/2021 | 1155.41 | 1155.41
509 | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/10593) | SM/10593 | 995.98 | 4937 | AUGMENTATION | 78 | On track | 70 | 18/04/2022 | 31/12/2025 | 05/01/2024 | 21/01/2022 | 695.73 | 680.3
510 | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M (SM/16469) | SM/16469 | 108.21 | 1180 | RETROFITTING | 78 | Delayed | 73 | 03/03/2023 | 31/12/2023 | 14/09/2023 | 19/04/2023 | 79.29 | 79.29
511 | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. (SM/10120) | SM/10120 | 1515.48 | 7239 | AUGMENTATION | 79 | Delayed | 73 | 08/02/2022 | 31/12/2023 | 06/11/2023 | 18/01/2022 | 1112.83 | 1087.45
512 | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block (SM/10432) | SM/10432 | 126.97 | 2488 | RETROFITTING | 80 | Delayed | 0 | 12/04/2022 | 31/03/2024 | 12/06/2023 | 25/04/2022 | 0 | 0
513 | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. (SM/12301) | SM/12301 | 112.8 | 2244 | RETROFITTING | 80 | Delayed | 61 | 09/09/2022 | 31/12/2023 | 05/10/2023 | 26/09/2022 | 68.76 | 68.76
514 | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. (SM/09804) | SM/09804 | 166.66 | 2783 | RETROFITTING | 80 | Delayed | 69 | 01/12/2021 | 31/03/2024 | 12/06/2023 | 19/01/2022 | 115.23 | 113.72
515 | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme (SM/10122) | SM/10122 | 1492.39 | 6387 | AUGMENTATION | 80 | Delayed | 74 | 08/02/2022 | 31/12/2023 | 06/11/2023 | 01/12/2021 | 1110.78 | 1080.14
516 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) (SM/11616) | SM/11616 | 838.08 | 0 | AUGMENTATION | 82 | Delayed | 79 | 26/07/2022 | 31/12/2023 | 05/10/2023 | 02/11/2022 | 660.03 | 660.03
517 | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) (SM/11618) | SM/11618 | 806.74 | 6291 | AUGMENTATION | 84 | Delayed | 98 | 26/07/2022 | 31/03/2024 | 14/09/2023 | 02/11/2022 | 788.49 | 788.49
518 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut (SM/10323) | SM/10323 | 1166.79 | 3895 | AUGMENTATION | 86 | Delayed | 61 | 07/03/2022 | 31/12/2023 | 19/07/2023 | 14/01/2022 | 711.65 | 708.68
519 | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai (SM/09446) | SM/09446 | 710.98 | 2679 | AUGMENTATION | 87 | Delayed | 59 | 19/11/2021 | 31/12/2023 | 12/06/2023 | 06/08/2021 | 416.79 | 416.79
520 | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani (SM/10127) | SM/10127 | 1418.64 | 5256 | AUGMENTATION | 87 | Delayed | 57 | 08/02/2022 | 31/12/2023 | 03/11/2023 | 14/01/2022 | 813.36 | 796.52
521 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara (SM/09288) | SM/09288 | 850.34 | 3398 | AUGMENTATION | 89 | Delayed | 62 | 03/11/2021 | 31/12/2023 | 03/11/2023 | 01/12/2021 | 528.23 | 526.51
522 | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. (SM/09803) | SM/09803 | 120.85 | 2633 | RETROFITTING | 90 | Delayed | 87 | 01/12/2021 | 31/12/2023 | 12/06/2023 | 19/01/2022 | 105 | 104.47
523 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II (SM/08758) | SM/08758 | 17.38 | 220 | RETROFITTING | 90 | On track | 90 | 09/09/2021 | 31/12/2024 | 18/04/2024 | 10/09/2021 | 15.68 | 15.68
524 | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda (SM/09445) | SM/09445 | 822.22 | 3171 | AUGMENTATION | 90 | Delayed | 62 | 19/11/2021 | 31/12/2023 | 06/11/2023 | 14/01/2022 | 506.34 | 505.96
525 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur (SM/10342) | SM/10342 | 800.14 | 2162 | AUGMENTATION | 90 | On track | 50 | 14/03/2022 | 31/12/2025 | 13/12/2023 | 14/01/2022 | 399.66 | 399.66
526 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai (SM/09287) | SM/09287 | 349.47 | 986 | AUGMENTATION | 90 | Delayed | 76 | 03/11/2021 | 31/03/2024 | 12/09/2023 | 02/12/2021 | 267.01 | 266.94
527 | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block (SM/07658) | SM/07658 | 178.36 | 3662 | RETROFITTING | 90 | On track | 93 | 07/01/2021 | 31/12/2024 | 18/04/2024 | 05/02/2021 | 165.43 | 165.25
528 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. (SM/09285) | SM/09285 | 932.77 | 4622 | AUGMENTATION | 90 | Delayed | 81 | 03/11/2021 | 31/12/2023 | 05/10/2023 | 01/11/2021 | 755.91 | 755.91
529 | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. (SM/10345) | SM/10345 | 43.75 | 13 | RETROFITTING | 90 | Delayed | 8 | 16/03/2022 | 31/12/2023 | 12/06/2023 | 08/03/2022 | 3.52 | 3.52
530 | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09272) | SM/09272 | 366.83 | 2201 | AUGMENTATION | 90 | On track | 80 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 25/01/2022 | 292 | 291.46
531 | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. (SM/09278) | SM/09278 | 678.53 | 3059 | AUGMENTATION | 90 | On track | 65 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 442.71 | 437.6
532 | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. (SM/09281) | SM/09281 | 681.09 | 2920 | AUGMENTATION | 90 | Delayed | 88 | 03/11/2021 | 31/12/2023 | 05/10/2023 | 01/12/2021 | 597.79 | 597.79
533 | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. (SM/08759) | SM/08759 | 471.12 | 1600 | RETROFITTING | 90 | On track | 83 | 09/09/2021 | 31/12/2024 | 18/04/2024 | 11/01/2022 | 392.24 | 392.24
534 | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. (SM/09334) | SM/09334 | 704.29 | 2536 | AUGMENTATION | 91 | Delayed | 66 | 12/11/2021 | 31/12/2023 | 06/11/2023 | 02/12/2021 | 463.25 | 463.25
535 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli (SM/09912) | SM/09912 | 1029.45 | 3862 | AUGMENTATION | 91 | Delayed | 64 | 10/12/2021 | 31/12/2023 | 03/11/2023 | 02/12/2021 | 663.68 | 663.68
536 | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09444) | SM/09444 | 726.52 | 2915 | AUGMENTATION | 92 | Delayed | 62 | 19/11/2021 | 31/12/2023 | 06/11/2023 | 17/02/2022 | 452.54 | 450.72
537 | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. (SM/10431) | SM/10431 | 106.97 | 1718 | RETROFITTING | 92 | Delayed | 97 | 12/04/2022 | 31/03/2024 | 12/06/2023 | 31/03/2022 | 103.86 | 103.86
538 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti (SM/10126) | SM/10126 | 1145.17 | 3753 | AUGMENTATION | 93 | On track | 56 | 08/02/2022 | 31/12/2025 | 06/11/2023 | 14/01/2022 | 638.84 | 638.84
539 | Augmentation of Ground Water Based Piped Supply Scheme for Majna (SM/09335) | SM/09335 | 556.85 | 2501 | AUGMENTATION | 94 | Delayed | 65 | 12/11/2021 | 01/04/2024 | 03/11/2023 | 01/12/2021 | 363.55 | 363.55
540 | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. (SM/09800) | SM/09800 | 149.22 | 2550 | RETROFITTING | 95 | Delayed | 71 | 01/12/2021 | 31/12/2023 | 12/06/2023 | 19/01/2022 | 106.19 | 106.19
541 | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. (SM/09275) | SM/09275 | 478.65 | 1878 | AUGMENTATION | 95 | On track | 94 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 449.54 | 449.54
542 | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09279) | SM/09279 | 366.62 | 2139 | AUGMENTATION | 95 | On track | 92 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 338.83 | 338.83
543 | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09277) | SM/09277 | 315.94 | 1586 | AUGMENTATION | 95 | On track | 83 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 262.85 | 262.85
544 | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. (SM/12302) | SM/12302 | 45.03 | 763 | RETROFITTING | 95 | Delayed | 94 | 09/09/2022 | 31/12/2023 | 06/11/2023 | 19/12/2022 | 42.38 | 42.38
545 | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. (SM/09280) | SM/09280 | 445.45 | 2013 | AUGMENTATION | 96 | On track | 52 | 03/11/2021 | 31/12/2024 | 18/04/2024 | 02/12/2021 | 231.26 | 231.26
546 | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) (SM/09286) | SM/09286 | 764.17 | 4335 | AUGMENTATION | 96 | Delayed | 87 | 03/11/2021 | 31/12/2023 | 06/11/2023 | 02/12/2021 | 661.86 | 661.27
547 | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (SM/09914) | SM/09914 | 1060.63 | 4407 | AUGMENTATION | 96 | Delayed | 80 | 10/12/2021 | 31/03/2024 | 03/11/2023 | 02/12/2021 | 843.6 | 843.6
548 | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme (SM/07107) | SM/07107 | 62.75 | 1258 | RETROFITTING | 97 | On track | 97 | 26/11/2020 | 31/12/2024 | 18/04/2024 | 20/01/2021 | 61 | 60.84
549 | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme (SM/07099) | SM/07099 | 99.16 | 2025 | RETROFITTING | 98 | On track | 100 | 26/11/2020 | 31/12/2024 | 18/04/2024 | 11/01/2021 | 99 | 96.25
550 | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) (SM/10647) | SM/10647 | 539.62 | 5157 | AUGMENTATION | 98 | Delayed | 98 | 22/04/2022 | 31/12/2023 | 14/09/2023 | 07/01/2022 | 527.18 | 527.18
551 | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur (SM/07660) | SM/07660 | 169.11 | 3545 | RETROFITTING | 98 | On track | 98 | 07/01/2021 | 31/12/2024 | 18/04/2024 | 25/02/2021 | 165.63 | 164.82
552 | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme (SM/06880) | SM/06880 | 81.66 | 1656 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 22/02/2021 | 79 | 76.77
553 | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme (SM/06882) | SM/06882 | 99.43 | 1950 | RETROFITTING | 100 | 100% Physical | 98 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 22/02/2021 | 97 | 94.28
554 | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS (SM/06890) | SM/06890 | 90.86 | 1842 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 18/12/2020 | 90 | 88.17
555 | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme (SM/06893) | SM/06893 | 75.12 | 1551 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 31/03/2024 | 18/04/2024 | 05/11/2020 | 75 | 72.23
556 | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. (SM/07477) | SM/07477 | 45.95 | 904 | RETROFITTING | 100 | 100% Physical | 93 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 10/02/2021 | 42.75 | 42.75
557 | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block (SM/07478) | SM/07478 | 46.94 | 937 | RETROFITTING | 100 | 100% Physical | 96 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 04/02/2021 | 45.25 | 45.25
558 | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) (SM/08230) | SM/08230 | 11.32 | 150 | RETROFITTING | 100 | 100% Physical | 94 | 09/02/2021 | 31/12/2021 | 12/06/2023 | 22/02/2021 | 10.63 | 10.63
559 | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I (SM/08223) | SM/08223 | 203.44 | 2832 | RETROFITTING | 100 | 100% Physical | 97 | 09/02/2021 | 31/03/2023 | 12/06/2023 | 25/02/2021 | 197.96 | 197.96
560 | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). (SM/09048) | SM/09048 | 37.06 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2023 | 12/06/2023 | 02/11/2021 | 35.66 | 35.66
561 | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) (SM/09056) | SM/09056 | 88.01 | 1600 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 85.36 | 85.36
562 | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, (SM/10434) | SM/10434 | 82 | 200 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/12/2023 | 12/06/2023 | 05/04/2022 | 79.61 | 79.61
563 | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- (SM/08985) | SM/08985 | 119.8 | 0 | DISASTER | 100 | 100% Physical | 0 | 29/10/2021 |  | 05/10/2023 | 01/06/2021 | 0 | 0
564 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X (SM/07117) | SM/07117 | 99.53 | 1905 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 23/12/2020 | 97 | 96.92
565 | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme (SM/07095) | SM/07095 | 88.28 | 1850 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/03/2022 | 12/06/2023 | 21/01/2021 | 86 | 56.88
566 | Rejuvenation to accommodate FHTC under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division PHE Dte Purba Medinipur Phase II (SM/08749) | SM/08749 | 65.32 | 450 | RETROFITTING | 100 | 100% Physical | 95 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 62.26 | 62.26
567 | Retrofitting to accommodate FHTC under JJM in Uttar Charikhia PWSS under Contai I Block (Phase-II). (SM/09047) | SM/09047 | 17.78 | 180 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2023 | 12/06/2023 | 02/11/2021 | 17.26 | 17.26
568 | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme (SM/06881) | SM/06881 | 99.51 | 1960 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2022 | 12/06/2023 | 05/11/2020 | 96.5 | 95.48
569 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XIII (SM/07118) | SM/07118 | 99.86 | 1985 | RETROFITTING | 100 | 100% Physical | 98 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 98.11 | 97.89
570 | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme (SM/06891) | SM/06891 | 83.27 | 1698 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 18/12/2020 | 83 | 82.64
571 | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme (SM/06892) | SM/06892 | 90.8 | 1791 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 31/03/2024 | 18/04/2024 | 05/11/2020 | 90 | 86.96
572 | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme (SM/07105) | SM/07105 | 99.66 | 2020 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/12/2021 | 12/06/2023 | 21/12/2020 | 96.67 | 96.67
573 | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme (SM/07110) | SM/07110 | 72.71 | 1500 | RETROFITTING | 100 | 100% Physical | 76 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 14/01/2021 | 55 | 47.29
574 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) (SM/07480) | SM/07480 | 87.9 | 1724 | RETROFITTING | 100 | 100% Physical | 99 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 27/01/2021 | 87.01 | 86.89
575 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. (SM/07485) | SM/07485 | 99.81 | 2050 | RETROFITTING | 100 | 100% Physical | 100 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 05/02/2021 | 99.72 | 98.39
576 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) (SM/08231) | SM/08231 | 176.93 | 1389 | RETROFITTING | 100 | 100% Physical | 99 | 09/02/2021 | 31/03/2024 | 18/04/2024 | 23/06/2021 | 175.93 | 175.93
577 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. (SM/08755) | SM/08755 | 91.37 | 1897 | RETROFITTING | 100 | 100% Physical | 100 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 90.94 | 90.94
578 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. (SM/08757) | SM/08757 | 25.02 | 548 | RETROFITTING | 100 | 100% Physical | 96 | 09/09/2021 | 31/12/2021 | 12/06/2023 | 10/09/2021 | 24 | 24
579 | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) (SM/08229) | SM/08229 | 31.23 | 206 | RETROFITTING | 100 | 100% Physical | 97 | 09/02/2021 | 31/10/2021 | 12/06/2023 | 01/09/2023 | 30.18 | 30.18
580 | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. (SM/09049) | SM/09049 | 41.88 | 505 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 40.65 | 40.65
581 | Shyampur Piped Water Supply Scheme. (SM/08878) | SM/08878 | 800.17 | 2571 | NEW | 100 | 100% Physical | 75 | 24/09/2021 | 31/12/2022 | 12/06/2023 | 17/11/2021 | 601.6 | 601.6
582 | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya (SM/09034) | SM/09034 | 829.85 | 3041 | AUGMENTATION | 100 | 100% Physical | 58 | 30/10/2021 | 31/12/2025 | 18/04/2024 | 02/12/2021 | 478.37 | 478.37
583 | Retrofitting to Accommodate FHTC (Balance Work) (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-V, Bloc (SM/10437) | SM/10437 | 19.89 | 200 | RETROFITTING | 100 | 100% Physical | 81 | 12/04/2022 | 31/12/2023 | 12/06/2023 | 05/04/2022 | 16.09 | 16.09
584 | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. (SM/09801) | SM/09801 | 160.98 | 2862 | RETROFITTING | 100 | 100% Physical | 90 | 01/12/2021 | 31/12/2023 | 12/06/2023 | 21/03/2022 | 144.09 | 144.09
585 | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme (SM/07096) | SM/07096 | 34.92 | 717 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 21/01/2021 | 34 | 33.44
586 | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme (SM/07094) | SM/07094 | 99.43 | 2010 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 09/02/2021 | 96.38 | 96.38
587 | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme (SM/07100) | SM/07100 | 90.02 | 1800 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 31/03/2022 | 12/06/2023 | 05/01/2021 | 89.5 | 87.39
588 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX (SM/07112) | SM/07112 | 56.55 | 1196 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 11/01/2021 | 54.91 | 54.91
589 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI (SM/07115) | SM/07115 | 99.73 | 1985 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 97.14 | 97.13
590 | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. (SM/07659) | SM/07659 | 228.34 | 4683 | RETROFITTING | 100 | 100% Physical | 98 | 07/01/2021 | 31/10/2021 | 12/06/2023 | 08/02/2021 | 222.75 | 222.75
591 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II (SM/08748) | SM/08748 | 60.25 | 700 | RETROFITTING | 100 | 100% Physical | 93 | 09/09/2021 | 31/03/2023 | 12/06/2023 | 10/09/2021 | 56.29 | 56.26
592 | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) (SM/08222) | SM/08222 | 92.76 | 1215 | RETROFITTING | 100 | 100% Physical | 70 | 09/02/2021 | 31/03/2022 | 12/06/2023 | 20/04/2023 | 65.29 | 65.29
593 | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) (SM/08225) | SM/08225 | 27.04 | 300 | RETROFITTING | 100 | 100% Physical | 87 | 09/02/2021 | 31/01/2022 | 12/06/2023 | 22/02/2021 | 23.49 | 23.49
594 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone X (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-III) (SM/09051) | SM/09051 | 93.24 | 1600 | RETROFITTING | 100 | 100% Physical | 90 | 29/10/2021 | 31/03/2022 | 12/06/2023 | 08/11/2021 | 84.01 | 84.01
595 | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) (SM/09053) | SM/09053 | 14.94 | 200 | RETROFITTING | 100 | 100% Physical | 82 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 12.23 | 12.22
596 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II (SM/08752) | SM/08752 | 145.47 | 1000 | RETROFITTING | 100 | 100% Physical | 99 | 09/09/2021 | 31/03/2024 | 18/04/2024 | 10/09/2021 | 143.66 | 143.26
597 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II (SM/07114) | SM/07114 | 99.94 | 1905 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 96 | 96
598 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII (SM/07116) | SM/07116 | 99.8 | 1945 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 28/01/2021 | 96.73 | 96.73
599 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme (SM/07120) | SM/07120 | 79 | 1561 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 76.78 | 76.68
600 | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) (SM/07976) | SM/07976 | 1280.9 | 27063 | RETROFITTING | 100 | 100% Physical | 94 | 21/01/2021 | 31/12/2023 | 18/04/2024 | 29/01/2021 | 1203.9 | 1202.42
601 | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme (SM/07106) | SM/07106 | 99.2 | 2000 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 11/01/2021 | 94.98 | 94.93
602 | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block (SM/07479) | SM/07479 | 79.84 | 1612 | RETROFITTING | 100 | 100% Physical | 96 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 11/02/2021 | 76.95 | 76.67
603 | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. (SM/07483) | SM/07483 | 76.83 | 1571 | RETROFITTING | 100 | 100% Physical | 96 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 27/01/2021 | 73.99 | 73.99
604 | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. (SM/07484) | SM/07484 | 99.86 | 2070 | RETROFITTING | 100 | 100% Physical | 97 | 29/12/2020 | 31/10/2021 | 12/06/2023 | 05/02/2021 | 96.68 | 96.68
605 | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block (SM/07654) | SM/07654 | 117.41 | 2449 | RETROFITTING | 100 | 100% Physical | 74 | 07/01/2021 | 31/03/2022 | 12/06/2023 | 04/02/2021 | 86.9 | 86.8
606 | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. (SM/09354) | SM/09354 | 199.18 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 30/09/2023 | 05/10/2023 | 26/03/2021 | 0 | 0
607 | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d (SM/09357) | SM/09357 | 223.89 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 30/09/2023 | 05/10/2023 | 26/03/2021 | 0 | 0
608 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II (SM/08745) | SM/08745 | 104.08 | 670 | RETROFITTING | 100 | 100% Physical | 100 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 104 | 101.34
609 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK (SM/08750) | SM/08750 | 99.92 | 1500 | RETROFITTING | 100 | 100% Physical | 96 | 09/09/2021 | 31/12/2021 | 12/06/2023 | 10/09/2021 | 96.12 | 96.12
610 | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. (SM/08756) | SM/08756 | 42.75 | 899 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/01/2022 | 12/06/2023 | 10/09/2021 | 41.31 | 41.31
611 | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) (SM/08224) | SM/08224 | 98.97 | 680 | RETROFITTING | 100 | 100% Physical | 88 | 09/02/2021 | 31/03/2022 | 12/06/2023 | 11/05/2021 | 87.23 | 86.69
612 | Retrofitting to accomodate FHTC under JJM in Bagmari W/S Scheme Potashpur-II Block (PHASE-II) (SM/08226) | SM/08226 | 91.23 | 1220 | RETROFITTING | 100 | 100% Physical | 63 | 09/02/2021 | 31/03/2022 | 12/06/2023 | 11/05/2021 | 57.72 | 57.72
613 | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) (SM/09339) | SM/09339 | 125.52 | 314 | RETROFITTING | 100 | 100% Physical | 98 | 12/11/2021 | 31/12/2023 | 12/06/2023 | 11/06/2019 | 122.89 | 122.73
614 | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. (SM/09074) | SM/09074 | 61.29 | 335 | RETROFITTING | 100 | 100% Physical | 47 | 28/10/2021 |  | 12/06/2023 | 22/11/2021 | 28.56 | 28.56
615 | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. (SM/09802) | SM/09802 | 164.09 | 2753 | RETROFITTING | 100 | 100% Physical | 55 | 01/12/2021 |  | 12/06/2023 | 19/01/2022 | 90.9 | 90.9
616 | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) (SM/09055) | SM/09055 | 71.42 | 160 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 31/03/2024 | 18/04/2024 | 02/11/2021 | 67.37 | 67.16
617 | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme (SM/06888) | SM/06888 | 93.57 | 1955 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 31/10/2021 | 12/06/2023 | 18/12/2020 | 93 | 90.78
618 | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme (SM/07097) | SM/07097 | 99.87 | 1890 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 28/01/2021 | 99.1 | 99.1
619 | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme (SM/07102) | SM/07102 | 99.76 | 2000 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2022 | 12/06/2023 | 05/01/2021 | 96.83 | 96.83
620 | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme (SM/06886) | SM/06886 | 99.67 | 2020 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2022 | 12/06/2023 | 05/11/2020 | 96.5 | 96.26
621 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IXA (SM/07113) | SM/07113 | 99.88 | 2091 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 96.71 | 96.7
622 | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur (SM/07661) | SM/07661 | 201.91 | 4231 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 30/11/2021 | 12/06/2023 | 05/02/2021 | 196.51 | 196.51
623 | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme (SM/06887) | SM/06887 | 99.71 | 1995 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 31/10/2021 | 12/06/2023 | 05/11/2020 | 99 | 96.73
624 | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme (SM/07109) | SM/07109 | 99.52 | 2024 | RETROFITTING | 100 | 100% Physical | 100 | 26/11/2020 | 31/10/2021 | 12/06/2023 | 05/01/2021 | 99.52 | 96.52
625 | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. (SM/07653) | SM/07653 | 116.61 | 2382 | RETROFITTING | 100 | 100% Physical | 98 | 07/01/2021 | 31/10/2021 | 12/06/2023 | 05/02/2021 | 114.56 | 114.36
626 | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. (SM/09355) | SM/09355 | 123.45 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 30/09/2023 | 05/10/2023 | 26/03/2021 | 0 | 0
627 | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di (SM/09356) | SM/09356 | 68.86 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 | 30/09/2023 | 05/10/2023 | 19/07/2021 | 0 | 0
628 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK (SM/08746) | SM/08746 | 98.91 | 1575 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 95.93 | 95.93
629 | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) (SM/08228) | SM/08228 | 37.55 | 310 | RETROFITTING | 100 | 100% Physical | 92 | 09/02/2021 | 31/12/2021 | 12/06/2023 | 22/02/2021 | 34.68 | 34.68
630 | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme (SM/07104) | SM/07104 | 97.26 | 2000 | RETROFITTING | 100 | 100% Physical | 87 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 22/02/2021 | 84.71 | 84.71
631 | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S (SM/09073) | SM/09073 | 21.74 | 300 | RETROFITTING | 100 | 100% Physical | 94 | 28/10/2021 |  | 12/06/2023 | 22/11/2021 | 20.5 | 18.98
632 | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block (SM/08233) | SM/08233 | 216.57 | 2466 | RETROFITTING | 100 | 100% Physical | 80 | 09/02/2021 | 31/03/2022 | 12/06/2023 | 25/02/2021 | 172.89 | 172.89
633 | Retrofitting to Accommodate FHTC (Balance Work) (579 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-IV, Blo (SM/10435) | SM/10435 | 94.29 | 579 | RETROFITTING | 100 | 100% Physical | 69 | 12/04/2022 | 31/12/2023 | 12/06/2023 | 05/04/2022 | 65.2 | 65.2
634 | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme (SM/07093) | SM/07093 | 73.12 | 1511 | RETROFITTING | 100 | 100% Physical | 97 | 26/11/2020 | 28/02/2022 | 12/06/2023 | 01/02/2021 | 71 | 70.61
635 | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme (SM/06877) | SM/06877 | 99.46 | 2030 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 31/12/2023 | 18/04/2024 | 22/02/2021 | 96.5 | 87.65
636 | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur (SM/07656) | SM/07656 | 164.81 | 3451 | RETROFITTING | 100 | 100% Physical | 92 | 07/01/2021 | 28/02/2022 | 12/06/2023 | 08/02/2021 | 152.25 | 152.11
637 | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) (SM/07482) | SM/07482 | 53.02 | 992 | RETROFITTING | 100 | 100% Physical | 97 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 05/01/2021 | 51.25 | 51.25
638 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II (SM/08747) | SM/08747 | 23.05 | 250 | RETROFITTING | 100 | 100% Physical | 92 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 21.15 | 21.15
639 | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. (SM/08754) | SM/08754 | 60.34 | 1100 | RETROFITTING | 100 | 100% Physical | 94 | 09/09/2021 | 31/12/2021 | 12/06/2023 | 10/09/2021 | 56.73 | 56.73
640 | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block (SM/09052) | SM/09052 | 76.42 | 76 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 74 | 74
641 | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) (SM/09054) | SM/09054 | 50.27 | 400 | RETROFITTING | 100 | 100% Physical | 99 | 29/10/2021 | 31/03/2024 | 18/04/2024 | 02/11/2021 | 50 | 46.55
642 | Retorfitting to accommodate FHTC under JJM in Dulalpur PWSS. (SM/09057) | SM/09057 | 59.18 | 1166 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 57.41 | 57.41
643 | Baharampur Piped Water Supply Scheme. (SM/08879) | SM/08879 | 688.64 | 2296 | NEW | 100 | 100% Physical | 76 | 24/09/2021 | 31/12/2022 | 12/06/2023 | 31/01/2022 | 523.42 | 522.13
644 | Narikeldaha Piped Water Supply Scheme. (SM/09342) | SM/09342 | 848.91 | 2272 | NEW | 100 | 100% Physical | 88 | 12/11/2021 | 31/12/2022 | 12/06/2023 | 30/11/2021 | 745.33 | 745.33
645 | Balance Work for Retrofitting to Accommodate FHTC (152 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of different nodal point of Dona Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk (SM/09443) | SM/09443 | 48.34 | 152 | RETROFITTING | 100 | 100% Physical | 98 | 19/11/2021 |  | 12/06/2023 | 13/12/2021 | 47.35 | 45.8
646 | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. (SM/10346) | SM/10346 | 26.17 | 410 | RETROFITTING | 100 | 100% Physical | 73 | 16/03/2022 |  | 12/06/2023 | 08/03/2022 | 19.06 | 19.06
647 | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl (SM/10436) | SM/10436 | 99.32 | 862 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/12/2023 | 12/06/2023 | 21/06/2022 | 96.36 | 96.36
648 | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme (SM/07101) | SM/07101 | 58.04 | 1167 | RETROFITTING | 100 | 100% Physical | 91 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 28/01/2021 | 53 | 52.6
649 | Retrofitting to accomodate FHTC under JJM in Saripur PWSS (SM/06889) | SM/06889 | 57.01 | 1114 | RETROFITTING | 100 | 100% Physical | 100 | 07/10/2020 | 31/10/2021 | 12/06/2023 | 18/12/2020 | 57 | 57
650 | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme (SM/06878) | SM/06878 | 77.32 | 1574 | RETROFITTING | 100 | 100% Physical | 96 | 07/10/2020 | 31/10/2021 | 12/06/2023 | 05/11/2020 | 73.99 | 73.96
651 | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme (SM/06885) | SM/06885 | 99.63 | 1966 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 28/02/2022 | 12/06/2023 | 22/02/2021 | 96.5 | 87.27
652 | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme (SM/07119) | SM/07119 | 78.45 | 1517 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 28/02/2022 | 12/06/2023 | 23/12/2020 | 77.77 | 77.76
653 | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. (SM/07481) | SM/07481 | 26.99 | 550 | RETROFITTING | 100 | 100% Physical | 29 | 29/12/2020 | 31/01/2022 | 12/06/2023 | 18/12/2020 | 7.75 | 7.75
654 | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block (SM/07652) | SM/07652 | 129.4 | 2629 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 31/03/2022 | 12/06/2023 | 04/02/2021 | 126.08 | 125.97
655 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II (SM/08751) | SM/08751 | 45.72 | 400 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 44.38 | 44.38
656 | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK (SM/08753) | SM/08753 | 100.13 | 1950 | RETROFITTING | 100 | 100% Physical | 97 | 09/09/2021 | 31/03/2022 | 12/06/2023 | 10/09/2021 | 97.49 | 97.49
657 | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone I (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-I) (SM/09050) | SM/09050 | 61.99 | 1100 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 |  | 12/06/2023 | 02/11/2021 | 59.87 | 59.87
658 | Balance work for Retrofitting to accommodate FHTC (907 Nos.) and laying of laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for (SM/09058) | SM/09058 | 130.31 | 907 | RETROFITTING | 100 | 100% Physical | 89 | 29/10/2021 |  | 12/06/2023 | 08/11/2021 | 115.86 | 115.86
659 | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. (SM/08698) | SM/08698 | 746.17 | 0 | NEW | 100 | 100% Physical | 84 | 01/09/2021 | 31/03/2024 | 18/04/2024 | 28/12/2021 | 628.1 | 628.1
660 | Balance work for Retrofitting to Accommodate FHTC (951 Nos.) and laying of Left-out portion UPVC pipeline due to uncovered area of this Zone and Damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme under Zone-III (SM/10096) | SM/10096 | 89.89 | 951 | RETROFITTING | 100 | 100% Physical | 86 | 01/02/2022 | 30/09/2022 | 12/06/2023 | 23/02/2022 | 77.04 | 77.04
661 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII (SM/08790) | SM/08790 | 353.17 | 7511 | RETROFITTING | 100 | 100% Physical | 97 | 13/09/2021 | 31/01/2022 | 12/06/2023 | 15/09/2021 | 342.75 | 342.75
662 | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme (SM/06879) | SM/06879 | 38.01 | 745 | RETROFITTING | 100 | 100% Physical | 99 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 18/12/2020 | 37.66 | 37.66
663 | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme (SM/06884) | SM/06884 | 37.82 | 745 | RETROFITTING | 100 | 100% Physical | 98 | 07/10/2020 | 31/12/2021 | 12/06/2023 | 18/12/2020 | 37 | 35.43
664 | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur (SM/07657) | SM/07657 | 177.82 | 3634 | RETROFITTING | 100 | 100% Physical | 97 | 07/01/2021 | 31/12/2023 | 18/04/2024 | 22/02/2021 | 172.13 | 169.2
665 | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. (SM/06651) | SM/06651 | 28.92 | 74 | NEW | 100 | 100% Physical | 97 | 12/02/2020 | 31/03/2024 | 18/04/2024 |  | 28.06 | 28.06
666 | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme (SM/07108) | SM/07108 | 97.82 | 1900 | RETROFITTING | 100 | 100% Physical | 99 | 26/11/2020 | 31/01/2022 | 12/06/2023 | 05/01/2021 | 96.59 | 93.09
667 | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme (SM/08232) | SM/08232 | 102.22 | 1375 | RETROFITTING | 100 | 100% Physical | 95 | 09/02/2021 | 28/02/2022 | 12/06/2023 | 25/02/2021 | 97.26 | 97.26
668 | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) (SM/09340) | SM/09340 | 449.59 | 0 | DISASTER | 100 | 100% Physical | 0 | 12/11/2021 |  | 05/10/2023 | 18/01/2021 | 0 | 0
669 | Balance Work for Retrofitting to Accommodate FHTC (750 Nos.) and Laying of left-out portion UPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-XI, Block-Kolaghat in this (SM/10095) | SM/10095 | 95.4 | 750 | RETROFITTING | 100 | 100% Physical | 97 | 01/02/2022 |  | 12/06/2023 | 08/02/2022 | 93 | 92.89
670 | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) (SM/08227) | SM/08227 | 27.42 | 427 | RETROFITTING | 100 | 100% Physical | 93 | 09/02/2021 | 28/02/2022 | 12/06/2023 | 22/02/2021 | 25.48 | 25.15
671 | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VIA (SM/07111) | SM/07111 | 54.94 | 1159 | RETROFITTING | 100 | 100% Physical | 96 | 26/11/2020 | 28/02/2022 | 12/06/2023 | 11/05/2021 | 53 | 51.1
672 | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme (SM/06883) | SM/06883 | 99.43 | 2000 | RETROFITTING | 100 | 100% Physical | 97 | 07/10/2020 | 31/01/2022 | 12/06/2023 | 05/11/2020 | 96.5 | 95.63
673 | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. (SM/06626) | SM/06626 | 106.33 | 0 | SUPPORT-WQMSP | 100 | 100% Physical | 0 | 05/02/2020 | 30/09/2023 | 05/10/2023 | 30/12/2020 | 0 | 0
Total |  |  | 328238.39 | 1066131 | [8 empty] | 104748.52 | 99998.14