## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Supply , Delivery and Installation of Computer & Peripherial Device for Official use Under Office of Executive Engineer , Alipurduar Division,P.H.E (SM/12120) | SM/12120 | 13.4 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 07/09/2022 |  | 11/09/2022 | 16/12/2022 | 0 | 0
2 | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. (SM/17189) | SM/17189 | 22.16 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 |  | 0 | 0
3 | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 (SM/19170) | SM/19170 | 99.19 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | 0% Physical | 0 | 08/02/2024 |  | 15/02/2024 | 31/12/2024 | 0 | 0
4 | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/19081) | SM/19081 | 58.05 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 24/04/2024 | 0 | 0
5 | BUXA PIPE WATER SUPPLY SCHEME (SM/16507) | SM/16507 | 219.61 | 219 | NEW | 2 | Delayed | 8 | 03/03/2023 | 31/12/2025 | 25/07/2025 | 23/03/2023 | 18.59 | 18.59
6 | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME (SM/16506) | SM/16506 | 990.41 | 1752 | NEW | 3 | Delayed | 12 | 03/03/2023 | 31/12/2025 | 25/07/2025 | 04/04/2023 | 120.59 | 119.31
7 | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME (SM/15914) | SM/15914 | 358.24 | 567 | NEW | 6 | Delayed | 13 | 22/02/2023 | 31/12/2025 | 25/07/2025 | 24/04/2023 | 45.73 | 45.73
8 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme (SM/07131) | SM/07131 | 73.16 | 567 | RETROFITTING | 10 | Delayed | 92 | 26/11/2020 | 30/09/2022 | 25/07/2025 | 12/11/2020 | 67.15 | 67.15
9 | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED MANAGED LABORATORIES (SM/12752) | SM/12752 | 41.13 | 0 | SUPPORT-WQMSP | 10 | Delayed | 0 | 20/09/2022 | 31/03/2025 | 29/01/2024 | 31/03/2023 | 0 | 0
10 | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME (SM/13249) | SM/13249 | 860.22 | 2652 | NEW | 20 | Delayed | 33 | 14/10/2022 | 31/10/2025 | 25/07/2025 | 01/11/2022 | 280.98 | 280.98
11 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12909) | SM/12909 | 12.66 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 11/01/2023 | 0 | 0
12 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12910) | SM/12910 | 12.66 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 11/01/2023 | 0 | 0
13 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12911) | SM/12911 | 32.31 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 02/09/2021 | 0 | 0
14 | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/16821) | SM/16821 | 405.28 | 442 | NEW | 25 | Delayed | 12 | 13/03/2023 | 31/07/2025 | 25/07/2025 | 31/03/2023 | 49.69 | 49.69
15 | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME (SM/10669) | SM/10669 | 161.24 | 50 | AUGMENTATION | 30 | Delayed | 13 | 29/04/2022 | 30/06/2025 | 25/07/2025 | 13/05/2022 | 20.83 | 20.83
16 | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME (SM/12361) | SM/12361 | 1269.79 | 1277 | AUGMENTATION | 35 | Delayed | 15 | 13/09/2022 | 30/06/2025 | 25/07/2025 | 27/02/2023 | 191.79 | 191.79
17 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme (SM/07180) | SM/07180 | 64.83 | 624 | RETROFITTING | 42 | Delayed | 55 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 23/03/2023 | 35.82 | 11.34
18 | Malangi Tea Garden Area Piped Water Supply Scheme (SM/18150) | SM/18150 | 561.45 | 2115 | NEW | 50 | Delayed | 18 | 29/03/2023 | 30/06/2026 | 25/07/2025 | 04/05/2023 | 102.53 | 102.53
19 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14213) | SM/14213 | 740.97 | 2268 | NEW | 50 | Delayed | 22 | 10/01/2023 | 30/06/2025 | 25/07/2025 | 03/08/2023 | 164.1 | 164.1
20 | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME (SM/16115) | SM/16115 | 240.25 | 0 | AUGMENTATION | 50 | Delayed | 26 | 22/02/2023 | 30/06/2025 | 25/07/2025 | 31/01/2023 | 61.62 | 61.62
21 | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/15482) | SM/15482 | 1380.67 | 5753 | NEW | 50 | Delayed | 32 | 13/02/2023 | 31/07/2025 | 25/07/2025 | 01/11/2022 | 441.32 | 441.32
22 | UMACHARANPUR PIPED WATER SUPPLY SCHEME (SM/16114) | SM/16114 | 950.07 | 3053 | NEW | 50 | Delayed | 41 | 22/02/2023 | 08/02/2025 | 25/07/2025 | 07/09/2023 | 388.99 | 388.99
23 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) (SM/07132) | SM/07132 | 88.7 | 1847 | RETROFITTING | 50 | Delayed | 21 | 26/11/2020 | 30/09/2025 | 25/07/2025 | 25/01/2021 | 18.73 | 18.55
24 | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME (SM/13241) | SM/13241 | 780.16 | 1437 | NEW | 50 | Delayed | 34 | 14/10/2022 | 30/06/2025 | 25/07/2025 | 17/01/2023 | 265.59 | 265.59
25 | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' (SM/09900) | SM/09900 | 45.23 | 0 | AUGMENTATION | 50 | Delayed | 7 | 08/12/2021 | 31/07/2025 | 25/07/2025 | 20/05/2022 | 2.97 | 2.87
26 | PAKRIGURI PIPED WAYER SUPPLY SCHEME. (SM/14223) | SM/14223 | 509.75 | 603 | NEW | 55 | Delayed | 33 | 10/01/2023 | 31/10/2025 | 25/07/2025 | 31/03/2023 | 165.83 | 165.83
27 | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. (SM/13242) | SM/13242 | 615.61 | 1001 | NEW | 55 | Delayed | 25 | 14/10/2022 | 31/05/2025 | 25/07/2025 | 16/03/2023 | 155.94 | 155.94
28 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) (SM/07061) | SM/07061 | 93.85 | 1581 | RETROFITTING | 55 | Delayed | 100 | 25/11/2020 | 31/07/2025 | 25/07/2025 | 15/12/2020 | 93.85 | 93.85
29 | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/11878) | SM/11878 | 21.39 | 0 | SUPPORT-WQMSP | 55 | Delayed | 0 | 17/08/2022 | 31/03/2025 | 29/01/2024 | 24/12/2021 | 0 | 0
30 | BENGKANDI PIPED WATER SUPPLY SCHEME (SM/16820) | SM/16820 | 964.09 | 2074 | NEW | 60 | Delayed | 56 | 13/03/2023 | 31/05/2025 | 25/07/2025 | 28/07/2023 | 544.2 | 544.2
31 | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. (SM/10670) | SM/10670 | 108.13 | 45 | AUGMENTATION | 60 | Delayed | 28 | 29/04/2022 | 31/07/2025 | 25/07/2025 | 19/09/2022 | 29.89 | 29.89
32 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme (SM/07130) | SM/07130 | 94.15 | 1568 | RETROFITTING | 60 | Delayed | 91 | 26/11/2020 | 30/06/2025 | 25/07/2025 | 16/09/2020 | 86.11 | 86.11
33 | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME (SM/14217) | SM/14217 | 409.38 | 794 | NEW | 60 | Delayed | 44 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 01/11/2022 | 179.16 | 179.16
34 | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. (SM/15210) | SM/15210 | 111.32 | 0 | AUGMENTATION | 60 | Delayed | 36 | 07/02/2023 | 31/07/2025 | 25/07/2025 | 13/03/2023 | 40.11 | 40.11
35 | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME (SM/16819) | SM/16819 | 658.29 | 1272 | NEW | 60 | Delayed | 52 | 13/03/2023 | 31/05/2025 | 25/07/2025 | 03/08/2023 | 342.03 | 342.03
36 | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/16822) | SM/16822 | 569.65 | 1184 | NEW | 60 | Delayed | 28 | 13/03/2023 | 31/07/2025 | 25/07/2025 | 19/05/2023 | 158.73 | 158.73
37 | Khagenhat Piped Water Supply Scheme (SM/18151) | SM/18151 | 822.98 | 2057 | NEW | 60 | Delayed | 36 | 29/03/2023 | 31/05/2025 | 25/07/2025 | 08/05/2023 | 298.23 | 298.23
38 | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME (SM/11765) | SM/11765 | 154.07 | 110 | AUGMENTATION | 60 | Delayed | 42 | 03/08/2022 | 31/05/2025 | 25/07/2025 | 20/09/2021 | 63.97 | 63.97
39 | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION (SM/11752) | SM/11752 | 18.35 | 0 | SUPPORT-WQMSP | 60 | Delayed | 0 | 03/08/2022 | 31/03/2025 | 29/01/2024 | 07/08/2023 | 0 | 0
40 | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME (SM/10667) | SM/10667 | 186.88 | 40 | AUGMENTATION | 61 | Delayed | 32 | 29/04/2022 | 31/07/2025 | 25/07/2025 | 24/02/2022 | 58.88 | 58.88
41 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) (SM/07128) | SM/07128 | 62.07 | 895 | RETROFITTING | 61 | Delayed | 100 | 26/11/2020 | 31/07/2025 | 25/07/2025 | 19/10/2020 | 62.07 | 62.07
42 | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME (SM/11959) | SM/11959 | 648.63 | 807 | AUGMENTATION | 65 | Delayed | 11 | 25/08/2022 | 30/06/2025 | 25/07/2025 | 05/09/2022 | 71.05 | 71.05
43 | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME (SM/14233) | SM/14233 | 2288.93 | 18867 | AUGMENTATION | 65 | Delayed | 43 | 11/01/2023 | 30/06/2025 | 25/07/2025 | 22/11/2021 | 981.3 | 978.5
44 | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME (SM/15207) | SM/15207 | 802.95 | 2097 | NEW | 65 | Delayed | 38 | 07/02/2023 | 31/12/2025 | 25/07/2025 | 20/07/2023 | 301.89 | 301.89
45 | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME (SM/16817) | SM/16817 | 808.5 | 1601 | NEW | 65 | On track | 60 | 13/03/2023 | 31/07/2026 | 25/07/2025 | 20/07/2023 | 483.9 | 483.9
46 | FOSKADANGA PIPED WATER SUPPLY SCHEME (SM/14210) | SM/14210 | 510.99 | 684 | NEW | 65 | Delayed | 53 | 10/01/2023 | 31/07/2025 | 25/07/2025 | 27/03/2023 | 268.41 | 268.41
47 | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME (SM/13448) | SM/13448 | 305.16 | 563 | NEW | 65 | Delayed | 36 | 02/11/2022 | 30/11/2025 | 25/07/2025 | 06/06/2023 | 109.98 | 109.98
48 | Chengmari Piped Water Supply Scheme (SM/18152) | SM/18152 | 772.15 | 1699 | NEW | 65 | Delayed | 53 | 29/03/2023 | 31/07/2025 | 25/07/2025 | 04/05/2023 | 407.38 | 407.38
49 | SIDHABARI PIED WATER SUPPLY SCHEME (SM/10175) | SM/10175 | 360.32 | 1605 | NEW | 65 | Delayed | 86 | 16/02/2022 | 31/07/2025 | 25/07/2025 | 05/01/2022 | 311 | 311
50 | NAOTHOARTARI PIPED WATER SUPPLY SCHEME (SM/12754) | SM/12754 | 415.72 | 295 | NEW | 68 | On track | 48 | 20/09/2022 | 30/04/2027 | 25/07/2025 | 31/03/2023 | 198.86 | 198.86
51 | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME (SM/10156) | SM/10156 | 706.17 | 1020 | AUGMENTATION | 68 | Delayed | 71 | 11/02/2022 | 30/06/2025 | 25/07/2025 | 25/01/2022 | 504.48 | 504.48
52 | Parpatla Khawa Piped Water Supply Scheme (SM/18158) | SM/18158 | 187.87 | 189 | NEW | 68 | Delayed | 48 | 29/03/2023 | 31/07/2025 | 25/07/2025 | 04/05/2023 | 90.33 | 90.33
53 | MALSAGAON PIPED WATER SUPPLY SCHEME (SM/16818) | SM/16818 | 777.46 | 1481 | NEW | 70 | Delayed | 76 | 13/03/2023 | 08/02/2025 | 25/07/2025 | 07/09/2023 | 590 | 590
54 | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme (SM/18157) | SM/18157 | 360.16 | 1538 | NEW | 70 | Delayed | 50 | 29/03/2023 | 31/12/2025 | 25/07/2025 | 22/05/2023 | 178.4 | 178.4
55 | AUGMENTATION OF DALIMPUR PWSS (SM/18254) | SM/18254 | 1020.25 | 4067 | AUGMENTATION | 70 | Delayed | 56 | 21/06/2023 | 31/10/2025 | 25/07/2025 | 12/07/2023 | 566.73 | 566.73
56 | Dhantali Piped Water Supply Scheme (SM/18153) | SM/18153 | 285.56 | 206 | NEW | 70 | Delayed | 51 | 29/03/2023 | 31/07/2025 | 25/07/2025 | 04/05/2023 | 147.02 | 147.02
57 | Rejuvenation Of Dima T.G. W.S.S (SM/09904) | SM/09904 | 44.51 | 0 | AUGMENTATION | 70 | Delayed | 38 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 16.93 | 13.51
58 | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME (SM/10674) | SM/10674 | 236.97 | 60 | AUGMENTATION | 70 | Delayed | 45 | 29/04/2022 | 31/07/2025 | 25/07/2025 | 06/09/2022 | 106.87 | 106.87
59 | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME (SM/13301) | SM/13301 | 875.66 | 1869 | NEW | 70 | Delayed | 53 | 17/10/2022 | 31/07/2025 | 25/07/2025 | 01/11/2022 | 464.09 | 464.09
60 | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME (SM/14222) | SM/14222 | 429.71 | 729 | NEW | 70 | Delayed | 51 | 10/01/2023 | 31/07/2025 | 25/07/2025 | 27/03/2023 | 220.4 | 220.4
61 | Uttar Dhalkar Piped Water Supply Scheme (SM/18154) | SM/18154 | 404.14 | 594 | NEW | 70 | Delayed | 46 | 29/03/2023 | 30/06/2025 | 25/07/2025 | 04/05/2023 | 184.16 | 184.16
62 | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME (SM/16538) | SM/16538 | 1074.69 | 1888 | NEW | 70 | Delayed | 42 | 10/03/2023 | 31/07/2025 | 25/07/2025 | 17/03/2023 | 449.78 | 449.78
63 | NARASINGPUR PIPED WATER SUPPLY SCHEME (SM/15758) | SM/15758 | 842.46 | 2461 | NEW | 70 | Delayed | 82 | 20/02/2023 | 31/07/2025 | 25/07/2025 | 20/07/2023 | 688.1 | 688.1
64 | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME (SM/11970) | SM/11970 | 1275.43 | 7780 | AUGMENTATION | 70 | Delayed | 37 | 29/08/2022 | 31/12/2025 | 25/07/2025 | 13/09/2021 | 476.79 | 475.51
65 | PARARPAR PIPED WATER SUPPLY SCHEME (SM/14209) | SM/14209 | 561.82 | 1187 | NEW | 70 | Delayed | 46 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 16/03/2023 | 259.93 | 259.93
66 | BARIGURI PIPED WATER SUPPLY SCHEME (SM/13246) | SM/13246 | 895.77 | 7373 | NEW | 70 | Delayed | 33 | 14/10/2022 | 31/07/2025 | 25/07/2025 | 16/05/2023 | 298 | 298
67 | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10177) | SM/10177 | 338.59 | 1248 | NEW | 70 | Delayed | 70 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 19/02/2021 | 237.81 | 237.14
68 | MAIRADANGA PIPED WATER SUPPLY SCHEME (SM/15206) | SM/15206 | 963.71 | 2583 | NEW | 70 | Delayed | 48 | 07/02/2023 | 31/05/2025 | 25/07/2025 | 16/05/2023 | 459.9 | 459.9
69 | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME (SM/11459) | SM/11459 | 1873.61 | 7440 | AUGMENTATION | 72 | Delayed | 60 | 12/07/2022 | 31/07/2025 | 25/07/2025 | 20/09/2021 | 1123.84 | 1121.88
70 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) (SM/07187) | SM/07187 | 73.94 | 828 | RETROFITTING | 72 | Delayed | 100 | 04/12/2020 | 31/07/2025 | 25/07/2025 | 10/12/2021 | 73.94 | 73.94
71 | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/11960) | SM/11960 | 512.91 | 1031 | AUGMENTATION | 72 | Delayed | 27 | 25/08/2022 | 30/06/2025 | 25/07/2025 | 22/12/2022 | 136.67 | 136.67
72 | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME (SM/09909) | SM/09909 | 45.46 | 0 | AUGMENTATION | 72 | Delayed | 84 | 08/12/2021 | 31/07/2025 | 25/07/2025 | 27/12/2021 | 38.37 | 35.45
73 | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. (SM/16824) | SM/16824 | 273.66 | 0 | AUGMENTATION | 72 | Delayed | 42 | 13/03/2023 | 30/06/2025 | 25/07/2025 | 22/03/2023 | 116.15 | 116.15
74 | KAYAKHATA PIPED WATER SUPPLY SCHEME (SM/13299) | SM/13299 | 682.41 | 1585 | NEW | 75 | On track | 49 | 17/10/2022 | 31/12/2025 | 25/07/2025 | 16/03/2023 | 331.04 | 331.03
75 | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10176) | SM/10176 | 426.36 | 1425 | NEW | 75 | Delayed | 73 | 16/02/2022 | 31/07/2025 | 25/07/2025 | 17/02/2022 | 311.03 | 310.72
76 | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME (SM/11401) | SM/11401 | 140.89 | 2981 | AUGMENTATION | 75 | Delayed | 95 | 04/07/2022 | 31/07/2025 | 25/07/2025 | 12/11/2020 | 133.68 | 133.68
77 | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. (SM/16537) | SM/16537 | 1261.38 | 2273 | NEW | 75 | Delayed | 49 | 10/03/2023 | 31/07/2025 | 25/07/2025 | 27/03/2023 | 614.54 | 614.54
78 | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10054) | SM/10054 | 332.16 | 2682 | NEW | 75 | Delayed | 44 | 25/01/2022 | 30/06/2025 | 25/07/2025 | 08/09/2023 | 146.71 | 146.71
79 | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME (SM/11766) | SM/11766 | 88.14 | 400 | AUGMENTATION | 75 | Delayed | 54 | 03/08/2022 | 31/07/2025 | 25/07/2025 | 13/12/2022 | 47.46 | 47.46
80 | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME (SM/11985) | SM/11985 | 2156.38 | 7273 | AUGMENTATION | 75 | Delayed | 54 | 01/09/2022 | 30/06/2025 | 25/07/2025 | 14/10/2020 | 1167.21 | 1162.96
81 | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/16823) | SM/16823 | 739.67 | 1298 | NEW | 75 | On track | 38 | 13/03/2023 | 31/12/2025 | 25/07/2025 | 31/03/2023 | 284.3 | 284.3
82 | KALABERIA PIPED WATER SUPPLY SCHEME (SM/13306) | SM/13306 | 461.28 | 1065 | NEW | 75 | Delayed | 48 | 17/10/2022 | 30/11/2025 | 25/07/2025 | 27/03/2023 | 223.7 | 223.7
83 | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME (SM/16539) | SM/16539 | 1121.63 | 2329 | NEW | 75 | Delayed | 60 | 10/03/2023 | 31/07/2025 | 25/07/2025 | 28/07/2023 | 676.44 | 676.44
84 | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME (SM/10672) | SM/10672 | 162.74 | 30 | AUGMENTATION | 75 | Delayed | 1 | 29/04/2022 | 31/07/2025 | 25/07/2025 | 10/08/2022 | 1.19 | 0
85 | TURTURI PIPED WATER SUPPLY SCHEME. (SM/14219) | SM/14219 | 948.08 | 1003 | NEW | 75 | Delayed | 47 | 10/01/2023 | 31/07/2025 | 25/07/2025 | 27/03/2023 | 441.15 | 441.15
86 | DHANIRAMPUR PIPED WATER SUPPLY SCHEME (SM/15208) | SM/15208 | 670.33 | 1552 | NEW | 78 | Delayed | 76 | 07/02/2023 | 30/06/2025 | 25/07/2025 | 31/03/2023 | 509.63 | 509.63
87 | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME (SM/09883) | SM/09883 | 451.23 | 6045 | AUGMENTATION | 78 | Delayed | 67 | 08/12/2021 | 31/07/2025 | 25/07/2025 | 13/09/2021 | 303.1 | 303.1
88 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) (SM/07188) | SM/07188 | 73.94 | 828 | RETROFITTING | 78 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 10/12/2021 | 73.94 | 54.01
89 | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14211) | SM/14211 | 530.22 | 1604 | NEW | 78 | Delayed | 35 | 10/01/2023 | 30/06/2025 | 25/07/2025 | 27/02/2023 | 186.91 | 186.91
90 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme (SM/07197) | SM/07197 | 84.07 | 1121 | RETROFITTING | 80 | Delayed | 75 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 16/09/2020 | 63.14 | 61.6
91 | CHALNIPAK PIPED WATER SUPPLY SCHEME. (SM/15534) | SM/15534 | 1024.4 | 1648 | NEW | 80 | On track | 45 | 16/02/2023 | 30/11/2025 | 25/07/2025 | 22/02/2023 | 465.69 | 465.69
92 | Bandpani Tea Garden Areas Piped Water Supply Scheme. (SM/11483) | SM/11483 | 528.37 | 1272 | NEW | 80 | Delayed | 57 | 14/07/2022 | 30/06/2025 | 25/07/2025 | 27/01/2021 | 299.1 | 299.07
93 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme (SM/07191) | SM/07191 | 62.8 | 788 | RETROFITTING | 80 | Delayed | 61 | 04/12/2020 | 30/04/2026 | 25/07/2025 | 26/08/2021 | 38.2 | 38.2
94 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) (SM/07136) | SM/07136 | 80.05 | 822 | RETROFITTING | 80 | Delayed | 84 | 26/11/2020 | 30/06/2025 | 25/07/2025 | 14/10/2020 | 67.16 | 67.16
95 | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME (SM/11767) | SM/11767 | 204.15 | 250 | AUGMENTATION | 80 | On track | 43 | 03/08/2022 | 31/12/2025 | 25/07/2025 | 20/09/2021 | 87.45 | 87.45
96 | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. (SM/15209) | SM/15209 | 112.19 | 0 | AUGMENTATION | 80 | Delayed | 38 | 07/02/2023 | 30/06/2025 | 25/07/2025 | 13/03/2023 | 42.47 | 42.47
97 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) (SM/07189) | SM/07189 | 97.67 | 895 | RETROFITTING | 81 | Delayed | 100 | 04/12/2020 | 30/06/2025 | 25/07/2025 | 19/10/2020 | 97.67 | 97.67
98 | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/12113) | SM/12113 | 821.35 | 2542 | NEW | 81 | Delayed | 47 | 02/09/2022 | 31/07/2025 | 25/07/2025 | 21/11/2022 | 384.88 | 384.88
99 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme (SM/08884) | SM/08884 | 398.83 | 2599 | RETROFITTING | 81 | Delayed | 97 | 27/09/2021 | 30/06/2025 | 25/07/2025 | 01/10/2020 | 387.21 | 387.18
100 | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME (SM/09891) | SM/09891 | 47.49 | 0 | AUGMENTATION | 82 | Delayed | 76 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 31/01/2022 | 36.16 | 21.62
101 | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME (SM/13248) | SM/13248 | 877.17 | 2462 | NEW | 82 | Delayed | 61 | 14/10/2022 | 31/05/2025 | 25/07/2025 | 27/03/2023 | 532.96 | 532.96
102 | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME (SM/15517) | SM/15517 | 1067.02 | 1645 | NEW | 83 | Delayed | 56 | 16/02/2023 | 31/05/2025 | 25/07/2025 | 22/02/2023 | 600.23 | 600.23
103 | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME (SM/12561) | SM/12561 | 1852.66 | 7617 | AUGMENTATION | 85 | On track | 63 | 14/09/2022 | 30/04/2026 | 25/07/2025 | 19/09/2022 | 1172.11 | 1172.11
104 | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME (SM/11958) | SM/11958 | 562.16 | 493 | AUGMENTATION | 85 | On track | 39 | 25/08/2022 | 30/11/2025 | 25/07/2025 | 28/06/2022 | 218.28 | 218.28
105 | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. (SM/13305) | SM/13305 | 760.21 | 1402 | NEW | 85 | On track | 61 | 17/10/2022 | 30/04/2027 | 25/07/2025 | 17/01/2023 | 466.3 | 466.3
106 | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' (SM/09908) | SM/09908 | 46.31 | 0 | AUGMENTATION | 85 | Delayed | 87 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 11/01/2022 | 40.19 | 40.19
107 | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME (SM/10675) | SM/10675 | 178.64 | 50 | AUGMENTATION | 85 | On track | 29 | 29/04/2022 | 31/10/2025 | 25/07/2025 | 16/03/2023 | 51.29 | 51.29
108 | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME (SM/09894) | SM/09894 | 44.01 | 0 | AUGMENTATION | 85 | Delayed | 62 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 14/01/2022 | 27.25 | 27.25
109 | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME (SM/11485) | SM/11485 | 389.92 | 1567 | NEW | 85 | On track | 67 | 14/07/2022 | 31/12/2025 | 25/07/2025 | 12/07/2022 | 260.28 | 260.28
110 | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME (SM/10673) | SM/10673 | 252.98 | 50 | AUGMENTATION | 85 | Delayed | 11 | 29/04/2022 | 30/06/2025 | 25/07/2025 | 15/03/2022 | 28.92 | 28.92
111 | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME (SM/09884) | SM/09884 | 484.93 | 2333 | AUGMENTATION | 85 | Delayed | 96 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 11/01/2022 | 464.08 | 463.25
112 | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME (SM/10676) | SM/10676 | 252.39 | 40 | AUGMENTATION | 85 | Delayed | 15 | 29/04/2022 | 31/05/2025 | 25/07/2025 | 06/01/2022 | 37.01 | 37.01
113 | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11696) | SM/11696 | 411.35 | 990 | NEW | 85 | Delayed | 60 | 29/07/2022 | 31/05/2025 | 25/07/2025 | 19/09/2022 | 247.02 | 247.02
114 | PASCHIM SATALI PIPED WATER SUPPLY SCHEME (SM/13245) | SM/13245 | 969.65 | 2797 | NEW | 85 | Delayed | 66 | 14/10/2022 | 30/06/2025 | 25/07/2025 | 17/01/2023 | 637.24 | 637.24
115 | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME (SM/10316) | SM/10316 | 281.05 | 2393 | AUGMENTATION | 85 | Delayed | 26 | 04/03/2022 | 30/06/2025 | 25/07/2025 | 27/09/2021 | 73.92 | 73.92
116 | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME (SM/10677) | SM/10677 | 192.09 | 2678 | AUGMENTATION | 85 | Delayed | 8 | 29/04/2022 | 31/05/2025 | 25/07/2025 | 05/10/2021 | 15.52 | 15.52
117 | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11992) | SM/11992 | 269.79 | 705 | NEW | 85 | Delayed | 63 | 01/09/2022 | 31/05/2025 | 25/07/2025 | 21/11/2022 | 170.61 | 170.61
118 | PRODHANPARA PIPED WATER SUPPLY SCHEME (SM/13247) | SM/13247 | 638.14 | 1353 | NEW | 85 | Delayed | 34 | 14/10/2022 | 31/05/2025 | 25/07/2025 | 16/03/2023 | 215.65 | 215.65
119 | BALLALGURI PIPED WATER SUPPLY SCHEME (SM/14221) | SM/14221 | 413.54 | 609 | NEW | 85 | Delayed | 48 | 10/01/2023 | 31/07/2025 | 25/07/2025 | 02/02/2023 | 199.67 | 199.67
120 | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10178) | SM/10178 | 577.33 | 1487 | NEW | 85 | Delayed | 93 | 16/02/2022 | 30/06/2025 | 25/07/2025 | 27/01/2021 | 534.44 | 533.58
121 | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME (SM/13302) | SM/13302 | 171.75 | 308 | NEW | 85 | On track | 57 | 17/10/2022 | 30/11/2025 | 25/07/2025 | 19/01/2023 | 97.16 | 97.16
122 | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. (SM/10637) | SM/10637 | 252.1 | 3877 | AUGMENTATION | 85 | Delayed | 49 | 21/04/2022 | 30/06/2025 | 25/07/2025 | 23/02/2021 | 124.4 | 124.4
123 | MARAKHATA PIPED WATER SUPPLY SCHEME. (SM/13304) | SM/13304 | 839.09 | 3129 | NEW | 86 | Delayed | 45 | 17/10/2022 | 31/05/2025 | 25/07/2025 | 17/01/2023 | 381.11 | 381.11
124 | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. (SM/08080) | SM/08080 | 1224.31 | 29206 | RETROFITTING | 86 | Delayed | 74 | 04/02/2021 | 31/07/2025 | 25/07/2025 | 01/10/2020 | 900.39 | 898.32
125 | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME (SM/10180) | SM/10180 | 376.91 | 1250 | NEW | 86 | Delayed | 94 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 17/02/2022 | 354.25 | 354.16
126 | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' (SM/09902) | SM/09902 | 47.49 | 0 | AUGMENTATION | 86 | Delayed | 79 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 10/12/2021 | 37.43 | 37.43
127 | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME (SM/14096) | SM/14096 | 2031.4 | 8070 | AUGMENTATION | 86 | On track | 51 | 15/12/2022 | 30/04/2026 | 25/07/2025 | 03/09/2021 | 1044.04 | 1041.95
128 | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME (SM/13240) | SM/13240 | 741.26 | 929 | NEW | 88 | Delayed | 38 | 14/10/2022 | 30/06/2025 | 25/07/2025 | 17/01/2023 | 278.13 | 278.13
129 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) (SM/07133) | SM/07133 | 95.65 | 1169 | RETROFITTING | 88 | Delayed | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 25/01/2021 | 95.65 | 95.65
130 | SISHA JUMRHA PIPED WATER SUPPLY SCHEME (SM/12753) | SM/12753 | 797.79 | 2683 | NEW | 88 | Delayed | 61 | 20/09/2022 | 30/06/2025 | 25/07/2025 | 27/03/2023 | 487.87 | 487.87
131 | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME (SM/10671) | SM/10671 | 152.39 | 38 | AUGMENTATION | 88 | Delayed | 15 | 29/04/2022 | 31/05/2025 | 25/07/2025 | 24/02/2022 | 22.83 | 22.83
132 | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/13239) | SM/13239 | 716.98 | 4031 | NEW | 88 | Delayed | 77 | 14/10/2022 | 31/05/2025 | 25/07/2025 | 17/01/2023 | 550.96 | 550.96
133 | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME (SM/13244) | SM/13244 | 710.27 | 1482 | NEW | 88 | Delayed | 60 | 14/10/2022 | 31/05/2025 | 25/07/2025 | 27/03/2023 | 425.5 | 425.5
134 | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/14092) | SM/14092 | 895.42 | 1884 | NEW | 88 | Delayed | 70 | 12/12/2022 | 31/05/2025 | 25/07/2025 | 02/02/2023 | 625.57 | 625.57
135 | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10173) | SM/10173 | 886.25 | 2277 | NEW | 88 | On track | 95 | 16/02/2022 | 31/12/2025 | 25/07/2025 | 14/10/2020 | 844.96 | 844.2
136 | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/13449) | SM/13449 | 695.45 | 1856 | NEW | 88 | On track | 70 | 02/11/2022 | 31/12/2025 | 25/07/2025 | 01/11/2022 | 487.64 | 487.64
137 | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. (SM/13243) | SM/13243 | 963.61 | 1919 | NEW | 89 | On track | 45 | 14/10/2022 | 30/04/2026 | 25/07/2025 | 27/03/2023 | 437.38 | 437.38
138 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) (SM/07182) | SM/07182 | 98.81 | 870 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 05/01/2022 | 98.81 | 98.81
139 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) (SM/07138) | SM/07138 | 96.46 | 2682 | RETROFITTING | 90 | Delayed | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 12/11/2020 | 96.46 | 96.46
140 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme (SM/07195) | SM/07195 | 98.84 | 1222 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 01/10/2020 | 98.84 | 98.84
141 | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10038) | SM/10038 | 247.03 | 567 | NEW | 90 | Delayed | 31 | 19/01/2022 | 30/06/2025 | 25/07/2025 | 31/08/2021 | 75.89 | 75.89
142 | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10039) | SM/10039 | 284.23 | 1348 | NEW | 90 | Delayed | 92 | 19/01/2022 | 30/06/2025 | 25/07/2025 | 21/02/2022 | 262.75 | 262.75
143 | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME (SM/10668) | SM/10668 | 69.44 | 20 | AUGMENTATION | 90 | Delayed | 30 | 29/04/2022 | 31/05/2025 | 25/07/2025 | 06/04/2023 | 20.89 | 20.89
144 | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14214) | SM/14214 | 527.26 | 1579 | NEW | 90 | Delayed | 83 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 16/03/2023 | 439.81 | 437.55
145 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme (SM/07129) | SM/07129 | 72.16 | 1328 | RETROFITTING | 90 | Delayed | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 26/08/2021 | 72.16 | 72.16
146 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) (SM/07069) | SM/07069 | 61.34 | 1509 | RETROFITTING | 90 | Delayed | 100 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 61.34 | 61.33
147 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) (SM/07060) | SM/07060 | 86.77 | 1400 | RETROFITTING | 90 | On track | 100 | 25/11/2020 | 31/07/2025 | 25/07/2025 | 15/12/2020 | 86.77 | 86.77
148 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme (SM/07064) | SM/07064 | 99.04 | 1612 | RETROFITTING | 90 | Delayed | 96 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 25/01/2021 | 95.51 | 95.26
149 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) (SM/07181) | SM/07181 | 89.66 | 571 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 16/10/2020 | 89.63 | 89.61
150 | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' (SM/09893) | SM/09893 | 45.22 | 0 | AUGMENTATION | 90 | Delayed | 67 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 21/01/2022 | 30.26 | 30.26
151 | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME (SM/10169) | SM/10169 | 378.84 | 1527 | AUGMENTATION | 90 | Delayed | 40 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 05/01/2022 | 150.8 | 144.78
152 | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME (SM/10174) | SM/10174 | 732.56 | 1867 | NEW | 90 | Delayed | 91 | 16/02/2022 | 30/06/2025 | 25/07/2025 | 17/02/2022 | 664 | 650.15
153 | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME (SM/09885) | SM/09885 | 449.91 | 3226 | AUGMENTATION | 90 | Delayed | 99 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 08/09/2020 | 443.61 | 443.61
154 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) (SM/07174) | SM/07174 | 76.33 | 1388 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 05/01/2021 | 76.33 | 76.07
155 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) (SM/07183) | SM/07183 | 56.02 | 870 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 05/01/2022 | 56.02 | 53.47
156 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme (SM/08880) | SM/08880 | 140.24 | 2328 | RETROFITTING | 90 | Delayed | 100 | 27/09/2021 | 31/05/2025 | 25/07/2025 | 14/10/2020 | 140.24 | 140.24
157 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme (SM/08881) | SM/08881 | 184.32 | 874 | RETROFITTING | 90 | Delayed | 77 | 27/09/2021 | 30/06/2025 | 25/07/2025 | 28/12/2020 | 142.8 | 140.37
158 | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME (SM/11484) | SM/11484 | 455.23 | 1520 | NEW | 90 | Delayed | 62 | 14/07/2022 | 31/05/2025 | 25/07/2025 | 15/07/2022 | 282.42 | 281.81
159 | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME (SM/10155) | SM/10155 | 140.66 | 1040 | AUGMENTATION | 90 | Delayed | 97 | 11/02/2022 | 30/06/2025 | 25/07/2025 | 22/11/2021 | 136.56 | 136.56
160 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) (SM/07137) | SM/07137 | 97.16 | 1073 | RETROFITTING | 90 | On track | 90 | 26/11/2020 | 31/07/2025 | 25/07/2025 | 14/10/2020 | 87.69 | 86.26
161 | Rejuvenation of Makrapara TG WSS. (SM/09895) | SM/09895 | 45.22 | 0 | AUGMENTATION | 90 | Delayed | 95 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 31/01/2022 | 42.81 | 42.81
162 | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME (SM/10678) | SM/10678 | 274.45 | 2100 | AUGMENTATION | 90 | Delayed | 27 | 29/04/2022 | 31/05/2025 | 25/07/2025 | 27/02/2023 | 73.02 | 73.02
163 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) (SM/07121) | SM/07121 | 82.27 | 2686 | RETROFITTING | 90 | Delayed | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 19/02/2021 | 82.27 | 79.34
164 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) (SM/07068) | SM/07068 | 85.62 | 1509 | RETROFITTING | 90 | Delayed | 93 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 80.01 | 78.16
165 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme (SM/07198) | SM/07198 | 69.04 | 882 | RETROFITTING | 90 | Delayed | 93 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 19/10/2020 | 64.04 | 62.48
166 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) (SM/07175) | SM/07175 | 91.69 | 2686 | RETROFITTING | 90 | Delayed | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 19/02/2021 | 91.69 | 91.69
167 | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10179) | SM/10179 | 364.15 | 647 | NEW | 90 | On track | 94 | 16/02/2022 | 31/12/2025 | 25/07/2025 | 17/02/2022 | 341.77 | 341.25
168 | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/12114) | SM/12114 | 588.27 | 1999 | NEW | 90 | On track | 61 | 02/09/2022 | 30/04/2027 | 25/07/2025 | 21/11/2022 | 358.34 | 358.34
169 | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14212) | SM/14212 | 570.23 | 2321 | NEW | 90 | Delayed | 68 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 31/01/2023 | 389.63 | 389.12
170 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) (SM/07066) | SM/07066 | 80.75 | 2682 | RETROFITTING | 90 | Delayed | 97 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 22/02/2021 | 78.4 | 78.08
171 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) (SM/07057) | SM/07057 | 99.09 | 2066 | RETROFITTING | 90 | Delayed | 100 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 15/12/2020 | 99.09 | 99.09
172 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) (SM/07059) | SM/07059 | 97.58 | 967 | RETROFITTING | 90 | Delayed | 100 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 97.58 | 97.58
173 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme (SM/08882) | SM/08882 | 129.45 | 1096 | RETROFITTING | 90 | Delayed | 100 | 27/09/2021 | 31/05/2025 | 25/07/2025 | 05/10/2021 | 129.45 | 128.72
174 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme (SM/08883) | SM/08883 | 87.85 | 1393 | RETROFITTING | 90 | Delayed | 100 | 27/09/2021 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 87.85 | 82.8
175 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) (SM/07058) | SM/07058 | 82.69 | 1036 | RETROFITTING | 90 | Delayed | 95 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 05/01/2021 | 78.7 | 76.99
176 | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10172) | SM/10172 | 810.28 | 2579 | NEW | 90 | Delayed | 74 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 17/02/2022 | 602.25 | 602.24
177 | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME (SM/10154) | SM/10154 | 632.84 | 3764 | AUGMENTATION | 90 | Delayed | 95 | 11/02/2022 | 30/06/2025 | 25/07/2025 | 27/01/2021 | 599.53 | 578.97
178 | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME (SM/11482) | SM/11482 | 395.23 | 1493 | NEW | 90 | Delayed | 56 | 14/07/2022 | 31/05/2025 | 25/07/2025 | 15/07/2022 | 221.81 | 221.8
179 | TELIPARA PIPED WATER SUPPLY SCHEME. (SM/13303) | SM/13303 | 488.14 | 1029 | NEW | 90 | On track | 40 | 17/10/2022 | 30/11/2025 | 25/07/2025 | 31/03/2023 | 196.8 | 196.8
180 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) (SM/07065) | SM/07065 | 73.85 | 596 | RETROFITTING | 90 | Delayed | 46 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 16/10/2020 | 34.11 | 34.11
181 | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' (SM/09901) | SM/09901 | 44.25 | 0 | AUGMENTATION | 90 | Delayed | 71 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 18/02/2022 | 31.47 | 31.47
182 | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME (SM/11402) | SM/11402 | 86.31 | 608 | AUGMENTATION | 90 | Delayed | 73 | 04/07/2022 | 30/06/2025 | 25/07/2025 | 13/09/2021 | 62.76 | 62.76
183 | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME (SM/11991) | SM/11991 | 432.05 | 1128 | NEW | 90 | Delayed | 77 | 01/09/2022 | 31/05/2025 | 25/07/2025 | 21/11/2022 | 332.44 | 332.44
184 | BRAJERKUTHI PIPED WATER SUPPLY SCHEME (SM/13300) | SM/13300 | 944.2 | 1847 | NEW | 90 | Delayed | 61 | 17/10/2022 | 31/05/2025 | 25/07/2025 | 17/01/2023 | 572.37 | 571.36
185 | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/14093) | SM/14093 | 528.73 | 1074 | NEW | 90 | Delayed | 43 | 12/12/2022 | 31/05/2025 | 25/07/2025 | 27/02/2023 | 229.49 | 229.49
186 | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. (SM/08580) | SM/08580 | 295.97 | 882 | NEW | 90 | On track | 71 | 10/02/2021 | 31/08/2025 | 25/07/2025 | 25/02/2021 | 209.39 | 201.21
187 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) (SM/07176) | SM/07176 | 70.54 | 1621 | RETROFITTING | 90 | Delayed | 98 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 68.86 | 68.86
188 | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14215) | SM/14215 | 336.47 | 1002 | NEW | 90 | On track | 63 | 10/01/2023 | 30/04/2027 | 25/07/2025 | 31/03/2023 | 212.27 | 212.27
189 | TORSHA FOREST PIPED WATER SUPPLY SCHEME (SM/14220) | SM/14220 | 142.14 | 201 | NEW | 90 | Delayed | 68 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 19/01/2023 | 95.99 | 95.99
190 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme (SM/07196) | SM/07196 | 67.24 | 803 | RETROFITTING | 90 | On track | 89 | 04/12/2020 | 30/11/2025 | 25/07/2025 | 15/07/2021 | 59.64 | 59.63
191 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme (SM/07199) | SM/07199 | 61.63 | 688 | RETROFITTING | 90 | Delayed | 87 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 53.58 | 48.89
192 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME (SM/10776) | SM/10776 | 167.97 | 0 | NEW | 91 | Delayed | 58 | 23/05/2022 | 31/05/2025 | 25/07/2025 | 31/05/2022 | 97.37 | 97.37
193 | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME (SM/10170) | SM/10170 | 509.72 | 2836 | AUGMENTATION | 92 | Delayed | 64 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 16/10/2020 | 327.27 | 312.74
194 | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME (SM/10171) | SM/10171 | 750.42 | 3164 | AUGMENTATION | 92 | Delayed | 84 | 16/02/2022 | 31/05/2025 | 25/07/2025 | 05/01/2021 | 627.8 | 618.84
195 | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME (SM/09903) | SM/09903 | 45.22 | 0 | AUGMENTATION | 93 | Delayed | 92 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 05/10/2021 | 41.67 | 29.71
196 | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME (SM/14216) | SM/14216 | 129.41 | 130 | NEW | 93 | Delayed | 68 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 19/01/2023 | 87.81 | 87.81
197 | NURPUR PIPED WATER SUPPLY SCHEME. (SM/14218) | SM/14218 | 451.36 | 423 | NEW | 93 | Delayed | 46 | 10/01/2023 | 31/05/2025 | 25/07/2025 | 27/02/2023 | 208.21 | 208.21
198 | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME (SM/09896) | SM/09896 | 45.23 | 0 | AUGMENTATION | 93 | On track | 66 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 31/01/2022 | 29.82 | 29.82
199 | Rejuvenation of Gargenda Tea Garden Water Supply Scheme (SM/09906) | SM/09906 | 45.22 | 0 | AUGMENTATION | 94 | On track | 33 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 31/08/2021 | 14.94 | 14.94
200 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme (SM/07184) | SM/07184 | 82.41 | 901 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 15/12/2020 | 82.41 | 82.27
201 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) (SM/07062) | SM/07062 | 87.86 | 2826 | RETROFITTING | 95 | On track | 100 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 14/10/2020 | 87.86 | 87.86
202 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) (SM/07126) | SM/07126 | 93 | 1051 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 93 | 93
203 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) (SM/07122) | SM/07122 | 98.68 | 1623 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 98.68 | 98.68
204 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) (SM/07067) | SM/07067 | 98.86 | 345 | RETROFITTING | 95 | On track | 100 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 98.86 | 98.86
205 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) (SM/07125) | SM/07125 | 90.17 | 1051 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 90.17 | 90.17
206 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) (SM/07127) | SM/07127 | 66.37 | 1051 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 66.37 | 66.37
207 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme (SM/07193) | SM/07193 | 60.86 | 608 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 01/10/2020 | 60.86 | 60.86
208 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme (SM/07190) | SM/07190 | 83.82 | 1026 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 83.82 | 83.8
209 | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' (SM/09888) | SM/09888 | 43.87 | 0 | AUGMENTATION | 95 | On track | 66 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 14/01/2022 | 29.08 | 29.08
210 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) (SM/07177) | SM/07177 | 68.96 | 761 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 05/01/2021 | 68.96 | 68.96
211 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) (SM/07179) | SM/07179 | 69.14 | 1419 | RETROFITTING | 95 | On track | 62 | 04/12/2020 | 30/06/2025 | 25/07/2025 | 15/12/2020 | 42.87 | 42.69
212 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) (SM/07178) | SM/07178 | 98.08 | 1419 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 15/12/2020 | 98.08 | 98.03
213 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) (SM/07123) | SM/07123 | 98.96 | 1051 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 14/10/2020 | 98.96 | 98.96
214 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) (SM/07135) | SM/07135 | 87.03 | 822 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 14/10/2020 | 87.03 | 87.03
215 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) (SM/07186) | SM/07186 | 99.29 | 345 | RETROFITTING | 95 | On track | 86 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 03/09/2020 | 85 | 81.62
216 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) (SM/07063) | SM/07063 | 91.9 | 1709 | RETROFITTING | 95 | On track | 97 | 25/11/2020 | 31/05/2025 | 25/07/2025 | 28/12/2020 | 89.1 | 88.58
217 | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME (SM/09910) | SM/09910 | 47.45 | 0 | AUGMENTATION | 95 | On track | 49 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 05/01/2022 | 23.06 | 23.06
218 | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11709) | SM/11709 | 817.44 | 1702 | NEW | 95 | Delayed | 83 | 29/07/2022 | 31/05/2025 | 25/07/2025 | 31/08/2022 | 676.55 | 676.53
219 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) (SM/07124) | SM/07124 | 55.28 | 1477 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 15/12/2020 | 55.28 | 47.81
220 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) (SM/07134) | SM/07134 | 89.44 | 1477 | RETROFITTING | 95 | On track | 100 | 26/11/2020 | 31/05/2025 | 25/07/2025 | 15/12/2020 | 89.44 | 89.4
221 | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME (SM/09898) | SM/09898 | 47.48 | 608 | AUGMENTATION | 95 | On track | 89 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 20/03/2020 | 42.47 | 38.71
222 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) (SM/07185) | SM/07185 | 82.87 | 1623 | RETROFITTING | 95 | On track | 100 | 04/12/2020 | 31/05/2025 | 25/07/2025 | 13/09/2021 | 82.87 | 82.87
223 | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME (SM/09886) | SM/09886 | 257.81 | 2202 | AUGMENTATION | 95 | Delayed | 96 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 11/01/2022 | 246.85 | 244.39
224 | Bhutri Forest Piped Water Supply Scheme (SM/18156) | SM/18156 | 59.54 | 48 | NEW | 95 | Delayed | 31 | 29/03/2023 | 31/05/2025 | 25/07/2025 | 18/04/2023 | 18.24 | 18.24
225 | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' (SM/09905) | SM/09905 | 45.51 | 0 | AUGMENTATION | 97 | On track | 24 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 03/09/2020 | 11 | 11
226 | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME (SM/09899) | SM/09899 | 45.28 | 0 | AUGMENTATION | 97 | On track | 80 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 31/01/2022 | 36.01 | 34.57
227 | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' (SM/09890) | SM/09890 | 45.21 | 0 | AUGMENTATION | 98 | On track | 46 | 08/12/2021 | 30/06/2025 | 25/07/2025 | 11/01/2022 | 20.92 | 20.92
228 | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME (SM/09897) | SM/09897 | 45.48 | 0 | AUGMENTATION | 98 | On track | 84 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 19/02/2021 | 38.35 | 37.82
229 | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME (SM/09907) | SM/09907 | 44.74 | 0 | AUGMENTATION | 98 | On track | 5 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 22/12/2021 | 2.12 | 2.39
230 | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME (SM/09887) | SM/09887 | 92.5 | 0 | AUGMENTATION | 98 | On track | 60 | 08/12/2021 | 30/04/2027 | 25/07/2025 | 26/08/2021 | 55.45 | 52.6
231 | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME (SM/09892) | SM/09892 | 47.49 | 0 | AUGMENTATION | 98 | On track | 73 | 08/12/2021 | 31/05/2025 | 25/07/2025 | 05/10/2021 | 34.43 | 32.83
232 | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. (SM/06623) | SM/06623 | 21.16 | 0 | SUPPORT-WQMSP | 99 | Delayed | 0 | 05/02/2020 | 31/03/2024 | 29/01/2024 | 23/06/2021 | 0 | 0
233 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme (SM/07192) | SM/07192 | 83.76 | 1000 | RETROFITTING | 100 | 100% Physical | 100 | 04/12/2020 | 31/07/2021 | 25/07/2025 | 29/07/2022 | 83.76 | 83.76
234 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme (SM/07194) | SM/07194 | 98.15 | 1298 | RETROFITTING | 100 | 100% Physical | 100 | 04/12/2020 | 30/09/2021 | 25/07/2025 | 22/11/2021 | 98.15 | 98.15
Total |  |  | 90019.48 | 362528 | [8 empty] | 49525.83 | 49299.23