## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Supply , Delivery and Installation of Computer & Peripherial Device for Official use Under Office of Executive Engineer , Alipurduar Division,P.H.E (SM/12120) | SM/12120 | 13.4 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 07/09/2022 |  | 11/09/2022 | 16/12/2022 | 0 | 0
2 | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the EE/NMD-II, AE/AMSD & Office of the AE/CMSD, PHE Dte. (SM/17189) | SM/17189 | 22.16 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 15/03/2023 |  | 22/03/2023 |  | 0 | 0
3 | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 (SM/19170) | SM/19170 | 99.19 | 0 | SUPPORT- IEC / BCC/ IPC | 0 | WO no issued | 0 | 08/02/2024 |  | 15/02/2024 |  | 0 | 0
4 | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/19081) | SM/19081 | 58.05 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 24/04/2024 | 0 | 0
5 | BUXA PIPE WATER SUPPLY SCHEME (SM/16507) | SM/16507 | 219.61 | 219 | NEW | 3 | Delayed | 7 | 03/03/2023 | 23/08/2024 | 01/12/2023 | 23/03/2023 | 16.34 | 16.34
6 | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME (SM/10672) | SM/10672 | 162.74 | 30 | AUGMENTATION | 5 | Delayed | 0 | 29/04/2022 | 31/12/2024 | 28/03/2024 | 10/08/2022 | 0 | 0
7 | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' (SM/09900) | SM/09900 | 45.23 | 0 | AUGMENTATION | 5 | Delayed | 7 | 08/12/2021 | 31/03/2024 | 01/12/2023 | 20/05/2022 | 2.97 | 2.87
8 | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10054) | SM/10054 | 332.16 | 2682 | NEW | 5 | Delayed | 19 | 25/01/2022 | 11/02/2025 | 06/03/2024 | 08/09/2023 | 62.28 | 15.33
9 | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME (SM/16506) | SM/16506 | 990.41 | 1752 | NEW | 7 | Delayed | 4 | 03/03/2023 | 23/09/2024 | 01/12/2023 | 04/04/2023 | 34.85 | 34.85
10 | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME (SM/15914) | SM/15914 | 358.24 | 567 | NEW | 9 | Delayed | 7 | 22/02/2023 | 24/09/2024 | 01/12/2023 | 24/04/2023 | 26.78 | 26.78
11 | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED MANAGED LABORATORIES (SM/12752) | SM/12752 | 41.13 | 0 | SUPPORT-WQMSP | 10 | Delayed | 0 | 20/09/2022 | 31/03/2025 | 29/01/2024 | 31/03/2023 | 0 | 0
12 | Parpatla Khawa Piped Water Supply Scheme (SM/18158) | SM/18158 | 187.87 | 189 | NEW | 12 | Delayed | 0 | 29/03/2023 | 04/10/2024 | 28/03/2024 | 04/05/2023 | 0 | 0
13 | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/16821) | SM/16821 | 405.28 | 442 | NEW | 14 | Delayed | 5 | 13/03/2023 | 31/12/2024 | 28/03/2024 | 31/03/2023 | 22.19 | 15.52
14 | UMACHARANPUR PIPED WATER SUPPLY SCHEME (SM/16114) | SM/16114 | 950.07 | 3053 | NEW | 15 | Delayed | 13 | 22/02/2023 | 02/01/2025 | 04/04/2024 | 07/09/2023 | 120.76 | 108.72
15 | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME (SM/13249) | SM/13249 | 860.22 | 2652 | NEW | 16 | Delayed | 13 | 14/10/2022 | 23/08/2024 | 29/02/2024 | 01/11/2022 | 114.33 | 114.33
16 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14213) | SM/14213 | 740.97 | 2268 | NEW | 16 | Delayed | 5 | 10/01/2023 | 31/12/2024 | 28/03/2024 | 03/08/2023 | 36.25 | 12.09
17 | FOSKADANGA PIPED WATER SUPPLY SCHEME (SM/14210) | SM/14210 | 510.99 | 684 | NEW | 17 | Delayed | 40 | 10/01/2023 | 27/08/2024 | 28/03/2024 | 27/03/2023 | 203.15 | 190.23
18 | Uttar Dhalkar Piped Water Supply Scheme (SM/18154) | SM/18154 | 404.14 | 594 | NEW | 18 | Delayed | 27 | 29/03/2023 | 04/10/2024 | 29/03/2024 | 04/05/2023 | 107.67 | 0
19 | PAKRIGURI PIPED WAYER SUPPLY SCHEME. (SM/14223) | SM/14223 | 509.75 | 603 | NEW | 18 | Delayed | 6 | 10/01/2023 | 30/09/2024 | 29/03/2024 | 31/03/2023 | 31.92 | 31.92
20 | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/16822) | SM/16822 | 569.65 | 1184 | NEW | 18 | Delayed | 9 | 13/03/2023 | 31/03/2025 | 28/03/2024 | 19/05/2023 | 49.65 | 49.65
21 | AUGMENTATION OF DALIMPUR PWSS (SM/18254) | SM/18254 | 1020.25 | 3047 | AUGMENTATION | 18 | Delayed | 15 | 21/06/2023 | 12/12/2024 | 28/03/2024 | 12/07/2023 | 151.56 | 134.61
22 | Khagenhat Piped Water Supply Scheme (SM/18151) | SM/18151 | 822.98 | 2057 | NEW | 19 | Delayed | 2 | 29/03/2023 | 04/10/2024 | 28/03/2024 | 08/05/2023 | 12.67 | 12.67
23 | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME (SM/16819) | SM/16819 | 658.29 | 1272 | NEW | 20 | Delayed | 21 | 13/03/2023 | 31/12/2024 | 10/05/2024 | 03/08/2023 | 140.9 | 123.13
24 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12911) | SM/12911 | 32.31 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 02/09/2021 | 0 | 0
25 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12910) | SM/12910 | 12.66 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 11/01/2023 | 0 | 0
26 | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 (SM/12909) | SM/12909 | 12.66 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/09/2022 | 31/03/2025 | 29/01/2024 | 11/01/2023 | 0 | 0
27 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) (SM/07132) | SM/07132 | 88.7 | 1847 | RETROFITTING | 22 | Delayed | 16 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 25/01/2021 | 13.95 | 13.76
28 | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. (SM/16824) | SM/16824 | 273.66 | 0 | AUGMENTATION | 22 | Delayed | 19 | 13/03/2023 | 31/12/2024 | 28/03/2024 | 22/03/2023 | 51.47 | 0
29 | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. (SM/13242) | SM/13242 | 615.61 | 1001 | NEW | 22 | Delayed | 22 | 14/10/2022 | 16/09/2024 | 29/03/2024 | 16/03/2023 | 134.76 | 134.76
30 | BARIGURI PIPED WATER SUPPLY SCHEME (SM/13246) | SM/13246 | 895.77 | 3454 | NEW | 28 | Delayed | 4 | 14/10/2022 | 16/11/2024 | 28/03/2024 | 16/05/2023 | 33.38 | 33.38
31 | PRODHANPARA PIPED WATER SUPPLY SCHEME (SM/13247) | SM/13247 | 638.14 | 1353 | NEW | 28 | Delayed | 32 | 14/10/2022 | 16/08/2024 | 28/03/2024 | 16/03/2023 | 203.28 | 181.9
32 | PARARPAR PIPED WATER SUPPLY SCHEME (SM/14209) | SM/14209 | 561.82 | 1187 | NEW | 28 | Delayed | 37 | 10/01/2023 | 16/08/2024 | 28/03/2024 | 16/03/2023 | 209.33 | 197.58
33 | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME (SM/16817) | SM/16817 | 808.5 | 1601 | NEW | 28 | Delayed | 36 | 13/03/2023 | 20/01/2025 | 04/04/2024 | 20/07/2023 | 293.68 | 279.25
34 | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME (SM/13241) | SM/13241 | 780.16 | 1437 | NEW | 29 | Delayed | 29 | 14/10/2022 | 17/06/2024 | 29/03/2024 | 17/01/2023 | 227.56 | 227.56
35 | NAOTHOARTARI PIPED WATER SUPPLY SCHEME (SM/12754) | SM/12754 | 415.72 | 295 | NEW | 31 | Delayed | 42 | 20/09/2022 | 31/08/2024 | 28/03/2024 | 31/03/2023 | 175.86 | 175.86
36 | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME (SM/11765) | SM/11765 | 154.07 | 110 | AUGMENTATION | 32 | Delayed | 34 | 03/08/2022 | 04/09/2024 | 01/12/2023 | 20/09/2021 | 51.71 | 51.71
37 | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/15482) | SM/15482 | 1380.67 | 5753 | NEW | 33 | Delayed | 19 | 13/02/2023 | 01/09/2024 | 28/03/2024 | 01/11/2022 | 259.16 | 189.63
38 | Malangi Tea Garden Area Piped Water Supply Scheme (SM/18150) | SM/18150 | 561.45 | 2115 | NEW | 33 | Delayed | 4 | 29/03/2023 | 28/10/2024 | 03/05/2024 | 04/05/2023 | 23.39 | 22.03
39 | BENGKANDI PIPED WATER SUPPLY SCHEME (SM/16820) | SM/16820 | 964.09 | 2074 | NEW | 33 | Delayed | 34 | 13/03/2023 | 28/01/2025 | 28/03/2024 | 28/07/2023 | 326.82 | 178.94
40 | NARASINGPUR PIPED WATER SUPPLY SCHEME (SM/15758) | SM/15758 | 842.46 | 2461 | NEW | 33 | Delayed | 53 | 20/02/2023 | 20/01/2025 | 28/03/2024 | 20/07/2023 | 442.96 | 427.92
41 | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME (SM/10669) | SM/10669 | 161.24 | 50 | AUGMENTATION | 33 | Delayed | 8 | 29/04/2022 | 31/12/2024 | 29/03/2024 | 13/05/2022 | 13.42 | 13.42
42 | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME (SM/12361) | SM/12361 | 1269.79 | 1277 | AUGMENTATION | 34 | Delayed | 11 | 13/09/2022 | 10/06/2024 | 28/03/2024 | 27/02/2023 | 138.99 | 138.99
43 | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME (SM/13448) | SM/13448 | 305.16 | 563 | NEW | 34 | Delayed | 21 | 02/11/2022 | 06/11/2024 | 29/03/2024 | 06/06/2023 | 62.7 | 62.7
44 | MAIRADANGA PIPED WATER SUPPLY SCHEME (SM/15206) | SM/15206 | 963.71 | 2583 | NEW | 35 | Delayed | 23 | 07/02/2023 | 16/10/2024 | 28/03/2024 | 16/05/2023 | 218.01 | 218.01
45 | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/11960) | SM/11960 | 512.91 | 1031 | AUGMENTATION | 36 | Delayed | 20 | 25/08/2022 | 27/05/2024 | 28/03/2024 | 22/12/2022 | 101.36 | 75.52
46 | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME (SM/13248) | SM/13248 | 877.17 | 2462 | NEW | 37 | Delayed | 48 | 14/10/2022 | 27/08/2024 | 28/03/2024 | 27/03/2023 | 421.41 | 397.05
47 | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME (SM/14222) | SM/14222 | 429.71 | 729 | NEW | 37 | Delayed | 27 | 10/01/2023 | 27/08/2024 | 28/03/2024 | 27/03/2023 | 115.69 | 115.69
48 | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME (SM/14217) | SM/14217 | 409.38 | 794 | NEW | 38 | Delayed | 27 | 10/01/2023 | 16/08/2024 | 28/03/2024 | 01/11/2022 | 110.34 | 110.34
49 | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme (SM/18157) | SM/18157 | 360.16 | 725 | NEW | 38 | Delayed | 24 | 29/03/2023 | 22/10/2024 | 29/03/2024 | 22/05/2023 | 85.16 | 75.23
50 | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME (SM/14096) | SM/14096 | 2031.4 | 8070 | AUGMENTATION | 38 | Delayed | 43 | 15/12/2022 | 21/05/2024 | 29/03/2024 | 03/09/2021 | 882.79 | 832
51 | MALSAGAON PIPED WATER SUPPLY SCHEME (SM/16818) | SM/16818 | 777.46 | 1481 | NEW | 38 | Delayed | 64 | 13/03/2023 | 02/01/2025 | 28/03/2024 | 07/09/2023 | 500.85 | 500.85
52 | Rejuvenation Of Dima T.G. W.S.S (SM/09904) | SM/09904 | 44.51 | 0 | AUGMENTATION | 39 | Delayed | 38 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 16.93 | 13.51
53 | CHALNIPAK PIPED WATER SUPPLY SCHEME. (SM/15534) | SM/15534 | 1024.4 | 1648 | NEW | 39 | Delayed | 39 | 16/02/2023 | 01/09/2024 | 29/03/2024 | 22/02/2023 | 394.91 | 394.53
54 | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME (SM/11767) | SM/11767 | 204.15 | 250 | AUGMENTATION | 39 | Delayed | 24 | 03/08/2022 | 13/05/2024 | 28/03/2024 | 20/09/2021 | 48.44 | 48.44
55 | KALABERIA PIPED WATER SUPPLY SCHEME (SM/13306) | SM/13306 | 461.28 | 1065 | NEW | 40 | Delayed | 34 | 17/10/2022 | 27/08/2024 | 28/03/2024 | 27/03/2023 | 157.42 | 157.42
56 | KAYAKHATA PIPED WATER SUPPLY SCHEME (SM/13299) | SM/13299 | 682.41 | 1585 | NEW | 42 | Delayed | 27 | 17/10/2022 | 16/09/2024 | 04/04/2024 | 16/03/2023 | 183.63 | 180.42
57 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme (SM/07180) | SM/07180 | 64.83 | 624 | RETROFITTING | 42 | Delayed | 55 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 23/03/2023 | 35.82 | 11.34
58 | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/16823) | SM/16823 | 739.67 | 1298 | NEW | 42 | Delayed | 29 | 13/03/2023 | 31/12/2024 | 28/03/2024 | 31/03/2023 | 215.9 | 189.79
59 | Dhantali Piped Water Supply Scheme (SM/18153) | SM/18153 | 285.56 | 206 | NEW | 43 | Delayed | 38 | 29/03/2023 | 04/10/2024 | 29/03/2024 | 04/05/2023 | 109.13 | 109.13
60 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) (SM/07059) | SM/07059 | 97.58 | 967 | RETROFITTING | 43 | Delayed | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 97.58 | 97.58
61 | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. (SM/15210) | SM/15210 | 111.32 | 0 | AUGMENTATION | 43 | Delayed | 26 | 07/02/2023 | 13/08/2024 | 28/03/2024 | 13/03/2023 | 28.84 | 8.44
62 | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME (SM/14233) | SM/14233 | 2288.93 | 9924 | AUGMENTATION | 46 | Delayed | 29 | 11/01/2023 | 17/06/2024 | 28/03/2024 | 22/11/2021 | 654.08 | 510.18
63 | DHANIRAMPUR PIPED WATER SUPPLY SCHEME (SM/15208) | SM/15208 | 670.33 | 1552 | NEW | 46 | Delayed | 58 | 07/02/2023 | 31/12/2024 | 28/03/2024 | 31/03/2023 | 391.35 | 371.65
64 | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME (SM/10678) | SM/10678 | 274.45 | 2100 | AUGMENTATION | 47 | Delayed | 27 | 29/04/2022 | 01/09/2024 | 28/03/2024 | 27/02/2023 | 73.02 | 73.02
65 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme (SM/07130) | SM/07130 | 94.15 | 1568 | RETROFITTING | 47 | Delayed | 91 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 16/09/2020 | 86.11 | 86.11
66 | Chengmari Piped Water Supply Scheme (SM/18152) | SM/18152 | 772.15 | 1699 | NEW | 47 | Delayed | 47 | 29/03/2023 | 04/10/2024 | 29/03/2024 | 04/05/2023 | 360.17 | 360.17
67 | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME (SM/15207) | SM/15207 | 802.95 | 2097 | NEW | 50 | On track | 32 | 07/02/2023 | 20/01/2025 | 28/03/2024 | 20/07/2023 | 254.59 | 254.59
68 | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME (SM/11959) | SM/11959 | 648.63 | 807 | AUGMENTATION | 50 | Delayed | 4 | 25/08/2022 | 19/11/2024 | 28/03/2024 | 05/09/2022 | 25.17 | 25.17
69 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme (SM/07131) | SM/07131 | 73.16 | 567 | RETROFITTING | 50 | Delayed | 92 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 12/11/2020 | 67.15 | 67.15
70 | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. (SM/15209) | SM/15209 | 112.19 | 0 | AUGMENTATION | 52 | Delayed | 32 | 07/02/2023 | 13/08/2024 | 28/03/2024 | 13/03/2023 | 36.07 | 20.28
71 | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' (SM/09893) | SM/09893 | 45.22 | 0 | AUGMENTATION | 52 | Delayed | 67 | 08/12/2021 | 23/08/2024 | 29/02/2024 | 21/01/2022 | 30.26 | 30.26
72 | TELIPARA PIPED WATER SUPPLY SCHEME. (SM/13303) | SM/13303 | 488.14 | 1029 | NEW | 52 | Delayed | 25 | 17/10/2022 | 30/09/2024 | 29/03/2024 | 31/03/2023 | 123.39 | 123.39
73 | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' (SM/09902) | SM/09902 | 47.49 | 0 | AUGMENTATION | 53 | Delayed | 59 | 08/12/2021 | 31/03/2024 | 28/03/2024 | 10/12/2021 | 27.8 | 19.74
74 | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME (SM/13302) | SM/13302 | 171.75 | 308 | NEW | 53 | Delayed | 52 | 17/10/2022 | 19/06/2024 | 28/03/2024 | 19/01/2023 | 88.7 | 79.53
75 | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. (SM/16537) | SM/16537 | 1261.38 | 1778 | NEW | 53 | Delayed | 25 | 10/03/2023 | 27/08/2024 | 04/04/2024 | 27/03/2023 | 309.28 | 294.27
76 | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION (SM/11878) | SM/11878 | 21.39 | 0 | SUPPORT-WQMSP | 55 | On track | 0 | 17/08/2022 | 31/03/2025 | 29/01/2024 | 24/12/2021 | 0 | 0
77 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme (SM/07129) | SM/07129 | 72.16 | 1328 | RETROFITTING | 56 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 26/08/2021 | 72.16 | 72.16
78 | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME (SM/13301) | SM/13301 | 875.66 | 1869 | NEW | 56 | Delayed | 42 | 17/10/2022 | 30/09/2024 | 29/03/2024 | 01/11/2022 | 368.96 | 313.55
79 | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10177) | SM/10177 | 338.59 | 1248 | NEW | 56 | Delayed | 69 | 16/02/2022 | 31/03/2024 | 29/02/2024 | 19/02/2021 | 232.54 | 231.87
80 | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. (SM/10670) | SM/10670 | 108.13 | 45 | AUGMENTATION | 56 | Delayed | 27 | 29/04/2022 | 31/05/2024 | 29/03/2024 | 19/09/2022 | 29.6 | 29.6
81 | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10176) | SM/10176 | 426.36 | 1425 | NEW | 56 | Delayed | 45 | 16/02/2022 | 31/03/2024 | 29/03/2024 | 17/02/2022 | 191.55 | 178.77
82 | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME (SM/11958) | SM/11958 | 562.16 | 493 | AUGMENTATION | 57 | Delayed | 30 | 25/08/2022 | 21/04/2024 | 29/03/2024 | 28/06/2022 | 166.15 | 154.41
83 | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME (SM/09894) | SM/09894 | 44.01 | 0 | AUGMENTATION | 57 | Delayed | 62 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 14/01/2022 | 27.25 | 8.86
84 | TURTURI PIPED WATER SUPPLY SCHEME. (SM/14219) | SM/14219 | 948.08 | 1003 | NEW | 57 | Delayed | 34 | 10/01/2023 | 27/08/2024 | 29/03/2024 | 27/03/2023 | 323.55 | 301.35
85 | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME (SM/11970) | SM/11970 | 1275.43 | 7780 | AUGMENTATION | 58 | Delayed | 29 | 29/08/2022 | 30/06/2024 | 28/03/2024 | 13/09/2021 | 374.96 | 360.69
86 | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME (SM/16115) | SM/16115 | 240.25 | 0 | AUGMENTATION | 58 | Delayed | 0 | 22/02/2023 | 18/09/2024 | 28/03/2024 | 31/01/2023 | 0 | 0
87 | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME (SM/09897) | SM/09897 | 45.48 | 0 | AUGMENTATION | 59 | Delayed | 84 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 19/02/2021 | 38.35 | 37.82
88 | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' (SM/09908) | SM/09908 | 46.31 | 0 | AUGMENTATION | 59 | Delayed | 64 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 11/01/2022 | 29.45 | 29.45
89 | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME (SM/11985) | SM/11985 | 2156.38 | 7273 | AUGMENTATION | 59 | Delayed | 37 | 01/09/2022 | 30/06/2024 | 29/03/2024 | 14/10/2020 | 798.1 | 779.71
90 | SIDHABARI PIED WATER SUPPLY SCHEME (SM/10175) | SM/10175 | 360.32 | 1605 | NEW | 60 | Delayed | 84 | 16/02/2022 | 31/03/2024 | 28/03/2024 | 05/01/2022 | 301.46 | 301.46
91 | Bandpani Tea Garden Areas Piped Water Supply Scheme. (SM/11483) | SM/11483 | 528.37 | 1272 | NEW | 60 | Delayed | 43 | 14/07/2022 | 31/03/2024 | 26/12/2023 | 27/01/2021 | 229.58 | 229.55
92 | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME (SM/11459) | SM/11459 | 1873.61 | 7440 | AUGMENTATION | 60 | Delayed | 53 | 12/07/2022 | 31/03/2024 | 28/03/2024 | 20/09/2021 | 989.73 | 927.32
93 | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME (SM/11401) | SM/11401 | 140.89 | 2981 | AUGMENTATION | 60 | Delayed | 90 | 04/07/2022 | 31/03/2024 | 28/03/2024 | 12/11/2020 | 126.61 | 126.06
94 | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION (SM/11752) | SM/11752 | 18.35 | 0 | SUPPORT-WQMSP | 60 | On track | 0 | 03/08/2022 | 31/03/2025 | 29/01/2024 | 07/08/2023 | 0 | 0
95 | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. (SM/13243) | SM/13243 | 963.61 | 1919 | NEW | 61 | On track | 39 | 14/10/2022 | 30/11/2024 | 29/03/2024 | 27/03/2023 | 377.08 | 356.7
96 | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME (SM/09909) | SM/09909 | 45.46 | 0 | AUGMENTATION | 61 | Delayed | 84 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 27/12/2021 | 38.37 | 34.91
97 | BALLALGURI PIPED WATER SUPPLY SCHEME (SM/14221) | SM/14221 | 413.54 | 609 | NEW | 61 | Delayed | 35 | 10/01/2023 | 01/09/2024 | 28/03/2024 | 02/02/2023 | 142.98 | 127.54
98 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme (SM/08883) | SM/08883 | 87.85 | 1393 | RETROFITTING | 61 | Delayed | 100 | 27/09/2021 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 87.85 | 82.8
99 | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14211) | SM/14211 | 530.22 | 1604 | NEW | 61 | Delayed | 26 | 10/01/2023 | 01/09/2024 | 28/03/2024 | 27/02/2023 | 139.33 | 139.33
100 | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14215) | SM/14215 | 336.47 | 1002 | NEW | 61 | Delayed | 38 | 10/01/2023 | 30/09/2024 | 28/03/2024 | 31/03/2023 | 129.26 | 129.26
101 | SISHA JUMRHA PIPED WATER SUPPLY SCHEME (SM/12753) | SM/12753 | 797.79 | 2683 | NEW | 62 | Delayed | 42 | 20/09/2022 | 27/09/2024 | 28/03/2024 | 27/03/2023 | 338.79 | 338.79
102 | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' (SM/09888) | SM/09888 | 43.87 | 0 | AUGMENTATION | 62 | Delayed | 65 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 14/01/2022 | 28.53 | 18.35
103 | REJUVENATION OF 'CHOTO SALKUMAR WATER SUPPLY SCHEME' (SM/09903) | SM/09903 | 45.22 | 0 | AUGMENTATION | 63 | Delayed | 85 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 05/10/2021 | 38.24 | 26.27
104 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) (SM/07061) | SM/07061 | 93.85 | 1581 | RETROFITTING | 64 | Delayed | 100 | 25/11/2020 | 31/03/2024 | 29/02/2024 | 15/12/2020 | 93.85 | 93.85
105 | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME (SM/11766) | SM/11766 | 88.14 | 400 | AUGMENTATION | 64 | Delayed | 40 | 03/08/2022 | 13/05/2024 | 28/03/2024 | 13/12/2022 | 35.67 | 30.66
106 | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME (SM/16539) | SM/16539 | 1121.63 | 2329 | NEW | 64 | On track | 33 | 10/03/2023 | 28/01/2025 | 28/03/2024 | 28/07/2023 | 370.18 | 327.12
107 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) (SM/07128) | SM/07128 | 62.07 | 895 | RETROFITTING | 65 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/02/2024 | 19/10/2020 | 62.07 | 62.07
108 | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/12114) | SM/12114 | 588.27 | 1999 | NEW | 66 | Delayed | 50 | 02/09/2022 | 21/04/2024 | 29/03/2024 | 21/11/2022 | 295.04 | 265.23
109 | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME (SM/15517) | SM/15517 | 1067.02 | 1645 | NEW | 66 | Delayed | 47 | 16/02/2023 | 01/09/2024 | 29/03/2024 | 22/02/2023 | 500.06 | 500.06
110 | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME (SM/16538) | SM/16538 | 1074.69 | 1888 | NEW | 66 | Delayed | 39 | 10/03/2023 | 31/08/2024 | 29/03/2024 | 17/03/2023 | 415.84 | 415.84
111 | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME' (SM/09898) | SM/09898 | 47.48 | 608 | AUGMENTATION | 67 | Delayed | 89 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 20/03/2020 | 42.47 | 38.71
112 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) (SM/07065) | SM/07065 | 73.85 | 596 | RETROFITTING | 68 | Delayed | 46 | 25/11/2020 | 31/03/2024 | 29/02/2024 | 16/10/2020 | 34.11 | 34.11
113 | Bhutri Forest Piped Water Supply Scheme (SM/18156) | SM/18156 | 59.54 | 48 | NEW | 68 | On track | 14 | 29/03/2023 | 18/10/2024 | 28/03/2024 | 18/04/2023 | 8.17 | 4.1
114 | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME (SM/14216) | SM/14216 | 129.41 | 130 | NEW | 69 | Delayed | 52 | 10/01/2023 | 29/08/2024 | 02/04/2024 | 19/01/2023 | 67.29 | 60.48
115 | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/13449) | SM/13449 | 695.45 | 1856 | NEW | 71 | On track | 49 | 02/11/2022 | 30/10/2024 | 10/05/2024 | 01/11/2022 | 340.21 | 320.91
116 | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11992) | SM/11992 | 269.79 | 705 | NEW | 71 | On track | 41 | 01/09/2022 | 31/10/2024 | 29/03/2024 | 21/11/2022 | 109.28 | 86.07
117 | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/13239) | SM/13239 | 716.98 | 1719 | NEW | 71 | Delayed | 59 | 14/10/2022 | 17/06/2024 | 28/03/2024 | 17/01/2023 | 425.07 | 390.84
118 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) (SM/07178) | SM/07178 | 98.08 | 1419 | RETROFITTING | 72 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 98.08 | 98.03
119 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME (SM/10776) | SM/10776 | 167.97 | 0 | NEW | 72 | On track | 58 | 23/05/2022 | 30/11/2024 | 28/03/2024 | 31/05/2022 | 97.37 | 97.37
120 | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14212) | SM/14212 | 570.23 | 2321 | NEW | 72 | Delayed | 56 | 10/01/2023 | 31/07/2024 | 28/03/2024 | 31/01/2023 | 321.32 | 294.79
121 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) (SM/07179) | SM/07179 | 69.14 | 1419 | RETROFITTING | 72 | Delayed | 62 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 42.87 | 42.69
122 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) (SM/07058) | SM/07058 | 82.69 | 1036 | RETROFITTING | 72 | Delayed | 93 | 25/11/2020 | 31/03/2024 | 29/02/2024 | 05/01/2021 | 77 | 76.99
123 | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. (SM/08080) | SM/08080 | 1224.31 | 29206 | RETROFITTING | 72 | Delayed | 71 | 04/02/2021 | 31/03/2024 | 01/12/2023 | 01/10/2020 | 875.21 | 873.14
124 | Rejuvenation of Makrapara TG WSS. (SM/09895) | SM/09895 | 45.22 | 0 | AUGMENTATION | 73 | Delayed | 95 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 31/01/2022 | 42.81 | 42.27
125 | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME (SM/13240) | SM/13240 | 741.26 | 929 | NEW | 73 | Delayed | 28 | 14/10/2022 | 17/06/2024 | 29/03/2024 | 17/01/2023 | 209.95 | 209.95
126 | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME (SM/11402) | SM/11402 | 86.31 | 608 | AUGMENTATION | 74 | Delayed | 64 | 04/07/2022 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 55.06 | 55.06
127 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) (SM/07187) | SM/07187 | 73.94 | 828 | RETROFITTING | 75 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/02/2024 | 10/12/2021 | 73.94 | 73.94
128 | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/14092) | SM/14092 | 895.42 | 1884 | NEW | 75 | On track | 52 | 12/12/2022 | 01/09/2024 | 28/03/2024 | 02/02/2023 | 467.63 | 461.82
129 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) (SM/07188) | SM/07188 | 73.94 | 828 | RETROFITTING | 75 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/02/2024 | 10/12/2021 | 73.94 | 54.01
130 | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/14093) | SM/14093 | 528.73 | 1074 | NEW | 76 | On track | 35 | 12/12/2022 | 01/09/2024 | 28/03/2024 | 27/02/2023 | 185.15 | 181.38
131 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme (SM/08884) | SM/08884 | 398.83 | 2599 | RETROFITTING | 77 | Delayed | 97 | 27/09/2021 | 31/03/2024 | 29/01/2024 | 01/10/2020 | 387.21 | 387.18
132 | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME (SM/13244) | SM/13244 | 710.27 | 1482 | NEW | 78 | On track | 32 | 14/10/2022 | 30/09/2024 | 28/03/2024 | 27/03/2023 | 228.94 | 216.79
133 | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/12113) | SM/12113 | 821.35 | 2542 | NEW | 78 | Delayed | 43 | 02/09/2022 | 21/04/2024 | 29/03/2024 | 21/11/2022 | 350.85 | 314.91
134 | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME (SM/11485) | SM/11485 | 389.92 | 1567 | NEW | 78 | Delayed | 60 | 14/07/2022 | 31/03/2024 | 29/03/2024 | 12/07/2022 | 235.31 | 234.77
135 | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11696) | SM/11696 | 411.35 | 990 | NEW | 79 | Delayed | 52 | 29/07/2022 | 10/04/2024 | 29/02/2024 | 19/09/2022 | 212.79 | 211.7
136 | MARAKHATA PIPED WATER SUPPLY SCHEME. (SM/13304) | SM/13304 | 839.09 | 3129 | NEW | 80 | Delayed | 37 | 17/10/2022 | 30/06/2024 | 04/04/2024 | 17/01/2023 | 306.47 | 302.17
137 | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME (SM/10674) | SM/10674 | 236.97 | 60 | AUGMENTATION | 80 | Delayed | 29 | 29/04/2022 | 30/06/2024 | 29/03/2024 | 06/09/2022 | 69.85 | 69.85
138 | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME (SM/10316) | SM/10316 | 281.05 | 2393 | AUGMENTATION | 80 | On track | 22 | 04/03/2022 | 02/11/2024 | 29/03/2024 | 27/09/2021 | 62.36 | 42.86
139 | PASCHIM SATALI PIPED WATER SUPPLY SCHEME (SM/13245) | SM/13245 | 969.65 | 2797 | NEW | 80 | Delayed | 63 | 14/10/2022 | 17/06/2024 | 26/12/2023 | 17/01/2023 | 614.54 | 597.02
140 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) (SM/07176) | SM/07176 | 70.54 | 1621 | RETROFITTING | 80 | Delayed | 98 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 68.86 | 68.86
141 | TORSHA FOREST PIPED WATER SUPPLY SCHEME (SM/14220) | SM/14220 | 142.14 | 201 | NEW | 80 | Delayed | 66 | 10/01/2023 | 19/06/2024 | 28/03/2024 | 19/01/2023 | 93.14 | 91.31
142 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) (SM/07068) | SM/07068 | 85.62 | 1509 | RETROFITTING | 81 | Delayed | 91 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 78.07 | 76.23
143 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme (SM/07197) | SM/07197 | 84.07 | 1121 | RETROFITTING | 81 | Delayed | 75 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 16/09/2020 | 63.14 | 59.32
144 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) (SM/07189) | SM/07189 | 97.67 | 895 | RETROFITTING | 81 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 19/10/2020 | 97.67 | 97.67
145 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme (SM/08880) | SM/08880 | 140.24 | 2328 | RETROFITTING | 81 | Delayed | 100 | 27/09/2021 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 140.24 | 140.24
146 | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10178) | SM/10178 | 577.33 | 1487 | NEW | 82 | Delayed | 92 | 16/02/2022 | 31/03/2024 | 28/03/2024 | 27/01/2021 | 528.86 | 514.63
147 | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. (SM/13305) | SM/13305 | 760.21 | 1402 | NEW | 83 | Delayed | 56 | 17/10/2022 | 17/06/2024 | 29/03/2024 | 17/01/2023 | 428.64 | 402.09
148 | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME (SM/10156) | SM/10156 | 706.17 | 4402 | AUGMENTATION | 84 | Delayed | 65 | 11/02/2022 | 31/03/2024 | 28/03/2024 | 25/01/2022 | 457.44 | 428.62
149 | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME (SM/10180) | SM/10180 | 376.91 | 1250 | NEW | 85 | Delayed | 94 | 16/02/2022 | 31/03/2024 | 29/02/2024 | 17/02/2022 | 354.25 | 348.14
150 | BRAJERKUTHI PIPED WATER SUPPLY SCHEME (SM/13300) | SM/13300 | 944.2 | 1847 | NEW | 85 | On track | 57 | 17/10/2022 | 17/06/2024 | 29/03/2024 | 17/01/2023 | 533.78 | 523.58
151 | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/14214) | SM/14214 | 527.26 | 1579 | NEW | 85 | On track | 53 | 10/01/2023 | 16/08/2024 | 28/03/2024 | 16/03/2023 | 278.43 | 258.33
152 | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME (SM/11484) | SM/11484 | 455.23 | 1520 | NEW | 86 | Delayed | 61 | 14/07/2022 | 31/03/2024 | 29/02/2024 | 15/07/2022 | 278.21 | 266.12
153 | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME (SM/11482) | SM/11482 | 395.23 | 1493 | NEW | 86 | Delayed | 51 | 14/07/2022 | 31/03/2024 | 29/03/2024 | 15/07/2022 | 202.56 | 202.01
154 | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME (SM/12561) | SM/12561 | 1852.66 | 7428 | AUGMENTATION | 86 | Delayed | 58 | 14/09/2022 | 30/04/2024 | 29/03/2024 | 19/09/2022 | 1074.92 | 1067.87
155 | Rejuvenation of Gargenda Tea Garden Water Supply Scheme (SM/09906) | SM/09906 | 45.22 | 0 | AUGMENTATION | 87 | Delayed | 33 | 08/12/2021 | 31/03/2024 | 29/02/2024 | 31/08/2021 | 14.94 | 14.94
156 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) (SM/07183) | SM/07183 | 56.02 | 870 | RETROFITTING | 87 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 05/01/2022 | 56.02 | 53.47
157 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) (SM/07136) | SM/07136 | 80.05 | 822 | RETROFITTING | 87 | Delayed | 84 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 67.16 | 67.16
158 | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME (SM/11991) | SM/11991 | 432.05 | 1128 | NEW | 88 | Delayed | 73 | 01/09/2022 | 21/04/2024 | 29/03/2024 | 21/11/2022 | 314.96 | 284.57
159 | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME (SM/09896) | SM/09896 | 45.23 | 0 | AUGMENTATION | 89 | Delayed | 35 | 08/12/2021 | 31/03/2024 | 29/02/2024 | 31/01/2022 | 15.77 | 15.77
160 | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' (SM/09901) | SM/09901 | 44.25 | 0 | AUGMENTATION | 89 | Delayed | 71 | 08/12/2021 | 31/03/2024 | 29/02/2024 | 18/02/2022 | 31.47 | 31.47
161 | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' (SM/09891) | SM/09891 | 47.49 | 0 | AUGMENTATION | 90 | Delayed | 75 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 31/01/2022 | 35.64 | 17.67
162 | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME (SM/10675) | SM/10675 | 178.64 | 50 | AUGMENTATION | 90 | On track | 29 | 29/04/2022 | 16/08/2024 | 29/03/2024 | 16/03/2023 | 51.29 | 51.29
163 | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/11709) | SM/11709 | 817.44 | 1702 | NEW | 90 | Delayed | 74 | 29/07/2022 | 10/04/2024 | 29/03/2024 | 31/08/2022 | 606.44 | 586.47
164 | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME (SM/10169) | SM/10169 | 378.84 | 1527 | AUGMENTATION | 90 | Delayed | 28 | 16/02/2022 | 31/03/2024 | 29/01/2024 | 05/01/2022 | 104.9 | 98.87
165 | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME (SM/10676) | SM/10676 | 252.39 | 40 | AUGMENTATION | 90 | Delayed | 2 | 29/04/2022 | 31/03/2024 | 29/03/2024 | 06/01/2022 | 5.02 | 5.02
166 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) (SM/07122) | SM/07122 | 98.68 | 1051 | RETROFITTING | 91 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 98.68 | 98.68
167 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) (SM/07125) | SM/07125 | 90.17 | 1051 | RETROFITTING | 91 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 90.17 | 90.17
168 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) (SM/07126) | SM/07126 | 93 | 1051 | RETROFITTING | 91 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 93 | 93
169 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) (SM/07123) | SM/07123 | 98.96 | 1051 | RETROFITTING | 91 | Delayed | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 98.96 | 98.96
170 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) (SM/07175) | SM/07175 | 91.69 | 2686 | RETROFITTING | 91 | Delayed | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 19/02/2021 | 91.69 | 91.69
171 | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10173) | SM/10173 | 886.25 | 2277 | NEW | 91 | Delayed | 95 | 16/02/2022 | 31/03/2024 | 29/02/2024 | 14/10/2020 | 844.96 | 844.2
172 | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME (SM/10673) | SM/10673 | 252.98 | 50 | AUGMENTATION | 92 | Delayed | 6 | 29/04/2022 | 31/03/2024 | 29/01/2024 | 15/03/2022 | 16.34 | 16.34
173 | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME (SM/09887) | SM/09887 | 92.5 | 0 | AUGMENTATION | 92 | Delayed | 52 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 26/08/2021 | 47.79 | 44.93
174 | NURPUR PIPED WATER SUPPLY SCHEME. (SM/14218) | SM/14218 | 451.36 | 423 | NEW | 92 | On track | 39 | 10/01/2023 | 01/09/2024 | 29/03/2024 | 27/02/2023 | 175.07 | 175.07
175 | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME (SM/10170) | SM/10170 | 509.72 | 2836 | AUGMENTATION | 93 | Delayed | 63 | 16/02/2022 | 31/03/2024 | 29/01/2024 | 16/10/2020 | 322.12 | 307.59
176 | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. (SM/10637) | SM/10637 | 252.1 | 3877 | AUGMENTATION | 93 | Delayed | 49 | 21/04/2022 | 31/03/2024 | 29/01/2024 | 23/02/2021 | 124.4 | 124.4
177 | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME (SM/10155) | SM/10155 | 140.66 | 1040 | AUGMENTATION | 94 | On track | 97 | 11/02/2022 | 24/07/2024 | 01/12/2023 | 22/11/2021 | 136.56 | 136.56
178 | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' (SM/09890) | SM/09890 | 45.21 | 0 | AUGMENTATION | 95 | Delayed | 46 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 11/01/2022 | 20.92 | 20.92
179 | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME (SM/10174) | SM/10174 | 732.56 | 1867 | NEW | 95 | Delayed | 89 | 16/02/2022 | 31/03/2024 | 29/03/2024 | 17/02/2022 | 654.8 | 640.26
180 | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME (SM/09910) | SM/09910 | 47.45 | 0 | AUGMENTATION | 95 | Delayed | 49 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 05/01/2022 | 23.06 | 23.06
181 | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME (SM/09885) | SM/09885 | 449.91 | 3226 | AUGMENTATION | 95 | Delayed | 98 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 08/09/2020 | 443.06 | 443.06
182 | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME (SM/10667) | SM/10667 | 186.88 | 40 | AUGMENTATION | 95 | Delayed | 28 | 29/04/2022 | 21/04/2024 | 29/03/2024 | 24/02/2022 | 51.71 | 51.71
183 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) (SM/07185) | SM/07185 | 82.87 | 1051 | RETROFITTING | 96 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 82.87 | 82.87
184 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) (SM/07124) | SM/07124 | 55.28 | 1477 | RETROFITTING | 96 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 55.28 | 47.81
185 | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME (SM/10668) | SM/10668 | 69.44 | 20 | AUGMENTATION | 96 | On track | 1 | 29/04/2022 | 14/08/2024 | 12/10/2023 | 06/04/2023 | 0.36 | 0.36
186 | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME (SM/10671) | SM/10671 | 152.39 | 38 | AUGMENTATION | 96 | Delayed | 15 | 29/04/2022 | 31/03/2024 | 29/03/2024 | 24/02/2022 | 22.83 | 22.83
187 | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME (SM/10171) | SM/10171 | 750.42 | 3164 | AUGMENTATION | 97 | On track | 79 | 16/02/2022 | 31/03/2025 | 29/02/2024 | 05/01/2021 | 591.89 | 580.56
188 | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME (SM/10154) | SM/10154 | 632.84 | 3764 | AUGMENTATION | 97 | On track | 95 | 11/02/2022 | 31/03/2024 | 29/01/2024 | 27/01/2021 | 599.53 | 578.97
189 | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME (SM/09884) | SM/09884 | 484.93 | 2333 | AUGMENTATION | 97 | On track | 96 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 11/01/2022 | 464.08 | 461.48
190 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme (SM/07191) | SM/07191 | 62.8 | 788 | RETROFITTING | 97 | On track | 49 | 04/12/2020 | 31/03/2024 | 29/02/2024 | 26/08/2021 | 30.7 | 30.7
191 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) (SM/07134) | SM/07134 | 89.44 | 1477 | RETROFITTING | 98 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 89.44 | 84.64
192 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme (SM/08882) | SM/08882 | 129.45 | 1096 | RETROFITTING | 98 | On track | 100 | 27/09/2021 | 31/03/2024 | 29/01/2024 | 05/10/2021 | 129.45 | 128.72
193 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme (SM/07190) | SM/07190 | 83.82 | 1026 | RETROFITTING | 98 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 83.82 | 83.8
194 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) (SM/07181) | SM/07181 | 89.66 | 571 | RETROFITTING | 98 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 16/10/2020 | 89.63 | 89.61
195 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme (SM/07194) | SM/07194 | 98.15 | 1298 | RETROFITTING | 98 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 22/11/2021 | 98.15 | 98.15
196 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) (SM/07060) | SM/07060 | 86.77 | 1400 | RETROFITTING | 98 | On track | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 86.77 | 86.77
197 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme (SM/07184) | SM/07184 | 82.41 | 901 | RETROFITTING | 98 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 82.41 | 82.27
198 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme (SM/07196) | SM/07196 | 67.24 | 803 | RETROFITTING | 98 | On track | 76 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 15/07/2021 | 51.07 | 51.06
199 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) (SM/07135) | SM/07135 | 87.03 | 822 | RETROFITTING | 98 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 87.03 | 87.03
200 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme (SM/07198) | SM/07198 | 69.04 | 882 | RETROFITTING | 98 | On track | 93 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 19/10/2020 | 64.04 | 62.48
201 | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10038) | SM/10038 | 247.03 | 567 | NEW | 98 | On track | 29 | 19/01/2022 | 31/03/2024 | 29/01/2024 | 31/08/2021 | 70.85 | 70.85
202 | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME (SM/09883) | SM/09883 | 451.23 | 2988 | AUGMENTATION | 98 | On track | 64 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 289.43 | 285.13
203 | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME (SM/10677) | SM/10677 | 192.09 | 2678 | AUGMENTATION | 98 | On track | 5 | 29/04/2022 | 31/03/2024 | 29/01/2024 | 05/10/2021 | 8.65 | 8.65
204 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme (SM/07193) | SM/07193 | 60.86 | 608 | RETROFITTING | 98 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 01/10/2020 | 60.86 | 60.86
205 | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10172) | SM/10172 | 810.28 | 2579 | NEW | 98 | On track | 72 | 16/02/2022 | 31/03/2024 | 29/03/2024 | 17/02/2022 | 585.31 | 576.24
206 | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. (SM/10039) | SM/10039 | 284.23 | 1348 | NEW | 98 | On track | 90 | 19/01/2022 | 31/03/2024 | 29/01/2024 | 21/02/2022 | 255.6 | 255.6
207 | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME (SM/09886) | SM/09886 | 257.81 | 2202 | AUGMENTATION | 98 | On track | 96 | 08/12/2021 | 31/03/2024 | 29/03/2024 | 11/01/2022 | 246.85 | 244.39
208 | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' (SM/09899) | SM/09899 | 45.28 | 0 | AUGMENTATION | 98 | On track | 80 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 31/01/2022 | 36.01 | 34.57
209 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) (SM/07121) | SM/07121 | 82.27 | 2686 | RETROFITTING | 99 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 19/02/2021 | 82.27 | 79.34
210 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) (SM/07067) | SM/07067 | 98.86 | 345 | RETROFITTING | 99 | On track | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 98.86 | 98.86
211 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) (SM/07182) | SM/07182 | 98.81 | 870 | RETROFITTING | 99 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 05/01/2022 | 98.81 | 98.81
212 | REJUVINATION OF 'CHANDIRJHAR WATER SUPPLY SCHEME' (SM/09892) | SM/09892 | 47.49 | 0 | AUGMENTATION | 99 | On track | 73 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 05/10/2021 | 34.43 | 31.03
213 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) (SM/07174) | SM/07174 | 76.33 | 1388 | RETROFITTING | 99 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 05/01/2021 | 76.33 | 76.07
214 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) (SM/07057) | SM/07057 | 99.09 | 2066 | RETROFITTING | 99 | On track | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 15/12/2020 | 99.09 | 99.09
215 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) (SM/07177) | SM/07177 | 68.96 | 761 | RETROFITTING | 99 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 05/01/2021 | 68.96 | 68.96
216 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) (SM/07062) | SM/07062 | 87.86 | 2826 | RETROFITTING | 99 | On track | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 87.86 | 87.86
217 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) (SM/07127) | SM/07127 | 66.37 | 1051 | RETROFITTING | 99 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 13/09/2021 | 66.37 | 66.37
218 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) (SM/07133) | SM/07133 | 95.65 | 1169 | RETROFITTING | 99 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 25/01/2021 | 95.65 | 95.65
219 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) (SM/07066) | SM/07066 | 80.75 | 2682 | RETROFITTING | 99 | On track | 97 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 22/02/2021 | 78.4 | 78.08
220 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) (SM/07069) | SM/07069 | 61.34 | 1509 | RETROFITTING | 99 | On track | 100 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 61.34 | 61.33
221 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme (SM/07195) | SM/07195 | 98.84 | 1222 | RETROFITTING | 99 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 01/10/2020 | 98.84 | 98.84
222 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) (SM/07063) | SM/07063 | 91.9 | 1709 | RETROFITTING | 99 | On track | 97 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 28/12/2020 | 89.1 | 88.58
223 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme (SM/08881) | SM/08881 | 184.32 | 874 | RETROFITTING | 99 | On track | 72 | 27/09/2021 | 31/03/2024 | 29/01/2024 | 28/12/2020 | 133.37 | 130.95
224 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) (SM/07138) | SM/07138 | 96.46 | 2682 | RETROFITTING | 99 | On track | 100 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 12/11/2020 | 96.46 | 96.46
225 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme (SM/07064) | SM/07064 | 99.04 | 1612 | RETROFITTING | 99 | On track | 96 | 25/11/2020 | 31/03/2024 | 29/01/2024 | 25/01/2021 | 95.51 | 95.26
226 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme (SM/07192) | SM/07192 | 83.76 | 1000 | RETROFITTING | 99 | On track | 100 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 29/07/2022 | 83.76 | 83.76
227 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) (SM/07186) | SM/07186 | 99.29 | 345 | RETROFITTING | 99 | On track | 86 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 85 | 81.62
228 | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' (SM/09905) | SM/09905 | 45.51 | 0 | AUGMENTATION | 99 | On track | 24 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 11 | 9.21
229 | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME (SM/09907) | SM/09907 | 44.74 | 0 | AUGMENTATION | 99 | On track | 5 | 08/12/2021 | 31/03/2024 | 29/01/2024 | 22/12/2021 | 2.12 | 2.39
230 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) (SM/07137) | SM/07137 | 97.16 | 1073 | RETROFITTING | 99 | On track | 90 | 26/11/2020 | 31/03/2024 | 29/01/2024 | 14/10/2020 | 87.69 | 86.26
231 | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME (SM/10179) | SM/10179 | 364.15 | 647 | NEW | 99 | On track | 94 | 16/02/2022 | 31/03/2024 | 29/03/2024 | 17/02/2022 | 341.77 | 341.25
232 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme (SM/07199) | SM/07199 | 61.63 | 688 | RETROFITTING | 99 | On track | 87 | 04/12/2020 | 31/03/2024 | 29/01/2024 | 03/09/2020 | 53.58 | 48.89
233 | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. (SM/06623) | SM/06623 | 21.16 | 0 | SUPPORT-WQMSP | 99 | On track | 0 | 05/02/2020 | 31/03/2024 | 29/01/2024 | 23/06/2021 | 0 | 0
234 | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. (SM/08580) | SM/08580 | 295.97 | 882 | NEW | 100 | 100% Physical | 51 | 10/02/2021 | 31/12/2023 | 25/08/2023 | 25/02/2021 | 151.9 | 143.72
Total |  |  | 90019.48 | 344018 | [8 empty] | 39412.92 | 37491.91