## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA (SM/09616) | SM/09616 | 143.99 | 50 | NEW | 0 | 0% Physical | 86 | 24/11/2021 | 25/08/2025 | 19/05/2025 | 24/06/2020 | 123.51 | 123.51
2 | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG (SM/09665) | SM/09665 | 142.76 | 221 | NEW | 0 | 0% Physical | 33 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 46.99 | 46.99
3 | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA (SM/09670) | SM/09670 | 122.05 | 65 | NEW | 0 | 0% Physical | 88 | 23/11/2021 | 25/08/2025 | 19/05/2025 | 14/08/2020 | 106.91 | 106.91
4 | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP (SM/10755) | SM/10755 | 201.1 | 160 | NEW | 0 | 0% Physical | 57 | 19/05/2022 | 31/03/2025 | 19/05/2025 | 25/05/2022 | 114.88 | 114.88
5 | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte (SM/10214) | SM/10214 | 753.18 | 0 | SCHOOL | 0 | 0% Physical | 0 | 24/02/2022 | 31/08/2025 | 19/05/2025 | 28/03/2022 | 0 | 0
6 | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10703) | SM/10703 | 286.37 | 407 | NEW | 0 | 0% Physical | 88 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 26/05/2022 | 252.26 | 252.26
7 | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE (SM/10741) | SM/10741 | 92.28 | 80 | NEW | 0 | 0% Physical | 70 | 19/05/2022 | 31/10/2025 | 19/05/2025 | 26/05/2022 | 64.7 | 64.7
8 | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA (SM/10743) | SM/10743 | 79.81 | 87 | NEW | 0 | 0% Physical | 87 | 19/05/2022 | 25/12/2025 | 19/05/2025 | 25/05/2022 | 69.1 | 69.1
9 | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN (SM/10745) | SM/10745 | 91.35 | 90 | NEW | 0 | 0% Physical | 82 | 19/05/2022 | 31/12/2025 | 19/05/2025 | 26/05/2022 | 74.93 | 74.93
10 | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11376) | SM/11376 | 191.02 | 147 | NEW | 0 | 0% Physical | 58 | 04/07/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 110.75 | 110.75
11 | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR (SM/11354) | SM/11354 | 143.23 | 106 | NEW | 0 | 0% Physical | 88 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 21/09/2022 | 126.58 | 126.58
12 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong (SM/14194) | SM/14194 | 747.62 | 1264 | NEW | 0 | 0% Physical | 54 | 10/01/2023 | 31/12/2025 | 19/05/2025 | 12/07/2023 | 406.06 | 393.76
13 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16232) | SM/16232 | 380.82 | 206 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 05/06/2023 | 1.23 | 1.23
14 | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON (SM/09615) | SM/09615 | 118.44 | 55 | NEW | 0 | 0% Physical | 100 | 24/11/2021 | 31/03/2025 | 19/05/2025 | 24/06/2020 | 118.44 | 118.44
15 | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG (SM/09669) | SM/09669 | 125.27 | 56 | NEW | 0 | 0% Physical | 88 | 23/11/2021 | 30/05/2025 | 19/05/2025 | 24/06/2020 | 110.7 | 110.7
16 | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG (SM/09547) | SM/09547 | 237.68 | 300 | NEW | 0 | 0% Physical | 54 | 19/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 128.7 | 128.7
17 | PWS from Samphong Khola to Kagey Busty District Kalimpong (SM/09548) | SM/09548 | 679.86 | 641 | NEW | 0 | 0% Physical | 88 | 19/11/2021 | 14/05/2025 | 19/05/2025 | 24/06/2020 | 598.98 | 598.98
18 | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP (SM/09667) | SM/09667 | 476.5 | 350 | NEW | 0 | 0% Physical | 97 | 23/11/2021 | 31/03/2025 | 19/05/2025 | 24/06/2020 | 462.62 | 462.62
19 | PWS SCHEME FROM KHANI KHOLA TO CHUKIM (SM/10753) | SM/10753 | 138.36 | 122 | NEW | 0 | 0% Physical | 85 | 19/05/2022 | 30/06/2025 | 19/05/2025 | 25/05/2022 | 117.83 | 117.83
20 | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING (SM/09609) | SM/09609 | 98.66 | 75 | NEW | 0 | 0% Physical | 82 | 23/11/2021 | 30/09/2025 | 19/05/2025 | 14/08/2020 | 80.79 | 80.79
21 | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK (SM/10747) | SM/10747 | 72.57 | 135 | NEW | 0 | 0% Physical | 86 | 19/05/2022 | 30/09/2025 | 19/05/2025 | 30/06/2022 | 62.34 | 62.34
22 | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11579) | SM/11579 | 312.68 | 249 | NEW | 0 | 0% Physical | 80 | 22/07/2022 | 30/12/2025 | 19/05/2025 | 14/10/2022 | 248.74 | 248.74
23 | Creating gravity based provision of Drinking water from spring water source for 13 Numbers Health care Facilities in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. (SM/11368) | SM/11368 | 54.35 | 0 | HEALTH CENTER | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
24 | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG (SM/13603) | SM/13603 | 341.66 | 664 | NEW | 0 | 0% Physical | 60 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 01/02/2023 | 206.13 | 206.13
25 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13617) | SM/13617 | 442.25 | 240 | NEW | 0 | 0% Physical | 69 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 14/12/2022 | 305.29 | 305.29
26 | Creating gravity based provision of drinking water from spring water source for 27 numbers school, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong (SM/11357) | SM/11357 | 142.95 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
27 | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11359) | SM/11359 | 261.22 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 | 31/03/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
28 | Creating gravity based provision of drinking water from spring water source for 48 Nos of Aganwadi under Gorubathan Block, in the District of Kalimpong under Neorakhola water supply Division, kalimpong PHE Directorate. (SM/11363) | SM/11363 | 241.95 | 0 | ANGANWADI | 0 | 0% Physical | 0 | 28/06/2022 | 31/08/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
29 | PAGRAN BONG KHASMAHAL PWSS (SM/16854) | SM/16854 | 473.77 | 187 | NEW | 0 | 0% Physical | 67 | 13/03/2023 | 31/12/2025 | 19/05/2025 | 12/07/2023 | 319.07 | 319.07
30 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong (SM/14193) | SM/14193 | 701.2 | 724 | NEW | 0 | 0% Physical | 1 | 10/01/2023 | 16/04/2025 | 19/05/2025 | 26/05/2023 | 4.46 | 4.46
31 | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON (SM/09596) | SM/09596 | 314.39 | 320 | NEW | 0 | 0% Physical | 100 | 23/11/2021 | 31/03/2025 | 19/05/2025 | 24/06/2020 | 313.01 | 312.99
32 | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme (SM/08693) | SM/08693 | 99.42 | 1000 | RETROFITTING | 0 | 0% Physical | 99 | 01/09/2021 | 31/12/2025 | 19/05/2025 | 06/09/2021 | 98.58 | 98.58
33 | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON (SM/09545) | SM/09545 | 160.48 | 125 | NEW | 0 | 0% Physical | 61 | 19/11/2021 | 31/07/2025 | 19/05/2025 | 07/01/2022 | 98.7 | 98.7
34 | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10704) | SM/10704 | 338.99 | 226 | NEW | 0 | 0% Physical | 89 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 05/08/2022 | 301.62 | 301.62
35 | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong (SM/10820) | SM/10820 | 47.33 | 48 | NEW | 0 | 0% Physical | 5 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 2.13 | 2.13
36 | PWS SCHEME FROM MANDIR KHOLA TO TANYANG (SM/10751) | SM/10751 | 214.24 | 195 | NEW | 0 | 0% Physical | 82 | 19/05/2022 | 30/04/2025 | 19/05/2025 | 26/05/2022 | 175.66 | 175.66
37 | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11578) | SM/11578 | 393.32 | 296 | NEW | 0 | 0% Physical | 76 | 22/07/2022 | 31/12/2025 | 19/05/2025 | 14/10/2022 | 297.56 | 297.56
38 | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG (SM/11342) | SM/11342 | 100.52 | 65 | NEW | 0 | 0% Physical | 84 | 13/06/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 84.53 | 84.53
39 | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. (SM/11369) | SM/11369 | 17.3 | 0 | HEALTH CENTER | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
40 | Creating gravity based Provision Of Drinking water from spring water source for 07 (Seven) Numbers of Gram Panchayat office in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11372) | SM/11372 | 43.43 | 7 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
41 | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE (SM/09666) | SM/09666 | 138.81 | 140 | NEW | 0 | 0% Physical | 74 | 24/11/2021 | 25/11/2025 | 19/05/2025 | 24/06/2020 | 103.07 | 103.07
42 | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS (SM/15554) | SM/15554 | 248.56 | 278 | NEW | 0 | 0% Physical | 44 | 15/02/2023 | 23/04/2025 | 19/05/2025 | 03/03/2023 | 109.74 | 109.74
43 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16512) | SM/16512 | 160.61 | 136 | NEW | 0 | 0% Physical | 1 | 03/03/2023 | 31/12/2025 | 19/05/2025 | 28/04/2023 | 2.38 | 2.38
44 | Extension of piped water supply scheme to Upper Pedong Lower Goan (St George Primary School) Anganwadi Centre under Pedong G.P and Pagang Gumtaline Anganwadi Centre under Paiyong G.P under Kalimpong lock-II, located within the commanding area of PWSS for (SM/09019) | SM/09019 | 8.21 | 0 | ANGANWADI | 0 | WO no issued | 0 | 30/10/2021 |  | 05/05/2023 |  | 0 | 0
45 | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI (SM/09539) | SM/09539 | 151.5 | 121 | NEW | 0 | 0% Physical | 80 | 19/11/2021 | 30/09/2025 | 19/05/2025 | 24/06/2020 | 121.37 | 121.37
46 | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong (SM/10052) | SM/10052 | 4402.74 | 0 | AUGMENTATION | 0 | 0% Physical | 18 | 25/01/2022 | 31/12/2025 | 19/05/2025 | 28/02/2022 | 787.17 | 787.17
47 | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10696) | SM/10696 | 115.09 | 135 | NEW | 0 | 0% Physical | 70 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 80.87 | 80.87
48 | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10697) | SM/10697 | 126.09 | 100 | NEW | 0 | 0% Physical | 58 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 01/08/2022 | 73.25 | 73.25
49 | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10705) | SM/10705 | 99.21 | 105 | AUGMENTATION | 0 | 0% Physical | 68 | 12/05/2022 | 30/06/2025 | 19/05/2025 | 13/04/2022 | 67.31 | 67.31
50 | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK (SM/12181) | SM/12181 | 695.67 | 514 | NEW | 0 | 0% Physical | 53 | 07/09/2022 | 31/12/2025 | 19/05/2025 | 03/11/2022 | 367.45 | 367.45
51 | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. (SM/11367) | SM/11367 | 15 | 0 | HEALTH CENTER | 0 | 0% Physical | 0 | 28/06/2022 | 30/05/2025 | 19/05/2025 | 26/05/2022 | 0 | 0
52 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG (SM/16231) | SM/16231 | 944.04 | 1175 | NEW | 0 | 0% Physical | 51 | 24/02/2023 | 26/03/2025 | 19/05/2025 | 26/05/2023 | 481.69 | 481.69
53 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16514) | SM/16514 | 896.34 | 538 | NEW | 0 | 0% Physical | 27 | 03/03/2023 | 31/12/2025 | 19/05/2025 | 05/06/2023 | 242.34 | 226.15
54 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG (SM/15643) | SM/15643 | 300.21 | 169 | NEW | 0 | 0% Physical | 16 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 49.11 | 49.11
55 | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY (SM/10754) | SM/10754 | 176.39 | 160 | NEW | 0 | 0% Physical | 89 | 19/05/2022 | 30/10/2025 | 19/05/2025 | 26/05/2022 | 157.47 | 157.47
56 | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY (SM/09614) | SM/09614 | 88.27 | 61 | NEW | 0 | 0% Physical | 78 | 24/11/2021 | 30/09/2025 | 19/05/2025 | 24/06/2020 | 68.87 | 68.87
57 | PWS SCHEME FROM MAWATAR TO UPPER DABLING (SM/09546) | SM/09546 | 192.44 | 50 | NEW | 0 | 0% Physical | 97 | 19/11/2021 | 31/12/2025 | 19/05/2025 | 07/01/2022 | 186.34 | 186.34
58 | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA (SM/09605) | SM/09605 | 164.46 | 220 | NEW | 0 | 0% Physical | 80 | 23/11/2021 | 30/06/2025 | 19/05/2025 | 24/06/2020 | 131.87 | 131.87
59 | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. (SM/10266) | SM/10266 | 187.99 | 1769 | RETROFITTING | 0 | 0% Physical | 88 | 09/02/2021 | 31/05/2025 | 19/05/2025 | 14/12/2022 | 165.14 | 163.77
60 | PWS SCHEME FROM KHARKHOLA TO LOWER REON (SM/10756) | SM/10756 | 105.07 | 102 | NEW | 0 | 0% Physical | 71 | 19/05/2022 | 25/08/2025 | 19/05/2025 | 25/05/2022 | 74.29 | 74.29
61 | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10695) | SM/10695 | 138.07 | 136 | NEW | 0 | 0% Physical | 81 | 12/05/2022 | 30/07/2025 | 19/05/2025 | 26/05/2022 | 111.81 | 111.81
62 | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10699) | SM/10699 | 152.76 | 350 | NEW | 0 | 0% Physical | 42 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 64.76 | 64.76
63 | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10702) | SM/10702 | 113.56 | 131 | NEW | 0 | 0% Physical | 70 | 12/05/2022 | 30/12/2025 | 19/05/2025 | 13/05/2022 | 79.21 | 79.21
64 | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY (SM/10752) | SM/10752 | 75.91 | 72 | NEW | 0 | 0% Physical | 83 | 19/05/2022 | 30/05/2025 | 19/05/2025 | 25/05/2022 | 62.73 | 62.73
65 | PWS SCHEME FROM DEORALI KHOLA TO PAKANG (SM/11341) | SM/11341 | 117.19 | 150 | NEW | 0 | 0% Physical | 77 | 13/06/2022 | 30/06/2025 | 19/05/2025 | 30/06/2022 | 89.7 | 89.7
66 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/13621) | SM/13621 | 236.28 | 124 | NEW | 0 | 0% Physical | 46 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 16/01/2023 | 109.49 | 109.49
67 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15640) | SM/15640 | 497.43 | 685 | NEW | 0 | 0% Physical | 53 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 261.21 | 261.21
68 | PWS SCHEME FROM CHAWA KHOLA TO RELLI (SM/09610) | SM/09610 | 122.01 | 125 | NEW | 0 | 0% Physical | 97 | 24/11/2021 | 30/04/2025 | 19/05/2025 | 24/06/2020 | 117.87 | 117.87
69 | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE (SM/09606) | SM/09606 | 198.35 | 230 | NEW | 0 | 0% Physical | 89 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 14/08/2020 | 176.2 | 176.2
70 | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. (SM/10265) | SM/10265 | 228.22 | 1475 | RETROFITTING | 0 | 0% Physical | 87 | 09/02/2021 | 31/03/2025 | 19/05/2025 | 14/12/2022 | 199.13 | 199.13
71 | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10700) | SM/10700 | 173.31 | 242 | NEW | 0 | 0% Physical | 79 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 24/05/2022 | 136.83 | 136.83
72 | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10701) | SM/10701 | 114.57 | 90 | NEW | 0 | 0% Physical | 71 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 81.26 | 81.26
73 | SURUK PIPED WATER SUPPLY SCHEME (SM/13607) | SM/13607 | 643.2 | 338 | NEW | 0 | 0% Physical | 35 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 09/02/2023 | 228.14 | 228.14
74 | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16233) | SM/16233 | 963.91 | 700 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 20/05/2025 | 19/05/2025 | 12/07/2023 | 3.98 | 3.98
75 | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong (SM/10512) | SM/10512 | 504.2 | 677 | RETROFITTING | 0 | 0% Physical | 81 | 13/04/2022 | 31/12/2025 | 19/05/2025 | 13/04/2022 | 409.33 | 409.03
76 | PWS SCHEME FROM PHENTO SOURCE TO DUKA (SM/10748) | SM/10748 | 165.77 | 143 | NEW | 0 | 0% Physical | 83 | 19/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 137.75 | 137.75
77 | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE (SM/10749) | SM/10749 | 105.72 | 105 | NEW | 0 | 0% Physical | 93 | 19/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 97.81 | 97.81
78 | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT (SM/12180) | SM/12180 | 520.75 | 295 | NEW | 0 | 0% Physical | 72 | 07/09/2022 | 30/09/2025 | 19/05/2025 | 18/10/2022 | 372.38 | 372.38
79 | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11955) | SM/11955 | 242.62 | 221 | NEW | 0 | 0% Physical | 64 | 24/08/2022 | 30/11/2025 | 19/05/2025 | 04/11/2022 | 156.13 | 156.13
80 | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte (SM/11358) | SM/11358 | 182.6 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 | 30/04/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
81 | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11364) | SM/11364 | 398.55 | 0 | ANGANWADI | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 0 | 0
82 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15642) | SM/15642 | 211.63 | 314 | NEW | 0 | 0% Physical | 97 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 205.46 | 205.46
83 | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON (SM/09598) | SM/09598 | 96.33 | 56 | NEW | 0 | 0% Physical | 97 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 93.52 | 93.52
84 | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA (SM/09600) | SM/09600 | 169.19 | 234 | NEW | 0 | 0% Physical | 80 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 135.91 | 135.91
85 | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR (SM/09601) | SM/09601 | 206.39 | 245 | NEW | 0 | 0% Physical | 83 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 171.41 | 171.41
86 | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG (SM/09611) | SM/09611 | 80.8 | 70 | NEW | 0 | 0% Physical | 88 | 24/11/2021 | 30/09/2025 | 19/05/2025 | 14/08/2020 | 70.87 | 70.87
87 | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE (SM/09617) | SM/09617 | 100.06 | 99 | NEW | 0 | 0% Physical | 74 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 14/01/2022 | 73.75 | 73.75
88 | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10694) | SM/10694 | 94.15 | 105 | NEW | 0 | 0% Physical | 59 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 55.95 | 55.95
89 | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10698) | SM/10698 | 206.41 | 169 | NEW | 0 | 0% Physical | 90 | 12/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 186.41 | 186.41
90 | PWS SCHEME FROM SISNEY JHORA TO SAMTHAR BAZAR (SM/10742) | SM/10742 | 197.78 | 252 | NEW | 0 | 0% Physical | 90 | 19/05/2022 | 30/09/2025 | 19/05/2025 | 25/05/2022 | 178 | 178
91 | PWS SCHEME FROM BANGLA JHORA TO JOGITAR (SM/10750) | SM/10750 | 65.73 | 60 | NEW | 0 | 0% Physical | 19 | 19/05/2022 | 31/12/2025 | 19/05/2025 | 25/05/2022 | 12.32 | 12.32
92 | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. (SM/11370) | SM/11370 | 27.84 | 6 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 0 | 0% Physical | 0 | 28/06/2022 | 31/12/2025 | 19/05/2025 | 26/05/2022 | 0 | 0
93 | PWSS FROM BHARKHOP JHORA TO LOWER KAFFER (SM/11343) | SM/11343 | 99.53 | 85 | NEW | 0 | 0% Physical | 70 | 13/06/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 69.95 | 69.95
94 | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG (SM/14191) | SM/14191 | 693.21 | 915 | NEW | 0 | 0% Physical | 64 | 10/01/2023 | 31/12/2025 | 19/05/2025 | 09/02/2023 | 445.04 | 445.04
95 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG (SM/16513) | SM/16513 | 304 | 369 | NEW | 0 | 0% Physical | 30 | 03/03/2023 | 31/12/2025 | 19/05/2025 | 28/04/2023 | 89.89 | 89.89
96 | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W (SM/10140) | SM/10140 | 436.51 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 08/02/2022 |  | 10/02/2022 | 31/12/2021 | 0 | 0
97 | Operational charges procurement of chemicals Glassware-computer maintenance of PHED managed laboratories related to water quality monitoring & surveillance under Jal Jeevan Mission (SM/19295) | SM/19295 | 21.75 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
98 | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. (SM/10513) | SM/10513 | 13.03 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 13/04/2022 |  | 18/04/2022 |  | 0 | 0
99 | Collection of Water Samples from different drinking water sources, tanks and reservoir etc. under Kalimpong district and submitting the same to the respective water testing laboratories (Neorakhola sub-district laboratory and Algarah sub-district laborato (SM/15669) | SM/15669 | 27.41 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 03/03/2023 | 0 | 0
100 | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. (SM/13680) | SM/13680 | 6.46 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 14/11/2022 |  | 17/11/2022 |  | 0 | 0
101 | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG (SM/18322) | SM/18322 | 1040.03 | 1196 | NEW | 10 | Delayed | 1 | 27/06/2023 | 25/03/2025 | 19/05/2025 | 18/07/2023 | 7.15 | 7.15
102 | UPPER FAGU PIPED WATER SUPPLY SCHEME. (SM/13954) | SM/13954 | 819.76 | 924 | NEW | 10 | Delayed | 1 | 01/12/2022 | 31/12/2025 | 19/05/2025 | 18/07/2023 | 6.33 | 6.33
103 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16234) | SM/16234 | 55.28 | 47 | NEW | 10 | Delayed | 5 | 24/02/2023 | 31/07/2025 | 19/05/2025 | 12/07/2023 | 2.71 | 2.71
104 | KUMAI FOREST PIPED WATER SUPPLY SCHEME. (SM/13612) | SM/13612 | 290.97 | 245 | NEW | 10 | Delayed | 40 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 05/06/2023 | 116.92 | 116.92
105 | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) (SM/07872) | SM/07872 | 72.63 | 625 | RETROFITTING | 11 | Delayed | 89 | 19/01/2021 | 31/12/2025 | 19/05/2025 | 12/10/2020 | 64.69 | 64.22
106 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13616) | SM/13616 | 268.04 | 123 | NEW | 15 | Delayed | 46 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 16/01/2023 | 122.38 | 121.23
107 | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I (SM/18442) | SM/18442 | 3858.84 | 3573 | AUGMENTATION | 15 | Delayed | 12 | 18/07/2023 | 07/11/2025 | 19/05/2025 | 06/12/2023 | 472.55 | 472.55
108 | GORUBATHAN-I PWSS (SM/14172) | SM/14172 | 1146.86 | 1818 | NEW | 20 | Delayed | 1 | 09/01/2023 | 31/12/2025 | 19/05/2025 | 18/07/2023 | 11.19 | 11.19
109 | PATEN GODAK KHASMAHAL PWSS (SM/18255) | SM/18255 | 1128.06 | 874 | NEW | 35 | Delayed | 31 | 21/06/2023 | 31/12/2025 | 19/05/2025 | 17/07/2023 | 345.78 | 345.78
110 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/12629) | SM/12629 | 752.8 | 588 | NEW | 40 | Delayed | 57 | 19/09/2022 | 31/12/2025 | 19/05/2025 | 29/09/2022 | 425.76 | 425.76
111 | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. (SM/18443) | SM/18443 | 3488.92 | 3512 | NEW | 40 | Delayed | 11 | 20/07/2023 | 31/03/2025 | 19/05/2025 | 24/07/2023 | 395.64 | 395.64
112 | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (SM/13613) | SM/13613 | 351.35 | 303 | NEW | 40 | Delayed | 15 | 11/11/2022 | 31/03/2026 | 19/05/2025 | 26/05/2023 | 52.73 | 52.73
113 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/18247) | SM/18247 | 1350.54 | 946 | NEW | 40 | Delayed | 0 | 16/06/2023 | 31/03/2025 | 19/05/2025 | 18/07/2023 | 4.38 | 4.38
114 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. (SM/19176) | SM/19176 | 2560.38 | 1749 | NEW | 44 | Delayed | 5 | 15/02/2024 | 31/03/2026 | 19/05/2025 | 20/02/2024 | 123.67 | 123.67
115 | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10576) | SM/10576 | 49.14 | 45 | NEW | 50 | Delayed | 63 | 18/04/2022 | 31/12/2025 | 19/05/2025 | 26/05/2022 | 30.78 | 30.78
116 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13615) | SM/13615 | 101.26 | 35 | NEW | 50 | Delayed | 54 | 11/11/2022 | 30/09/2025 | 19/05/2025 | 01/02/2023 | 54.49 | 54.49
117 | GODAK BUSTY PIPED WATER SUPPLY SCHEME. (SM/13608) | SM/13608 | 356.95 | 136 | NEW | 50 | Delayed | 46 | 11/11/2022 | 31/07/2025 | 19/05/2025 | 24/07/2023 | 165.11 | 165.11
118 | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16649) | SM/16649 | 437.66 | 351 | NEW | 50 | Delayed | 1 | 14/03/2023 | 31/12/2025 | 19/05/2025 | 28/04/2023 | 3.41 | 3.41
119 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/15042) | SM/15042 | 213.24 | 161 | NEW | 50 | Delayed | 45 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 09/02/2023 | 96.21 | 96.21
120 | RANGO FOREST PWSS (SM/18823) | SM/18823 | 1664.29 | 1892 | NEW | 50 | Delayed | 24 | 11/09/2023 | 07/11/2025 | 19/05/2025 | 21/09/2023 | 392.88 | 392.88
121 | PANKHASARI KHASMAHAL PWSS (SM/14170) | SM/14170 | 1201.07 | 666 | NEW | 50 | Delayed | 82 | 09/01/2023 | 31/12/2025 | 19/05/2025 | 06/02/2023 | 985 | 985
122 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG (SM/16235) | SM/16235 | 233.82 | 199 | NEW | 50 | Delayed | 30 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 12/07/2023 | 70.57 | 70.57
123 | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11377) | SM/11377 | 89.16 | 55 | NEW | 56 | Delayed | 58 | 04/07/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 51.77 | 51.77
124 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG (SM/13606) | SM/13606 | 427.72 | 692 | NEW | 60 | Delayed | 0 | 11/11/2022 | 21/06/2025 | 02/01/2025 | 24/07/2023 | 0 | 0
125 | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS (SM/13953) | SM/13953 | 882.37 | 663 | NEW | 60 | Delayed | 55 | 01/12/2022 | 31/12/2025 | 19/05/2025 | 09/02/2023 | 484.49 | 484.49
126 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG (SM/15644) | SM/15644 | 650.72 | 538 | NEW | 60 | Delayed | 1 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 10/05/2023 | 4.41 | 4.41
127 | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11577) | SM/11577 | 47.54 | 32 | NEW | 60 | Delayed | 38 | 22/07/2022 | 31/12/2025 | 19/05/2025 | 28/09/2022 | 18.08 | 18.08
128 | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY (SM/09543) | SM/09543 | 365.16 | 213 | NEW | 65 | Delayed | 78 | 19/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 285.41 | 285.41
129 | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. (SM/11806) | SM/11806 | 204.57 | 139 | NEW | 65 | Delayed | 68 | 10/08/2022 | 31/12/2025 | 19/05/2025 | 12/08/2022 | 138.48 | 138.48
130 | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE (SM/09594) | SM/09594 | 776.35 | 480 | NEW | 70 | Delayed | 75 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 04/04/2022 | 582.85 | 582.85
131 | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10792) | SM/10792 | 606.74 | 457 | NEW | 70 | On track | 63 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 380.26 | 380.26
132 | Creating gravity based provision of Drinking water from spring water source for 12 Numbers of Gram panchayat Buildings in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. (SM/11371) | SM/11371 | 39.73 | 12 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 70 | Delayed | 0 | 28/06/2022 | 30/09/2023 | 21/07/2023 | 12/07/2022 | 0 | 0
133 | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/11313) | SM/11313 | 829.3 | 462 | NEW | 70 | Delayed | 76 | 15/06/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 632.69 | 632.69
134 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG (SM/16230) | SM/16230 | 921.36 | 1068 | NEW | 70 | On track | 73 | 24/02/2023 | 31/12/2025 | 19/05/2025 | 29/05/2023 | 671.1 | 671.1
135 | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG (SM/16511) | SM/16511 | 964.71 | 1013 | NEW | 70 | Delayed | 29 | 03/03/2023 | 21/05/2025 | 19/05/2025 | 05/06/2023 | 278.48 | 278.48
136 | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. (SM/10267) | SM/10267 | 127.68 | 1116 | RETROFITTING | 72 | Delayed | 92 | 09/02/2021 | 31/03/2025 | 19/05/2025 | 14/12/2022 | 116.84 | 116.84
137 | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME (SM/13602) | SM/13602 | 335.49 | 445 | NEW | 75 | On track | 57 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 16/01/2023 | 190.68 | 190.68
138 | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS (SM/15937) | SM/15937 | 657.46 | 782 | NEW | 75 | On track | 74 | 22/02/2023 | 31/12/2025 | 19/05/2025 | 03/03/2023 | 485.81 | 485.81
139 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG (SM/15645) | SM/15645 | 973.41 | 651 | NEW | 75 | On track | 73 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 10/05/2023 | 706.56 | 706.56
140 | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. (SM/18589) | SM/18589 | 1104.14 | 1130 | NEW | 75 | On track | 70 | 31/07/2023 | 31/12/2025 | 19/05/2025 | 07/08/2023 | 767.82 | 758.96
141 | BINDU PIPED WATER SUPPLY SCHEME (SM/13622) | SM/13622 | 130.17 | 174 | NEW | 75 | On track | 50 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 65.67 | 65.67
142 | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN (SM/09607) | SM/09607 | 108.86 | 208 | NEW | 80 | On track | 69 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 75.45 | 75.45
143 | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON (SM/09542) | SM/09542 | 108.18 | 87 | NEW | 80 | On track | 83 | 19/11/2021 | 30/09/2025 | 19/05/2025 | 28/03/2022 | 89.57 | 89.57
144 | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON (SM/09668) | SM/09668 | 182.37 | 140 | NEW | 80 | On track | 80 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 146.67 | 146.67
145 | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON (SM/09612) | SM/09612 | 180.96 | 110 | NEW | 80 | On track | 50 | 24/11/2021 | 31/12/2025 | 19/05/2025 | 28/02/2022 | 90.46 | 90.46
146 | NIM KHASMAHAL & PHASINTING KHASMAL PWSS (SM/18415) | SM/18415 | 1069.7 | 475 | NEW | 80 | On track | 29 | 13/07/2023 | 31/12/2025 | 19/05/2025 | 17/08/2023 | 309.14 | 309.14
147 | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong (SM/13605) | SM/13605 | 419.43 | 991 | NEW | 80 | On track | 15 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 04/05/2023 | 62.92 | 62.92
148 | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10791) | SM/10791 | 470.31 | 373 | NEW | 85 | On track | 75 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 351.96 | 351.96
149 | TODAY TANGTA KHASMAHAL PWSS (SM/14171) | SM/14171 | 1635.15 | 970 | NEW | 85 | On track | 42 | 09/01/2023 | 31/12/2025 | 19/05/2025 | 28/04/2023 | 684.52 | 684.52
150 | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY (SM/11340) | SM/11340 | 220.09 | 280 | NEW | 85 | Delayed | 51 | 13/06/2022 | 31/03/2024 | 03/08/2023 | 30/06/2022 | 111.36 | 111.36
151 | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/13610) | SM/13610 | 260.67 | 309 | NEW | 85 | On track | 77 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 199.75 | 199.75
152 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG (SM/15463) | SM/15463 | 226.88 | 165 | NEW | 85 | On track | 78 | 04/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 176.68 | 176.68
153 | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10635) | SM/10635 | 143.53 | 70 | NEW | 85 | Delayed | 83 | 20/04/2022 | 30/06/2025 | 19/05/2025 | 30/06/2022 | 119.03 | 119.03
154 | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI (SM/09541) | SM/09541 | 568.83 | 400 | NEW | 86 | Delayed | 71 | 19/11/2021 | 31/03/2025 | 19/05/2025 | 04/04/2022 | 405.35 | 405.35
155 | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10793) | SM/10793 | 731.44 | 342 | NEW | 90 | On track | 80 | 25/05/2022 | 30/05/2025 | 19/05/2025 | 12/07/2022 | 586.1 | 586.1
156 | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/13611) | SM/13611 | 648.24 | 383 | NEW | 90 | On track | 69 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 09/02/2023 | 445.05 | 445.05
157 | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING (SM/09540) | SM/09540 | 91.94 | 61 | NEW | 90 | On track | 79 | 19/11/2021 | 31/12/2025 | 19/05/2025 | 14/01/2022 | 72.27 | 72.27
158 | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME (SM/11312) | SM/11312 | 100.81 | 98 | NEW | 90 | On track | 66 | 13/06/2022 | 31/12/2025 | 19/05/2025 | 30/06/2022 | 66.22 | 66.22
159 | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10625) | SM/10625 | 49.5 | 62 | NEW | 90 | On track | 86 | 20/04/2022 | 31/07/2025 | 19/05/2025 | 26/05/2022 | 42.76 | 42.76
160 | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. (SM/09599) | SM/09599 | 312 | 502 | NEW | 90 | On track | 73 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 227.79 | 227.79
161 | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA (SM/09584) | SM/09584 | 138.09 | 160 | NEW | 90 | On track | 87 | 22/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 119.64 | 119.64
162 | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong (SM/13604) | SM/13604 | 564.2 | 1015 | NEW | 90 | On track | 90 | 11/11/2022 | 31/12/2025 | 19/05/2025 | 01/11/2022 | 506.59 | 506.59
163 | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR (SM/09608) | SM/09608 | 367.78 | 448 | NEW | 90 | On track | 74 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 271.36 | 271.36
164 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/12630) | SM/12630 | 939.41 | 530 | NEW | 90 | On track | 73 | 19/09/2022 | 31/12/2025 | 19/05/2025 | 29/09/2022 | 685.16 | 685.16
165 | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10575) | SM/10575 | 49.33 | 43 | NEW | 90 | Delayed | 58 | 18/04/2022 | 31/03/2025 | 19/05/2025 | 26/05/2022 | 28.68 | 28.68
166 | Pws scheme from 7th Mile Jhora to Algarah (SM/09602) | SM/09602 | 321.38 | 450 | NEW | 93 | On track | 74 | 23/11/2021 | 30/05/2025 | 19/05/2025 | 21/02/2022 | 237.76 | 237.76
167 | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. (SM/10787) | SM/10787 | 975.33 | 613 | NEW | 95 | On track | 90 | 25/05/2022 | 31/12/2025 | 19/05/2025 | 12/07/2022 | 876.02 | 876.02
168 | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10599) | SM/10599 | 67.06 | 28 | NEW | 95 | On track | 79 | 18/04/2022 | 30/06/2025 | 19/05/2025 | 26/05/2022 | 52.65 | 52.65
169 | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10601) | SM/10601 | 9.66 | 10 | NEW | 95 | On track | 90 | 18/04/2022 | 30/05/2025 | 19/05/2025 | 26/05/2022 | 8.69 | 8.69
170 | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10624) | SM/10624 | 40.13 | 42 | NEW | 95 | On track | 95 | 20/04/2022 | 30/06/2025 | 19/05/2025 | 25/05/2022 | 38.03 | 38.03
171 | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10739) | SM/10739 | 5.37 | 7 | NEW | 95 | On track | 89 | 20/05/2022 | 31/07/2025 | 19/05/2025 | 26/05/2022 | 4.77 | 4.77
172 | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10602) | SM/10602 | 25.25 | 27 | NEW | 95 | On track | 40 | 18/04/2022 | 31/07/2025 | 19/05/2025 | 26/05/2022 | 10.13 | 10.13
173 | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10562) | SM/10562 | 132.05 | 67 | NEW | 95 | On track | 80 | 18/04/2022 | 31/03/2025 | 19/05/2025 | 24/05/2022 | 106.04 | 106.04
174 | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10603) | SM/10603 | 41.32 | 55 | NEW | 95 | On track | 90 | 18/04/2022 | 31/03/2025 | 19/05/2025 | 26/05/2022 | 37.19 | 37.19
175 | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE (SM/09603) | SM/09603 | 258.69 | 120 | NEW | 95 | On track | 84 | 23/11/2021 | 30/09/2025 | 19/05/2025 | 24/06/2020 | 218.44 | 214.89
176 | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON (SM/09613) | SM/09613 | 110.68 | 88 | NEW | 95 | On track | 74 | 24/11/2021 | 30/06/2025 | 19/05/2025 | 28/02/2022 | 81.5 | 81.5
177 | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI (SM/09664) | SM/09664 | 137.62 | 60 | NEW | 95 | On track | 90 | 24/11/2021 | 31/03/2025 | 19/05/2025 | 07/01/2022 | 124.19 | 124.17
178 | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10623) | SM/10623 | 41.4 | 28 | NEW | 95 | On track | 81 | 20/04/2022 | 31/03/2025 | 19/05/2025 | 25/05/2022 | 33.46 | 33.46
179 | PAREN FOREST PIPED WATER SUPPLY SCHEME (SM/13609) | SM/13609 | 133.18 | 46 | NEW | 95 | On track | 56 | 11/11/2022 | 31/07/2025 | 19/05/2025 | 17/07/2023 | 74.13 | 74.13
180 | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. (SM/09544) | SM/09544 | 198.74 | 147 | NEW | 95 | On track | 94 | 19/11/2021 | 25/04/2025 | 19/05/2025 | 14/01/2022 | 186.54 | 186.45
181 | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. (SM/10600) | SM/10600 | 10.62 | 13 | NEW | 95 | On track | 0 | 18/04/2022 | 31/03/2025 | 19/05/2025 | 26/05/2022 | 0 | 0
182 | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/15646) | SM/15646 | 226.84 | 171 | NEW | 96 | On track | 44 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 99.64 | 99.64
183 | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. (SM/10729) | SM/10729 | 136.35 | 197 | NEW | 98 | On track | 65 | 18/05/2022 | 30/06/2025 | 19/05/2025 | 26/05/2022 | 89.26 | 89.26
184 | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10563) | SM/10563 | 62.89 | 34 | NEW | 98 | On track | 70 | 18/04/2022 | 31/05/2025 | 19/05/2025 | 26/05/2022 | 44.12 | 44.12
185 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong (SM/14192) | SM/14192 | 839.64 | 690 | NEW | 100 | 100% Physical | 53 | 10/01/2023 | 31/12/2025 | 19/05/2025 | 03/03/2023 | 446.69 | 446.69
186 | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA (SM/09597) | SM/09597 | 199.67 | 74 | NEW | 100 | 100% Physical | 86 | 23/11/2021 | 31/12/2025 | 19/05/2025 | 24/06/2020 | 172.38 | 172.38
187 | PWS SCHEME FROM UNEAK KHOLA TO DABLING (SM/09595) | SM/09595 | 126.98 | 95 | NEW | 100 | 100% Physical | 97 | 23/11/2021 | 31/03/2024 | 19/05/2025 | 24/06/2020 | 123.28 | 123.18
188 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15641) | SM/15641 | 214.02 | 275 | NEW | 100 | 100% Physical | 67 | 20/02/2023 | 31/12/2025 | 19/05/2025 | 28/02/2023 | 144.39 | 144.39
189 | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION (SM/10744) | SM/10744 | 225.47 | 405 | NEW | 100 | 100% Physical | 97 | 19/05/2022 | 20/03/2024 | 19/05/2025 | 25/05/2022 | 218.46 | 218.46
190 | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS (SM/19112) | SM/19112 | 1414.95 | 784 | NEW | 100 | 100% Physical | 0 | 21/12/2023 | 07/11/2025 | 19/05/2025 | 03/01/2024 | 4.82 | 4.82
191 | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON (SM/10746) | SM/10746 | 194.83 | 205 | NEW | 100 | 100% Physical | 97 | 19/05/2022 | 31/03/2025 | 19/05/2025 | 25/05/2022 | 189.16 | 189.16
Total |  |  | 75507.75 | 67087 | [8 empty] | 32895.66 | 32851.24