## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) (SM/07872) | SM/07872 | 72.63 | 625 | RETROFITTING | 0 | 0% Physical | 89 | 19/01/2021 | 28/02/2022 | 12/06/2023 | 12/10/2020 | 64.69 | 59.08
2 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG (SM/13606) | SM/13606 | 427.72 | 692 | NEW | 0 | 0% Physical | 0 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 24/07/2023 | 0 | 0
3 | GORUBATHAN-I PWSS (SM/14172) | SM/14172 | 1146.86 | 1818 | NEW | 0 | 0% Physical | 0 | 09/01/2023 | 09/01/2025 | 12/06/2023 | 18/07/2023 | 0 | 0
4 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG (SM/16235) | SM/16235 | 233.82 | 199 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 12/07/2023 | 0 | 0
5 | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. (SM/11367) | SM/11367 | 15 | 0 | HEALTH CENTER | 0 | 0% Physical | 0 | 28/06/2022 |  | 05/05/2023 | 26/05/2022 | 0 | 0
6 | GODAK BUSTY PIPED WATER SUPPLY SCHEME. (SM/13608) | SM/13608 | 356.95 | 136 | NEW | 0 | 0% Physical | 0 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 24/07/2023 | 0 | 0
7 | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG (SM/18322) | SM/18322 | 1040.03 | 1196 | NEW | 0 | 0% Physical | 0 | 27/06/2023 | 27/06/2025 | 27/06/2023 | 18/07/2023 | 0 | 0
8 | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. (SM/10266) | SM/10266 | 187.99 | 1769 | RETROFITTING | 0 | 0% Physical | 88 | 09/02/2021 | 09/05/2021 | 12/06/2023 | 14/12/2022 | 165.14 | 155.87
9 | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11359) | SM/11359 | 261.22 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 |  | 05/05/2023 | 12/07/2022 | 0 | 0
10 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16232) | SM/16232 | 380.82 | 206 | NEW | 0 | 0% Physical | 0 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 05/06/2023 | 1.23 | 1.23
11 | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. (SM/11369) | SM/11369 | 17.3 | 0 | HEALTH CENTER | 0 | 0% Physical | 0 | 28/06/2022 |  | 05/05/2023 | 12/07/2022 | 0 | 0
12 | Creating gravity based provision of drinking water from spring water source for 27 numbers school, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong (SM/11357) | SM/11357 | 142.95 | 0 | SCHOOL | 0 | 0% Physical | 0 | 28/06/2022 |  | 05/05/2023 | 12/07/2022 | 0 | 0
13 | RANGO FOREST PWSS (SM/18823) | SM/18823 | 1664.29 | 1892 | NEW | 0 | 0% Physical | 1 | 11/09/2023 | 11/09/2025 | 18/09/2023 | 21/09/2023 | 11.65 | 11.65
14 | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. (SM/10265) | SM/10265 | 228.22 | 1475 | RETROFITTING | 0 | 0% Physical | 87 | 09/02/2021 | 09/05/2021 | 12/06/2023 | 14/12/2022 | 199.13 | 199.13
15 | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10624) | SM/10624 | 40.13 | 42 | NEW | 0 | 0% Physical | 95 | 20/04/2022 | 20/10/2023 | 12/06/2023 | 25/05/2022 | 38.03 | 38.03
16 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG (SM/16231) | SM/16231 | 944.04 | 1175 | NEW | 0 | 0% Physical | 1 | 24/02/2023 | 24/08/2024 | 12/06/2023 | 26/05/2023 | 7.2 | 7.2
17 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/18247) | SM/18247 | 1350.54 | 946 | NEW | 0 | 0% Physical | 0 | 16/06/2023 | 16/06/2025 | 22/06/2023 | 18/07/2023 | 0 | 0
18 | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I (SM/18442) | SM/18442 | 3858.84 | 3573 | AUGMENTATION | 0 | 0% Physical | 0 | 18/07/2023 | 18/07/2024 | 20/07/2023 | 06/12/2023 | 0 | 0
19 | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. (SM/18443) | SM/18443 | 3488.92 | 3512 | NEW | 0 | 0% Physical | 0 | 20/07/2023 | 20/07/2025 | 20/07/2023 | 24/07/2023 | 0 | 0
20 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. (SM/19176) | SM/19176 | 2560.38 | 1749 | NEW | 0 | 0% Physical | 0 | 15/02/2024 |  | 15/02/2024 | 20/02/2024 | 0 | 0
21 | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS (SM/13953) | SM/13953 | 882.37 | 663 | NEW | 0 | 0% Physical | 1 | 01/12/2022 | 01/06/2024 | 12/06/2023 | 09/02/2023 | 8.17 | 8.17
22 | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG (SM/16511) | SM/16511 | 964.71 | 1013 | NEW | 0 | 0% Physical | 1 | 03/03/2023 | 03/09/2024 | 12/06/2023 | 05/06/2023 | 6.24 | 6.24
23 | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS (SM/19112) | SM/19112 | 1414.95 | 784 | NEW | 0 | 0% Physical | 0 | 21/12/2023 |  | 21/12/2023 | 03/01/2024 | 0 | 0
24 | Extension of piped water supply scheme to Upper Pedong Lower Goan (St George Primary School) Anganwadi Centre under Pedong G.P and Pagang Gumtaline Anganwadi Centre under Paiyong G.P under Kalimpong lock-II, located within the commanding area of PWSS for (SM/09019) | SM/09019 | 8.21 | 0 | ANGANWADI | 0 | WO no issued | 0 | 30/10/2021 |  | 05/05/2023 |  | 0 | 0
25 | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. (SM/10267) | SM/10267 | 127.68 | 1116 | RETROFITTING | 0 | 0% Physical | 92 | 09/02/2021 | 09/05/2021 | 12/06/2023 | 14/12/2022 | 116.84 | 116.84
26 | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10601) | SM/10601 | 9.66 | 10 | NEW | 0 | 0% Physical | 90 | 18/04/2022 | 18/10/2023 | 12/06/2023 | 26/05/2022 | 8.69 | 8.69
27 | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong (SM/10820) | SM/10820 | 47.33 | 48 | NEW | 0 | 0% Physical | 5 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 30/06/2022 | 2.13 | 2.13
28 | Creating gravity based Provision Of Drinking water from spring water source for 07 (Seven) Numbers of Gram Panchayat office in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11372) | SM/11372 | 43.43 | 7 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 0 | 0% Physical | 0 | 28/06/2022 |  | 05/05/2023 | 12/07/2022 | 0 | 0
29 | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W (SM/10140) | SM/10140 | 436.51 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 08/02/2022 |  | 10/02/2022 | 31/12/2021 | 0 | 0
30 | Collection of Water Samples from different drinking water sources, tanks and reservoir etc. under Kalimpong district and submitting the same to the respective water testing laboratories (Neorakhola sub-district laboratory and Algarah sub-district laborato (SM/15669) | SM/15669 | 27.41 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 17/02/2023 |  | 23/02/2023 | 03/03/2023 | 0 | 0
31 | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. (SM/13680) | SM/13680 | 6.46 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 14/11/2022 |  | 17/11/2022 |  | 0 | 0
32 | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. (SM/10513) | SM/10513 | 13.03 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 13/04/2022 |  | 18/04/2022 |  | 0 | 0
33 | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (SM/13613) | SM/13613 | 351.35 | 303 | NEW | 5 | Delayed | 0 | 11/11/2022 | 31/12/2023 | 03/08/2023 | 26/05/2023 | 0.45 | 0.45
34 | UPPER FAGU PIPED WATER SUPPLY SCHEME. (SM/13954) | SM/13954 | 819.76 | 924 | NEW | 5 | Delayed | 1 | 01/12/2022 | 31/12/2023 | 03/08/2023 | 18/07/2023 | 6.14 | 6.14
35 | TODAY TANGTA KHASMAHAL PWSS (SM/14171) | SM/14171 | 1635.15 | 970 | NEW | 5 | Delayed | 8 | 09/01/2023 | 31/10/2023 | 03/08/2023 | 28/04/2023 | 122.77 | 122.77
36 | PATEN GODAK KHASMAHAL PWSS (SM/18255) | SM/18255 | 1128.06 | 874 | NEW | 5 | Delayed | 0 | 21/06/2023 | 31/12/2023 | 03/08/2023 | 17/07/2023 | 1.35 | 1.35
37 | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10603) | SM/10603 | 41.32 | 55 | NEW | 10 | Delayed | 90 | 18/04/2022 | 31/03/2024 | 20/03/2024 | 26/05/2022 | 37.19 | 37.19
38 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG (SM/15463) | SM/15463 | 226.88 | 165 | NEW | 10 | Delayed | 53 | 04/02/2023 | 04/08/2024 | 12/06/2023 | 28/02/2023 | 119.24 | 112.03
39 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16234) | SM/16234 | 55.28 | 47 | NEW | 10 | Delayed | 5 | 24/02/2023 | 24/08/2024 | 03/11/2023 | 12/07/2023 | 2.71 | 2.71
40 | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. (SM/11364) | SM/11364 | 398.55 | 0 | ANGANWADI | 10 | Delayed | 0 | 28/06/2022 | 31/03/2024 | 21/09/2023 | 12/07/2022 | 0 | 0
41 | KUMAI FOREST PIPED WATER SUPPLY SCHEME. (SM/13612) | SM/13612 | 290.97 | 245 | NEW | 10 | Delayed | 1 | 11/11/2022 | 11/05/2024 | 16/10/2023 | 05/06/2023 | 3.91 | 2.6
42 | PAREN FOREST PIPED WATER SUPPLY SCHEME (SM/13609) | SM/13609 | 133.18 | 46 | NEW | 10 | Delayed | 4 | 11/11/2022 | 11/05/2024 | 16/10/2023 | 17/07/2023 | 5.9 | 3.94
43 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong (SM/14193) | SM/14193 | 701.2 | 724 | NEW | 10 | Delayed | 0 | 10/01/2023 | 10/07/2024 | 03/10/2023 | 26/05/2023 | 0 | 0
44 | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME (SM/13610) | SM/13610 | 260.67 | 309 | NEW | 10 | Delayed | 52 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 01/11/2022 | 134.74 | 101.9
45 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13616) | SM/13616 | 268.04 | 123 | NEW | 15 | Delayed | 33 | 11/11/2022 | 11/05/2024 | 12/06/2023 | 16/01/2023 | 88.77 | 50.62
46 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG (SM/15644) | SM/15644 | 650.72 | 538 | NEW | 17 | Delayed | 1 | 20/02/2023 | 20/08/2024 | 16/04/2024 | 10/05/2023 | 4.41 | 4.41
47 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG (SM/15645) | SM/15645 | 973.41 | 651 | NEW | 18 | Delayed | 0 | 20/02/2023 | 16/09/2025 | 16/04/2024 | 10/05/2023 | 2.99 | 2.99
48 | SURUK PIPED WATER SUPPLY SCHEME (SM/13607) | SM/13607 | 643.2 | 338 | NEW | 20 | Delayed | 0 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 09/02/2023 | 0 | 0
49 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16514) | SM/16514 | 896.34 | 538 | NEW | 20 | Delayed | 0 | 03/03/2023 | 03/09/2024 | 13/03/2024 | 05/06/2023 | 3.33 | 3.33
50 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong (SM/14192) | SM/14192 | 839.64 | 690 | NEW | 24 | Delayed | 1 | 10/01/2023 | 10/07/2024 | 16/04/2024 | 03/03/2023 | 6.87 | 5.34
51 | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME (SM/13602) | SM/13602 | 335.49 | 445 | NEW | 26 | Delayed | 30 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 16/01/2023 | 101.92 | 6.58
52 | BINDU PIPED WATER SUPPLY SCHEME (SM/13622) | SM/13622 | 130.17 | 174 | NEW | 35 | Delayed | 1 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 01/11/2022 | 1.07 | 1.07
53 | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS (SM/15937) | SM/15937 | 657.46 | 782 | NEW | 35 | Delayed | 42 | 22/02/2023 | 22/08/2024 | 29/04/2024 | 03/03/2023 | 278.74 | 254.82
54 | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG (SM/13603) | SM/13603 | 341.66 | 664 | NEW | 37 | Delayed | 2 | 11/11/2022 | 30/05/2024 | 27/02/2024 | 01/02/2023 | 6.97 | 5.18
55 | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. (SM/13611) | SM/13611 | 648.24 | 383 | NEW | 40 | Delayed | 15 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 09/02/2023 | 96.26 | 84.25
56 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/12629) | SM/12629 | 752.8 | 588 | NEW | 40 | Delayed | 57 | 19/09/2022 | 19/03/2024 | 12/06/2023 | 29/09/2022 | 425.76 | 425.76
57 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15641) | SM/15641 | 214.02 | 275 | NEW | 40 | Delayed | 2 | 20/02/2023 | 20/08/2024 | 29/01/2024 | 28/02/2023 | 3.67 | 2.79
58 | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16233) | SM/16233 | 963.91 | 700 | NEW | 40 | Delayed | 0 | 24/02/2023 | 24/08/2024 | 27/02/2024 | 12/07/2023 | 0 | 0
59 | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong (SM/13605) | SM/13605 | 419.43 | 991 | NEW | 40 | Delayed | 1 | 11/11/2022 | 11/05/2024 | 27/02/2024 | 04/05/2023 | 4.13 | 3.96
60 | NIM KHASMAHAL & PHASINTING KHASMAL PWSS (SM/18415) | SM/18415 | 1069.7 | 475 | NEW | 40 | On track | 0 | 13/07/2023 | 13/07/2025 | 27/03/2024 | 17/08/2023 | 0 | 0
61 | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong (SM/10052) | SM/10052 | 4402.74 | 0 | AUGMENTATION | 47 | Delayed | 15 | 25/01/2022 | 31/03/2024 | 05/07/2023 | 28/02/2022 | 652.36 | 642.99
62 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/15042) | SM/15042 | 213.24 | 161 | NEW | 50 | Delayed | 32 | 04/02/2023 | 04/08/2024 | 20/03/2024 | 09/02/2023 | 67.98 | 1.98
63 | PANKHASARI KHASMAHAL PWSS (SM/14170) | SM/14170 | 1201.07 | 666 | NEW | 50 | Delayed | 55 | 09/01/2023 | 09/01/2025 | 30/11/2023 | 06/02/2023 | 661.85 | 210.91
64 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13615) | SM/13615 | 101.26 | 35 | NEW | 50 | Delayed | 50 | 11/11/2022 | 11/05/2024 | 19/01/2024 | 01/02/2023 | 50.22 | 50.22
65 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong (SM/14194) | SM/14194 | 747.62 | 1264 | NEW | 50 | Delayed | 25 | 10/01/2023 | 10/07/2024 | 18/03/2024 | 12/07/2023 | 184.19 | 7.79
66 | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR (SM/11354) | SM/11354 | 143.23 | 106 | NEW | 50 | Delayed | 50 | 28/06/2022 | 28/12/2023 | 12/06/2023 | 21/09/2022 | 72.04 | 72.04
67 | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/16649) | SM/16649 | 437.66 | 351 | NEW | 50 | Delayed | 1 | 14/03/2023 | 14/09/2024 | 13/03/2024 | 28/04/2023 | 3.22 | 3.05
68 | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10576) | SM/10576 | 49.14 | 45 | NEW | 50 | Delayed | 63 | 18/04/2022 | 18/10/2023 | 09/10/2023 | 26/05/2022 | 30.78 | 30.78
69 | Creating gravity based provision of Drinking water from spring water source for 13 Numbers Health care Facilities in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. (SM/11368) | SM/11368 | 54.35 | 0 | HEALTH CENTER | 55 | Delayed | 0 | 28/06/2022 | 31/12/2023 | 31/07/2023 | 12/07/2022 | 0 | 0
70 | PWS SCHEME FROM PHENTO SOURCE TO DUKA (SM/10748) | SM/10748 | 165.77 | 143 | NEW | 55 | Delayed | 70 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 115.72 | 115.72
71 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG (SM/16230) | SM/16230 | 921.36 | 1068 | NEW | 55 | Delayed | 36 | 24/02/2023 | 31/03/2024 | 01/08/2023 | 29/05/2023 | 334.18 | 311.58
72 | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11377) | SM/11377 | 89.16 | 55 | NEW | 56 | Delayed | 58 | 04/07/2022 | 31/12/2023 | 21/07/2023 | 12/07/2022 | 51.77 | 22.73
73 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/13621) | SM/13621 | 236.28 | 124 | NEW | 60 | Delayed | 19 | 11/11/2022 | 11/05/2024 | 28/11/2023 | 16/01/2023 | 44.7 | 44.7
74 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/16512) | SM/16512 | 160.61 | 136 | NEW | 60 | Delayed | 1 | 03/03/2023 | 03/09/2024 | 16/05/2024 | 28/04/2023 | 2.19 | 1.93
75 | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11577) | SM/11577 | 47.54 | 32 | NEW | 60 | Delayed | 38 | 22/07/2022 | 22/01/2024 | 12/06/2023 | 28/09/2022 | 18.08 | 18.08
76 | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong (SM/13604) | SM/13604 | 564.2 | 1015 | NEW | 60 | Delayed | 62 | 11/11/2022 | 14/10/2023 | 11/07/2023 | 01/11/2022 | 348.77 | 348.77
77 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG (SM/15643) | SM/15643 | 300.21 | 169 | NEW | 60 | Delayed | 16 | 20/02/2023 | 20/08/2024 | 27/02/2024 | 28/02/2023 | 49.11 | 1.04
78 | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG (SM/14191) | SM/14191 | 693.21 | 915 | NEW | 60 | Delayed | 0 | 10/01/2023 | 10/07/2024 | 13/03/2024 | 09/02/2023 | 1.87 | 1.09
79 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG (SM/16513) | SM/16513 | 304 | 369 | NEW | 60 | Delayed | 30 | 03/03/2023 | 03/09/2024 | 27/02/2024 | 28/04/2023 | 89.7 | 3.36
80 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/12630) | SM/12630 | 939.41 | 530 | NEW | 60 | Delayed | 54 | 19/09/2022 | 10/10/2023 | 12/07/2023 | 29/09/2022 | 510.22 | 277.53
81 | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS (SM/15554) | SM/15554 | 248.56 | 278 | NEW | 65 | Delayed | 22 | 15/02/2023 | 15/08/2024 | 29/04/2024 | 03/03/2023 | 55.2 | 0.86
82 | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY (SM/09543) | SM/09543 | 365.16 | 213 | NEW | 65 | Delayed | 51 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 185.51 | 185.51
83 | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. (SM/11806) | SM/11806 | 204.57 | 139 | NEW | 65 | Delayed | 45 | 10/08/2022 | 28/02/2023 | 05/07/2023 | 12/08/2022 | 91.72 | 91.72
84 | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON (SM/09668) | SM/09668 | 182.37 | 140 | NEW | 65 | Delayed | 54 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 98.34 | 98.31
85 | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10700) | SM/10700 | 173.31 | 242 | NEW | 66 | Delayed | 44 | 12/05/2022 | 31/08/2023 | 06/07/2023 | 24/05/2022 | 75.53 | 75.53
86 | Creating gravity based provision of Drinking water from spring water source for 12 Numbers of Gram panchayat Buildings in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. (SM/11371) | SM/11371 | 39.73 | 12 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 70 | Delayed | 0 | 28/06/2022 | 30/09/2023 | 21/07/2023 | 12/07/2022 | 0 | 0
87 | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/11313) | SM/11313 | 829.3 | 462 | NEW | 70 | Delayed | 54 | 15/06/2022 | 15/12/2023 | 12/06/2023 | 12/07/2022 | 449.15 | 448.58
88 | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE (SM/09594) | SM/09594 | 776.35 | 480 | NEW | 70 | Delayed | 75 | 23/11/2021 | 31/03/2024 | 21/07/2023 | 04/04/2022 | 582.85 | 382.53
89 | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10792) | SM/10792 | 606.74 | 457 | NEW | 70 | Delayed | 63 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 12/07/2022 | 380.26 | 380.26
90 | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/15646) | SM/15646 | 226.84 | 171 | NEW | 70 | Delayed | 39 | 20/02/2023 | 20/08/2024 | 29/01/2024 | 28/02/2023 | 88.38 | 31.05
91 | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11376) | SM/11376 | 191.02 | 147 | NEW | 74 | Delayed | 56 | 04/07/2022 | 30/11/2023 | 21/07/2023 | 12/07/2022 | 106.89 | 106.89
92 | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10702) | SM/10702 | 113.56 | 131 | NEW | 75 | Delayed | 70 | 12/05/2022 | 12/11/2023 | 12/06/2023 | 13/05/2022 | 79.21 | 79.21
93 | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE (SM/09666) | SM/09666 | 138.81 | 140 | NEW | 75 | Delayed | 74 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 103.07 | 103.07
94 | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10701) | SM/10701 | 114.57 | 90 | NEW | 75 | Delayed | 71 | 12/05/2022 | 12/11/2023 | 12/06/2023 | 30/06/2022 | 81.26 | 81.26
95 | PWS SCHEME FROM KHANI KHOLA TO CHUKIM (SM/10753) | SM/10753 | 138.36 | 122 | NEW | 75 | Delayed | 85 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 117.83 | 104.57
96 | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP (SM/10755) | SM/10755 | 201.1 | 160 | NEW | 75 | Delayed | 57 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 114.88 | 114.88
97 | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10694) | SM/10694 | 94.15 | 105 | NEW | 75 | Delayed | 59 | 12/05/2022 | 12/11/2023 | 12/06/2023 | 25/05/2022 | 55.95 | 55.95
98 | PWS SCHEME FROM KHARKHOLA TO LOWER REON (SM/10756) | SM/10756 | 105.07 | 102 | NEW | 75 | Delayed | 71 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 74.29 | 74.29
99 | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10793) | SM/10793 | 731.44 | 342 | NEW | 75 | Delayed | 63 | 25/05/2022 | 31/12/2023 | 31/07/2023 | 12/07/2022 | 458.04 | 456.98
100 | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. (SM/11370) | SM/11370 | 27.84 | 6 | GOVT. INSTITUTIONAL BUILDING (GP BUILDING, COMMUNITY CENTRE, COMMUNITY TOILET, OTHER GOVT. OFFICES) | 75 | Delayed | 0 | 28/06/2022 | 31/03/2024 | 06/07/2023 | 26/05/2022 | 0 | 0
101 | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. (SM/18589) | SM/18589 | 1104.14 | 1130 | NEW | 75 | On track | 34 | 31/07/2023 | 31/07/2025 | 29/04/2024 | 07/08/2023 | 378.67 | 369.82
102 | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte (SM/11358) | SM/11358 | 182.6 | 0 | SCHOOL | 80 | Delayed | 0 | 28/06/2022 | 31/03/2024 | 09/11/2023 | 12/07/2022 | 0 | 0
103 | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON (SM/09542) | SM/09542 | 108.18 | 87 | NEW | 80 | Delayed | 83 | 19/11/2021 | 31/03/2024 | 11/01/2024 | 28/03/2022 | 89.57 | 89.57
104 | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10704) | SM/10704 | 338.99 | 226 | NEW | 80 | Delayed | 75 | 12/05/2022 | 30/09/2023 | 15/07/2023 | 05/08/2022 | 255.11 | 255.11
105 | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10705) | SM/10705 | 99.21 | 105 | AUGMENTATION | 80 | Delayed | 68 | 12/05/2022 | 31/10/2023 | 07/08/2023 | 13/04/2022 | 67.31 | 67.31
106 | PAGRAN BONG KHASMAHAL PWSS (SM/16854) | SM/16854 | 473.77 | 187 | NEW | 80 | On track | 38 | 13/03/2023 | 13/09/2024 | 27/02/2024 | 12/07/2023 | 182.17 | 81.45
107 | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG (SM/09665) | SM/09665 | 142.76 | 221 | NEW | 80 | Delayed | 33 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 46.99 | 46.99
108 | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA (SM/09600) | SM/09600 | 169.19 | 234 | NEW | 80 | Delayed | 37 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 62.52 | 62.38
109 | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG (SM/09547) | SM/09547 | 237.68 | 300 | NEW | 80 | Delayed | 54 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 128.7 | 121.25
110 | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI (SM/09539) | SM/09539 | 151.5 | 121 | NEW | 80 | Delayed | 80 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 121.37 | 121.37
111 | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN (SM/09607) | SM/09607 | 108.86 | 208 | NEW | 80 | Delayed | 69 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 75.45 | 75.45
112 | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON (SM/09612) | SM/09612 | 180.96 | 110 | NEW | 80 | Delayed | 50 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 28/02/2022 | 90.46 | 90.46
113 | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE (SM/10741) | SM/10741 | 92.28 | 80 | NEW | 84 | Delayed | 70 | 19/05/2022 | 19/11/2023 | 16/04/2024 | 26/05/2022 | 64.7 | 64.39
114 | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10791) | SM/10791 | 470.31 | 373 | NEW | 85 | Delayed | 75 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 30/06/2022 | 351.96 | 288.58
115 | PWS SCHEME FROM SISNEY JHORA TO SAMTHAR BAZAR (SM/10742) | SM/10742 | 197.78 | 252 | NEW | 85 | Delayed | 90 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 178 | 178
116 | PWS from Samphong Khola to Kagey Busty District Kalimpong (SM/09548) | SM/09548 | 679.86 | 641 | NEW | 85 | Delayed | 88 | 19/11/2021 | 31/03/2024 | 07/08/2023 | 24/06/2020 | 598.98 | 412.57
117 | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10697) | SM/10697 | 126.09 | 100 | NEW | 85 | Delayed | 58 | 12/05/2022 | 12/11/2023 | 12/06/2023 | 01/08/2022 | 73.25 | 73.25
118 | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY (SM/11340) | SM/11340 | 220.09 | 280 | NEW | 85 | Delayed | 51 | 13/06/2022 | 31/03/2024 | 03/08/2023 | 30/06/2022 | 111.36 | 111.36
119 | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10703) | SM/10703 | 286.37 | 407 | NEW | 85 | Delayed | 88 | 12/05/2022 | 30/09/2023 | 11/09/2023 | 26/05/2022 | 252.26 | 252.26
120 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG (SM/13617) | SM/13617 | 442.25 | 240 | NEW | 85 | Delayed | 69 | 11/11/2022 | 11/05/2024 | 16/04/2024 | 14/12/2022 | 305.29 | 304.86
121 | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. (SM/10635) | SM/10635 | 143.53 | 70 | NEW | 85 | Delayed | 76 | 20/04/2022 | 20/10/2023 | 12/06/2023 | 30/06/2022 | 109.46 | 109.46
122 | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI (SM/09541) | SM/09541 | 568.83 | 400 | NEW | 86 | Delayed | 71 | 19/11/2021 | 30/09/2023 | 10/07/2023 | 04/04/2022 | 405.35 | 405.35
123 | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10625) | SM/10625 | 49.5 | 62 | NEW | 90 | Delayed | 86 | 20/04/2022 | 20/10/2023 | 12/06/2023 | 26/05/2022 | 42.76 | 24.58
124 | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11955) | SM/11955 | 242.62 | 221 | NEW | 90 | Delayed | 41 | 24/08/2022 | 30/04/2024 | 27/03/2024 | 04/11/2022 | 99.2 | 99.2
125 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15642) | SM/15642 | 211.63 | 314 | NEW | 90 | On track | 48 | 20/02/2023 | 20/08/2024 | 27/03/2024 | 28/02/2023 | 101.51 | 96.35
126 | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte (SM/10214) | SM/10214 | 753.18 | 0 | SCHOOL | 90 | Delayed | 0 | 24/02/2022 | 30/09/2023 | 19/07/2023 | 28/03/2022 | 0 | 0
127 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG (SM/15640) | SM/15640 | 497.43 | 685 | NEW | 90 | On track | 2 | 20/02/2023 | 20/08/2024 | 27/02/2024 | 28/02/2023 | 8.44 | 8.44
128 | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. (SM/09599) | SM/09599 | 312 | 502 | NEW | 90 | Delayed | 73 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 227.79 | 227.79
129 | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA (SM/09584) | SM/09584 | 138.09 | 160 | NEW | 90 | Delayed | 87 | 22/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 119.64 | 119.64
130 | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG (SM/09669) | SM/09669 | 125.27 | 56 | NEW | 90 | Delayed | 88 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 110.7 | 110.7
131 | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10575) | SM/10575 | 49.33 | 43 | NEW | 90 | Delayed | 58 | 18/04/2022 | 31/03/2024 | 26/07/2023 | 26/05/2022 | 28.68 | 28.68
132 | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR (SM/09608) | SM/09608 | 367.78 | 448 | NEW | 90 | Delayed | 74 | 23/11/2021 | 31/12/2023 | 16/04/2024 | 24/06/2020 | 271.36 | 205.98
133 | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING (SM/09540) | SM/09540 | 91.94 | 61 | NEW | 90 | Delayed | 79 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 14/01/2022 | 72.27 | 72.27
134 | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10699) | SM/10699 | 152.76 | 350 | NEW | 90 | Delayed | 39 | 12/05/2022 | 12/11/2023 | 28/09/2023 | 25/05/2022 | 60 | 60
135 | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA (SM/10743) | SM/10743 | 79.81 | 87 | NEW | 90 | Delayed | 82 | 19/05/2022 | 19/11/2023 | 28/09/2023 | 25/05/2022 | 65.18 | 65.18
136 | PWS SCHEME FROM BANGLA JHORA TO JOGITAR (SM/10750) | SM/10750 | 65.73 | 60 | NEW | 90 | Delayed | 19 | 19/05/2022 | 19/11/2023 | 12/06/2023 | 25/05/2022 | 12.32 | 12.32
137 | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10623) | SM/10623 | 41.4 | 28 | NEW | 95 | Delayed | 81 | 20/04/2022 | 31/08/2023 | 06/07/2023 | 25/05/2022 | 33.46 | 33.46
138 | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10698) | SM/10698 | 206.41 | 169 | NEW | 95 | Delayed | 72 | 12/05/2022 | 31/10/2023 | 10/08/2023 | 25/05/2022 | 149.04 | 149.04
139 | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong (SM/10512) | SM/10512 | 504.2 | 677 | RETROFITTING | 95 | Delayed | 63 | 13/04/2022 | 13/07/2022 | 12/06/2023 | 13/04/2022 | 315.69 | 270.68
140 | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG (SM/11578) | SM/11578 | 393.32 | 296 | NEW | 95 | Delayed | 74 | 22/07/2022 | 22/01/2024 | 03/10/2023 | 14/10/2022 | 292.7 | 292.7
141 | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA (SM/09597) | SM/09597 | 199.67 | 74 | NEW | 95 | Delayed | 86 | 23/11/2021 | 31/07/2023 | 06/07/2023 | 24/06/2020 | 172.38 | 172.38
142 | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. (SM/11579) | SM/11579 | 312.68 | 249 | NEW | 95 | Delayed | 80 | 22/07/2022 | 22/01/2024 | 03/10/2023 | 14/10/2022 | 248.74 | 248.74
143 | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON (SM/09545) | SM/09545 | 160.48 | 125 | NEW | 95 | Delayed | 61 | 19/11/2021 | 31/12/2023 | 16/04/2024 | 07/01/2022 | 98.7 | 98.7
144 | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. (SM/10787) | SM/10787 | 975.33 | 613 | NEW | 95 | Delayed | 90 | 25/05/2022 | 25/11/2023 | 12/06/2023 | 12/07/2022 | 876.02 | 876.02
145 | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. (SM/10562) | SM/10562 | 132.05 | 67 | NEW | 95 | Delayed | 80 | 18/04/2022 | 31/08/2023 | 21/07/2023 | 24/05/2022 | 106.04 | 106.04
146 | Pws scheme from 7th Mile Jhora to Algarah (SM/09602) | SM/09602 | 321.38 | 450 | NEW | 97 | Delayed | 74 | 23/11/2021 | 31/10/2023 | 08/08/2023 | 21/02/2022 | 237.76 | 237.76
147 | PWS SCHEME FROM MANDIR KHOLA TO TANYANG (SM/10751) | SM/10751 | 214.24 | 195 | NEW | 97 | On track | 82 | 19/05/2022 | 16/06/2024 | 16/05/2024 | 26/05/2022 | 175.66 | 175.66
148 | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME (SM/11312) | SM/11312 | 100.81 | 98 | NEW | 98 | Delayed | 66 | 13/06/2022 | 31/10/2023 | 21/07/2023 | 30/06/2022 | 66.22 | 66.22
149 | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON (SM/09596) | SM/09596 | 314.39 | 320 | NEW | 100 | 100% Physical | 100 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 313.01 | 312.99
150 | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON (SM/09598) | SM/09598 | 96.33 | 56 | NEW | 100 | 100% Physical | 97 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 93.52 | 93.52
151 | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG (SM/09611) | SM/09611 | 80.8 | 70 | NEW | 100 | 100% Physical | 73 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 14/08/2020 | 59.3 | 59.3
152 | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION (SM/10744) | SM/10744 | 225.47 | 405 | NEW | 100 | 100% Physical | 97 | 19/05/2022 |  | 12/06/2023 | 25/05/2022 | 218.46 | 218.46
153 | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE (SM/10749) | SM/10749 | 105.72 | 105 | NEW | 100 | 100% Physical | 93 | 19/05/2022 |  | 12/06/2023 | 25/05/2022 | 97.81 | 97.81
154 | PWSS FROM BHARKHOP JHORA TO LOWER KAFFER (SM/11343) | SM/11343 | 99.53 | 85 | NEW | 100 | 100% Physical | 70 | 13/06/2022 | 15/03/2024 | 27/02/2024 | 30/06/2022 | 69.95 | 69.95
155 | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY (SM/10754) | SM/10754 | 176.39 | 160 | NEW | 100 | 100% Physical | 89 | 19/05/2022 | 19/11/2023 | 15/09/2023 | 26/05/2022 | 157.47 | 157.47
156 | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR (SM/09601) | SM/09601 | 206.39 | 245 | NEW | 100 | 100% Physical | 44 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 91.27 | 90.93
157 | PWS SCHEME FROM CHAWA KHOLA TO RELLI (SM/09610) | SM/09610 | 122.01 | 125 | NEW | 100 | 100% Physical | 97 | 24/11/2021 | 31/12/2022 | 16/04/2024 | 24/06/2020 | 117.87 | 117.87
158 | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE (SM/09617) | SM/09617 | 100.06 | 99 | NEW | 100 | 100% Physical | 68 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 14/01/2022 | 67.75 | 67.44
159 | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10563) | SM/10563 | 62.89 | 34 | NEW | 100 | 100% Physical | 55 | 18/04/2022 |  | 12/06/2023 | 26/05/2022 | 34.37 | 34.37
160 | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING (SM/09609) | SM/09609 | 98.66 | 75 | NEW | 100 | 100% Physical | 82 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 14/08/2020 | 80.79 | 80.79
161 | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10695) | SM/10695 | 138.07 | 136 | NEW | 100 | 100% Physical | 81 | 12/05/2022 |  | 12/06/2023 | 26/05/2022 | 111.81 | 111.81
162 | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG (SM/11342) | SM/11342 | 100.52 | 65 | NEW | 100 | 100% Physical | 84 | 13/06/2022 | 13/12/2023 | 15/09/2023 | 30/06/2022 | 84.53 | 84.53
163 | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON (SM/09613) | SM/09613 | 110.68 | 88 | NEW | 100 | 100% Physical | 74 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 28/02/2022 | 81.5 | 81.5
164 | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme (SM/08693) | SM/08693 | 99.42 | 1000 | RETROFITTING | 100 | 100% Physical | 99 | 01/09/2021 |  | 12/06/2023 | 06/09/2021 | 98.58 | 98.58
165 | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON (SM/10746) | SM/10746 | 194.83 | 205 | NEW | 100 | 100% Physical | 97 | 19/05/2022 |  | 12/06/2023 | 25/05/2022 | 189.16 | 189.16
166 | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME (SM/10696) | SM/10696 | 115.09 | 135 | NEW | 100 | 100% Physical | 70 | 12/05/2022 |  | 12/06/2023 | 25/05/2022 | 80.87 | 67.51
167 | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK (SM/10747) | SM/10747 | 72.57 | 135 | NEW | 100 | 100% Physical | 86 | 19/05/2022 |  | 12/06/2023 | 30/06/2022 | 62.34 | 62.34
168 | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY (SM/10752) | SM/10752 | 75.91 | 72 | NEW | 100 | 100% Physical | 83 | 19/05/2022 |  | 12/06/2023 | 25/05/2022 | 62.73 | 62.73
169 | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON (SM/09615) | SM/09615 | 118.44 | 55 | NEW | 100 | 100% Physical | 100 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 118.44 | 118.44
170 | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA (SM/09670) | SM/09670 | 122.05 | 65 | NEW | 100 | 100% Physical | 88 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 14/08/2020 | 106.91 | 106.91
171 | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE (SM/09603) | SM/09603 | 258.69 | 120 | NEW | 100 | 100% Physical | 84 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 218.44 | 213.44
172 | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA (SM/09616) | SM/09616 | 143.99 | 50 | NEW | 100 | 100% Physical | 86 | 24/11/2021 | 31/12/2022 | 15/09/2023 | 24/06/2020 | 123.51 | 123.51
173 | PWS SCHEME FROM MAWATAR TO UPPER DABLING (SM/09546) | SM/09546 | 192.44 | 50 | NEW | 100 | 100% Physical | 97 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 07/01/2022 | 186.34 | 186.34
174 | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10599) | SM/10599 | 67.06 | 28 | NEW | 100 | 100% Physical | 79 | 18/04/2022 | 31/03/2024 | 01/08/2023 | 26/05/2022 | 52.65 | 52.65
175 | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN (SM/10745) | SM/10745 | 91.35 | 90 | NEW | 100 | 100% Physical | 82 | 19/05/2022 | 15/12/2023 | 29/01/2024 | 26/05/2022 | 74.93 | 74.93
176 | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT (SM/12180) | SM/12180 | 520.75 | 295 | NEW | 100 | 100% Physical | 64 | 07/09/2022 | 07/03/2024 | 15/09/2023 | 18/10/2022 | 334.77 | 334.77
177 | PWS SCHEME FROM DEORALI KHOLA TO PAKANG (SM/11341) | SM/11341 | 117.19 | 150 | NEW | 100 | 100% Physical | 77 | 13/06/2022 | 13/12/2023 | 15/09/2023 | 30/06/2022 | 89.7 | 89.7
178 | PWS SCHEME FROM UNEAK KHOLA TO DABLING (SM/09595) | SM/09595 | 126.98 | 95 | NEW | 100 | 100% Physical | 97 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 123.28 | 123.18
179 | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY (SM/09614) | SM/09614 | 88.27 | 61 | NEW | 100 | 100% Physical | 78 | 24/11/2021 | 15/03/2024 | 27/02/2024 | 24/06/2020 | 68.87 | 68.87
180 | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA (SM/09605) | SM/09605 | 164.46 | 220 | NEW | 100 | 100% Physical | 80 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 131.87 | 131.87
181 | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. (SM/10729) | SM/10729 | 136.35 | 197 | NEW | 100 | 100% Physical | 65 | 18/05/2022 |  | 12/06/2023 | 26/05/2022 | 89.26 | 89.2
182 | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10739) | SM/10739 | 5.37 | 7 | NEW | 100 | 100% Physical | 89 | 20/05/2022 |  | 12/06/2023 | 26/05/2022 | 4.77 | 4.77
183 | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK (SM/12181) | SM/12181 | 695.67 | 514 | NEW | 100 | 100% Physical | 51 | 07/09/2022 | 07/03/2024 | 15/09/2023 | 03/11/2022 | 355.77 | 251.17
184 | Creating gravity based provision of drinking water from spring water source for 48 Nos of Aganwadi under Gorubathan Block, in the District of Kalimpong under Neorakhola water supply Division, kalimpong PHE Directorate. (SM/11363) | SM/11363 | 241.95 | 0 | ANGANWADI | 100 | 100% Physical | 0 | 28/06/2022 |  | 06/07/2023 | 12/07/2022 | 0 | 0
185 | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI (SM/09664) | SM/09664 | 137.62 | 60 | NEW | 100 | 100% Physical | 90 | 24/11/2021 | 31/12/2022 | 12/06/2023 | 07/01/2022 | 124.19 | 124.17
186 | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE (SM/09606) | SM/09606 | 198.35 | 230 | NEW | 100 | 100% Physical | 89 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 14/08/2020 | 176.2 | 176.2
187 | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. (SM/09544) | SM/09544 | 198.74 | 147 | NEW | 100 | 100% Physical | 94 | 19/11/2021 | 31/12/2022 | 12/06/2023 | 14/01/2022 | 186.54 | 186.45
188 | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP (SM/09667) | SM/09667 | 476.5 | 350 | NEW | 100 | 100% Physical | 97 | 23/11/2021 | 31/12/2022 | 12/06/2023 | 24/06/2020 | 462.62 | 462.62
189 | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. (SM/10602) | SM/10602 | 25.25 | 27 | NEW | 100 | 100% Physical | 40 | 18/04/2022 |  | 12/06/2023 | 26/05/2022 | 10.13 | 10.13
190 | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. (SM/10600) | SM/10600 | 10.62 | 13 | NEW | 100 | 100% Physical | 0 | 18/04/2022 |  | 12/06/2023 | 26/05/2022 | 0 | 0
Total |  |  | 75486 | 67087 | [8 empty] | 21729.21 | 19422.33