## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | KHAS JANGAL AND ADJOINING MOUJAS PWSS (SM/12439) | SM/12439 | 408.33 | 617 | NEW | 0 | WO no issued | 0 | 13/09/2022 | 13/03/2024 | 12/06/2023 | 26/05/2023 | 0 | 0
2 | PINDRAKULI AND ADJOINING MOUJAS PWSS (SM/12450) | SM/12450 | 376.23 | 871 | NEW | 0 | WO no issued | 0 | 13/09/2022 | 13/03/2024 | 12/06/2023 | 26/05/2023 | 0 | 0
3 | Providing solarization of WBSEDCL energised pumping installation at Netai w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16684) | SM/16684 | 5.17 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
4 | Providing solarization of WBSEDCL energised pumping installation at Noagoan w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16918) | SM/16918 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
5 | Providing solarization of WBSEDCL energised pumping installation at Jakua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16925) | SM/16925 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
6 | Providing solarization of WBSEDCL energised pumping installation at Shaluka And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16699) | SM/16699 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
7 | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS (SM/16675) | SM/16675 | 652.47 | 1017 | NEW | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2024 | 12/06/2023 | 02/08/2023 | 0 | 0
8 | providing solarization of WBSEDCL energised pumping installation at Balishira And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram (SM/16709) | SM/16709 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
9 | Providing solarization of WBSEDCL energised pumping installation at Amlachati w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17042) | SM/17042 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
10 | Providing solarization of WBSEDCL energised pumping installation at Chorchita piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18035) | SM/18035 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
11 | Providing solarization of WBSEDCL energised pumping installation at Barasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18006) | SM/18006 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
12 | Providing solarization of WBSEDCL energised pumping installation at Petbindhi And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17967) | SM/17967 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
13 | providing solarization of WBSEDCL energised pumping installation at Darukuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18121) | SM/18121 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
14 | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17077) | SM/17077 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
15 | Providing solarization of WBSEDCL energised pumping installation at TENTULIA AND ADJOINING MOUJAS Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17082) | SM/17082 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
16 | Providing solarization of WBSEDCL energised pumping installation at PARIHATI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17650) | SM/17650 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 22/03/2023 | 22/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
17 | Providing solarization of WBSEDCL energised pumping installation at Bhaman Sankrail w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16920) | SM/16920 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
18 | Providing solarization of WBSEDCL energised pumping installation at Metial w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17117) | SM/17117 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
19 | Providing solarization of WBSEDCL energised pumping installation at Murakati And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17119) | SM/17119 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
20 | Providing solarization of WBSEDCL energised pumping installation at DOMAHANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17078) | SM/17078 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
21 | Providing solarization of WBSEDCL energised pumping installation at Rajband w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17079) | SM/17079 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
22 | Providing solarization of WBSEDCL energised pumping installation at Bhila w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18000) | SM/18000 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
23 | Providing solarization of WBSEDCL energised pumping installation at Dalkati w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17058) | SM/17058 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
24 | Providing solarization of WBSEDCL energised pumping installation at Burimol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17071) | SM/17071 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
25 | Providing solarization of WBSEDCL energised pumping installation at JIRAPARA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17080) | SM/17080 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
26 | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS (SM/18604) | SM/18604 | 1025.14 | 1843 | NEW | 0 | WO no issued | 0 | 31/07/2023 | 31/07/2025 | 04/08/2023 | 10/08/2023 | 0 | 0
27 | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. (SM/10353) | SM/10353 | 425.01 | 0 | ANGANWADI | 0 | WO no issued | 0 | 16/03/2022 | 30/06/2023 | 05/05/2023 | 23/11/2022 | 0 | 0
28 | BAGMURI AND ADJOINING MOUJAS PWSS (SM/12523) | SM/12523 | 389.63 | 992 | NEW | 0 | WO no issued | 0 | 13/09/2022 | 13/03/2024 | 12/06/2023 | 26/05/2023 | 0 | 0
29 | Providing solarization of WBSEDCL energised pumping installation at Dumri-Nakrasuli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16919) | SM/16919 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
30 | Providing solarization of WBSEDCL energised pumping installation at Karkatasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16924) | SM/16924 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
31 | Providing solarization of WBSEDCL energised pumping installation at TILABANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16704) | SM/16704 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
32 | Providing solarization of WBSEDCL energised pumping installation at Sijua And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16708) | SM/16708 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
33 | Providing solarization of WBSEDCL energised pumping installation at Ghora Pincha w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18024) | SM/18024 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
34 | providing solarization of WBSEDCL energised pumping installation at Gramohan w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17116) | SM/17116 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
35 | Providing solarization of WBSEDCL energised pumping installation at Rautarapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17121) | SM/17121 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
36 | Providing solarization of WBSEDCL energised pumping installation at Pithapura And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18026) | SM/18026 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
37 | providing solarization of WBSEDCL energised pumping installation at Shona Konia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17962) | SM/17962 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
38 | Providing solarization of WBSEDCL energised pumping installation at Dudkundi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17114) | SM/17114 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
39 | Providing solarization of WBSEDCL energised pumping installation at Bhalukasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18015) | SM/18015 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
40 | Providing solarization of WBSEDCL energised pumping installation at Chhahazari humtia w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17982) | SM/17982 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
41 | providing solarization of WBSEDCL energised pumping installation at PALASHBANI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17124) | SM/17124 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
42 | Providing solarization of WBSEDCL energised pumping installation at Simli w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17050) | SM/17050 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
43 | Providing solarization of WBSEDCL energised pumping installation at Khas Jangal w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17054) | SM/17054 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
44 | Providing solarization of WBSEDCL energised pumping installation at KAPGARI AND IT'S ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17056) | SM/17056 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
45 | RAJABASA AND ADJOINING MOUJAS PWSS (SM/14184) | SM/14184 | 1292.08 | 3502 | NEW | 0 | WO no issued | 0 | 02/01/2023 | 02/01/2025 | 12/06/2023 | 26/05/2023 | 0 | 0
46 | Providing solarization of WBSEDCL energised pumping installation at Satkuli Charar w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16917) | SM/16917 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
47 | Providing solarization of WBSEDCL energised pumping installation at RAGHUNATHPUR AND ADJOING MOUJUAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16692) | SM/16692 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
48 | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16707) | SM/16707 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
49 | providing solarization of WBSEDCL energised pumping installation at PARSHULI AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17125) | SM/17125 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
50 | Providing solarization of WBSEDCL energised pumping installation at Gohalmara And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17968) | SM/17968 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
51 | Providing solarization of WBSEDCL energised pumping installation at Chingra And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18031) | SM/18031 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
52 | Providing solarization of WBSEDCL energised pumping installation at Tentulia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18033) | SM/18033 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
53 | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS (SM/17930) | SM/17930 | 730.76 | 1639 | NEW | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2024 | 12/06/2023 | 14/08/2023 | 1.89 | 1.89
54 | Providing solarization of WBSEDCL energised pumping installation at Dahatmal w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17051) | SM/17051 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
55 | Providing solarization of WBSEDCL energised pumping installation at Sushni And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17081) | SM/17081 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
56 | Providing Solarization of WBSEDCL energised pumping installation at Beliabera and its adjacent w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18734) | SM/18734 | 127.07 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/08/2023 | 14/02/2024 | 14/08/2023 | 20/09/2023 | 0 | 0
57 | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10489) | SM/10489 | 81.98 | 45 | AUGMENTATION | 0 | WO no issued | 14 | 13/04/2022 | 13/10/2022 | 12/06/2023 | 26/11/2020 | 11.53 | 11.53
58 | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. (SM/12326) | SM/12326 | 469.77 | 1110 | NEW | 0 | WO no issued | 0 | 09/09/2022 | 09/03/2024 | 12/06/2023 | 26/05/2023 | 0 | 0
59 | Providing solarization of WBSEDCL energised pumping installation at HARDA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16686) | SM/16686 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
60 | Providing solarization of WBSEDCL energised pumping installation at NEPURA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16689) | SM/16689 | 46.57 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
61 | Providing Solarization of WBSEDCL energised pumping installation at Chatinasole w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram (SM/16678) | SM/16678 | 5.17 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
62 | Providing solarization of WBSEDCL energised pumping installation at Junsola And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18022) | SM/18022 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
63 | Providing solarization of WBSEDCL energised pumping installation at Murabani w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17118) | SM/17118 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
64 | Providing solarization of WBSEDCL energised pumping installation at Radhanagar w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17122) | SM/17122 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
65 | Providing solarization of WBSEDCL energised pumping installation at Kankridahi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18003) | SM/18003 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
66 | Providing solarization of WBSEDCL energised pumping installation at Tiakitpur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17978) | SM/17978 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
67 | Providing solarization of WBSEDCL energised pumping installation at Chakkua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17048) | SM/17048 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
68 | Providing solarization of WBSEDCL energised pumping installation at CHANDABILA AND ADJOINING MOPUJAS Pwss under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17066) | SM/17066 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
69 | Providing solarization of WBSEDCL energised pumping installation at UTTAR BARASHOL AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17073) | SM/17073 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
70 | Providing solarization of WBSEDCL energised pumping installation at Noharia And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17012) | SM/17012 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
71 | RAJBAND AND ADJOINING MOUJAS PWSS (SM/12842) | SM/12842 | 344.49 | 786 | NEW | 0 | WO no issued | 0 | 22/09/2022 | 22/03/2024 | 12/06/2023 | 30/09/2023 | 0 | 0
72 | Providing solarization of WBSEDCL energised pumping installation at Gobindapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16926) | SM/16926 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
73 | Providing solarization of WBSEDCL energised pumping installation at BANDARBANI AND ADJONING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16691) | SM/16691 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
74 | Providing Solarization of WBSEDCL energised pumping installation at Chichira w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram (SM/16677) | SM/16677 | 5.17 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
75 | Providing solarization of WBSEDCL energised pumping installation at Simladanga And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16710) | SM/16710 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
76 | providing solarization of WBSEDCL energised pumping installation at Kendana And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17971) | SM/17971 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
77 | Providing solarization of WBSEDCL energised pumping installation at Mahapal And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18034) | SM/18034 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
78 | Providing solarization of WBSEDCL energised pumping installation at Barabari w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17044) | SM/17044 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
79 | Providing solarization of WBSEDCL energised pumping installation at Ramchandrapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17068) | SM/17068 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
80 | Providing solarization of WBSEDCL energised pumping installation at Brahmandana w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17064) | SM/17064 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
81 | DARUKULI AND ADJOINING MOUJAS PWSS (SM/12358) | SM/12358 | 417.84 | 869 | NEW | 0 | WO no issued | 0 | 12/09/2022 | 12/03/2024 | 12/06/2023 | 03/08/2023 | 0 | 0
82 | providing solarization of WBSEDCL energised pumping installation at Chandri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17011) | SM/17011 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
83 | SUSHNI AND ADJOINING MOUJAS PWSS (SM/12389) | SM/12389 | 605.9 | 1536 | NEW | 0 | WO no issued | 1 | 13/09/2022 | 31/12/2024 | 12/06/2023 | 21/09/2023 | 3.04 | 3.04
84 | Providing solarization of WBSEDCL energised pumping installation at Sonarimara w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16685) | SM/16685 | 5.17 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
85 | Providing solarization of WBSEDCL energised pumping installation at Rampura w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16923) | SM/16923 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
86 | Providing solarization of WBSEDCL energised pumping installation at JANGALKHAS AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16688) | SM/16688 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
87 | Providing solarization of WBSEDCL energised pumping installation at ANKRO AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16690) | SM/16690 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
88 | Providing solarization of WBSEDCL energised pumping installation at THAKURPARA AND ADJOINING MOUJA piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16693) | SM/16693 | 37.26 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
89 | Providing solarization of WBSEDCL energised pumping installation at Champasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17115) | SM/17115 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
90 | Providing solarization of WBSEDCL energised pumping installation at Uransaol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17127) | SM/17127 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
91 | providing solarization of WBSEDCL energised pumping installation at Bagmuri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17041) | SM/17041 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
92 | providing solarization of WBSEDCL energised pumping installation at Mahulbani w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17981) | SM/17981 | 27.94 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
93 | Providing solarization of WBSEDCL energised pumping installation at Upar Baghuasol w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18011) | SM/18011 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
94 | Providing solarization of WBSEDCL energised pumping installation at KHAMARPARA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17053) | SM/17053 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
95 | providing solarization of WBSEDCL energised pumping installation at Mahisamura & Adjoining Moujas Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17060) | SM/17060 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
96 | Providing solarization of WBSEDCL energised pumping installation at Chenchur gerya w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17062) | SM/17062 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
97 | Providing solarization of WBSEDCL energised pumping installation at Haripurbirua w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16922) | SM/16922 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
98 | Providing solarization of WBSEDCL energised pumping installation at GOBINDAPUR AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16687) | SM/16687 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
99 | Providing solarization of WBSEDCL energised pumping installation at Dahamunda w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16679) | SM/16679 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
100 | Providing solarization of WBSEDCL energised pumping installation at Bankati And It'S Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16703) | SM/16703 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
101 | Providing solarization of WBSEDCL energised pumping installation at Patharnala w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17126) | SM/17126 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
102 | Providing solarization of WBSEDCL energised pumping installation at Sumitrapur w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18025) | SM/18025 | 18.63 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
103 | Providing solarization of WBSEDCL energised pumping installation at Gobindapur And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/18030) | SM/18030 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 17/03/2023 | 17/09/2023 | 12/06/2023 | 05/09/2023 | 0 | 0
104 | Providing solarization of WBSEDCL energised pumping installation at Mantipa w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17059) | SM/17059 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 29/08/2023 | 0 | 0
105 | Providing solarization of WBSEDCL energised pumping installation at BELDA AND ADJOINING MOUJAS Piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17083) | SM/17083 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
106 | providing solarization of WBSEDCL energised pumping installation at Bhaudi w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17052) | SM/17052 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
107 | Providing solarization of WBSEDCL energised pumping installation at Panchami w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17057) | SM/17057 | 10.33 | 0 | SOLARISATION | 0 | WO no issued | 0 | 16/03/2023 | 16/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
108 | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission (SM/18228) | SM/18228 | 78.13 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 15/03/2023 |  | 17/05/2023 |  | 0 | 0
109 | Operation charges of PHED & NGO managed Laboratories Related to Water Quality Monitoring & Surveillance under JJM (SM/16656) | SM/16656 | 23.51 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 14/03/2023 |  | 20/03/2023 |  | 0 | 0
110 | Design Development and Installation of web and mobile application based Monitoring system for Duel use Solar PWSS at different pin point location district Jhargram (SM/08059) | SM/08059 | 64.56 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 01/02/2021 |  | 30/06/2022 |  | 0 | 0
111 | Supply, Supply, Delivery and Installation of Computer, Printer, Projector, Copier, UPS, Furniture etc. through GeM portal For Office of the Executive Engineer under Jhargram Division, PHE Dte. (SM/16630) | SM/16630 | 75.66 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 14/03/2023 |  | 20/03/2023 |  | 0 | 0
112 | Supply, delivery of Computer and other allied accessories (through GeM portal) for Office of the Executive Engineer, Jhargram Mechanical Division, PHE Dte. in the district of Jhargram (SM/18717) | SM/18717 | 11.29 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | WO no issued | 0 | 10/08/2023 |  | 10/08/2023 |  | 0 | 0
113 | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. (SM/16680) | SM/16680 | 92.17 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 14/03/2023 |  | 20/03/2023 | 31/10/2023 | 0 | 0
114 | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. (SM/12324) | SM/12324 | 464.32 | 1053 | NEW | 1 | WO no issued | 40 | 09/09/2022 | 31/12/2024 | 26/01/2024 | 30/09/2023 | 185.87 | 185.87
115 | BANKSOL AND ADJOINING MOUJAS PWSS (SM/17931) | SM/17931 | 480.2 | 1008 | NEW | 1 | WO no issued | 5 | 17/03/2023 | 01/01/2025 | 11/04/2024 | 12/09/2023 | 24.68 | 24.68
116 | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. (SM/18435) | SM/18435 | 2052.61 | 0 | AUGMENTATION | 1 | WO no issued | 1 | 18/07/2023 | 31/12/2024 | 11/04/2024 | 21/07/2023 | 22.64 | 22.64
117 | KAPGARI AND IT'S ADJOINING MOUJAS PWSS (SM/12454) | SM/12454 | 387.68 | 935 | NEW | 2 | WO no issued | 1 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 21/09/2023 | 2.99 | 2.99
118 | BHATAN DIA AND ADJOINING MOUJAS PWSS (SM/17582) | SM/17582 | 374.62 | 1164 | NEW | 2 | WO no issued | 0 | 18/03/2023 | 01/02/2025 | 11/04/2024 | 30/09/2023 | 0 | 0
119 | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS (SM/17584) | SM/17584 | 513.68 | 1908 | NEW | 2 | WO no issued | 0 | 18/03/2023 | 01/01/2025 | 11/04/2024 | 30/09/2023 | 0 | 0
120 | JIRAPARA AND ADJOINING MOUJAS PWSS (SM/12533) | SM/12533 | 677.48 | 1616 | NEW | 2 | WO no issued | 4 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 09/08/2023 | 28.39 | 28.39
121 | AMARDA AND ADJOINING MOUJAS PWSS (SM/17586) | SM/17586 | 519.04 | 1630 | NEW | 2 | WO no issued | 0 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 0 | 0
122 | JUNSOLA AND ADJOINING MOUJAS PWSS (SM/12342) | SM/12342 | 311.62 | 592 | NEW | 2 | WO no issued | 1 | 12/09/2022 | 30/01/2024 | 08/09/2023 | 26/05/2023 | 3.65 | 3.65
123 | Providing solarization of WBSEDCL energised pumping installation at BAHIR GRAM AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17069) | SM/17069 | 27.94 | 0 | SOLARISATION | 2 | WO no issued | 0 | 16/03/2023 | 31/12/2024 | 28/03/2024 | 05/09/2023 | 0 | 0
124 | DHADANGIRI AND ADJOINING MOUJAS (SM/16992) | SM/16992 | 611.94 | 1997 | NEW | 2 | WO no issued | 3 | 16/03/2023 | 01/02/2025 | 09/05/2024 | 16/08/2023 | 16.17 | 12.3
125 | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS (SM/16993) | SM/16993 | 885.79 | 1504 | NEW | 2 | WO no issued | 1 | 16/03/2023 | 01/02/2025 | 11/04/2024 | 10/08/2023 | 9.26 | 9.26
126 | Providing solarization of WBSEDCL energised pumping installation at BELIA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/17076) | SM/17076 | 27.94 | 0 | SOLARISATION | 2 | WO no issued | 0 | 16/03/2023 | 31/12/2024 | 28/03/2024 | 05/09/2023 | 0 | 0
127 | MAHULBANI AND ADJOINING MOUJAS PWSS (SM/12534) | SM/12534 | 613.77 | 1020 | NEW | 3 | WO no issued | 23 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 138.27 | 127.52
128 | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS (SM/16994) | SM/16994 | 540.88 | 1645 | NEW | 3 | WO no issued | 6 | 16/03/2023 | 01/02/2025 | 11/04/2024 | 10/08/2023 | 34.9 | 34.9
129 | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram (SM/12386) | SM/12386 | 311.48 | 891 | NEW | 3 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 5.48 | 5.48
130 | KALADABAR AND ADJOINING MOUJAS PWSS (SM/17597) | SM/17597 | 380.65 | 505 | NEW | 4 | WO no issued | 2 | 18/03/2023 | 30/11/2024 | 11/04/2024 | 19/09/2023 | 6.17 | 6.17
131 | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS (SM/17929) | SM/17929 | 522.47 | 1420 | NEW | 4 | WO no issued | 30 | 17/03/2023 | 31/12/2024 | 11/04/2024 | 18/05/2023 | 158.54 | 158.54
132 | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. (SM/12327) | SM/12327 | 455.43 | 1451 | NEW | 5 | WO no issued | 16 | 09/09/2022 | 31/12/2024 | 09/04/2024 | 26/05/2023 | 73.12 | 73.12
133 | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. (SM/08081) | SM/08081 | 3498 | 36 | NEW | 5 | WO no issued | 3 | 04/02/2021 | 07/06/2024 | 25/04/2024 | 13/01/2022 | 103.49 | 103.49
134 | BAHIR GRAM AND ADJOINING MOUJAS PWSS (SM/12441) | SM/12441 | 563.95 | 1204 | NEW | 5 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 21/09/2023 | 10.73 | 10.73
135 | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. (SM/12328) | SM/12328 | 562.67 | 1663 | NEW | 5 | WO no issued | 2 | 09/09/2022 | 31/12/2024 | 25/04/2024 | 30/09/2023 | 9.1 | 9.1
136 | BHAMAL AND ADOINING MOUJAS PWSS (SM/17417) | SM/17417 | 313.06 | 1300 | NEW | 5 | WO no issued | 3 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 9.07 | 9.07
137 | PETBINDHI AND ADJOINING MOUJAS PWSS (SM/12354) | SM/12354 | 522.37 | 1862 | NEW | 5 | WO no issued | 9 | 12/09/2022 | 31/12/2025 | 03/05/2024 | 26/05/2023 | 44.5 | 36.24
138 | PARIHATI AND ADJOINING MOUJAS PWSS (SM/12455) | SM/12455 | 487.27 | 1365 | NEW | 5 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/07/2023 | 11.66 | 11.66
139 | MURAKATI AND ADJOINING MOUJAS PWSS (SM/12339) | SM/12339 | 411.75 | 1111 | NEW | 5 | WO no issued | 2 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 21/09/2023 | 7.68 | 7.68
140 | NOHARIA AND ADJOINING MOUJAS (SM/12885) | SM/12885 | 433.66 | 1592 | NEW | 5 | WO no issued | 3 | 23/09/2022 | 31/12/2024 | 21/02/2024 | 21/09/2023 | 13.83 | 13.83
141 | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS (SM/12845) | SM/12845 | 508.1 | 1075 | NEW | 5 | WO no issued | 11 | 22/09/2022 | 22/03/2025 | 04/04/2024 | 30/09/2023 | 57.72 | 47.96
142 | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS (SM/16934) | SM/16934 | 661.95 | 1389 | NEW | 7 | WO no issued | 5 | 16/03/2023 | 31/12/2024 | 11/04/2024 | 26/07/2023 | 30.82 | 30.82
143 | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS (SM/16982) | SM/16982 | 362.71 | 905 | NEW | 7 | WO no issued | 2 | 16/03/2023 | 31/12/2024 | 11/04/2024 | 26/07/2023 | 5.57 | 5.57
144 | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS (SM/12532) | SM/12532 | 338.87 | 751 | NEW | 7 | WO no issued | 0 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 0 | 0
145 | TIAKITPUR ANAD AJOINING MOUJAS PWSS (SM/12349) | SM/12349 | 415.83 | 1683 | NEW | 7 | WO no issued | 17 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 70.05 | 2.88
146 | TENTULIA AND ADJOINING MOUJAS PWSS (SM/12449) | SM/12449 | 416.02 | 963 | NEW | 9 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/07/2023 | 9.23 | 9.23
147 | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS (SM/12448) | SM/12448 | 421.06 | 1264 | NEW | 9 | WO no issued | 1 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 4.24 | 4.24
148 | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS (SM/12723) | SM/12723 | 601.69 | 1326 | NEW | 9 | WO no issued | 2 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 13.2 | 13.2
149 | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. (SM/12332) | SM/12332 | 397.66 | 1020 | NEW | 9 | WO no issued | 0 | 09/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 0 | 0
150 | BARBARIA AND ITS ADJOINING MOUJAS PWSS (SM/14133) | SM/14133 | 1067.06 | 3050 | NEW | 9 | WO no issued | 34 | 02/01/2023 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 362.02 | 176.24
151 | BURIJHOR AND ADJOINING MOUJAS PWSS (SM/17928) | SM/17928 | 472.21 | 681 | NEW | 9 | WO no issued | 5 | 17/03/2023 | 31/10/2024 | 11/04/2024 | 29/09/2023 | 22.85 | 7.79
152 | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. (SM/09378) | SM/09378 | 134.9 | 390 | AUGMENTATION | 9 | WO no issued | 9 | 12/11/2021 | 31/12/2024 | 24/04/2024 | 01/02/2022 | 11.49 | 7.99
153 | CHAKKUA AND ADJOINING MOUJAS PWSS (SM/12356) | SM/12356 | 451.72 | 861 | NEW | 9 | WO no issued | 40 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 181.44 | 181.44
154 | Water Supply System at Anganwadi Centers(174 nos.) within Sankrail Block under Jhargram District. (SM/10350) | SM/10350 | 413.04 | 0 | ANGANWADI | 10 | WO no issued | 0 | 16/03/2022 | 08/02/2024 | 24/11/2023 | 07/02/2023 | 0 | 0
155 | Providing solarization of WBSEDCL energised pumping installation at Bakra w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16921) | SM/16921 | 18.63 | 0 | SOLARISATION | 10 | WO no issued | 0 | 13/03/2023 | 13/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
156 | Water Supply System at Anganwadi Centers (137 nos.) within Gopiballavpur-II Block under Jhargram District. (SM/10352) | SM/10352 | 192.67 | 0 | ANGANWADI | 10 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 17/10/2023 | 04/11/2022 | 0 | 0
157 | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. (SM/10358) | SM/10358 | 198.43 | 0 | SCHOOL | 10 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 22/08/2023 | 12/09/2022 | 0 | 0
158 | Water Supply System at Anganwadi Centers(306 nos) within Binpur-II Block under Jhargram District. (SM/10356) | SM/10356 | 436.93 | 0 | ANGANWADI | 10 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 08/09/2023 | 28/09/2022 | 0 | 0
159 | Water Supply System at Anganwadi Centers(220 nos.) within Gopiballavpur-I Block under Jhargram District. (SM/10351) | SM/10351 | 561.16 | 0 | ANGANWADI | 11 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 04/09/2023 | 02/05/2023 | 0 | 0
160 | RAMPURA AND ADJOINING MOUJAS (SM/12880) | SM/12880 | 406.33 | 1248 | NEW | 11 | WO no issued | 14 | 23/09/2022 | 31/12/2024 | 13/05/2024 | 04/05/2023 | 55.64 | 45.47
161 | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS (SM/17924) | SM/17924 | 522.61 | 978 | NEW | 12 | WO no issued | 10 | 17/03/2023 | 31/12/2024 | 11/04/2024 | 06/06/2023 | 50 | 48.96
162 | SHIYARBINDA AND ADJOINING MOUJAS PWSS (SM/17591) | SM/17591 | 432.68 | 636 | NEW | 13 | WO no issued | 7 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 06/09/2023 | 31.59 | 8.68
163 | Rejuvenation (Phase-II) of Ground Water Based Netai PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18007) | SM/18007 | 115.77 | 10 | AUGMENTATION | 13 | WO no issued | 18 | 17/03/2023 | 31/12/2024 | 11/04/2024 | 03/08/2023 | 21.33 | 21.33
164 | BHALUKASOL AND ADJOINING MOUJAS PWSS (SM/12391) | SM/12391 | 613.27 | 1260 | NEW | 14 | WO no issued | 31 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 192.19 | 25.95
165 | ANKRO AND ADJOINING MOUJAS PWSS (SM/12447) | SM/12447 | 599.18 | 1175 | NEW | 14 | WO no issued | 4 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 23.53 | 23.53
166 | SIMLADANGA AND ADJOINING MOUJAS PWSS (SM/12343) | SM/12343 | 830.61 | 1993 | NEW | 14 | WO no issued | 2 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 12.58 | 12.58
167 | MAHISAMURA & ADJOINING MOUJAS PWSS (SM/12521) | SM/12521 | 396.51 | 1012 | NEW | 15 | WO no issued | 5 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 21/09/2023 | 20.78 | 20.78
168 | HIJLA AND ADJOINING MOUJAS PWSS (SM/17594) | SM/17594 | 463.44 | 1257 | NEW | 15 | WO no issued | 5 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 01/09/2023 | 25.34 | 24.37
169 | CHAKADOBA AND ADJOINING MOUJAS PWSS (SM/17596) | SM/17596 | 589.96 | 1434 | NEW | 17 | WO no issued | 5 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 19/09/2023 | 28.2 | 28.2
170 | GIDIGHATI AND ADJOINING MOUJAS PWSS (SM/17926) | SM/17926 | 436.42 | 694 | NEW | 17 | WO no issued | 7 | 17/03/2023 | 01/12/2024 | 11/04/2024 | 06/09/2023 | 32.42 | 9.89
171 | Chingra And Adjoining Moujas PWSS (SM/12385) | SM/12385 | 519.22 | 1216 | NEW | 18 | WO no issued | 5 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 25.9 | 25.9
172 | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram (SM/12350) | SM/12350 | 363.72 | 1079 | NEW | 18 | WO no issued | 7 | 12/09/2022 | 31/12/2024 | 25/04/2024 | 30/09/2023 | 26.71 | 17.67
173 | DHOBA KURYA AND ADJOINING MOUJAS PWSS (SM/17570) | SM/17570 | 380.58 | 819 | NEW | 18 | WO no issued | 23 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 20/07/2023 | 87.77 | 87.77
174 | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS (SM/18746) | SM/18746 | 789.66 | 2017 | NEW | 18 | WO no issued | 8 | 17/08/2023 | 31/12/2024 | 11/04/2024 | 18/08/2023 | 61.01 | 60.08
175 | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. (SM/17039) | SM/17039 | 539.48 | 895 | NEW | 18 | WO no issued | 9 | 16/03/2023 | 30/11/2024 | 11/04/2024 | 15/09/2023 | 46.53 | 43.67
176 | PITHAPURA AND ADJOINING MOUJAS PWSS (SM/12355) | SM/12355 | 323.12 | 927 | NEW | 18 | WO no issued | 9 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 30/08/2023 | 29.19 | 20.97
177 | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS (SM/17925) | SM/17925 | 639.18 | 1663 | NEW | 19 | WO no issued | 19 | 17/03/2023 | 31/12/2024 | 11/04/2024 | 06/06/2023 | 123.24 | 116.94
178 | BALISHIRA AND ADJOINING MOUJAS PWSS (SM/12388) | SM/12388 | 534.67 | 1736 | NEW | 19 | WO no issued | 6 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 30.66 | 30.66
179 | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS (SM/17932) | SM/17932 | 497.89 | 874 | NEW | 19 | WO no issued | 11 | 17/03/2023 | 31/08/2024 | 11/04/2024 | 06/09/2023 | 53.82 | 19.1
180 | KHARIYARATA AND ADJOINING MOUJAS PWSS (SM/17592) | SM/17592 | 443.46 | 713 | NEW | 19 | WO no issued | 2 | 18/03/2023 | 31/10/2024 | 11/04/2024 | 19/09/2023 | 8.93 | 8.93
181 | BHAUDI AND ADJOINING MOUJAS PWSS (SM/12353) | SM/12353 | 484.38 | 1365 | NEW | 19 | WO no issued | 2 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 7.55 | 7.55
182 | CHAMPASOL AND ADJOINING MOUJAS PWSS (SM/12387) | SM/12387 | 504.16 | 1160 | NEW | 20 | WO no issued | 0 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 0 | 0
183 | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. (SM/10349) | SM/10349 | 816.31 | 0 | ANGANWADI | 20 | WO no issued | 0 | 16/03/2022 | 30/11/2023 | 30/06/2023 | 03/02/2023 | 0 | 0
184 | DAKAI AND ADJOINING MOUJAS PWSS (SM/17927) | SM/17927 | 456.15 | 727 | NEW | 21 | WO no issued | 3 | 17/03/2023 | 01/11/2024 | 11/04/2024 | 29/09/2023 | 11.65 | 3.3
185 | KULIANA AND ADJOINING MOUJAS PWSS (SM/17587) | SM/17587 | 310.7 | 1241 | NEW | 22 | WO no issued | 2 | 18/03/2023 | 31/12/2024 | 25/04/2024 | 30/09/2023 | 6.8 | 6.8
186 | SHONA KONIA AND ADJOINING MOUJAS PWSS (SM/12345) | SM/12345 | 292.84 | 1021 | NEW | 22 | WO no issued | 2 | 12/09/2022 | 30/06/2025 | 03/05/2024 | 30/09/2023 | 5.02 | 0
187 | GAJPATHAR AND ADJOINING MOUJAS PWSS (SM/17590) | SM/17590 | 450.65 | 841 | NEW | 23 | WO no issued | 4 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 29/09/2023 | 19.69 | 19.69
188 | MANTIPA & IT'S ADJOINING MOJAS PWSS (SM/12525) | SM/12525 | 401.24 | 622 | NEW | 23 | WO no issued | 0 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 0 | 0
189 | GOBINDAPUR AND ADJOINING MOUJAS PWSS (SM/12347) | SM/12347 | 403.45 | 1091 | NEW | 23 | WO no issued | 3 | 12/09/2022 | 31/12/2025 | 03/05/2024 | 26/05/2023 | 13.09 | 7.06
190 | METIAL AND ADJOINING MOUJAS PWSS (SM/12437) | SM/12437 | 491.35 | 1356 | NEW | 23 | WO no issued | 6 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 30.5 | 30.5
191 | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/17959) | SM/17959 | 41.56 | 194 | AUGMENTATION | 25 | WO no issued | 18 | 17/03/2023 | 30/09/2024 | 11/04/2024 | 14/07/2023 | 7.36 | 7.36
192 | BIRMADAL AND ADJOINING MOUJAS PWSS (SM/17593) | SM/17593 | 452.34 | 634 | NEW | 25 | WO no issued | 5 | 18/03/2023 | 30/11/2024 | 11/04/2024 | 29/09/2023 | 24.12 | 2.72
193 | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS (SM/17595) | SM/17595 | 437.57 | 695 | NEW | 25 | WO no issued | 6 | 18/03/2023 | 31/07/2024 | 11/04/2024 | 06/09/2023 | 27.49 | 15.81
194 | DALKATI AND ADJOINING MOUJAS PWSS (SM/12357) | SM/12357 | 416.55 | 1148 | NEW | 28 | WO no issued | 11 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 47.7 | 47.7
195 | GOBINDAPUR AND ADJOINING MOUJAS PWSS (SM/17571) | SM/17571 | 463.29 | 1343 | NEW | 28 | WO no issued | 19 | 18/03/2023 | 31/12/2025 | 25/04/2024 | 26/05/2023 | 86.46 | 86.46
196 | NEPURA AND ADJOINING MOUJAS PWSS (SM/12776) | SM/12776 | 824.12 | 1724 | NEW | 29 | WO no issued | 3 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 28.43 | 13.85
197 | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. (SM/18428) | SM/18428 | 4219.65 | 7292 | AUGMENTATION | 29 | WO no issued | 7 | 18/07/2023 | 31/12/2024 | 11/04/2024 | 31/08/2023 | 300.54 | 300.54
198 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. (SM/11475) | SM/11475 | 995 | 542 | NEW | 30 | WO no issued | 53 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 526.65 | 525.81
199 | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte (SM/17964) | SM/17964 | 188.03 | 150 | AUGMENTATION | 32 | WO no issued | 5 | 17/03/2023 | 31/10/2024 | 11/04/2024 | 08/06/2023 | 9.19 | 9.19
200 | BRAHMANDANA AND ADJOINING MOUJAS PWSS (SM/12392) | SM/12392 | 492.42 | 1459 | NEW | 32 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 10.17 | 10.17
201 | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS (SM/12445) | SM/12445 | 533.24 | 1583 | NEW | 33 | WO no issued | 26 | 13/09/2022 | 31/12/2024 | 07/05/2024 | 26/05/2023 | 140.74 | 132.03
202 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Jhargram District. (SM/08978) | SM/08978 | 175.91 | 0 | SUPPORT-M&E | 33 | WO no issued | 0 | 29/10/2021 | 18/08/2023 | 25/02/2023 | 18/08/2022 | 0 | 0
203 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. (SM/11476) | SM/11476 | 993 | 887 | NEW | 34 | WO no issued | 51 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 503.25 | 503.04
204 | DOMAHANI AND ADJOINING MOUJAS PWSS (SM/12438) | SM/12438 | 469.57 | 1160 | NEW | 37 | WO no issued | 2 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 28/09/2022 | 9.94 | 9.94
205 | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. (SM/12333) | SM/12333 | 513.84 | 1532 | NEW | 37 | WO no issued | 26 | 09/09/2022 | 30/06/2025 | 25/04/2024 | 26/05/2023 | 136.11 | 136.11
206 | SHALUKA AND ADJOINING MOUJAS PWSS (SM/12520) | SM/12520 | 316.15 | 662 | NEW | 38 | WO no issued | 9 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 27.53 | 27.53
207 | THAKURPARA AND ADJOINING MOUJAS PWSS (SM/12453) | SM/12453 | 688.86 | 2106 | NEW | 41 | WO no issued | 15 | 13/09/2022 | 30/12/2024 | 11/04/2024 | 18/07/2023 | 104.84 | 64.23
208 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. (SM/11477) | SM/11477 | 985 | 882 | NEW | 42 | WO no issued | 32 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 310.73 | 310.73
209 | CHANDRI AND ADJOINING MOUJAS PWSS (SM/12715) | SM/12715 | 545.91 | 2066 | NEW | 42 | WO no issued | 28 | 20/09/2022 | 31/12/2024 | 25/04/2024 | 26/05/2023 | 153.82 | 153.82
210 | JANGALKHAS AND ADJOINING MOUJAS PWSS (SM/12775) | SM/12775 | 665.38 | 1336 | NEW | 42 | WO no issued | 26 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 171.1 | 164.27
211 | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. (SM/12330) | SM/12330 | 478.38 | 1193 | NEW | 42 | WO no issued | 58 | 09/09/2022 | 31/12/2024 | 11/04/2024 | 20/07/2023 | 279.51 | 279.51
212 | KENDANA AND ADJOINING MOUJAS PWSS (SM/12346) | SM/12346 | 496.74 | 1308 | NEW | 43 | WO no issued | 5 | 12/09/2022 | 31/12/2024 | 03/05/2024 | 30/09/2023 | 25.07 | 10.02
213 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. (SM/11478) | SM/11478 | 982 | 1167 | NEW | 44 | WO no issued | 17 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 168.46 | 167.83
214 | BANDARBANI AND ADJONING MOUJAS PWSS (SM/12442) | SM/12442 | 648.02 | 1931 | NEW | 45 | WO no issued | 18 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 117.5 | 74.77
215 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. (SM/11480) | SM/11480 | 974 | 1218 | NEW | 46 | WO no issued | 65 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 635.71 | 635.5
216 | PATHARNALA AND ADJOINING MOUJAS PWSS (SM/12527) | SM/12527 | 568.25 | 1207 | NEW | 47 | WO no issued | 39 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 221.07 | 221.07
217 | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. (SM/12334) | SM/12334 | 717.22 | 2225 | NEW | 47 | WO no issued | 15 | 09/09/2022 | 31/12/2024 | 11/04/2024 | 04/05/2023 | 104.18 | 104.18
218 | BANKATI AND IT'S ADJOINING MOUJAS (SM/12351) | SM/12351 | 604.79 | 1278 | NEW | 47 | WO no issued | 92 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 554.78 | 544.79
219 | SUMITRAPUR AND ADJOINING MOJAS PWSS (SM/12528) | SM/12528 | 534.56 | 1725 | NEW | 47 | WO no issued | 38 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 202.33 | 202.33
220 | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10483) | SM/10483 | 29.32 | 15 | AUGMENTATION | 48 | WO no issued | 92 | 13/04/2022 | 31/12/2024 | 25/01/2024 | 25/06/2021 | 26.87 | 26.87
221 | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. (SM/18190) | SM/18190 | 46.68 | 294 | AUGMENTATION | 48 | WO no issued | 28 | 31/03/2023 | 31/07/2024 | 11/04/2024 | 14/07/2023 | 13.13 | 13.13
222 | SIJUA AND ADJOINING MOUJAS PWSS (SM/12519) | SM/12519 | 508.92 | 1135 | NEW | 48 | WO no issued | 13 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 67.42 | 46.75
223 | MURABANI AND ADJOINING MOUJAS PWSS (SM/12440) | SM/12440 | 411.12 | 1367 | NEW | 48 | WO no issued | 27 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 111.76 | 111.76
224 | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. (SM/17966) | SM/17966 | 59.97 | 25 | AUGMENTATION | 48 | WO no issued | 11 | 17/03/2023 | 31/10/2024 | 11/04/2024 | 10/08/2023 | 6.3 | 6.3
225 | RADHANAGAR AND ADJOINING MOUJAS PWSS (SM/12777) | SM/12777 | 566.07 | 1591 | NEW | 49 | WO no issued | 41 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 11/05/2023 | 234.34 | 234.34
226 | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09372) | SM/09372 | 118.7 | 26 | AUGMENTATION | 50 | WO no issued | 29 | 12/11/2021 | 31/12/2024 | 19/04/2024 | 29/08/2022 | 33.89 | 33.89
227 | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. (SM/10355) | SM/10355 | 451.57 | 0 | ANGANWADI | 50 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 27/07/2023 | 23/11/2022 | 0 | 0
228 | GHORA PINCHA AND ADJOINING MOJAS PWSS (SM/12408) | SM/12408 | 405.39 | 881 | NEW | 50 | WO no issued | 25 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 14/07/2023 | 99.99 | 99.99
229 | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS (SM/12713) | SM/12713 | 742.21 | 1927 | NEW | 51 | WO no issued | 12 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 87.5 | 58.03
230 | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. (SM/17956) | SM/17956 | 73.08 | 0 | AUGMENTATION | 51 | WO no issued | 0 | 17/03/2023 | 17/02/2024 | 26/01/2024 | 29/09/2023 | 0 | 0
231 | HARDA AND ADJOINING MOUJAS PWSS (SM/12436) | SM/12436 | 817.7 | 2827 | NEW | 51 | WO no issued | 82 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 668.77 | 653.57
232 | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/13678) | SM/13678 | 46.29 | 270 | AUGMENTATION | 52 | WO no issued | 63 | 14/11/2022 | 31/12/2024 | 11/04/2024 | 01/12/2022 | 28.96 | 28.96
233 | TILABANI AND ADJOINING MOUJAS PWSS (SM/12530) | SM/12530 | 723 | 2339 | NEW | 53 | WO no issued | 7 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 52 | 21.56
234 | HARIPURBIRUA AND AJOINING MOUJAS PWSS (SM/12409) | SM/12409 | 836.25 | 2752 | NEW | 53 | WO no issued | 59 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 491.56 | 491.56
235 | TENTULIA AND ADJOINING MOUJAS PWSS (SM/12341) | SM/12341 | 438.2 | 1398 | NEW | 53 | WO no issued | 6 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 30/09/2023 | 27.23 | 27.23
236 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. (SM/11481) | SM/11481 | 485 | 360 | NEW | 54 | WO no issued | 1 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 6.15 | 6.15
237 | GOBINDAPUR AND ADJOINING MOUJAS PWSS (SM/12724) | SM/12724 | 460.54 | 1289 | NEW | 55 | WO no issued | 12 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 18/07/2023 | 55.91 | 34.59
238 | BHILA AND ADJOINING MOUJAS PWSS (SM/12452) | SM/12452 | 488.63 | 1197 | NEW | 56 | WO no issued | 44 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 15/09/2023 | 213.74 | 213.74
239 | SAFTALDIHA AND ADJOINING MOUJAS PWSS (SM/17580) | SM/17580 | 516.78 | 1498 | NEW | 56 | WO no issued | 47 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 241.95 | 241.95
240 | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. (SM/09915) | SM/09915 | 9931.41 | 23490 | NEW | 56 | WO no issued | 54 | 10/12/2021 | 31/12/2024 | 11/04/2024 | 01/02/2022 | 5369.29 | 5274.53
241 | GOHAL BURA AND ADJOINING MOUJAS PWSS (SM/17585) | SM/17585 | 542.43 | 1718 | NEW | 56 | WO no issued | 50 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 08/06/2023 | 269.14 | 265.82
242 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. (SM/11479) | SM/11479 | 967 | 515 | NEW | 57 | WO no issued | 2 | 14/07/2022 | 31/12/2024 | 11/04/2024 | 09/03/2023 | 16.12 | 10.71
243 | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS (SM/12352) | SM/12352 | 668.4 | 2020 | NEW | 57 | WO no issued | 36 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 25/04/2023 | 238.61 | 238.61
244 | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18002) | SM/18002 | 67.65 | 50 | AUGMENTATION | 58 | WO no issued | 21 | 17/03/2023 | 31/10/2024 | 11/04/2024 | 18/07/2023 | 13.95 | 13.95
245 | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18014) | SM/18014 | 163.98 | 50 | AUGMENTATION | 58 | WO no issued | 41 | 17/03/2023 | 31/07/2024 | 11/04/2024 | 25/04/2023 | 67.34 | 67.34
246 | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS (SM/12725) | SM/12725 | 562.67 | 1400 | NEW | 58 | WO no issued | 51 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 288.44 | 288.44
247 | JAKUA AND ADJOINING MOUJAS PWSS (SM/12344) | SM/12344 | 345.73 | 764 | NEW | 58 | WO no issued | 41 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 142.48 | 142.48
248 | KHAMARPARA AND ADJOINING MOUJAS PWSS (SM/12446) | SM/12446 | 420.68 | 1200 | NEW | 59 | WO no issued | 49 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 26/07/2023 | 206.26 | 206.26
249 | ANDHARI AND ADJOINING MOUJAS PWSS (SM/16991) | SM/16991 | 334.36 | 1064 | NEW | 59 | WO no issued | 47 | 16/03/2023 | 31/12/2024 | 11/04/2024 | 25/04/2023 | 157.55 | 157.55
250 | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram (SM/17953) | SM/17953 | 576.13 | 1880 | AUGMENTATION | 59 | WO no issued | 0 | 17/03/2023 | 31/12/2024 | 11/04/2024 | 09/01/2024 | 0 | 0
251 | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. (SM/12336) | SM/12336 | 446.27 | 1416 | NEW | 60 | WO no issued | 62 | 09/09/2022 | 30/04/2025 | 11/04/2024 | 11/05/2023 | 276.93 | 259.9
252 | Providing solarization of WBSEDCL energised pumping installation at Gidhni w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram (SM/16683) | SM/16683 | 5.17 | 0 | SOLARISATION | 60 | WO no issued | 0 | 14/03/2023 | 14/09/2023 | 12/06/2023 | 25/08/2023 | 0 | 0
253 | BAKRA AND ITS ADJOINING MOUJAS PWSS (SM/12390) | SM/12390 | 637.82 | 1897 | NEW | 61 | WO no issued | 53 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 338.02 | 338.02
254 | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. (SM/12329) | SM/12329 | 487.29 | 1079 | NEW | 63 | WO no issued | 55 | 09/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 270.08 | 270.08
255 | ANANDAPUR AND ADJOINING MOUJAS PWSS (SM/17583) | SM/17583 | 373.73 | 1073 | NEW | 63 | WO no issued | 64 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 25/04/2023 | 240.56 | 240.56
256 | GOHALMARA AND ADJOINING MOUJAS PWSS (SM/12340) | SM/12340 | 442.07 | 613 | NEW | 64 | WO no issued | 36 | 12/09/2022 | 31/12/2024 | 16/04/2024 | 30/09/2023 | 157.27 | 157.27
257 | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. (SM/09881) | SM/09881 | 32.05 | 0 | AUGMENTATION | 65 | WO no issued | 34 | 08/12/2021 | 31/12/2024 | 20/03/2024 | 04/04/2022 | 10.92 | 10.73
258 | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS (SM/12524) | SM/12524 | 474.81 | 1457 | NEW | 65 | WO no issued | 71 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 335.59 | 335.59
259 | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09379) | SM/09379 | 304.18 | 1187 | AUGMENTATION | 67 | WO no issued | 59 | 12/11/2021 | 12/04/2024 | 11/04/2024 | 29/08/2022 | 178.63 | 178.61
260 | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS (SM/12359) | SM/12359 | 587.48 | 1798 | NEW | 68 | WO no issued | 55 | 12/09/2022 | 31/12/2024 | 11/04/2024 | 23/03/2023 | 321.75 | 321.75
261 | DHANSOL AND ADJOINING MOUJAS PWSS (SM/17581) | SM/17581 | 453.32 | 1361 | NEW | 69 | WO no issued | 68 | 18/03/2023 | 31/12/2024 | 11/04/2024 | 25/04/2023 | 307.83 | 307.83
262 | RAGRA AND ADJOINING MOUJAS PWSS (SM/17174) | SM/17174 | 428.5 | 1318 | NEW | 69 | WO no issued | 63 | 16/03/2023 | 31/12/2024 | 11/04/2024 | 04/05/2023 | 270.06 | 270.06
263 | Water Supply System at Anganwadi Centers(176 nos.) within Jhargram Block under Jhargram District. (SM/10354) | SM/10354 | 297.57 | 0 | ANGANWADI | 70 | WO no issued | 0 | 16/03/2022 | 31/12/2023 | 07/09/2023 | 21/10/2022 | 0 | 0
264 | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18008) | SM/18008 | 57.02 | 10 | AUGMENTATION | 70 | WO no issued | 50 | 17/03/2023 | 31/05/2024 | 11/04/2024 | 18/05/2023 | 28.32 | 28.32
265 | BELDA AND ADJOINING MOUJAS PWSS (SM/12451) | SM/12451 | 423.84 | 911 | NEW | 71 | WO no issued | 55 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 09/08/2023 | 233.93 | 172.54
266 | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. (SM/12325) | SM/12325 | 343.02 | 936 | NEW | 72 | WO no issued | 40 | 09/09/2022 | 31/12/2024 | 26/01/2024 | 11/05/2023 | 136.72 | 136.72
267 | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/17965) | SM/17965 | 46.72 | 0 | AUGMENTATION | 72 | WO no issued | 50 | 17/03/2023 | 31/12/2024 | 29/03/2024 | 08/06/2023 | 23.39 | 23.39
268 | BELIA AND ADJOINING MOUJAS PWSS (SM/12444) | SM/12444 | 523.17 | 1409 | NEW | 72 | WO no issued | 45 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 31/05/2023 | 233.17 | 233.17
269 | PALASHBANI AND ADJOINING MOUJAS PWSS (SM/12711) | SM/12711 | 441.75 | 673 | NEW | 73 | WO no issued | 63 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 17/02/2023 | 280.06 | 280.06
270 | BARABARI AND ADJOINING MOUJAS PWSS (SM/12722) | SM/12722 | 537.44 | 883 | NEW | 73 | WO no issued | 49 | 20/09/2022 | 31/12/2024 | 11/04/2024 | 26/05/2023 | 263.81 | 263.81
271 | NOAGOAN AND ADJOINING MOUJAS PWSS (SM/12526) | SM/12526 | 591.31 | 2019 | NEW | 73 | WO no issued | 49 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 04/05/2023 | 289.7 | 289.7
272 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09381) | SM/09381 | 41.53 | 100 | AUGMENTATION | 73 | WO no issued | 85 | 12/11/2021 | 31/12/2024 | 01/12/2023 | 04/04/2022 | 35.27 | 35.27
273 | PARSHULI AND ADJOINING MOUJAS PWSS (SM/12531) | SM/12531 | 463.62 | 1115 | NEW | 75 | WO no issued | 60 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 28/09/2022 | 279.15 | 279.15
274 | CHANDABILA AND ADJOINING MOPUJAS PWSS (SM/12435) | SM/12435 | 374.55 | 1219 | NEW | 76 | WO no issued | 61 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 20/07/2023 | 230.09 | 230.09
275 | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram (SM/10064) | SM/10064 | 1060.66 | 4792 | AUGMENTATION | 77 | WO no issued | 91 | 28/01/2022 | 31/12/2024 | 11/04/2024 | 29/04/2022 | 969.66 | 969.61
276 | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS (SM/12535) | SM/12535 | 652.02 | 1191 | NEW | 77 | WO no issued | 63 | 13/09/2022 | 31/12/2024 | 11/04/2024 | 14/03/2023 | 412.12 | 412.12
277 | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. (SM/17945) | SM/17945 | 36.98 | 0 | AUGMENTATION | 77 | WO no issued | 42 | 17/03/2023 | 31/12/2023 | 11/04/2024 | 11/05/2023 | 15.56 | 15.56
278 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. (SM/08734) | SM/08734 | 50.87 | 541 | RETROFITTING | 78 | WO no issued | 83 | 09/09/2021 | 31/12/2024 | 11/04/2024 | 13/09/2021 | 41.97 | 41.97
279 | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District (SM/10492) | SM/10492 | 214.93 | 1768 | AUGMENTATION | 78 | WO no issued | 60 | 13/04/2022 | 31/12/2024 | 11/04/2024 | 25/11/2022 | 128.81 | 128.81
280 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. (SM/08736) | SM/08736 | 67.82 | 804 | RETROFITTING | 81 | WO no issued | 86 | 09/09/2021 | 09/12/2021 | 26/09/2023 | 17/09/2021 | 58.31 | 58.31
281 | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. (SM/09376) | SM/09376 | 131.31 | 89 | AUGMENTATION | 81 | WO no issued | 53 | 12/11/2021 | 30/06/2023 | 11/04/2024 | 15/03/2022 | 70.22 | 70.22
282 | Installation of Iron Elemination Plant(IEP) and related works in different schemes(Barajharia PWSS, Lalgarh PWSS, Baratilaboni PWSS) within Nayagram and Binpur-I Blocks in Jhargram District under Jhargram Division, PHE Dte. (SM/17948) | SM/17948 | 85.96 | 0 | AUGMENTATION | 83 | WO no issued | 19 | 17/03/2023 | 30/06/2024 | 11/04/2024 | 14/07/2023 | 16.55 | 16.55
283 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail (SM/06833) | SM/06833 | 67.61 | 1319 | RETROFITTING | 85 | WO no issued | 100 | 06/10/2020 | 31/12/2024 | 11/04/2024 | 26/11/2020 | 67.6 | 52.14
284 | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. (SM/09375) | SM/09375 | 133.96 | 375 | AUGMENTATION | 85 | WO no issued | 56 | 12/11/2021 | 31/12/2024 | 06/10/2023 | 01/02/2022 | 74.99 | 71.99
285 | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram (SM/17950) | SM/17950 | 70.53 | 0 | AUGMENTATION | 88 | WO no issued | 6 | 17/03/2023 | 17/09/2023 | 08/09/2023 | 03/01/2023 | 4.36 | 4.36
286 | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. (SM/09374) | SM/09374 | 401.09 | 2314 | AUGMENTATION | 88 | WO no issued | 84 | 12/11/2021 | 31/12/2024 | 11/04/2024 | 24/06/2020 | 336.39 | 329.94
287 | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10491) | SM/10491 | 344.86 | 1752 | AUGMENTATION | 89 | WO no issued | 58 | 13/04/2022 | 31/07/2024 | 11/04/2024 | 18/10/2022 | 200.11 | 200.11
288 | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District (SM/09377) | SM/09377 | 187.46 | 520 | AUGMENTATION | 91 | WO no issued | 77 | 12/11/2021 | 31/12/2024 | 16/10/2023 | 12/08/2021 | 143.9 | 143.9
289 | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09373) | SM/09373 | 485.2 | 2490 | AUGMENTATION | 91 | WO no issued | 86 | 12/11/2021 | 31/12/2024 | 11/04/2024 | 12/08/2021 | 415.48 | 415.46
290 | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18010) | SM/18010 | 53.1 | 30 | AUGMENTATION | 92 | WO no issued | 89 | 17/03/2023 | 31/05/2024 | 11/04/2024 | 08/06/2023 | 47.4 | 47.4
291 | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10490) | SM/10490 | 353.34 | 1755 | AUGMENTATION | 94 | WO no issued | 94 | 13/04/2022 | 31/12/2024 | 11/04/2024 | 05/08/2022 | 331.21 | 331.21
292 | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II (SM/06831) | SM/06831 | 97.11 | 1818 | RETROFITTING | 95 | WO no issued | 100 | 06/10/2020 | 31/12/2024 | 11/04/2024 | 26/11/2020 | 97.1 | 87.69
293 | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/18012) | SM/18012 | 50.5 | 10 | AUGMENTATION | 99 | WO no issued | 65 | 17/03/2023 | 31/10/2023 | 08/09/2023 | 04/05/2023 | 32.93 | 32.93
294 | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II (SM/06828) | SM/06828 | 98.98 | 1720 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 27/06/2023 | 26/11/2020 | 98.97 | 71.01
295 | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II (SM/06829) | SM/06829 | 98.99 | 2031 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 27/06/2023 | 11/12/2020 | 98.99 | 81.65
296 | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. (SM/09384) | SM/09384 | 919.72 | 17796 | RETROFITTING | 100 | WO no issued | 76 | 12/11/2021 | 22/12/2023 | 11/04/2024 | 24/06/2020 | 698.12 | 692.73
297 | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. (SM/10439) | SM/10439 | 6.76 | 90 | RETROFITTING | 100 | WO no issued | 56 | 12/04/2022 |  | 12/06/2023 | 04/04/2022 | 3.8 | 3.8
298 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram (SM/06832) | SM/06832 | 84.05 | 1635 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 27/06/2023 | 02/07/2021 | 84.05 | 66.23
299 | Retrofitting to accommodate FHTC under JJM in Bahadurpur P.W.S.S. (Phase-II) within Binpur-I Block (SM/08173) | SM/08173 | 4.66 | 69 | RETROFITTING | 100 | WO no issued | 80 | 08/02/2021 |  | 12/06/2023 | 22/02/2021 | 3.73 | 3.73
300 | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) (SM/09102) | SM/09102 | 2.68 | 52 | RETROFITTING | 100 | WO no issued | 0 | 28/10/2021 |  | 12/06/2023 |  | 0 | 0
301 | Rejuvenation of Ground Water Based Netai PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10488) | SM/10488 | 34.89 | 22 | AUGMENTATION | 100 | WO no issued | 0 | 13/04/2022 |  | 16/01/2024 |  | 0 | 0
302 | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. (SM/09434) | SM/09434 | 25.96 | 0 | AUGMENTATION | 100 | WO no issued | 31 | 18/11/2021 |  | 27/06/2023 | 04/04/2022 | 8.17 | 8.17
303 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. (SM/08735) | SM/08735 | 187.73 | 1849 | RETROFITTING | 100 | WO no issued | 61 | 09/09/2021 |  | 27/06/2023 | 10/09/2021 | 114.95 | 114.95
304 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09380) | SM/09380 | 25.11 | 65 | AUGMENTATION | 100 | WO no issued | 25 | 12/11/2021 |  | 27/06/2023 | 30/12/2021 | 6.19 | 6.19
305 | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. (SM/09385) | SM/09385 | 8.38 | 150 | RETROFITTING | 100 | WO no issued | 83 | 12/11/2021 |  | 08/09/2023 | 15/02/2022 | 7 | 6.11
306 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte (SM/08733) | SM/08733 | 52.37 | 559 | RETROFITTING | 100 | WO no issued | 98 | 09/09/2021 |  | 12/06/2023 | 13/07/2021 | 51.11 | 51.11
307 | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. (SM/09882) | SM/09882 | 40.96 | 0 | AUGMENTATION | 100 | WO no issued | 39 | 08/12/2021 | 31/03/2023 | 27/06/2023 | 28/09/2022 | 15.87 | 15.87
308 | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. (SM/09386) | SM/09386 | 32.56 | 603 | RETROFITTING | 100 | WO no issued | 45 | 12/11/2021 | 31/05/2023 | 08/09/2023 | 16/02/2023 | 14.63 | 14.63
309 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09383) | SM/09383 | 141.62 | 2232 | AUGMENTATION | 100 | WO no issued | 95 | 12/11/2021 |  | 27/06/2023 | 22/07/2021 | 134.3 | 134.3
310 | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. (SM/06834) | SM/06834 | 85.93 | 2218 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 12/06/2023 | 26/11/2020 | 85.93 | 84.12
311 | Retrofitting to accommodate FHTC under JJM in Lohamelya P.W.S.S. (Phase-II) within Jhargram Block (SM/08175) | SM/08175 | 7.8 | 155 | RETROFITTING | 100 | WO no issued | 0 | 08/02/2021 |  | 12/06/2023 |  | 0 | 0
312 | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo (SM/07875) | SM/07875 | 39.75 | 816 | RETROFITTING | 100 | WO no issued | 97 | 19/01/2021 | 19/04/2021 | 26/09/2023 | 25/02/2021 | 38.59 | 38.59
313 | Providing solarization of WBSEDCL energised pumping installation at Damro w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16681) | SM/16681 | 10.33 | 0 | SOLARISATION | 100 | WO no issued | 0 | 14/03/2023 |  | 12/06/2023 | 25/08/2023 | 0 | 0
314 | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. (SM/10485) | SM/10485 | 100.61 | 303 | AUGMENTATION | 100 | WO no issued | 4 | 13/04/2022 |  | 27/06/2023 | 05/08/2022 | 4.37 | 4.37
315 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni (SM/06830) | SM/06830 | 91.19 | 1771 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 27/06/2023 | 18/07/2022 | 91.17 | 82.61
316 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. (SM/09382) | SM/09382 | 37.85 | 194 | AUGMENTATION | 100 | WO no issued | 60 | 12/11/2021 | 31/12/2023 | 03/07/2023 | 28/12/2022 | 22.86 | 22.86
317 | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. (SM/06827) | SM/06827 | 79.24 | 1989 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 27/06/2023 | 26/11/2020 | 79.23 | 66.18
318 | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. (SM/08029) | SM/08029 | 337.45 | 4581 | RETROFITTING | 100 | WO no issued | 76 | 29/01/2021 | 31/05/2023 | 08/09/2023 | 25/02/2021 | 257.35 | 257.01
319 | Retrofitting to accommodate FHTC under JJM in Junsola P.W.S.S. (Phase-II) within Gopiballavpur-II Block (SM/08174) | SM/08174 | 5.13 | 100 | RETROFITTING | 100 | WO no issued | 0 | 08/02/2021 |  | 12/06/2023 |  | 0 | 0
320 | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME (SM/10289) | SM/10289 | 6.36 | 0 | SOLARISATION | 100 | WO no issued | 0 | 25/02/2022 |  | 12/06/2023 | 03/03/2022 | 0 | 0
321 | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. (SM/06835) | SM/06835 | 81.41 | 1641 | RETROFITTING | 100 | WO no issued | 100 | 06/10/2020 |  | 12/06/2023 | 26/11/2020 | 81.4 | 78.88
322 | Providing solarization of WBSEDCL energised pumping installation at Dahijuri w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. (SM/16682) | SM/16682 | 5.17 | 0 | SOLARISATION | 100 | WO no issued | 0 | 14/03/2023 |  | 12/06/2023 | 25/08/2023 | 0 | 0
Total |  |  | 108471.1 | 276389 | [8 empty] | 27165.07 | 25952.83