## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18886) | SM/18886 | 350.95 | 1888 | AUGMENTATION | 0 | 0% Physical | 68 | 05/10/2023 | 31/12/2026 | 16/10/2025 | 20/09/2023 | 240.36 | 239.4
2 | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman (SM/12224) | SM/12224 | 689.44 | 181 | AUGMENTATION | 0 | 0% Physical | 61 | 07/09/2022 | 31/07/2025 | 16/10/2025 | 25/04/2023 | 418.32 | 418.32
3 | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME (SM/10605) | SM/10605 | 608.44 | 2994 | AUGMENTATION | 0 | 0% Physical | 53 | 19/04/2022 | 30/06/2025 | 16/10/2025 | 17/12/2021 | 321.12 | 321.12
4 | Augmentation PWSS of RCFA Part-II (Zone - 9 A) (SM/12221) | SM/12221 | 462 | 2224 | AUGMENTATION | 0 | 0% Physical | 42 | 07/09/2022 | 30/06/2025 | 16/10/2025 | 24/03/2023 | 191.83 | 191.83
5 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. (SM/12031) | SM/12031 | 481.52 | 2558 | AUGMENTATION | 0 | 0% Physical | 66 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 03/02/2023 | 318.45 | 318.45
6 | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. (SM/09063) | SM/09063 | 29.57 | 477 | RETROFITTING | 0 | 0% Physical | 96 | 28/10/2021 | 31/03/2025 | 16/10/2025 | 28/10/2021 | 28.48 | 27.85
7 | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. (SM/18889) | SM/18889 | 250.38 | 0 | AUGMENTATION | 0 | 0% Physical | 12 | 05/10/2023 | 31/12/2025 | 16/10/2025 | 02/01/2024 | 29.3 | 29.3
8 | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman (SM/12226) | SM/12226 | 440.82 | 2324 | AUGMENTATION | 0 | 0% Physical | 53 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 24/03/2023 | 234.18 | 234.18
9 | Augmentation PWSS of RCFA Part-II (Zone - 9 B) (SM/12225) | SM/12225 | 424.86 | 1992 | AUGMENTATION | 0 | 0% Physical | 38 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 03/02/2023 | 160.31 | 160.31
10 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JEMUA, UNDER DURGAPUR W/S DIVISION , BLOCK : DURGAPUR FARIDPUR, DISTRICT : PASCHIM BARDDHAMAN (SM/18890) | SM/18890 | 219.38 | 1657 | AUGMENTATION | 0 | 0% Physical | 69 | 05/10/2023 | 14/12/2025 | 16/10/2025 | 01/08/2022 | 152.12 | 152.12
11 | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (SM/18891) | SM/18891 | 941.12 | 0 | AUGMENTATION | 0 | 0% Physical | 29 | 05/10/2023 | 31/10/2025 | 16/10/2025 | 01/08/2023 | 277.4 | 277.4
12 | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. (SM/16775) | SM/16775 | 198.21 | 0 | AUGMENTATION | 0 | 0% Physical | 71 | 13/03/2023 | 31/03/2026 | 16/10/2025 | 04/04/2023 | 140.3 | 140.3
13 | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. (SM/15654) | SM/15654 | 988.24 | 2479 | AUGMENTATION | 0 | 0% Physical | 53 | 17/02/2023 | 31/07/2025 | 16/10/2025 | 15/09/2022 | 525.22 | 525.22
14 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18877) | SM/18877 | 313.27 | 1986 | AUGMENTATION | 0 | 0% Physical | 58 | 05/10/2023 | 21/08/2025 | 16/10/2025 | 21/02/2024 | 183.02 | 183.02
15 | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman (SM/12227) | SM/12227 | 543.54 | 1237 | AUGMENTATION | 0 | 0% Physical | 60 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 20/12/2022 | 324.26 | 324.26
16 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. (SM/12027) | SM/12027 | 818.76 | 3468 | AUGMENTATION | 0 | 0% Physical | 51 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 23/03/2023 | 414.82 | 414.82
17 | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. (SM/09065) | SM/09065 | 92.6 | 1613 | RETROFITTING | 0 | 0% Physical | 80 | 28/10/2021 | 31/12/2025 | 16/10/2025 | 27/03/2023 | 74.14 | 73.81
18 | Augmentation PWSS of RCFA Part-II (Zone - 9) (SM/12222) | SM/12222 | 579.22 | 2096 | AUGMENTATION | 0 | 0% Physical | 62 | 07/09/2022 | 31/03/2026 | 16/10/2025 | 23/03/2023 | 360.98 | 360.94
19 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18888) | SM/18888 | 175.3 | 0 | AUGMENTATION | 0 | 0% Physical | 13 | 05/10/2023 | 31/12/2025 | 16/10/2025 | 20/07/2023 | 22.79 | 22.79
20 | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. (SM/10287) | SM/10287 | 118.75 | 0 | SCHOOL | 0 | 0% Physical | 0 | 25/02/2022 | 31/05/2025 | 16/10/2025 | 17/12/2021 | 0 | 0
21 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18826) | SM/18826 | 460.11 | 1034 | AUGMENTATION | 0 | 0% Physical | 60 | 12/09/2023 | 31/12/2025 | 16/10/2025 | 13/09/2023 | 274.61 | 274.61
22 | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18887) | SM/18887 | 220.53 | 1377 | AUGMENTATION | 0 | 0% Physical | 10 | 05/10/2023 | 30/09/2025 | 16/10/2025 | 08/03/2019 | 22.81 | 22.81
23 | Augmentation of Roshna Piped Water Supply Scheme . (SM/10642) | SM/10642 | 844.67 | 1250 | AUGMENTATION | 0 | 0% Physical | 77 | 22/04/2022 | 31/03/2026 | 16/10/2025 | 18/01/2021 | 651.43 | 651.43
24 | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. (SM/09389) | SM/09389 | 111 | 2400 | RETROFITTING | 0 | 0% Physical | 100 | 12/11/2021 | 31/05/2025 | 16/10/2025 | 29/11/2021 | 111 | 110.55
25 | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. (SM/09061) | SM/09061 | 48.52 | 850 | RETROFITTING | 0 | 0% Physical | 40 | 28/10/2021 | 31/12/2025 | 16/10/2025 | 30/01/2023 | 19.3 | 19.3
26 | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. (SM/16777) | SM/16777 | 204.12 | 0 | AUGMENTATION | 0 | 0% Physical | 71 | 13/03/2023 | 31/12/2025 | 16/10/2025 | 04/04/2023 | 145.59 | 145.59
27 | Procurement of Chemical & Consumables, Glassware etc. required for smooth running of Laboratory at Kalyaneswari Water treatment Plant. (SM/06635) | SM/06635 | 8.79 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/02/2020 |  | 31/07/2022 | 07/11/2019 | 0 | 0
28 | Supply and delivery of Chemicals, Consumables, Glassware, etc. required for smooth running. (SM/06618) | SM/06618 | 6.78 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/02/2020 |  | 31/05/2021 |  | 0 | 0
29 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. (SM/08984) | SM/08984 | 176.06 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 | 09/11/2022 | 0 | 0
30 | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. (SM/10680) | SM/10680 | 10.96 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 06/05/2022 |  | 06/05/2022 | 22/11/2022 | 0 | 0
31 | DRINKING WATER SAMPLES COLLECTION, TESTING OF DRINKING WATER SAMPLES THROUGH FTK & UPLOADING CHARGES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JJM FROM FEB 22 TO MAR 23 (SM/11817) | SM/11817 | 46.12 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 16/08/2022 |  | 17/08/2022 | 18/07/2022 | 0 | 0
32 | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman (SM/13358) | SM/13358 | 8.83 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 19/10/2022 |  | 20/10/2022 | 30/06/2022 | 0 | 0
33 | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. (SM/13406) | SM/13406 | 2.82 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 02/11/2022 |  | 04/11/2022 |  | 0 | 0
34 | Providing service by assigning resource person for a period of 3 month supervision of process of preparation for NABL recognition for chemical testing of potable water of sub-District level water quality testing laboratory including supply, installation o (SM/16428) | SM/16428 | 20.56 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 28/02/2023 |  | 06/03/2023 | 15/02/2024 | 0 | 0
35 | Procurement of Computer and Peripherals for the office use in Asansol Mechanical Division, Kalyaneswari Water Testing Laboratory, P.H.E. Dte., District:- Paschim Bardhaman. (SM/17412) | SM/17412 | 11.84 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 20/03/2023 |  | 23/03/2023 |  | 0 | 0
36 | Operational charges of PHED Managed Laboratory under Asansol Mechanical Division Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/17190) | SM/17190 | 6.26 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 15/03/2023 |  | 22/03/2023 |  | 0 | 0
37 | Operational Charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. (SM/19257) | SM/19257 | 30.07 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 10/09/2024 |  | 11/09/2024 | 30/10/2024 | 0 | 0
38 | Operational Charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. (SM/19258) | SM/19258 | 8.25 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 10/09/2024 |  | 11/09/2024 |  | 0 | 0
39 | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. (SM/18769) | SM/18769 | 46405.37 | 0 | AUGMENTATION | 5 | Delayed | 46 | 24/08/2023 | 31/05/2025 | 16/10/2025 | 25/08/2023 | 21474.84 | 21474.84
40 | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE (SM/12024) | SM/12024 | 365.56 | 3551 | RETROFITTING | 5 | Delayed | 95 | 01/09/2022 | 31/03/2026 | 16/10/2025 | 30/08/2022 | 348.87 | 348.87
41 | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. (SM/07391) | SM/07391 | 1841 | 36446 | RETROFITTING | 6 | Delayed | 100 | 21/12/2020 | 31/03/2025 | 16/10/2025 | 22/09/2020 | 1841 | 1841
42 | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. (SM/18468) | SM/18468 | 5020.98 | 0 | AUGMENTATION | 10 | Delayed | 69 | 20/07/2023 | 31/05/2025 | 16/10/2025 | 04/08/2023 | 3459.59 | 3459.59
43 | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN (SM/14888) | SM/14888 | 882.66 | 0 | AUGMENTATION | 10 | Delayed | 56 | 03/02/2023 | 31/03/2026 | 16/10/2025 | 12/07/2023 | 497.41 | 497.41
44 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/16903) | SM/16903 | 64.9 | 171 | AUGMENTATION | 16 | Delayed | 17 | 13/03/2023 | 31/12/2025 | 16/10/2025 | 21/08/2023 | 11.32 | 11.32
45 | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman (SM/12223) | SM/12223 | 833.27 | 2270 | AUGMENTATION | 16 | Delayed | 81 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 30/01/2023 | 674.88 | 674.88
46 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. (SM/12025) | SM/12025 | 901.05 | 3450 | AUGMENTATION | 20 | Delayed | 58 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 25/04/2023 | 526.29 | 526.29
47 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. (SM/12030) | SM/12030 | 991.93 | 4933 | AUGMENTATION | 20 | Delayed | 58 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 16/05/2023 | 571.77 | 571.77
48 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. (SM/12028) | SM/12028 | 530.12 | 1976 | AUGMENTATION | 20 | Delayed | 58 | 01/09/2022 | 30/06/2025 | 16/10/2025 | 12/04/2023 | 307.81 | 307.81
49 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. (SM/12216) | SM/12216 | 868.69 | 1685 | AUGMENTATION | 20 | Delayed | 65 | 07/09/2022 | 29/08/2025 | 16/10/2025 | 25/04/2023 | 564.16 | 564.16
50 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. (SM/12026) | SM/12026 | 910.23 | 4411 | AUGMENTATION | 20 | Delayed | 47 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 16/05/2023 | 429.47 | 429.47
51 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. (SM/12210) | SM/12210 | 610.16 | 2833 | AUGMENTATION | 20 | Delayed | 91 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 11/04/2023 | 556.9 | 556.9
52 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. (SM/12041) | SM/12041 | 896.96 | 6807 | AUGMENTATION | 20 | Delayed | 48 | 01/09/2022 | 31/03/2026 | 16/10/2025 | 31/05/2023 | 430.91 | 430.91
53 | BANAGRAM PIPED WATER SUPPLY SCHEME (SM/11223) | SM/11223 | 34.78 | 112 | NEW | 20 | Delayed | 66 | 16/06/2022 | 31/03/2025 | 16/10/2025 | 18/05/2022 | 22.89 | 22.89
54 | Operation charges of 2 Two) Nos Sub-District Laboratories under Durgapur Water Supply Division,PHE Dte ,Dist-Paschim Bardhaman related to Water quality monitoring and surveillance programme under Jal jeevan Mission. (SM/13908) | SM/13908 | 8.54 | 0 | SUPPORT-WQMSP | 20 | Delayed | 0 | 29/11/2022 | 31/10/2023 | 15/12/2022 | 31/01/2023 | 0 | 0
55 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. (SM/12029) | SM/12029 | 771.55 | 2623 | AUGMENTATION | 25 | Delayed | 61 | 01/09/2022 | 30/09/2025 | 16/10/2025 | 23/03/2023 | 472.48 | 472.48
56 | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman (SM/13416) | SM/13416 | 909.45 | 861 | AUGMENTATION | 30 | Delayed | 49 | 02/11/2022 | 30/06/2025 | 16/10/2025 | 15/09/2022 | 447.25 | 447.25
57 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. (SM/12032) | SM/12032 | 731.25 | 4129 | AUGMENTATION | 30 | Delayed | 70 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 16/05/2023 | 509.93 | 509.93
58 | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC (SM/11576) | SM/11576 | 808.08 | 3367 | AUGMENTATION | 30 | Delayed | 87 | 22/07/2022 | 31/12/2025 | 16/10/2025 | 24/03/2023 | 701.15 | 701.15
59 | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM (SM/16249) | SM/16249 | 579.21 | 943 | NEW | 32 | Delayed | 72 | 24/02/2023 | 31/03/2025 | 16/10/2025 | 27/03/2023 | 418.36 | 418.36
60 | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. (SM/13685) | SM/13685 | 137.13 | 1404 | RETROFITTING | 32 | Delayed | 68 | 14/11/2022 | 30/11/2025 | 16/10/2025 | 03/05/2023 | 93.8 | 93.8
61 | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. (SM/18417) | SM/18417 | 2340.61 | 2776 | NEW | 35 | Delayed | 82 | 13/07/2023 | 31/05/2025 | 16/10/2025 | 19/07/2023 | 1922.61 | 1918.76
62 | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. (SM/12219) | SM/12219 | 681.87 | 2886 | AUGMENTATION | 35 | Delayed | 70 | 07/09/2022 | 31/03/2026 | 16/10/2025 | 24/03/2023 | 475.66 | 475.66
63 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18824) | SM/18824 | 860 | 1916 | AUGMENTATION | 35 | Delayed | 58 | 12/09/2023 | 31/07/2025 | 16/10/2025 | 19/09/2023 | 502.08 | 501.6
64 | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC (SM/11575) | SM/11575 | 661.28 | 4240 | AUGMENTATION | 40 | Delayed | 78 | 22/07/2022 | 31/12/2025 | 16/10/2025 | 24/02/2022 | 512.62 | 512.62
65 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. (SM/12039) | SM/12039 | 587.31 | 2426 | AUGMENTATION | 40 | Delayed | 30 | 01/09/2022 | 31/03/2026 | 16/10/2025 | 16/05/2023 | 177.31 | 177.31
66 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18825) | SM/18825 | 306.19 | 683 | AUGMENTATION | 40 | Delayed | 25 | 12/09/2023 | 31/12/2025 | 16/10/2025 | 21/09/2023 | 75.5 | 66.05
67 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. (SM/12033) | SM/12033 | 809.92 | 2865 | AUGMENTATION | 40 | Delayed | 61 | 01/09/2022 | 31/03/2026 | 16/10/2025 | 25/04/2023 | 490.67 | 490.67
68 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/15639) | SM/15639 | 989.75 | 1738 | AUGMENTATION | 45 | Delayed | 59 | 17/02/2023 | 31/05/2025 | 16/10/2025 | 23/03/2023 | 581.75 | 581.75
69 | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE (SM/12215) | SM/12215 | 898.82 | 2548 | AUGMENTATION | 50 | Delayed | 87 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 22/03/2023 | 781.67 | 781.66
70 | Augmentation of Ondal (Phase-I) Water Supply Scheme (SM/10641) | SM/10641 | 887.89 | 5205 | AUGMENTATION | 50 | Delayed | 83 | 22/04/2022 | 31/07/2025 | 16/10/2025 | 18/01/2021 | 739.09 | 739.09
71 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/16901) | SM/16901 | 340.79 | 769 | AUGMENTATION | 50 | Delayed | 51 | 13/03/2023 | 31/12/2025 | 16/10/2025 | 29/03/2023 | 173.29 | 173.29
72 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA (SM/15657) | SM/15657 | 929.97 | 2092 | AUGMENTATION | 50 | Delayed | 55 | 17/02/2023 | 31/07/2025 | 16/10/2025 | 11/05/2023 | 507.06 | 507.06
73 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. (SM/12042) | SM/12042 | 831.03 | 4861 | AUGMENTATION | 50 | Delayed | 81 | 01/09/2022 | 31/05/2025 | 16/10/2025 | 13/12/2022 | 673.11 | 673.11
74 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/16902) | SM/16902 | 94.57 | 262 | AUGMENTATION | 50 | Delayed | 87 | 13/03/2023 | 31/12/2025 | 16/10/2025 | 20/07/2023 | 82.66 | 82.66
75 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/15663) | SM/15663 | 227.43 | 574 | AUGMENTATION | 50 | Delayed | 61 | 17/02/2023 | 31/12/2025 | 16/10/2025 | 08/10/2022 | 138.59 | 138.59
76 | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/16250) | SM/16250 | 638.71 | 8674 | AUGMENTATION | 55 | Delayed | 48 | 24/02/2023 | 31/03/2026 | 16/10/2025 | 27/03/2023 | 308.01 | 308.01
77 | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. (SM/12220) | SM/12220 | 754.7 | 1364 | AUGMENTATION | 55 | Delayed | 80 | 07/09/2022 | 31/03/2026 | 16/10/2025 | 24/03/2023 | 603.82 | 603.82
78 | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME (SM/10844) | SM/10844 | 945.42 | 2435 | AUGMENTATION | 55 | Delayed | 97 | 30/05/2022 | 31/08/2025 | 16/10/2025 | 08/01/2021 | 921.5 | 921.5
79 | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. (SM/15666) | SM/15666 | 905.76 | 2454 | NEW | 60 | Delayed | 45 | 17/02/2023 | 31/05/2025 | 16/10/2025 | 04/07/2022 | 410.4 | 410.4
80 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/16900) | SM/16900 | 98.83 | 252 | AUGMENTATION | 60 | Delayed | 54 | 13/03/2023 | 31/12/2025 | 16/10/2025 | 15/05/2023 | 53.64 | 53.64
81 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA,DISTRICT : PASCHIM BARDDHAMAN (SM/18467) | SM/18467 | 1401.03 | 6356 | AUGMENTATION | 60 | Delayed | 48 | 20/07/2023 | 31/07/2025 | 16/10/2025 | 20/07/2023 | 675.09 | 675.09
82 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. (SM/12218) | SM/12218 | 878.95 | 1081 | AUGMENTATION | 60 | Delayed | 74 | 07/09/2022 | 31/05/2025 | 16/10/2025 | 24/03/2023 | 648.61 | 648.61
83 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/15659) | SM/15659 | 157.71 | 350 | AUGMENTATION | 60 | Delayed | 74 | 17/02/2023 | 31/12/2025 | 16/10/2025 | 15/05/2023 | 116.77 | 116.77
84 | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) (SM/11454) | SM/11454 | 2799.63 | 12405 | AUGMENTATION | 60 | Delayed | 77 | 12/07/2022 | 31/03/2026 | 16/10/2025 | 13/01/2021 | 2153.77 | 2153.77
85 | Augmentation of Jamuria (Rural) (Zone-II) PWSS. (SM/10640) | SM/10640 | 866.51 | 0 | AUGMENTATION | 60 | Delayed | 22 | 22/04/2022 | 31/12/2025 | 16/10/2025 | 18/01/2021 | 186.84 | 186.84
86 | DANDESHWAR PIPED WATER SUPPLY SCHEME. (SM/11282) | SM/11282 | 254.22 | 703 | NEW | 63 | Delayed | 74 | 28/06/2022 | 31/12/2025 | 16/10/2025 | 31/08/2022 | 188.03 | 188.03
87 | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC (SM/13418) | SM/13418 | 904.57 | 5982 | AUGMENTATION | 65 | Delayed | 66 | 02/11/2022 | 31/03/2026 | 16/10/2025 | 24/02/2022 | 595.86 | 595.86
88 | NAPARA PIPED WATER SUPPLY SCHEME. (SM/11932) | SM/11932 | 657.52 | 2252 | NEW | 65 | Delayed | 84 | 24/08/2022 | 31/12/2025 | 16/10/2025 | 02/08/2022 | 555.6 | 555.6
89 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN (SM/18469) | SM/18469 | 2403.3 | 7434 | AUGMENTATION | 65 | Delayed | 23 | 20/07/2023 | 31/07/2025 | 16/10/2025 | 12/07/2023 | 560.31 | 560.31
90 | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) (SM/13861) | SM/13861 | 41.75 | 60 | NEW | 69 | Delayed | 94 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 39.27 | 39.27
91 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) (SM/10209) | SM/10209 | 489.84 | 2450 | AUGMENTATION | 70 | Delayed | 96 | 24/02/2022 | 31/12/2025 | 16/10/2025 | 04/02/2021 | 471.01 | 471.01
92 | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. (SM/12040) | SM/12040 | 568.7 | 3700 | AUGMENTATION | 70 | Delayed | 79 | 01/09/2022 | 30/06/2025 | 16/10/2025 | 11/01/2023 | 451.11 | 451.11
93 | BIRUDIHA PIPED WATER SUPPLY SCHEME (SM/11224) | SM/11224 | 633.08 | 1697 | NEW | 70 | Delayed | 86 | 16/06/2022 | 30/06/2025 | 16/10/2025 | 18/08/2022 | 544.96 | 544.96
94 | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) (SM/10211) | SM/10211 | 811.61 | 3815 | AUGMENTATION | 70 | Delayed | 94 | 24/02/2022 | 30/06/2025 | 16/10/2025 | 11/03/2022 | 760.86 | 760.86
95 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) (SM/10212) | SM/10212 | 663.97 | 2984 | AUGMENTATION | 70 | Delayed | 92 | 24/02/2022 | 31/12/2025 | 16/10/2025 | 24/01/2022 | 607.98 | 607.34
96 | Ground water based mini piped water supply scheme (Max 100 House Hold) for Pathardiha,GP-Gopalpur,Block -Kanksa,Dist-Paschim Bardhaman under Durgapur W/s Division,PHE Dte (Part-G) (SM/18745) | SM/18745 | 39.36 | 0 | NEW | 75 | Delayed | 62 | 17/08/2023 | 31/03/2025 | 15/01/2025 | 20/02/2023 | 24.49 | 24.49
97 | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) (SM/10208) | SM/10208 | 700.46 | 2538 | AUGMENTATION | 75 | Delayed | 94 | 24/02/2022 | 31/12/2025 | 16/10/2025 | 09/12/2020 | 657.75 | 657.56
98 | Shyambazar Piped water Supply Scheme (SM/11228) | SM/11228 | 309.98 | 882 | NEW | 75 | Delayed | 82 | 17/06/2022 | 31/05/2025 | 16/10/2025 | 31/08/2022 | 253.98 | 253.98
99 | BAMUNARA PIPED WATER SUPPLY SCHEME. (SM/11227) | SM/11227 | 773.34 | 5234 | NEW | 76 | Delayed | 80 | 17/06/2022 | 31/12/2025 | 16/10/2025 | 31/08/2022 | 620.01 | 620.01
100 | GARADAHA PIPED WATER SUPPLY SCHEME. (SM/11934) | SM/11934 | 51.33 | 171 | NEW | 80 | Delayed | 77 | 24/08/2022 | 31/05/2025 | 16/10/2025 | 17/05/2022 | 39.74 | 39.74
101 | Augmentation of Sub-Surface water based Churulia PWSS. (SM/11205) | SM/11205 | 996.67 | 555 | AUGMENTATION | 80 | Delayed | 88 | 06/06/2022 | 31/08/2025 | 16/10/2025 | 02/06/2022 | 872.6 | 860.25
102 | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. (SM/07519) | SM/07519 | 97.53 | 1880 | RETROFITTING | 82 | Delayed | 69 | 29/12/2020 | 31/12/2025 | 16/10/2025 | 04/02/2021 | 67.16 | 65.55
103 | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte (SM/10203) | SM/10203 | 943.11 | 0 | AUGMENTATION | 83 | On track | 79 | 24/02/2022 | 31/03/2026 | 16/10/2025 | 28/01/2021 | 748.33 | 746.95
104 | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. (SM/07518) | SM/07518 | 96.32 | 0 | RETROFITTING | 85 | Delayed | 93 | 29/12/2020 | 31/08/2025 | 16/10/2025 | 24/05/2021 | 89.4 | 89.4
105 | JATGARIA PIPED WATER SUPPLY SCHEME. (SM/11933) | SM/11933 | 275.4 | 762 | NEW | 85 | On track | 68 | 24/08/2022 | 31/12/2025 | 16/10/2025 | 31/08/2022 | 187.81 | 187.81
106 | AMLAJORA PIPED WATER SUPPLY SCHEME (SM/11937) | SM/11937 | 529.96 | 1738 | NEW | 85 | On track | 93 | 24/08/2022 | 31/12/2025 | 16/10/2025 | 31/08/2022 | 494.74 | 491.52
107 | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . (SM/12726) | SM/12726 | 2832.34 | 13807 | AUGMENTATION | 85 | On track | 73 | 21/09/2022 | 31/03/2026 | 16/10/2025 | 13/01/2021 | 2073.99 | 2088.39
108 | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman (SM/10372) | SM/10372 | 835.05 | 0 | ANGANWADI | 88 | On track | 0 | 16/03/2022 | 31/12/2025 | 16/10/2025 | 28/01/2021 | 0 | 0
109 | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) (SM/10210) | SM/10210 | 780.77 | 3113 | AUGMENTATION | 89 | On track | 97 | 24/02/2022 | 31/12/2025 | 16/10/2025 | 28/12/2020 | 754.57 | 754.48
110 | Augmentation of Madantor Water Supply Scheme (SM/10845) | SM/10845 | 587.44 | 1125 | AUGMENTATION | 90 | On track | 57 | 30/05/2022 | 31/03/2026 | 16/10/2025 | 18/01/2021 | 337.55 | 337.55
111 | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman (SM/11986) | SM/11986 | 997.15 | 5048 | AUGMENTATION | 90 | On track | 86 | 01/09/2022 | 31/12/2025 | 16/10/2025 | 24/02/2022 | 859.94 | 859.94
112 | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. (SM/09062) | SM/09062 | 82.87 | 1555 | RETROFITTING | 90 | Delayed | 97 | 28/10/2021 | 31/03/2025 | 16/10/2025 | 28/10/2021 | 80.35 | 80.26
113 | Augmentation of Jamgram Piped Water Supply Scheme. (SM/10643) | SM/10643 | 774.12 | 1738 | AUGMENTATION | 90 | Delayed | 78 | 22/04/2022 | 30/06/2025 | 16/10/2025 | 18/01/2021 | 605.43 | 604.46
114 | DHOBARU PIPED WATER SUPPLY SCHEME (SM/10999) | SM/10999 | 57.63 | 197 | NEW | 90 | Delayed | 79 | 31/05/2022 | 31/03/2025 | 16/10/2025 | 17/05/2022 | 45.57 | 45.57
115 | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman (SM/10373) | SM/10373 | 391.11 | 0 | SCHOOL | 90 | Delayed | 0 | 16/03/2022 | 31/03/2025 | 16/10/2025 | 01/02/2022 | 0 | 0
116 | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME (SM/10165) | SM/10165 | 971.48 | 3513 | AUGMENTATION | 90 | On track | 87 | 11/02/2022 | 31/12/2025 | 16/10/2025 | 18/01/2021 | 841.72 | 841.72
117 | KOTALPUKUR PIPED WATER SUPPLY SCHEME (SM/10996) | SM/10996 | 54.17 | 173 | NEW | 90 | Delayed | 81 | 31/05/2022 | 31/05/2025 | 16/10/2025 | 17/05/2022 | 44.06 | 44.06
118 | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) (SM/09060) | SM/09060 | 244.75 | 4170 | RETROFITTING | 90 | On track | 97 | 28/10/2021 | 31/12/2025 | 16/10/2025 | 28/10/2021 | 238.17 | 237.45
119 | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte (SM/09875) | SM/09875 | 1310.24 | 0 | AUGMENTATION | 92 | On track | 84 | 07/12/2021 | 31/03/2026 | 16/10/2025 | 16/12/2021 | 1097.22 | 1073.71
120 | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) (SM/13862) | SM/13862 | 33.6 | 20 | NEW | 95 | Delayed | 83 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 27.86 | 27.86
121 | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. (SM/10998) | SM/10998 | 41.17 | 126 | NEW | 95 | Delayed | 65 | 31/05/2022 | 31/05/2025 | 16/10/2025 | 13/05/2022 | 26.92 | 26.92
122 | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) (SM/13864) | SM/13864 | 40.28 | 53 | NEW | 95 | Delayed | 84 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 33.78 | 33.78
123 | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. (SM/09064) | SM/09064 | 169.66 | 3371 | RETROFITTING | 95 | Delayed | 81 | 28/10/2021 | 30/06/2025 | 16/10/2025 | 08/05/2023 | 136.75 | 136.75
124 | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) (SM/13866) | SM/13866 | 47.8 | 99 | NEW | 95 | Delayed | 93 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 44.64 | 44.64
125 | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. (SM/08877) | SM/08877 | 1167.42 | 7821 | NEW | 95 | Delayed | 98 | 23/09/2021 | 31/05/2025 | 16/10/2025 | 29/12/2021 | 1139.24 | 1139.11
126 | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) (SM/13863) | SM/13863 | 34.64 | 25 | NEW | 95 | Delayed | 85 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 29.28 | 29.28
127 | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. (SM/07524) | SM/07524 | 86.82 | 1686 | RETROFITTING | 95 | Delayed | 100 | 29/12/2020 | 31/03/2025 | 16/10/2025 | 12/05/2021 | 86.82 | 86.82
128 | Telipara Piped Water Supply Scheme. (SM/10311) | SM/10311 | 389.8 | 7427 | NEW | 95 | Delayed | 90 | 04/03/2022 | 31/05/2025 | 16/10/2025 | 21/04/2022 | 350.23 | 349.66
129 | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Maheshpur,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-A) (SM/13879) | SM/13879 | 42.44 | 68 | NEW | 95 | Delayed | 88 | 25/11/2022 | 31/03/2025 | 16/10/2025 | 01/08/2022 | 37.25 | 37.25
130 | Improvement of RCFA (Part-I) Piped Water Supply Scheme. (SM/09916) | SM/09916 | 11874.12 | 30062 | AUGMENTATION | 98 | On track | 94 | 10/12/2021 | 31/12/2025 | 16/10/2025 | 18/01/2021 | 11107.04 | 11096.63
131 | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. (SM/09242) | SM/09242 | 10.72 | 0 | SCHOOL | 98 | On track | 0 | 03/11/2021 | 31/12/2025 | 16/10/2025 | 01/02/2022 | 0 | 0
132 | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District (SM/07558) | SM/07558 | 94.74 | 2015 | RETROFITTING | 100 | 100% Physical | 96 | 04/01/2021 | 31/03/2026 | 16/10/2025 | 07/06/2021 | 91.04 | 91.04
133 | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district (SM/07392) | SM/07392 | 627.42 | 9726 | RETROFITTING | 100 | 100% Physical | 97 | 21/12/2020 | 31/03/2025 | 16/10/2025 | 24/12/2020 | 609.46 | 609.36
134 | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District (SM/07559) | SM/07559 | 94.74 | 2015 | RETROFITTING | 100 | 100% Physical | 95 | 04/01/2021 | 31/03/2026 | 16/10/2025 | 07/06/2021 | 89.59 | 89.68
135 | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) (SM/09059) | SM/09059 | 244.75 | 4170 | RETROFITTING | 100 | 100% Physical | 97 | 28/10/2021 | 31/12/2025 | 16/10/2025 | 28/10/2021 | 237.62 | 236.11
136 | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District (SM/07561) | SM/07561 | 94.68 | 2014 | RETROFITTING | 100 | 100% Physical | 94 | 04/01/2021 | 31/03/2026 | 16/10/2025 | 07/06/2021 | 89.23 | 89.23
137 | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District (SM/07560) | SM/07560 | 94.68 | 2014 | RETROFITTING | 100 | 100% Physical | 95 | 04/01/2021 | 31/03/2026 | 16/10/2025 | 07/06/2021 | 89.69 | 89.69
138 | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. (SM/09387) | SM/09387 | 188.03 | 3720 | RETROFITTING | 100 | 100% Physical | 98 | 12/11/2021 | 31/05/2025 | 16/10/2025 | 29/11/2021 | 184.68 | 179.92
139 | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . (SM/10144) | SM/10144 | 25.6 | 0 | AUGMENTATION | 100 | 100% Physical | 98 | 09/02/2022 | 31/08/2023 | 16/10/2025 | 11/02/2022 | 25.02 | 25.02
140 | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District (SM/07562) | SM/07562 | 62.01 | 1125 | RETROFITTING | 100 | 100% Physical | 96 | 04/01/2021 | 31/12/2025 | 16/10/2025 | 07/06/2021 | 59.3 | 58.95
141 | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. (SM/09388) | SM/09388 | 220.61 | 4045 | RETROFITTING | 100 | 100% Physical | 96 | 12/11/2021 | 31/05/2025 | 16/10/2025 | 29/11/2021 | 212.38 | 210.22
142 | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. (SM/06638) | SM/06638 | 4.1 | 0 | SUPPORT-WQMSP | 100 | 100% Physical | 0 | 05/02/2020 |  | 10/11/2022 | 08/10/2020 | 0 | 0
Total |  |  | 134801.18 | 350147 | [8 empty] | 84432.73 | 84366.26