## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | SM/07217 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapno Programme for Rupandighi and Sahananda village of Guabari Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. (Part B). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000052/2020-2021 | 1008/SWSD | 11/12/2020 | 10/01/2021 | UJJWAL ROY | 35.77 | 32.75 | 91.57 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | SM/07217 | Retrofitting | Providing functional house hold tap connection under Jal Swapno programme for Guabari village of Guabari piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. No. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000079/2021-2022 | 1827/SWSD | 13/01/2022 | 12/02/2022 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 23.24 | 10.14 | 43.62 | 30
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | SM/07217 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 1669/SWSD | 28/12/2021 |  | Resource Division | 1.87 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | SM/07217 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
Total | [13 empty] | 161.24 | 42.89 | 26.6