## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block | SM/07425 | Retrofitting | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Mingharer Chhat, Nimubhitar Chhat, Atal of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000122/2021-2022 | 2363/SWSD | 08/03/2022 | 02/04/2022 | ARUN KUMAR SHRIVASTAVA | 19.04 | 19.04 | 100 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block | SM/07425 | Retrofitting | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Damdama, Grammani, Grammanir Chhat of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000125/2021-2022 | 2364/SWSD | 08/03/2022 | 28/03/2022 | DEBOL,S ENTERPRISE | 9.63 | 9.32 | 96.71 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block | SM/07425 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Bairbhita Habitation Bairvita Madanjote village Atal Habitation Atal village Nimubhita chat Habitation Nimuvita, village Minghara chat Habitation Minghar chhat of Damdama Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 04 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000205/2020-2021 | 1525/SWSD | 22/02/2021 | 19/03/2021 | ARUN KUMAR SHRIVASTAVA | 20.95 | 5.31 | 25.32 | 75
Total | [13 empty] | 49.62 | 33.66 | 67.83