## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | Laying distribution system along with boring of new tubewells, construction of pump house, boundary walls at 3rd and 4th tubewell site and providing FHTC at Uttam Chand, Hoda Bhitar Chhat, Uttam Chander Chhat, Mudir Jangal, Satbhaiya, Ghusuru, Raghuram, Raghuramer Chhat, Bhaktaram mouza in connection with rejuvenation of GHUSURU PIPED WATER SUPPLY SCHEME under JJM at Naxalbari block, Darjeeling District under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000267/2022-2023 | 2365/SWSD | 24/01/2023 | 24/04/2023 | SUBIR CH. CHOWDHURY | 142.14 | 78.02 | 54.89 | 80
2 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1808/SWSD | 30/09/2023 |  | Resource Division | 9.89 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 2029/SWSD | 16/12/2022 |  | Resource Division | 1.97 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | New Service Connection Charge for rrjuvenation of Ghusuri PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144975 ; Reference ID : 403013463] |  |  | BILL/00041/2023-2024 | BP/23-24/10 | 16/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | New Service Connection Charge for Rejuvenation of Ghusuri PWSS, TW No. II, NAXALBARI CCC [APPLICATION NO. 4003144980 ; Reference ID : 403013029] |  |  | BILL/00042/2023-2024 | BP/23-24/10 | 16/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000055/2023-2024 | 549/NMD | 15/05/2023 | 14/06/2023 | M/S B.ENTERPRISE | 23.18 | 19.31 | 83.31 | 70
Total | [13 empty] | 178.63 | 97.33 | 54.49