## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | Laying Rising Main, laying distribution pipe line with Functional Household Tap Connection (FHTC), construction of two number Pump Houses (5.40 X 3.60 M), Iron Elimination Plant (IEP) with Blower Room and sinking of 2 (two) Nos. Tube well (ODEX-165 method) for HATIDOBA PWSS, Block - Kharibari, Dist. Darjeeling under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000046/2023-2024 | 654/SWSD | 15/06/2023 | 13/10/2023 | M/S DOLPHIN CONSTRUCTION CO | 178.07 | 38.65 | 21.7 | 25
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000058/2023-2024 | 251/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.8 | 2.8 | 100 | 100
3 | DARJEELING |  | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 2046/SWSD | 16/12/2022 |  | Resource Division | 13.77 | 0 | 0 | 0
4 | DARJEELING |  | Central Drilling | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | DARJEELING |  | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | New Service Connection Charge for HATIDOBA, T/W No. I, under KHORIBARI CCC [APPLICATION NO. 4003296374 ; Reference ID : 403127440] |  |  | BILL/01745/2023-2024 | BP/23-24/223 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.71 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | New Service Connection Charge for HATIDOBA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003321646, Reference ID : 403147923] |  |  | BILL/01947/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2023-2024 | 1643/NMD | 29/09/2023 | 29/10/2023 | M/S SIMARR | 11.92 | 4.05 | 34.02 | 70
Total | [13 empty] | 21555.05 | 45.5 | 0.21