## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED KHOKLONG PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000066/2023-2024 | 259/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.02 | 1.01 | 50 | 100
2 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | Laying distribution pipeline and Rising Main allied with construction of 2 nos. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.65 m), Iron Elemination Plant (10 cu.m/hr.), Boundary Wall including FHTC at KHOKLONG Piped Water Supply Scheme under Matigara Blok, Darjeeling Dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) |  | ORD/000086/2023-2024 | 1042/SWSD | 27/07/2023 | 09/11/2023 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 112.28 | 0 | 0 | 0
3 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 79/SWSD | 10/01/2024 |  | Resource Division | 1.08 | 0 | 0 | 0
4 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2038/SWSD | 16/12/2022 |  | Resource Division | 12.83 | 0 | 0 | 0
5 | DARJEELING | Matigara | Central Drilling | Khoklong Piped Water Supply Scheme | SM/13437 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Power Service connection charges at T.W No-II of Khoklong PWSS under Northern Mechanical Division dist. Darjeeling CONSUMER ID:- 403230623 |  |  | BILL/00528/2024-2025 | BP/24-25/130 | 24/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.9 | 0 | 0 | null
7 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | New Service Connection Charge for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003460490 Reference ID : 403255264 |  |  | BILL/00973/2024-2025 | BP/24-25/166 | 14/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | null
8 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Infrastructure development cost for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115666 Reference ID : 860308376 |  |  | BILL/00980/2024-2025 | BP/24-25/166 | 14/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.39 | 0 | 0 | null
9 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | New Service Connection Charge for KHOKLONG, T/W No.I, under MATIGARA CCC, [APPLICATION NO. 4003316039, Reference ID : 403143725] |  |  | BILL/01952/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.35 | 0 | 0 | 0
10 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOKLONG PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 1674/NMD | 29/09/2023 | 29/10/2023 | B.B. CONCERNED | 11.43 | 8.78 | 76.86 | 70
Total | [13 empty] | 21495.86 | 9.79 | 0.05