## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra | SM/10561 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Home Dara(Tower Dara) Gram Panchyat -Relling , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009299 SM Code-SM/08927 GO2223000391PH |  |  | ORD/000025/2022-2023 | 258/NKWSMD | 10/05/2022 | 09/07/2022 | M/S DIVYA ENTERPRISES | 13.79 | 4.66 | 33.8 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra | SM/10561 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 1258/NKWSMD | 05/09/2022 |  | Resource Division | 0.68 | 0 | 0 | 0
Total | [13 empty] | 14.47 | 4.66 | 32.2