## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay | SM/10780 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Bansbotay, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009477 SM Code-SM/08923 |  |  | ORD/000076/2022-2023 | 592/NKWSMD | 26/05/2022 | 25/07/2022 | HARI PRASAD CHETTRI | 16.66 | 6.92 | 41.57 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay | SM/10780 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1256/NKWSMD | 05/09/2022 |  | Resource Division | 0.17 | 0 | 0 | 0
Total | [13 empty] | 16.83 | 6.92 | 41.14