## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | SM/10789 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00174/2023-2024 | BP-2023-24-129 | 27/07/2023 |  | WBSEDCL | 0.09 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | SM/10789 | New | WATER SUPPLY SCHEME FOR TWO NOS OF VILLAGES UNDER BLOCK KURSEONG DISTRICT OF DARJEELING [TSM NO - 10476 / 10473] 1. Septiguri Khelaghar tea garden 2. Pairikumari |  |  | ORD/000084/2022-2023 | 608/NKWSMD | 26/05/2022 | 21/01/2023 | M/S KAMAK ENGINEERS AND CO. | 199.42 | 17.57 | 8.81 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | SM/10789 | New | Material Requisition To Resource Division |  |  | RTOR000158/2022-2023 | 2374/NKWSMD | 03/02/2023 |  | Resource Division | 1.8 | 0 | 0 | 0
Total | [13 empty] | 201.32 | 17.57 | 8.73