## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00492/2023-2024 | BP-2023-24-291 | 02/11/2023 |  | WBSEDCL | 0.36 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00493/2023-2024 | BP-2023-24-292 | 02/11/2023 |  | WBSEDCL | 0.46 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | payment for wbsedcl |  |  | BILL/00706/2023-2024 | BP-2023-24-475 | 28/01/2024 |  | WBSEDCL | 4.15 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | payment for wbsedcl |  |  | BILL/00707/2023-2024 | BP-2023-24-476 | 28/01/2024 |  | WBSEDCL | 5.49 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 25/02/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 45.54 | 6.41 | 80
6 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 2373/NKWSMD | 03/02/2023 |  | Resource Division | 4.21 | 0 | 0 | 0
Total | [13 empty] | 724.87 | 45.54 | 6.28