## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | New | Balance work for water supply scheme for Murmudang, Kom Busty, & Lower Kolbong under Jal Jeevan Mission & JSP programme under Pull Bijanbari Block PHED-GTA. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000152/2023-2024 | 880/NKWSMD | 03/08/2023 | 02/10/2023 | AMRIT KUMAR SUBBA | 96.3 | 68.77 | 71.41 | 50
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | New | PIPED WATER SUPPLY SCHEME FOR MURMIDANG, KOM BUSTY & LOWER KOLBONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000221/2022-2023 | 1119/NKWSMD | 05/08/2022 | 01/02/2023 | AMRIT KUMAR SUBBA | 107.92 | 82.37 | 76.32 | 50
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 1366/NKWSMD | 21/09/2022 |  | Resource Division | 1.49 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1883/NKWSMD | 15/12/2022 |  | Resource Division | 1.49 | 0 | 0 | 0
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | New | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 2592/NKWSMD | 17/02/2023 |  | Resource Division | 1.49 | 0 | 0 | 0
Total | [13 empty] | 208.69 | 151.13 | 72.42