## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III | SM/11301 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme for including augmentatin work for PWS scheme for okaity ward no. 03 Gram panchyat PGSD-I, Block-Mirik TSM No. 009304 |  |  | ORD/000012/2022-2023 | 784/NKWSMD | 30/06/2022 | 29/08/2022 | ROSHAN BISWAKARMA | 7.58 | 4.32 | 56.9 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III | SM/11301 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1312/NKWSMD | 09/09/2022 |  | Resource Division | 0.28 | 0 | 0 | 0
Total | [13 empty] | 7.86 | 4.32 | 54.89