## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon | SM/11304 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Ektis Goan: Gram Panchyat-Paila Goan School Dara-I, Block- Mirik TSM No. 009307 SM Code-SM/08942 |  |  | ORD/000014/2022-2023 | 786/NKWSMD | 30/06/2022 | 29/08/2022 | PUSHKAR GURUNG | 20.13 | 10.67 | 53.02 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon | SM/11304 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1311/NKWSMD | 09/09/2022 |  | Resource Division | 0.27 | 0 | 0 | 0
Total | [13 empty] | 20.4 | 10.67 | 52.31